# Outer Planets/Solar Probe Project

# Mission Assurance Plan

Note: Printed copies of this document may not be relied on for official purposes.  The current version is in the Product Data Management System (PDMS) at http://pdms

# Prepared by:  Section 515

# Richard Kemski

OP/SP Mission Assurance Manager

# JPL D-18353, Rev. B

# August 21, 2000

# Jet Propulsion Laboratory

California Institute of Technology

# OP/SP Mission Assurance Plan

# TABLE OF CONTENTS

Document Log	iv

1.0	MISSION ASSURANCE PLAN	1

1.1	General	1

1.2	Implementation	1

1.3	Reviews	2

1.4	Environmental Requirements	2

1.4.1	Radiation Control Plan	2

1.5	Systems Safety	3

1.6	Risk Management	3

1.7	Configuration Management	3

1.8	Lessons Learned	3

1.9	Materials and Processes Control	3

1.10	Contractor Requirements	4

1.11	Waivers	4

2.0	QUALITY ASSURANCE REQUIREMENTS FOR OP/SP	5

2.1	Purpose	5

2.2	Scope	5

2.3	Applicable Documents	5

2.4	Resource Management	5

2.4.1	Training and Certification	5

2.4.2	Information	6

2.5	Product Realization	6

2.5.1	General Requirements	6

2.5.2	Design and Development Review	6

2.5.3	Quality Assurance Requirements for Engineering Model Hardware	7

2.5.4	Acceptance and Environmentsl Test Verification	7

2.5.5	Ground Support Equipment	8

2.5.6	Control of Changes	8

2.5.7	Procurement Activities	9

2.5.8	JPL Quality Assurance Activities at Contractors and Suppliers	10

2.6	Measurement, Analysis and Improvement	11

2.6.1	Measurement and Monitoring of System Performance	11

2.6.2	Measurement and Monitoring of Processes	11

2.6.3	Measurement and Monitoring of Product	11

2.6.4	Control of Nonconforming Product	13

2.6.5	Records	13

2.6.6	End Item Data Package	14

2.6.7	Assembly, Test, and Launch Operations Support	15

2.7	Software Development Process Tailoring	15

2.7.1	General Software Development Process Requirements	15

2.8	Software Process and Product Metrics	16

2.8.1 	Metrics Requirements	16

2.8.2	Software Assurance Activities	17

2.9	Software Safety	17

2.9.1	Software Safety Requirements	17

2.9.2	Software Assurance Activities	17

3.0	HARDWARE RELIABILITY ASSURANCE PLAN	19

3.1	Introduction	19

3.1.1	Scope	19

3.1.2	Purpose	19

3.1.3	Objectives	19

3.1.4	Responsibilities	19

3.2.	Applicable Documents	19

3.2.1	Documents	19

3.3	Reliability Assurance Requirements	20

3.3.1	Reliability Analyses Requirements	20

3.3.2	Success-Critical Single Failure Point (SFP)	21

3.3.3	Reliability Analyses	21

3.3.3.1	FMECA	21

3.3.3.2.	Electrical/Electronic Worst Case Analysis	21

3.3.3.3.	Mechanical Worst Case Analysis	22

3.3.3.4.	Electronic and Electromechanical Parts Stress Analysis	23

3.3.3.5.	Structural	23

3.3.3.6.	Thermal	23

3.3.3.7	Single Event Effects Analysis	23

3.3.3.8	Sneak circuit analysis	24

3.3.4	Operating Time Requirements	24

4.0	PFR PLAN	25

4.1	Introduction	25

4.1.1	Purpose	25

4.1.2	Scope	25

4.2	Applicable Documents	25

4.3	Problem/Failure Reporting System Requirements	25

4.3.1	General	25

4.3.2	PFR and AR Starting Points	26

4.3.2.1	 PFRs for:	26

4.3.2.2	ARs for:	26

4.3.3	Requirements for PFRs and ARs	26

4.3.3.1	Incidents Requiring Reports	26

4.3.3.2	Timeliness of Reporting and Release	27

4.3.3.3	Responsibility of Reporting	27

4.3.3.4	Form for Reporting	27

4.3.3.5	Analysis Requirements	27

4.3.3.6	Corrective Action Requirements	27

4.3.3.7	Criticality and Cause/Corrective Action Rating	28

4.3.3.7.1	Failure Effect Rating	28

4.3.3.7.2	Cause and Corrective Action Rating	29

4.3.3.8	Risk Assessment	30

4.3.3.8.1	Red Flag PFRs	30

4.3.3.8.2	Preliminary Rating of PFRs	30

4.3.3.9	Safety Rating and Assessment	31

4.3.3.10	Spacecraft Significant Event File (SSEF) and Alert/Concern Assessment	31

4.3.3.11	Review, Approval, and Closure	31

4.3.3.11.1	PFR Review, Approval and Closure	31

4.4	Contractor Problem/Failure Reporting Requirements	34

4.4.1	General	34

4.4.2	Liaison and Submittals to JPL	34

5.0	ELECTRONIC PARTS PROGRAM REQUIREMENTS	35

5.1	Introduction	35

5.1.1	Purpose	35

5.1.2	Applicability	35

5.1.3	Applicable Documents	35

5.2	Requirements	36

5.2.1	Management Requirements	36

5.2.2	Reviews	36

5.3	Parts Selection	36

5.3.1	Parts Classification	36

5.3.1.1	Standard Parts	37

5.3.1.2	Nonstandard Parts	37

5.3.1.3	Die	38

5.3.1.4	Noncompliant Parts	38

5.3.2	Application Specific Integrated Circuit (ASIC) Requirements	38

5.3.2.1	Digital ASIC Test Requirements	38

5.3.2.2	Mixed-Signal ASIC Test Requirements	38

5.3.3	MCM/Hybrid Requirements	39

5.4	 Radiation Requirements	40

5.4.1 	Total Ionizing Dose (TID)	40

5.4.2 	Dose Rate	40

5.4.3 	Displacement Damage	40

5.4.4 	Single Event Latchup (SEL)	41

5.4.5 	Single Event Upset (SEU)	41

5.4.6 	Single Event Burnout (SEB)	41

5.4.7 	Single Event Gate Rupture (SEGR)	41

5.5	Parts Acquisition	42

5.5.1	Use of Residual (Heritage) Parts Inventory	42

5.5.2 	Parts Procurement	42

5.5.3 	Backward Traceability	42

5.5.4 	Parts Data Requirements	42

5.5.5	Customer Source inspection	42

5.5.6 	Post-Programming Burn-In for Programmable Devices	42

5.5.7 	Destructive Physical Analysis (DPA)	43

5.6	Electronic Parts Application	43

5.6.1	Parts Derating	43

5.6.2	Electrostatic Discharge (ESD) Control Requirements for Static-Sensitive Parts	43

5.6.3	NASA and Government Industry Data Exchange Program (GIDEP) Alerts	44

5.6.4 	Parts Failure Analysis	44

5.6.5 	As-Built Parts List	44

5.7	System Contractors	45

Acronym List	47

# Document Log

| Issue | Date | Pages Affected | Description |
| --- | --- | --- | --- |
| Rev. B | 8/21/00 | Pg. 31-32, par. 4.3.3.11.1 | Added Flight Instruments Development Manager to PRB membership and PFR closure process. |
| Rev.B | 8/21/00 | Pg. 33, Figure 1 | Added Flight Instruments Development Manager to PFR flow. |
| Rev. B | 8/21/00 | Pg. 40, Par. 5.4.1 | Added GaAs transistors and MMIC device exception to RLAT requirement. |
| Rev. B | 8/21/00 | Pg. 47, Acronym List | Added Flight Instruments Development Manager (FIDM) to list. |

# 1.0	MISSION ASSURANCE PLAN

## 1.1	General

This section defines the Outer Planets/Solar Probe (OP/SP) Project’s approach to Mission Assurance.  The approach described here is in compliance with the JPL Process for Tailoring Mission Assurance to Specific Projects (JPL D-12872, Rev. 1).  The Mission Assurance Plan is tailored to the OP/SP Project requirements of developing and integrating hardware and software for the Europa Orbiter, Pluto/Kuiper Express and Solar Probe Missions.

The following characteristics of this Project will be given appropriate consideration in the development of all aspects of the Mission Assurance Program:

Assumed Mission Lifetimes:  Europa Orbiter – 6 1/2 years, Pluto/Kuiper Express - 14 years, Solar Probe - 6 years,

The implementation approach defined herein was determined by identifying the driving customer mission characteristics and requirements followed by the identification of the various Mission Assurance activities that address the mission’s characteristics and requirements.  These results were then reviewed by the Mission Assurance team, Project Management and PEMs and are incorporated in this document.  The driving requirements on Mission Assurance are:

Radiation (Europa Orbiter)

Long life (Pluto/Kuiper Express (14 years), Europa Orbiter (6 ½ years), Solar Probe (6 years)

## 1.2	Implementation

A Mission Assurance Manager (MAM) shall be assigned as a member of the OP/SP  Project staff, reporting to the Project Manager.  The MAM shall be responsible for coordinating the support and participation of the various areas of mission assurance expertise and will advise the Project Manager on all aspects of risk management and control..  The Mission Assurance Program and its functional supporting elements will have high visibility to both the Project Management and the independent Safety and Mission Assurance Directorate (SMAD).  The MAM, with the concurrence of the Project Manager, will be responsible for reporting the status of the OP/SP  Mission Assurance Program. At the Project MMRs and monthly SMAD status reviews.

The Mission Assurance Program will be implemented using a concurrent engineering approach in all related disciplines.  The MAM and other key personnel being an integral part of the Project Design Team will facilitate this.

Due to the complexity of the individual Mission Assurance disciplines, the MAM will have control of the funding resources to obtain the support of engineering specialists, including quality assurance, reliability engineering, electronic parts, software assurance, environmental requirements and testing, to assure Mission Assurance technical excellence.

## 1.3	Reviews

The Project shall implement a formal review program commensurate with the guidelines described in the JPL Guidelines for Reviews (JPL D-10401, Rev. A)  This document is compliant with the requirements of NPG 7120.5A.  The Project Manager shall appoint a Standing Review Board and conduct, as a minimum, the following formal reviews for each mission:

- PDR

- CDR

- Assembly and/or Subsystem PDRs and CDRs

- Inheritance Reviews (where applicable)

- Test Readiness Reviews (TRRs)

- Hardware Readiness and Certification Reviews (HRCR)

- Software Readiness and Certification Reviews (SRCR)

- Spacecraft Pre-ship Review

- Launch Readiness Review (LRR)

Pre-environmental test reviews, functional requirements review, and ASIC reviews may be informal peer reviews.  Additional informal reviews may be convened at the Project Manager’s discretion.

## 1.4	Environmental Requirements

The environmental requirements for OP/SP  are contained in JPL D-18354.  The environmental requirements for X2000 IFDP, which is applicable to the avionics subsystem, are contained in the X2000 First Delivery Project Environmental Design and Test Requirements (JPL D-15517, Rev. B).  The environmental requirements specific to the Stirling Radioisotope Power Source (SRPS) are contained in JPL D-18868.  The intent of these documents is to qualify the OP/SP deliverables over the enveloped set of mission requirements.   The environmental requirements for the F5 RTG will be determined by JPL and DOE.

### 1.4.1	Radiation Control Plan

The extreme Jovian and near-Sun radiation environments necessitate the implementation of a Radiation Control Plan (RCP).  The RCP (JPL D-18357) shall be implemented to verify that the OP/SP hardware has been evaluated for survivability in the Jovian and Solar radiation environments.  The Radiation Control Engineer (RCE) shall work concurrently with the CogEs, Reliability Engineer and Parts Program Engineer in order to facilitate: the completion of the Radiation Analysis Completion Statements (RACS) and the verification that  all OP/SP hardware meets the mission radiation requirements.

## 1.5	Systems Safety

The OP/SP Project Systems Safety Plan (JPL D-18355) establishes the overall systems safety for the OP/SP Project. The plan provides a management approach for assuring safe design and operations throughout all activities associated with development and delivery to the user projects.  It is the policy of JPL and the OP/SP Project to ensure personnel and hardware safety in consonance with Project achievement.  Personnel involved with the OP/SP Project  will have a thorough knowledge of systems safety practices and shall apply it to assure safe and successful missions.

## 1.6	Risk Management

The OP/SP Project shall implement a risk management program consistent with NASA NPG 7120.5A.  The OP/SP  Project Manager shall assign a Project level Risk Manager.  The Risk Manager shall be responsible for the coordination of the Significant Risk Lists (SRL’s), risk status reporting, risk analyses and shall participate in risk management decisions.  The Outer Planets/Solar Probe Project Risk Management Plan (JPL D-18863) describes the implementation of risk management for OP/SP .

## 1.7	Configuration Management

OP/SP  shall implement a configuration management program at all levels of hardware and software development.  The OP/SP  Project Manager shall assign a Project level Configuration  Engineer (CE).  The Configuration  Engineer shall be responsible for managing the configuration of  prototype, ProtoFlight, EM and FM hardware.  The CE shall coordinate software configuration management with TMOD/MDS to provide overall CE cognizance. The Configuration Management Plan (JPL D-18356) describes the implementation of configuration management for OP/SP. .

## 1.8	Lessons Learned

The OP/SP Project shall implement the infusion of NASA  (including JPL) lessons learned into the design, development, and test and integration of the Project’s hardware and software deliverables.  The Mission Assurance Manager will support the development and implementation of the lessons learned process.  The OP/SP  PEMs and CogEs shall be responsible for documenting their responses to each lesson learned prior to the Mission CDR.

## Materials and Processes Control

All implementing organizations, both internal and external to JPL, shall meet the requirements of the OP/SP Materials and Process Control Plan, JPL D-18570.

## 1.10	Contractor Requirements

All Project contractors and their subcontractors shall observe all requirements contained herein.  Project contractors shall submit for JPL review and approval, ISO 9000 compliant Implementation Plans describing how the requirements of this document are to be met.  Contractors shall designate an individual within their project organization to be responsible for planning and management of Mission Assurance activities including:

- Overall Product Assurance

- Hardware Quality Assurance

- Software Quality Assurance

- Reliability Assurance

- Problem Reporting System

- Parts Program

- System Safety

- Materials and Processes Control

- Contamination Control

That person shall be responsible for monitoring to assure proper and timely accomplishment of the required Mission Assurance tasks. The contractors Mission Assurance organization, in general,  will have an independent path to upper management to raise Mission Assurance issues. The contractor shall implement and maintain a system of monthly reporting to the OP/SP Project Office, in a manner and format such as to provide JPL the visibility and status of the contractor’s and all subcontractor’s Mission Assurance Programs (i.e., Product Assurance).  Deviations from JPL approved contractor plans shall be documented by the Contract Technical Manager (CTM) per the JPL Waiver Procedure (DMIE-15032).

## 1.11	Waivers

All deviations from the requirements stated herein shall be documented per the JPL Waiver Procedure (DMIE-15032).  The Project waiver request initiators may obtain waiver numbers electronically in the Project Data Management System (PDMS).

# 2.0	QUALITY ASSURANCE REQUIREMENTS FOR OP/SP

## 2.1	Purpose

This section covers three specific areas for the OP/SP Project: the policies and procedures required in the JPL Product Delivery System (PDS), the processes and resources needed to achieve the desired results, and the verification activities and criteria required for acceptability.

## 2.2	Scope

This plan defines the detailed quality assurance requirements and activities to be implemented during the formulation, design, build, assemble and test (DBAT) phases of the OP/SP Project. It includes only those quality system requirements required by the Project, and/or by the nature of the product, necessary to produce conforming product.  It encompasses all program flight, non-flight, test and ground support hardware and software.

The following Quality Assurance Requirements apply to all JPL organizations supporting the OP/SP Project.

## 2.3	Applicable Documents

ISO 9001	Quality Assurance for Design, Development, Production, Installation and Servicing

JPL D-15378	The JPL Software Development Process Description

ISO 9000-3	Quality management and quality assurance standards-Part 3: Guidelines for the application of ISO 9001: 1994 to the development, supply, installation and maintenance of computer software, second edition 1997-12-17.

JPL D-18864	OP/SP Software Management Plan

JPL D-18356	OP/SP Configuration Management Plan

JPL D-16635	Mission Data System Software Quality Assurance Plan

## 2.4	Resource Management

### 2.4.1	Training and Certification

Individuals working on flight shall be trained and certified to the requirements of D-8208 or the approved equivalent supplier document.

### 2.4.2	Information

The QAR (lead hardware Quality Assurance Representative) and SAR (lead Software quality Assurance Representative) shall define, monitor, collect, analyze and report to the OP/SP Project, through the MAM, the information necessary for the control of processes and to ensure conformity of products.  Metrics that characterize the program with respect to trends observed over time allow for both predictive behavior and continuous improvement efforts. The selection and definition of appropriate value-added metrics will be a joint OP/SP Project Office-Quality Assurance activity.

## 2.5	Product Realization

### 2.5.1	General Requirements

The Assembly and Inspection Data Sheet (AIDS), Forms 2916 and 2916-1, shall be utilized for hardware fabrication, assembly, integration and testing performed on-site at JPL. The AIDS, or equivalent planning, will provide clear and concise instructions defining specific assembly instructions, inspection points, inspection criteria and special techniques.  The AIDS, or equivalent, will be reviewed, approved and signed prior to the beginning of operations defined in the text.  Flight hardware at JPL must be accompanied by the appropriate documentation at all times.

Workmanship standards on OP/SP Project Flight Hardware shall meet or exceed the requirements of D-8208.

### 2.5.2	Design and Development Review

The QAR and SAR shall participate in the following reviews, as appropriate:

# Preliminary Design Reviews

- Critical Design Reviews

# Inheritance Reviews

- Readiness Reviews (Manufacturing, Pre-environmental, Test, Launch Vehicle Integration, etc.)

- Pre-Shipment Acceptance Reviews

- Contractor End-Item-Data-Package Reviews

- Hardware Certification Reviews

- Software Review and Certification Requirement (SRCR)

The QAR and SAR perform Quality Assurance risk assessments early in the formulation phase, during the design process, and throughout the project/program life cycle to ensure that hardware and software process/development issues are evaluated relative to end-user goals. The QAR and SAR shall analyze designs for completeness and correctness in addressing mission critical and interface requirements.  Special attention is paid to verifying requirement traceability and monitoring performance constraints.

The SAR shall pay particular attention to the area of fault protection and safety critical requirements during all reviews. The details of software safety/hazards analysis are provided in Section 2.9.

### 2.5.3	Quality Assurance Requirements for Engineering Model Hardware

Quality assurance support of hardware engineering models shall be on an as-requested basis.  In general, quality involvement with engineering model hardware is limited to inspection for workmanship and safety, and verification of hardware/software and test set-up configuration.  Engineering models which are later used for protoflight or flight purposes shall require additional quality review, as determined by the QAR and Project personnel.

### 2.5.4	Acceptance and Environmentsl Test Verification

JPL Quality Assurance shall support the implementation of the OP/SP Project functional

and environmental test program. QA shall monitor and/or witness acceptance  and environmental testing on EM Qualification and FM hardware. Guidelines for QA activities in support of testing are listed below:

• Verification of released test procedures and specifications

• Completion of Facility and Operation Safety Survey’s

• Completion of  ESD Surveys

• Verification that test area is controlled to the extent necessary to protect hardware

• Verification that requirements for hardware handling, storage, contamination, and environmental controls are in effect

• Verification that test equipment is within calibration and/or proof test cycles

• Verification that changes to procedures are documented and approved by the appropriate engineering authority

• Verification that test data is properly recorded

The SAR shall assure that test processes are properly defined and followed.  For mission critical requirements, the SAR shall analyze the test objectives and assure that entry and exit criteria for each level of testing is properly defined and any/all performance shortfalls are documented and properly addressed. As a goal, exit criteria should be met before the OP/SP Project completes the last level of validation testing.

The SAR should also assure proper existence of evidence for performing major software system functional capabilities testing and interface testing.

### 2.5.5	Ground Support Equipment

Quality assurance involvement in Ground Support Equipment (GSE) shall be limited to the level necessary to assure:

•	Flight hardware/software interfaces, mechanical and/or electrical are compliant to requirements

- Current calibration of Electrical GSE

- Current proof-load of Mechanical GSE

- Cleanliness and contamination control requirements are compliant

# Proper and legible identification of the product

- Safety requirements are satisfied and potential hazards are identified

### 2.5.6	Control of Changes

Quality assurance shall participate in the control of changes by:

- Reviewing and approving software system requirement changes after initial baseline is completed

# Ensure that master red-line drawing sets are maintained when necessary

- Verifying all approved changes are properly incorporated/implemented

- Verifying product as-built configuration

- Ensure all software system configurations under system test are properly identified and controlled

- Verifying the appropriateness of the Release Description Document (RDD)

Hardware inspected to pre-released or redlined documents shall be written-up on an Inspection Report (IR).  Pre-released and redlined documentation shall be handled in accordance with the OP/SP Configuration Management Plan, JPL D-18356 sections 3.4.2 and 3.4.3.

For class A/B software, the SAR shall also participate in assessing the criticality of the ARs (Anomaly Reports), software-related PFRs (Problem Failure Reports) or engineering change requests, and evaluating/reviewing the risks associated with its disposition.

The SAR may also author the software portion of the Configuration Management (CM) plan and provide a project CM library function, if requested by the OP/SP Project.

### 2.5.7	Procurement Activities

Contracts, purchase orders and off-lab fabrication work orders will be coordinated with technical and quality assurance personnel to ensure incorporation of applicable quality and technical requirements.  The OP/SP Project QAR and SAR shall support the Contract Technical Managers during the implementation of the procurement phase in the following areas:

- Review procurement documentation, including Requests For Proposals (RFP’s),  Statement-Of-Work (SOW’s), Procurement Requisitions and Equipment Specifications to ensure appropriate quality provisions and clauses are defined, including Contractor End-Item-Data-Package requirements

- Provide the Cognizant Engineer or Contract Technical Manager with pertinent information about the supplier by researching the Quality Assurance Documentation Center (QADC) Vendor Survey Database

# Perform Vendor Survey’s at potential supplier’s, as required

- Interpret and clarify quality activities that are anticipated in support of the Contract Negotiator, to include review of supplier Quality Assurance plans, and Software Configuration Management as applicable

- Participate in vendor Fabrication/Manufacturing Readiness Reviews

- Assist the project management in determining proper contract monitoring points based on risk assessment of contractor’s capability, functional complexity, and mission criticality

### 2.5.8	JPL Quality Assurance Activities at Contractors and Suppliers

JPL Quality Assurance shall monitor procurements at contractor’s facilities.  Their activities shall include, but not be limited to:

- Providing insight/oversight (as applicable), monitoring and auditing of contractor quality assurance activities, to include source inspection when necessary, to assure compliance with documented program quality requirements

- Participating in contractor’s design reviews

- Review of manufacturing processes

- Participating in the disposition of nonconforming hardware and acting as “NASA/Government Quality Representative” on Contractor Material Review Boards (MRB’s)

- Monitoring specified test operations

- Performing final, pre-ship inspections and participating in Pre-ship reviews at the Contractor’s facility

- Verifying accuracy and completeness of end-item-data-packages per purchase order

- Generating a Final Inspection Report (JPL Form 1898) signifying acceptance and Certification of Flight Hardware and its data package

- Verifying packaging, shipping/handling is appropriate for flight hardware prior to shipment to or from JPL

Receiving inspection shall be performed to the extent necessary to assure that JPL procured hardware is compliant to specifications.  Quality Assurance responsibilities for receiving inspection include maintaining a system of calibrated equipment capable of measuring mechanical hardware and generating the necessary documentation required by the OP/SP Project to certify hardware for flight upon its’ acceptance.  Additional receiving inspection activities include documenting, segregating and obtaining disposition of non-conforming hardware or material and maintaining a system that provides for continuous assessment of supplier performance.

## 2.6	Measurement, Analysis and Improvement

### 2.6.1	Measurement and Monitoring of System Performance

All hardware and software intended for flight shall have documented evidence of acceptance by Quality Assurance.  Certification of hardware for flight will be by virtue of a final Inspection Report (IR), which will establish the flight pedigree. As a goal, all Inspection Report’s should be closed-out prior to the Hardware Review and Certification Record (HRCR).

Quality Assurance shall verify that all hardware is certified by virtue of completion of Hardware Review and Certification Review (HRCR).  The JPL HRCR Form TBD will be used to verify and document the minimum OP/SP Project requirements have been satisfied.  A signed and completed HRCR form will be necessary to accompany any critical hardware prior to delivery to Assembly, Test, and Launch Operations (ATLO).  Hardware with open liens from the HRCR shall be authorized for flight system integration with approval of the ATLO Manager.

The SAR shall participate in and support the delivery manager in ensuring that all required items (including source code and documentation) are available, prior to any Software Review and Certification Requirement (SRCR), or delivery review.  Software with open liens from the SRCR shall be authorized for flight system integration with approval of the ATLO Manager.

Software system metrics for monitoring the software development is included in Section 2.8.

### 2.6.2	Measurement and Monitoring of Processes

All processes used in the fabrication of OP/SP Project Flight Hardware will be qualified in accordance with NASA or JPL’s internal procedures.  Qualification of processes shall be performed by the cognizant Technical Division or Organization, and approved by Quality Assurance.

Software development process tailoring and requirements are specified in Section 2.7.

### 2.6.3	Measurement and Monitoring of Product

Quality Assurance evaluates the delivered hardware/software against the agreed to requirements and ensures any outstanding liens resulting from deferred requirements and open problem failure reports are properly addressed. The SAR shall also assure the delivered hardware/software has been properly tested and that proper traceability is present.

All hardware or material destined for Qualification, Protoflight, Flight or Flight Spare status shall be subjected to inspections performed at the level necessary to assure:

- Information, Electrical, Mechanical and physical dimensions and conditions are compliant to applicable Interface Control Documents (ICD’s)

- Work-stations and areas in which Flight Hardware will meet the required Electrostatic Discharge (ESD) protective measures as defined in D-1348

# Hardware traceability requirements are satisfied

- Compliance with the Training and Certification requirements specified in  D-8208

- Evidence of Supplier/Contractor or JPL inspection acceptance has been provided by virtue of a Certificate of Conformance, or equivalent

- Applicable handling, packaging, packing and storage requirements have been attained

# Any electrical interfaces and requirements are compliant

- Compliance to the requirements for workmanship, fit, form and function

- Identification of unacceptable workmanship and processing conditions by documenting any findings on an Inspection Report

All software destined for Qualification, Protoflight, Flight or Flight Spares shall be subjected to the following assurance activities by the SAR:

- Accuracy of as-built product identification

- Existence of instructions for installing the software or appropriate reference to the software manual/user’s manual

- Proper test plans/procedures/reports have been released

- Software system requirements are properly traced in a test traceability matrix or equivalent

- A listing of all problem/failure reports (including open and closed) generated against the latest release of software has been published

Inspection status of hardware will be indicated by means of inspection stamps on applicable documentation that accompanies the hardware.  Records of JPL stamp assignments will be maintained in the JPL Office of Quality Assurance organization files.

Post-test hardware inspections will be performed to determine if the condition of the hardware has been adversely affected by being subjected to the specified testing.  All changes that may have resulted from the testing will be documented on an Inspection Report.

### 2.6.4	Control of Nonconforming Product

A closed-loop system for identifying, documenting, controlling and correcting nonconformances will be implemented on the OP/SP Project.  When hardware, material or documentation is found to be non-compliant, it shall be identified as a nonconforming article, documented as such on an Inspection Report or Problem Failure Report and segregated, to the extent practicable, from acceptable articles.  Each nonconformance will be reviewed and dispositioned by the Cognizant Engineer and that disposition will require concurrence by Quality Assurance Engineering.  Nonconformances documented on IR’s and PFR’s requiring rework or repair to flight or engineering model hardware shall be verified by the QAR.  Corrective action will be taken to prevent recurrence of similar discrepancies.  When a software item is found to be nonconforming to specified requirements, it shall be controlled by the software CM process to ensure that it is prevented from unintended use or installation.

Contractor Material Review Boards shall be convened by Contractor QA.  The JPL Quality Assurance Representative will be a member of the OP/SP Project Contractors’ MRB(s).  The QAR will obtain concurrence from the appropriate JPL Engineering Cognizant Engineer before signing and approving any Contractor dispositions. Contractor nonconformance reports will become a part of the hardware’s End-Item-Data-Package.

### 2.6.5	Records

Quality Assurance shall maintain records that provide evidence of inspections, tests, as-built, configuration and hardware/software status during all phases of the hardware fabrication, assembly, integration and test process.  Records will be clearly identified as OP/SP Project hardware/software and maintained in a manner that provides accessibility for audit review.  These records will become a part of the End Item Data Package that will be retained to support the OP/SP Project. The Engineering Data Management Group will be the focal point for compilation of End-Item-Data-Package(s).  These records will be archived at a location and for a period of time determined by the OP/SP Project Office.

### 2.6.6	End Item Data Package

Hardware fabricated and/or assembled at JPL or procured from a contractor shall have a data package sufficient enough to validate a pedigree as flight worthy and to support a failure investigation, if necessary.  Contractor End-Item-Data-Package and As-Built-Data requirements will be clearly defined in the Purchase Order or Contract Statement of Work (SOW).

Software End-Item Data Package (EIDP) shall be prepared for each delivered software item. The contents of the package shall include, but are not limited to the following:

- As-built product identification for the software, including:

- Operating System name and version.

- Programming language name and compiler manufacturer and version.

- Supporting development environment name and version (if any).

- Software version and release date.

- All needed programs and files necessary to re-build the software executable.

- A set of detailed building instructions.

- Instructions for installing the software or appropriate reference to the software manual/user’s manual.

- A list of new or changed capabilities and liens (comparing to the agreed-to baseline).  Also list the approved change requests. (The liens refer to those baselined capabilities which are not delivered and hence shall not be included in the subsequent testing.)

- List of dates and versions of all required documents.

- A list of all open or closed problem/failure reports discovered against this release of software. (This is needed only when the problems are required to be tracked via problem/failure reports.)

- Verification test procedures/results.

For class A/B software delivery, the following three are also required:

- Acceptance test plan/procedure/report.  This shall address acceptance test configuration, including versions of the interfacing software in the RAM/PROM.  Requirements traceability shall also be included to demonstrate that the deliverables meet the specified requirements.

- Completed Software Review/Certification Requirements (SRCR) form for the delivered item.

- Evidence of acceptance by the implementation organization’s software QA.

### 2.6.7	Assembly, Test, and Launch Operations Support

JPL Quality Assurance support activities for Assembly, Test, and Launch Operations will include, but not be limited to the following:

• Work proactively in the safety and contamination control activity to ensure hardware integrity

• Provide configuration support for test and flight software

• Assure that project documentation requirements are met

• Conduct a physical verification of all hardware to ensure that it meets workmanship, configuration management and other project requirements

• Witness critical operations

• Maintain a spacecraft configuration log

## Software Development Process Tailoring

### 2.7.1	General Software Development Process Requirements

The project shall tailor its software development process following the JPL document D-15378. It also responds to the ISO 9000-3 guidelines. The tailored software development process shall be addressed in the OP/SP Software Management Plan (SMP).

Based on the criteria defined in JPL D-15378, the software will be classified by the OP/SP project software engineer. Detailed classification shall be included in its SMP.

The SMP shall also address the following:

- Deliverables, including documents required to be generated.

As a minimum, the following documents for different class of software as listed in the table below shall be produced.

| Software Class | Minimum Deliverables |
| --- | --- |
| A/B | Software requirements document, interface specifications (APIs & ICDs), software design documentation, test plans/procedures/reports, and user guides/software operator’s manuals adaptation guides |
| C | Software functional requirements document (or software capabilities list), test plans/procedures/reports and user guides |

- The criticality of the products and the type of review that the products are subjected to.

(c) Appropriate metrics

(d)	 Software development methodology.

(e) Software development life cycle phases.

- (f) Software adaptation approach.

(g) Governing standards and guidelines (for example, design guidelines, interface specification standards, and coding standards).

The SAR shall assure proper deliverables are generated and reviewed in accordance with their processes.  The SAR shall also review the quality records periodically to assure proper process is followed.

The SAR shall assist the Project Management in tailoring the software development process, within the constraints of cost and schedule, and with acceptable risks.

## 2.8	Software Process and Product Metrics

### 2.8.1 	Metrics Requirements

The project shall define software system metrics to meet the following two goals:

- To characterize the software development process/product with respect to defects, modifications, requirements, and delivered products from the point of view of progress monitoring and product assurance.

- To build software development historical data to allow predictive behavior with respect to requirements, defect density, anomaly reports, schedules, and effort characteristics from the point of view of progress monitoring, product assurance and process improvement.

For class A/B software, the following five metrics will be collected and analyzed:

- Product Delivery Metric

- Earned Value Progress Tracking Metric

- Use Case/Scenario (or Capabilities) Verification Metric

- Anomaly Closure Metrics

The details of the first four metrics definitions and samples are provided in the MDS Software Quality Assurance Plan (JPL D-16635).

### 2.8.2	Software Assurance Activities

The selection/definition of appropriate metrics for progress monitoring or product quality assessment will be elaborated upon and agreed-to by the SAR and the implementation organization Management.  The criteria of selection should be based on the added values the metric provides.  The deployment of metrics collection should be supported by an infrastructure which is minimally intrusive to the development activities.

By agreement of all parties involved, the SAR will perform the metric data collection and analysis.

## 2.9	Software Safety

### 2.9.1	Software Safety Requirements

During the system safety Preliminary Hazard Analysis (PHA), the OP/SP project shall determine the allocation of safety controls to either hardware or software.  As software controls become more clearly defined, the SAR shall perform software safety/hazard analyses to identify individual components, modules, etc. that are safety-critical. The results from the OP/SP Failure Mode Effects and Criticality Analysis (FMECA) will also be used as part of the inputs for the software safety requirements.  The design shall not allow any software components to become safety critical and impact personnel safety.

### 2.9.2	Software Assurance Activities

The SAR shall assure the identification, implementation, and verification of safety-critical components are properly performed. The SAR should assure that the software will execute within a system context without contributing to hazards.  The SAR should assure the software will not affect system safety in the following two ways:

- It cannot produce output values or timing that puts the system in a hazardous state.

- It cannot fail to recognize or handle hardware failures which it is required to control or respond to.

# 3.0	HARDWARE RELIABILITY ASSURANCE PLAN

## 3.1	Introduction

### 3.1.1	Scope

This section establishes the detailed reliability assurance requirements to be satisfied and activities to be implemented during the design, fabrication, integration, test, and delivery of all hardware elements for the OP/SP  project.

### 3.1.2	Purpose

The purpose of this section is to define the reliability assurance requirements, which when satisfied, will serve as verification that all assemblies and subsystems meet their performance requirements in the intended operating environment.

### 3.1.3	Objectives

The objective of this section is to identify the reliability tasks and activities necessary to accomplish the mission goals.  To this end, this section has the following specific objectives:

- Assure that adequate consideration is given to reliability during the design and development of the flight hardware (assemblies and system).

- Assure that possible sources of reliability risk are identified and eliminated through the design verification process.

### 3.1.4	Responsibilities

Primary responsibility for the implementation and accomplishment of activities that satisfy the requirements of this section belong to the JPL responsible design agencies and their respective contractors and subcontractors.   Technical adequacy of the analyses shall be verified and approved  by JPL  independent review or concurrent engineering generation of the analyses.

## 3.2.	Applicable Documents

### 3.2.1	Documents

# JPL D-18357	OP/SP Project Radiation Control Plan

# JPL D-5703 	JPL Reliability Analyses Handbook

# JPL D-8545, Rev. B  	JPL Derating Guidelines

## 3.3	Reliability Assurance Requirements

### 3.3.1	Reliability Analyses Requirements

Analyses of the hardware design shall be performed to ensure proper designed-in reliability and consistency with mission requirements and objectives.  The analyses  will be performed concurrently with the design effort.  The following reliability analyses shall utilize the methodology  described in JPL D-5703 or PEM and MAM approved methodologies:

a.	Failure Modes, Effects, and Criticality Analysis (FMECA)

- At assembly level interfaces

- At fault containment region boundaries

- At GSE interfaces

- At the flight system level

b.	Worst Case Analysis (WCA)

1.  On all circuits and interfaces

c.	Stress Analysis

1.	Parts Stress Analysis (PSA) on all Electrical and Electromechanical Parts

2.	Structural

3.	Thermal

d.	Single Event Effect Analysis

      - On all flight assemblies

      - At the system level by considering the combined effect the assembly level SEE analysis results

Responsible design agencies within JPL, contractors, and subcontractor organizations, shall be responsible for performing, documenting, and updating all of their analyses.  All analyses shall be maintained in a current state and reflect the currently approved design.  These agencies shall take appropriate actions driven by the results of each analysis.

The results of the WCAs, PCAs, and SEE Analyses, and all supporting data shall be documented and provided to the Radiation Control Engineer to facilitate the completion of the Radiation Analysis Completion Statement (RACS) as required by the OP/SP Project Radiation Control Plan (JPL D-18357).

For inherited hardware, existing analyses may be satisfactory if applicability is demonstrated by verification that all originally applied requirements, environments, and other bounding conditions envelope the corresponding elements required by the current application.  Analyses shall be performed and documented, if applicability cannot be demonstrated or analysis has not been performed.

### 3.3.2	Success-Critical Single Failure Point (SFP)

OP/SP  hardware may contain SFPs provided that a single failure will not adversely affect hardware in another fault containment region or across a spacecraft interface.  All system SFPs shall be identified and documented in a SFP list.  No safety critical single point failures are allowed.

### 3.3.3	Reliability Analyses

#### 3.3.3.1	FMECA

The main objective of a FMECA is to identify SFPs and to verify that failures will not propagate and damage other hardware.  The FMECA shall be performed and documented to analyze postulated failures and identify the potential resultant effects.  The FMECA shall be performed on the Flight configurations.  The FMECA shall, as a minimum:

For interface FMECA:

- Be performed at the slice and/or assembly level interfaces to the piece part level to verify that a failure in any slice and/or assembly interface circuit cannot propagate to and/or damage the interfacing circuit and or damage hardware in another fault containment region.

- Verify that failures in ground support or test equipment cannot propagate to and damage the OP/SP  hardware.

For system level FMECA:

- Consider all operational modes

- Verify that a failure in a system element will be detected and determine the system reaction to the failure.

- Verify that a failure in a non-critical circuit (e.g., telemetry, current monitoring, test interfaces not used in flight) will not affect the performance of a critical function.

#### 3.3.3.2.	Electrical/Electronic Worst Case Analysis

A WCA shall be documented for all circuit designs to demonstrate that sufficient operating margins exist for all operating conditions and performance requirements  considering the combination of the following:

- Part temperature range, based on those stated in the environmental requirements document.  If the thermal analysis indicates a part temperature outside of the specified range, the WCA must be amended to take into account the thermal analysis predicted temperatures.

- Piece part initial tolerance

- Part aging for the operating life of the mission including ground test time

- Radiation effects

- Special factors such as shock, vibration, or vacuum where such conditions would contribute to variations in the circuit parameters, voltage, frequency, and load variations shall also be included.

The analysis shall be at least a 3-sigma worst case analysis (i.e., extreme value or extreme value with temperature tracking) in that the value for each of the variable parameters shall be set to limits that will drive the output to a maximum (or minimum) and shall consider AC, DC, and transient condition effects on the circuit.  Piece part parametric data should be obtained from test and/or the appropriate procurement documentation.

Analysis of protective circuitry shall be performed to ensure proper operation if a fault were to occur. (i.e., Assume a fault condition occurred such that the protective circuit is operating and will continue to operate under worst case conditions.)

Electrical noise on power lines, including ground differences, and interface signal lines shall be considered.  Power supply turn on and turn off transients shall be included.

The documentation of the WCAs shall describe all identifiable deficiencies and performance restrictions.

#### 3.3.3.3.	Mechanical Worst Case Analysis

Worst case mechanical analyses shall be performedto ensure that worst case mechanical tolerances and thermal environments cannot adversely affect the performance of mechanical and/or optical assemblies.

#### 3.3.3.4.	Electronic and Electromechanical Parts Stress Analysis

Parts Stress Analysis shall be performed under worst case operating conditions and documented to verify that the applied stress on each piece part does not exceed the derating values established in JPL D-8545, Rev. B.  All analyses shall be documented on JPL-provided or approved forms.  The stress analysis shall utilize the predicted part case temperature over the qualification temperature range .

#### 3.3.3.5.	Structural

A structural stress analysis shall be performed on mechanical and electromechanical (e.g., actuators) subsystems/assemblies at the slice and subsystem level.  The analysis shall address the effects to be experienced by the structure due to the dynamic environment (i.e., acceleration, shock, vibration, and acoustic noise), including worst case estimates for design environmental conditions.

#### 3.3.3.6.	Thermal

The thermal analysis shall address the effect of the thermal environment, including worst case estimates, for all anticipated environmental conditions.  The analysis shall address material properties and the effect of thermal cycling on solder joints, conformal coating, and other critical materials.  As a guideline, the conservative assumption of a maximum temperature rise from the thermal control surface to the part case of no greater than 35(C, may be applied.

#### 3.3.3.7	Single Event Effects Analysis

Circuit designs containing parts susceptible to SEE (Single Event Upsets and Single Event Transients) shall be analyzed to provide either an assembly upset rate or upset probablility during a mission critical time. The requirements regarding performance with respect to SEE during operation for any microprocessor or its peripheral family, or any other parts, are as follows:

- Temporary loss of function or loss of data shall be permitted provided that the loss does not compromise subsystem/system health, full performance can be recovered, and there is no time in the mission that the loss is mission critical.

- Normal operation and function shall be restored via internal correction methods without ground intervention in the event of an SEU.

- Fault traceability shall be provided in the telemetry stream to the greatest extent practical for all anomalies involving SEEs.

- Irreversible actions shall not occur as the result of an SEE.

#### 3.3.3.8	Sneak circuit analysis

Subsystem interface circuits should be analyzed to determine if sneak paths exist with powered and unpowered circuits.  If sneak paths do exist, there must be assurance that they will not affect the function of the circuits involved nor cause overstress to any parts.

### 3.3.4	Operating Time Requirements

Cumulative test operating time shall be tracked on OP/SP  hardware.  All OP/SP  flight hardware deliveries to Europa Orbiter, Pluto/Kuiper Express, and Solar Probe shall have accumulated 500 hours (goal of 1000 hours) of operating time prior to delivery to ATLO; 1000 hours (goal of 2000) prior to launch.

# 4.0	PFR PLAN

## 4.1	Introduction

### 4.1.1	Purpose

The purpose of this section is to define the requirements for reporting, analysis, corrective action, review, and closure of problem/failures documented for the OP/SP  Project.

### 4.1.2	Scope

This section covers all OP/SP  hardware, software, and support equipment and associated software.  The provisions of this document apply to all activities affecting these items up to and including  ATLO and launch.

## 4.2	Applicable Documents

The following documents, of the latest issue, form a part of this document to the extent specified herein.  In case of conflict between a referenced document and this document, the conflict shall be presented to the Mission Assurance Manager for resolution.

D-1926	Reporting System and Procedure for Spaceflight Significant Events File

D-8091	JPL Standards Document, Problem/Failure Reporting System, Guidelines and Procedures

D-11119	Alert/Concerns Handbook

## 4.3	Problem/Failure Reporting System Requirements

### 4.3.1	General

The requirements and processes described herein have been tailored from D-8091.  OP/SP  hardware and software shall be supported by a problem/failure reporting,  analysis and corrective action program.  Two types of problem/failure reports shall be utilized:

- Problem Failure Reports shall be used for:

- Prototypes, Engineering Models (both qualified and nonqualified), ProtoFlight and Flight  hardware

- Hardware and software during I & T (hardware testbed) and ATLO

- Support equipment (hardware and software)

- Anomaly Reports (ARs) shall be used for:

- Developmental and Flight software

### 4.3.2	PFR and AR Starting Points

The required starting points for PFRs are defined below.  Reporting requirements continue during all subsequent phases of testing and integration.

#### 4.3.2.1	 PFRs for:

- Hardware to begin at first application of power of each PT, EM, PF, and FM assembly.

- Support equipment hardware and software (including test and facility equipment) after GSE acceptance testing.

GSE anomalies that occur during GSE acceptance testing shall be logged and included in the End Item Data Package.

#### 4.3.2.2	ARs for:

(1) Software to begin at S/W development, integration and/or  test on workstations.

ARs will be converted to PFRs, within 24 hours, at the start of System I & T.

### 4.3.3	Requirements for PFRs and ARs

# This section outlines the requirements for PFRs and ARs.

#### 4.3.3.1	Incidents Requiring Reports

All incidents require the initiation of a PFR or AR, including:

- All hardware failures, damage, problems, malfunctions, anomalies, nonstandard or unexpected results, and incidents of performance outside specification limits; also incidents of anomalous dynamic performance such as glitches, drifts, transients, stepping, oscillation, etc., within specification limits.

- All software and procedure problems, errors, ambiguities encountered with the software while utilized with OP/SP  hardware or while being checked in preparation for operation with OP/SP  hardware or while in the workstation environment.

- All support equipment, test equipment, or test facilities problems, failures, and anomalous performance, including procedures and operator actions, while being utilized in conjunction with OP/SP hardware or while being checked in preparation for operation with OP/SP hardware.

- All incidents involving actual or potential damage to hardware, software, or injury to personnel, from testing, handling, shipping, or storage.

#### 4.3.3.2	Timeliness of Reporting and Release

All reportable incidents shall be documented within one working day of incident/observation.  The reports shall be released without delay, regardless of the incident’s apparent magnitude.

#### 4.3.3.3	Responsibility of Reporting

The individual in charge of the activity, or of the OP/SP hardware, software, test equipment, or support equipment at the time a reportable incident occurs has the primary responsibility to originate the  P/FR or AR; however, any individual observing a reportable incident has a responsibility to originate a PFR or AR.

#### 4.3.3.4	Form for Reporting

All problem/failure incidents shall be documented by entering the appropriate information electronically into the JPL UPRS (Unified Problem Reporting System), AAMS (Automated Anomaly Management System) or contractors equivalent system (with Mission Assurance Manager approval).

#### 4.3.3.5	Analysis Requirements

Analyses of the PFRs and ARs shall be conducted to the extent necessary to define the problem, determine the failure mechanism, identify whether parts may have been overstressed as a result of the failure, address the effect of the incident on associated elements of the subsystem and the system (including near and long-term effects on desired functional performance), and determine the necessary corrective action.  The proposed corrective action shall be analyzed to ensure that the implementation will address both the problem and any interactions with other elements of the subsystem and the system.

#### 4.3.3.6	Corrective Action Requirements

When corrective action is implemented, all documents defining changes in design configuration, or document revisions shall be processed in accordance with configuration control requirements and referenced on the PFR or ARs prior to closeout review and approval.

Verification of corrective action shall involve appropriate analyses, breadboard or prototype tests, rerun of qualification, protoflight or acceptance tests, regression testing, or the completion of special tests to ensure that correction has been accomplished.  After completion of the corrective action, the item must again be subjected to the conditions under which the problem/failure occurred and must perform successfully under those conditions.

#### 4.3.3.7	Criticality and Cause/Corrective Action Rating

Each PFR shall be assigned a two-factored rating.

##### 4.3.3.7.1	Failure Effect Rating

The Failure Effect Rating is an assessment of the consequence or the impact of the problem or failure if it had occurred in flight.  It shall not be an assessment of the adequacy of the corrective action.  Redundancy shall not be considered in making this assessment.  The assessment shall be 1, 2, or 3 based on the criteria listed below.  Table 1 indicates the P/FR rating requirements.

Rating 1:  Negligible effect on mission performance and system safety.

- No appreciable change in functional capability.

- Minor degradation of engineering or science capability.

- Support equipment or test equipment problem/failure.

- SE, TE, or operator induced failure.

- Workmanship failures found at initial test opportunity.

- Causes negligible operational difficulties or constraints.

- Negligible or no reduction in lifetime.

- Cannot occur in flight.

Rating 2:  Significant effect on mission performance or system safety.

- Appreciable change/degradation in functional capability.

- Appreciable degradation of engineering or science capability.

- Causes significant operational difficulties or constraints.

- Significant reduction in lifetime.

Rating 3:  Major or catastrophic effect on mission performance or system safety.

- Major change/degradation in functional capability.

- Major degradation of engineering or science capability.

- Causes major operational difficulties or constraints.

- Major reduction in lifetime.

##### 4.3.3.7.2	Cause and Corrective Action Rating

The Cause/Corrective Action Rating is an assessment of the certainty that the exact failure cause has been determined and that the corrective action will eliminate any known possibility of recurrence of the problem/failure in flight.

The assessment shall be 1, 2, 3, or 4 based on the criteria listed below.

Rating 1:  Known Cause/Certainty in corrective action.
Analysis, corrective action and verification of correction are considered to have determined the cause and have defined an effective corrective action that has been implemented and verified by test or other demonstration.  No known possibility of recurrence in flight.

Rating 2:  Unknown Cause/Certainty in corrective action.
The cause could not be completely determined, but an effective corrective action has been implemented and verified by test or other demonstration; or the problem/failure (observed incident) could not be repeated in tests or checkouts.  No known possibility of recurrence in flight.

Rating 3:  Known Cause/Uncertainty in corrective action.
Analysis, corrective action and verification of correction are considered to have determined the cause, but effective corrective action has not been implemented and verified by test or other demonstration.  Some possibility of recurrence in flight.

Rating 4: Unknown Cause/Uncertainty in corrective action.
The cause could not be completely determined and no effective corrective action has been implemented and verified by test or other demonstration.  Some possibility of recurrence in flight.

#### 4.3.3.8	Risk Assessment

##### 4.3.3.8.1	Red Flag PFRs

All PFRs having a Failure Effect Rating of 2 or 3 coupled with a Failure Cause/Corrective Action rating of 3 or 4 are defined as “Red Flag” Problem Logs and PFRs.

Each Red Flag PFR must include a statement regarding the rationale for accepting the residual risk.

All Red Flag PFRs shall be discussed at subsequent formal reviews.

|  | Failure Effect | Failure Cause/Corrective Action |
| --- | --- | --- |
| Negligible | 1 | 1 | Known cause/Certainty in corrective action. |
| Significant | 2 | 2 | Unknown cause/Certainty in corrective action. |
| Major | 3 | 3 | Known cause/Uncertainty in corrective action. |
|  |  | 4 | Unknown cause/Uncertainty in corrective action. |

Table 1  P/FR ratings

##### 4.3.3.8.2	Preliminary Rating of PFRs

A preliminary rating in accordance with 4.3.3.7 above shall be assigned within 10 working days from date of incident to determine if there are potential Red Flag issues.

#### 4.3.3.9	Safety Rating and Assessment

Each PFR and AR shall be reviewed by the Reliability Engineer to determine if there is any potential adverse effect on personnel safety or hardware safety associated with the problem/failure.  It is the responsibility of each PFR/AR reviewer to determine that the assigned safety ratings are appropriate.

All PFRs and ARs with a hardware or personnel safety issue shall have a safety risk assessment made by the JPL Systems Safety office and shall be signed by the JPL Systems Safety Engineer and the Contractor Safety Engineer (if applicable).

#### 4.3.3.10	Spacecraft Significant Event File (SSEF) and Alert/Concern Assessment

Each PFR and ARs shall be reviewed to determine if it meets the criteria for an SSEF issue as defined in D-1926 and or if it meets the criteria for a JPL alert/concern issue (reference D-11119).

#### 4.3.3.11	Review, Approval, and Closure

##### 4.3.3.11.1	PFR Review, Approval and Closure

Each PFR and AR shall be subjected to a review, approval, and closure process as follows:

The subsystem cognizant engineer and reliability engineer shall perform  a preliminary review of each PFR and AR.  Each PFR and AR shall be assessed and rated for safety concerns.  Each PFR and AR shall be  assigned a cause code, and a cause/corrective action rating by the Flight Systems Engineer.

PFRs and ARs ready for closure shall be sent to the appropriate signatories prior to a  Problem Review Board (PRB) meeting.  The PRB membership, as a minimum, shall consist of the following:

- Subsystem CogEs

- Subsystem PEMs

- Reliability Engineer

- Flight Systems Engineer

- System Safety Engineer

- Mission Assurance Manager

- ATLO Test Conductor (at start of I & T)

- Flight Systems Manager

- Flight Instruments Development Manager (for science instruments)

Additionally for ARs:

- Project Software Engineer

The  PRB  shall meet to review, approve and sign PFRs and ARs on a regular basis.  Closure of a PFR or AR requires that all appropriate signatures are on the PFR or  AR as follows (see figure1):

- Project Element Manager for all PFRs and ARs.

- Hardware and/or Software Reliability Engineer for all PFRs and ARs.

- System Engineer for PFRs and ARs which:

- Result in an E/BCR to OP/SP  hardware or software

- Result in a waiver to level 4 or higher functional requirements

- Have an unknown cause

- Have a cause/corrective action rating of 3 or 4

In addition, the cognizant engineer or reliability engineer can decide that any other PFR or AR should be reviewed by the System Engineer.

- Safety Engineer will review all PFRs and ARs to assess for hardware or personnel safety issues.

- Mission Assurance Manager for all PFRs and ARs (Project S/W Engineer for ARs) with a rating >1/1 or 1/2.

- OP/SP Project Manager, Flight System Manager and Flight Instruments Development Manager (science instruments) for Red Flag PFRs and ARs (Project S/W Engineer for ARs).

## 4.4	Contractor Problem/Failure Reporting Requirements

### 4.4.1	General

Each Contractor organization external to JPL that is providing OP/SP  hardware and/or software shall establish a system for controlling and monitoring the status of problem/failure reports prepared under its cognizance.  The requirements for such a system shall be in accordance with Section 4 herein.  The use of a contractor’s problem/failure reporting form requires the approval of the JPL Reliability Engineer or the OP/SP  Mission Assurance Manager.  Contractors shall pass these requirements down to subcontractors/suppliers.

### 4.4.2	Liaison and Submittals to JPL

The initial submittal to JPL shall consist of JPL PFR Form 1846 or equivalent as approved by JPL with at least Section I (Description) completed, or a copy of the Contractor’s report as released with initial reporting data sections completed.  The submittal shall be sent electronically to the JPL UPRS or entered directly into the web-based UPRS system within 2 working days of the incident.  The UPRS will then electronically inform the Contract Technical Manager and JPL Cognizant Engineer that the report is in the JPL UPRS automated system.  The Monthly Technical Progress Reports shall include a summary of problem logs and/or PFRs generated during the reporting period.

Interim submittals to JPL shall consist of updated releases of the Contractor’s report and copies of referenced supplemental data and documents.  Submittals shall be sent to the JPL UPRS.

The final submittal to JPL shall consist of the Contractor’s signed PFR with copies of referenced supplemental data/documents not previously submitted. Submittals shall be sent to the JPL UPRS.

Prior to submittal of a Contractor signed PFR to JPL, the verification analysis and corrective action must be reviewed and approved by both contractor’s Project Engineer and the Contractor’s Product Assurance Manager.  Also, in the case of Red Flag PFRs, the Contractor’s Project Manager must review and approve the PFR.  After the receipt of a Contractor signed PFR at JPL, it shall be reviewed by the JPL cognizant engineer and/or PEM.  The PFR shall not be considered closed by the contractor until it has been approved by the appropriate signatories at JPL.

# ELECTRONIC PARTS PROGRAM REQUIREMENTS

## 5.1	Introduction

### 5.1.1	Purpose

This section defines OP/SP  Electronic Parts Program requirements and their applicability to organizations both within and external to JPL.

### 5.1.2	Applicability

The requirements specified herein are applicable to all OP/SP EM and FM hardware. This includes all JPL, contractor, subcontractor and other supporting organizations providing flight equipment.  In cases of conflict between this document and any applicable document, this document shall take precedence.

### 5.1.3	Applicable Documents

The latest revision of the following documents applies to the extent specified herein.

# JPL Documents

JPL D-1348, Rev. D	Electrostatic Control for Assembly and test Area for Flight Projects

JPL D-8545 Rev. B	JPL Derating Guidelines

JPL D-16389	Guidelines for Insuring Known-Good-Die (KGD) in JPL Space Flight Hardware

JPL D-18354	OP/SP Project Environmental Design Requirements

JPL D-18357	OP/SP Project Radiation Control Plan

# NASA and Military Documents

MIL-STD-883	Test Methods and Procedures for Microelectronics

MIL-PRF-19500	General Specification for Semiconductor Devices

MIL-PRF-38534	General Specification for Hybrid Microcircuits

MIL-PRF-38535	General Specification for Manufacturing Integrated Circuits

QML-38534	Qualified Manufacturers List of Custom Hybrid Microcircuits

QML-38535	Qualified Manufacturers List of Microcircuits Manufactured to the Requirements of MIL-I-38535 (including Appendix A where applicable)

QPL-19500	Qualified Products List of Products Qualified under PRF-19500, General Specification for Semiconductor Devices

SSQ25000	Destructive Physical Analysis Testing Specification for the Space

Station Program, Revision B

SSQ25001	Upgrade Screening, Space Station Program

## 5.2	Requirements

### 5.2.1	Management Requirements

The OP/SP Parts Program  Engineer (PPE) shall be responsible for the overall implementation and enforcement of this portion of the Mission Assurance Plan.

### 5.2.2	Reviews

The OP/SP Parts Program Manager shall report on contractors Electronic Parts Program Plan (EPPP) compliance to this section of the Mission Assurance Plan at the Preliminary Design Review (PDR) and at the Critical Design Review (CDR) Management reviews of the Parts Program shall be conducted by the procuring agency on a monthly basis until all flight parts have been delivered.  These reviews shall include selection and procurement status, Alert resolution, waiver status, problem description/solutions, qualification status and DPA results.  Actions items resulting from the reviews shall be documented and reported. Designers shall submit the preliminary parts lists by their PDR to the Parts Program Engineer for reliability and radiation assessments.

A review by the JPL Office 514 Component Specialists shall be performed on a complete part list of all OP/SP electronic assemblies.  The OP/SP PPE shall evaluate the results of the review.

The PPE will provide monthly reports to the Mission Assurance Manager and the Project.  This information shall include selection and procurement status, Alert resolution, waiver status, problem description/solutions, evaluation/qualification status, DPA results and, when JPL is the procuring agency, the Electronic Parts Quality Assurance status.  Action items shall be documented and reported, as appropriate.

## 5.3	Parts Selection

Only parts of acceptable quality, reliability, and radiation characterization compliance, as demonstrated through evaluation and/or verified performance, shall be selected for application in flight equipment.  Use of lower quality level parts shall not be allowed without an approved waiver.

### 5.3.1	Parts Classification

#### 5.3.1.1	Standard Parts

The OP/SP  electronic hardware for Engineering Model qualification units shall use parts from the same manufacturer and process as the flight parts as a minimum.  Parts from the same wafer lot or inspection lot are preferred.

The OP/SP  electronic hardware for flight shall use packaged electronic parts that conform to the following minimum reliability standards:

- MIL-STD-975, Grade 1

- Parts successfully meeting the Class K (or equivalent) requirements of MIL-PRF-38534, the appropriate detail specification and listed in QML-38534

- Parts successfully meeting the Level V requirements of MIL-PRF-38535, the appropriate detail specification and listed in QML-38535 (including appendix A where applicable)

- MIL-STD-883, Class S compliant (when QML listed parts are unavailable)

- QPL-19500, JANS

- Military Established Reliability (ER) passive devices, Failure Rate Level R or S

Science instruments shall use “Class S” parts where possible, however, as a minimum shall conform to the “Class B” requirements of the specifications listed below. The Class B requirements of the specifications listed below shall be considered as standard parts for Science Instruments.

- MIL-STD-975, Grade 2

- Parts successfully meeting the Class H (or equivalent) requirements of MIL-PRF-38534, the appropriate detail specification and listed in QML-38534

- Parts successfully meeting the Level Q requirements of MIL-PRF-38535, the appropriate detail specification and listed in QML-38535 (including appendix A where applicable)

- MIL-STD-883, Class B compliant (when QML listed parts are unavailable)

- QPL-19500, JANTXV

- Military Established Reliability (ER) passive devices, Failure Rate Level R or S

#### 5.3.1.2	Nonstandard Parts

All parts not meeting the minimum reliability criteria of the standard parts in 5.4.1.1  are defined as nonstandard parts.  All nonstandard parts shall be upgraded to Class S, Level V, Class B for Science Instruments or equivalent level.  A list of the nonstandard parts accompanied by supporting documents (including reliability test data/analysis, radiation test data/analysis, procurement and screening specifications) shall be submitted to and approved by the JPL Parts Program Engineer prior to use.

#### 5.3.1.3	Die

When, based on technology maturity, development cost and risk, the Project decides to implement a Known Good Die program for hybrid microcircuits and MCMs, a Known Good Die (KGD) program (JPL D-16389) level-V shall be implemented for all die, with JPL approval.

#### 5.3.1.4	Noncompliant Parts

Whenever either a standard or nonstandard part fails to fully comply with the standard or nonstandard parts requirements identified herein, and it is decided that the parts will be used in flight equipment, a waiver shall be initiated and submitted to the Mission Assurance Manager for approval.  The waiver shall be approved before the part may be kitted for assembly.

### 5.3.2	Application Specific Integrated Circuit (ASIC) Requirements

Screening and qualification testing shall be in accordance with MIL-PRF-38535, QML level-V (QML Level-Q for Science Instruments) or equivalent.

#### 5.3.2.1	Digital ASIC Test Requirements

Digital logic circuitry in ASICs (including the microprocessor, microcontroller and all custom designs) shall be tested to at least 98% stuck-at fault coverage as is defined by MIL-STD-883, Method 5012.

Quiescent current (all vector IDDQ method) tests shall be based on a set of vectors that will toggle 99.5% of the nodes.

Additional tests shall be conducted that include: 1) operating speed (or maximum testable speed) functional test to verify all functions of the design and 2) DC and AC parametric test vectors.

#### 5.3.2.2	Mixed-Signal ASIC Test Requirements

For mixed-signal ASIC’s the digital portions shall be tested separately from the analog portions; the digital parts will be tested as above.  The analog portions shall be SPICE modeled and tests performed to measure the correspondence of the actual die to the SPICE models.  The ASIC designer and the die manufacturer will jointly specify these tests.  Each die must meet its analog performance specifications. As a minimum, these tests shall be performed prior to incorporation into Slices or MCM’s.  Parametric tests shall be performed over the full military temperature range of –55(C to +125(C.

Digital logic circuitry in ASICs (including the microprocessor, microcontroller and all custom designs) shall be tested to at least 98% stuck-at fault coverage as is defined by MIL-STD-883, Method 5012.  Quiescent current (all vector IDDQ method) tests shall be based on a set of vectors that will toggle 99.5% of the nodes.  Additional tests shall be conducted that include: 1) operating speed (or maximum testable speed) functional test to verify all functions of the design and 2) DC and AC parametric test vectors.  As a minimum, these tests shall be performed prior to incorporation into Slices or MCM’s.  Parametric tests shall be performed over the full military temperature range of –55(C to +125(C.

A minimum sample of 22 die from each ASIC wafer run shall be packaged, tested and subjected to life test. Qualification testing shall be in accordance with MIL-PRF-38535.

Read and record variables test data shall be taken at each test stage of the Life tests; it is anticipated that this data will be used to verify the Worst Case Analysis (WCA) and to characterize the parameter variations.  This characterization will be used to evaluate the SPICE model vs. test data correspondence described above.

A product monitoring plan shall be implemented which includes a provision for the procuring activity to monitor the ASIC vendor’s progress, problems, corrective actions, schedule impacts and requirements for the following:

- Performance of design reviews, including PDR and CDR.

- Performance of 100% customer precap visual inspection.

- Demonstration that the selected vendor’s ASIC parts can meet the Programs Radiation requirements set forth in this section.

### 5.3.3	MCM/Hybrid Requirements

Each custom hybrid microcircuit contractor shall include a plan for meeting the following requirements.

A pre-award survey for the candidate manufacturer’s facilities and controls shall be conducted.  The hybrid microcircuit processing and controls shall be in accordance with the following.

- Element evaluation per paragraph 3.2 Method 5008 in MIL-STD-883.

- Process control per paragraph 3.3 of method 5008 in MIL-STD-883

- One-hundred percent (100%) customer pre-seal visual inspection per Method 2017 of MIL-STD-883.

- Delidding of packaged parts for rework or reseal shall not be permitted.

Following the award of a contract to a manufacturer for a hybrid microcircuit procurement, a post-award hybrid design review shall be  convened by the CogE to demonstrate design adequacy.  Also, a hybrid manufacturing readiness review shall be conducted prior to initiating assembly of the flight devices to verify all necessary procedures, facilities and quality assurance controls are in place and ready to support flight build.

## 5.4	 Radiation Requirements

All parts shall be selected to meet the highest radiation levels available as indicated in the following paragraphs.  All selected parts shall meet the RDM requirements as specified in JPL D-18354 OP/SP Environmental Design and Test Requirements.  Compliance with the following requirements will be verified by implementing the process described in the OP/SP Project Radiation Control Plan (JPL D-18357).

### 5.4.1 	Total Ionizing Dose (TID)

All Parts shall be selected to meet the highest TID levels available. All parts shall be selected to meet a minimum TID level of 100k (Si) at the die level.  Parts not meeting this requirement shall not be used without an approved waiver.  RLAT shall be performed on all flight lots, except GaAs transistors and MMIC devices, per (MIL-STD 883, M-5005, Group E.)

The RLAT specifications shall be submitted with the procurement and screening specifications to the JPL OP/SP Parts Program Engineer for review and approval.

The external radiation environment is specified in the OP/SP Project Environmental Requirements Document (JPL D-18354).

### 5.4.2 	Dose Rate

All linear bipolar, BiCMOS IC’s, and embedded structures in ASICs (e.g., voltage references) shall be evaluated and reported to JPL for susceptibility to enhanced low dose rate (ELDR) effects to assure that parametric degradation due to ELDR have been accounted for in the ASIC or subsystem worst case analysis.

### 5.4.3 	Displacement Damage

All parts shall be evaluated and reported to JPL for displacement damage sensitivity to assure that parametric degradation due to displacement damage has been accounted for in the subsystem worst case analysis.  Selected parts shall have a minimum susceptibility to displacement damage of 1013 n/cm2 equivalent 1 MeV neutron fluence.  Potentially susceptible parts include but are not limited to optical devices, photodetectors, charge, coupled devices, optocouplers, LEDs, laser diodes bipolar power transistors and precision bipolar linear devices.  Displacement damage (beyond that associated with total dose) may also be an issue with neutrons and heavy ions in optoelectronics and certain linear devices.

### 5.4.4 	Single Event Latchup (SEL)

All CMOS devices (including those with epitaxial layers) shall be subject to latchup evaluation.  All parts shall exhibit no latchup with an LET of 75 MeV-cm2/mg.

### 5.4.5 	Single Event Upset (SEU)

All microcircuits containing bistable elements (e.g. flip-flops, counters, RAMs, microprocessors, etc.) shall be characterized so that an upset rate or upset probability  calculation can be performed.  A sufficient number of data points (a minimum of three) shall be taken to determine the curve of device cross section versus LET (to saturation or to an LET of 75 meV-cm2 /mg, whichever comes first).

The requirements for parts SEU acceptability are:

- No upsets during SEU testing to LET of 75 MeV-cm2/mg, OR

- Verification of device bit error rate of 10-10 upsets per bit per day or less in the galactic cosmic ray environment (GCR),  OR

- Calculation of a device’s upset rate in the GCR, Solar Flare Protons, Jovian environment shall be equal to or less than the required circuit upset rate as determined by the Flight Systems Engineer.

### 5.4.6 	Single Event Burnout (SEB)

All power transistors operated in the off-mode may be susceptible to and shall be evaluated for single event burnout (SEB) at the lowest application VBE  or VGS .  The survival voltage (VCE  for bipolar and VDS for MOSFETs) shall be established.  The application voltage shall be derated to 75% of the established survival voltage.

### 5.4.7 	Single Event Gate Rupture (SEGR)

All power MOSFETs operated in the off-mode may be susceptible to, and shall be evaluated for single event gate rupture (SEGR) at the lowest application VGS.  The established survival voltage (VDS) shall be established.  The application voltage shall be derated to 75% of the established survival voltage.

## 5.5	Parts Acquisition

### 5.5.1	Use of Residual (Heritage) Parts Inventory

Residual inventory (i.e., heritage parts) refers to parts previously approved and procured for prior flight Project applications.  Residual electronic parts may be used for OP/SP  only if they meet all requirements of this document.

### 5.5.2 	Parts Procurement

Semiconductors and IC’s shall come from identifiable, non-mixed lots.

Purchase orders shall not take exception to reference specifications or requirements therein unless approved by the OP/SP  Parts Program Engineer via waiver.

### 5.5.3 	Backward Traceability

All parts shall be traceable by manufacturer's part number, serial number, and lot date code.  All ASICs shall have wafer traceability.

### 5.5.4 	Parts Data Requirements

All test and evaluation data shall be submitted electronically. The manufacturer’s or vendor’s certificate of conformance for each electronic part lot shall be obtained and retained at JPLuntil the end of mission.   All parts, electrical test parametric data (variables data) shall be read and recorded.  The parametric data shall be traceable to each serialized part.  All variables and attributes data generated in compliance with the specification shall be delivered to the procuringagency.  The data package shall be reviewed by the procuring agency for completeness. The read and record data may be required for standard parts when the project needs to establish worst case circuit analysis acceptability. This should be included in the parts procurement as requested by the project.

### 5.5.5	Customer Source inspection

Pre-seal visual inspection shall be performed on all packaged, flight ASICs, hybrid microcircuits, MCMs, crystal oscillators and relays.

### 5.5.6 	Post-Programming Burn-In for Programmable Devices

For "one time" programmable devices (i.e. PROMs and FPGAs) a post programming 160-hour burn-in at 125(C followed by DC parametric and functional testing is required for all flight units.

### 5.5.7 	Destructive Physical Analysis (DPA)

DPAs shall be performed on a sample of each manufacturing lot date code for microcircuits, oscillators, resistor networks, crystals, filters, ceramic capacitors (except MIL-C-123), relays, MIL-C-39010 inductors, and all nonstandard packaged parts (including MCM’s and hybrids).  MIL-C-39010 inductors/transformers shall be sectioned to examine the adequacy of the termination.

DPAs shall be performed using only JPL-approved DPA specifications, which may be modeled after SSQ25000.  The results of the DPA shall be evaluated by the procuring activity and the lot shall be accepted or rejected based on the criteria of the specification.

## 5.6	Electronic Parts Application

### 5.6.1	Parts Derating

Each part used in flight equipment shall be applied in a manner such that the temperatures experienced and electrical stresses produced when it is operating do not exceed the derating criteria defined in JPL D-8545, Rev.B.

### 5.6.2	Electrostatic Discharge (ESD) Control Requirements for Static-Sensitive Parts

ESD damage or degradation may occur in static-sensitive electronic parts during handling of the parts from procurement through incoming inspection, testing, screening, storing and final assembly/test.  To protect static-sensitive parts from ESD, handling of parts shall be controlled by the requirements of JPL D-1348.

### 5.6.3	NASA and Government Industry Data Exchange Program (GIDEP) Alerts

All hardware-delivering design agencies, both internal and external to JPL, shall establish and implement a system to review GIDEP Alerts, take appropriate action, and notify their respective GIDEP Alert coordinators of significant parts problems that may warrant issuance of new Alerts.

Design agencies which do not presently receive Alerts directly should request distribution from the Defense Supply Center Corporation (DSCC), GIDEP Operations Center or the JPL Electronic Parts Engineering Office. The design agency is responsible for reviewing all Alerts, and for immediately reporting corrective action for applicable Alerts (i.e. for parts used in the hardware) to the project.

The design agency shall present a report at the CDR, and another at the Pre-Ship Review, that lists all of the Alerts which are pertinent to the parts used in the flight design, the possible impact should the part fail, and the actions proposed and those taken.  It is the responsibility of the design agency to avoid the use of defective parts in flight equipment.

### 5.6.4 	Parts Failure Analysis

Failure analysis is required for all part failures that occur subsequent to screening.  The only exceptions are parts damaged by human error (e.g., improper installation).  Analysis shall be carried to the point that lot dependency of the failure mode can be determined.  Failure analysis reports shall be written to document the analysis approach, the determined failure mode and mechanism (i.e., cause) responsible for the failure, and the corrective actions required to prevent recurrence of the failure.  If a lot dependency is found, the MAM will disposition the  assemblies using the suspect lot.

### 5.6.5 	As-Built Parts List

An As-Built Parts List shall be released prior to hardware integration and test and shall be included in the end item data package (EIDP).  In addition to the information required in the Preliminary Parts Lists, the As-Built Parts List shall include for each different part the:

- Generic part number,

- Actual part marking,

- Manufacturer,

- Lot date code,

- Serial number (for serialized parts),

- Wafer and wafer lot numbers (when required),

- Parts test lot numbers (where applicable),

- Procurement specification number,

- Traceability number (when assigned by the cognizant parts organization), the serial number and part number of the next assembly level into which the part is installed (e.g., board or module),

- Reference designator of the location where each part is used on the next assembly level.

The as-built parts list shall be supplied to the JPL Electronic Parts Engineering Section in a computer readable format.

## 5.7	System Contractors

All Cognizant Engineers who manage contractors and subcontractors shall be responsible for ensuring that hardware delivered to JPL meet all the requirements of this section unless a waiver in accordance with Section 1.11 of this document is first approved by the OP/SP  Project Office.

Each organization responsible for implementing a parts program (contractors and subcontractors) shall prepare an Electronic Parts Program Plan (EPPP) responsive to the requirements of this Parts Program Requirements section.  The OP/SP Project Parts Program Engineer shall review and approve each EPPP, which will include:

- The flight equipment affected including identification of hardware designated as critical.

- The organizational responsibilities, relationships, and key managerial, programmatic and technical roles planned for the implementation of the parts program.

- The implementation plan for meeting the parts requirements of this document, including monitoring its contractors' compliance with their respective EPPP.

- The plan by which the contractors shall demonstrate and report monthly to JPL their compliance with this document.

The contractor shall describe in an EPPP how the technical requirements in this section flow down to subcontractors, how subcontractors' implementation of the requirements shall be reviewed and monitored, and how part selection and procurement status, Alert resolution, nonstandard parts review status, waiver status, problems, problem solutions, and schedules of the contractor and subcontractors shall be reported to JPL.  The contractor shall submit to JPL, for review and approval, a list of all the contractor's and subcontractors' nonstandard parts including part specifications (viz., procurement, screening, lot demonstration, additional testing, upgrade, and DPA), and radiation lot acceptance test plans. The EPPP shall also specify the procedures for maintaining lot traceability and integrity of surplus parts that will be returned to JPL at the conclusion of the contract as well as the procedures for returning surplus parts to JPL Flight Stores.

The contractor shall implement and maintain a system of monthly reporting to the Project Office, in a manner and format such as to provide JPL the visibility and status of the contractors and all subcontractors' parts programs.

All contractors (system/instrument contractors and subcontractors) shall be responsible for the performance of failure analysis on parts that the contractor procures or builds, in accordance with failure analysis requirements delineated in Section 5.7.4 of thissection.  Failure analysis results shall be made available to JPL as the contractor determines them (typically through the Monthly Management Review).  Failure analysis reports shall be delivered to JPL within two months after the discovery of the cause of failure and in no case more than six months after the part failure is discovered.  All failure analysis reports shall be completed and submitted prior to hardware delivery.

## Acronym List

The following is a list of the acronyms and their meanings used in this document:

Acronym	Meaning

AAMS	Automated Anomaly Management System

AIDS	Assembly and Inspection Data Sheets

API	Application Program Interface

ATLO	Assembly, Test, and Launch Operations

AR	Anomaly Report

ASIC	Application Specific Integrated Circuit

CDR	Critical Design Review

CE	Configuration Engineer

CM	Configuration Management

CMOS	Complementary Metal Oxide Semiconductor

CogE	Cognizant Engineer

DBAT	Design, Build, Assembly, and Test

DI	Dielectrically Isolated

DMIE	Define and Maintain the Institutional Environment

DPA	Destructive Physical Analysis

DSCC	Defense Supply Center Corporation

E/BCR	Engineering/Budget Change Request

EIDP	End Item Data Package

EM	Engineering Model

EPPP	Electronic Parts Program Plan

EPPR	Electronic Parts Program Requirements

ESD	Electrostatic Discharge

FIDM	Flight Instruments Development Manager

FM	Flight Model

FMECA	Failure Modes, Effect, and Criticality Analysis

FSM	Flight System Manager

GIDEP	Government Industry Data Exchange Program

GSE	Ground Support Equipment

HRCR	Hardware Review and Certification Record

ICD	Interface Control Drawing

IR	Inspection Report

ISO	International Standards Organization

I & T 	Integration and Test

JPL	Jet Propulsion Laboratory

KGD	Known Good Die

LET	Linear Energy Transfer

MAM	Mission Assurance Manager

MCM	Multi-Chip Module

MDS	Mission Data System

MeV	Million Electron Volts

MOSFET	Metal Oxide Semiconductor Field Effect Transistor

MRB	Materials Review Board

NASA	National Aeronautics and Space Administration

NPG	NASA Program Guideline

OP/SP	Outer Planets/Solar Probe

PDR	Preliminary Design Review

PDS	Project Data System

PEM	Project Element Manager

PF	Proto-Flight

PFR	Problem Failure Report

PHA	Preliminary Hazard Analysis

PPE	Parts Program Engineer

PRB	Problem Review Board

PROM	Programmable Read Only Memory

PSA	Parts Stress Analysis

QA	Quality Assurance

QADC	Quality Assurance Documentation Center

QAR	Quality Assurance Representative

QCI	Quality Conformance Inspection

QML	Qualified Manufacturers List

QPL	Qualified Parts List

RAM	Random Access Memory

RCP	Radiation Control Plan

RGA	Residual Gas Analysis

RLAT	Radiation Lot Acceptance Test

SAR	Software Assurance Representative

SCM	Software Configuration Management

SEB	Single Event Burnout

SEE	Single Event Effect

SEGR	Single Event Gate Rupture

SEL	Single Event Latchup

SEU	Single Event Upset

SFP	Single Failure Point

SMAD	Safety and Mission Assurance Directorate

SMP 	Software Management Plan

SOI	Silicon On Insulator Semiconductor

SOS	Silicon On Sapphire Semiconductor

SOW	Statement of Work

SRCR	Software Review and Certification Requirement

SRL	Significant Risk List

TBD	To Be Determined

TID	Total Ionizing Dose

TMOD	Telecommunications and Mission Operations Directorate

UPRS	Unified Problem Reporting System

WCA	Worst Case Analysis

# Text boxes

N

N

Y

Y

Y

PEM, Reliability Eng., Systems Eng., MAM, FSM, FIDM (for science instruments), Project Mgr. Signatures; Also Project Engineer and Project Software Engineer for ARs

Generate Red Flag summary

PEM, Reliability Eng., Systems Eng., MAM signatures;

Also Project Software Engineer for ARs

PEM, Reliability Eng. signature

Red Flag

1/3, 1/4, 2/1, 2/2, 3/1,3/2

1/1,1/2

CogE institutes corrective action, verifies corrective action

PRT reviews PFR for correct FE rating and closure action plan- assignments

CogE or test conductor initiates PFR, assigns preliminary Failure Effect rating

Incident occurs

PFR/AR flow

Figure 1