## FY2007 Reports
[8 empty] | Cap. $ in blue | [5 empty] | LEAD AGENCY, PRINIPLE INVESTIGATOR, COMMENTS
| BOR AGREEMENT | PROJECT |  | TECH. | TECH. |  | PROJECT | FY 2007 | FY 2007 | FY 2007 | FY 2007 | FY 2007 | FY 2007 |  | FY 2007 | SERVICE (DIRECT FUNDING) | OVER HEAD
| NUMBER | NUMBER |  | COMM. | COMM. | COORD. | TITLE | TOTAL | ANN. FUNDS | CAP. FUNDS | O&M FUNDS | SEC. 7 FUNDS | OTHER FUNDS |  | COMMENTS |  |  | FWS+OH
I. Instream Flow Identification and Protection
O&M, STA |  | 8, 8a | O | WAC | WAC | Smith/Mohrman | Recovery Program Gage O&M (budget includes #8a) | 136245 |  |  | 78245 |  | 58000 | FWS, George Smith. | Program cost reduced from $86.9K. USGS $56K; CWCB/SEO $2K
NR$ |  | 9 | O | WAC | WAC | Smith/Mohrman | Water Right Acq. Consultant | 10000 |  |  |  | 10000 |  | FWS. George Smith. Up to $10K. | Up to $10K | 10000 | 0 | 10000
GOV, ONG, PGM | 07-AA-40-2625 | 19 | OR | WAC/BC | WAC/BC | Smith/Mohrman | Hydrology Support | 189810 | 189810 |  |  |  |  | FWS, George Smith | Increased by $6,500 for GIS work. | 171000 | 18810 | 189810
NR$ |  | 70 | O | WAC | WAC | Smith/Mohrman | Colorado Instream Flow Protection | 15000 |  |  |  |  | 15000 | CWCB, Randy Seaholm, Michelle Garrison. | Colorado additional in-kind funds.
NR$ |  | 71 | O | WAC | WAC | Smith/Mohrman | Colo. R. Decision Support Sys. | 150000 |  |  |  |  | 150000 | CWCB, Ray Alvarado, Michelle Garrison. | Colorado additional in-kind funds.
CAP |  | C-11 | O | WAC | WAC | Smith/Mohrman | Grand Valley Water Management | 0 | [5 empty] | BR, Brent Uilenberg, Bob Norman. No report needed unless work was done on GVWM in FY 07.
NR$ |  | 86 | O | BC/WAC | BC/WAC | Smith/Mohrman | Geomorphology Peer Review | 10000 |  |  |  | 10000 |  | FWS, George Smith. | Up to $10K | 10000 | 0 | 10000
CAP |  | C-9 | O | WAC/BC | WAC/BC | Smith/Mohrman | Elkhead enlargement | 0 | [5 empty] | FWS, George Smith; CRWCD, Dan Birch.
O&M |  | 135 | O | WAC | WAC | Smith/Mohrman | O&M for Ruedi Reservoir 10,825 af | 79710 |  |  | 79710 |  |  | BR, Brent Uilenberg/Terry Gomoll | Reduced from $45K estimate based on 12/12/06 bill from BOR-Loveland. Pre-paid estimated $49,510 FY 08 cost because funds were available at EOY.
CRD |  | C-32 | O | WAC | WAC | Smith/Mohrman | Ruedi Reservoir 10,825 af (capital cost) | 735000 |  |  |  |  | 735000 | BR, Brent Uilenberg/Terry Gomoll.
|  | FR |  |  |  |  | Evaluate Flow Recs.
| 04-AA-40-2169 | FR-Sed. Mon | OR | WAC/BC | WAC/BC | Smith/Mohrman | USGS sediment monitoring | 155000 | 132500 |  |  |  | 22500 | USGS, Paul Vonguerard. FWS, George Smith. | 11/21/06: Revised SOW from USGS req. total of $155K for FY 07; $132.5 from RP and $22.5K from USGS (previous total was $135.5K with $128.2 from RP), 7/7/05: PD's office realized they mis-calculated budget when they included only $67.8K; total of $135.5K needed. Assume $7.3K available from USGS, and remaining $60.4K added in for FY 07.
ONG, NNA | 07-AA-40-2667 | 124 | OR | BC | BC | Chart | Duchesne River riffle eval. | 2882.67 | 2882.67 |  |  |  |  | FWS, Finney | Was nna fish mgmt. But discontinued in '07; reduced from $31.5K. Now just observation of riffle habitat to evaluate Duchesne baseflow recs. | 2597 | 285.67 | 2882.67
|  | FR-Du Sed. Mon | OR | WAC/BC | BC | Smith/Mohrman | USGS sediment monitoring Duchesne | 27000 | 16200 |  |  |  | 10800 | CUWCD, Terry Hickman | FY 06 annual report says '07 budget $19K; RIP share $11.4K.
II. Habitat Restoration
O&M, ONG | 07-AA-40-2626 | C4b-Red | O | BC | MC/BC | Czapla | Redlands Selective Fish Passage Oper. (FWS) | 51171 |  |  | 51171 |  |  | FWS, McAda, Burdick | Program guidance contemplated one scope of work for both Redlands and GVP fish passage operation for $58.7K. Redlands SOW submitted for $46.1K; GVP for $39.2K. | 46100 | 5071 | 51171
| 07-AA-40-2649 | C4b-GVP | OR | BC | MC/BC | Czapla | GVP Selective Fish Passage Oper. (FWS) | 12867.12 |  |  | 12867.12 |  |  | FWS, McAda, Burdick | Reduced operation in FY 07. | 11592 | 1275.12 | 12867.12
CAP |  | C-5 | O | MC/BC | BC | Czapla | Price-Stubb Fish Passage | 2750000 |  | 2400000 |  |  |  | BR, Brent Uilenberg
O&M, ONG |  | C-23 | O | MC/BC | MC/BC | Czapla | Grand Valley Project fish screen & passage O&M | 40000 |  | 225000 | 40000 |  |  | BR, Brent Uilenberg, Bob Norman; GVWUA | Program guidance contemplated $85K O&M, but SOW $79K for FY 07. REDUCE TO 40K, NO PASSAGE OPERATION IN FY 07 (ACTUALLY, ACCORDING TO BOB NORMAN, THERE IS NO BOR/GVP O&M ON THE PASSAGE EVEN WHEN IT IS OPERATED. THEY ONLY O&M THE SCREEN).
CAP |  | C-28 | 0 | MC/BC | MC/BC | Czapla | Tusher Wash diversion screen | 0 |  | 200000 |  |  |  | BR, Brent Uilenberg, Bob Norman.
O&M, ONG |  | C-29 | O | MC/BC | BC | Czapla | GVIC fish screen & passage O&M | 65600 |  |  | 65600 |  |  | BR, Brent Uilenberg, Bob Norman; GVIC. | Program guidance contemplated $93.6K O&M, but SOW shows $85K for FY 07. 2/15/07: Pat checked GVIC annual work plan submitted to BOR from GVIC; total cost $65.6, so reduced from $80K.
ONG, GOV | 07-AA-40-2646 | C-29a | O | BC | BC | Czapla | Retrieve native fish from GVP & GVIC canals | 28130.73 |  |  | 28130.73 |  |  | FWS, Chuck McAda, Bob Burdick. | Salvage native fish from canals in case screens not fully operated (spent in early FY 07, per Chuck McAda). | 25343 | 2787.73 | 28130.73
O&M, ONG |  | 116/C-33 | O | MC/BC | BC | Czapla | Redlands screen, passage & gage O&M | 84400 |  | 20000 | 84400 |  |  | BR, Brent Uilenberg, Bob Norman, Redlands. | Program guidance contemplated $15K O&M, but SOW shows $96.5K for FY 07. (Does include gage maint., also, however.) Muth 8/24/06: $96.5 in FY 07 contains some capital costs. 2/15/07: Per Burdick, subtract $14.5K of the $16.5K for gage O&M. FY 07 O&M $82.4K; capital $14.5K (per 9/13/06 letter), so reduced O&M to $82.4K + 2K for gage = $84.4K. (Reduced from $96.5K)
|  | C-6 |  |  |  |  | Floodplain Restoration Program
ONG, NR$ |  | HYD | O | BC | BC | Chart | Hydrology/geomorphology | 0 |  | 0 |  |  |  | FWS, Pat Nelson.
GOV, $SH | 07-AA-40-2664 | EASEMENT | O | BC | BC | Chart | Easement & weeds mgmt. | 67500 |  |  | 55500 |  | 12000 | FWS, Dan Alonso, Pat Nelson. |  | 62000 | 5500 | 67500
CAP, NR$ |  | CONST. | O | BC | BC | Chart | Construction | 0 |  | 0 |  |  |  | FWS, Pat Nelson; BOR, Brent Uilenberg, Bob Norman. No report required if no work done in FY 07.
ONG, CESU | 05-FG-40-2329 (UDWR), 05-FC-40-2391 (LFL) | RZ-ENTR | P | BC | BC | Chart | Evaluate floodplain drift model for larval razorback | 15000 | 15000 |  |  |  |  | UDWR, Trina Hedrick; LFL Kevin Bestgen.
|  | RZ-RECR |  |  | BC | Chart | Razorback emigration from the Stirrup floodplain | 18143 | 18143 |  |  |  |  | UDWR, Trina Hedrick.
CESU | 06-FC-40-2505 | 146 | N | BC | BC | Chart | Eval. Pikeminnow entrainment in Yampa diversion structures | 14000 | 14000 |  |  |  |  | LFL, John Hawkins
III. Reduce Nonnative Fish and Sportfish Impacts
NR$ |  | C-20 | O | BC | BC | Chart | Highline Net O&M | 8000 |  |  |  |  | 8000 | CDOP, Chris Foreman.
ONG, NNA, $SH | 05-FG-40-2355 FWS: 07-AA-40-2654 | 98a | OR | BC | BC | Chart | Middle Yampa pike translocation | 114121.94 | 114121.94 |  |  |  |  | CDOW, Lori Martin | Increased to continue expansion into South Beach. (No new SOW yet, but should just be the amt in the SOW +$4200) Pat has new SOW, but hasn't had time to review yet; $113.6K | 4254 | 467.94 | 4721.94
ONG, NNA | 07-AA-40-2647 | 98b | OR | BC | BC | Chart | Upper Yampa pike translocation | 183841.53 | 183841.53 |  |  |  |  | FWS, Sam Finney. |  | 165623 | 18218.53 | 183841.53
ONG, NNA | 05-FG-40-2326 | 109 | OR | BC | BC | Chart | Middle Green northern pike management | 10000 | 10000 |  |  |  |  | UDWR, Trina Hedrick | FY 07 cost was previously unknown and not included in Program guidance. Includes synthesis report. Funds went to 123, 109 reduced from $41.7K to $10K just for synth rpt.
ONG, NNA | 07-AA-40-2602 | 110 |  | BC | BC | Chart | Lower Yampa bass and catfish management | 142137.72 | 142137.72 |  |  |  |  | FWS, Mark Fuller |  | 128052 | 14085.72 | 142137.72
ONG, CESU | 07-AA-40-2648 (FWS) 05-FC-40-2318 (LFL) | FR-115 | OR | BC | BC | Chart | Effects of Flaming Gorge releases on Lodore/Whirlpool Canyon fish comm. | 84096.11 | 84096.11 |  |  |  |  | LFL, Bestgen. FWS, Irving | SOW requests $64K. 2/15/07: $10.5K added for SMB otolith analysis added. | 19601 | 2156.11 | 21757.11
ONG, NNA | 07-FG-40-2600 (FWS) 05-FG-40-2325 (UDWR) | 123a&b | OR | BC | BC | Chart | Green River bass management | 331220.02 | 331220.02 |  |  |  |  | UDWR, Paul Badame, Trina Hedrick, Leisa Monroe, FWS, Mark Fuller, | Increased from $232.3 to do more work, then increased from $242.3 to do still more. | 109982 | 12098.02 | 122080.02
ONG, NNA, CESU | 05-FG-40-2316 | 125 | OR | BC | BC | Chart | Middle Yampa River smallmouth bass and pike translocation | 215980 | 215980 |  |  |  |  | LFL, Hawkins. | Added $22.07K due to math error (originally $193,915).
ONG, NNA | 07-AA-40-2651 | 126 | OR | BC | BC | Chart | Colorado River smallmouth bass removal | 163185.54 | 163185.54 |  |  |  |  | FWS, Burdick, McAda | Removal will continue into FY 07, and synthesis report included, so total cost increased from Program Guidance $76K. FY 07: Increased from 4 to 7 passes, budget increased from $95.1K. | 147014 | 16171.54 | 163185.54
|  | 126b |  |  | BC | Chart | CDOW assistance | 43900 | 43900 |  |  |  |  | CDOW, Lori Martin
ONG, NNA, CESU | 05-FC-40-2319 | 140 | OR | BC | BC | Chart | Yampa fish response to nna mgmt | 45120 | 45120 |  |  |  |  | LFL, Bestgen, Hawkins. | 2/15/07: $10.5K added for SMB otolith analysis.
ONG, NNA, NR$ | 06-FG-40-2503 | 144 | OR | BC | BC | Chart | Green R. fish response to nna mgmt | 33200 | 33200 |  |  |  |  | UDWR, Trina Hedrick
ONG, NNA, $SH | 06-FG-40-2504 | C-18-19 | OR | BC | BC | Chart | Nonnative fish isotope work | 42800 | 42800 |  |  |  |  | CDOW, Pat Martinez, CSU, Brett Johnson.
|  | 150 | N | BC | BC | Chart | White sucker removal | 0 | 0 |  |  |  |  | UDWR, Trina Hedrick, FWS, Mark Fuller. | Added in FY 07 as part of other work, no $ needed.
IV. Propagation & Genetics Management
|  | 29 |  |  | BC |  | O&M Propagation Facilities
O&M | 07-AA-40-2599 | 29a | OR | BC | BC | Czapla | Grand Valley | 486052.39 |  |  | 486052.39 |  |  | FWS, Chuck McAda | Funds will be needed to fix leak problems at hatchery, but apparently not until FY 08. | 401849 | 44203.39 | 446052.39
O&M, $SH |  | 29b | OR | BC | BC | Czapla | Ouray | 479430 |  |  | 479430 |  |  | FWS, Mike Montagne | SOW requests $483.3K. FWS has committed to funding 100% of Ouray O&M. | 479430 |  | 479430
O&M |  |  | OR | BC | BC | Czapla | Ouray well-field development/repair | 5000 |  |  | 5000 |  |  | FWS, Mike Montagne
O&M | 05-FG-40-2324 | 29c | OR | BC | BC | Czapla | Wahweap | 111200 |  |  | 111200 |  |  | UDWR, Quent Bradwisch | Need funds to repair outlet structures (flood damage), est. at $31.2K. Only ~$80K needed for hatchery for total of $111 instead of $224.1K. Final totals in late August, but that's too late, so if they need more, we'll tx in FY 08. Actually only needed $92,048.29 (including the repair), so will reduce '08 request by $19,152.
O&M | 05-FG-40-2324 | 29d | OR | BC | BC | Czapla | Mumma native species hatchery | 70800 |  |  | 70800 |  |  | CDOW, Dave Schnoor, Tom Nesler | SOW requests $77.2K, but CDOW has funds available from BOR FY 05 and 06 obligations that are still unbilled.
0 |  | C-7 |  |  | BC |  | Propagation Facilities & Equipment
|  | PONDS | O | BC | BC | Czapla | Growout pond leases, etc. | 5000 |  |  | 5000 |  |  | FWS, Tom Czapla, Chuck McAda; BOR, Dave Speas. | $5K for O&M at DeBeque and Peters ponds is needed every year.
|  | PONDS | N |  | BC | Czapla | Fencing Horsethief ponds | 13000 |  |  | 13000 |  |  | FWS, Chuck McAda | Added 10/06. THIS CAME OUT OF $ BOR CARRIED OVER FROM FY 07. 3/19: Fence & labor $12-$13K, per Terry Stroh (so I reduced this from $27K and added $14K to 29e)
ONG, COMP | 06-CR-40-8133 | TAGS | O | BC | BC | Czapla | PIT tags | 100250 |  |  | 100250 |  |  | BR, Dave Speas. | Hopefully this number will be reduced (perhaps by half), but we won't know until after we make decisions about tags. Speas: 7/18: Should be about $90K of FY 06 $ left, which BOR can carry over and purchase in Oct., so probably won't need FY 07 $ for PIT tags. 2/25/07: PD ofc. put in $100K for PIT tags for use in FY 08 to reduce 08 costs. 4/2: Dave thinks they can only spend $42K for PIT tags, $10K for readers, and maybe another $15K for add'l PIT tags, if needed, for a total of $67K (have a ceiling). 5/17: $42K in PIT tags, $8,250 in readers, leaving $49,750 for something else. 7/24: Dave will order $50K more in PIT tags; should reduce FY 08 cost to $0.
V. Research, Monitoring & Data Management
ONG, CESU | 05-FC-40-2315 | 15 | O | BC | BC | Czapla | Larval Fish Lab Identification | 51200 |  |  | 51200 |  |  | LFL, Kevin Bestgen, Darrel Snyder.
ONG, GOV, NR$ |  | 16 | OR | BC | BC | Czapla | Database Management | 39900 |  |  | 39900 |  |  | FWS, Chuck McAda. |  | 39900 | 0 | 39900
ONG, CESU | 07-AA-40-2682 | 22f | OR | BC | BC | Czapla | Yampa & middle Green CPM & RBS larval survey | 108959.03 |  |  | 108959.03 |  |  | LFL, Kevin Bestgen. FWS, Dave Irving. |  | 34173 | 3759.03 | 37932.03
ONG, POP | 05-FG-40-2350 | 121a | O | BC | BC | Czapla | Survey for larval RBS in Gu & Co R's | 79400 |  |  | 79400 |  |  | FWS, Doug Osmundson, Bob Burdick, Chuck McAda. |  | 57400 | 0 | 57400
|  | 121b |  |  | BC | Czapla | Gunnison R. electrofishing survey | 35786 |  |  | 35786 |  |  | FWS, Bob Burdick, Chuck McAda | 3/15: Currently ~$21K in '07 (with $0 and no write-up in '08), but the SOW needs to be revised to add survey work at tributary entrances for spawning razorback in the spring and at river mile 32.5 in the summer for spawning C. pikeminnow. | 35786 |  | 35786
ONG, POP | 06-FG-40-2506 (UDWR), 07-AA-40-2601(FWS) 06-FC-40-2507 (LFL) | 128 | O | BC | BC | Czapla | Green R. CPM est. | 383894.78 |  |  | 383894.78 |  |  | LFL, Kevin Bestgen; UDWR, Paul Badame, Patrick Goddard; CDOW, Tom Nesler | 3/22: Includes est. of survival rates of stocked RBS (since data collected under this project). | 120398 | 13243.78 | 133641.78
ONG, POP | 06-FG-40-2515 | 129 | O | BC | BC | Czapla | HBC pop est in Deso/Grey | 105400 |  |  | 105400 |  |  | UDWR, Patrick Goddard.
ONG, POP | 07-AA-40-2665 | 131 | O | BC | BC | Czapla | HBC in Black Rocks | 44289 |  |  | 44289 |  |  | FWS, Chuck McAda, Bob Burdick | SOW requests $20.8K, but some of this may be for FY 08 work. | 39900 | 4389 | 44289
ONG, POP | 05-FG-40-2322 | 132 | O | BC | BC | Czapla | HBC in Westwater | 44300 |  |  | 44300 |  |  | UDWR, Paul Badame, Patrick Goddard. | Leave funds in, but BC to discuss whether this work begins in 07 or 08 as part of population estimate workshop summary review.
ONG, POP |  | 138 | OR | BC | BC | Czapla | Green R. YOY CPM monitoring | 58072 |  |  | 58072 |  |  | UDWR, Patrick Goddard, LFL, Kevin Bestgen
ONG | 05-FC-40-2428 (LFL) 06-CR-40-8133 (SWCA) | 145 | N | BC | BC | Czapla | Pop est data integration (research framework) | 29500 |  |  | 29500 |  |  | FWS, Tom Czapla. SWCA, Valdez. LFL, Bestgen. | SOW requested only $29.5K ($60K had been anticipated).
NR$ |  | 147 | N | BC | BC | Czapla | Standardize electrofishing boats | [6 empty] | CDOW, Pat Martinez, Larry Kolz (contract) | S7 funds provided in FY 06
0 |  | 149 | N | BC | BC | Czapla | Cyprinid computer key | 0 | [5 empty] | LFL, Kevin Bestgen, Darrel Snyder | Obligated 07 costs in FY 06. There will be '08 & '09 costs.
VI. Information, Education & Public Involvement
ONG, PGM, GOV, $SH, FWS competes | 07-AA-40-2666 | 12 | O | I&E | I&E | Felker | General Information and Education | 61388.33 | 31388.33 |  |  |  | 30000 | FWS, Debbie Felker. | Reduced from est. of $50 K 3/06. 11/06: added $12K for $ that couldn't be spent in FY 06 and was de-obligated. An additional $7.5K from SJRIP still needed (never obligated in FY 06). 5/17: SJRIP will contribute $30K in FY 07 to make up for FY 06. Speas 6/21: UCRIP needs to cover the 11% overhead, so breakdown is $30K SJRIP, 30,388 UCRIP. | 24403 | 2684.33 | 30388.33
CAP |  | 12B | O | I&E | I&E | Felker | Grand Valley projects | 32000 |  | 32000 |  |  |  | BR, Justyn Hock.
ONG, GOV, PGM, $SH |  | 12C | P | I&E, WAC | I&E, WAC | Smith/Mohrman | Coord. Resv. Operations | 12000 |  |  | 0 |  | 12000 | BR, Kara Lamb, CDOW, Randy Seaholm | Colorado in-kind funds.
ONG, PGM, FWS competes | 07-AA-40-2652 | 12H | O | I&E | I&E | Felker | Interpretive signs and exhibits | 22200 | 22200 |  |  |  |  | FWS, Debbie Felker. | See #12. | 20000 | 2200 | 22200
ONG, PGM, GOV, FWS competes | 07-AA-40-2650 | 12L | OR | I&E | I&E | Felker | Nonnative fish control public involvement | 5550 | 5550 |  |  |  |  | FWS, Debbie Felker |  | 5000 | 550 | 5550
VII. Program Management
ONG, PGM, GOV, $SH | 05-FG-40-2321 | 1 | O | MC | MC | Kantola | Utah Program Management | 154000 | 154000 |  |  |  |  | UDWR, Krissy Wilson, Trina Hedrick.
ONG, PGM, GOV |  | 2 | O | MC | MC | Kantola | Reclamation Program Management | 174100 | 174100 |  |  |  |  | BR, Dave Speas.
ONG, PGM, GOV, $SH | 07-AA-40-2598 | 3 | O | MC | MC | Kantola | Service Program Management | 1142836.66 | 1142836.66 |  |  |  |  | FWS, Angela Kantola. |  | 1083106 | 59730.66 | 1142836.66
ONG, NR$ |  | 4 | O | MC | MC | Kantola | Colorado Program Management | 110000 | 110000 |  |  |  |  | CDOW, Tom Nesler. CWCB, Randy Seaholm.
ONG, NR$ |  | 5 | O | MC | MC | Kantola | Wyoming Program Management | 15300 | 15300 |  |  |  |  | WSEO, John Shields.
CAP |  | C-21 | O | MC | MC | Kantola | Capital Projects Coordination | 400000 |  | 400000 |  |  |  | BR, Bob Norman.
NR$ |  | 142 | 0 | 0 | MC | Kantola | Recovery Goals tech. asst. | 45500 |  |  |  | 45500 |  | FWS, Bob Muth, Tom Czapla. Rich Valdez. |  | 45500 | 0 | 45500