## USDA Project Plan Update

April 2004

Initiative Name:    Disaster Assistance

Lead USDA Agency: Office of the Chief Information Officer, eGovernment Office

Lead USDA Liaison: Barbara LaCour

Other USDA personnel participating in the initiative:Jeff Kerby, FSA.

| Project Milestone (including date) | USDA Actions to Achieve Milestones | Completion Date (for each action mm/dd/yyyy) | Where Today | USDA Person Leading Action | Assistance Needed to Complete Project |
| --- | --- | --- | --- | --- | --- |
| October 2003 – Deploy an integrated channel for access to Disaster Management organizations, knowledge, services and tools. Develop portal design and content Populate the Disaster.usda.gov website with content. | Identify Agency website. Maintain currency website links | 09/03 05/04 | 100% 0% Note: Some links may be outdated and in error. | Barbara LaCour & Jeff Kerby Barbara LaCour & Howard Baker | None – Actions completed during FY 2003 USDA webmasters review DisasterHelp.gov site to ensure website links are current. |
| -Identify Agency Disaster Assistance Contacts and request website content database information to populate Disasterhelp.gov database. | Compile list of Agency contacts – email & phone. | 04/30/04 | Short list created—need to verify and expand. | Barbara LaCour & Howard Baker | Need to contact agencies. |
| DHS Program Management -Re-align Program Management Office -Confirm governance structure -Complete funding model -Complete execution of MOAs -Legislative compliance & schedule -Partner interaction & performance measures |  | 10/01/04 02/27/04 02/27/04 02/27/04 02/27/04 09/30/04 08/31/04 | In progress by DHS DHS/FEMA In progress by DHS DHS/FEMA In progress by DHS DHS/FEMA In progress by DHS DHS/FEMA USDA MOU signed 3/15/04 In progress by DHS DHS/FEMA In progress by DHS DHS/FEMA | DHS Action DHS Action DHS Action DHS Action Chris Niedermayer & Barbara LaCour DHS Action DHS Action | None None None None Complete None None |
| Coordinate USDA-wide Knowledge of Disaster Management Presidential Initiative and its tools and capabilities & identify current and future USDA initiatives for inclusion. Passback Language: “USDA will coordinate all disaster and emergency management investments, including incident management or emergency management systems, through the Disaster Management eGov initiative to ensure compliance with the interoperability standards adopted by the federal government. “ Agencies in order of financial contributions: FS, NRCS, FSA, FSIS, APHIS, RD, FNS, CSREES, RMA, FAS OTHER: COOP/CAT, USDA Office of Homeland Security, DA | 1. Meet with Agencies Staffs 2. Letter to Agency Heads to est. management commitment. 3. Develop plan to advertise, identify and populate portal. 4. Create Working Groups 5. Brief agency working groups. | 1. Ongoing 2. 05/04 3. 05/04 4. 06/04 5. 06/04 | 1.a Briefed National Wildland Fire Coordination Group (NWCG)– 10/03 & 03/24/04 1.b APHIS 1.b.1 Emergency Response tracking system 04/01/04 1.b.2 DTRA & DisasterHelp.gov portal – potential duplications 1.c FSA mapping completed. 1.d FSIS joint-ownership of Food “Channel” with FDA 2. 25% 3. 25% 4. 10% 5. 10% | 1a. DHS, Appian, & Barbara LaCour 1b. DHS, Appian, & Barbara LaCour 1.b.2 DHS & Barbara Lacour 1.c Complete 1.d USDA contacted by FDA and DHS/FEMA re partnership 1.d.1 Need to identify FSIS decision-maker & representative for follow through 2. Barbara LaCour & Howard Baker 3. Barbara LaCour & Howard Baker 4. Barbara LaCour & Howard Baker 5. Barbara LaCour | 1a. The NWCG is currently assessing the technical capabilities of this initiative. The IRMTW of the NWCG will make a recommendation to the NWCG regarding use of the capabilities of both DisasterHelp.gov & DMIS. 1.b.1. Appian began work on the APHIS on its emergency response tracking system 04/05/04. The project will take approximately 3 weeks. 1.b.2 Waiting response from DHS as of 04/15/04 1.c None 1.d.1 Need to meet with FSIS. 2. None. 3. None. 4. Coordinate meeting schedules with agency groups contributing financial resources: FS, NRCS, FSA, FSIS, APHIS, RD, FNS, CSREES, RMA, FAS, i.e., USDA Homeland Security, Departmental Administration, eGovernment Working Groups Members, Program Managers, Agency CIO organizations, Webmasters. See attached contact list. 5. See No. 4 above. |
| Responder Application Tools (Basic) -SW Maintenance -Response Planning Release -Playbook Release -Scheduled development -Emerging development -NETC Support |  | 07/01/04 01/30/04 06/30/04 06/30/04 06/30/04 06/30/04 04/30/04 | In progress by DHS DHS/FEMA | DHS Action | None |
| Knowledge Management -Infrastructure (telecommunications, C&A, 508 Compliance, etc.) -Operations (network, help desk, user training, etc.) -Shared Applications -Shared Processes -Determine requirements, design, build, deploy -Continuity of Operations |  | 10/01/04 09/30/04 10/01/04 06/30/04 06/30/04 05/31/04 | In progress by DHS DHS/FEMA | DHS Action | None |
| System Interoperability Phase 1 -Level 1 Reportable Interoperability -Level 2 Presentable Interoperability |  | 06/30/04 03/31/04 06/30/04 | In progress by DHS DHS/FEMA | DHS Action | None |
| Responder Application Tools (Advanced) -Re-assess requirements -Implement design analysis -Confirm tools and scope of build -Propose development schedule -Confirm funding is available to meet schedule -Create target dates for deployment |  | 09/30/05 12/31/04 03/01/05 05/02/05 05/31/05 02/28/05 03/30/05 | In progress by DHS DHS/FEMA | DHS Action | None |
| System Interoperability Phase 2 -Level 3 Processable |  | 08/31/04 06/30/04 | In progress by DHS DHS/FEMA | DHS Action | None |
| Citizen Services -Software Operations & Maintenance -Enhancements / Combined resources of federal agencies (Base-lined as of 10/01/03) -Schedule funding partners in 30 day increments for requirements discussion based upon MOAs -Schedule interim eval. for ROI -Schedule final evaluation for program performance |  | 07/30/04 09/30/04 08/31/04 11/28/03 05/31/04 08/13/04 | In progress by DHS DHS/FEMA | DHS Action | None |

USDA  AGENCY  CONTACTS  LIST

Department of Homeland Security		Sheryl Maddox, 202-720-3631

APHIS					Mark Teachman, 301-734-8073

Jessica Fantinato, 301-436-3123

AMS						Neil Blevins, 202-720-6766

Eric Forman, 202-690-0262

ARS						Gary Rich, 301-504-1052*

Emergency Operations Center		Jim Redding, 202-720-5711

David Sloan, 202-720-2181

ERS						Paul Chen, 202-694-5100*

FSA						Jeff Kerby, 202-720-1593

Jerry Alanko, 202-690-1003

Diane Sharp, 202-720-7641

Carolyn Cooksie, 202-720-4671

Leona Dittus, NDPC, 202-720-3168

FAS						Steven Rhodes, 720-1759

FS						Mike Watts, 703-605-4648

Mike Funston, 202-205-1504

FSIS						Charlie Danner, 202-501-7642

D. W. Chen, 202-690-6418

Sandy Facinoli, 202-720-2786*

FNS						Jackie Hawkins, 512-345-213*

GIPSA					Mack Manis, 202-720-0244

NASS						Marshall Dantzler, 202-720-4557

NRCS						Carlos Henning, 202-690-2621

RD						Sherie Hinton Henry, 202-692-0200

National Wildland Fire Coordination Group

Barry Mathias, 208-947-3740

Al Borup, 208-947-3743

Allen Deitz, 208-947-3742

*eGovrnment Working Group Members

Agency CIO’s

USDA AGENCY DISASTER ASSISTANCE PROGRAMS

| Agency/Program | Web Site URL | Functional Area | Customer Category |
| --- | --- | --- | --- |
| USDA Office of Communications |
| Newsroom | http:/www.usda.gov/newsroom.html | Preparedness/Planning | Media |
| Animal & Plant Health Inspection Service (APHIS) |
| Pest Detection | http://www.aphis.usda.gov/ppq/ep/pestdetection/ | Monitoring | Citizen |
| SEPPC Weekly Notices | http://www.aphis.usda.gov/ppq/emergencyprograms | Monitoring | Citizen/Media |
| Emergency Programs Manual | http://www.aphis.usda.gov/ppq/ep/manual.pdf | Preparedness | Federal/State |
| Animal Management in Disasters | http://www.animaldisasters.com/ | Preparedness | Federal/State |
| Cooperative State Research, Education, and Extension Service (CSREES) |
| The Extension Disaster Education Network (EDEN) | http://www.agctr.lsu.edu/eden/ | Preparedness/Planning | Citizen/Business/Media |
| Food & Nutrition Service (FNS) |
| FNS Food Distribution Program (FDP) | http://www.fns.usda.gov/fdd/ | Emergency Response | Citizen |
| FNS FDP's Food Assistance in Disaster Situations | (URL is unavailable) | Emergency Response | Citizen |
| FNS Food Stamps Program (FSP) | http://www.fns.usda.gov/fsp/ | Mitigation | Citizen |
| EBT Disaster Guidelines | http://www.fns.usda.gov/fsp/MENU/ADMIN/EBT/EBT%20Disaster%20Guidelines%20-%20without%20case%20studies%20(October%202000).PDF | Preparedness | Federal/State |
| FNS FSP State Hotlines | http://www.fns.usda.gov/fsp/menu/CONTACTS/hotlines.htm | Emergency Response | Citizen |
| Forest Service (FS) |
| Fire and Aviation | http://www.fs.fed.us/fire/ | Preparedness/ Emergency Response | Federal/State |
| Farm Service Agency (FSA) |
| Emergency Conservation Program (ECP) | http://www.fsa.usda.gov/pas/disaster/ecp.htm | Preparedness | Citizen/Federal |
| Noninsured Crop Disaster Assistance Program (NAP) | http://www.fsa.usda.gov/pas/disaster/nap.htm | Emergency Response | Citizen |
| Emergency Loan Assistance (EM) | http://www.fsa.usda.gov/pas/disaster/emloan.htm | Emergency Response | Citizen |
| Emergency Haying and Grazing Assistance | http://www.fsa.usda.gov/pas/disaster/emhaygrz.htm | Emergency Response | Citizen |
| Where Can I Apply for FSA Emergency Assistance? | http://www.fsa.usda.gov/pas/disaster/wherapply.htm | Emergency Response | Citizen |
| Food Safety & Inspection Service (FSIS) |
| E. coli Testing Program Results | http://www.fsis.usda.gov/OPHS/ecoltest/ecpositives.htm | Monitoring | Business/Federal/State |
| Recall Information Center | http://www.fsis.usda.gov/oa/recalls/rec_intr.htm | Emergency Response | Citizen/Media |
| Food Net | http://www.fsis.usda.gov/OPHS/rpcong98/rpcong98.htm | Monitoring | Business/Federal/State |
| 2000 Blue Book | http://www.fsis.usda.gov/OPHS/blue2000/index.htm | Monitoring | Business/Federal/State |
| 2000 FSIS National Residue Program | http://www.fsis.usda.gov/OPHS/nrp2000/index.htm | Monitoring | Business/Federal/State |
| Progress Report on Salmonella Testing | http://www.fsis.usda.gov/OPHS/haccp/salm4year.htm | Monitoring | Citizen/Business |
| Accredited Laboratory Program | http://www.fsis.usda.gov/OPHS/accrlab/alpinfo.htm | Monitoring | Business/Federal |
| Baseline Data | http://www.fsis.usda.gov/OPHS/baseline/contents.htm | Monitoring | Business/Federal |
| Microbiology Laboratory Guidebook | http://www.fsis.usda.gov/OPHS/microlab/mlgbook.htm | Monitoring | Business/Federal |
| ADRS Data | http://www.fsis.usda.gov/OPHS/adrsdata/adrsindx.htm | Monitoring | Business/Federal |
| Natural Resources Conservations Service (NRCS) |
| Emergency Watershed Protection | http://www.nrcs.usda.gov/programs/ewp/ | Emergency Response | Citizen |
| Emergency Conservation Program | (No URL available) | Emergency Response | Citizen |
| Risk Management Agency (RMA) |
| Crop Policies | http://www.rma.usda.gov/policies/ | Preparedness | Federal |
| Federal Crop Insurance Corporation | http://www.rma.usda.gov/aboutrma/fcic/ | Preparedness | Citizen |
| Rural Utilities Service (RUS) |
| Rural Electrification Loans | http://www.usda.gov/rus/electric/loans.htm | Preparedness | Citizen |