Computing and Physics PROJECT STATUS REPORT No. 6

REPORTING PERIOD

##### Q4 2002

July-September 2002

Table of Contents

# 1.  Project Objective

# 2.  Project Manager’s Summary (John Huth, Harvard)

3.  WBS 2.1 Physics Manager’s Report (Ian Hinchliffe, LBL)

4.  WBS 2.2 U.S. ATLAS Software Manager’s Report (Torre Wenaus, BNL)

5.  WBS 2.3 U.S. ATLAS Facility Manager’s Report (B. Gibbard, R. Baker, BNL)

6.  WBS 2.3.2 Distributed IT Infrastructure (Rob Gardner, Indiana University)

## 7.  WBS 2.4 Financial Report (Chuck Butehorn, BNL)

# 1.  Project Objective

The U.S. ATLAS Project consists of the activities to design, supply, install and commission the U.S. portion of the ATLAS detector.  The detector will become part of the Large Hadron Collider (LHC) at CERN, the European Laboratory for Particle Physics.  The ATLAS detector is being designed to understand the dynamics of electroweak symmetry breaking.  The U.S. ATLAS collaboration is funded jointly by the U.S. Department of Energy and the National Science Foundation.

The fundamental unanswered problem of elementary particle physics relates to the understanding of the mechanism that generates the masses of the W and Z gauge bosons and of quarks and leptons.  To attack this problem, one requires an experiment that can produce a large rate of particle collisions of very high energy.  The LHC will collide protons against protons every 25 ns with a center-of-mass energy of 14 TeV and a design luminosity of 1034 cm-2 s-1.  It will probably require a few years after turn-on to reach the full design luminosity.

The detector will have to be capable of reconstructing the interesting final states.  It must be designed to fully utilize the high luminosity so that detailed studies of rare phenomena can be carried out.  While the primary goal of the experiment is to determine the mechanism of electroweak symmetry breaking via the detection of Higgs bosons, supersymmetric particles or structure in the WW scattering amplitude, the new energy regime will also offer the opportunity to probe for quark substructure or discover new exotic particles.  The detector must be sufficiently versatile to detect and identify the final state products of these processes.  In particular, it must be capable of reconstructing the momenta and directions of quarks (hadronic jets, tagged by their flavors where possible), electrons, muons, taus, and photons, and be sensitive to energy carried off by weakly interacting particles such as neutrinos that cannot be directly detected.  The ATLAS detector will have all of these capabilities.

The ATLAS detector is expected to operate for twenty or more years at the CERN LHC, observing collisions of protons, and recording more than 107 events per year.  The critical objectives to achieve these goals are:

- Excellent photon and electron identification capability, as well as energy and directional resolution.

- Efficient charged particle track reconstruction and good momentum resolution.

- Excellent muon identification capability and momentum resolution.

- Well-understood trigger system to go from 1 GHz raw interaction rate to ~100 Hz readout rate without loss of interesting signals.

- Hermetic calorimetry coverage to allow accurate measurement of direction and magnitude of energy flow, and excellent reconstruction of missing transverse momentum.

- Efficient tagging of b-decays and b-jets.

# 2.  Project Manager’s Summary

The major driving forces for our computing effort in this quarter were, once again,  the ATLAS Data Challenges (DC) and demonstrations for the SuperComputing 2002 meeting in Baltimore November 2002.  During this period the US effort added a new element to the ATLAS Data Challenges by using much of the existing grid middleware tools such as the iVDGL Virtual Data Toolkit(VDT) for real production.  This used facilities at the U.S. Tier 1 center at BNL as well as those of the U.S. ATLAS testbed.

Work continues on the LCG common project. POOL with substantial US ATLAS participation. We are also active in a number of RTAG’s (Requirements Technical Assessment Group).

Because of our budget constraints we continue to hold off on the expansion of the Tier 1 facility at BNL which needs ramping up to participate fully in future ATLAS Data Challenges. The ramp up of manpower for critical core software areas like database management has also been delayed

3.  WBS 2.1 Physics Manager’s Report (Ian Hinchliffe, LBNL)

This quarter saw the completion of the production for DC1 phase 1 and the preparations for Phase 2. More parameter sets were provided for the productions related to Higgs bosons to be used primarily for the study of b tagging algorithms. These can be found at

http://www-theory.lbl.gov/~ianh/dc/

STDHEP has been removed from the atlas releases, providing a simplification of the ATLAS generator codebase. Support for the minimum bias generator Phojet was established. This program is thought to have a better model for these events that that contained in the multipurpose generators such as Herwig. Good modeling of these events is important for understanding the effect of pile up at high luminosity when as many as 400 event can be overlapped in the LiAr calorimeters.

The Pythia interface was extended to allow users more control over internal parameters and the type of output provided.

A prototype GUI

interface for the setting of Monte-Carlo parameters has been

written. It could be used as the basis for a more general system for

setting user options in Athena. This will be demonstrated at the ATLAS

week (October 7) and user feedback will be solicited. It is expected

that this tool will become part of the release during the next quarter.

Integration of the ALPGEN special purpose package was completed. This

package calculates rates for W+2 bquark jets and a number of other

jets in kinematic regimes where the multipurpose generators are either

slow or unreliable.

An RTAG mandated by the CERN-LCG was set up to consider the support

that CERN-IT should provide to the experiments in the area of

Monte-Carlo event Generators. Hinchliffe was the ATLAS representative

to this which was chaired by A. De Roeck (CMS/CERN). Its report will be

presented on October 8th. The report calls for the establishment of a

repository at CERN where the Monte Carlo codes required by the

experiments will be held and the manpower to maintain it.

If established this repository will replace the "external"

area in ATLAS which is currently maintained on an ad-hoc basis by

volunteers. The experiments will be asked to help in the establishment

of at test suite that can be used for validating new releases. This

would guarantee a level of quality control that is currently

lacking. The RTAG also addressed the level of support needed from the

CLHEP team at FNAL for the HepMC interface package that was originally

written by Atlas members but has now become a common product.

4.  WBS 2.2 Software Manager’s Report (Torre Wenaus, BNL)

Software project efforts in the quarter have largely focused on infrastructure and operations development and support for the first phase of Data Challenge 1, which was underway during the period, and preparatory work for DC 1 phase 2 (reconstruction production and physics dataset processing) which begins in the next quarter. Other activities were associated with contributions the LCG project, in which US ATLAS is an important contributor to software design and development in the LCG Applications Area. A long awaited creation of a software support and quality assurance team took place in ATLAS, in which the U.S. is strongly involved, providing a better context for continuing efforts in the U.S. to improve QA particularly through automated testing.

### WBS 2.2.1.1, 2.2.1.2, 2.2.1.4 Framework, Architecture and Event Model

Work during this reporting period has been focused primarily towards the Second Phase of Data Challenge 1 and the Trigger TDR. Significant developments during this reporting period are:

o After a common integration effort with the LHCb core software team Gaudi release 11 incorporates all new features introduced by Atlas in the common code repository.

o To allow modules to declare proxies for the data objects they can provide, a new Gaudi Incident is now triggered by the event loop manager. A better engineered implementation of the same ProxyProvider concept is underway and should be completed by November.

o A new python package AthenaAsk has been introduced to address the needs of new athena users. The Athena Startup Kit provides a GUI and a command line interface to run common Atlas programs (e.g. the fast simulation AtlFast or the "Common Reconstruction Example"), and even to create new Algorithms in a new package, compile, link and run them.

o The pile-up framework has reached pre-production quality. New features like in-memory caching and re-use of events have dramatically improved the performance. There are pile-up algorithms for InnerDetector hits and for the LAr calorimeter. Performance studies using both sub-detectors and data from Zebra and/or Root have started with results expected by Jan 2003.

o  A major reengineering of StoreGate internals has been performed to address the code review findings and the expected access patterns from High Level Trigger algorithms.  A new reference-counted pointer and containers of "data pointers" have been introduced to provide better memory management. The persistable data object references API (DataLink) has also been simplified to ease the job of the developers and of the automatic code generator.

o Data Dictionary and ADL data definition language have been extended to support the DataVector<T> collection and ElementLink<T> object association class. The data model for the Atlfast fast simulation and event generators are in the process of being converted to use ADL.

o The emphasis on the event data model and detector description for the Trigger TDR continues. The ByteStream infrastructure is in place and preliminary converters exist for the inner detector, liquid argon and tile calorimeters, with that for the muon detector under active development.

o  The handling of non-event data (e.g. alignments, calibrations) requires the framework to update asynchronously data structures seen by the algorithms which will see e.g. the position of a detector element change transparently when the interval of validity of the relevant alignment data is crossed. As this position will be in general determined by the combination of several alignment constants the updating procedure is highly non-trivial. An Interval Of Validity service that steers the updating as well as the interaction with the geometry and calibration databases has been designed and is being prototyped. A fully functional service is expected to be delivered in January 2003.

o A prototype monitoring service has been developed that allows an Athena application to be instrumented with a binding to the Grid Monitoring Architecture (GMA) and in particular the NetLogger component of this. This will form part of the SC2000 demonstration in November.

### WBS 2.2.1.3 Databases and Data Management

Emerging themes in this reporting quarter include an increasing emphasis on database support for detector description, the beginning of component development for the LCG common persistence project (POOL), a growing role for MySQL, and a transition from Data Challenge 0 to Data Challenge 1.

At the request of the ATLAS detector description group, the U.S. database group delivered a relational database infrastructure for storage and retrieval of "primary numbers" parameterizing the ATLAS detector description, and the means to populate this database from data used in ATLAS Geant3 simulations. In this reporting quarter, the U.S. also delivered an Athena conversion service for access to these primary numbers, so that reconstruction and simulation are indeed relying upon the same sources, and Athena-based applications are reading by means of services that are completely consistent with those used for access to event data. The U.S. group continues to maintain this database and the Athena services to read it, and to ensure that it is appropriately updated with each software release.

Access to conditions data is becoming an increasingly high priority in ATLAS.  The U.S. group has initiated a collective effort involving the offline, TDAQ, and Technical Coordination database communities to define the scope, requirements, use cases, and priorities for ATLAS-wide storage of and access to conditions data.  A synopsis of the current offline database strategy, a bibliography, and a survey to users have been produced.  The first face-to-face meeting of this group will take place in the coming quarter.

Much of the U.S. development effort is now directed toward advancing the LHC-wide common persistence project called POOL.  ATLAS is committed to using POOL as its principal technology for building and managing its event store.  The U.S. has principal responsibility for the collections and metadata components, which are due for delivery in the coming quarter.  The U.S. group is contributing substantially to the infrastructure for ROOT persistence of non-ROOT objects, to the definition of reflection and dictionary services, and to the overall LCG persistence architecture.

Data Challenge 0 was declared officially over in this reporting quarter.  Its conclusion has allowed a reduction of database effort in support of Objectivity/DB infrastructure and services to a subsistence level, and redirection of that effort to LCG software development.  Objectivity/DB will be retired from ATLAS software releases after Release 5.0.0, so that Release 6.0.0 (January 2003) will be Objectivity-free.  Old Objectivity-based releases for the Lund physics workshop and for Data Challenge 0 will continue to be available, but no new development with Objectivity will be supported.  Support for existing Objectivity databases and servers will likely be phased out in 2003.

The U.S. group has substantial production and support responsibilities for Data Challenge 1, which is now underway, and is using this effort as a testbed for virtual data concepts developed under the aegis of the U.S. GriPhyN (Grid Physics Networks) project. Details of the substantial role of Magda in this data challenge appear in the following section.

An increasing number of components in ATLAS offline software releases rely on MySQL. MySQL deployments to date (including a principal deployment at BNL providing services throughout ATLAS) have been managed by local site database administrators, with no overall ATLAS strategy and no support for a CERN-hosted database. A U.S.-led working group was formed in this reporting quarter to propose a near-term server deployment strategy, and long-term requirements that will serve as input to an LHC-wide group on fabric management. Partly as an LCG POOL contribution and partly to ensure coherence between ATLAS and LHC-wide strategies, the U.S. ATLAS database group has volunteered to take responsibility for MySQL-related external packages in the LCG POOL project.  The ATLAS working group will report during the November ATLAS Software Week, and will host an LHC-wide discussion at a November LCG applications meeting. In related PPDG work, the U.S. group has agreed to a limited evaluation of grid certificate authorization technologies for use with MySQL servers.

The first implementation of the dataset model was completed. It includes an abstract base class Dataset which defines the dataset interface, supporting classes and a few dataset implementations. One implementation, TDatasetFileDataset, allows one of the new ATLAS ROOT event data files to be used to define a dataset. Another, EventMergeDataset, merges events in multiple datasets to form a single dataset.

Discussions were continued on integrating the dataset model with event collections envisioned in the ATLAS database architecture document. Once these are resolved, then the common product will be included in the CERN LCG. This integration is targeted for the next quarter.

The Argonne database group lost Chris Lain, who had been working half-time on ATLAS, most recently on LCG POOL event collections, due in part to shortfalls and delays in funding. The expected FY '03 budget is intended to suffice to support his replacement with another software engineer.

### WBS 2.2.1.8 Distributed Analysis

Most of the pieces needed for the first implementation of DIAL (Distributed Interactive Analysis of Large datasets) were put in place during the quarter. In addition to all the supporting components, these include a local scheduler which can be used to run jobs on the local machine.

DIAL provides a connection between an analysis framework and a data-processing application. Our first choice for the former is ROOT and we plan to integrate DIAL with ROOT in the next quarter.

The obvious data-processing application in ATLAS is Athena. ATLAS plans to move much of its data into ROOT files and so ROOT itself might be a candidate for this application. Most of the terabytes of DC1 data generated during the quarter are in zebra format so atlsim might also be a candidate. During the next quarter, we plan to choose one of these and integrate it to provide users with the DIAL-based capability to directly analyze ATLAS data from ROOT.

The next step will be to provide a distributed scheduler which makes it possible to carry out an analysis task on multiple nodes at a site. After this, the plan is to GRID-enable DIAL (or more precisely the DIAL scheduler) so that it can locate and process data over the GRID.

WBS 2.2.1.10 Distributed Data Management and Processing Software

During this period Magda was used in the testbed production for the Atlas Data Challenge 1 (DC1), and was shown to be a useful and practical tool. 'globus-url-copy' and 'globus-job-run' were integrated into magda_putfile. magda_putfile can be used to do third-party transfers, put files to BNL HPSS directly, and register files in the Magda database. 'globus-url-copy' was also used in the bulk data replication between BNL and CERN. Another trans-Atlantic transfer engine used is 'bbftp', which worked very well also. A rate of 300 GBytes/day was observed from BNL HPSS to CERN castor, and about 4 TBytes data had been copied for the Atlas DC1. The file spider worked diligently as usual. 35K DC1 files are available through Magda.

Magda servers were moved and split in this period. The database now is on 'magda.usatlas.bnl.gov', which is a dedicated MySQL server. Significant performace improvements had been reported by our principal production user Kaushik De - no more MySQL timeout error occurred to him after the transition. The main Magda web site now is http://www.atlasgrid.bnl.gov/magda/dyShowMain.pl

The command magda_getfile was developed and gridified. It does file copying economically: it figures out which file instances to retrieve, and fetches remote instances only if it is necessary. magda_putfile automatically determines which remote host to contact if the remote host is not provided as an argument and it is needed; if it is provided, use the provided host as a means to access storage site, should be hidden from users if possible.

A new attribute was added to the Magda location. The file spider checks that attribute to decide whether or not it needs to crawl a location. This was found to be very useful. In Magda, for a logical file, only one prime instance is allowed, while multiple replica instances can be distributed at different locations. If two primary instances exists for some reasons, the file spider can be disabled to scan one of the locations until problems are reported and fixed.

The interfaces for the deleting of file records have been developed both on the web and on command line. A protection of empty input from the web form was added.

Metadata proposed by the Grappa developers was saved to the Magda database, can be retrieved with file name from both the web and the command line.

The integration of Magda with GDMP was tried in Milan: 'gdmp_register_local_file' and 'gdmp_publish_catalogue' were put into magda_putfile; it seems to be working as expected. The strategy of managing files which are distributed on local disk of each individual node of a Linux farm, was discussed and will be implemented soon. A farm can be seen a special 'Magda' site, and the location associated with it will be a directory path preceded by the host name of the node. The Magda web services were implemented with perl SOAP::Lite module. They can be invoked to query the database and register files. With web services, Magda provides one more option to interact with the database. Magda commands are available by default on BNL Linux farm. Shared disk cache is supported: users could share the same instance if they need the same file. This should reduce the traffic with the mass storage.

We set up a new development machine with root privilege located outside the BNL firewall. The installation of software has been started to do the RLS test.

A poster about Magda and live demonstrations of file transferring with Magda are in preparation for SC2002 demo.

The  STAR experiment has Magda servers running and is evaluating it.

### WBS 2.2.2 Simulation and Reconstruction Software

The ATLAS detector simulation infrastructure and production was supported during Data Challenge 1 phase 1, which was underway during the period.

ATLSIM has been upgraded with new components (shared libraries) to provide extra I/O  facilities (ROOT, Objectivity) and to load the ATLAS detector geometry. The description of the ATLAS geometry is taken from the DICE package. Compared to the physics TDR, several updates have been made to reflect the design modifications since 1998:

- Beam pipe: multi-layer beam pipe design.

- Pixel detectors: symmetrical, insertable layout, more realistic digitization

- SCT: tilt angle reversed (to minimize cluster size)

- TRT: modular design of the Barrel, full readout simulation in digitization.

- Inner detector services material updated

- Realistic field in Inner Detector

- All End-Cap Calorimeters shifted by 4 cm

- ENDE: dead material, readout updated

- TILE: material and readout update

- HEND: dead material updated

- FWDC: detailed design with precise rod positions

- Muon system design corresponds to the AMDB version P.03

During the simulation phase, di-jet events produced by PYTHIA were analyzed by a filtering routine which looked for a predefined energy deposition in two neighboring towers in h-f space. Only events selected by the filter were passed to the simulations step and then written out.

### In the process of the ATLAS Data Challenge we have evaluated the virtual data approach for the production of several datasets. A virtual data catalogue database prototype was deployed for evaluation in the context of the ATLAS Data Challenges. The prototype is being used successfully for data challenge event generation and detector simulation. Production job options for physics event generation and production scripts for detector simulation were recast as parameterized transformations to be catalogued, with the resulting parameterizations represented as derivations. ATLAS DC0 and DC1 parameter settings for simulations are recorded in the virtual data catalogue database.

The production system, based on the virtual data catalogue prototype, implemented the scatter-gather data processing architecture to enable high-throughput computing. The production fault tolerance has been enhanced by the use of the independent computing agents, adoption of the pull-model for agent tasks assignment (instead of push model typically used in batch production) and by the local caching of output and input data. An interesting feature provided by this architecture is the possibility for the automatic "garbage collection" in the job planner in the following sequence: production agents pull the next derivation from the virtual data catalogue; after the data has been materialized, agents register "success" in the database; when previous invocation has not been completed within the specified timeout period, it can be invoked again.

VDC based production system using Magda for data access and Pacman for software distribution was used to produce 3,200 fully simulated jet events and about 10,000 minimum bias events in the pace of DC1.

WBS 2.2.4 Software Support and QA/QC

In an important and long awaited development, ATLAS established a software infrastructure and testing (SIT) team in this quarter responsible for central and remote software librarian duties, release management, quality assurance and testing, software compliance with coding standards, etc. The U.S. is an active contributor to this group through the U.S. ATLAS Librarian, Alex Undrus.

The ATLAS nightly build facility at CERN was monitored and improved. A new feature that monitors the build progress and reflects this information on the nightly build web page was added. With this feature, users are better notified about the status of the nightly builds.

Nightly builds of ATLAS software were restarted at BNL. These builds mirror CERN builds and normally use the same packages versions as the corresponding CERN build. As a result, the U.S. users have local access to the latest modifications of ATLAS software. The BNL nightly builds are helpful for all ATLAS software developers in quite frequent cases of CERN nightly builds failing due to technical problems.

An ongoing program of incorporating greater QA in the automated build system continued. Several Athena testing jobs were added in the nightlies with the results reflected on the nightlies web page. That includes saves and reads Generator transient event store objects in ROOT, writes and reads of digits event model information, and various tests of LAr software. These tests are currently described in the nightlies scripts. They should shortly be moved to a new package organization for tests that the SIT group is in the process of setting up with U.S. participation.

The AtlasROOT package was maintained, and the ROOT version changes were synchronized with corresponding changes in Gaudi (the event processing framework underlying ATLAS software).

New ATLAS software was promptly installed at the BNL Tier I Center, usually in one to three days after CERN installation. The BNL software support page is updated in a timely way with details and examples of usage of new Atlas Software releases.

The U.S. Atlas MySQL and web server and cvs pserver were maintained and administered and their services were actively used by the U.S. Atlas community. The U.S. Atlas MySQL server was moved to a dedicated machine, db1.usatlas.bnl.gov.

The evaluation of the SCRAM release management tool (at the request of the LCG) was finished and the memorandum that compares two release tools, SCRAM and CMT, was made available to the public. The memorandum was written with Ianna Osborne, CMS representative.

## Project Management

## The XProject project planning software developed in US ATLAS was adopted by the Applications Area of the LCG Project.

## Summary of Major Milestones and Deliverables

### WBS 2.2.1.2

- ATLAS and LHCb convergence on shared Gaudi kernel complete

- Bytestream (DAQ data format) infrastructure in place

- New ‘GeoModel’ detector description prototype implemented for muons

- Python-based shell for new users in place

- Pre-production pile-up support in Athena 1-detector prototype in place

- Prototype Athena monitoring service in place

### WBS 2.2.1.3

- NOVA geometry description conversion service prototype in place

- LCG POOL hybrid data store initial internal release

### WBS 2.2.1.10

- Third party transfers implemented in Magda

- DC1 phase 1 simulation dataset (35k files) cataloged in Magda

- Magda moved to higher performance dedicated DB server

### WBS 2.2.4

- Nightly builds started at BNL

- Several Athena tests added to nightly builds

- SCRAM/CMT evaluation report for the LCG completed

# Forthcoming Milestones and Deliverables

### WBS 2.2.1.2

- Reengineered ProxyProvider complete (Nov)

- Results from pile-up performance studies (Jan)

- ByteStream converters in place (Dec)

- Interval of validity service fully functional (Jan)

### WBS 2.2.1.3

- Delivery of LCG POOL collection service prototype (Dec)

- Retirement of Objectivity/DB from releases (Jan)

- Interval of validity database connection to Athena (Jan)

### WBS 2.2.1.10

- Production application of Magda in DC1 phase 2 (Nov)

### WBS 2.2.4

- Migration of Athena and systems tests from nightly scripts to test packages (Dec)

- Incorporation of production chain testing into standard test suite (Dec)

5.  WBS 2.3 US ATLAS Facility Manager’s Report (B. Gibbard, R. Baker, BNL)

# Introduction

During the fourth quarter of FY ’02, facility staffing was maintained at the level of 4.5 FTE on project plus an additional 0.5 FTE for ATLAS Grid support funded via PPDG.  This is the staffing level that was presented in the FY’02 plans during the review conducted in November.  During the first two months of the quarter, the facility was fully engaged in Monte Carlo production for phase 1 of ATLAS Data Challenge 1.  The facility performed extremely well, delivering nearly 7,000 CPU days and producing 3.4 TeraBytes of data.  The US Tier 1 facility out-produced all other ATLAS facilities except for the prototype Tier 0 center at CERN.

### WBS 2.3.1 Tier 1 Computing Facility at Brookhaven National Laboratory

### WBS 2.3.1.1 Hardware

During the fourth quarter of FY’02, $200k of special end-of-year capital for the purchase of hardware was received.  Based on experience with the first phase of DC1 and the expected needs of DC1 phase 2, an expansion of the disk storage system from 1.6 TB to 10 TB, and the addition of a high performance dedicated file server was initiated..  This hardware was purchased and delivered late in the fourth quarter and will be integrated into the facility during the first quarter of FY 2003.

In order to maximize the CPU resources available for DC1, the facility began a CPU resource sharing arrangement with the much larger RHIC Computing Facility (RCF) during the third quarter of FY ’02.   With this arrangement, idle US ATLAS Tier 1 CPUs are made available to designated production managers from RHIC through a special low priority batch queue.  In return, idle RCF CPUs are available for ATLAS production work.  Jobs in the low priority queues are preempted when higher priority jobs are present, so this arrangement has no negative impact on resources available to ATLAS.  During the fourth quarter, the RCF had significant idle CPU resources that were used by the ATLAS DC1 production manager.  This was a major factor in making the US Tier 1 production the largest of any prototype ATLAS Tier 1 facility worldwide.

The level of effort directed to WBS 2.3.2.1.1 during this quarter was constant at 1.6 FTE.

### WBS 2.3.1.2 Tier 1 Facility Software

During the quarter, continuing maintenance and upgrade work went into the major commercial products used in the facility including HPSS, AFS, Objectivity, LSF and Veritas.  Much of the effort for this is accounted for under WBS 2.3.1.2.  The level of effort for WBS 2.3.1.2 was at the planned 1.2 FTE during the quarter.

### WBS 2.3.1.3 Tier 1 Facility Administration and Support

Management efforts were focused on dealing with the evolving funding realities and the slippage of the LHC startup schedule into 2007.  There was also active in planning for the facility upgrades needed for the remainder of Data Challenge 1 and the upcoming Data Challenge 2.  Work has started on new funding proposals to be submitted to the NSF later this year.

The level of effort for WBS 2.3.1.3 was 1.7 FTE, which includes Tier 1 Facility management and planning, oversight of the full US ATLAS facilities effort and also Tier 1 operation and monitoring support.

## Summary of Major Milestones and Deliverables

This quarter saw completion of one milestone (US ATLAS Online Storage System Prototype). This deliverable were originally scheduled for completion in the fourth quarter of FY ’01, but the funding for the required hardware was not available until August 2001.  This completed all of the components of the facility required for Data Challenge 1 phase 1, a major project milestone.

### WBS 2.3.1.2

### US ATLAS Online Storage System Upgrade (Scheduled for completion 10/1/2001, expected completion 10/31/2002)  Hardware procured during Q4 FY ’02 will be integrated into facility in October.

# Forthcoming Milestones and Deliverables

In addition to the Online Storage System upgrade, the processor farm and tertiary storage system were scheduled for upgrade in the fourth quarter of FY ’02.  Based on reduced available funding, not all of these milestones could be achieved.  Based on experiences with the first phase of Data Challenge 1 and expected needs of the next phase DC1 and DC2, combined with the evolving data analysis environment for US physicists, the disk storage was deemed most critical.  A modest upgrade for the tertiary storage system (upgrading the existing tape drive) is also likely during the first quarter of FY ’03, but significant upgrades to the CPU and tertiary storage systems will be delayed into FY ’04 unless additional funding is made available.  The original plan was to have a 10% Processing Farm Prototype in place for Data Challenge 2 by December 2002.  Although the schedule for DC 2 is still evolving, it will almost certainly begin before FY ’04.  Although the US managed to out-produce the actual hardware resources available in phase 1 of DC1, this was achieved largely through extraordinary personal efforts (notably by P. Nevski) and borrowed resources.  The lack of sufficient CPU may be alleviated by extremely efficient utilization of existing hardware and by capitalizing on unused RCF CPUs.  Tier 2 facilities and other US institutions will also be harnessed to produce some of the data required.  The contributions from these other facilities may make up for some of the Tier 1 capacity shortfall, but the Tier 2 contributions were already included in the original plans for DC2, and the availability of unused RCF CPUs is far from certain.

6.  WBS 2.3.2 Distributed IT Infrastructure (Rob Gardner, Indiana University)

Computing for U.S. ATLAS will rely on a distributed information technology infrastructure, which includes distributed computing resources and data stores interconnected by high-speed networks.   Grid middleware systems will be deployed to utilize these resources efficiently.  The Distributed IT Infrastructure subproject, WBS 2.3.2, is organized to meet these requirements for US ATLAS.  R. Gardner is the project manager for WBS 2.3.2, and reports to R. Baker/B. Gibbard, the Facility Project Managers.  The distributed IT project planning page is:

http://www.usatlas.bnl.gov/computing/mgmt/dit/

From this page are links to WBS 2.3.2 with projections into the Grid Project Planning numbering scheme developed for US ATLAS using XProject.

### WBS 2.3.2.1, 2.3.2.2  ATLAS Requirements and Grid Architecture

Efforts to define the requirements for worldwide ATLAS computing and the

Grid Architecture required to support that computing continued, largely driven by data challenge activities both within the US and the worldwide Data Challenge 1 phase 1 which occurred during the second half of FY'02.  These exercises were instrumental in the formulation of ATLAS requirements for the second phase of DC1.  This exercise will start with a loosely

coupled worldwide Grid of computing resources and attempt to build

additional commonality, including a first implementation of an ATLAS

Virtual Organization and a single resource broker managing the entire

worldwide ATLAS Grid.  The worldwide computing model and architecture will

certainly evolve based on experience with DC 1 phase 2 and the subsequent

DC 2.

### WBS 2.3.2.3  Integration of Grid Software

2.3.2.3.1         Toolkit configuration, deployment and support

PACMAN news from Saul Youssef (Boston U.):

Continued to Develop Pacman 2 with new features necessary for ATLAS DC’s, SuperComputing 2002 demos and in anticipation of future needs.

Supervised students in using Grappa to help in software development

and testing of the testbed.  Continued development of Pacman, worked

with Alain Roy in Wisconson and CMS to re-pacmanize VDT and pacmanize

CMS.  Coordinated installation and software upgrades on the US Atlas

testbed.

WBS 2.3.2.3.2    Grid Workflow Management

2.3.2.3.2.3            Distributed Scheduling

Grappa work from D. Engh U. of Chicago:

the jul-aug quarter more significant improvements in Grappa:

1) development of a script based job submission framework allowing

interactive and automatic (eg cron based) job scheduling.

2) addition of monitoring tools allowing interactive viewing of job info

including diagnostic physics plots, metadata, logfiles and error messages.

3) development of US-EDG inter-grid compatibility

4) initial discussions and tests for a magda web service allowing

development of magda/grappa inter-functionality.

Evaluating the Capabilities of GRAPPA:

The month of August was devoted almost entirely to evaluating the current

Athena capabilities available through the GRAPPA web-portal.  Jerry Gieraltowski created a

user's guide for the existing  Athena capabilties:

http://www.hep.anl.gov/grappa/athena

This provided an easy user's guide for members of the US-ATLAS grid to

execute

Athena "atlfast" and "atlsim" jobs using the GRAPPA web-portal.  Jerry  worked

closely with Dan Engh (U of Chicago) to debug various flavors of

executing atlfast and atlsim (i.e., locally, boxed and transmitted to a

remote end for execution, or via the afs network). He also worked closely

with Pawel Nevski of BNL to debug various releases of the atlsim software

executing in the GRAPPA environment.

Inter-Grid Connectivity:

In early September, the GRAPPA web-portal was used to sucessfully submit

an Athena fast simulation (atlfast) job to a site in the US-ATLAS grid

and, in parallel, to  a site in the EDG Testbed1 Production grid. The job

generated 100 events. In the US-ATLAS Grid, the job was executed at

Boston University on a Linux, RedHat 7.2 system. In the EDG Grid, the job

was first submitted to a  I/Gatekeeper server at Argonne, routed to the

CERN Resource Broker and  subsequently  dispatched by that RB to the CERN

compute resource (lxshare0339.cern.ch) for execution. GRAPPA was able to

monitor the status of both jobs and successfully

returned all output to a destination specified by the user.

Further architectural changes were needed to allow GRAPPA to successfully

submit boxed jobs to US and EDG nodes running the Condor job scheduler.

These changes were jointly created and tested with Dan Engh (Univ. of

Chicago) and Shava Smallen (Univ of Indiana).T

An comparison of the grid functionalities of the US-ATLAS, EDG, and

NorduGrid grid networks was performed to assess the possibility of

inter-grid connectivity.  A report of my findings was presented by John

Huth at the ATLAS Software Week in late September.  The report can be

found at:

http://www.hep.anl.gov/gfg/us-edg-interconnect/jerryg-intergrid-comparison.ppt

Members of the US ATLAS grid community

have been working closely with  Flavia Donno and others from various grid projects

to define inter-grid connectivity requirements and ensure that

they are implemented in the US-ATLAS, US-CMS, and DataTAG servers.

2.3.2.3.3         Generic interfacing to Mass Stores

Magda:

During this period of time, Magda was tried out for the first time in the

testbed production for the Atlas Data Challenge 1 (DC1), and was proved to

be a useful and feasible tool. 'globus-url-copy' and 'globus-job-run' were

integrated into magda_putfile. magda_putfile can be used to do third-party

transfer, put files to BNL HPSS directly, and register files to the Magda

database. 'globus-url-copy' was also used in the bulk data replication

between BNL and CERN. Another trans-Atlantic transfer engine used is

'bbftp', which worked very well also. A rate of 300 GBytes/day was

observed from BNL HPSS to CERN castor, and about 4 TBytes data had been

copied for the Atlas DC1. The file spider worked diligently as usual. 35K

DC1 files are available through Magda. Magda servers were moved and split

in this period. The database now is on 'magda.usatlas.bnl.gov', which is a

dedicated MySQL server. Significant performance improvement had been

reported by our user Kaushik De - no more mysql timeout error occurred to

him after the transition. The main Magda web site now is

http://www.atlasgrid.bnl.gov/magda/dyShowMain.pl The command magda_getfile

was developed and gridified. It does file copying economically: it figures

out which file instances to retrieve, and fetches remote instances only if

it is necessary. magda_putfile automatically determines which remote host

to contact if the remotehost is not provided as an argument and it is

needed; if it is provided, use the provided. Host as a means to access

storage site, should be hidden from users if possible. A new attribute was

added to the Magda location. The file spider checks that attribute to

decide whether or not it needs to crawl a location. This was found to be

very useful. In Magda, for a logical file, only one prime instance is

allowed, while multiple replica instances can be distributed at different

locations. If two primary instances exists for some reasons, the file

spider can be disabled to scan one of the locations until problems are

reported and fixed. The interfaces for the deleting of file records had

been developed both on the web and on command line. A protection of empty

input from the web form was added. The metainfo proposed by the Grappa

developers was saved to the Magda database, can be retrieved with file

name from both the web and the command line. The integration of Magda with

GDMP was tried in Milan: 'gdmp_register_local_file' and

'gdmp_publish_catalogue' were put into magda_putfile; it seems working as

expected. The strategy of managing files which are distributed on local

disk of each individual node of a Linux farm, was discussed and will be

implemented soon. A farm can be seen a special 'Magda' site, and the

location associated with it will be a directory path preceded by the host

name of the node. The Magda web services were implemented with perl

SOAP::Lite module. They can be invoked to query the database and register

files. With web services, Magda provides one more option to interact with

the database. Magda commands are available by default on BNL Linux farm.

Shared disk cache is supported: users could share the same instance if

they need the same file. This should reduce the traffic with the mass

storage. We finally got a workable machine with root privilege. The

installation of software has been started to do the RLS test. A poster

about Magda and live demonstrations of file transferring with Magda are in

preparation for SC2002 demo. The star experiment has Magda servers running

and is evaluating it.

### WBS 2.3.2.3.4  Grid Monitoring

This effort is being led by Dantong Yu of Brookhaven National Laboratory.

Initial steps in organizing a monitoring effort were taken during this period. U.S. ATLAS  participates in the joint PPDG/GriPhyN effort for Grid monitoring. Use cases and requirements for a cross-experiment testbed were developed and collected.   Work now focuses on developing facilities monitors and MDS information providers.

1.  Work on PPDG/SC2002 Grid Monitoring Project.

a. Deployed US-ATLAS Map Center for SC2002 ATLAS demo. Grid Map Center has been designed to logically and graphically represent all elements, applications  and services running over grids. It polls grid entities and services (GridFtp, MDS, Gatekeeper), check their status and builds aggregated views of difference types of grid entities.

b. Modify US-ATLAS Map Center for the need of SC2002. The Web site can be found at:

http://www.atlasgrid.bnl.gov/mapcenter/

c. Testing GLUE Schema.

### WBS 2.3.2.4  Testbeds

The testbed group continues to hold weekly teleconference

coordination meetings.

A face-to-face meeting of the testbed participants occurred for one

day of the 3 day meeting "US ATLAS Grid Workshop" at LBNL July 29-31,

2002. See http://annwm.lbl.gov/henp/meet/usatlas_grid_jul02/agenda.html

for presentations. A principal focus was a review of the results of

the 1st USAtlas testbed run of Atlas Athena running in production mode

with GRATS. Also readiness of testbed for SC2002. Informal discussion of

having USAtlas Testbed participate in the ATLAS DC1 part 1.  Other days

of this meeting were devoted to coordinating grid software with ATLAS

core software and software preparation for SC 2002.

During September, 4 of the 8 sites were used to run (successfully) the

DC1 part1 production codes and contributed significantly to the overall

US effort in DC1 part 1.  Results were reported at the Atlas Software

Workshop Sept 17-20 at UK.

Significant upgrades and hardware moves will be made at PDSF and Indiana U

during Sept.

The testbed continues to host activities associated with the

R&D projects: Atlas Grid, PPDG, Griphyn, and iVDGL.

### WBS 2.3.2.5  Wide Area Network Integration

Presentation on networking at ICFA-SCIC meeting at CERN.

Discontinued network monitoring using Perl scripts.  Exploring

alternatives: Ganglia, Nagios and Network Weather Service (NWS).

Network "monitor and beacon" boxes being prototyped at Michigan to be

used to provide active "on-demand" network test results as well as

passive monitoring to develop baseline network performance metrics.

IXIA network test and monitoring equipment grants to Michigan, Oklahoma

and UTA.   Plans for WAN and LAN testing using the boxes.

HENP WG goal pages on the WWW are being developed as a resource for

network issues.

### WBS 2.3.2.7, 2.3.2.8  Prototype Tier 2 Centers

Boston University. Most of our effort during this period was in deploying the software needed for ATLAS data challenges and the upcoming Supercomputing 2002 demo. Soul Youssef is managing the work for the upcoming SC02 demos which include interoperating grid middleware on the US testbed and European DataTag sites. A large amount of effort during this period went into establishing and interoperable grid environment between US ATLAS testbed sites and European DataTag sites. We continue to delay buying new hardware until it is needed for the participation in DC2 of ATLAS scheduled for early 2003. We do make use of existing hardware of the university/s Scientific Computing and Visualization department to run ATLAS testbed production and test software development.

Indiana University.

- Installed Ganglia to monitor site.

- Updated pacman.

- Installed grappa demo using pacman.

- Got trouble ticket system installed.

- Had "all-hands" meeting with computer center personnel doing work related to

the center.

## 7. Financial Report (Chuck Butehorn, BNL)