NASA Office of Earth Science – Applications Program

___________________________________________________________________________

Aviation Weather Applications Program

Program Plan:  2003-2007

Science for Society

Accelerating the realization of economic

and societal benefits from Earth science,

information, and technology …

Contents

I.	Purpose and Scope

II.	Aviation Weather Applications Program Operating Plan for FY  2003

a.	Program Management

b.	Primary Program Elements

c.	Program Overview

1.	Missions, Models, and Decision Support Systems

2.	Roadmap

d.	Goals and Objectives

III.	Support Functions

a.	Education and Outreach

b.	Partnership Strategy

c.	Interoperability

d.	Related currently funded efforts

IV	Gantt Chart of Schedule, Milestones and Deliverables

V.	Budget Spreadsheets

Appendix I  Statements of Work for FY 2003

- UW CIMSS Core ASAP Team

- NCAR RAP Turbulence Research

- NASA LaRC  Icing Research

- 2003 Pacific THORPEX Operational Science Test Plan

e.   NCAR ATD Driftsonde System

Aviatiion Weather Applications Program

Program Plan:  2003-2007

I.	Purpose and Scope

ESE & Applications Program

The purpose of NASA’s Earth Science Enterprise (ESE) is to increase our knowledge of the Earth system, including its response to natural and human-induced changes to enable improved predictions of climate, weather, and natural hazards.  ESE and the Applications Program serve NASA and Society by expanding and accelerating the realization of societal and economic benefits from Earth science, information, and technology research and development.

The overarching goal of the Applications Program is to bridge the gap between Earth science research results and the adoption of data and prediction capabilities for reliable and sustained use in decision support.

The Enterprise works through partnerships with public, academic, and private organizations to develop innovative approaches for using Earth science information and technology.  The Applications Program enhances the availability, interoperability, and utility of Enterprise and private sector data sets, communications, computing, and modeling capabilities to serve specific national applications.

Overall, the approach is to enable the assimilation of Earth science data and model outputs to serve as inputs to decision support tools and assessments.  Developments may be specific to a national application or may be served through a cross-cutting solution.  The outcomes and impacts are manifest in enhanced decision support and the social and economic benefits gained through improved decision making, public information, and efficient and effective management.

National Applications

The specific National Applications partner with organizations, especially Federal and private-sector organizations, with appropriate information infrastructure to apply NASA data and models.  These partners own and operate Decision Support Systems for their policy, analysis and management responsibilities.

The Applications Program supports the national applications by providing the partners with opportunities to enhance their Decision Support Systems.  A challenge is to integrate copious volumes of data with computationally demanding scientific models in order to produce and package products that operational users can accommodate in their systems for analysis and decision making.  Decision Support Systems provide systematic mechanisms to handle the volumes of data, incorporate model outputs and predictions, and benchmark the value of the products.

The Enterprise Applications Program employs functional steps of Applications Research, Verification & Validation, and Benchmarking in its systematic approach to bridge the gaps between the research and operational domains.

Applications Research:  Evaluate the requirements and technical feasibility of Earth science data and models, information products, and predictions in partners’ operational decision support needs.

Verification & Validation:  Measure the performance characteristics of data, information, models, and predictions to meet requirements for the applications.

Benchmark:  Enable the adaptation and adoption of geospatial information and methods derived from Earth science results to serve decision support

The desired outcome of the national applications is for the partner organization to use the project results, such as guidelines and prototypes and procedures, as benchmarks for operational use and enhance their management and decision-making capabilities with appropriate Earth science products and tools.

The following Program Plan describes the activities for a systematic approach to evaluate, verify, benchmark, and extend the use of Earth Science knowledge, data, and technology to support our partners’ decision support tools and management responsibilities.

II.	Aviation Weather Applications Program Operating Plan - Fiscal Year 2003

a.	Program Management

Robert A. Venezia, Dr.P.H.

Program Manager for Aviation Weather Applications

NASA Headquarters

John J. Murray

Deputy Program Manager for Aviation Weather Applications

Advanced Satellite Aviation-weather Products (ASAP) Project Manager

NASA Langley Research Center

b.	Primary Program Elements

NASA Aviation Safety Program (AvSP)

Weather Accident Prevention Project (WxAP)

Aviation Weather Information Element (AWIN)

Advanced Satellite Aviation-weather Products Sub-element (ASAP)

FAA Aviation Weather Research Program (AWRP)

AWRP Convective Weather Product Development Team (PDT)

AWRP In-flight Icing PDT

AWRP Oceanic Weather PDT

AWRP Turbulence PDT

NOAA Cooperative Institute for Meteorological Satellite Studies (CIMSS)

NOAA  /University of Wisconsin (CIMSS) ASAP Support Team

National Center for Atmospheric Research (NCAR)

NCAR  Research Applications Program (RAP)

NASA Langley Research Center (LaRC)

NASA LaRC Atmospheric Sciences Competency (AtSC)

NASA LaRC AtSC Satellite Icing Research Team

NASA Glenn Research Center (GRC)

WxAP In-flight Icing Element

NASA Stennis Space Center

Earth Sciiences Applications Directorate

c.	Program Overview

The purpose of this operating plan is to chart near-term directions for the Aviation Weather Applications Program.  In this plan, Fiscal Year 2003 is best characterized as a Program-implementation year.  Emphasis will be placed on enabling research strategies outlined in the Advanced Satellite Aviation-weather Products (ASAP) Requirements Study that was conducted in Fiscal Year 2002. These strategies were developed in consonance with the common objectives of the NASA Earth Science Enterprise Aviation Weather Applications Program, the NASA Aviation Safety Program and the FAA Aviation Weather Research Program. Research objectives will be further focused in the best interests of the nation after careful consideration of an ASAP Benefits Analysis that will be completed during the first quarter of Fiscal Year 2003. This is geared to ensure the alignment of existing investments with the ESE Applications Strategy for 2002-2012, identifying and defining requirements for additional aviation safety decision support system products, and building Program capacity in certain critical areas to support current and future partnerships.  Specifically, the critical areas include: 1) maximizing infusion of satellite data sources into the National Airspace System (NAS), 2) outreach toward NAS managers and users, and 3) inter-disciplinary collaboration and training for key researchers and service providers in those partner agencies.

The overall direction of the Program for FY03 is to enable and strengthen NASA's partnerships with the aviation safety community beginning with the Advanced Satellite Aviation-weather Products (ASAP) initiative and to sustain those partnerships throughout the applications process.  As the goals for FY03 are met, the Program will be better able to perform the scientific and technical advisory functions needed to co-invest with its partners in aviation safety decision support system enhancement and operations.  Cross-disciplinary competency will enable NASA and its partners to make better use of available academic, commercial, and non-profit resources.  This will facilitate a more diverse investment strategy that includes competitive announcements of opportunity, expanding cooperative agreements, and other approaches to Program implementation.

The purpose of the near-term plan is not to build Program infrastructure, per se.  Rather, it is to equip NASA and its partners with the tools needed to manage their joint efforts more effectively.  Given a successful implementation of ASAP during FY03, the anticipated operating plan for FY04 will describe: 1) an inventory of current and targeted aviation safety decision support system investments and the partnerships supporting them, 2) technology roadmaps for the intended improvements to those systems, and 3) recommendations for the appropriate procurement mechanisms needed to implement the road-mapped activities.  As a result, the Program will become fully aligned with the Applications Strategy, and it will be better positioned to utilize all of its internal and external assets in the most cost-efficient and appropriate manner.

The ASAP initiative is currently administered under the NASA Aviation Safety Program  (AvSP), Weather Accident Prevention Project (WxAP), Aviation Weather Information (AWIN) element. It is being conducted in partnership with the NASA Code YO, the  Earth Science Enterprise Applications Division where it is designated the NASA ESE Aviation Weather Applications Program.  This program plan is maintained at NASA HQ, Code YO  for the realization and support of that program, however research management authority is maintained within the Aviation Safety Program. The objectives of ASAP are 1- to fill a critical gap in the integration of current Geostationary Operational Environmental Satellite GOES imagery and sounding data in the production of operational aviation weather products that are developed by the FAA Aviation Weather Research Program (AWRP) and 2- to bridge the gap between developing aviation weather products using current satellite imagery and sounding data to integrating the next generation of of high-resolution, hyperspectral satellite data into aviation weather product development.  ASAP will fundamentally employ data obtained by the NPOESS Airborne Sounder Test-bed (NAST) and Scanning Hyperspectral Infrared Sounder (S-HIS) instruments, the Airborne Infrared Sounder (AIRS), the Cross-track Infrared Sounder (CrIS) as well as Polar and Geostationary Orbiting Environmental Satellites (POES and GOES). The goal of these efforts is to support FAA AWRP Product Development for ground and airborne product production and to conduct applications product demonstrations including a NASA Geosynchronous Imaging Fourier Transform Spectrometer (GIFTS) AWIN demonstration in FY2007. GIFTS, a major satellite project under NASA’s New Millennium Program, has been accepted as the baseline for the next generation of atmospheric sounders to be flown by NOAA on their GOES satellites.

d.	Goals and Objectives

Goal #1:  Align Program investments with the Applications Division strategy.

Rationale

This was established as a direct partnership between the NASA ESE and the NASA Aviation Safety Program to respond to the need for the proactive infusion of ESE satellite data and expertise into the production of operational aviation weather products and services and to align this effort with the Earth Science Enterprise Applications Strategy for 2002-2012.   This partnership directly responds to evolving national aviation safety priorities identified jointly by NASA and the FAA in the development of  aviation safety objectives and the necessary project elements required to meet these objectives. These elements focus on the infusion of NASA ESE data and expertise for the enhancement of aviation weather nowcasting and forecasting products which include but are not limited to aviation weather hazards such as:

    - Convective Weather

    - Ceiling and Visibility

    - In-flight Icing

    - Clear Air and Convectively Induced Turbulence

    - Flight Level Wind

    - Volcanic Effluents

To meet this goal the following objective was met:

# Objective #1

# To align all project activities with the Applications Strategy.  This objective has been met and the implementation phase has begun. These activities have included:

1.  the establishment of goals and objectives for the identified decision support systems including a preliminary roadmap of the basic research, applied research, verification and validation, and applications demonstration activities needed to traverse the applications process toward decision support system enhancement.

2.   coordination with the NASA Aviation Safety Program and FAA Aviation Weather Research Program to establish performance measures for each element of ASAP.  The Headquarters Program Office is using  this information to establish a program baseline and to report progress on program realignment.  These measures includes such details as full information on the aviation safety partnership, decision support system requirements, i.e. aviation hazard mitigation products, and system architecture, among others.

3.  a line item proposed budget of individual project requirements and resources for FY04.

Primary Effort:

CoordinatedASAP Research by the  NASA ESE, NASA AvSP and FAA AWRP beginning with integrated data collection, laboratory research and aviation weather product enhancement efforts begun in Fiscal Year 2003

Proposed Budget for FY 2003

$1,000,000 to NASA LaRC / ASAP.

A detailed research plan and budget was submitted in consonance with NASA and FAA priorities and requirements identified in the ASAP Requirements Study of 2002. Actual budget allocations each for ASAP element and for major supporting functions have been identified. This allocation has been matched with $1,000,000 for ASAP by the NASA Aviation Safety Program. These funds leverage a $25,000,000 annual FAA AWRP budget for the purpose of infusing current NASA ESE and NOAA satellite data and future satellite data from systems developed by the NASA ESE into operational aviation weather products developed by the AWRP. The direction of the $2,000,000 NASA investment for FY2003 is as follows:

- $512, 800 to University of Wisconsin CIMSS to establish a core ASAP team of satellite data applications development experts and begin targeted research

- $525,200 to support ASAP Winter Data Collection Requirements

  - $225,200 to NCAR RAP for Driftsonde System

  - $180,000 to NASA DFRC for ER-2 Flight Services

  - $109,000 to NOAA for Gulfstream IV Flight Services

  - $11,000 to NASA LaRC for ASAP Scientists Field Support Costs

- $100,000 to support ASAP Summer Data Collection Requirements

  - $90,000 to NASA/NOAA/DOD IPO for Flight Services

  - $10,000 to NASA LaRC for ASAP Scientists Field Support Costs

- $70,000 to NCAR RAP for Hyperspectral Simulations by Turbulence PDT

- $307,000 to NASA AvSP

  - $33,800 for AvSP Program Support (AvSP, WxAP and AWIN)

  - $273,200 surcharge for NASA (Code R) Aviation Security Initiative

- $150,000 to NASA GRC and LaRC for in-flight product validation

- $100,000 to NASA LaRC AtSC Satellite Icing Team

- $235,000 to NASA LaRC for ESSPO and AtSC Program Support

III.	Support Functions (UNDER CONSTRUCTION)

a.	Education and Outreach

- Partnering Strategy

  - Federal Agency Partners

    - NASA . Aviation Safety Program, Weather Accident Prevention Project.

NASA Code R (NASA Office of Aerospace Technology)

NASA Code YO (NASA Earth Science Enterprise, Applications Division.)

    - FAA. The FAA AWRP and the FAA LaRC Field Office are key ASAP partners.

    - NOAA CIMSS . The NOAA Cooperative Institute for Meteorological Satellite Studies (CIMSS). is a key partner on the NASA GIFTS Project and provides the lead for GIFTS for data requirements and validation. The NOAA relationship with UW CIMSS spans over 25 years. The NWS Aviation Forecast Services Branch and NWS OS&T AWIN representatives are members of the ASAP advisory board.

    - NOAA NCEP. The National Center for Environmental Prediction affiliates with ASAP through its WSRP – Winter Storm Research Program. Much of ASAP’s THORPEX data collection effort is leveraged through the WSRP.

  - Academic Research Partners

    - University of Wisconsin/NOAA CIMSS. CIMSS is NOAA’s primary research lab for the production of geostationary weather satellite data applications. The University of Wisconsin, Space Science Engineering Center, where CIMSS is located, is a prime contractor on the NASA GIFTS Project.

    - NCAR. The National Center for Atmospheric Research is the FAA AWRP’s most significant research partner.

    - NOAA FSL. The NOAA Forecast Systems Lab in Boulder, CO is a major FAA AWRP research partner.

    - MIT Lincoln Labs.  MIT Linclon Labs is a major FAA AWRP research partner. Incidentially, MIT LL is also a major collaborator in the NAST-M (NPOESS Atmospheric Sounder Test-bed) project which provides airborne applications and validation data for the

c.	Interoperability

d.	Related currently funded efforts

IV	Gantt Chart of Schedule, Milestones and Deliverables

a.  An ASAP Gantt Chart is currently under construction. Figure 1 delineates the project timeline through FY2007.

Figure 1. ASAP Elements and Timeline

b.  Major Milestones and Deliverables.

1.3.1 FY02 Milestones.

IHOP Field Experiment Participation (Convective Initiation Data Collection)

CRYSTAL-FACE Field Experiment Participation (Water Vapor Data Collection)

ASAP Study Report Completed July 31, 2002

ASAP Benefits Analysis (January 31, 2003 delivery date)

THORPEX Field Experiment Planning Meeting (September 17, 2002)

1.3.2 FY03 Milestones.

ASAP papers presented at AIAA meeting in Reno, NV on Jan 7, 2003.

ASAP Benefits Analysis Delivered January 31, 2003.

UW ASAP Research (See Appendix 1).

NCAR ASAP Research (See Appendix 1)

LaRC ASAP Research (See Appendix 1)

THORPEX Pacific data collection (Feb 18 – Mar 12, 2003).

ER-2 Deliverables – Flight Hours for NAST-I, M, S-HIS, ; In Situ O3

NOAA G-IV Flight Hours and Dropsonde Services

NCAR Driftsonde Systems (2) with Dropsonde Services

THORPEX Atlantic data collection (September and October 2003)

1.3.3 FY04 Anticipated Milestones.

Icing Product Research – ICE PDT (NCAR RAP) and LaRC Icing Team.

Convective Product Research - UW CIMSS and FAA AWRP CVN PDT.

Turbulence Simulation - FAA AWRP TURB PDT at NCAR RAP.

1.3.4 FY05 Anticipated Milestones.

Icing Product Status

Convective Product Status

Turbulence Simulation Status

Peer Reviewed Journal Articles

1.3.5 FY06 Anticipated Milestones.

Icing Product Status

Convective Product Status

Turbulence Simulation Status

Peer Reviewed Journal Articles

1.3.6 FY07 Anticipated Milestones.

Icing Product Status

Convective Product Status

Turbulence Simulation Status

Peer Reviewed Journal Articles

GIFTS AWIN Demonstration

- Budget Spreadsheets

| 2004 | ASAP $K |
| --- | --- |
| Total UW Core ASAP Team | $552.8 |
| Collaborative AWRP research | $420.0 |
| LaRC/GRC/NCAR Icing Research | $100.0 |
| Field Testing | $300.0 |
| Service Pool Charges (Code YO $) | $220.0 |
| AvSP Overhead | $400.0 |
| Total | $1992.8 |
| Core ASAP Team |  |
| UW Research | $283.5 |
| UW NCAR Detail | $100.0 |
| Travel | $13.0 |
| UW Load | $156.3 |
| Subtotal | $552.8 |
| Collaborative AWRP Research |  |
| AWRP Convective wx research | $140.0 |
| AWRP Icing wx research | $140.0 |
| AWRP Turbulence wx research | $140.0 |
| Subtotal | $420.0 |

| 2005 | ASAP $K |
| --- | --- |
| Total UW Core ASAP Team | $569.6 |
| Collaborative AWRP research | $420.0 |
| LaRC/GRC/NCAR Icing Research | $100.0 |
| Field Testing | $300.0 |
| Service Pool Charges (Code YO $) | $220.0 |
| AvSP Overhead | $400.0 |
| Total | $2009.6 |
| 2006 | ASAP $K |
| Total UW Core ASAP Team | $587.1 |
| Collaborative AWRP research | $420.0 |
| LaRC/GRC/NCAR Icing Research | $100.0 |
| Field Testing | $300.0 |
| Service Pool Charges (Code YO $) | $220.0 |
| AvSP Overhead | $400.0 |
| Total | $2027.1 |
| 2007 | ASAP $K |
| Total UW Core ASAP Team | $604.6 |
| Collaborative AWRP research | $420.0 |
| LaRC/GRC/NCAR Icing Research | $100.0 |
| Field Testing | $300.0 |
| Service Pool Charges (Code YO $) | $220.0 |
| AvSP Overhead | $400.0 |
| Total | $2044.6 |

## Appendix 1

###### 1A   University of Wisconsin(Madison, Cooperative Institute for Meteorological Satellite Studies (UW(CIMSS) participation in the Advanced Satellite Aviation-weather Products (ASAP) Project for Fiscal Year 2003

The following is a list of the tasks and goals (and accompanying level of man-hour effort) for fiscal year 2003 (FY03) through fiscal year 2005 (FY05) for “Phase I” activities within the ASAP initiative at UW–CIMSS. The activities listed below are primarily focused on FY03 (the first funding year of ASAP). The work outlined below will be done in collaboration and coordination with the National Center for Atmospheric Research (NCAR) Research Applications Program (RAP) as outlined in the ASAP Study Report (UW–CIMSS/NCAR/NASA Langley Research Center 2002).

The following three elements will initiate immediately within Year 1 as they are key to all subsequent ASAP activities:

- Assemble “core” ASAP team at UW–CIMSS, which involves identifying the long-term UW–CIMSS scientists who will motivate the ASAP agenda.

- Establish, through a dedicated UW–CIMSS employee, a UW–CIMSS presence at NCAR to facilitate the transfer of meteorological satellite technology, as well as to educate the users of these satellite technologies.

- Begin to infuse proven scientific methods of processing satellite information toward improving the diagnosis and forecasting of aviation hazards, in particular, atmospheric convection, turbulence, in-flight icing, weather over the oceans, and those caused by suspended volcanic ash clouds.

The activities listed below detail the three elements above.

1) Establish points-of-contact (POCs) at UW–CIMSS that will directly interact with one or more Aviation Weather Research Program (AWRP) Product Development Teams (PDTs) at NCAR. Each UW–CIMSS POC will develop collaboration with AWRP PDT leaders to facilitate the necessary PDT-specific and relevant satellite technology transfer. The UW–CIMSS POC will guide the research at UW through continuous feedback with PDT leads. Communications in the form of teleconferencing and travel to NCAR will occur as necessary. Once established, the POC will facilitate research as needed by the PDTs through all of Phase I of ASAP.

2) Identify the scientist who will become the UW–CIMSS liaison at NCAR, and prepare this person in the scientific methods for using meteorological satellite information addressing aviation hazards. CIMSS will immediately begin time-sharing this person with NCAR during FY03, eventually working to make this UW–CIMSS employee a long-term visiting scientist at NCAR. This personnel transfer will begin during FY03, and evolve to a mostly NCAR-based employee by early in FY04 of ASAP.

3) Turbulence: Important work in this area to begin in FY03 will be to assist the Turbulence PDT in evaluating the fundamental scales of turbulence as determined from numerical simulation. Since clear air turbulence (CAT) is relatively poorly understood, UW–CIMSS will work with this PDT to isolate the signatures in satellite imagery that correspond with aircraft-observed CAT. It is anticipated that some level of automated pattern detection algorithm development for CAT in satellite imagery will be developed during FY03, but will become mature in FY04 and FY05. Research will also be performed in the area of including satellite cloud-motion winds in algorithms that detect turbulence, as well as evaluate how profiling remote sensing systems can be used to evaluate low-level (below 5 km) CAT. Work will also begin in monitoring the relationship between satellite-derived ozone and abnormal folds in the tropopause. For high-flying commercial aircraft, this has implications for moderate to severe CAT. We expect this work to consume approximately 2 UW–CIMSS researchers 50% of the time during FY03.

4) In-Flight Icing: Work on the evaluation of supercooled clouds will begin immediately in FY03 as MODIS imagery is employed as twice-daily analyses of cloud microphysical patterns or thermodynamic phase (e.g., liquid cloud drops versus ice crystals) across regions. MODIS data will be particularly helpful during winter months when large stratus cloud sheets, covering large geographical regions, are evaluated for their potential to create significant icing hazards for aircraft flying through them. Work will also proceed on using GOES data for similar purposes, namely to assess cloud microphysical patterns; this research follows upon ongoing work at NASA Langley. We expect this work to consume approximately 2 UW–CIMSS researchers 50-75% of the time during FY03.

5) Atmospheric Convection: During year 1 of ASAP we will continue development of a number of parameters for evaluating convective initiation using geostationary satellite data. This development will continue from past work with pattern recognition schemes to recognize the location of small, growing cumulus clouds in satellite imagery. Beyond this, work will continue on the identification of cumulus cloud lines, the relationships between cumulus cloud lines and existing frontal/low-level outflow boundaries, the longevity and growth rates of cumulus clouds, and cloud deepening rates. We will also develop procedures to assess cloud-top glaciation as an important precursor to convection first producing precipitation. Over oceans, our methods will seek to identify areas of convection-dominated weather and employ the above techniques. In addition, ASAP will begin preparing PDT nowcasting systems to use derived product imagery (DPI) of atmospheric stability. These include convective available potential energy (CAPE), lifted index (LI) and convective inhibition (CIN), as currently produced in realtime at UW–CIMSS. All of the research listed above will be transferred into the nowcasting systems run at NCAR by directly employing proven methods at UW–CIMSS into their processing routines. We expect this work to consume approximately 3 UW–CIMSS researchers 50-75% of the time during FY03.

6) Oceanic Weather: The above methods for evaluating turbulence, in-flight icing and convection will be employed over large oceanic regions by processing geostationary data from GOES, METEOSAT and GMS. In particular, emphasis will be placed on more accurately locating hazards surrounding the intertropical convergence zone (ITCZ) and other semi-permanent regions of strong oceanic thunderstorm activity. ASAP will immediately begin incorporating satellite-derived winds into PDT algorithms where they prove useful for diagnosing oceanic weather hazards (e.g., CAT), as well as for identifying jet stream locations for flight route planning purposes. ASAP will be able to immediately employ satellite-derived information like cloud top heights, cloud depths and cloud layer information into systems that diagnose clouds over data-void oceanic regions. We expect this work to consume approximately 2 UW–CIMSS researchers 50% of the time during FY03.

7) Volcanic Ash Hazards: Due to the significant hazard that suspended volcanic ash presents to high-flying aircraft, work will immediately commence on procedures to analyze volcanic ash plumes in an automated sense using MODIS data. This involves developing a system that automatically collects the appropriate MODIS imagery to continuously monitor the vertical and spatial extent and qualities of ash plumes. The existing analysis techniques at UW–CIMSS for processing 32-channel MODIS imagery will be tested and employed within the existing volcanic ash-detection schemes at NCAR. We will seek to exploit the direct broadcast capabilities of MODIS toward developing a semi-continuous monitoring of active volcanoes across large portions of the globe (e.g., across the Pacific rim). The AWRP PDTs will work with the Volcanic Ash Advisory Centers (VAAC) to use these MODIS imagery processing in conjunction with information from these Centers. We expect this work to consume approximately 1-2 UW–CIMSS researchers 50% of the time during FY03.

8) The ASAP FY03 budget will directly support the above UW–CIMSS(NCAR liaison, the development of the core UW–CIMSS POCs and UW–CIMSS scientists, the time to perform the scientific research, and the necessary communications and scientific interactions between these two institutions. We will communicate by way of teleconferencing, internet meetings, travel between NCAR and UW–CIMSS, as well as through joint-institutional travel to scientific conferences.

1B  National Center for Atmospheric Research RAP participation in the Advanced Satellite Aviation-weather Products (ASAP) Project for Fiscal Year 2003: Exploratory investigations of turbulence incidents

This task addresses Section 5.3 of the NASA ASAP Study Report (2002) which involves performing high-resolution numerical simulations of turbulence encounters to reconstruct both the isolated regions of turbulence and the three-dimensional environment associated with the turbulence.  The goal of this task is to provide high-resolution datasets for satellite imagery sensitivity studies, and to better understand through the simulations the linkage between large- scale features (that may be observed in satellite imagery) and the smaller scale turbulence (which generally will not be observable).  These simulations will use the nonhydrostatic, terrain-following, three-dimensional multi-nested cloud model developed at NCAR by Terry Clark and Bill Hall (e.g, Clark, 1977, Clark and Hall, 1991, Clark, 1979).  This model has been successfully used in simulations of thunderstorm clouds, downslope windstorms, and a variety of other applications over the years.  Recent applications of particular relevance to this proposal are high-resolution simulations of a) an extreme clear-air turbulence encounter (Clark et al, 2000) and b) an above-cloud severe turbulence encounter (Lane, et al, 2002).

Using the Clark-Hall model the following tasks will be performed:

- Format as necessary the previously generated high resolution gridded data sets from the simulations mentioned above (Clark et al, 2000 and Lane, et al, 2002).  The first case contained a series of horizontal vortex tubes (HVTs) of diameter about 14 km and length about 200 km (also observed in a high resolution DMSP image) causing very large horizontal shears that were responsible for the severity of the encounter.  It may be possible that current or future satellite (GIFTS) imagery techniques could have been able to detect the presence of these HVTs.  The second case contained convectively-induced gravity waves which lead to strong shears and wave breaking above the cloud top, which may also be observable in satellite imagery.

- Perform a very high resolution (roughly 100m horizontally and vertically) of a near cloud turbulence encounter.  The ideal case would be one that contains interesting dynamics and has accurate cloud location information and precise positional and turbulence magnitude data from the aircraft’s digital flight data recorder.  The case to be simulated will be researched and possibilities discussed with major airlines.  We already have three such cases from two of the major airlines, one of which was over the S. Pacific Ocean just north of New Zealand.  This might be a particularly interesting case since satellite imagery would be the only way the conditions conducive to turbulence could have been observed.

- Perform a systematic study of the effects of resolution on the satellite imagery.  This would be done by sequentially degrading (sampling and smoothing to ensure relevant dynamics are preserved) the high resolution grids to a series of lower resolution grids.  Each set of grids could then be used in satellite imagery simulations to be performed by UW CIMSS personnel, to determine minimum resolution requirements to observe turbulence events.

The deliverables associated with this work would be:

- A total of three datasets of various resolutions resulting from the simulations listed above.  Each dataset would contain gridded data of density, pressure, temperature and water content (in all three phases) and other variables as required to be used as input to satellite imagery simulations at UW CIMSS.  The first two datasets from the previously generated simulations will be delivered to NASA and interested parties 3 months after contract award.  The third dataset containing output from the proposed new simulation in task 2 above would be delivered in Sept. 2003.

- A report or technical paper describing the results of the simulation listed in task 2 above.  The report will detail the parameters of the simulation and an assessment of the physical causes of the severe turbulence.  This will be delivered to NASA in Sept. 2003.

###### 1C  NASA Langley Research Center, Atmospheric Science Competency, Radiation and Aerosols Branch participation in the Advanced Satellite Aviation-weather Products (ASAP) Project for Fiscal Year 2003

Icing Detection from GOES Over the Continental USA

Objective

Develop a near-real time methodology to determine areas with super-cooled cloudiness over the continental USA (CONUS) for application to detection of aircraft icing conditions from high temporal resolution Geostationary Operational Environmental Satellite (GOES) imager data.

Tasks

1. Expand domain of current Visible-infrared-solar infrared- split window technique (VISST) to CONUS from current limited domains over Florida and south central USA.

a. Develop clear-sky albedo maps & updating system for 10’ domain over CONUS

b. Develop and test ingest and interpolation system for RUC or other suitable high-resolution US numerical weather analysis product to CONUS domain

c. Develop automated ingest system for reception and navigation of data from GOES-East & GOES-West to CONUS domain

d. Implement VISST to produce pixel level cloud properties

e. Develop & test product output to identify areas with supercooled liquid water clouds

f. Develop prototype missing data procedures

g. Refine algorithm and output

2. Validate supercooled cloud retrievals and relate to icing conditions

a. Compare with icing flights at NASA Glenn Research Center

b. Participate in THORPEX and compare data with retrievals when available

c. Compare characteristics of derived cloud properties with PIREPS icing reports

During this year, we expect to accomplish Tasks 1a - 1e to provide a prototype algorithm and to perform the initial validations. The remaining tasks (1f-1g) will be performed if time warrants. This effort involves the ingesting and management of a huge data volume that will require a considerable computing system. We had expected to have available a large SGI processing system (Samantha with 64 processors) that was formerly used by CERES. However, delays in upgrading the CERES computers have delayed our accessibility to Samantha. Thus, logistics in running the large datasets will need to be developed to complete the prototype processing system. The current estimate for access to Samantha is June 2003.

1D  THORPEX data collection in support of the Advanced Satellite Aviation-weather Products (ASAP) Project for Fiscal Year 2003.

See 2003 THORPEX Pacific Operational Science Test Plan at http://etc.

1E  National Center for Atmospheric Research ATD Driftsonde System in support of the Advanced Satellite Aviation-weather Products (ASAP) Project for Fiscal Year 2003.

See 2003 THORPEX Pacific Operational Science Test Plan at http://etc.