Central Subway

San Francisco, California

(November 2005)

The San Francisco Municipal Railway (Muni) and the San Francisco County Transportation Authority (SFCTA) are planning the Central Subway project, a 1.5-mile extension of the Third Street light rail transit (LRT) line (currently under construction) from its termini at Fourth and King Streets, north under Market Street and into Chinatown.  Three new stations would be constructed along the Central Subway alignment and four light rail vehicles would be purchased to augment the existing fleet.  The current Third Street LRT project extends 5.4 miles south from Fourth and King Streets along Third Street and Mission Bay Boulevard to the Bayshore Caltrain Station in Visitacion Valley.  Taken together, the Third Street LRT, scheduled to open in December 2005, and the Central Subway project would provide a continuous 6.9-mile light rail system serving the heavily transit-dependent communities of Bayshore and Chinatown.

The Financial District, Union Square, and Chinatown have a very high level of existing transit service.  Bus routes that serve the project corridor operate on two-minute headways during peak hours and typically carry passenger loads which are at or above capacity.  Currently, commuter rail passengers from the south must board these crowded buses or walk over a mile from the CalTrain Station to reach the San Francisco central business district (CBD).  The Central Subway project would provide high-capacity rail service, with 2.5-minute peak headways, to an area of San Francisco that has demand for transit which exceeds the extensive existing bus service.  Additionally, implementation of the Central Subway project would restore a continuous transportation link from the communities of Visitacion Valley, Bayshore, and South of Market area (SOMA) to Union Square and Chinatown that was lost when the Embarcadero Freeway was destroyed by the Loma Preita earthquake in 1989.   This restored connection is anticipated to improve transit service between these areas, accommodate redevelopment of SOMA, and serve large crowds attending events at the Moscone Center and SBC Park (home of the San Francisco Giants).

| Summary Description |
| --- |
| Proposed Project: | Light Rail Transit |
|  | 1.5 Miles 3 Stations |
| Total Capital Cost ($YOE): | $1,412.5 Million |
| Section 5309 New Starts Share ($YOE): | $762.2 Million (54%) |
| Annual Forecast Year Operating Cost: | $24.6 Million |
| Ridership Forecast (2030): | 45,900 Average Weekday Boardings |
|  | 20,800 Daily New Riders |
| FY 2007 Finance Rating: | Medium |
| FY 2007 Project Justification Rating: | Medium-High |
| FY 2007 Overall Project Rating: | Medium |

Division H of the Consolidated Appropriations Act, 2005, includes language directing FTA to permit Muni to use local funding expended for the construction of the Third Street LRT project as match for the Central Subway.  This action reduces the overall New Starts share from 54 percent for the Central Subway project alone to less than 38 percent of the cost of the combined projects.

Project Development History and Current Status

In October 1996, FTA Muni began preparation of a Draft Environmental Impact Statement (EIS)/Draft Environmental Impact Report for the Third Street/Central Subway light rail line.  Because of their phased implementation schedule, the two segments are considered separate projects.   Muni is currently constructing the Third Street light rail line using local, State, and non-New Starts Federal funding.  FTA approved the Central Subway project to advance into preliminary engineering in July of 2002.  While the Central Subway alignment has recently been revised, requiring supplemental environmental work, ongoing consideration of alternative alignments is expected to delay further advancement of the project.

Significant Changes Since FY 2006 Evaluation (November 2004)

The alignment of the Central Subway project has been changed to use a more direct configuration under 4th Street, and the number of stations has been reduced from five to three.  Because of the revised alignment, an increased level of engineering, and extension of the project implementation schedule, the project capital cost has increased from $994.4 million.  Additionally, Muni has updated its travel forecasts for the project to reflect a 2030 design year, and the systemwide operations and maintenance cost estimate used in calculating project cost effectiveness has been corrected.

Project Justification Rating: Medium-High

The project is rated Medium-High based on a Medium-Low rating for cost effectiveness and a High rating for transit-supportive land use.

Cost Effectiveness Rating: Medium-Low

The Medium-Low cost effectiveness rating reflects the level of travel-time benefits (11,300 hours each weekday) relative to the project’s annualized costs.  Given the uncertainty of the project scope, this estimate of project cost effectiveness carries some risk.

| Cost Effectiveness |
| --- |
| Cost per Hour of Transportation System User Benefit Incremental Cost per Incremental Trip | New Start vs. Baseline $23.05* $11.28 |

* Indicates that measure is a component of Cost Effectiveness rating.

The Central Subway provides a new direct transit link between the San Francisco CBD and southeastern San Francisco, and provides an improved connection between these areas and CalTrain and other commuter services from the region’s South Bay area.  Without the Central Subway, commuters from Mission Bay, Bayview, and the South Bay destined for Chinatown and Union Square must travel along the circuitous Embarcadero alignment to reach Market Street on the far eastern end of the CBD, or transfer to local bus service at King Street.  The proposed project provides a more direct connection to downtown and eliminates transfers for riders originating within the City; fully one-third of work trip benefits are attributable to this market.  The project also generates a significant level of travel time benefits for reverse commute trips to industrial areas in the Third Street corridor.  Approximately 85 percent of forecast benefits are attributable to San Francisco residents; the remainder of benefits accrue to residents from other jurisdictions in the region taking advantage of improved LRT connections to CalTrain and BART.  Over 40 percent of benefits accrue to low-income households.

MUNI has revised the capital cost estimate to reflect increased finance costs, a revised construction schedule, added contingencies, a higher inflation rate, and a more comprehensive construction cost estimate.  The revised cost estimate is considered reasonable and reliable for this stage of project development, although FTA notes that the cost contingency is still considered marginal for an extensive tunnel investment.

Transit-Supportive Land Use Rating: High

The High land use rating is based upon the High ratings assigned to existing land use and performance of land use policies, and the Medium-High rating for transit-supportive land use plans and policies.

Existing Land Use: High

- Population density is approximately 35,300 people per square mile in the corridor, and total employment in project station areas is approximately 217,600 jobs.

- The San Francisco CBD is the densest and most transit accessible downtown on the west coast.  Union Square is the primary retail district in the city with dense pedestrian and transit-oriented development.  Chinatown has extremely dense concentrations of residential units, retail, and some office and small-scale industrial uses.

- Available parking in the corridor is generally on-street, with some off-street parking for commuters and city-owned parking garages for commuters and shoppers.  The daily cost to park in city-owned lots in the corridor is high, ranging from $20 to $30 per day.

Transit-Supportive Plans and Policies: Medium-High

- While the city and entire Bay Area have a number of physical constraints to growth such as topographical limitations, it does not have a unified or enforceable growth management policy.

- San Francisco’s General Plan has long encouraged higher-density and transit-oriented development.  The city is undertaking additional planning initiatives to focus higher-intensity growth in transit corridors. The city is considering zoning changes that would require residential community-oriented retail development near transit nodes.

- The city’s zoning regulations are intended to maintain a medium to high-density profile and scale, with a mixture of land uses in many areas.  The city’s plan generally supports transit-supportive densities. There are no minimum parking requirements or off-street parking provisions in the CBD and other major employment areas.

- The City of San Francisco Redevelopment Agency employs a number of special tools to help implement land use policies contained in the city’s General Plan such as tax increment financing, special land acquisition rules, and special land assembly abilities.

- San Francisco’s existing land use pattern includes the densest development along its major transportation corridors.  The objective of the City Planning Department and directing codes and ordinances is to reinforce this pattern of development along corridors that have high transit capacity such as the Central Subway corridor.  Thus, land use planning in the Central Subway corridor is focused more on the corridor and neighborhood level than around individual stations or stops.

Performance and Impacts of Policies: High

- The existing high-density development and pedestrian accessibility in the City of San Francisco demonstrates the strength of city policies and market forces at achieving transit-oriented intensities and urban design.  The number of jobs in the San Francisco CBD has doubled since the 1970s with no increase in the volume of traffic entering the area.

- The South of Market area within the New Central Subway corridor is expected to experience strong growth over the next two decades, with high density residential, high-tech office, and a variety of retail uses continuing to fill in sites formerly occupied by industrial uses.

Other Project Justification Criteria

| Mobility Improvements Rating: High |
| --- |
| Within ½-mile radius of boarding areas: Existing Employment Projected Employment (2030) Low Income Households (% of total HH) Average Per Station: Employment Low Income Households Transportation System User Benefit Per Project Passenger Mile (Minutes) | 217,600 268,700 6,000 (18%) 72,520* 2,000* New Start vs. Baseline 3.35* |
| Environmental Benefits Rating: High |
| Criteria Pollutant (Reduction in tons) Carbon Monoxide (CO) Nitrogen Oxide (NOx) Volatile Organic Compounds (VOC) Particulate Matter (PM10) Carbon Dioxide (CO2) Criteria Pollutant Status Carbon Monoxide (CO) 8-Hour Ozone (O3) Annual Energy Savings (million British Thermal Units) | New Start vs. Baseline 1 9 3 0 429 EPA Designation Maintenance Area* Marginal Non-Attainment Area* 4,079 |
| Operating Efficiencies Rating: Medium |
| System Operating Cost per Passenger Mile (current year dollars) | Baseline $0.717* | New Start $0.734* |

* Indicates that measure is a component of rating for each criterion.

N/A indicates information was not available for this entry.

# Local Financial Commitment Rating: Medium

The Medium local financial commitment rating is based upon the Medium ratings assigned to both the capital and operating finance plans.

Section 5309 New Starts Share of Total Project Costs: 54%

Rating: Medium

Division H of the Consolidated Appropriations Act, 2005, permits Muni to use non-New Starts funds expended for the Third Street LRT project as match to the Central Subway.  While the New Starts share rating reflects the Central Subway project alone ($1,412.5 million), the legislative language lowers the New Starts share to approximately 38 percent of the total costs of the combined Third Street/Central Subway project ($2,012.5 million).

| Locally Proposed Financial Plan |
| --- |
| Source of Funds | Total Funds ($million) | Percent of Total |
| Federal: Section 5309 New Starts STIP Funds | $762.2 $92.2 | 54.0% 6.5% |
| State: Traffic Congestion Relief Plan | $14.0 | 1.0% |
| Local: Proposition B/K Sales Tax Funds Other Local Sources | $126.0 $418.1 | 8.9% 29.6% |
| Total: | $1,412.5 | 100.0% |

NOTE:  The financial plan reflected in this table has been developed by the project sponsor and does not reflect a commitment by DOT or FTA.  The sum of the figures may differ from the total as listed due to rounding.

*STIP funds are state-administered Federal flexible funds augmented by state gas tax and other revenues.  These funds are passed from the state to local transportation agencies as STIP funds, but all Federal requirements apply.

# Capital Finance Plan Rating: Medium

The capital finance plan is rated Medium, based upon the average of the ratings assigned to each of the subfactors listed below.  The commitment of capital funds subfactor was rated High; the capital condition was rated Medium-High; the completeness and capital cost estimates and planning assumptions subfactors were rated Medium-Low; and the capital funding capacity subfactor was rated Low.

#### Agency Capital Condition: Medium-High

- The average age of Muni’s bus fleet is 4.9 years, which is significantly younger than the industry average.

- Muni’s good bond ratings, which were issued in May 2004, are as follows: Moody’s Investors Service Aa3, Standard & Poor’s Corporation AA, and Fitch AA-.

#### Completeness of Capital Plan: Medium-Low

- The financial plan omits key explanatory details such as a funding source for the $418 million increase in the project’s cost, details on the financing costs, and a sensitivity analysis.

#### Commitment of Capital Funds: High

- Over 50 percent of the Non-Section 5309 New Starts funds (Muni Third Street Light Rail and New Central Subway) have been committed and budgeted.  Sources of funds include traffic congestion relief funding and proposition B and K sales tax revenues.

#### Capital Funding Capacity: Low

- The project’s financial plan does not specify how Muni intends to pay for the recent $418 million project cost increase and, therefore, does not provide for any additional funding capacity to cover additional cost increases or funding shortfalls.

#### Capital Cost Estimate and Planning Assumptions: Medium-Low

### Muni’s financial plan contains numerous inconsistencies.  Assumptions regarding project financing were lacking detail.

- There are ongoing uncertainties regarding the project’s scope at this stage of preliminary engineering.

#### Operating Finance Plan Rating: Medium

The operating finance plan is rated Medium, based upon the averaged ratings of the five subfactors listed below.  The commitment of operating funds subfactor was rated High; operating funding capacity was rated Medium-Low; and the remaining subfactors were rated Medium.

#### Agency Operating Condition: Medium

- Muni is undergoing a challenging economic environment with some recent service cuts (roughly four percent reduction in service hours).

- Muni’s current ratio of assets to liabilities as reported in its most recent audited financial statement is 1.53.

#### Completeness of Operating Plan: Medium

- The submission was complete and included a 20-year cash flow statement, more than five years of historical data, identification of key assumptions, and a moderate level of detail.  The plan did not include a sensitivity analysis.

#### Commitment of Operating Funds: High

- Over 50 percent of operating funding is committed.  The main revenue sources are fares, parking fees, General Fund contributions, and sales tax and fuel assistance revenues.

#### Operating Funding Capacity: Medium-Low

- The project’s financial plan shows projected reserve accounts and/or access to credit exceeding 12 percent of annual operating expenses.

#### Operating Cost Estimates and Planning Assumptions: Medium

- The operating plan assumes frequent fare increases that differ from history.  However, the project has only a minimal impact on overall system-wide operating costs.  Other assumptions are generally in line with historical experience

Map