6 December 2004

To:	Paul Philp, DOE Project Manager, Run IIb D-Zero Detector Project

From:	Vivian O’Dell, Project Manager, Run IIb D-Zero Detector Project

Subject:	Run IIb D-Zero Detector Project Report for October 2004

Attached is the monthly report summarizing the October 2004 activities and progress for the Fermilab RunIIb D-Zero Detector Project.

electronic cc:

M.	Abolins

J.	Appel

E.	Arroyo

L.	Bagby

E.	Barberis

A.	Bean

J.	Blazey

A.	Bross

W.	Cooper

M.	Demarteau

D.	Edmunds

T.	Erickson

H.	Evans

S.	Fuess

G.	Ginther

U.	Heintz

M.	Hildreth

R.	Hirosky

D.	Hoffer

K.	Johns

M.	Johnson

- Knapp

R.	Lipton

P.	Lukens

R.	McCarthy

J.	Monhart

H.	Montgomery

M.	Narain

A.	Nomerotski

V.	O’Dell

P.	Padley

R.	Partridge

V.	Pavlicek

TJ	Sarlina

R.	Sidwell

P.	Slattery

K.	Stanfield

RP	Smith

J.	Strait

L.	Stutte

E.	Temple

C.	Trimby

V. 	White

M.	Witherell

J.	Womersley

D.	Wood

C.	Yoshikawa

Fermi National Accelerator Laboratory

Run IIb D-Zero Detector Project

Fermilab Experiment Number E925

Progress Report No. 23

October 2004

- Project Description

The Tevatron Collider at Fermilab offers a unique capability to elucidate many of the major issues currently facing particle physics. Its high center-of-mass energy and recently upgraded luminosity offer us the capability of shedding light on the Higgs mechanism - which has the potential of offering insight into the origin of mass - and pushing the boundaries of searches for supersymmetry and other new phenomena beyond the Standard Model.  It also makes accessible improved precision measurements of the W boson and top quark properties that, by further constraining the Standard Model, provide increasingly stringent tests of its precepts.  The Tevatron offers the most cogent experimental probes of Standard Model physics, and beyond, during the coming 5+ years.

The Run IIb D-Zero Detector Project has been designed to allow the D-Zero Experiment to continue operating in the high intensity Tevatron environment for the remainder of the coming decade. The integrated exposure of the D-Zero Detector to colliding beam will result in radiation damage to the silicon detector that will compromise its efficiency. Adequate b-tagging is an essential ingredient of the Run II physics program. In order to maintain adequate b-tagging, D-Zero is adding an inner layer detector of radiation-hard silicon to enhance tracking efficiency as the Run IIa detector ages. In addition, the trigger system must be upgraded in order to provide sufficient rejection and to limit the dead time at the higher instantaneous rates that will be delivered by the Tevatron as the run progresses. The Run IIb D-Zero Detector Project provides for the additional D-Zero Layer 0 silicon detector and the upgrade of the D-Zero trigger, DAQ, and online systems in order to enable the continued efficient running of the experiment, and the acquisition of forefront physics data, for the foreseeable lifetime of the Tevatron collider program.

- Overview of Project Status

Strip testing at Stony Brook was completed for one sensor of each of the four types ordered, and all sensors met specifications. Four test modules are being readout and first results look good, with a signal/noise of ~14:1. Four Layer 0 readout chains were installed into DZero during the shutdown, and work on firmware and software is in progress. A Layer 0 carbon fiber support structure was completed at the University of Washington and shipped to Fermilab. This structure arrived intact and is expected to be mechanically and electrically accurate. As planned, University of Washington will build an additional Layer 0 structure as a backup. Most of the silicon assembly fixtures needed for the sensor-hybrid module fabrication have fabricated at Michigan State University and have been delivered.

Measurements were made of the clearances for the Layer 0 detector inside the current Run IIa silicon, and while the clearances were smaller than expectations, the difference should not be significant. Additional infrastructure work was done during October, including installing the Wiener LV Power Supplies needed for the Layer 0. The power supply installation and integration should be finished by the end of the shutdown.

For the trigger upgrade, the layout work for the ADF v2 board is now finished and different fabrication/assembly houses are being contacted to build the boards. The TAB/GAB Production Readiness Review occurred at Nevis on October 7 (see attached report), and assembly of the TAB/GAB boards will go forward. Work continued on a 5% prototype test for the BLS-ADF transition system, needed to feed signals from the calorimeter readout to the new L1 Calorimeter ADF boards. The Cal Track-Match boards have been submitted for fabrication. The preproduction DFEA boards have been tested with the new crate and crate controller at BU and all seems to be working well. A DFE subrack and power supplies were installed, cabled and inspected on the west platform in the DZero collision hall and ORC was granted. A DFEA/M board was installed on the west platform and integration with the experiment in ongoing. A new single board computer for the L2 processor project was selected and ordered. It will be evaluated in November. Scenarios for the L2STT project are still being considered and a decision will be made late November or early December. Meanwhile the Buffer Controller production at Columbia will move forward.

The trigger simulation work continues, and studies of the electron algorithm and isolation region for the L1Cal are nearing completion. The L1Cal simulation has been carefully debugged against data. The L1CTT IIb equations are now being used to generate test vectors for the verification of the firmware on the IIb boards on the platform. The AFE II prototype boards and the TripT chips have been received and are under test.

The online systems are progressing well. Most of the new server system backbones will be installed during the 2004 shutdown with the bulk of the CPU and disk purchases in 2005. We are still on target for migrating online operations to the new servers by the end of the fall shutdown.

- Project Milestone Summary (as of 31 October 2004)

The DOE baseline milestones are shown in Figure 1 as solid diamonds.  These fixed milestones are defined in the modified DOE Project Execution Plan approved in December 2003.  Shown as open diamonds on the same line, are the project’s projected dates for achieving the milestones.  Actual dates of achieving milestones are shown as solid stars.  The silicon, trigger and online milestones are shown separately with milestones sorted by current forecast date.

Table 1 shows the difference in the current forecast and last month’s forecast for achieving the DOE milestones. This table lists all the approved Level 0-1-2 DOE milestone dates along with the project’s current (and previous month’s) forecast for achieving them. The list is sorted by DOE Milestone date. Milestones with forecast dates that have changed significantly in the last month are discussed in Section VIII of this report.

Figure 1:  Run IIb D-Zero Detector Project DOE Level 2/Director’s Milestones.  Closed (open) diamonds represent baseline (current forecast) dates.  Closed stars represent completed milestones.

| L2/Director's Milestones vs Current Forecast |
| --- |
| (Sorted by L2/Director's Baseline Date) |
| Milestone Description | L2/Director's Baseline (10/04) | Last Month's Forecast (9/04) | This Month's Forecast (10/04) | L2/Director's Variance (work days) | Monthly Variance (work days) | Notes |
| WBS 1.2 Trigger |  |  |  |  |  |  |
| L1 Calorimeter Trigger TAB/GAB Prototyping Complete | 05/03/04 | 05/26/04 | 05/26/04 | 18 | 0 | Complete |
| Start Production TAB Fabrication | 02/25/05 | 10/22/04 | 10/08/04 | (90) | (10) | Complete |
| L2 Silicon Track Trigger Production and Testing Complete | 10/17/05 | 04/01/05 | 05/27/05 | (138) | 40 |  |
| L1 Trigger Cal-Trk Match Production and Testing Completed | 01/03/06 | 05/31/05 | 05/31/05 | (143) | 0 |  |
| L1 Calorimeter Trigger Production And Testing Complete | 01/05/06 | 08/03/05 | 08/17/05 | (91) | 10 |  |
| L2 Beta Trigger Production And Testing Complete | 01/05/06 | 05/23/05 | 05/23/05 | (151) | 0 |  |
| L2 Trigger Upgrade Production and Testing Complete | 01/05/06 | 05/23/05 | 05/27/05 | (147) | 4 |  |
| L1 Central Track Trigger Production And Testing Complete | 01/10/06 | 08/19/05 | 08/19/05 | (92) | 0 |  |
| L1 Trigger Upgrade Production and Testing Complete | 04/10/06 | 08/19/05 | 08/19/05 | (154) | 0 |  |
| WBS 1.3 Online/DAQ |  |  |  |  |  |  |
| Online System Production and Testing Complete | 10/07/05 | 06/17/05 | 06/17/05 | (78) | 0 |  |
| WBS 1.6 Layer 0 Silicon Detector |  |  |  |  |  |  |
| Freeze Mechanical Parameters | 01/06/04 | 12/15/03 | 12/15/03 | (9) | 0 | Complete |
| Release Sensors for Production | 05/26/04 | 02/26/04 | 02/26/04 | (63) | 0 | Complete |
| Release Hybrids for Production | 06/04/04 | 03/25/04 | 03/25/04 | (50) | 0 | Complete |
| Release Analog Cables for Production | 06/04/04 | 03/19/04 | 03/19/04 | (54) | 0 | Complete |
| All Analog Cables Delivered and Tested | 03/11/05 | 08/10/04 | 08/10/04 | (141) | 0 | Complete |
| All Sensors Delivered and Tested | 05/23/05 | 09/28/04 | 09/28/04 | (159) | 0 | Complete |
| All L0 Hybrids Delivered, Stuffed, and Tested | 08/25/05 | 01/10/05 | 01/10/05 | (160) | 0 |  |
| All Adapter Cards Delivered and Tested | 10/17/05 | 03/16/05 | 03/11/05 | (153) | (3) |  |
| Silicon L0 Module Production Complete | 11/29/05 | 02/16/05 | 02/16/05 | (198) | 0 |  |
| Layer 0 Silicon Detector Ready to Move to DAB | 05/25/06 | 07/08/05 | 07/05/05 | (217) | (3) |  |
|  |  |  |  |  | status date: | 10/31/2004 |

Table 1:  Run IIb D-Zero Detector Project DOE Level 2/Director’s Milestones vs. Current Month and Previous Month’s forecast.  Entries are sorted by DOE L2/Director’s Milestone date.  Monthly variances are also provided.

- Management Highlights – V. O’Dell

A TAB/GAB production readiness review was held October 7. The committee was comprised of I. Bertram (Trigger Board chair), D. Edmunds (ADF expert), R. Hirosky (review committee chair and Level 2 expert) and J. Steinberg (Cal Trk-Match expert). The committee agreed that the TAB/GAB boards had been extensively tested and were ready for production.

More information about the review and the review report can be found at:

http://d0server1.fnal.gov/projects/run2b/Management/Posted_Info/PRRs/RunIIb_PRRs.htm

We also scheduled a Layer 0 silicon module production PRR for November 24.

Procurement Highlights – V. O’Dell

The remaining large procurements for the project are mainly going through Universities.  The MOUs for Columbia University, Boston University and the University of Arizona are in place. The University of Virginia requisition is working its way through the system. The FY05 Boston University and University of Arizona requisitions are being held pending resolution of the Continuing Resolution. This should not present a big problem until the end of  November.

- Silicon L0 (WBS 1.6) Schedule and Budget Information – A. Bean, R. Lipton

  - Sensors (WBS 1.6.1) – M. Demarteau, R. McCarthy

In October one sensor of each type underwent full strip testing at Stony Brook.  Of 1024 strips on the 4 sensors, one strip was found to be bad due to a pinhole.  The reason for the problem was found, actually before the testing.  The sensor was scratched at Hamamatsu.  The scratch was observed on arrival at Fermilab from Hamamatsu and was also observed on arrival at Stony Brook from Fermilab.  (Most of the sensors are not scratched.)  One per cent of the strips are allowed to be bad.    Hence the sensors meet specifications.

  - Readout (WBS 1.6.2) – A. Nomerotski, R. Sidwell

Testing the hybrids at both 132ns and 396ns is required because test stand operations with the Standalone Sequencer default is normally 132ns, but operation in the experiment is at 396ns timing. Tests were made to look for dependence of signal on bandwidth(BW), leaking of charge to neighbor channels, crosstalk, and noise vs BW to optimize signal/noise. It was concluded that the charge leakage at 132ns is greater than for 396ns, for higher bandwidth settings, and a 10% charge loss occurs. S/N is optimzed for BW> 5 (this is a download parameter to the SVX 4 chips).

Four modules are being read out, and first results are being compiled of a study of noise vs spacer thickness, which is an ongoing study. Noise is excellent and corresponds to S/N of ~14:1.

In terms of installing electronics into DZero, four Layer 0 readout chains were installed, replacing 4 non-working H-disks. The chains included two modules (with sensors), and two bare hybrids, and are located between the Calorimeter and the first muon layer at eta~-0.4. Work on firmware and software was in progress at the end of the reporting period. Recabling of H-disks was begun.

The first 40 hybrids were stuffed with the wrong resistor value (this affects the gain calibration). This is fixable, with care. The hybrids are in any case useable for testing and other studies.

  - Mechanical Design and Fabrication (WBS 1.6.3) – W. Cooper

A Layer 0 carbon fiber support structure, which is expected to be dimensionally and electrically accurate, was completed by the University of Washington and shipped to Fermilab.  Thanks to careful packaging, the structure was delivered without incident.  CMM measurements of the structure are in progress.  Measurements of deflection under load will also be made.  Based upon current information, we expect that this structure will be used for layer 0 and installed at D-Zero.  The only known defect is a slight, local loss of gold plating at a few locations on one of the kapton-copper mesh ground circuits.  The circuit vendor has been contacted and will check with his plating sub-contractor.  We had planned to make two support structures so that a back-up would be available should the first structure be damaged.  While we do not anticipate that a second structure will be needed, the University of Washington will begin its fabrication.

Fabrication of silicon assembly fixtures continued at Michigan State University, with completed fixtures arriving at a regular rate.  The majority of fixtures for sensor– hybrid module fabrication have been delivered.  The design of fixtures for placing modules on the layer 0 support structure was completed.  Drawings of those fixtures will be sent to Michigan State University for fixture fabrication.  The design of fixturing to hold the support structure during sensor–hybrid module installation is progressing at a good rate.

While not directly included in the layer 0 project, measurements were made of clearances for layer 0 installation within the existing Run IIa silicon.  Measured radial installation clearance (0.86 mm) is consistent with, but slightly less than, expectation (0.91 mm).  The difference should not be significant.

  - Detector Modules and Final Detector Integration (WBS 1.6.4, 1.6.5) – L. Bagby

The Wiener LV Power Supply is now operating correctly after a visit from the vendor to correct construction errors. Four modules, one for each detector quadrant, are fully operational with a spare module available in the mainframe housing.  Interlock permits from the Glycol and VESDA safety systems are in place and operational. Integration of the power supply status into the EPICS monitoring system is underway. Documentation for Partial Operation Readiness Clearance is being finalized. Operation clearance is expected to occur before the shutdown ends.

- Trigger (WBS 1.2) Schedule and Budget Information – B. P. Padley, D. Wood

Among the main events in October were the successful Production Readiness review for the TAB and GAB boards for L1cal (Oct 7th at Nevis) and a simulation meeting to decide on the EM algorithm for L1cal (Oct 22nd at Fermilab).

The accelerator shutdown continued, and progress was made in the

collision has for L1CTT and L1cal-track systems.

  - Level 1 Calorimeter Upgrade (WBS 1.2.1) – M. Abolins, H. Evans

Layout work on the ADF v2 at MSU finished in October.  Discussion is ongoing with several PCB fabricators and assemblers to determine who is capable of producing these boards.

At Nevis, the TAB/GAB production readiness review was held on October 7.  The review committee determined that the boards are ready for production with no modifications to the prototype design required.  Since we fabricated enough boards for the full production run in the prototype phase (the incremental cost of doing this was negligible), the only remaining step is to assemble them.  An order to do this has now been submitted and the boards are currently undergoing a safety review at Fermilab.

October saw continuing work on TAB and GAB firmware at Nevis.  A first pass at a simple list of L1Cal trigger terms, output by the GAB has been implemented in the GAB's firmware.  This list replicates the existing Run IIa terms and adds a few example topological triggers.  The firmware has been simulated, but not yet tested in the actual GAB board.  This testing will be started in November.

We have also determined, through Monte Carlo and data studies, that the baseline EM trigger algorithm is not optimal.  A new algorithm with significantly better performance has been proposed and studied.  This new algorithm will be implemented in the TAB firmware during the months of November and December.

At Fermilab, work continued on the 5% prototype run of all the components of the BLS-to-ADF transition system.  In particular, tests of signal quality using different impedance matching schemes between the existing BLS cables and the transition system were made.  Additionally, a mock-up of the system's mechanical connection was also constructed.  This was used to show that cable routing in the new system should not be a problem.

  - Level 1 Calorimeter/Track Matching (WBS 1.2.2) – K. Johns

The production MTCxx cards were fabricated and will be submitted for assembly shortly.  Layout changes to the production UFB cards were completed and the cards will be sent out for fabrication in the next couple of days.  Termination of the long haul cables from the collision hall to MCH1 was completed.

  - Level 1 Track Trigger (WBS 1.2.3) – M. Narain

Digital Front-End Card (DFEM/DFEA):

DFEA board test data injection and data capture features have been successfully tested.  Design files with both Run IIa and Run IIb equations were provided to the Fermilab group for tests.  New equation formats have been implemented.  An equation file reduction program has been developed and tested.  Some problems in the equation files were found.  At the moment, event capturing features are under revision to meet the new requirements put forward by Jamieson Olsen and are expected to be finished soon.  The SLDB interface has not been tested yet due to lack of SLDB hardware.  A board was sent to Fermilab and it has been installed on the platform.

DFE Stand-Alone Tester (DSAT):

We are still awaiting the SLDB hardware.  No progress on this tester board.  Since the DFE board is now on the platform, we can test the serial link interface directly at FNAL, but we still plan to make it work at BU (pending hardware arrival).

Backplane, Subrack and Power Supplies:

A fully assembled DFE subrack was installed in PW02 (west platform in the DZero collision hall) this week.  Power supplies have been installed, cabled, and inspected.  Permission to run unattended was given on 26 October 2004.  The power supply GUI is up and running and everything looks good.

A DFEA/M board has been installed on the west platform.  We were able to initialize this board with no problems.  A 9th CTOC (Central Tracker Octant Card) board has also been installed and connected to the DFEA/M outputs.  The L3 output of this CTOC feeds into our readout crate X13.  We are just beginning to look at the status bits from the DFEA/M and new CTOC now.

ERNI connectors for the SLDB-to-backplane "pigtail" are at FNAL.  Ken Johns will arrange to have these cables assembled.  All LVDS cables are installed.

Gigabit Ethernet Fiber optics are installed. Online Linux PCs (d0ol10 and d0ol11) have been moved into place in MCH2.  We are using the command line utilities to download the latest firmware to the board on the west platform.

Crate Controller:

The crate controller is working well with the DFEB boards on the BU test stand.  The DFEB can be initialized from files stored on Linux.  The major firmware development is completed, and Jamieson Olsen is working on minor bug fixes and improving performance.

Eight DFEC2 boards are back from B.E.S.T. after having the BGA and QFN components reflowed and inspected.  These boards are being stuffed and checked out now.  Two new DFEC2's have been fully stuffed, tested and check out OK.

  - Level 2 Beta (WBS 1.2.4) – R. Hirosky

We reviewed literature and contacted technical support for several alternate Single Board Comupter (SBC) manufacturers.  A new SBC was ordered to test in the L2Beta motherboards.  The new board manufactured by ADLINK uses about 30% less power than other boards in its class and requires no connections from a mezzanine connector.

We expect delivery around mid-November.  This board may require a us to design a simple IDE cable connector.

Develop & Simulate New Run2b Algorithms:

In algorithm development and simulation, a new MSU graduate student has began to study missing ET tools at L2.

  - Silicon Track Trigger (WBS 1.2.5) – U. Heintz

We are still debating the wisdom of going forward with the STT upgrade. A decision will be made end of November or beginning of December. Meanwhile, production of the additional buffer controllers, needed in any event for the Layer 0 detector, will go ahead at Columbia University.

  - Trigger Simulation (WBS 1.2.6) – E. Barberis, M. Hildreth

More studies were carried out on the electron algorithm.  They suggest that a 1x2or2x1 Atlas type of Region of Interest performs better than any other selection, for a wide range on pT's.  This forms the basis of the default algorithm, although more cross-checks are underway.  More studies are also been carried out to define the shape of the isolation region.  In order to do that, we must understand the treatment of pedestals in the upgraded L1Cal, and therefore, the behavior of negative tower energies.

The L1Cal simulator (tsim_l1cal2b) has been updated against the implementation of the Sliding window in the trigger_rate_tool.  We have also began studying how the simulator needs to be modified in order to interface it with tsim_l1l2, within trigsim.

Work on the L1CTT updated simulator is also underway.  Most of the infrastructure, which will operate for both IIa, and IIb, is in place.  We are currently working on feeding the IIb equations to the code.  The L1CTT IIb equations are being used, with a preliminary version of the simulation, to generate test vectors for the verification of the firmware on the prototype DFEP Boards.

Work on the L1Caltrack simulator is progressing, and we are starting to look at possible L2 algorithms, although a clear identification of manpower is needed there.

  - Analog Front End II (WBS 1.2.8) – A. Bross

The first 3 loaded AFE II prototype boards have been received and are under test.  A few parts were installed improperly, but these problems have been fixed.  Power-on studies have been completed and the all power-on functionality has been verified.  Download studies have begun as well as testing of the firmware.  There are an additional 18 boards ready to be stuffed once we give the OK.

The TriPt chips from the MOSIS run have been received and the first few devices have been tested.  So far, all functionality of the chip works.  There are some pedestal shifts associated with the timing information and these are being studied.  Even if this effect cannot be eliminated, the problem can be addressed in the FPGA’s.

The transfer of the AFE II schematic from ORCAD into Veribest has been completed and layout of the AFE IIt board has begun.

- DAQ/Online (WBS 1.3) Schedule and Budget information– S. Fuess

Activity in October 2004 continued on work to be completed during the current accelerator shutdown.  We expect to meet the target of having most of the RunIIb Online system components operational by the end of the Fall 2004 accelerator shutdown period.

  - Level 3 Systems (WBS 1.3.1) D. Chapin, G. Watts

There were no scheduled tasks in this subproject during October 2004.  Operation of the most recent Level 3 farm node acquisition continues without problem.  The next activity in this WBS is another farm node acquisition, with the process to begin in Spring 2005.

  - Network and Host Systems (WBS 1.3.2) – J. Fitzmaurice, S. Krzywdzinski

Control and Monitoring systems: 1.3.2.2, 1.3.2.3

A set of 12 Linux systems for general-purpose control room and DAQ monitoring functions was received on 9/15/2004.  These systems were installed and configured during October.

DAQ Host, ORACLE, and File Server Systems: 1.3.2.6, 1.3.2.7, 1.3.2.8

The bulk of the activity and progress in the DAQ/Online area has been in the installation, configuration, and commissioning of the clustered server systems.  There are four operational clusters for DAQ, database, file serving, and general “service” (web, alarms, electronic log) functions.  All computing and network hardware has been installed and configured.  We made the transition of the development and production Oracle systems to the new cluster in late October.  Performance tests of the DAQ process chain (data logging, data transmission to the FCC) have continued during this period; all indications are that system capabilities are more than adequate for planned DAQ rates.  The new NFS cluster is in partial use; we have discovered and are addressing some issues with the Linux kernel that affect operations with a large number of files.  Cluster functions, such as power controller operation and redundant failover mechanisms, have been tested.  We remain on target for migrating Online operations to the Linux servers from the current Alpha servers by the end of the Fall shutdown period.

  - Control Systems (WBS 1.3.3) – F. Bartlett, G. Savage, V. Sirotenko

Testing continues on a Motorola PowerPC 8500 processor.  Additional applications have been verified to properly function.  More of these processors will be purchased in Spring 2005, for installation in the Summer 2005 shutdown period.

  - DAQ/Online Management (WBS 1.3.4) – S. Fuess

This is a continuing task for the long term, low duty-factor management activities for the DAQ/Online subsystem.  There continues to be a minimal level of effort required to evaluate future personnel needs.

Schedule Variance Analysis (as of 31 October 2004)

Schedule variances are reported against director’s milestones in section III.  Eight milestones have already been successfully achieved.  All remaining milestones are projected ahead of the DOE baseline dates.

  - D-Zero Run IIb L0 Upgrade (WBS 1.6)

There are no unfavorable schedule variances for this subproject.

  - D-Zero Run IIb Trigger Upgrade (WBS 1.2)

The L2STT complete milestone slipped 40 days in the last month. This is because no work is going on for building new boards while we decide the best course of action. There will likely be a change control in December documenting the decision and corrections needed to the project.

The only other slip of notice is 10 days in the L1 Calorimeter Trigger Production and Testing Complete milestone, due to the ongoing slips in the ADFv2 board. However, the board layout was completed in October, and the board is now going out for fabrication.

3.  D-Zero Run IIb Online (WBS 1.3)

There is no unfavorable schedule variance for this subproject.

- Department of Energy Milestones (as of 31 October 2004)

No additional milestones were predicted or achieved during the month of October.  Table 2 shows the status of the DOE Milestones.

| L1 DOE Milestones vs Current Forecast |
| --- |
| (Sorted by L1 Baseline Date) |
| Milestone Description | L2/Director's Baseline (10/04) | Last Month's Forecast (9/04) | This Month's Forecast (10/04) | L2/Director's Variance (work days) | Monthly Variance (work days) | Notes |
| WBS 1.2 Trigger |  |  |  |  |  |  |
| L2 Trigger Upgrade Production and Testing Complete | 01/05/06 | 5/23/2005 | 5/27/2005 | (147) | 4 |  |
| L1 Trigger Upgrade Production and Testing Complete | 04/10/06 | 8/19/2005 | 8/19/2005 | (154) | 0 |  |
| WBS 1.3 Online/DAQ |  |  |  |  |  |  |
| Online System Production and Testing Complete | 10/07/05 | 06/17/05 | 06/17/05 | (78) | 0 |  |
| WBS 1.6 Layer 0 Silicon Detector |  |  |  |  |  |  |
| Layer 0 Silicon Detector Ready to Move to DAB | 05/25/06 | 7/08/2005 | 7/05/2005 | (210) | (3) |  |
|  |  |  |  |  | status date: | 10/31/2004 |

Table 2:  Run IIb D-Zero Detector Project DOE Level 1 Milestones vs. Current Month and Previous Month’s forecast.  Entries are sorted by DOE L1 Milestone date.  Monthly variances are also provided.

- Obligation Reports (as of 31 October 2004)

The DZero Obligation Reports can be found below. The first report shows total obligations without the cost of the original Run IIb silicon and related closeout costs. The second report shows all obligations.