# F.1	Clauses and Provisions Incorporated by Reference

This screening information request (SIR) or contract, as applicable, incorporates by reference the provisions or clauses listed below with the same force and effect as if they were given in full text.  Upon request, the Contracting Officer (CO) will make the full text available or Offerors and contractors may also obtain the full text via the Internet at: http://conwrite.faa.gov (on this webpage, select “Search and View Clauses”, then “Download All Clauses”).

FAA Acquisition Management System Clauses by Reference:

3.10.1-9 	Stop-Work Order (October 1996)

3.10.1-11 	Government Delay of Work (April 1996)

3.10.1-24	Notice of Delay (November 1997)

3.11-34 	F.O.B. Destination (April 1999)

### F.2	Clauses and Provisions

3.2.2.8-6  	Time of Delivery (November 1997)

- The Government requires delivery to be made according to the following schedule:

REQUIRED DELIVERY SCHEDULE

___________________________________________________________________

ITEM NO. 			QUANTITY 		DAYS

AFTER DATE

OF CONTRACT

_____________________________________________OR DELIVERY ORDER (DO)

CLIN 0001   			1			13 months

CLIN 0002			1			15 months

CLIN 0003			1			17 months

CLIN 0004			1			17 months

CLIN 0005			20			210 days after receipt of DO

CLIN 0006			7			210 days after receipt of DO

CLIN 0007			7			210 days after receipt of DO

CLIN 0008			20			5 months after CLIN 0017

CLIN 0009			7			Option 5 months after CLIN 0018

CLIN 0010			7			Option 5 months after CLIN 0019

CLIN 0011			20			Upon completion of CLIN 0014

CLIN 0012			7			Option Upon completion of CLIN 0015

CLIN 0013			7			Option Upon completion of CLIN 0016

CLIN 0014			20			10 months after receipt of DO

CLIN 0015			7			Option 10 months after receipt of DO

CLIN 0016			7			Option 10 months after receipt of DO

CLIN 0017			20			2 months after CLIN 0014 completion

CLIN 0018			7			Option 2 months after CLIN 0015 completion

CLIN 0019			7			Option 2 months after CLIN 0016 completion

CLIN 0020			Multiple		Upon issuance of DO

CLIN 0021			1			Upon issuance of DO

CLIN 0022			1			Upon issuance of DO

CLIN 0023			1			Upon issuance of DO

CLIN 0024			1			Upon issuance of DO

CLIN 0025			1			Upon issuance of DO

CLIN 0026			1			Upon issuance of DO

CLIN 0027			1			Upon issuance of DO

*CLINs 0021 and 0026 require that the Offeror maintain a troubleshooting/repair system that will enable airport sites to obtain phone assistance and/or on-site technical assistance within 24hrs of receipt of a request for technical assistance or report of component failure

The Government reserves the right to award under either the required delivery schedule or the proposed delivery schedule, when an offeror offers an earlier delivery schedule than required above. If the offeror proposes no other delivery schedule, the required delivery schedule above will apply.

OFFEROR'S PROPOSED DELIVERY SCHEDULE

_____________________________________________________________________

ITEM NO. 			QUANTITY 			WITHIN DAYS

AFTER DATE

OF CONTRACT

_____________________________________________________________________

____________________    ______________________   ____________________

____________________    ______________________   ____________________

____________________    ______________________   ____________________

_____________________________________________________________________

- Attention is directed to provisions of the screening information request/contract that provide that a written award or acceptance of offer mailed, or otherwise furnished to the successful offeror, results in a binding contract. The Government will mail or otherwise furnish to the offeror an award or notice of award not later than the day award is dated. Therefore, the offeror should compute the time available for performance beginning with the actual date of award, rather than the date the written notice of award is received from the Contracting Officer through the ordinary mails. However, the Government will evaluate an offer that proposes delivery based on the Contractor's date of receipt of the contract or notice of award by adding (i) five calendar days for delivery of the award through the ordinary mails, or (ii) one working day if the solicitation states that the contract or notice of award will be transmitted electronically. (The term 'working day' excludes weekends and U.S. Federal holidays.) If, as so computed, the offered delivery date is later than the required delivery date, the offer may be rejected.

### F.3	Period of Performance

The base period of performance (POP) of the Contract is three (3) years from the contract award date. The POP of the contract may be extended by an additional two (2)  years upon exercise of two (2) individual one year options by the Contracting Officer (CO). The total contract POP including options is five (5) years from the contract award date. The CO will issue Delivery Orders (DOs) during this three (3) year period (five (5) years with options) to specify which Contract Line Item Numbers (CLINs) are being ordered.

# F.4	Option to Extend the Term of the Contract

The Government may extend the term of this contract by written notice to the Contractor within 30 days before the end of the POP provided that the Government shall give the Contractor a preliminary written notice of its intent to extend at least 60 days before the POP of the contract expires.  The preliminary notice does not commit the Government to an extension.

If the Government exercises this option, the extended contract shall be considered to include this option provision.

F.5	Place of Performance

The effort required by this contract shall be performed at various locations to include, but not be limited to, contractor facilities, designated airports, and the FAA Mike Monroney Aeronautical Center (MMAC).

The Mike Monroney Aeronautical Center (MMAC) is located at:

6500 South MacArthur

Oklahoma City, Oklahoma 73169

The Airports identified at time of Contract Award are:

Orlando (First Article System Designated Site)	MCO

The first 20 sites in the Base Period of Performance are:

Seattle-Tacoma					SEA

Charlotte Douglas				CLT

Washington-Dulles			 	IAD

Hartsfield-Jackson Atlanta			ATL

Phoenix Sky Harbor				PHX

Ft. Lauderdale					FLL

John F. Kennedy				JFK

Detroit Metro					DTW

Newark					EWR

Philadelphia					PHL

Denver					DEN

Houston-George Bush				IAH

Las Vegas McCarran				LAS

Baltimore-Washington International		BWI

Minneapolis-St. Paul				MSP

Dallas-Ft. Worth				DFW

San Diego					SAN

Los Angeles					LAX

Chicago O’Hare				ORD

Boston Logan					BOS

The fourteen sites in Option 1 and Option 2 Periods of Performance are:

Hartford – Bradley				HFD

Chicago Midway				MDW

Milwaukee - General Mitchell 			MKE

Honolulu International – Hickam FB		HNL

John Wayne - Orange County			SNA

St. Louis - Lambert 				STL

Louisville International –Standiford Field	SDF

Miami 					MIA

Memphis 					MEM

New York – LaGuardia				LGA

Ronald Reagan Washington National		DCA

Salt Lake City					SLC

Providence - Theodore Francis Green State	PVD

Houston - William P. Hobby			HOU

### F.6	Exercise of Options

The Government may at any time before the dates set forth in Section B exercise any or all options by giving written notice to the Contractor.  The Contractor shall update all documentation and modify other support (e.g., training and maintenance) to reflect the most current set configuration of the RWSL system when any options are exercised.

The Government may exercise options identified in the Schedule, if at all, on or before the dates indicated for the Option items listed below:

| Item | Description | Qty | Unit | Option Exercise Date |
| --- | --- | --- | --- | --- |
| CLIN 0006 | Site Design | 1-7 | Each | FY-10 |
| CLIN 0007 | Site Design | 1-7 | Each | FY-11 |
| CLIN 0009 | Production Systems – RWSL | 1-7 | Each | FY-11 |
| CLIN 0010 | Production Systems – RWSL | 1-7 | Each | FY-12 |
| CLIN 0012 | Production Systems - FLS | 1-7 | Each | FY-11 |
| CLIN 0013 | Production Systems - FLS | 1-7 | Each | FY-12 |
| CLIN 0015 | Construction to support installation of FLS Systems | 1-7 | Each | FY-11 |
| CLIN 0016 | Construction to support installation of FLS Systems | 1-7 | Each | FY-12 |
| CLIN 0018 | Installation of FLS Systems | 1-7 | Each | FY-11 |
| CLIN 0019 | Installation of FLS Systems | 1-7 | Each | FY-12 |
| CLIN 0024 | Depot Facility | 1 | Each | FY-10 |
| CLIN 0026 | Engineering Services | 1 | Lot | FY-10 |
| CLIN 0027 | Training Facility | 1 | Each | FY-10 |

F.7 	Delivery Requirements

The following First Article CLINs, Contract Data Requirements Line items (CDRLs), and/or contract milestone events shall be delivered in accordance with the following table. The First Article period of performance is Contract Award through completion of the acceptance by the FAA.

| ITEM NO. | SUPPLY/SERVICE | QTY | UNIT | DATE OF DELIVERY / ACCEPTANCE (See Note 1) | PLACE OF DELIVERY |
| --- | --- | --- | --- | --- | --- |
| 0001 | Post Award Conference SOW Para 3.1.7.1 | 1 | EA | *30 DAC | Contractor’s Facility |
|  | Integrated Baseline Review SOW Para 3.1.7.3 | Multiple | Each | 60 DAC; subsequent meetings at Government discretion | TBD |
|  | Program Management Review SOW Para 3.1.7.2 | Multiple | Each | 30 DAC; monthly thereafter | TBD |
|  | Program Management Plan (PM01)** | One | Each | 45 DAC | Per CDRL |
|  | Program Status Report (PM02)*** | Multiple | Each | Monthly 3 days prior to PMR | Per CDRL |
|  | Program Metrics Report (PM03)*** | Multiple | Each | Monthly 3 days prior to PMR | Per CDRL |
|  | Contractor Work Breakdown Structure (PM04)** | One | Each | 30 DAC; updates as required | Per CDRL |
|  | Risk Management Plan (PM05)** | One | Each | 45 DAC | Per CDRL |
|  | Risk Assessment Report (PM06)*** | Multiple | Each | Monthly 3 days prior to PMR | Per CDRL |
|  | Contract Funds Status Report (PM07)*** | Multiple | Each | Monthly 3 days prior to PMR | Per CDRL |
|  | Contract Performance Report (PM08)*** | Multiple | Each | Monthly | Per CDRL |
|  | Integrated Master Schedule (PM09)*** | One | Each | 30 DAC | Per CDRL |
|  | Agenda (PM10) | Multiple | Each | Per CDRL | Per CDRL |
|  | Meeting Minutes (PM11) | Multiple | Each | Per CDRL | Per CDRL |
|  | Preliminary Design Review SOW Para 3.1.7.4 | 1 | Each | TO BE PROVIDED BY CONTRACTOR | Contractor’s Facility |
|  | Critical Design Review SOW Para 3.1.7.4 | 1 | Each | TO BE PROVIDED BY CONTRACTOR | Contractor’s Facility |
|  | Final Design Review SOW Para 3.1.7.4 | 1 | Each | TO BE PROVIDED BY CONTRACTOR | Contractor’s Facility |
|  | System Safety Program Plan (SA01)** | 1 | Each | 30 days prior to PDR | Per CDRL |
|  | Quality Assurance Plan (QA01)** | 1 | Each | 45 DAC | Per CDRL |
|  | System/Subsystem Design Description (SE01) | 1 | Each | At PDR; Revisions at CDR and FDR | Per CDRL |
|  | Security Plan (SE02) | 1 | Each | At PDR; Final at CDR; revisions as required | Per CDRL |
|  | Software Development Plan (SW01) | 1 | Each | At SRR | Per CDRL |
|  | Software Requirements Specification (SW02) | 1 | Each | 30 days prior to SRR | Per CDRL |
|  | Software Design Description (SW03) | 1 | Each | 30 days prior to SRR; Final 30 days prior to CDR | Per CDRL |
|  | Software Version Description (SW04) | 1 | Each | At CDR; Final at FDR; Resubmission with software releases | Per CDRL |
|  | Software User Manual (SW05) | 1 | Each | At FDR; submissions with software releases | Per CDRL |
|  | Software Product Specification (SW06) | 1 | Each | 60 days prior to FCA/ PCA; submissions with software releases | Per CDRL |
|  | Software Transition Plan (SW07) | 1 | Each | 60 days prior to FDR | Per CDRL |
|  | Computer Programmer’s Manual (SW08) | 1 | Each | At FDR | Per CDRL |
|  | Configuration Management Plan (CM01)** | 1 | Each | 30 DAC | Per CDRL |
|  | Engineering Change Proposal (CM 02) | Multiple | Each | As Required | Per CDRL |
|  | Request For Deviation (CM03) | Multiple | Each | As Required | Per CDRL |
|  | Request For Waiver (CM04) | Multiple | Each | As Required | Per CDRL |
|  | Configuration Status Accounting Report (CM05) | Multiple | Each | 60 DAC; Monthly | Per CDRL |
|  | System Problem Report (CM06) | Multiple | Each | As Required | Per CDRL |
|  | Interface Control Document (HW01) | 1 | Each | 30 days prior to PDR; Final 30 days prior to CDR | Per CDRL |
|  | Interface Design Description (HW02) | 1 | Each | 30 days prior to PDR; Final 30 days prior to CDR | Per CDRL |
|  | Human Engineering Design Approach Document – Operator (HE01) | 1 | Each | 30 days prior to PDR; Final 30 days prior to CDR; Revisions as required | Per CDRL |
|  | Human Engineering Design Approach Document – Maintainer (HE02) | 1 | Each | 30 days prior to PDR; Final 30 days prior to CDR; Revisions as required | Per CDRL |
|  | Contractor Master Test Plan (TE01)* | 1 | Each | 45 DAC | Per CDRL |
|  | Test Plan (TE02) | Multiple | Each | IAW approved CMTP for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Test Procedure (TE03) | Multiple | Each | 90 days prior to test for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Test Report (TE04) | Multiple | Each | 30 days after completion of tests for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Design Review Data Package (TE05) | Multiple | Each | 30 days prior to PDR, CDR and FDR | Per CDRL |
|  | Analysis Report (TE06) | Multiple | Each | IAW VRTM Requirements and approved CMTP | Per CDRL |
|  | Notification of Test Letter (TE07) | Multiple | Each | 5 days prior to scheduled tests | Per CDRL |
|  | Test Log (TE08) | Multiple | Each | IAW approved CMTP | Per CDRL |
| 0001 | Reliability Program/ Demonstration Plan (RP01) | 1 | Each | 30 days prior to CDR | Per CDRL |
|  | Contractor Repair Service Status Report (RP02) | 1 | Each | Monthly | Per CDRL |
|  | Maintainability Program/ Demonstration Plan (MP01) | 1 | Each | 60 days prior to the start of M-Demo Test per CMTP | Per CDRL |
| 0002 | Implementation Task Plan (IC01) | 1 | Each | 45 days prior to start of construction | Per CDRL |
|  | Site Survey SOW Para 3.5.2.1 | 1 | Each | 90 DAC | Key Site |
|  | Contractor Site Engineering Report (IC02) | 1 | Each | Preliminary: 90 days after site survey | Per CDRL |
|  | Red-Lined Drawings (IC03) | Multiple | Each | With delivery of Preliminary CSER | Per CDRL |
|  | Facility Standard Drawings (IC04) | Multiple | Each | With delivery of Preliminary CSER | Per CDRL |
|  | Final As-Built Drawings (IC05) | Multiple | Each | 30 days after installation; final drawings 30 days after completion of SAT | Per CDRL |
|  | Security Plan (SE02) | 1 | Each | Prior to Site Survey | Key Site |
|  | Agenda (PM10) | Multiple | Each | Per CDRL | Per CDRL |
|  | Meeting Minutes (PM11 | Multiple | Each | Per CDRL | Per CDRL |
|  | Construction SOW Para 3.5.2 | 1 | Each | 6 Months After CA; Complete by 13 Months after CA | Key Site |
|  | Installation SOW Para 3.5.3 | 1 | Each | 13 Months after CA; Complete by 15 Months after CA | Key Site |
|  | Test Plan (TE02) | Multiple | Each | IAW approved CMTP for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Test Procedure (TE03) | Multiple | Each | 90 days prior to test for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Test Report (TE04) | Multiple | Each | 30 days after completion of tests for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Analysis Report (TE06) | 1 | Each | IAW VRTM Requirements and approved CMTP | Per CDRL |
|  | Notification of Test Letter (TE07) | Multiple | Each | 5 days prior to scheduled tests | Per CDRL |
|  | Test Log (TE08) | Multiple | Each | IAW approved CMTP | Per CDRL |
|  | Contractor Acceptance Inspection SOW Para 3.5.3.4 | 1 | Each | 2 month after start of First Article SDQT | Key Site |
| 0003 | Configuration Audit Plan (CM07) | 1 | Each | 60 days prior to FCA/PCA | Per CDRL |
|  | Functional and Physical Configuration Audit Summary Report (CM08) | 1 | Each | 2 days after completion of audits | Per CDRL |
|  | Test Report (TE04) | Multiple | Each | 30 days after completion of tests for PQT, FQT, FDQT, SDQT, 1st Article, FAT and SAT | Per CDRL |
|  | Test Log (TE08) | Multiple | Each | IAW approved CMTP | Per CDRL |
|  | Agenda (PM10) | Multiple | Each | Per CDRL | Per CDRL |
|  | Meeting Minutes (PM11) | Multiple | Each | Per CDRL | Per CDRL |
| 0004 | Integrated Support Plan (LM01) | 1 | Each | 60 DAC | Contractor’s Facility |
|  | Logistics Guidance Conference SOW Para 3.6.1.1.1 | 1 | Each | 30 DAC in conjunction with Post Award Conference | Contractor’s Facility |
|  | Training Guidance Conference SOW Para 3.6.7.2 | 1 | Each | TBD | Government or Contractor’s Facility |
|  | Provisioning Conference SOW Para 3.6.1.1.2 | 1 | Each | No Later than 30 days after PCA | Contractor’s Facility |
|  | Logistics Management Information (LMI) Data Products (LM02) | 1 | Each | 60 days prior to Provisioning Conference | Per CDRL |
|  | List of Recommended Site Spares (LM03) | 1 | Each | 30 days after CDR | Per CDRL |
|  | List of Recommended Consumables (LM04) | 1 | Each | 30 days after CDR | Per CDRL |
|  | Support and Test Equipment List (LM05) | 1 | Each | 30 days after CDR | Per CDRL |
|  | LRU Markings Report (LM06) | 1 | Each | 30 days after CDR | Per CDRL |
|  | Contractor Transition Plan (LM07) | 1 | Each | 30 days after notification by the Government | Per CDRL |
|  | Engineering Drawing Tree (TD01) | 1 | Each | 30 days after CDR; Final 60 days prior to FCA/PCA | Per CDRL |
|  | Product Drawings (TD02) | Multiple | Each | 60 days prior to FCA/PCA | Per CDRL |
|  | Commercial Off the Shelf (COTS) Drawings (TD03) | Multiple | Each | 60 days prior to FCA/PCA | Per CDRL |
|  | Commercial Off the Shelf (COTS) Manuals (TD04) | Multiple | Each | 30 days after PDR | Per CDRL |
|  | COTS Hardware Description (TD05) | 1 | Each | 60 days prior to Provisioning Conference | Per CDRL |
|  | Manuscript Plan (TD06) | 1 | Each | 30 days after CA | Per CDRL |
|  | Manuscript Prospectus (TD07) | 1 | Each | 60 days after CA | Per CDRL |
|  | Verification and Validation Plan (TD08) | 1 | Each | 60 days after CA | Per CDRL |
|  | Manuscript (TD09) | 1 | Each | Per CDRL | Per CDRL |
|  | Comment Resolution Report (TD10) | 1 | Each | Per CDRL | Per CDRL |
|  | Support & Test Equipment Manuals (TD11) | 1 | Each | Per CDRL | Per CDRL |
|  | Air Traffic Operator’s Manual (TD12) | 1 | Each | Per CDRL | Per CDRL |
|  | FAA Installation Point of Contact Manual (TD13) | 1 | Each | Per CDRL | Per CDRL |
|  | Agenda (PM10) | Multiple | Each | Per CDRL | Per CDRL |
|  | Meeting Minutes (PM11) | Multiple | Each | Per CDRL | Per CDRL |

# CLIN 0005 has been deleted in its entirety from Section F.7.

# .

# Note 1: Denotes specified start date.

* This CDRL applies to the entire contract and is included in all applicable CLINs where testing is required.

** This CDRL applies to the entire contract and is included in all CLINs, but is delivered only once under this CLIN and updated as required in accordance with the CDRL language

*** This CDRL applies to the entire contract and is included in all CLINs, but is delivered under this CLIN and is updated periodically throughout the contract in accordance with the  CDRL’s requirements.

# F.8	Deliverables

The Contractor shall prepare and submit all deliverable items as specified in the delivery order or task order.

The contractor shall provide the deliverables in “calendar” days unless otherwise specified.

The contractor shall reference the “Contract Data Requirements List (CDRL) number”, the “SOW Section”, and the “Description” for any correspondence, information, label and/or title that designates a deliverable.

Any and all correspondence being submitted to the Contracting Officer, including copies of all correspondence transmitting required documentation to the Technical Officer, shall be addressed as follows:

Federal Aviation Administration

Attn: Robert Valdes, Contracting Officer, AJA-46

600 Independence Avenue, SW

Washington, D.C. 20591

In addition, all items required to be delivered hereunder shall be prepared in accordance with the terms and conditions of this Contract and shall be delivered F.O.B. Destination.

# F.9	Meetings and Conferences

The Contractor shall notify the Contracting Officer of meetings and conferences, including time, date, location, at least ten (10) working days in advance of any meeting or conference.

F.10	Request for Shipping Instructions

- This paragraph is applicable to any contract line item which provides for Contractor installation. If the Contractor has not been furnished the consignee’s address or any other data needed to enable him to make shipment, the Contractor shall request such information from the Contracting officer, at least 30 days before the date the Contractor expects to make shipment. The information needed will furnished by the Contracting Officer or his/her representative by whatever means is most appropriate. FAA Form 4500-1 will not be used to authorize shipment.

- This paragraph is applicable to any contract line item which the Contractor will not install:

  - At least 30 calendar days before the date the Contractor expects to make shipment of any unit (or portion thereof, when authorized), the Contractor shall request shipping instructions form the Contracting officer. Each request for shipping instructions shall include:

- The expected date of shipment.

- The number of units to be shipped.

- The contract line item(s) involved.

- The current contract unit price of each contract line item to be shipped.

- Whether commercial bill of lading forms and procedures are desired to be used.

- The weight and dimensions of the shipment (if unknown, estimate must be provided).

- A statement of any specialized carriage which may be necessary (e.g. whether padded van or flatbed is needed; if shipment is to be made by air, etc.)

  - Shipping instruction will be issued in accordance with FAA order 4650.30.

  - The Contractor shall expressly state if shipment will be delivering Government property previously provided to the Contractor for modification, reconfiguration, or incorporation as a line item under the contract.

- If any contract line item is to be delivered F.O.B point of origin, the Transportation Officer will furnish Government bills of lading to the Contactor, or authorize him to use commercial bill of adding forms and procedures as provided in paragraph (d) below.

- Partial shipments (shipments of less than one complete unit of a lone item) are not authorized unless specifically approved in advance (on an individual basis) by the Contracting Officer. Authorization of a partial shipment is the prerogative of the Government and will not be authorized unless a definite benefit to the Government will be realized or to meet an unexpected or emergency situation.

- If the transportation charges per shipment do not exceed $100, the Contractor may be authorized by the Transportation Officer to use commercial bill of lading forms and procedures in lieu of Government Bill of lading. In such cases, transportation charges shall be prepaid by the Contractor and the charges shall be included as a separate item on the invoice. A copy of the receipted freight bill shall be included with the invoice.

- Under paragraph (b) above, the Transportation Officer is the only person authorized to issue FAA Form 4500-1, unless the Contracting Officer specifically authorizes otherwise. No shipment pursuant to paragraph (b) shall be made by the Contractor, whether F.O.B origin or destination unless and until FAA Form 4500-1 has been received. Failure of the Contractor to observe these requirements may delay invoice payment.