## GPEA Non-Completed Trns. Report
Transaction ID | Agency | OMB Control No. | Form No. | Interaction Name | Original GPEA Compliance Estimate | Original GPEA Comment | Revised: Date of Completion | Explanation
| AMS | 0581-0006 | FV-498-1 | Weekly Report of Berries Received for Processing (WA and OR) | 2003-10-31 | <empty> | 2004-05-31 | Date for E-authentication is 5/31/04. AMS will be putting a plan in place to determine if this agency will be going to meet the Department's anticipated guidelines.
| AMS | 0581-0056 | TB-87 | Imported Tobacco Pesticide Residues and End User(s) Certification | 2003-10-31 | <empty> | 2004-05-31 | Date for E-authentication is 5/31/04. AMS will be putting a plan in place to determine if this agency will be going to meet the Department's anticipated guidelines.
| AMS | 0581-0065 | FV-57 | Background Statement (Producer Member/Alternate Member) | 2003-10-31 | <empty> | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0065 | FV-58 | Background Statement (Public Member/Alternate Member) | 2003-10-31 | <empty> | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0071 | FV-176 | Producer Nominee Questionnaire | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0071 | FV-177 | Handler Nominee Questionnaire | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0071 | FV-178 | Producer Referendum Ballot | 2003-10-31 | <empty> | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0071 | FV-179 | Cooperative's Referendum Ballot | 2003-10-31 | <empty> | TBD | Eligibility to vote using this form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process.
| AMS | 0581-0093 | DA-19 | Nominations and Selections-Dairy (Producer) | 2003-10-31 | <empty> | 2003-11-14 | This form was originally considered not practical by the program, but the program area altered their decision after the compliance deadline.
| AMS | 0581-0093 | DA-19-1 | Nominations and Selections-Dairy (Processor) | 2003-10-31 | <empty> | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0113 | PY-155 | Registration of Shell Egg Handlers | 2003-10-31 | <empty> | 2004-05-31 | The estimated integration date for E-authentication is 5/31/04. AMS will be putting a plan in place to determine if this agency will be going to meet the Department's anticipated guidelines.
| AMS | 0581-0123 | FV-159 | Application for Unofficial Samples | 2003-10-31 | <empty> | TBD | Samples of the Processed Products must accompany this form.
| AMS | 0581-0123 | FV-468 | Application for Licenses to Sample Processed Foods | 2003-10-31 | This form is completed subsequent to employment with F&V, PPB. This form requests information that is considered private and confidential and requires a person's personal information. There would be no advantage to making this form available to the public. | TBD | This form is completed subsequent to employment with F&V, PPB. This form requests information that is considered private and confidential and requires a person's personal information. There would be no advantage to making this form available to the public.
| AMS | 0581-0177 | FV-46 | Background/Acceptance Statement (Producer and Handler Member/Alternate) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0177 | FV-47 | Background/Acceptance Statement (Public Member/Alternate) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-109 | =-- Southeastern Potatoes | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-112 | -- Walla Walla Onions (producer/handler) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-115 | =-- Walla Walla Onions (Public Member) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-133 | Background Questionnaire w/letter of acceptance -- Idaho/E. Oregon Potatoes | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-134 | =-- Texas Melons | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-134-1 | =-- Texas Melons | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-138 | -- Hazelnuts (producer/handler) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-139 | =-- Hazelnuts (Public Member) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-165 | =-- CA Dried Prunes (cmte nominee) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-166 | =-- CA Dried Prunes (Public rep.) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-174 | -- Vidalia Onions (Producer & Producer/Handler) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-175 | =-- Vidalia Onions (Public Member) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-219 | =-- CA Raisins (handlers) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-220 | =-- CA Raisins (Public Member) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-222 | =-- CA Raisins (Growers) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-223 | Committee Ballots/Nominations -- Raisins (independent producer's ballot) | 2003-10-31 | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process. | TBD | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. an electronic voting system will be established separately to support this process.
| AMS | 0581-0178 | FV-224 | =-- California Raisins | 2003-10-31 | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process. | TBD | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process.
| AMS | 0581-0178 | FV-225B | California Raisins - Cooperative Association Ballot (Amendment or Termination) | 2003-10-31 | <empty> | TBD | Eligibility to vote using this form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process at a later date.
| AMS | 0581-0178 | FV-283 | =-- Florida Tomatoes | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost-justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost-justifiable for this program.
| AMS | 0581-0178 | FV-285 | =-- California Dates | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost-justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost-justifiable for this program.
| AMS | 0581-0178 | FV-32 | -- Idaho / Oregon Onions (Producer/Handler) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-33 | =-- Idaho/Oregon Onions (Public Member) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-41 | Background Questionnaire -- WA Potatoes | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-52 | =-- Colorado Potatoes | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-61 | =-- Oregon/California Potatoes | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0178 | FV-90 | =-- Texas Onions | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-120 | =-- Winter Pears | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-129 | =-- Fresh Bartlett Pears | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-15 | =-- Fresh Prunes | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-152 | =-- Apricots | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-163 | Confidential Background Stmt -- Citrus Grown in FL --f/Admin | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-164 | =-- Citrus Grown in FL -- f/Admin Committee - Public Member | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-216 | #NAME? | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-23 | =-- Sweet Cherries | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-259 | -- Cranberries (Public Mbr & Alternt) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-260 | -- Cranberries (Grower/Alt. Member) | 2003-10-31 | <empty> | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-266 | =-- Kiwifruit (producer) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-266-1 | -- Kiwifruit (Public Mbr & Alternate) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-286 | -- Cranberries (Amendatory Co-op and Certif. Of Resolution) | 2003-10-31 | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process. | TBD | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process.
| AMS | 0581-0189 | FV-287 | =-- Cranberries-Amendatory Processor | 2003-10-31 | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this pro | TBD | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this process.
| AMS | 0581-0189 | FV-288 | =-- Cranberries (Amendatory Grower) | 2003-10-31 | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this pro | TBD | Eligibility to vote using the form must be determined and electronic credentials for one-time use issued in advance of each referendum. An electronic voting system will be established separately to support this pro
| AMS | 0581-0189 | FV-74 | =-- CA Desert Grapes | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-75 | =-- Peaches (Shipper CTFA) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-76 | =-- Peaches (producer CTFA) | 2003-10-31 | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of annual responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-82 | =-- Texas Citrus | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-84 | =-- Nectarines | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-97 | =-- Avocados | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0189 | FV-97-1 | -- Avocados (Public Mbr & Alternates) | 2003-10-31 | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program. | TBD | Because of the limited number of responses, the cost of supporting e-authentication would average hundreds of dollars for each transaction received and is not cost justifiable for this program.
| AMS | 0581-0191 | TM-11 | Export Certificate | 2003-10-31 | <empty> | 2004-03-30
| AMS | 0581-NEW | FV-649 | Certified Organic Producers and Marketers | 2003-10-31 | This form was recently approved by OMB. The rule has not been finalized. It will be made electronic at a later date. | TBD | This form was recently approved by OMB. The rule has not been finalized. Branch is assessing whether this form is practical or not for the electronic forms site.
| APHIS | 0579-0013 | APHIS 2008A | Continuation for Veterinary Biologics Production and Test Reports | 2003-10-20 | The Risk Impact Assessment Tool has been completed for this transaction. The transaction was determined to be a level 4 risk. This transaction needs electronic signature and cannot be made available electronically until there is a Digital signature soluti | TBD | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0013 | APHIS 2020 | Shipment and Receipt of Biologics Samples | 2003-10-20 | Completion date dependent on development of new Laboratory Information Management System (LIMS) to incorporate and process data. This system should be implemented in late 2005 or early 2006. In the interim, a fillable PDF will available as agreed upon for | 2004-10-20 | Completion date dependent on development of new Laboratory Information Management System (LIMS) to incorporate and process data. This system should be implemented in late 2005 or early 2006. In the interim, a fillable PDF will available.
| APHIS | 0579-0013 | APHIS 2008 | Veterinary Biologics Production and Test Report | 2003-10-31 | <empty> | TBD | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0032 | VS 17-145 | U.S. Origin Health Certificate for the Export of Horses from the U.S. to Canada | 2003-09-01 | At a minimum, the presentation and the ability for clients to submit web-based electronic forms will be automated by the projected date. Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes a | 2004-09-01 | Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes and the need to develop USDA-wide approaches. These infrastructure components are needed immediately to accomplish the full transformation.
| APHIS | 0579-0036 | APHIS 7003 | Application for License Renewal | 2003-09-30 | Agency equipment required for completion has been ordered but hasn’t arrived for implementation | 2004-03-30 | Dependent upon installation of Oracle 9i Application Server infrastructure which has been delayed until February 2004.
| APHIS | 0579-0036 | APHIS 7003A | Application for License New | 2003-09-30 | Agency equipment required for completion has been ordered but hasn’t arrived for implementation | 2004-03-30 | Dependent upon installation of Oracle 9i Application Server infrastructure which has been delayed until February 2004.
| APHIS | 0579-0036 | APHIS 7011 | Application for Registration | 2003-09-30 | Agency equipment required for completion has been ordered but hasn’t arrived for implementation | 2004-03-30 | Dependent upon installation of Oracle 9i Application Server infrastructure which has been delayed until February 2004.
| APHIS | 0579-0040 | VS 17-135A | U.S. Permit to Transit Poultry, Pigeons, Hatching Eggs of Birds | 2003-09-01 | At a minimum, the presentation and the ability for clients to submit web-based electronic forms will be automated by the projected date. Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes a | 2004-09-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0040 | VS 17-29 | Declaration of Importation for Animals, Animal Semen, Birds, Poultry, and Eggs for Hatching | 2003-09-01 | At a minimum, the presentation and the ability for clients to submit web-based electronic forms will be automated by the projected date. Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes a | 2004-09-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0040 | VS 10-4 | Specimen Submission | 2003-10-20 | At a minimum, the presentation and the ability for clients to submit web-based electronic forms will be automated by the projected date. Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes a | 2004-10-20 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0040 | VS 17-128 | Application/Permit for Ratites or Ratite Hatching Eggs and Space Reservation Request | 2003-10-20 | At a minimum, the presentation and the ability for clients to submit web-based electronic forms will be automated by the projected date. Implementation of the underlying eGovernment structure has been impacted by various moratoriums and waiver processes a | 2004-10-20 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| APHIS | 0579-0117 | APHIS 2060 | Environmental Monitoring | 2003-10-01 | <empty> | TBD | This form will be automated as part of the Laboratory Information Management System.
| FAS | 0551-0004 | Non-Form | Notice of Default | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0004 | Non-Form | Amendment to Application for Payment Guarantee | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0004 | Non-Form | Evidence of Export | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0004 | Non-Form | Assignment Notification | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0004 | Non-Form | Application for a Payment Guarantee | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0005 | Non-Form | Shipping Agent Nomination Form | 2003-10-01 | <empty> | TBD | This interaction with the public does exist. However, the Title-I user with whom this interaction takes place believes that it would not be practical to develop an Internet-based form to handle it.
| FAS | 0551-0005 | Non-Form | Report of New Sales/Price Approval | 2003-10-01 | <empty> | TBD | This interaction with the public exists. However, the interaction is currently performed over the phone. The need for this interaction will most likely become unnecessary, once the Declaration of Sale form is presented to the public over the Internet.
| FAS | 0551-0005 | Non-Form | Prospective Supplier Information Sheet | 2003-10-01 | <empty> | TBD | While this interaction with the public does exist, it is not, in fact an interaction handled by a form. The information supplied to this Agency is in the form of a packet of several types of documents, including company financial statements, bank statement, etc.
| FAS | 0551-0005 | Non-Form | Request for Approval of Amendment to Sale | 2003-10-01 | <empty> | TBD | The interaction contains free-form information that does not lend itself to the use of a standard Internet-based form. There are many terms and conditions used to describe a particular sales transaction, under Title-I.
| FAS | 0551-0005 | Non-Form | Shipping Agent Certifications | 2003-10-01 | <empty> | TBD | While this interaction with the public does exist, it is similar to the "Request for Approval of Amendment to Sale" in that almost all of the relevant information provided during this interaction is in the form of free-form text.
| FAS | 0551-0037 | Non Form | Evidence of Export/Amendments/Certifications | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0037 | Non Form | Exporter Qualifications/Certification | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0037 | Non Form | Payment Guarantee Amendments | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0037 | Non Form | Notice of Default | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FAS | 0551-0037 | Non Form | Application for Payment Guarantee/Certification | 2003-10-01 | <empty> | 2004-04-30 | This project is behind the original schedule. Funding issues caused part of the problem.
| FNS | 0584-0041 | FNS-143 | Claim for Reimbursement, Summer Food Service Program for Children | 2003-06-01 | <empty> | 2004-03-31
| FNS | 0584-0055 | FNS-342 | Application for Participation and Management Plan for Sponsoring Organizations in the Child and Adult Care Food Program | 2003-10-01 | <empty> | 2005-03-31
| FNS | 0584-0055 | FNS-82 | Child and Adult Care Food Program Claim for Reimbursement | 2003-10-01 | Although the Form FNS-82 will be part of ROAP, it was not intended to be deployed in the initial rollout of the application. | 2004-12-01 | The original comment did not indicate that the ROAP forms would be phased in according to which program the forms was used for reimbursement.
| FNS | 0584-0280 | FNS-81 | Sponsor Application for Participation, Summer Food Service Program | 2003-10-01 | <empty> | 2005-03-31 | This is an application form which will be made available via an internet application and will not likely be part of the primary ROAP system.
| FNS | 0584-0280 | FNS-81-1 | Site Information Document, Summer Food Service Program | 2003-10-01 | <empty> | 2005-03-31
| FNS | 0584-0284 | FNS-806 | School Lunch, Breakfast and Special Milk Programs - Monthly Claim for Reimbursement | 2003-06-15 | <empty> | 2004-03-31
| FNS | 0584-0293 | FNS-52 | Food Requisition | 2003-06-01 | <empty> | 2004-05-01
| FNS | 0584-0332 | FNS-339 | Federal-State Special Supplemental Nutrition Program Agreement | 2003-10-01 | Due to the low volume use of this form, it will only be provided as a printable form on the Internet | 2005-03-31 | Due to the low volume use of this form, it will only be provided as a printable form on the Internet
| FNS | 0584-0512 | FNS-728 | Uniform Grant Application | 2003-10-31 | <empty> | 2004-06-30
| FSA | 0560-0052 Retired due to PRA exemption | CCC-20 | Supplement to Uniform Storage Agreement and Amendments | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | CCC-25-1 | Schedule of Warehouses | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | CCC-34 | Successor's Agreement | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | CCC-34-1 | Transfer of Rights and Interest | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-1042 | Guide for Completing Uniform Grain and Rice Storage Agreement Documents | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-227 | Raw Sugar Acquisition Report and Invoice for Related Charges | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-227-A | Refined Sugar Acquisition Report and Invoices for Related Charges | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-232 | Notice of Approval or Change in Status of Storage Agreement or Contract | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-250 | Truck Bill of Lading | 2003-10-31 | <empty> | TBD
| FSA | 0560-0052 Retired due to PRA exemption | KC-371 | Guide for Completing Processed Commodities Storage Agreement Documents | 2003-10-31 | <empty> | TBD
| FSA | 0560-0058 | MQ-76-1 | Request to Retain Producer's Marketing Card | 2003-10-31 | <empty> | TBD
| FSA | 0560-0087 | CCC-665 | Agreement for Grain Pledged Collateral for CC Comms Lns | 2002-08-31 | Not Applicable | TBD
| FSA | 0560-0120 | WA-140, 141 | Agreement to Assume Grain Storage Obligations Agreement With Respect to Agricultural Product Storage Obligations | 2003-10-31 | Internal Exam.form only -- not for general public use | TBD | Internal Exam.form only -- not for general public use
| FSA | 0560-0120 | WA-302, 303 | Warehouse Inspection Report (Grain & Misc) | 2003-10-31 | Internal Exam.form only -- not for general public use | TBD | Internal Exam.form only -- not for general public use
| FSA | 0560-0125 | CRP-1 | Conservation Reserve Program Contract and Continuation | 2003-03-31 | The CRP Contract form will be considered for automation as conversion/migration of the system is completed. | 2004-01-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0125 | CRP-1 (Appendix) | CRP Appendix | 2003-03-31 | The CRP Contract form will be considered for automation as conversion/migration of the system is completed. | 2004-01-31 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0125 | CRP-1F Addendum | CRP-1 Modification to Extend the Expiration Date for 1 Year | 2003-03-31 | The CRP Contract form will be considered for automation as conversion/migration of the system is completed. | 2004-01-31 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0125 | CRP-1H Addendum | CRP-1 Modification to Extend the Expiration Date for 3 Years | 2003-10-21 | The CRP Contract form will be considered for automation as conversion/migration of the system is completed. | 2004-01-04 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0125 | CRP-41 | Conservation Reserve Program Early Termination Agreement | 2003-10-21 | An enhancement is planned for the eForms site which will enable the FSA office to initiate the form to the customer via the eForms service. When that is possible, the customer could esign the form and send it back to the FSA office. | 2004-01-01 | An enhancement is planned for the eForms site which will enable the FSA office to initiate the form to the customer via the eForms service. When that is possible, the customer could esign the form and send it back to the FSA office. Enterprise Architecture
| FSA | 0560-0125 | CRP-817U | Certification for Compliance for CRP | 2003-10-21 | The use of this form on the internet is was determined to be not practicable due to information needed from USDA before a person could complete the form. | 2005-01-01 | The use of this form on the internet is was determined to be not practicable due to information needed from USDA before a person could complete the form. However, Enterprise Architecture migration is currently underway at FSA.
| FSA | 0560-0125 | OR CRP-1 Addendum | OR CRP-1 Addendum | 2003-10-21 | The use of this form on the internet is was determined to be not practicable for two reasons. This form is used only in one State, Oregon, therefore its use is limited. 2. Information is needed from USDA before a person could complete the form. | TBD | The use of this form on the internet is was determined to be not practicable for two reasons. This form is used only in one State, Oregon, therefore its use is limited. However, Enterprise Architecture migration is currently underway at FSA.
| FSA | 0560-0138 | CCC-831 | Sugar Production and Distribution Report: Sugar Beet Processors | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-832 | Sugar Production and Distribution Report: Sugarcane Processors | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-833 | Sugar Deliveries for Human Consumption | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-835 | Sugar Production and Distribution Report: Cane Sugar Refiners | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-836 | Sugar Beet Processors Annual Information Request Form | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-837 | Sugarcane Processors Annual Information Request Form | 2003-10-21 | <empty> | TBD
| FSA | 0560-0138 | CCC-838 | Cane Sugar Refiners Annual Information Request Form | 2003-10-21 | <empty> | TBD
| FSA | 0560-0155 | FSA 1980-89 | Shared Appreciation Agreement | 2003-06-02 | Completed | TBD
| FSA | 0560-0158 | FmHA 1965-11 | Accelerated Repayment Agreement | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FmHA 1965-13 | Assumption Agreement (Farmer Programs) | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FmHA 1965-15 | Assumption Agreement (Single Family Housing) | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FmHA 440-26 | Consent and Subordination Agreement | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming. Form generated by agency is used as a security instrument. | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming. Form generated by agency is used as a security instrument.
| FSA | 0560-0158 | FmHA 440-9 | Supplemental Payment Agreement | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FmHA 443-16 | Assignment of Income for Rural Estate | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FmHA 465-1 | Application for Partial Release Subordination or Consent | 2003-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming | 2004-01-04 | Shared form with RD. Forms need to be reviewed, updated and converted to FSA prior to eforming
| FSA | 0560-0158 | FSA 440-2 | County Committee Certification or Recommendation | 2003-01-04 | This form has been converted to FSA 440-2 on 6/10/02 | 2004-01-04 | This form has been converted to FSA 440-2 on 6/10/02
| FSA | 0560-0162 | 1940-51 | Crop Share Lease | 2003-06-02 | Completed | 2004-01-01 | An electronic submission by customers is underway for the form.
| FSA | 0560-0162 | 1940-53 | Cash Lease | 2003-06-02 | Completed | 2004-01-01 | An electronic submission by customers is underway.
| FSA | 0560-0162 | 1940-55 | Livestock Share Lease | 2003-06-02 | Completed | 2004-01-01 | An electronic transaction by customer is underway.
| FSA | 0560-0162 | 1940-56 | Annual Supplement to Farm Lease | 2003-06-02 | Completed | 2004-01-01 | An electronic transaction by customers is underway.
| FSA | 0560-0162 | 441-10 | Non-Disturbance Agreement | 2003-10-03 | Form is currently in Forms and Graphics waiting upload to the web | 2004-01-01 | Form is currently in Forms and Graphics waiting upload to the web.
| FSA | 0560-0177 | KC 327 Dairy 5A-D | Dairy-5 Offer Forms/Price Support Cancellation Request | 2003-10-01 | <empty> | TBD
| FSA | 0560-0182 | MQ-76-1C | Receiving Station Request for Authorization to Retain Producers' Marketing Cards | 2003-10-31 | <empty> | 2004-01-01 | An electronic submission will be implemented in 2004.
| FSA | 0560-0182 | MQ-78C | Tobacco Receiving Station Registration | 2003-10-31 | <empty> | 2004-01-01 | The electronic submission will be implemented in 2004.
| FSA | 0560-0182 | MQ-79 (CF&B) | Buyer's Record | 2003-10-31 | This transaction is accompanied by remission of funds for deposit | 2004-01-01 | This transaction is accompanied by remission of funds for deposit. However, customers with electronic supporting document(s) can currently transmit them to FSA using the WebCAAF eAuthentication system.
| FSA | 0560-0182 | MQ-80-C | Receiving Station Purchase Day Summary | 2003-10-31 | <empty> | 2004-01-01 | An electronic submission will be implemented.
| FSA | 0560-0183 | CCC-36 | CCC-36 | 2003-03-04 | Security issues w/ multiple signature requirements & associating individuals to an entity. | 2004-01-01 | FSA has almost completed it's development for electronic transactions with multiple signatures. Our first multiple signature applications should be released in early 2004 and will continue into 2006.
| FSA | 0560-0183 | CCC-37 | Joint Payment Authorizations | 2003-03-04 | Security issues w/ multiple signature requirements & associating individuals to an entity. | 2004-01-04 | FSA has almost completed it's development for electronic transactions with multiple signatures. Our first multiple signature applications should be released in early 2004 and will continue into 2006.
| FSA | 0560-0185 | AD-1026B | Highly Edible Land Conservation Exemption Request | 2003-10-04 | <empty> | 2004-05-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0185 | AD-1068 | Good Faith Determination-Highly Erodible Land Conservation Violations | 2003-10-04 | <empty> | 2004-05-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0185 | AD-1069 | Good Faith Determination-Wetland Conservation Violation | 2003-10-04 | <empty> | 2004-05-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0185 | CCC-21 | Supplement to Uniform Storage Agreements Declaration of Eligibility to Receive Storage payments Under a Commodity Credit Corporation Storage Agreement | 2003-10-04 | <empty> | 2004-05-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0185 | FSA-492 | Data Needed for Third Party Determinations | 2003-10-04 | <empty> | 2004-05-01 | Enterprise Architecture migration is currently underway at FSA. Migration started in 2001 and will continue through 2006. In some program areas electronic transactions with FSA's customers depends on the migration date and available funding.
| FSA | 0560-0201 | CCC-1045ELS-2 | Exporter Application for Payment | 2003-10-31 | <empty> | 2004-01-01 | It will be an electronic submission. Also, Customers with electronic supporting document(s) can currently transmit them now to FSA using the WebCAAF eAuthentication system.
| FSA | 0560-0214 | KC-1TQ | Audit Summary | 2003-10-01 | The internet may not be available or accessible from the audit location since connectivity is a problem outside of cities and large towns. | TBD | The data can be emailed to KCCO for processing but requires original signatures on the forms. However, the Internet may not be available or accessible from the audit location since connectivity is a problem outside of cities and large towns.
| FSIS | 0583-0082 | 10,120-1 | Residue Check Sample Results | 2003-10-21 | <empty> | 2004-03-31
| FSIS | 0583-0082 | 6200-18 | Food Chemistry Check Sample Results | 2003-10-21 | <empty> | 2004-03-31
| FSIS | 0583-0092 | 7234-1 | Application for Approval of Labels, Marking or Devices | 2003-10-01 | <empty> | 2004-03-31
| NASS | 0535-0001 |  | Juice Storage Survey | 2003-10-21 | <empty> | 2004-01-26 | The first web survey that will be offered: 1/26/04
| NASS | 0535-0002 |  | Sugarbeets | 2003-10-21 | <empty> | 2004-10-21
| NRCS | 0578-0013 | AD-1155 | Conservation Plan Schedule of Operations | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form (i.e., cost basis, cost share rate, completion schedule, etc). The program participant reviews and agrees to the terms outlined AD-1155 prior to signing the form.
| NRCS | 0578-0013 | AD-1155A | Conservation Plan Schedule of Operations | 2003-10-21 | Must accompany the AD-1155 form | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form, i.e., summary of conservation plan schedule and cost outlays for practices installed using NRCS or CCC funds.
| NRCS | 0578-0013 | AD-1156 | Revision of Plan/Schedule of Operations or Modification of Contract | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form, i.e., revised date, conservation practices, cost outlay, etc. Customer is expected to review and sign.
| NRCS | 0578-0013 | AD-1157 | Option Agreement to Purchase, Amendment 1 | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form. This form is currently on the eForms site with a notation that it is “For Information only”.
| NRCS | 0578-0013 | AD-1157A | Option Agreement to Purchase | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form. Current instructions state (in part) “This form used…to modify the terms of an option agreement to purchase with a landowner (form AD-1157).
| NRCS | 0578-0013 | AD-1158 | Subordination Agreement and Limited Lien Waiver | 2003-10-21 | Court document requires signature to be notarized for legal purposes. Therefore, this interaction will not be GPEA compliant. We will offer an eForm that is available for download via the web. | TBD | NRCS determined that this form could not be GPEA compliant due to its use as a real estate document requiring a notary and/or requires delivery by certified mail. NRCS initiates and provides all information on this form.
| NRCS | 0578-0013 | AD-1160 | Compatible Use Authorization | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form (Including; purpose, “statement of Affect and compatibility, and requires attachment of map showing approximate area of compatible use”).
| NRCS | 0578-0013 | NRCS-LTP-13 | Conservation Program Status Review | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form i.e., progress in applying plan, need for revision to plan, need for technical assistance, etc.
| NRCS | 0578-0013 | NRCS-LTP-152 | Transfer Agreement | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and completes with the customer. Requires the participation of both the old and new program participants.
| NRCS | 0578-0013 | NRCS-LTP-153 | Agreement Covering Non-Compliance with Provisions of the Contract | 2003-10-21 | <empty> | TBD | NRCS has no plans for GPEA compliance at this time. NRCS initiates and provides all information on this form. “By signing this form a program participant agrees that under the identified agreement or contract the participant forfeiture, refund, or payment.
| RUS | 0572-0015 | Non-Form | Reimbursement of Special Equipment Costs | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0015 | Non-Form | Interest Rate Term | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0015 | RUS FORM 595 | Financial Requirement and Expenditure Statement | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0015 | RUS-FORM-219 | Inventory of Work Orders | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0023 | Non-Form | Budget Adjustment | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0023 | Non-Form | Other Information Requested | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0023 | Non-Form | Description of Advances Desired | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0023 | RUS-FORM-481 | 7 CFR Part 1744-C, Advance and Disbursement of Funds - Telecommunications | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0031 | FORM 479 | Financial and Statistical Report for Telecommunications Borrowers | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | AD-1047 | Certification regarding debarment suspension and other responsibility matters - primarily covered transactions | 2003-10-01 | <empty> | 2004-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | FORM 12 | Operating Report | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | FORM 7 | Financial and Statistical Report | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Federal Debt Delinquency Requirements | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Articles of Incorporation and Bylaws | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Construction Work Plan, Related Engineering Studies | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Transmittal Letter | 2003-10-01 | <empty> | 2005-01-21 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Area Coverage and Line Extension Policies | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Uniform Relocation Act | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Certification Regarding Lobbying | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Board Resolution | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Mortgage Information | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | non-form | State Regulatory Approvals | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Power Requirements Study | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Rate Data | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0032 | Non-Form | Pending Litigation | 2003-10-01 | <empty> | 2004-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | Non-Form | Alternative Sources of Power Statement | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0032 | RUS-FORM-266 | Compliance Assurance | 2003-10-01 | <empty> | 2004-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | RUS-FORM-325 | Long Range Financial Forecast | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | RUS-FORM-726 | Borrower Checklist | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | RUS-FORM-740C | Cost Estimates and Loan Budget for Electric Borrowers | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | RUS-FORM-740G | Application for Headquarters Facilities | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | SF-100 | Equal Employment Opportunity Employer Report | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0032 | SF-LLL | Disclosure of Lobbying Activities | 2003-10-01 | <empty> | 2005-01-01 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0041 | Non-Form | Board Resolution | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0041 | Non-Form | Formal Release of Lien | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0041 | Non-Form | Appraisal | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0041 | RUS-FORM-793 | Request for Release of Lien and/or Approval of Sale | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0059 | RUS FORM 158 | Certification of Contract or Force Account Proposal Approval | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0059 | RUS FORM 159 | Summary of Completed Construction | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0059 | RUS FORM 771 | Summary of Work Orders | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0059 | RUS FORM 771a | Summary of Work Orders | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0074 | RUS FORM 675 | Certification of Authority | 2003-10-01 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0079 | Non-Form | Supplementary Information and Toll Settlement Data | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | Non-Form | Prerequisites to release and advance of funds | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | Non-Form | Narrative for Loan Design | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | RUS FORM 507 | Report on Telephone Acquisitions | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | RUS FORM 569 | Area Coverage Survey Report | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | RUS-FORM-490 | Application for Telecommunications Loan or Loan Guarantee | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | RUS-FORM-494 | Loan Design Summary | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0079 | RUS-FORM-495 | Construction Cost Estimates | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Legal Authority and Responsibility | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Transfer and Assumptions | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Proof of Lender Eligibility | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Preguarantee Review | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Construction Contracts | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Bankruptcy Responsibilities | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Loan Servicing/Audited Financial Statements | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Preapplication Development | 2003-10-03 | submit relevant attachments required by regulation | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Disposition of Acquired Property | 2003-10-03 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0122 | Non-Form | Borrower Default | 2003-10-03 | <empty> | 2005-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0122 | Non-Form | Intergovernmental review | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Liquidation | 2003-10-03 | <empty> | 2004-01-31 | The results of a risk assessment combined with additional justification prepared by the responsible business area have led the agency to a determination that an authentication assurance level of 3 is required. Understanding that the USDA eAuthentication solution, WebCAAF, can only support assurance requirements of level 1 and 2, the agency was unable to offer the public an electronic alternative for conducting business by the October 21, 2003 deadline. A project plan and an estimated GPEA compliance date will be provided after an appropriate architecture is defined for the government-wide eAuthentication initiative that reflects the integration of WebCAAF.
| RUS | 0572-0122 | Non-Form | Commitment Cancellation | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0122 | Non-Form | Inspections | 2003-10-03 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Additional Supplementary Information, as needed | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Evidence of Legal Notification | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Business Plan | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Market Survey | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Financial Forecast | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Environmental Report | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | <empty> | Certified System Design | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | Non-Form | Proof of Compliance with other Federal Statutes and Regulations | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | Non-Form | Certification of Availability of Broadband Service | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.
| RUS | 0572-0130 | RUS FORM 532 | Loan Application Form | 2003-10-01 | <empty> | 2004-06-30 | This form is submitted on behalf of an entity (business), by an individual of the entity. There is a need to tie the individual to the entity. A capability to do this is under development and should be available in 2004. Until this capability is implemented, RUS cannot offer an electronic alternative for this transaction.