Archived Information

ATTACHMENT A

U.S. Department of Education

ED Pubs Performance Work Statement

# Table of Contents

- Purpose and General Requirements

- Background

- Scope of Work

  - Tasks

    - Project Management

    - Operate Customer Service Contact Center

    - Provide Receiving, Storage, and Inventory Control

    - Conduct Fulfillment Operations

      - Distribute/Ship Materials for Individual Requests

      - Perform Bulk Distribution

      - Perform Mass Mailings

    - Maintain Mailing Lists

    - Develop and Conduct Enhanced Customer Satisfaction Surveys

    - Provide Promotional Support

    - Conduct Routine and Special Analyses

  - Additional Requirements

3.2.1  Reporting

3.2.2  Technology Security

3.2.3  Safety

3.2.4  Contingencies

3.2.5  Contract Transition

4.0 Quality Assurance/Quality Control

4.1 Government’s QASP

4.2 Contractor’s Quality Control Plan

5.0 Contractor Personnel

5.1 Basic Requirements

5.2 Key Staff Qualifications

5.3 Other Staff Qualifications

Appendix A: Minimum Standards of Performance/ Performance-Based Quality Assurance Surveillance Plan / Service Level Requirements

Appendix B: Government-Furnished Facilities, Equipment, and Services/Contractor-Furnished Property, Services, Equipment, Materials, Tools, and Supplies

Appendix C. Acronyms, Abbreviations, and Definitions

#### Appendix D.  Reporting

U.S. Department of Education

##### ED Pubs Performance Work Statement

1.0 Purpose and General Requirements

The purpose of this contract is to support the information dissemination objectives of Principal Offices throughout the U.S. Department of Education (ED) by providing a customer service center and associated services that include a full range of customer service, warehouse management, contact center, customer information management, Customer Relationship Management (CRM) System, storage, product ordering, database management with tracking and reporting capability, real-time integration, and distribution services.

The work entails four principal areas:

1.	Customer service;

2.	Mail fulfillment (individual, bulk, mass mailings);

3.   Storage; and

4.	Reports.

General work requirements of the contract include, but are not limited to:

(1) Receiving and documenting internal and external customer requests for publications, documents, and other information products by phone (staff and automated systems), TDD, fax, mail, Internet, EDNet, and personal visits.

(2) Referring customers to personnel designated by the COR who need products and services that are beyond the scope of this contract to the appropriate office.

(3) Responding to all requests within specific turn around times (see Quality Assurance Surveillance Plan, Attachment A).

(4) Receiving and storing ED products.

(5) Developing, maintaining, and updating an accurate centralized mailing list system.

(6) Designing, formatting, and preparing an ED publications catalog, both in hard copy and online versions.

(7) Developing, maintaining, and updating the departmental publications database.

(8) Operating unique toll-free phone lines facilitating information referrals and product ordering services.

(9) Developing, maintaining, and updating a customer database.

(10) Providing a full range of fulfillment services, including but not limited to mailing, shipping, faxing, and electronic delivery via Internet and electronic dissemination capabilities.

(11) Measuring customer satisfaction through enhanced user surveys developed, distributed, analyzed, and reported by the Contractor.

(12) Producing and providing documents in Braille, large print, audiotape, computer diskette, or other alternate formats, as-requested.

(13) Providing grant applications to customers.

(14) Providing ongoing operational review, recommendations, and enhancements of all processes.

(15) Developing, hosting, operating, maintaining, and developing enhancements for a separate online ordering system website.

(16) Providing reports; i.e. activity, inventory reports, weekly and monthly, customer profiles, order history, ad hoc activity on an as requested basis; reports on problems if a product has not moved; required daily activity reports on the high volume Bulk Publication Ordering System (BPOS); financial breakout costs for each Principal Office for labor, storage, shipping, and postage; and mandatory Departmental reports; and other financial reports upon request by ED staff.

(17) Operating and maintaining a website for the online ordering and Bulk Publication Ordering.

2.0 Background

Each year, ED creates and distributes hundreds of information products, such as publications, brochures, posters, grant applications, and other information products, which are available at no charge to customers. In addition, various organizations in the department make their products available via fax on demand, electronically via the Internet, as well as on CD-ROM and by other means, such as alternate formats for people with disabilities. Together, these products help define the mission and vision of the Department.

The Education Publications Center [ED Pubs] is a customer care center that focuses on quality control and customer satisfaction as it facilitates referral and distribution services. It is a state-of-the-art information, warehousing, and distribution center that processes phone, fax, Internet, email, print-on-demand, and mail orders for publications and other products. Inclusive audiences are reached through Spanish speaking operators and TDD systems.

Senior management at ED recognizes the need to improve and enhance its dissemination program through the effective implementation of cost-effective technologies that will enable broader outreach to constituent groups without cost increases, and preferably with cost savings. Contractors are encouraged to offer proven, state-of-the-art solutions to achieve ED’s mission of quality and comprehensive information sharing. Strategies should be offered that provide the government “more for less” in terms of increased dissemination options through advanced technology applications.

In this publications environment, ED Principal Offices retain editorial authority and are responsible for funding and printing their own publications. The process operates as follows:

Each Principal Office is responsible for internal clearance and production of a publication through either ED’s Office of Public Affairs (OPA) or the Institute of Educational Sciences (IES).

Prior to publication, the Principal Office initiates a publication distribution order to the COR. The order will include the target release date, a dissemination plan, and any other information that impacts on the distribution of the documents.

The publication is shipped from the printer to the Contractor who manages distribution in accordance with the plan.

3.0 Scope of Work

The Contractor shall be required to provide all of the services and perform all of the tasks described in this section of the Performance Work Statement (PWS).

3.1 Tasks

The Contractor shall perform the following tasks in operating the entire operation of the offsite publications distribution center for the U.S. Department of Education. The Contractor shall be responsible for products upon delivery at its location. The Contractor shall provide the necessary integrated IT infrastructure to meet all contract objectives and to fulfill all tasks and requirements detailed in below. The contractor shall develop and maintain the databases as identified in Appendix B.  The government will not provide databases to the Contractor.  The contractor shall receive data in varying formats for the databases required for operations.  The Contractor will provide the necessary integrated IT infrastructure system for the appropriate work requirement.  The government shall own the data.  The Contractor shall develop the integrated IT infrastructure system with tracking and reporting capability.

The Contractor shall provide al property, services, equipment, materials, tools, databases, customer relationship management (CRM) system, and the necessary integrated IT infrastructure for the appropriate work requirement.

For performance standards, refer to Appendix A to this PWS..

Task 3.1.1: Project Management

The contractor shall provide project management and quality control sufficient to meet the requirements in this SOW and the performance standards detailed in Appendix A.  The Contractor shall provide all property, services, equipment, materials, tools, databases, customer relationship management (CRM) system, and the necessary integrated IT infrastructure system for the appropriate work requirement.  The term “systems” refers to a customized, integrated infrastructure developed and maintained by the new contractor.

ED requires that the contractor make available the following management information:

Management and Quality Control - e.g., management systems that will provide real-time data on contract operations for contractor and ED staff, track workflow, provide automatic alerts of potential problems, and allow monitoring of work performance and instant quality control checks and reports.

Financial Control and Billing - e.g., automated tools for tracking individual labor, storage, shipping, and postage costs, by each of ED’s Principal Offices, and provide real-time information on the status of each individual, bulk, and mass mailing request.

Databases – e.g. real-time access to inventory data, concept searching, word stemming, and relevancy ranking, interfacing databases, order history, financial breakout costs, track workflow, mailing lists, customer profiles, etc.

The Contractor shall also have e-mail capability to correspond with the COR and various Principal Office representatives within ED.

The contractor shall monitor, assess, and recommend emerging leading-edge technology methodologies that can be applied to operations to reduce costs, enhance customer service, and/or streamline processes and procedures.

### Task 3.1.2: Operate Customer Service Contact Center

The contractor shall ensure optimum customer contact through a variety of media (telephone, e-mail, fax, letter) and provide fast, cost-efficient response to customer requests that meets the performance standards in Appendix A.

The Contractor shall provide toll free telephone service to receive requests for information and customer service complaints, and refer requests for publications from customers and departmental staff. This contact center will serve as the Contractor’s primary point of contact for all incoming calls. The personnel at the contact center shall be familiar with the contractor’s standard operating procedures for performing work under this contract.

The Contractor shall operate unique inbound toll free lines, each requiring customized scripts and prompts that must be delivered in both English and Spanish. A TDD service line shall also be available.

The new contractor shall provide unique services for the following toll-free lines:

- ED Pubs toll-free line for general ordering

- BPOS toll-free line for financial aid administrators with questions regarding BPOS

- Safe and Drug Free toll-free line for product ordering and referrals

- National Library of Education (NLE) toll-free line for product ordering and research referrals to the NLE help desk

- National Institute for Literacy (NIFL) toll-free line for product orders and referrals to literacy service providers in the callers’ locality utilizing the America’s Literacy Database (ALD).

Toll free telephone lines shall be operational on normal Government workdays, between the hours of 9:00 a.m. and 6:00 p.m. local Eastern Standard or Daylight Time.  The Contractor shall provide automated telephone answering capability for voice and TDD inquiries after normal working hours, on weekends, and holidays. During business hours, calls shall be answered by a live operator. (Initial prompts may be used to direct calls to English or Spanish speaking customer service staff or to capture specific customer information such as ZIP Codes or account numbers.) The Contractor may use an automated voice mail system during regular hours of operation as long as the customer reaches a customer service representative within 18 seconds.  The Contractor may use a prompt call choice for customers placing orders and a prompt call choice for speaking to a live operator within the required time. The Contractor shall provide an appropriate number of customer service representatives with proficiency in the Spanish language (speaking, reading, and writing) to meet the performance requirements of Appendix A. Staff with other language proficiency is desired.

The Contractor shall use a variety of tools to respond to inquiries, including the publications database and other systems developed to support contract operations.

If the Contractor does not have specific information requested by the customer, the Contractor shall use the ERIC database and/or other Web resources to help the customer locate information or identify the appropriate referral contact.  ED Pubs customers typically request products or need referral assistance.  The government will provide the appropriate ED referral and special promotion assistance, and training on the Educational Resource information Center CD ROM publications database to the Contractor.

The Literacy Hotline service supported by ED Pubs for NIFL requires dedicated, well-trained staff empowered to make knowledgeable decisions.  The staff must be supported by a state-of-the-art telephone system and off-hours interactive voice response (IVR) technology.  To serve customers well, staff must have access to an up-to-date database, in-depth training, competent scripts, and flexible staffing to manage peak period during national literacy campaigns.

The new contractor shall provide the following services to the NIFL hotline:

- Provide a toll-free line to U.S. citizens that information specialists will use to answer questions and assist callers by providing information verbally and/or providing printed materials during normal business hours.

- Match callers with program and technical assistance providers in their local communities using a national database of literacy and adult education providers and programs.

- Serve as a single source for the location for literacy and adult education information and materials not generally found through other sources.

- Provide callers with direct transfer to literacy and adult education referrals, the ability to place publication orders, or the ability to leave messages through an after-hours IVR service.

- Maintain an up-to-date repository of information on literacy providers and adult education information.

- Maintain a copy of the America’s Literacy Database, resource database, for purpose of referrals and updating and adding new records. (The ALD master is maintained by a NIFL contractor.  The ED Pubs contractor will receive and send updated ALD copies from the NIFL contractor in order to maintain accurate information.)

For all toll-free lines that are maintained, the Contractor must be able to manage unforeseen surges in call and/or order volume that may reach as high as 100 percent greater than the previous month’s daily average. There is a possibility that weekend service may be required on special projects.

The Contractor shall provide all property, services, equipment, materials, tools, databases, customer relationship management (CRM) system, and the necessary integrated IT infrastructure system for the appropriate work requirement.

In addition to responding to requests received via toll free telephone service, the Contractor shall receive and process requests via electronic means and by traditional mail. The Contractor shall host, operate, and maintain the ED Pubs Online Ordering website provided by the government.  The contractor shall also develop, operate, and maintain an online ordering system and databases supporting the website that provides the following:

- Real-time access to inventory data,

- Concept searching,

- Word stemming,

- Relevancy ranking,

- Real-time integration between the ordering site and the CRM system developed and provided by the Contractor, and

- Customer ordering that enables customers to order publications as well as view the status of their current orders, view their order history, and their profile, including both e-mail and physical address.

The Contractor shall receive mail correspondence from customers that covers the same subjects as those encountered on the toll-free telephone service. Daily mail must be opened, sorted, batched, and prepared for order data entry into the Contractor’s CRM automated system.

Task 3.1.3: Provide Receiving, Storage, and Inventory Control

The Contractor shall maintain the entire operation and facilities (i.e. physical warehouse, call center, etc.) with a warehouse management system that allows real time inventory management on all publications and be located within the Greater Washington Metro area identified as a radius of 50 miles of Federal Building 6, ED headquarters.  The Department’s present inventory consists of approximately 6,300 unique titles and includes publications, CD-ROMs, audiovisual tapes, posters, pamphlet brochures, grant applications, bookmarks and press releases. The Contractor shall be responsible for developing and providing the information required to maintain a publication database based on this inventory through a collaborative effort with ED. The database shall interact with the various functions of ED Pubs. The databases must interface so that information can be easily accessed by ED employees and compiled into report formats in real-time.

Poster will not likely be received in poster tubes.  Some received posters will be folded and some other posters will be received flat.  The Department of Education will determine if the posters will be shipped folded or non-folded.

The Contractor shall have the capability to track, store, retrieve and manage large quantities of materials through automated mechanisms and provide real-time inventory data and reports to ED staff. The Contractor shall maintain an industry standard perpetual inventory system meeting the accuracy requirements outlined in Appendix A.

The Contractor shall develop recommended reorder points as defined in Appendix A for all demand stock items and establish automated re-order points with appropriate lead times, and inform the appropriate ED Pubs Representative of the need to replenish stock to ensure that all adequate stock is on hand to meet identified requirements.

Only designated ED staff may contract the appropriate ED Pubs’ staff for specific assistance regarding inventory, receiving, ordering, and shipping requests.  The government will provide a list of designated ED staff and their approved interaction with the Contractor.  The contractor should expect the ED Pubs COR to visit the physical facility.

The Contractor shall receive all information from GPO or outside printing contractors, store all publications, and provide adequate protection. The facility shall have sufficient loading/unloading access to meet GPO and postal service shipping requirements, including forklift mechanisms for various sizes of pallets. The Contractor shall have the capacity to manage an appropriate number of inbound and outbound tractor-trailers at the facility on a daily basis.

Warehousing facilities and environmental conditions shall be appropriate to maintain all stock in good condition.

The contractor shall accommodate peak seasons as well as sudden surges in non-peak seasons in receiving, storage, and inventory control.  During the current contract, approximately 100,000 square feet to 130,000 square feet was required during peak seasons.  However, past history may not accurately represent future activity.

Task 3.1.4: Conduct Fulfillment Operations

The contractor shall distribute products to satisfy individual requests, bulk distribution, and mass mailings. The contractor shall track the status each order or request electronically and ensure accurate, timely, cost-effective distribution of materials to customers in conformance with the performance standards in Appendix A.  Product types shipped in mass mailing vary but will fall within the product categories listed in 6.3 Schedule B Pricing section.  Such products listed are brochures, flyers, lanyards, pencils, videos, inserts, press releases, kits, etc.

Distribution of materials shall include such activities as packaging, metering, electronic dissemination, kit building, fax capabilities, print on demand, and other capabilities that will provide expedited, accurate materials handling and delivery.

The Contractor shall produce or arrange for the production and distribution of publications and other education materials in Braille, large print, audiotape, computer diskette, or other alternate formats on an as-requested basis. In consultation with the COR, the Contractor shall establish a relationship with, and develop alternate format policy in conjunction with the Department’s Alternate Format Center, Section 504 Coordinator, and Section 508 Coordinator to ensure that alternate format requests are handled in the most expeditious manner. As appropriate, the Government will provide the Contractor with documents in standard formats such as ASCII text, Word Perfect, Microsoft Word, or other standard text formats for their production in alternate formats.

The Contractor shall actively participate in dissemination planning activities with ED and provide expert recommendations on increasing electronic dissemination of education products.

Rush Service. The Contractor shall have the ability to provide fulfillment operations on a rush basis (within one (1) business day of the request) at the request of the COR.

Messenger Service. Due to the need for frequent communication, transmittal of materials between the various ED components, and emergency requests for rush shipments to training and conference sites, the Contractor shall provide daily messenger service to all 10 ED offices within the metropolitan DC area and delivery capability through the most cost efficient process. On occasion, the Contractor may be required to conduct more than one messenger trip per day. The number of offices and buildings may vary throughout the life of the contract.

### Task 3.1.4.1: Distribute/Ship Materials for Individual Requests

The Contractor shall ship and distribute individual educational information/products upon request in the most effective manner for the government, considering both cost and delivery time.

ED reserves the right to limit the number of copies distributed per individual order. This number will be identified on a case-by-case basis.  The contractor shall have the capability to identify limited release items in its picking process. Only the COR can release additional quantities.

The contractor shall furnish appropriate levels of packaging material inventory and have appropriate tracking abilities to meet the performance standards in Appendix A.

Because of the large numbers to be handled annually, the Contractor shall use proper handling and delivery techniques for this function to ensure rapid turnaround, accurate delivery, and lowest possible mailing costs.

The Contractor shall maintain an appropriate administrative arrangement to provide mail handling statistics and penalty indicia accountability for all official government items.

The Contractor shall actively support ED’s desire to increase electronic dissemination as a percentage of overall outreach activities. The Contractor shall directly and strongly encourage requestors to access Web-based versions of publications, where available. The Contractor shall offer education information products, particularly short publications, by fax. To limit storage requirements, the Contractor shall provide print on demand capabilities; however, the government will create and provide the content. The contractor shall report quarterly the percentage of requests satisfied by electronic dissemination of publications and forms.

The contractor shall provide a variety of print on demand binding and production formats. Typical products conducive to print on demand are products in low demand and/or unanticipated exhausted inventory for time-sensitive products requiring customer response such as grant applications.  The Department of Education office requesting this service will meet with the COR, identify the product involved, select the type of binding and production format, and agree on the cost before the contractor proceeds.  Offerors shall provide samples of print on demand.

### Task 3.1.4.2: Perform Bulk Distribution

The Contractor shall process the bulk distribution of materials as requested by COR or POC designee, or in response to orders received from external customers by telephone, fax, or other means. A single order processed by the Contractor may include bulk quantities of up to 75,000 copies of publications.

It is estimated that the Contractor may distribute up to as many as 15 million documents (during peak periods) in bulk mailings per month.  Most of these peak period mailings will be handled through the Bulk Publication Ordering [web site] (BPOS), which is a Web site which last year supported more than 125,000 annual orders with a fulfillment requirement reaching 50 million copies of various Federal Student Aid documents. The peak volume for this work occurs in the months of October through January when 75% of the orders are filled.

The government will furnish the Bulk Publication Ordering System website. The contractor will manage integrated databases containing the government’s data that the contractor has developed as well as the contractor’s integrated IT infrastructure system with tracking and reporting capability for operation of each appropriate task. The Contractor shall manage the customized ED Pubs Online Ordering (BPOS) website and provide an integrated IT infrastructure system with tracking and reporting capability for operation of each appropriate task.  The Contractor shall provide the automated system for customer support and manual entry for schools that have had difficulty placing an order, or who are experiencing delivery problems.

The contractor shall provide tools that will support ED’s integrated process for online ordering of bulk federal student aid materials (BPOS), including providing full-cycle, self-service online commerce support, continuous updating of product information, real-time status of publication availability, automated tracking of BPOS materials from storage to customer, etc.

The Contractor shall provide the integrated infrastructure containing the government’s data and provide support to this highly customized, tailored order processing website based on specific Financial Student Assistance requirements such as geographical location, customer classification, product availabilities, and other parameters.  This website often requires customized attention from the contractor.

Because of the large number of documents handled, the Contractor shall use large volume handling and delivery techniques to support ED’s bulk distribution requirements and to ensure rapid turnaround, accurate delivery, and lowest possible costs.

The Contractor shall have the capability for preparing conference materials, kits, and handouts for insertion in a wide variety of packaging and formats; i.e. binders of varying sizes and mailers. The number of items and size of items in each kit will vary.  The size of kits will vary such that some could be inserted into envelopes while other may require cartons.   The Contractor shall have the capability to perform “matching jobs”, where the inserts and products require an exact matching order, processing the conference orders, packing, and shipping to and from conference sites.  The Contractor is not required to create departmental materials except for promotional products as described in Task 3.1.7.

The contractor shall not be required to personally attend conferences on behalf of ED but only to provide processing, packing and shipping of conference orders.

The Contractor may handle up to five hundred (500) special bulk material delivery shipments per month for workshop and conference sites.  Typically, the fall and spring are the busiest times for workshop and conference work although major media promotions, and/or departmental sponsored special events may cause unexpected volume of conference and/or workshop activity.

The ED reserves the right to limit the number of copies distributed per individual order. This number may be set in advance for each publication type.

When the Contractor or ED staff identify delivery problems based on calls received, the Contractor shall place and ship expedited orders using the fastest and most reliable mode of shipment available. The Contractor shall respond to these urgent requests within one day of the receipt of the request.

### Task 3.1.4.3: Perform Mass Mailings

The Contractor shall develop procedures for regular mailings of single or multiple materials to ED mailing lists. These mailings will be initiated by ED offices, as opposed to requests received by the Contractor by telephone or other means from members of the public. The Contractor shall have the capability to generate address labels from diskettes that ED provides, or to print the address directly on the envelopes or mailers. The Contractor shall have the capability of folding or otherwise preparing materials for insertion in a wide variety of envelops and mailers. The contents of these mailings range from one-page letters to 1,000 page handbooks that are boxed by the printer. In the past, the number of pieces per mailing have ranged from a low of 25 to a high of 260,000. The Contractor shall have the capability to perform occasional “matching jobs”, where a printout or label specific to the addressee has to be placed in an envelope that has the correct address for that packet.

The Contractor shall process ED requests to perform broadcast e-mails as well as manage any resulting correspondence. The Contractor shall also provide comprehensive quarterly reports that detail the success and failure rates of these communications.

The Contractor shall provide real time Web-based reporting on the status of each mass mailing.

Task 3.1.5: Maintain Mailing Lists

The Contractor shall host, operate, and maintain a centralized mail list management system that stores more than 250 mail lists containing more than 800,000 records. At a minimum, the mail list management system must satisfy the following requirements:

a.	The Contractor must update all records at least twice a year through United States Postal change of address data files.

b.	The Contractor shall ensure duplicates on mailing lists are identified and eliminated from all mailing lists at the time they are submitted to ED Pubs and again prior to being used to perform a mass or bulk mailing.

c.	The Contractor shall create, update, and maintain mailing lists from historical distribution records for a specific product or products.

d.	The Contractor shall provide, at the request of the Department, all or part of any mailing lists that can be downloaded for ED staff

evaluation and analysis.

e.	The Contractor shall provide a detailed listing of all mailing lists to ED staff.

- The Contractor shall establish registered user lists that will allow for more effective targeting of interest groups and ensure that only people who state their desire to be on ED’s mailing list will receive notices/products.

- The contractor shall provide the capability to import data from external mailing lists, sort mailing lists multiple ways, e.g., zip codes.

The Contractor will develop a mail list management system from the government-owned ED Pubs master Mail List Data.  The Contractor shall provide the capability to manipulate, format, and import data from external mailing using various formats.

The Government will provide information to update the mailing lists to the Contractor either in electronic (i.e. e-mail, or disk) or hard copy (i.e. postcards, business cards, handwritten lists) format.

In addition, the Contractor shall purchase outside mailing lists and expand ED’s mailing list based on dissemination needs that are expressed by POC liaisons and the COR. The Contractor shall perform mail merges, which allow for individualized personalization of both physical and electronic mass mailings.

The Government retains ownership of all mailing lists and controls their dissemination.

The Contractor must provide secure backup of all government furnished data and a Department of Education approved security contingency plan.

Task 3.1.6: Develop and Conduct Customer Satisfaction Surveys

To increase the effectiveness and utility of all ED products and services to researchers, practitioners, and the public, the Contractor shall perform telephone, hard copy and electronic surveys of customers regarding service and product satisfaction and impact.

The contractor shall transmit the existing ED Pubs Customer Satisfaction Survey with every tenth order. The Ed Pubs Customer Satisfaction Survey is an OMB approved survey.  Although there are no current plans for publishing a hard copy of the ED Pubs Customer Satisfaction Survey in other languages, the requirement to perform telephone, hard copy, and electronic surveys of customers regarding service and product satisfaction and impact may include other languages in the future. Workload data for telephone surveys are not available.  The Contractor’s proposal shall contain their approach for compiling the results of this survey (which has an historical return rate of approximately 28%), including  analysis and formatting for Department of Education use.

In addition, the Contractor shall determine results through enhanced user surveys to obtain such information as customer satisfaction with the service and quality of the document. Enhanced Customer User Surveys are different than the Customer Satisfaction Survey.  An example of the current survey and feedback format is on the RFP web site.  A possible enhanced survey might query the customer in more detail on how they use the product, what type of audiences receive the products, what type of products they need, etc.  Each enhanced survey will be a customized survey based upon the needs of a specific office.  The ability to produced enhanced user surveys in alternate languages is desirable, but not required.  There are no current plans to produce non-English language surveys.

The Contractor shall provide the capability to design, format, and develop the content provided by the government.  Survey instruments shall be reviewed and approved by the COR.  Office of Management and Budget (OMB) clearance for new survey instruments will most likely be necessary. It is the responsibility of the Contractor to have a working knowledge of the OMB clearance process and to prepare all documents necessary to obtain such clearance in a timely fashion. In addition, the Contractor will conduct routine and special analyses on ED Pubs activities with short turnaround times.

Users of alternate format documents shall be included in these surveys and the Contractor shall provide alternate formats as required.  Alternate formats include producing and providing documents in Braille, large print, audiotape, computer diskette, or other alternate formats as requested.

The Contractor shall provide the capability to design enhanced surveys for a variety of audiences based upon Department of Education requirements and provide marketing analysis for a variety of products.  The types of ED Pubs customers include the following:  parents, business organizations, community organizations, classroom teachers, college professors, ED staff, legislators, principals, students, government staff/not ED, reporters, health-care providers, Head-Start and other early childhood providers, and journalists.

All reports reflecting user feedback and every complaint (written or verbal), complement, or suggestion shall be provided monthly to the COR. The Contractor shall also provide a brief note explaining how each complaint was resolved by the contractor. The Contractor shall group comments and complaints by POC. All completed submissions of the ED Pubs Customer Satisfaction Surveys shall be provided monthly to the COR. The Contractor’s proposal shall reflect their approach to such feedback.

Task 3.1.7: Provide Promotional Support

The Contractor shall design, format and develop ED publications/information products hardcopy and online catalogs utilizing information maintained in the publications database and complying with ED’s web style sheets.  The Contractor shall have the capability to scan documents to produce product images for the online ordering website. The Contractor shall update the online version continuously as new products become available and remove products as requested by ED.  The contractor’s proposal shall reflect their approach to providing an online ordering capability.

Upon request by the COR, the Contractor shall design, format, and develop information promotional materials to assist the Office of Management in educating Principal Offices on capability of services provided by ED Pubs.  All requests for promotional activities will be reviewed and approved by the COR prior to involving the contractor.  This support shall not be limited to but include such information products as such as publication catalogs, mini catalogs, flyers, tent cards, Rolodex card, and other informational guides. The COR shall approve the materials before production and dissemination.

At the request of the COR, the contractor shall be required to conduct promotional activities regarding ED products and ED Pubs.  Such activities shall include but are not limited to designing promotional surveys, analyzing promotional mailing results, and suggesting promotional activities for COR consideration.  At the request of the COR, the Contractor shall provide informational briefings on its services. A promotional survey is a survey not yet developed that measures a specific initiative the Department may be promoting.  The survey would measure the effectiveness of the initiative and accompanying materials in addition to assisting the Department with funding and other decisions.

### Task 3.1.8: Conduct Routine and Special Analyses

The Contractor shall conduct routine and special analyses on ED Pubs activities as requested by the COR. These analyses may include, but are not limited to the following:

( Cost Estimates

( Product(s) dissemination histories

( Customer profiling

( Dissemination trends

( Quality of service

The Contractor must provide Web-based access to ED Pubs workload data and costs to the COR.

3.2 Additional Requirements

3.2.1 Reporting

The Contractor shall submit all reports identified in Appendix D. In addition, the Contractor shall produce and submit ad hoc reports at the request of the COR.

The warehouse and customer service center management system shall store and maintain costs (if applicable) and transactional data on all dissemination activities. The system shall be capable of generating pre-formatted and ad hoc reports.

This system shall contain but not be limited to the following information regarding each transaction:

- Date received (day, month, year);

- Mode of receipt (letter, telephone, etc);

- Source of request (individual, school, superintendent, principal, ED staff, Congress, other Federal agencies)

- Method of distribution (regular mail, express mail)

- Publication requested (by code)

- Number of copies by publication,

- Date mailed (day, month, year)

- Name of person placing the order

- Source of how the requestor became aware of the product (i.e. magazine, newspaper)

- Information requested by alternate format and what type of format was delivered

- Customer type (i.e. parent, teacher, administrator, business, etc)

- Referrals to internal offices and external organizations

- Estimated cost of each line of inventory

3.2.2	Technology Security

The Contractor shall develop an Information Technology (IT) Project Plan, which will be reviewed by ED and the Technical Review Board (TRB) of ED’s Office of the Chief Information Officer (OCIO), to ensure that the IT Project Plan conforms to ED standards. The plan shall address accessibility for people with disabilities, technical profile documentation, security, privacy, and records management and acknowledge compliance with all ED information systems policies, including but not limited to the following:

U.S. Department of Education Product Support Plan

U.S. Department of Education Handbook for Information Technology Security Policy (ACS OCIO-1)

U.S. Department Requirements for Accessible Software Design

Section 508 of the Rehabilitation Act of 1973, as amended, 29 U.S.C. 794 Electronic and information technology and the federal accessibility standard

Electronic and Information Technology Accessibility Standards, Architectural and Transportation Barriers Compliance Board [published in the Federal Register on December 21,2000] 36 CFR Part 1194 [Docket No. 2000-01], RIN 3014-AA25.

3.2.3 Safety

The Contractor shall comply with all applicable safety and occupational health requirements set forth in 29 CFR 1910, OSHA’s General Industry Standards. If the Contractor fails or refuses to promptly comply with safety requirements, the CO may issue an order stopping all or part of the work until satisfactory corrective action has been taken by the Contractor.

The Contractor shall inform the COR via phone of any unsafe/hazardous conditions within thirty (30) minutes of becoming aware of the condition, and in writing within one (1) workday. If the condition is within the scope of the Contractor’s responsibility, as contained in this PWS, the Contractor shall correct the unsafe condition and notify the COR and CO.

The Contractor shall orally inform the COR within two (2) business hours of the occurrence of all types of injuries and illnesses (first aid, limited duty, lost items and facility) sustained by a Contractor employee arising out of and in the course of his/her employment; a detailed written report is required within 24 hours to the CO. The Contractor shall comply with OSHA and other regulatory agency requirements for record keeping and reporting of all accidents.

The Contractor shall report to the COR and CO all incidents where Contractor employees damage Government property. A verbal report shall be made within four (4) business hours of an occurrence; a written report of the facts and extent of damage is due within three (3) workdays. The Contractor shall be responsible for all damages caused purposively or by negligence of its employees.

The Contractor shall meet and maintain compliance with OMB Circular A-130, Appendix III, “Security of Federal Automated Information Resources,” and the U.S. Department of Education’s Certification and accreditation program requirements.

3.2.4 Contingencies

In the event of a national disaster or major disruption at ED, the Contractor shall be prepared to continue, and expand if necessary, performance to meet the mission requirements of the operations and maintenance support services included in this PWS. In all such situations, the Contractor shall assume that the Government cannot provide supplemental forces and continue to need the same or additional performance under the contract. In the event that a national disaster or emergency occurs and results in an increase of work directed by the CO and an increase in the cost of performance, such increase will be subject to the “Changes” clause (FAR subpart 52.2). Such emergency situations may include, but will not be limited to:

A national or local emergency (i.e. national terrorist attack, epidemic or localized outbreak of disease) that increases contract requirements.

A national disaster (i.e. fire, flood, terrorist attack, weather [OIIA] acts of God) that impacts upon the Contractor’s ability to perform.

In the technical proposal, Offerors shall include an emergency/disaster contingency plan that describes procedures for responding to the above-cited emergency situations. The plan shall describe an alternate facility that will be used in the event the main facility is unavailable to ensure continuity of service.

Within 60 days following contract award, the Contractor shall formally submit an emergency/disaster contingency plan for COR review and approval. Each year, the COR shall review the plan to verify the Contractor’s capability to provide an alternate facility in cases of emergency.

The Contractor shall develop a strike contingency plan for the continuation of services required by this PWS in the event of a work stoppage, slowdown, or similar action by Contractor or subcontractor employees. Any strike will not involve any government personnel.  The Contractor’s plan shall also provide for the continuation of subcontractor services in the event a subcontractor is unable to satisfactorily implement his strike contingency plan. All proposed changes to this strike contingency plan shall be approved by the COR prior to their implementation.

3.2.5 Contract Transition

The Contractor shall provide: (1) a phase-in plan that describes procedures for a smooth transition from the time of contract award to full operational status; and (2) a phase-out plan from current contract performance to performance by a different contractor in a follow-on period. Phase-Out plans shall include provisions for completion of appropriate Contractor responsibilities should there be a contract termination proceeding.

Technical proposals shall include phase-in and phase-out plans, as described below.

Phase-In Plan

The phase-in plan shall address how the Offeror will provide a work force that is fully qualified and capable of performing all work required under this contract upon award. The plan shall also address how the Offeror will set up the ED Pubs facility, secure necessary equipment and resources, assume responsibility and accountability for all Government-furnished property, transfer existing ED Pubs inventory and online catalog without disrupting operations, and work with the COR and OCIO to arrange and install Department of Education-provided FTS 2000 800 numbers.  The Contractor shall pay for the cost of transferring materials to the new site.  The Contractor shall be responsible for setting up the facility, ensuring necessary personnel for transition and assuming all responsibility of materials and government property.

The plan shall include a schedule for performing these phase-in tasks, not to exceed 90 days following contract award.

Phase-Out Plan

The phase-out plan shall present procedures for phasing out contract performance, regardless of precipitating reasons. The plan shall include procedures for retaining the required staffing level (including key personnel) necessary to provide complete contractual support through expiration of the contract and describe how responsibility and accountability will be relinquished for all Government-furnished equipment.  The plan shall also address coordination procedures with the incoming Contractor to effect a smooth and orderly transition at the end of the contract period.

4.0 Quality Assurance/Quality Control

4.1 Government’s Quality Assurance Surveillance Plan

To ensure the highest quality performance, ED has established a performance-based Quality Assurance Surveillance Plan (QASP), which establishes performance standards and methods of measuring the Contractor’s achievement of all contract objectives. ED will monitor, assess, record, and report on the Contractor’s technical performance in accordance with the procedures, methods, and guidelines set forth in its QASP (see Appendix A).

To support ED’s surveillance activities, the Contractor shall provide real-time access for the COR and other designated ED staff to view current and historical transactions and transaction status. All QASP measures must be applied and shown in real time for all transactions. This real-time access shall allow the COR to extract and analyze transaction information for any product over any time period, by any user characteristic (e.g., “requester type”).  “Real-time” refers to contractor’s system reports that document exact system completion times for tasks that can be reflected by such reports.  For example, the Call Center Application Report would reflect a detail report on each call for time of day, calls received, calls answered, calls dispostioned, average delay, service level, in or out of compliance, average talk time, etc. For mailings, the Fulfillment report would reflect a detail report on order number, amount of order, date order received, shipped date, in or out of compliance status.  For QASP measurements that do not lend themselves to real-time reporting, the COR will perform traditional monitoring means.   The contractor’s proposal shall reflect their approach.

In addition, the Contractor shall provide the COR with the capability of monitoring service calls undetected to evaluate the Contractor’s phone service performance.

To ensure adequate communication between the Contractor and ED regarding quality performance issues, the Contractor, its designated Project Director, Project Manager, or both, shall meet with the COR and/or CO at the COR’s request or if deemed necessary by the COR.  The meetings shall be held weekly for the first three months of the contract and biweekly for next three months. Thereafter, meetings shall be held as often as deemed necessary by the COR and/or CO. At these meetings, a mutual effort will be made to resolve any problems identified. Written minutes of these meetings shall be prepared by the Contractor and submitted to ED for approval.

4.2 Contractor’s Quality Control Plan

The Contractor shall establish a performance-based Quality Control Plan to ensure that the minimum standards of performance detailed in the QASP are fully met as specified in Appendix A. Technical proposals shall include a draft quality control plan. An updated copy shall be provided to the COR and the CO on the contract start date and as changes occur. This performance-based Quality Control Plan shall include but not be limited to the following:

An inspection program addressing all the services/tasks stated in the PWS. It must specify the areas to be inspected on either a scheduled or unscheduled basis and the names, titles, and qualifications of the individuals performing inspections and the extent of their authority. Their functional roles must be depicted in an organizational chart.

Methods of identifying deficiencies in the quality of services performed before the level of performance becomes unacceptable and the corrective actions needed to be taken; procedures for notifying the COR when deficiencies are encountered; planned corrective actions and descriptions of proposed sampling techniques. The Contractor is expected to implement a continuous improvement system.

Methods of documenting and enforcing quality control operations of both the Contractor’s and subcontractors’ (if any) work, including inspection and testing.

The format for the Contractor’s Quality Control Reports.

For each option year, the contractor shall include a section on problems it has encountered, solutions implemented, and steps taken to avoid the same problems in the future.

Throughout the term of the contract, the Contractor shall maintain documentation of all Quality Control Inspections, inspection results, and any corrective action required and/or performed. This documentation shall become the property of the Government and made available to both the COR and CO upon request. The documentation shall be turned over to the CO within ten (10) days after completion or termination of the contract.

5.0 Contractor Personnel

The Contractor shall provide staff with the demonstrated experience, education, and qualifications necessary to perform all PWS tasks and to meet the minimum standards of performance described in Appendix A. At minimum, Contractor staff must meet the requirements iterated in 5.1—5.3 below.

5.1 Basic Requirements

Contractor personnel responsible for answering the telephone and dealing with ED employees must be able to clearly speak and easily understand the English language, operate a TDD, and be familiar with and experienced in using the GPO style manual and United States Postal Service (USPS) address conventions.

5.2 Key Staff Qualifications

The Contractor shall provide a project director, project manager, and systems manager as key staff for the contract, or staff positions with comparable qualifications, as follows:

Project Director shall have demonstrated corporate management experience, particularly in the federal government contracting arena; be familiar with the mission and policies of the U.S. Department of Education and the role of this contract in supporting ED’s mission; understand the needs of the Education field, its practitioners and researchers; and possess at least five (5) years of experience in overseeing contracts that entail contact center/distribution functions similar in magnitude to this procurement.

Project Manager shall have a minimum of five (5) years of recent experience in managing a combined contact center and distribution facility of similar size, scope, and complexity; familiarity with the mission and policies of the U.S. Department of Education and the role of this contract in supporting ED’s mission; an understanding of Education policymakers, practitioners, researchers, and others who constitute ED constituents; and shall have technical experience and be knowledgeable in all facets of the work required under the contract. The Project Manager shall provide administration and technical supervision of Contractor employees and shall be the Contractor’s primary representative and have the Contractor’s full authority to act on matters pertaining to the performance of services under this contract

.

Systems Manager shall have a minimum of six (6) years of experience in overseeing the development and maintenance of automated systems to support complex contact center/distribution activities, including technologies and automated tools used to support the functions listed in PWS 3.1. Familiarity with ED’s IT standards and policies is preferred.

5.3 Other Staff Qualifications

The Contractor shall employ staff who have knowledge of call center operations, mail fulfillment, warehousing, and the ability to serve ED employees and customers in a professional and courteous manner. At minimum, the Contractor’s personnel shall possess the following knowledge, skills, and abilities:

Extensive knowledge in the mail fulfillment process, including familiarity with the U.S. Postal Service rules and regulations as well as other delivery services.

Skill in call center operations with focus on customer service.

Knowledge of “best practices” in information dissemination and distribution.

Skill in using databases and key word searches on the computer.

Ability to process orders in an effective and expeditious manner.

Skill in mailing list database management.

Experience in recommending, procuring, and implementing state-of-the-art information technology upgrades.

Appendix A

MINIMUM STANDARDS OF PERFORMANCE/ PERFORMANCE-BASED QUALITY ASSURANCE SURVEILLANCE (QASP) PLAN/ SERVICE LEVEL REQUIREMENTS/

The Government will monitor the Contractor’s performance in accordance with procedures set forth in its QASP (B.1) and will take appropriate action for all documented instances where performance falls below the minimum standards of performance (MSP).  The Contractor shall meet the MSP described below (B.2) in performing the work described in the PWS.  The MSP identifies the point of demarcation between satisfactory and unsatisfactory performance. In addition, the Contractor will meet the lower control limits of the Service Level Requirements (SLR) described in (B.3).

A.1 Performance-Based Quality Assurance Surveillance Plan

INTRODUCTION

This Performance-Based Quality Assurance Surveillance Plan (QASP) has been developed pursuant to the requirements of the Performance Based Statement of Work in this contract. This plan sets forth procedures and guidelines that the Department of Education will use in evaluating the technical performance of the Contractor in Exhibit A. A copy of this plan will be furnished to the Contractor so that it will be aware of the methods that the government will employ in evaluating its performance, and address any concerns that the Contractor might have prior to initiating work. (All percentages indicated shall be quantitatively measured on a quarterly basis.)

PURPOSE OF THE QASP

The QASP is intended to accomplish the following:

● Define the roles and responsibilities of participating Government officials.

● Define the types of work to be performed with required end results, i.e., work orders, preventive maintenance, distribution processes, etc.

● Describe the evaluation methods that will be employed by the Government assessing the Contractor’s performance.

● Provide copies of the quality assurance monitoring forms that will be used by the government in documenting and evaluating the Contractor’s performance.

● Describe the process of performance documentation.

The Contractor must develop a performance based Quality Control Plan that sets forth procedures and responsibilities for controlling high-quality work.  The Contractor must designate employee(s) to be responsible for implementation of the quality control plan.

ROLES AND RESPONSIBILITIES OF PARTICPATING GOVERNMENT OFFICIALS

The following Government Officials will participate in assessing the quality of the Contractor’s performance. Their roles and responsibilities are described as follows:

Judy A. Craig will serve as the Contracting Officer’s Representative (COR). She or her authorized representative will be responsible for monitoring, assessing, recording and reporting on the technical performance of the Contractor on a day-to-day basis. She will have the primary responsibility for measuring and completing the “Quality Assurance Surveillance” report that will be used to document integrated system work, inspection, and evaluation of the Contractor’s work performance. It is extremely important for the COR to establish and maintain a team-oriented line of communication with the contractor’s Project Manager (PM) and the PM’s office staff due to daily interface necessary in performing monitoring functions. The COR will work directly with designated ED Pubs Representatives to help facilitate work requests performed by the Contractor on behalf of the Department of Education. The COR will submit monthly costs for labor, storage, postage, and shipping to PO budget officers.

Mr. Terence Haynes will serve as the Contracting Officer (CO) and have overall responsibility for overseeing the Contractor’s performance. The Contract Specialist (CS) will also be responsible for the day-to-day monitoring of the Contractor’s performance in the areas of contract compliance, contract administration, cost control and property control; reviewing the COR’s assessment of the Contractor’s performance; and resolving all differences between the COR’s version and the Contractor’s version. The CO may appoint CS to attend meetings with Contractor and act on her/his behalf. The CO may call upon the expertise of other government individuals as required. The Contracting Officer’s procurement authorities include the following:

FINAL authority for any decisions which produce an increase or decrease in the scope of the contract.

FINAL authority for any actions subject to the “Changes” clause.

FINAL authority for any decisions to be rendered under the “Disputes” clause.

FINAL authority to approve the substitution or replacement of the Project Manager and other key personnel.

FINAL authority to approve the Contractor’s invoices for payment, subject to the Limitation of Costs clause and the Limitation of Funds clause.

FINAL authority to approve the GFE/GFP inventory turnover to the Contractor.

FINAL authority to monitor and enforce Department of Labor-promulgated labor requirements.

FINAL authority to administer all property-related clauses contained in the contract.

Authority to arrange for and supervise QA activities under this contract.

FINAL authority to approve the Contractor’s Quality Control Plan, preventive maintenance program, emergency/disaster contingency plan, strike contingency plan, and phase-in/phase-out plan.

FINAL authority to approve significant subcontracts for work completed on this contract.

Signatory authority for the issuance of all modifications to the contract.

IDENTIFICATION OF THE TYPES OF WORK TO BE PERFORMED

This contract calls for the Contractor to provide publications distribution/warehousing support services for the U.S. Department of Education. The work to be performed under the contract falls into the categories listed below:

Distribution/shipping-individual orders

Bulk and mass distribution

Inventory Accuracy

Customer service/contact center

Order Filling/database maintenance/marketing

Mailing list maintenance

Enhanced user surveys

Receiving Storage Inventory Control

Fax on Demand/Print on Demand

Scanning documents

Ad hoc reports on distribution and costs association for individual products

Electronic Dissemination

Intranet/Internet Web work

METHODOLOGIES TO BE USED TO MONITOR THE CONTRACTOR’S PERFORMANCE

Even though the Government through its COR will be monitoring the Contractor’s performance on a continuous basis, the sheer volume of tasks performed by the Contractor make 100% technical or manual inspections impractical. Accordingly, the Department of Education will use four methodologies (random sampling, validated complaints from ED employees and outside customers, third party independent audit, and automated systems reports) to monitor the Contractor’s performance under this contract. The use of these methodologies is described in Exhibit A.

QUALITY ASSURANCE REPORTING FORMS

The COR will review and file system reports and use six quality assurance monitoring forms to document and evaluate the contractor’s performance under this contract.

The six forms, when completed, will document the COR’s understanding of Contractor requirements, what was actually done, and the impact or consequences of what was not done.

Tally sheet indicating performance totals for each performance standard for months to be measured and overall percentage total of the QASP.

The COR will evaluate each event in accordance with the following definitions of contractor performance:

- Superior (+)(a level of performance that exceeds the target standards of performance with biannual award incentives to the contractor.

- Acceptable (0)(, an acceptable level of performance that meets the target standards of performance without biannual incentives or deductions to the contractor.

- Unacceptable (-)(, a level of performance that is not acceptable and fails to meet the minimum standards of performance with monetary deductions imposed upon the contractor.

For example, if a standard of performance is weighted 10 percent and the contractor performs at a superior performance level it will receive 10 percent of the incentive award for that time period.  If, on the other hand, the contractor performs at the acceptable level it will receive no incentive award.  Finally, if the contractor performs at an unacceptable level, it will be penalized 10 percent of the incentive award amount.  This calculation would be computed for each performance standard.

The COR must substantiate all tasks that he/she judges to be indicative of “superior” or “unacceptable” performance. Performance at the “Acceptable” level is expected from the Contractor. Performance at all three (3) levels will be evaluated.

The COR will retain a file of system reports, customer complaints, and monitoring forms for audit purposes. The COR will quarterly forward to the COR/CS a completed COR QASP report containing a summary of pertinent actions and observations by the COR and a completed ED PUBS Surveillance Plan Results Report during the surveillance period. The QASP report shall be submitted to the CO/CS within fifteen (15) working days of the next quarter. The Contractor is required to respond in writing to any negative QA monitoring form(s) within five (5) working days after receipt of the form(s).

If a problem is discovered upon audit by COR, the Contractor will respond in writing within five (5) working days the method(s) for correcting the problem.

ANALYSIS OF SURVEILLANCE RESULTS

The CO/CS will review the completed QASP report prepared by the COR. When appropriate, the CO/CS may review all files and reports to determine if the facts and circumstances surrounding the COR QASP Report were considered in the COR’s opinions outlined in the report. The CO/CS will immediately discuss every event receiving a substandard rating with the Contractor to ensure that corrective action is promptly initiated.

INCENTIVES

The Department of Education shall establish performance incentives and deductions.  Incentive fee ranges shall focus on the areas that directly contribute to customer service.  Performance incentives that are included in the contract shall be renegotiated annually to adjust for new processes, advancements in technology, and economic factors.  The Department of Education reserves the right to not raise the range of incentive fees. The attached Inventive Plan provides additional details on available incentives.

A.2	Minimum Standards of Performance

A.2.1 Fulfillment Metrics

A.2.1.1 DISTRIBUTION/SHIPPING-INDIVIDUAL ORDER REQUESTS

The contractor shall ship in-stock items within two (2) business days upon receipt of order 95% of the time.

All orders shall be shipped the most efficient and effective manner. Timeframes for alternate format production and distribution will be determined by COR and Contractor after award.

The Contractor shall provide real-time cost analysis prior to each order being shipped to ensure the most cost efficient method is used.

A.2.1.2 BULK and MASS DISTRIBUTION

The contractor shall ship in-stock items within three (3) business days upon receipt of order 95% of the time when the total number of simultaneous mailings does not exceed 300,000 names or 5 separate lists of requests.

All orders shall be shipped the most efficient and effective manner. Timeframes for alternate format production and distribution will be determined by COR and Contractor after award.

The Contractor shall establish and maintain a Quality Assurance Team for bulk and mass distribution. The Quality Assurance Team shall perform a comprehensive “after-pack” quality check on no less than 10 percent of the total orders shipped each day to ensure the contents correctly match the details of the order.

All shipping labels shall state the product name and quantity so that BPOS clerks can verify a correct product match as the boxes flow down the production lines.

The Contractor shall provide a system real-time cost analysis before each order being shipped to ensure the most cost efficient method is used. The contractor shall provide documentation of cost analysis upon request to the COR.

The Contractor shall provide shipping and/or postage costs to the Department and have the ability to sort these costs in a variety of ways including, but not limited to, breakdowns for individual offices, products, states, date ranges, and customers.

The Contractor shall provide comprehensive shipment/expenditure estimates to the Department within 24 hours upon receiving a shipment request unless the COR grants a waiver.

The Contractor shall provide, upon request by ED staff, professional advice regarding such issues as packaging, to ensure the most cost effective final product. The Contractor shall consider details such as but not limited to size, indicia, color, and texture.

The Contractor shall provide extensive training and quality checking to warehouse personnel to ensure the most appropriate and least expensive package (i.e. envelope, box, jiffy bag, etc.) is used to guarantee a safe and efficient delivery.

The Contractor shall maintain a Web site that is accessible real time to the ED staff for purpose of viewing status of orders, order history and inventory levels.

A.2.1.3 INVENTORY ACCURACY

The Contractor shall maintain an accurate inventory such that the difference between the physical inventory level and the perpetual inventory is within 5%.

A.2.1.4 LINES COMPLETE

[Lines Complete:  The number of survey respondents indicating they received what was ordered.]

The contractor shall ensure that 95% of all orders received during a time period are completed within the same time period.  The COR will specify the time period.  The percentage is calculated as the number of completed orders divided by the total number of orders processed during the specified time period. Backordered items will be excluded from the calculation.

A.2.1.5 Order Filling

The contractor shall process 95% of all orders correctly.  A correct order is an order delivered on time, with the correct product, the correct number of copies requested, and with the correct supporting documentation. The Contractor shall accept and process requests by telephone, fax, letters, Internet, e-mail, etc.

The Contractor shall establish and maintain an automatic e-mail script service to customers whose order is returned to the Contractor.

A.2.2 Customer Service/Contact Center Metrics

A.2.2.1 CUSTOMER COMPLAINTS

No more than .05% (1 per 2,000 customers served) of total quarterly customers will make a complaint concerning contractor performance of the fulfillment process.

A.2.2.2 AVERAGE SPEED TO ANSWER

Customers will not wait longer than an average of eighteen (18) seconds for a customer service representative.  The contractor shall answer all calls in a courteous manner and accurately transcribe the customer’s request into a modern, Web-based warehouse management system.  The Contractor shall provide accurate and useful information on publications to the customer.

A.2.2.3 ABANDON RATE

Less than 4% of customers will abandon calls before being helped by a customer service representative.

### A.3 Service Level Requirements

The Department of Education uses these service level requirements to measure workload outputs.  The contractor will not receive additional monetary incentives for achieving the requirements of the SLR because these requirements are lower control limits.

A.3.1 ADVANCE ORDERS

Advance orders occur when customers place requests for items that are not currently in stock but that are expected to be ready for release in a short period of time. The Contractor shall process advance orders within three (3) days of receiving inventory.

A.3.2 CUSTOMER INQUIRY RESPONSE TIME

The Contractor should respond to all customer inquiries within eight (8) working hours.

A.3.3 MAILING LIST MAINTENANCE

The Contractor shall update the Department of Education’s more than 250 mailing lists containing more than 800,000 records on a continuous basis to attain 98% accuracy.

The Contractor shall maintain a file and a system of noting dates returned, reason for return, and re-mail information.  No more than 2% of all mail outs based upon Contractor’s maintained lists are to be returned as undeliverable. Quality assurance standards apply only to Contractor-maintained mailing lists.

The Contractor shall receive the U.S. Post Office Biannual National Change of Address (NCOA) entries and electronically update the Contractor maintained records and addresses.

The Contractor shall update the system within 24 hours of receipt of information.

The Contractor shall maintain specialized software packages to zip sort each mail list to ensure maximum postal discounts.

The Contractor shall maintain mailing lists from historical distribution records for a specific product or products.

The Contractor shall provide at the request of the Department all or part of mailing lists that can be downloaded for ED staff evaluation and analysis.

The Contractor shall maintain mailing lists separated by POCs on a web site that is accessible to ED staff.

The Contractor shall establish registered users lists that will allow for more effective targeting of interest groups and ensure that only people who state their desire to be on ED’s mailing list will receive notices/products.

The Contractor will request and maintain e-mail addresses from all entities on mailing lists so that future time and costs could be saved when sending announcements or other simple communications to members of a mailing list.

The Contractor shall provide proactive searching for potentially interested individuals or groups that could be added to high-profile mailing lists or used to establish new mailing lists.

A.3.4 ENHANCED USER SURVEY

The contractor shall conduct surveys at a pre-determined schedule jointly agreed to by Contractor and the government for customer service, measuring product satisfaction, impact, courteousness of Contractor staff, and whether the order was filled correctly. Enhanced user surveys are different than the Customer Satisfaction Survey.  The Contractor’s approach should include user satisfaction forms with appropriate products requested on a pre-determined schedule. Surveys will generally be in written format, but occasionally may be taken by telephone or via the Web.  The Contractor shall include individuals with disabilities in these surveys. Returned surveys must have their responses entered into a centralized database, which must be used to perform monthly analysis and reporting of survey responses. Contractor must perform physical and electronic surveying.

A.3.5 DISCREPANCY RESOLUTION

The Contractor will resolve all discrepant shipment by re-shipping within one (1) working day.

A.3.6 EXCESS STOCK NOTIFICATION

The Contractor will notify the PO when a stocked item has not received any demands in the prior eighteen (18) months.

A.3.7 REORDER NOTIFICATION

The Contractor will notify the PO when stock needs to be reordered.  An inventory level equal to one hundred twenty (120) days should be maintained.

A.3.8 INVENTORY MANAGEMENT

The Contractor should recycle products upon request.  Recycling requests shall be complete with five (5) work days.

A.3.9 REPORTING

The Contractor should provide ad hoc reports within three (3) work days of the request.

EXHIBIT A

QUALITY ASSURANCE SURVEILLANCE PLAN

(QASP)

The table below summarizes the minimum standards of performance required.  The weight for each standard will be used to determine incentive awards as described in section B.1.  More detailed descriptions for each standard are provided below the table.

| Minimum Standards of Performance and Associated Weights |
| --- |
| Standard | Definition | Weight | Target | Reporting Frequency |
| Fulfillment Metrics |
| 1. Distribution of individual requests | Requests for 1-5 titles/pieces with a maximum of 5 pieces | 5% | 95% of all individual orders are shipped within 2 business days | Monthly |
| 2. Bulk Shipments | Requests for 6 or more titles/pieces | 5% | 95% of all orders are shipped within 3 business days | Monthly |
| 3. Mass Distribution | Shipments from a mailing list | 5% | 95% of all mass mailings are shipped within 3 business days | Daily |
| 4. Inventory accuracy | Difference between physical inventory and perpetual inventory | 10% | Inventory differences are within 5% | Weekly |
| 5. Lines Complete | The number of survey respondents indicating they received what was ordered | 5% | 95% of survey respondents indicate they received complete orders, excluding back orders | Monthly |
| 6. Order fulfillment | The number of orders filled correctly, with supporting documentation, and on time divided by the total orders processed | 25% | 95% of all orders are processed correctly | Monthly |
| Customer Service/ Contact Center Metrics |
| 7. Customer Complaints | Number of customer complaints regarding contractor performance. | 10% | Less than .05% of total customers make a complaint | Monthly |
| 8. Average Speed to Answer (ASA) | Also called Average Delay. The average delay of all calls. It is total Delay divided by total number of calls. | 20% | The average call is answered within 18 seconds | Real time |
| 9. Abandon Rate | The caller hangs up before reaching an agent. | 15% | Less than 4% of callers hang up before reaching an agent | Real time |
| Total |  | 100% |  |  |

1. DISTRIBUTION/SHIPPING-INDIVIDUAL ORDER REQUESTS

Contract Requirement:  Section 3.1.4.1 of SOW

Performance Indicator:  The Contractor shall be responsible for shipping all in-stock items.  Orders shall be shipped in the most efficient manner.  The Contractor shall ship 95% of all single/individual orders within 2 business days.  A single/individual order is defined as requests for 1-5 titles/pieces with a maximum of 5 pieces.

Primary Method of Surveillance:  The COR will use two (2) methods of measurement:  1) Order Turnaround Reports (weight of 80% of this task) and 2) Random Sampling of work in progress on conveyor (weight of 20% of this task).  Random sampling of packages shall be performed on each day of audit.  Packages, envelopes, poster tubes, videos and CD-ROMs from the conveyer belt and reviewed for compliance regarding shipping within 2 business days and accuracy of the order being filled.  In all cases, sampled orders contained 1-5 products for this task.

Measured Standard of Performance (MSP):

Target standard:  95% of all single/individual orders within 2 business days.

Weight measurement:  5%.

Level of Surveillance:

The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size:  10

Sampling Procedures: The COR shall select at random a variety of packages from the conveyor belt and review for accuracy.  A variety of packages shall include flat packages, tubes, kits, flyers, publications, thick packages, large and small boxes, and flat package/poster containers.

Evaluation Procedures:  The COR shall review reports extracted from the inventory system and open various sizes of packages from the conveyor belt.  The order number, type of order, task required, clerk initials, order correctness or error shall be noted.

Analysis of Results:  The COR will compute the compliance percentages from the Order Turnaround reports and random samplings.  The percentage that will be used to determine incentive awards will be a computation of the report and sampling percentages as defined above.

2. BULK DISTRIBUTION

Contract Requirement:  Section 3.1.4.2 of SOW

Performance Indicator:  The Contractor shall be required to perform bulk and mass distribution of products.  Items shall be shipped in the most cost efficient manner.  A bulk shipment is defined as requests for 6 or more titles/pieces.  A bulk shipment shall be shipped within 3 business days.

Primary Method of Surveillance:  The COR shall review reports extracted from the ED Pubs Fulfillment System and opening sealed boxes ready for shipping.  After opening the boxes, the contents shall be inspected for quality and checked against the shipment address, the mailing number, number of items in each box, number of correct items, and the quality rate.

Measured Standard of Performance (MSP):

Target standard: 95% of all bulk orders are shipped within (3) business days.

Weight measurement:  5%.

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size:  10

Sampling Procedures:  The COR shall select random sampling of packages on each day of audits.  Packages, envelopes, and posters that contain more than 6 products from the conveyor belt shall be reviewed for compliance regarding shipping within 3 business days and overall accuracy of the order being filled.  In all cases, sampled orders shall contain 6 or more products for this task.

Evaluation Procedures:  The COR shall review reports extracted from the inventory system and open various sizes of packages from the conveyor belt.  The order number, type of order, task required, clerk initials, order correctness or error shall be noted.

Analysis of Results:  The COR will compute the compliance percentages from the Order Turnaround reports and random samplings.  The percentage that will be used to determine incentive awards will be a computation of the report and sampling percentages as defined above.

3. MASS DISTRIBUTION

Contract Requirement:  Section 3.1.4.3 of SOW

Performance Indicator: The Contractor shall be required to perform bulk and mass distribution of products.  Items shall be shipped in the most cost efficient manner.  A mass shipment is defined as shipments from a mailing list.  All mass mailing requests shall be shipped within 3 business days when the total of simultaneous mailings do not exceed 300,000 names or 5 separate lists.

Primary Method of Surveillance: The COR will use two (2) methods of measurement:  1) Order Turnaround Reports (weight of 80% of this task) and 2) Random Sampling of work in progress on conveyor (weight of 20% of this task).  Random sampling of packages shall be performed on each day of audit.  Packages, envelopes, poster tubes, videos and CD-ROMs from the conveyer belt will be reviewed for compliance regarding shipping within 3 business days and accuracy of the order being filled.

The COR shall review reports extracted from the Order Turnaround Reports and opening sealed boxes ready for shipping.  After opening the boxes, the contents shall be inspected for quality and checked against the mass shipping request, shipment address, the mailing number, number of items in each box, number of correct items, and the quality rate.

Measured Standard of Performance (MSP):

Target standard: 95% of all mass mailings are shipped within 3 business days.

Weight measurement:  5%.

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size:  10

Sampling Procedures:  The COR shall review mass mailing requests from the system reports and select mass mailing requests and mass mailings in progress, on conveyor belts, and in carrier trucks.

Evaluation Procedures:  The COR shall open sealed pallets, counting boxes, inspect contents against shipping order and inspecting address.  The order number, type of order, task required, clerk initials, order correctness or error shall be noted.

Analysis of Results:  The COR will compute the compliance percentages from the Order Turnaround reports and random samplings.  The percentage that will be used to determine incentive awards will be a computation of the report and sampling percentages as defined above.

4. INVENTORY ACCURACY

Contract Requirement:  Section 3.1.4 of SOW

Performance Indicator:  All incoming products shall be received and logged into an inventory control system within 8 business hours of receipt.  The Contractor shall maintain an accurate inventory such that the difference between the physical inventory level and the perpetual inventory is within 5%.  The Contractor shall complete recycle requests from the government within 5 business days.  The Contractor shall resolve discrepant shipments by reshipping within 1 business day.  The Contractor shall notify the PO when stock activity reports reflect no demands within 18 months.  The Contractor shall notify the POC when stock need to be reordered.

Primary Method of Surveillance:  The COR will use two (2) methods of measurement – The integrated inventory system and comparative analysis of actual inventory on each day of the audit.

Measured Standard of Performance (MSP):

Target standard: Inventory accuracy within 5%

Weight measurement: 10%.

Level of Surveillance:

The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size:  10 deliveries

Sampling Procedures:  The COR shall select, at random, products in the system, physically locate the products as indicated in the system, check for accuracy at the location, and note the inventory number, warehouse location, and if correct or incorrect on the Quality Incident Log. The COR shall review the Contractor’s inventory log for receiving.

Evaluation Procedures:

The inventory differences shall be within 5%.  The COR shall review the Contractor’s inventory system and complete comparative analysis of the product received during the audit period.

Analysis of Results:

The COR will compute the compliance percentage from the random samplings. The percentage that will be used to determine incentive awards will be a computation of the sampling percentages.

5. LINES COMPLETE

Contract Requirement: Section 3.1.4 of the SOW

Performance Indicator: The Contractor shall be responsible for packing orders with the correct product and the correct number of copies requested on the packing slip or label and operating and maintaining the complete and accurate database. The Contractor is also responsible for performing standard error-checking routines to ensure accuracy and consistency of data entered.  All updates shall be entered into the ED Pubs Customer Database on a daily basis in an accurate and complete manner.

Primary Method of Surveillance: The COR will use the ED Pubs Customer Satisfaction Survey as a method of measurement. The Contractor will provide the COR an interpretation of the results from the ED Pubs Customer Satisfaction Survey reflecting service and product quality satisfaction. The percentage of respondents indicating they had received what they had ordered will be used as the method of measurement. The COR will also use validated complaints as an additional sampling method of surveillance.

Measured Standard of Performance:

Target standard: 95% of respondents from the ED Pubs Customer Satisfaction Survey indicate that they have what they had ordered. Backordered items will not be counted as part of the calculation.

Weight measurement: 5%

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size: Monthly survey results and validated complaints.

Evaluation Procedures: The COR will compute the compliance percentages from the ED Pubs Customer Satisfaction Survey.

Analysis of Results: The COR will compute the compliance percentages from the ED Pubs Customer Satisfaction Survey indicating they have what they ordered.

6. QUALITY ORDER FILLING

Contract Requirement: Section 3.1.4 of the SOW

Performance Indicator: The Contractor shall be responsible for packing orders with the correct product and the correct number of copies requested on the packing slip or label and operating and maintaining the complete and accurate database. The Contractor is also responsible for performing standard error-checking routines to ensure accuracy and consistency of data entered.  All updates shall be entered into the ED Pubs Customer Database on a daily basis in an accurate and complete manner.

Primary Method of Surveillance: The COR will use the Quality Incident Log as a method of measurement. The Contractor will provide the COR a monthly Quality Incident Log containing documentation of the date, name of employee packing the order, customer type, description of the incident, immediate action taken to resolve issue, resolution of the problem, and description of error responsibility.

Measured Standard of Performance:

Target standard: 95% of all orders are filled correctly.

Weight measurement: 25%

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size: Two (2) each of the following assortment of shipping sizes: flat, tube, kit, flat publication, flat flyer, small box, large box, flat poster, and other assorted sizes.

Evaluation Procedures: The COR will compute the compliance percentages from the Quality Incident Log, complaints received.  Sampling results of individual orders will be reflected on the Quality Assurance Daily Log for Fulfillment. The COR will indicate the task, order number, order type, correctness of order, error type, problems encountered, and corrective action.

Analysis of Results: The COR will compute the compliance percentage from the random samplings. The percentage that will be used to determine incentive awards will be a computation of the sampling percentages.

7. CUSTOMER COMPLAINTS

Contract Requirement, Section 3.1.2 of SOW

Performance Indicator: No more than .05% of total quarterly customers will register a complaint regarding items under contractor control per quarter. For these complaints related to contractor performance, this equates to one complaint in 2,000 customer contacts. The Contractor will be expected to obtain complete information on the nature of all calls/requests for publications from the caller and accurately transcribe it onto a publications request order form. The Contractor will also be responsible for answering routine questions on publications and be able to determine the exact publication the customer is seeking through the data base key word or abstract search components.

Primary Method of Surveillance: Call Distribution System Reports (80%) and Random Call Sampling (20%).  Validated complaints will be used as second method of surveillance. Also, the COR will periodically call customers.

Measured Standard of Performance (MSP):

Target standard: No more than .05% (1 per 2,000 customers served) of total quarterly customers will register a complaint per quarter.

Weight measurement: 10%.

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size: 15 calls

Sampling Procedures: The COR will randomly select a two-hour period during a work day (work days will also be selected on a random basis) during which the COR will monitor the time taken by the employee assigned to the Customer Service Desk to answer incoming calls/requests for publications. The COR will not inform the Contractor of the randomly selected day or times during the day.

Evaluation Procedures: The COR will periodically monitor the Customer Service Desk and will also review monthly reports supplied by the contractor informing telephonic data. In addition, the government reserves the right to monitor phone calls for quality of service.

Analysis of Results: The COR will review the Call Distribution System Report and random sampling results to determine total customer complaints.

8.  AVERAGE SPEED TO ANSWER

Contract Requirement, Section 3.1.2 of SOW

Performance Indicator: Incoming calls shall be answered in a courteous manner with no caller waiting more than eighteen (18) seconds on average for a customer service representative. The Contractor will be expected to obtain complete information on the nature of all calls/requests for publications from the caller and accurately transcribe it onto a publications request order form. The Contractor will also be responsible for answering routine questions on publications and be able to determine the exact publication the customer is seeking through the data base key word or abstract search components.

Primary Method of Surveillance: Call Distribution System Reports (80%) and Random Call Sampling (20%).

Measured Standard of Performance (MSP):

Target standard: Average Speed of Answer (ASA) will not be greater than eighteen (18) seconds per call.

Weight measurement: 20%.

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size: 15 calls

Sampling Procedures: The COR will randomly select a two-hour period during a work day (work days will also be selected on a random basis) during which the COR will monitor the time taken by the employee assigned to the Customer Service Desk to answer incoming calls/requests for publications. The COR will not inform the Contractor of the randomly selected day or times during the day.

Evaluation Procedures: The COR will periodically monitor the Customer Service Desk and record the number of calls received by the Customer Service Desk and length of time each caller waited. The COR will also review monthly reports supplied by the contractor informing telephonic data. In addition, the government reserves the right to monitor phone calls for quality of service.

Analysis of Results: The COR will review the Call Distribution System Report for random computation of compliance percentage for the average speed of answer.

9. ABANDON RATE

Contract Requirement, Section 3.1.2 of SOW

Performance Indicator: No more than 4% of callers should abandon a call before it is answered by a customer service representative. The Contractor will be expected to obtain complete information on abandoned calls and time before abandonment.

Primary Method of Surveillance: Call Distribution System Reports (80%) and Random Call Sampling (20%).

Measured Standard of Performance (MSP):

Target standard: Abandon rate will be no more than 4%.

Weight measurement: 15%.

Level of Surveillance:  The initial level of surveillance will be at the discretion of the COR to verify end item quality or quality control soundness.  The level of surveillance may be adjusted monthly based on the Contractor’s performance.

Sample Size: 15 calls

Sampling Procedures: The COR will randomly select a two-hour period during a work day (work days will also be selected on a random basis) during which the COR will monitor calls. The COR will not inform the Contractor of the randomly selected day or times during the day.

Evaluation Procedures: The COR will periodically monitor the Customer Service Desk and record the number of calls abandoned by customers and length of time each caller waited. The COR will also review monthly reports supplied by the contractor informing telephonic data. In addition, the government reserves the right to monitor phone calls for quality of service.

Analysis of Results: The COR will review the Call Distribution System Report for random computation of compliance percentage for the abandon rate and average time before abandonment.

Appendix B

GOVERNMENT-FURNISHED FACILITIES, EQUIPMENT, AND SERVICES

CONTRACTOR-FURNISHED PROPERTY, SERVICES,

EQUIPMENT, MATERIALS, TOOLS, AND SUPPLIES

B-1 Government-Furnished

Space and Building Services

N/A

Furniture, Furnishings, and Office Equipment

N/A

Equipment and Tools

N/A

Property

Publications/educational information inventory

FTS 2000-800 numbers

ED Pubs Master Mailing List Data

Publications Data

Data of Existing Customers

ERIC CD ROM Publication database system

Bulk Publications Ordering System (website)

America’s Literacy Database (copy)

Online ordering website

Printing Services

The Government Printing Office (GPO) must print or, by delegation, authorize the printing of the publications, brochures, pamphlets, and other printed materials used in the performance of this contract.

The Contractor shall receive data for the databases required for operation for this task.

Government-Provided Training

The Government will provide training to the Contractor on the use and operation of the

Education Resources Information Center. (ERIC) CD ROM publications database system and the Bulk Publication Ordering System (BPOS) during the transition period. Periodic training, as necessary, will be performed by the Government.

B-2 Contractor-Furnished

The Contractor shall provide all property, services, equipment, materials, tools, databases, and supplies necessary to accomplish the work under this contract to the government’s satisfaction and in accordance with minimum standards of performance.  The Contractor shall receive data for the databases required for operation for this task.

OFFICE SPACE/WAREHOUSE SPACE

The Contractor shall provide adequate protection from damage and facilities consistent with the standards and regulations based on the Occupational Safety and Health Act (OSHA) of 1970.

Should the Government consider the facilities unacceptable, the Government retains the right to require the Contractor to relocate to facilities that meet Federal Government Standards, at the Contractor’s expense.

The Contractor shall provide sufficient space with a capacity to manage all of ED’s inventory as well as offices and call center infrastructure required for inquiry handling.

OFFICE SUPPLIES

The Contractor shall supply all office supplies and materials, including supplies required for computer operation, throughout the contract’s duration.

EQUIPMENT, MATERIALS, TOOLS, AND SUPPLIES

The Contractor shall be responsible for furnishing all equipment, materials, tools, databases, and supplies necessary to accomplish the work under this contract. These include but are not limited to heavy distribution-related machinery, conveyance systems, warehouse storage materials, telephone system, mailing equipment, packing materials, computers, manifesting system, etc.

The Contractor shall be responsible for obtaining necessary supplies and materials of sufficient quality to meet all performance requirements of the contract.

The Contractor shall receive data for the databases required for operation for this task.

All equipment by the Contractor shall meet OSHA safety requirements. This equipment must operate using existing building circuits. It shall be the responsibility of the Contractor to prevent the operation or attempted operation of electrical equipment or combinations of equipment that require power exceeding the capability of existing guiding circuits.

Appendix C:

Acronyms, Abbreviations, and Definitions

Acronyms used through out this Performance Work Statement (PWS) are defined as follows:

ALD - America’s Literacy Database

BPOS — Bulk Publication Ordering System

CCR- Customer Communications Representative

CIP — Continuous Improvement Process

CO — Contracting Officer

COR — Contracting Officer’s Representative

CRM - Customer Relationship Management

CTI - Computer-Telephony Integration

ED — The U.S. Department of Education

ERIC — Education Resources Information Center

FAQ — Frequently Asked Questions

FAR — Federal Acquisition Regulation

FDO — Fee Determination Official

IFDB — Incentive Fee Determination Board

IRC — Information Resource Center (ED)

IVR - Interactive Voice Response

MSP — Minimum Standards of Performance

NIFL — National Institute for Literacy

NLE — National Library of Education (ED)

OCIO — Office of Chief Information Officer (OCIO)

PO — Principal Office within the U.S. Department of Education

PWS — Performance Work Statement

QASP — Quality Assurance Surveillance Plan

ODR — Observed Defect Rate

OPE — Office of Postsecondary Education (ED)

SOW — Statement of Work incorporated into this solicitation

TDD — Telecommunications Device for the Deaf

Definitions used throughout this PWS are defined as follows:

ALTERNATE FORMATS(Any format of a publication or information product that is accessible to people with disabilities, such as Braille, large print, audio tape versions of text documents, captioned versions of videotapes or text only electronic formats of documents.

BULK PUBLICATION ORDERING SYSTEM (BPOS)(A restricted website for postsecondary schools, high schools, libraries, nonprofit centers and agencies, guarantee agencies, higher education association and ED regional offices to place and to check their order history for bulk publications.

BULK DISTRIBUTION(Any mailing of bulk quantities of a printed product, such as a box of applications (or a partial box), usually in response to an order placed by an external customer or a conference coordinator within ED.

CONTRACTING OFFICER(A person duly appointed with the authority to enter into and administer contracts on behalf of the government.

CONTRACT DISCREPANCY(A failure of the contractor to perform in accordance with contract requirements and specifications. A contract discrepancy may result from a failure of the contractor to provide, or provide on time, the required contract products or services; or it may result because delivered products or services do not meet specific contract standards.

CONTRACT DISCREPANCY REPORT (CDR)(A report used to document unsatisfactory contractor performance. The CDR requires the contractor to explain, in writing, why performance is unsatisfactory; how performance shall be returned to satisfactory levels; and how recurrence of the problem shall be prevented in the future.

CONTRACTING OFFICER’S REPRESENTATIVE (COR)(An individual designated in writing by the Contracting Officer to act as his/her authorized representative of the and perform specific contract administrative functions within the scope and limitations as defined by the Contracting Officer.

CONTRACTOR(The contractor, its subsidiaries and affiliates, joint ventures involving the contractor, or any entity which the contractor may have merged or any individual or entity that assisted or advised the contractor in the preparation of a proposal under this solicitation.

GOVERNMENT FURNISHED PROPERTY (GFP)(All equipment, goods, and land possessed by the government and, subsequently, delivered or otherwise made available to the contractor.

MASS DISTRIBUTION(Mailings of individual bulletins, publications, diskettes, etc., that are initiated by the Department o the addresses on one or more of its mailing lists.

PERFORMANCE INDICATOR(A characteristic of an output of a work process that can be measured.

PERFORMANCE REQUIREMENTS SUMMARY (PRS)(Identifies the key service OUTPUTS AND END RESULTS of the contract that will be evaluated by the government to assure contract performance standards are met by the contractor.

PUBLICATION/INFORMATION PRODUCTS(An electronic document or hard copy including but to limited to written works, CD-ROMs, audio-visual tapes, pamphlets, posters, brochures and various applications. Documents in alternate formats, such as Braille, audiotape and large print are also included in this definition.

QUALITY ASSURANCE(Those actions taken by the government to assure that the quality of purchased goods and services received are acceptable in accordance with established standards and requirements of the contract.

QUALITY ASSURANCE SURVEILLANCE PLAN (QASP)(A written document used by the government for quality assurance surveillance. The document contains specific surveillance methods used by the government in quantifying and evaluating the contractor’s performance.

QUALITY CONTROL(Actions taken by the contractor to control the production of goods and/or services to meet the requirements of the contract.

RANDOM SAMPLE(A statistical sampling method whereby each service output and resultant accomplishment has an equal chance of being selected.

RANDOM SAMPLING(A statistical method of evaluating a few individual items and measuring the quantity and/or quality against pre-determined standards.

RUSH—The need to complete an activity in less time than the established performance standard, generally within one business day.

SAMPLE(A sample consists of one or more service outputs in accordance with random sampling procedures to be evaluated by government personnel.

SAMPLE SIZE(The number of outputs in the statistical sample; a group of one or more tasks draw from the specified performance.

SYSTEM—A customized, integrated infrastructure developed and maintained by the contractor, to include all hardware, software, and technology required to support the contract requirements.

Appendix D

Reporting

The Contractor shall submit the reports listed below.  The U.S. Department of Education reserves the right to change, modify, delete, or add report requirements for compliance by the Contractor as may be required for ED administrative purposes.  If reporting requirements are significantly increased an equitable adjustment will be made.    The Contractor shall submit a Monthly Report and an Allocation Report to the CO and the COR no later than 15 working days from the beginning of each month.

- Monthly Progress Report

  - The Contractor shall submit concise monthly progress reports summarizing the previous month’s activities and identifying problems, accomplishments, and any projected problems for the forthcoming moths.  The MPR shall include, but not be limited to the following: An Executive Summary and an Operations Summary.

  - The Executive Summary shall contain concise statistical highlights of Customer Service Contact Center including telephone and written request statistics, statistics from the Receiving Fulfillment Center including receiving and distribution statistics, costs savings, accomplishments on pertinent activities, Top Ten Most Requested Products, and special reports.

  - The Operations Summary shall contain detail statistics of the Customer Service Contact Center.  The detail statistics shall include the current month, total to-date, and total contract to-date.  Detail statistics include but not limited to the following:

    - Call Statistics and Analysis

    - Written Order Statistics

    - Month’s Caller Feedback

    - Top Ten Most Requested Products

    - Comments on ED Pubs’ Service

    - Comments on ED’s Materials

    - Incoming Products from Government Printing Office (GPO)

    - Aisle Audit Statistical Report

    - Cycle Count Statistical Report

    - Recycled Materials

    - Shipments by Order Type (Individual Orders/mass Mailings/BPOS Bulk Shipments)

    - Expedited Orders

    - Postage/Expressage Cost Savings

    - Summary of Customer Types

    - Mailing List Maintenance

    - Information Systems

    - ED Pubs Fulfillment System

    - ED Pubs Extranet

    - Quality Assurance

    - Staff Training

    - Deliverables

    - ED Pubs Customer Satisfaction Survey

    - ED Pubs Marketing Plan

    - Online Ordering Catalog

    - Publication Scanning

    - Bulk Publication Ordering System

    - Individual Hotlines

    - Special/ad hoc reports

- Allocation Report

  - The Contractor shall submit a monthly Allocation Report.  The Allocation Report is an itemized expenditure report covering all services and materials furnished during the preceding month.

  - The expenditure report shall be prepared and grouped in such a manner that separate accounting is maintained for each Principal Office and include, but not be limited to costs for each Principal Office for the following:

    - Storage costs

    - Bulk and individual requests distribution costs

    - Postage costs

    - Aggregate total

  - The Contractor shall prepare and submit required Postal Service Forms and shall make a full accounting of all postage and shipping charges.

- Invoice Details

  - The Contractor shall submit detailed information with the monthly invoices.

  - The Schedule A invoice shall contain one-twelfth of the annual fixed price. It shall itemize separately BPOS maintenance, NIFL hotline, any future optional items or contract modifications, and any other fixed price CLINS designated by the COR.  It shall also display a credit for any monies earned by the Contractor for recycling of items.

  - The Schedule B invoice shall provide separate invoices for Office of Student Financial Aid, Partnership for Reading, the National Institute for Literacy, and all other ED Pubs activity.

  - The Schedule B monthly invoice shall contain the following:

    - a breakdown of the quantity and unit rate for each Sub CLIN, with a subtotal for each category.  For example, the invoice detail for bulk distribution should reflect the following:

| Bulk Distribution | Quantity | Unit Rate | Total |
| --- | --- | --- | --- |
| Distribute materials in bulk, up to one box |  |  |  |
| Distribute materials in bulk, 2 to 15 boxes |  |  |  |
| Distribute materials in bulk, 16 to 49 boxes |  |  |  |
| Distribute materials in bulk, 50 or more boxes |  |  |  |
| Assemble kits (e.g. binders for conferences) |  |  |  |
| Subtotal |  |  |  |

    - a separate section summarizing each rush job, including the quantity, unit rate, total, and ED Principal Office requesting the rush job.

    - Total shipping and handling costs

    - Any credits or adjustments

In addition, the Contractor shall create and submit any ad hoc reports requested by the COR.