Hazard Analysis

Work Plan Title:	CDF / B0 LOW BETA SURVEY  (Collision Hall & Tunnel)

Date: 30 July 2007

Amended: 14 November 2007

Prepared By:	 Gary W. Crutcher / Alignment Metrology Group

Reviewed By:(optional)

Approved By:  Gary H. Coppola

Description of work:  As-found / As-set alignment surveys of low beta magnets and separators either side of CDF Collision Hall

Personal Protective Equipment:  (Check protective equipment required for the job.)

□ Safety glasses     □ Side shields	□ Chemical splash goggles

X Hearing Protection	X Hard Hats

□ 3.0 Braising goggles	□ Impact goggles

□ Face shield	□ Rubber apron

□ Leather gloves	□ Hot/Cold thermal protective gloves

□ Chemical resistant gloves (specify type):	□ Respirators

□ Other required PPE (specify): 	X Fall protection equipment (specify):

Harnesses and retractable lanyards

Equipment required for the job:

This equipment list is for the Q2, Q3, and Q4 alignments:

3 each Brunson 76 Alignment scopes, 4 each N3 Precision Level, 2 each stick-mic kit, 2 each Dijak Bolt Kits, 1 each 6 foot Starrett scale, 3 each trivets with 4 way heads, 3 each short tripods, 1 each regular wood tripod, 1 each laptop computer with excel spreadsheets for (Q2 thruQ4) low beta quads and Separators, recent copy of AMG data base vertical control, Lighting (i.e. 4 foot fluorescent light, and small hand lanterns.

This equipment list is for the Q1, Q5, and Separator alignments:

1 each Brunson 76 alignment scope, 1 each Brunson instrument stand, 1 N3 precision level, 1 regular wood tripod, 1 stick-mic kit, 1 Laptop computer with excel spreadsheets for the Q1 and Q5, recent copy of the AMG data base vertical control.

Work Plan History Information:  Includes “A” and  “B” sides of CDF

The first portion herein is for the alignment of a triplet (Q2 thru Q4 located either side of the CDF Collision Hall, Q3&Q4 are completely inside CDF, Q2 only partially penetrates the shielding walls). It is best to only perform alignment work on one triplet at a time. Six personnel needed minimally for the alignment of a triplet.

Prior to starting any work the survey ports must be unlocked, the poly-bead bags and the loose beads removed (loose beads are a slip / fall hazard), the fiducials uncovered, and the steel shielding stacked out of the way for the instrumentation setup. Also, in the Collision Hall, scaffolding with handrails must be setup, man-lifts available, and ladders with tie offs, swivel hoist rings for retractable lanyards installed on I.M.U.

“A” side as founds and alignment:

AQ2 setup requires two Brunson 76 alignment scopes, two trivets for the 76s, and one N3 level on a short tripod. The downstream end of the Q2 requires someone to crawl into a small opening in the concrete shielding blocks to access the fiducials and the vertical, and horizontal adjustments located on the bottom side of the Q2. There is only enough room for one person along each side of the magnet meaning a third person should remain outside of the crawl space to monitor those inside. Access to the Q2 is from the Tevatron tunnel only.

The control scope is bucked in on a parallel line to the Murphy Line using the following control points: 307149, 307021, and 307201, all located in the Tevatron tunnel floor. A second alignment scope is setup parallel and adjacent to the control scope along side the Q2 in a position in which allows the observation of the beam-right fiducials, (located between the beam-right magnet skin and the concrete block shielding wall). The N3 is setup in a position to observe 2 vertical control points and all the fiducials on the Q2. The procedure is to as-found the Low Beta’s position, and then make the appropriate moves.

AQ3, AQ4 setup requires one Brunson 76 alignment scope, and three N3 levels. This equipment is placed on the alcove using a lift, or for lighter weight items pulled up by rope. The alignment scope is bucked in on a parallel line to the Murphy Line using a combination of 3 of the 5 following control points: 307149, 307021, 307201, 307202 or 307203. The first three points listed above are inside the Tevatron tunnel, the last two are in the CDF “A” side alcove. It is recommended to use two points in the alcove and one point inside the Tevatron tunnel. Once a line of sight (L.O.S.) is established, the L.O.S. must be extended downstream into CDF. This is accomplished by double centering to a K&E target on the upstream face of the I.M.U. The forward L.O.S. is the split of the two readings. No one is to access any of the fiducials or adjustments located outside the alcove without the use of harnesses, retractable lanyards, tied-off ladders, scaffolding, or lifts. Three N3 levels are required for the vertical portion due to the configuration of steel shielding blocks and other obstructions.

One N3 is setup at the upstream end of the AQ3 looking through an opening in the shielding that accesses the “A”, “H” fiducials. The second N3 level is setup to observe the downstream end of the AQ3 and upstream end of the AQ4’s fiducials. This setup is above the shielding blocks. This requires personnel to occupy the top of the shielding steel with the use of a harness and retractable lanyard attached to the ceiling.  The third N3 is setup looking beneath the longitudinal steel rails and above the AQ4’s downstream fiducials. This requires personnel to occupy the top of the electronics rack with the use of a retractable lanyard and harness attached to the swivel hoist ring on the I.M.U. To access the electronics rack the use of a tied off step ladder or extension ladder is required. The top center of the rack is covered by heavy screen mesh and should be reinforced to support one person.

THESE SETUPS MUST STAY IN PLACE UNTIL THE AQ2, AQ3, AND AQ4 ARE ASFOUND AND ALIGNMENT IS COMPLETE. OUR EXPERIENCE HAS TAUGHT US THAT THE MANOR IN WHICH THE Q2, Q3, AND Q4 ARE COUPLED TOGETHER (TIEBARS) MOVES THE ADJACENT MAGNETS OUT OF POSITION DURING THE ALIGNMENT PROCESS. ONCE ALL THE MAGNETS ARE ALIGNED FINAL AS SET OBSERVATIONS ARE TAKEN AND RECORDED.

“B” side as founds and alignment:

BQ2 setup requires two Brunson 76 alignment scopes, two trivets for the 76’s, and one N3 level on a short tripod. The upstream end of the BQ2 requires someone to crawl into a small opening in the concrete shielding blocks to access the fiducials as well as the vertical and horizontal adjustments located on the bottom of the BQ2. Insufficient room was left in the crawl space to kneel down beside the magnet during the as found and alignment process. Only enough room exists for one person to access the magnet adjustments. That person will have to invert themselves over the top of the magnet to access the adjustments located on the underneath side. This condition is questionable from a safety standpoint with regard to an emergency egress. The physical position required to access the adjustments may compromise safety standards and places the personnel making the adjustments in an awkward and possibly hazardous situation if an emergency arises. A second person is needed to access the fiducials. A third person should remain outside of the crawl space to monitor those inside and take instrument readings. To compound this problem there are numerous cryogenic pipes that present a freeze-burn hazard. You must use a small shipping blanket laid over the cryogenic piping for insulation and to help inhibit any freeze-burn to exposed skin. Note that the observation scope and N3 have to be setup between the cryogenics piping on the beam left side of the tunnel. (See freeze-burn hazards, comments).

The control scope is bucked in on a parallel line to the Murphy Line using the following control points: 307206, 307207 in “B” side alcove, 307209, 307211, and B11 brass, located in the Tevatron Tunnel floor unless otherwise noted. A second alignment scope is setup parallel and adjacent to the control scope along side the upstream Separator in a position that allows the observation of the beam-left fiducials (located between the beam-left magnet skin and the concrete block shielding wall). The N3 is setup in a position that allows observation of two vertical control points and all the fiducials on the BQ2. The procedure is to as-found the Low Beta’s position then make the appropriate moves.

BQ3 and BQ4 setup requires one Brunson 76 alignment scope, and three N3 levels. This equipment is placed on the alcove using a lift, or for lighter weight items pulled up by rope. No one is to access any of the fiducials or adjustments located outside the alcove without the use of harnesses, retractable lanyards, tied-off ladders, scaffolding, or lifts. The alignment scope is bucked in on a parallel line to the Murphy Line using a combination of 3 of the 5 following control points: 307206, 307207 in “B” side alcove, 307209, 307211 or B11 brass in Tevatron tunnel. It is preferred to use two points in the alcove and one point inside the Tevatron tunnel. Once a line of sight (L.O.S.) is established, the L.O.S. must be extended upstream into CDF. This is accomplished by double centering to a K&E target on the downstream face of the I.M.U. Three N3s are required for the vertical portion due to the configuration of steel shielding blocks and other obstructions. One N3 is setup at the down stream end of the BQ3 looking through an opening in the shielding that accesses the “A”, “H” fiducials. The second N3 is setup to observe the upstream end of the BQ3 and downstream end of the BQ4’s fiducials. This setup is above the shielding blocks. This requires personnel to occupy the top of the shielding steel with the use of a harness and retractable lanyard attached to the ceiling.  The third N3 is setup looking beneath the longitudinal steel rails and above the BQ4’s upstream fiducials. This requires personnel to occupy the top of the electronics rack with the use of a retractable lanyard and harness attached to the swivel hoist ring on the I.M.U. To access the electronics rack the use of a tied off step ladder or extension ladder is required. The top center of the rack is covered by heavy screen mesh and should be reinforced to support one person.

THESE SETUPS MUST STAY IN PLACE UNTIL THE Q2, Q3, AND Q4 ARE ASFOUND AND ALIGNMENT IS COMPLETE. OUR EXPERIENCE HAS TAUGHT US THAT THE MANOR IN WHICH THE Q2, Q3, AND Q4 ARE COUPLED TOGETHER (TIEBARS) MOVES THE ADJACENT MAGNETS OUT OF POSITION DURING THE ALIGNMENT PROCESS. ONCE ALL THE MAGNETS ARE ALIGNED FINAL AS SET OBSERVATIONS ARE TAKEN AND RECORDED.

PREVIOUSLY SIGHTED PROBLEMS:

Broken adjustment bolts

Broken, missing, stripped, inaccessible or unknown lockdowns

Uncharged or inoperable lifts

Lack of proper scaffolding (partially corrected) / still have assembly problems

Missing tie offs for lanyards (corrected)

Standing water in “B” side alcove

Ice balls covering the horizontal adjustment bolts on BQ2

# HAZARD ANALYSIS

| Step | Description | Hazards | Precautions / Safety Procedures |
| --- | --- | --- | --- |
| 1 | Lift Operation | Collisions while maneuvering the lift inside of CDF | Be aware of your surroundings (i.e. fans, electrical cabling, walls, magnet cradles, waterlines, and people) Must have had lift training to operate all lifts in CDF Harnesses may be required for operation of some lifts. |
| 2 | Fall Protection | Falling from lifts, ladders, scaffolding, or the alcoves located either side of the collision hall | Tie-off ladder or use a buddy to secure as necessary. Use harness if necessary or required Make sure that all guardrails are replaced after equipment is set onto alcoves. Must wear a harness while accessing the magnets suspended in the cradles, tie-offs are in place and mounted in the ceiling and on the I.M.U. Scaffolding requires handrails and proper access mode. (i.e., ladder and or hatch) |
| 3 | Trip / Slip Hazards | Tripping over equipment, extension cords, or materials stored on floor, loose poly beads | Walk cautiously and be aware of your surroundings. Clear work area of unnecessary items as needed. |
| 4 | Loud Noises | Hearing damage caused by excessive noise, from machinery, water lines, and fans. | Carry ear protection with you and use as needed. |
| 5 | Head Injuries | Material falling | Hard Hats to be worn whenever anyone is working overhead, or any cranes are in operation in the area. CDF requires that everyone entering the collision hall should wear a hard hat. |
| 6 | Back / Body Injury | Back or body injury caused from lifting too much weight or improper lifting technique | Use proper lifting techniques. Do not place your body in awkward positions while lifting. Utilize a buddy while lifting excessive weight or moving ladders or heavy equipment. |
| 7 | Temperature Extremes | Exposure to hot / cold environments | Use shipping blankets to cover up exposed cryogenic piping to prevent freeze burn. “B” side of CDF (tunnel) requires one’s body to be in very close proximity to the cryo-pipes. |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |

(Use additional pages as needed.)

My supervisor has reviewed this hazard analysis with me and I understand the hazards and required precautionary actions.  I will follow the requirements of this hazard analysis or notify my supervisor if I am unable to do so.  I understand that there are Environmental, Safety and Health Professionals on staff if I need further assistance or clarification.

| Name and ID (please print) | Signature | Date |
| --- | --- | --- |