# Table of Contents

executive summary	1

why explore public-private partnerships?	1

This study builds on Earlier Efforts	3

Findings	3

Scope and Legislation	3

Public Support And Outreach -- “Selling” P3	4

Financing, Risk Allocation, and the Division of Public and Private Sector Roles	4

Relations With Private Proposers	4

Where do we go from here?	5

introduction	6

Study objective	6

structure of this report	7

lessons learned	8

Introduction	9

Scope and legislation	9

Maximizing Legislative Flexibility For The DOT	10

Solicited And Unsolicited Proposals And Open Scopes	11

Using a Two-Step Selection Process for Unsolicited Proposals	12

public support and outreach	15

Garnering Internal Support	15

Gaining External Support	16

Financing, risk allocation, and the division of public and private sector roles	18

Issues Regarding Public and Private Sector Role Definitions	20

Relations with the private sector	21

Attracting Private Involvement	21

Maintaining Private Sector Interest	21

Negotiating With The Private Sector	22

Conclusion	23

review of state p3 programs	24

INTRODUCTION	25

State by state review	26

ARIZONA	27

CALIFORNIA	30

DELAWARE	32

FLORIDA	34

MINNESOTA	36

OREGON	38

PUERTO RICO	40

SOUTH CAROLINA	41

VIRGINIA	44

WASHINGTON	46

FLOW CHARTS OF STATE PROCESSES	51

OTHER STATES	61

COLORADO	61

Maryland	61

Missouri	62

New Jersey	62

NEW YORK	62

Pennsylvania	62

Texas	63

Utah	63

Table: PUBLIC-PRIVATE PROJECT EXPERIENCE (BY STATE)	65

case studies	68

introduction	69

Virginia	70

Overview	71

Dulles Greenway Public-Private Partnership	71

Background/Scope and Legislation	71

Process and Agreement	71

Project Description	72

Status	72

Lessons and Highlights	72

Public-Private Partnerships Under Virginia’s Public-Private Transportation Act of 1995	74

Background	74

Process	74

Project Descriptions	77

Project and Program Status	81

Lessons and Highlights	81

washington state: new partners initiative	85

Background	86

Process	86

Program Development	86

Scope and Legislation	87

Initiation of P3 Proposals	87

Selection	88

Finance	88

Project Descriptions	89

Project and Program Status	92

Timeline	94

Lessons and Highlights	94

Widespread Support in the DOT and in the General Public	95

Rate of Return was Regulated but Flexible	95

Financial Assistance was Available from the State	95

Outreach Should Be A Joint Responsibility	95

Public Outreach Efforts Must Use The Right People To Reach The Right People	96

Undertaking Six Partnership Projects From Scratch Overwhelmed The DOT	96

Transparency Vs. Confidentiality	96

States May Wish To Guide Proposers To Projects Wanted By Regional Jurisdictions	97

E-470:  Public-Private Partnership in Denver Metropolitan Area	98

Background	99

process and project description	100

lessons and highlights	103

Locally Initiated Programs Need To Involve The State	103

Outreach Can Alleviate The Perception Of “Bait And Switch”	103

California:  San Diego Expressway Project	104

Background	105

Effects of NAFTA	105

TransNet Program	106

Process:  AB 680	106

Scope and Legislation	106

California Transportation Ventures, Inc. (CTV) Rationale for Proposing San Diego Project Under AB 680	107

Project Description	107

Timeline for SR 125 Tollway	109

project Status	110

Lessons and Highlights	112

Financial Arrangements Should Be A Function Of The Project’s Risk Profile	112

Environmental Clearances Should Be Sought To Maximize Flexibility and Minimize Objections	112

Any Non-Compete Clause Must Be Clear and Binding	113

Using Funds to Support Private Toll Road Projects	113

Appendix 1: Individuals contacted for this Report	115

Appendix 2: “Role of 63-20 Nonprofit Corporations in Public/Private Infrastructure Financings”	118

# executive summary

# why explore public-private partnerships?

Our nation’s potential for economic growth hinges on, among other factors, its ability to provide adequate infrastructure, such as bridges, roads, rail and port terminals.  Indeed, recent empirical evidence suggests that regional and national transport networks directly support growth in private-sector economic productivity. Highway infrastructure in recent decades has been provided largely with public funds based on motor fuel taxes and other user fees, channeled through the Federal Highway Trust Fund and comparable state transportation trust funds.  This system has worked well, providing a reliable source of development capital to build new roads and rebuild old ones. Public funds, however, have not kept pace with the demand to maintain and improve the nation's extensive network of roads and bridges.

At the Federal level, fiscal and budgetary pressures have held Federal aid for highways to gradual, uneven growth. In fact, Federal aid has declined significantly relative to State and local highway spending over the period since the Highway Trust Fund was initiated in 1956, not withstanding periodic Federal tax increases.  State and local government highway programs are feeling these same pressures.  Moreover, traditional sources of funding are no longer sufficient to meet transportation needs and public resistance to general tax increases is high and growing.  States are thus in a seemingly impossible situation: they cannot afford to rely on traditional methods to meet their infrastructure needs, and they cannot afford to wait to meet those needs.  As a result, Federal, state, and local administrations and legislatures are exploring many options for new funding sources. One of the more promising options is to allow partnerships with the private sector to develop, finance, own, operate, and maintain highway facilities.

In recognition of the critical importance transportation plays in supporting and facilitating economic health and growth, states have begun to make broader use of market-based techniques to supplement traditional public grants, in particular engaging the private sector in transportation service provision.  While experience is still developing across the US, public-private partnerships (commonly referred to as P3) show promise both for attracting private capital to projects traditionally financed solely by the public sector and for getting projects built faster.

It is imperative, therefore, that FHWA continue to assist states as they work to implement P3 programs, helping them to understand not only the kinds of programs being used across the country, but what lessons can be learned from these efforts and how they may be applied to their state.  This report is intended to provide that roadmap.

Models of Highway Delivery Through Public-Private Partnerships

A public-private partnership can be built on virtually any mix of public and private financial sponsorship that departs from the traditional public highway model. Several prototypical models have developed, incorporating increasing amounts of private involvement in development and operations along with the infusion of non-governmental funds. As the private sector contributes more equity financing and assumes more risks, the partnership develops more characteristics of full privatization. The array of potential structures span the continuum from traditional public to mostly private:

- Traditional New Public Highway. Government ownership and funding with investment commonly justified by general system-wide public needs.

- Traditional New Public Toll-Road Delivery. Public authority ownership and operation, using toll revenues to finance non-recourse or state-backed tax-exempt debt to construct the facility and provide interim operating funds.

- Innovative Financing for New Public Faci1ities. Public ownership and operation with full or partial reliance on local benefits, captured by targeted exactions such as development-impact fees as well as tolls.

- Blended Public-Private Financing for New Public Toll Road Delivery. Control and direction under governmental oversight, usually by a local authority; non-recourse financing delivers a complete, stand-alone project.

- Public-Private Partnerships to Deliver New Road Capacity. Substantial private equity participation and a strong private role in structure, delivery, and operation; public role tends more toward framing the concession agreement, contributing predevelopment costs, or assembling rights-of-way.

- Privately Supplied New Highway. Finance provided and risk borne almost entirely by private developers and their financial supporters; significant at-risk equity combined with the issuance of taxable debt or, in some instances, special purpose non-recourse tax-exempt debt.

Role for Public-Private Partnerships

The appropriate role for partnerships is evolving. Two essential determinants are public acceptance and the level of unmet highway needs. Beyond these are a number of unresolved issues regarding the blending of public and private roles in project development and finance.  It is clear, however, that partnership development can effectively augment traditional financing sources for highway construction and reconstruction. The infusion of private financial participation necessarily introduces marketplace discipline: essentially, the relative uncertainty of an attractive return on investment will be required. Hence, an important feature of a majority of partnership projects is the imposition of project-related user fees, tolls, development impact fees, and other exactions associated with value capture from the project.

In essence, project users and beneficiaries will be expected to pay for use of a given facility in a given location. Where the facilities are needed and users are willing to bear these direct charges, public-private partnerships should enable highway development to proceed more quickly than traditional funding sources. The development of proposals by private syndicates is also likely to produce some innovative solutions to transport problems. Reliance on user charges, in turn, may well moderate the demand for some potential new facilities and result in more disciplined or realistic highway needs assessments.

# THIS study builds on Earlier EFforts

This report builds on a continuous effort on the part of FHWA to educate and help states as they explore P3 options.  Preceding this report, FHWA has:

- Sponsored a Symposium on Overcoming Barriers to Public-Private Partnerships (December 1993);

- Published the Symposium Summary in the Searching for Solutions Series (Number 11, September 1994); and

- Published Implications of Changes and Procedures and Laws to Advance Public-Private Partnerships (April 1995).

Since 1995, however, many more states have passed enabling legislation or otherwise embarked on P3 programs.  The continued mixed success of these efforts indicates that a further examination of how these programs are structured and what lessons can be learned from state efforts is warranted.

# FINDINGS

In general, state experience with P3 efforts indicate:

- Substantial benefits -- Public-private partnerships can offer significant benefits to both the public and private sectors, lowering costs and speeding project completion while creating and expanding business opportunities.

- Mixed success -- Implementing partnerships in the US has met with only mixed success.

- Movement away from complete privatization towards true partnership -- As the public and private sector each have different advantages, the more successful efforts have involved substantial contributions from both sectors.

The path some states have taken reflect a number of specific lessons that may help other states achieve the potential benefits and establish successful partnerships.  This report focuses on drawing out these lessons.  “Lessons learned” may be characterized in terms of how a state approaches:

- Program Scope and Legislation;

- Public Support And Outreach -- “Selling” P3;

- Financing, Risk Allocation, and the Division of Public And Private Sector Roles; and

- Relations with Private Proposers.

# Scope and Legislation

Most, but not all, P3 efforts have begun with general enabling legislation that has described a program scope and implementation process.  The success or failure of partnerships under different legislative structures suggests:

- Flexibility is critical to negotiate partnerships that meet the unique nature of individual proposals, specifically with respect to project selection, negotiation, and the overlay between the P3 legislation and existing laws and procedures for procurement of bids;

- States may wish to think carefully about whether to accept unsolicited proposals and under what conditions they are permitted as this structure affects other activities such as outreach and selection;

- Some projects lend themselves better to a P3 approach than others and states may want to guide or dictate the nature of proposals submitted; and

- The public partner does not necessarily need to be the state -- local governments can also play a role.

# Public Support And Outreach -- “Selling” P3

While there is no single model for implementing P3, all successful P3 efforts share two characteristics:

- Strong public sector support among the key stakeholders: (i.e., the DOT, the legislature, and the Governor’s office); and

- A strong, visible, and continuous outreach effort headed by the public sector to the general public (with private participation in latter phases).

While many states have understood the importance of the latter, many have downplayed the critical role played by the former, and in particular, the importance of internal support:  If the DOT does not support and want a P3 program (where this support must extend beyond the Secretary and designated P3 champion) the program will fail.  This is the single most important “dealbreaker” that exists.

# Financing, Risk Allocation, and the Division of Public and Private Sector Roles

Two lessons regarding risk sharing and financial roles stand out:

- The public partner must first identify and be able to articulate their objectives in risk and return sharing; and

- The financial arrangements need to reflect the nature of the project, the financial strengths of the private partner, and the project’s risk profile.

Even where the public sector’s ability to provide direct cash to a project is limited or prohibited, it can share risk with the private sector in other ways.

The public sector can:

- Play a lead role in outreach;

- Facilitate the environmental and governmental permitting approval process;

- Take complementary planning actions to support the project; and

- Use their position to provide transparency and consistency to every activity.

# Relations With Private Proposers

To take advantage of private participation, the public partner needs to:

- Attract good teams and good proposals -- by conducting outreach to private proposers and using a transparent and well-defined process;

- Maintain private sector interest and support -- by adhering to the program developed in terms of purpose and goals, selection, and schedule; and

- Conduct negotiations successfully -- focusing on the fact that conclusion of an agreement is a joint goal -- the partners will be working together for a long time.

# Where do we go from here?

There is no single model for success.  State efforts have succeeded, however, where support is widespread, the DOT (or responsible government entity) has clear goals and has communicated those goals, and private players have been willing to enter into a real partnership.  The lessons learned presented in this report can help states think about whether private participation is something that will help meet their goals, and if so, how to travel down this new path to project development and finance.

# introduction

# STUDY OBJECTIVE

This report is intended to fulfill two objectives:

- To inform states of current public-private partnership (P3) activities; and

- To provide specific guidance to states considering initiating private participation

in transportation service provision.

It builds on previous efforts by FHWA to keep states abreast of recent P3 developments and potential barriers to success.  This report, however, is far more specific than prior reports, thus providing a roadmap to states as they begin the possible journey down the road to private participation in the provision of public transportation services.

What are Public-Private Partnerships?

Public-private partnerships are a relatively new and rapidly evolving financing tool already contributing significantly to highway development.  At the Federal level, the Intermodal Surface Transportation Efficiency Act of 1991 (ISTEA) provides the flexibility to enable private partners to be part of a Federal-aid project.  Likewise, several states have passed enabling legislation in order to integrate private funds into their highway programs.

A public-private partnership can be built on virtually any mix of public and private financial sponsorship that departs from the traditional public highway model. Several prototypical models have developed, incorporating increasing amounts of private involvement in development and operations along with the infusion of non-governmental funds. As the private sector contributes more equity financing and assumes more risks, the partnership develops more characteristics of full privatization. The array of potential structures span the continuum from traditional public to mostly private:

- Traditional New Public Highway. Government ownership and funding with investment commonly justified by general system-wide public needs.

- Traditional New Public Toll Road Delivery. Public authority ownership and operation, using toll revenues to finance non-recourse or state-backed tax-exempt debt to construct the facility and provide interim operating funds.

- Innovative Financing for New Public Faci1ities. Public ownership and operation with full or partial reliance on local benefits, captured by targeted exactions such as development-impact fees as well as tolls.

- Blended Public-Private Financing for New Public Toll Road Delivery. Control and direction under governmental oversight, usually by a local authority; non-recourse financing delivers a complete, stand-alone project.

- Public-Private Partnerships to Deliver New Road Capacity. Substantial private equity participation and a strong private role in structure, delivery, and operation; public role tends more toward framing the concession agreement, contributing predevelopment costs, or assembling rights-of-way.

- Privately Supplied New Highway. Finance provided and risk borne almost entirely by private developers and their financial supporters; significant at-risk equity combined with the issuance of taxable debt or, in some instances, special purpose non-recourse tax-exempt debt.

# structure of this report

This report is composed of three sections.  It first describes lessons that may be learned from individual states’ experiences with P3.  A brief review of state programs follows.  The report concludes with four in-depth case studies from which many, but not all, of the lessons were drawn.

# lessons learned

# Introduction

In this section, lessons and highlights of the public-private partnership process are given. The section is broken up into four parts.  The first describes enabling legislation used in Washington State and Virginia, considered models for legislation development.  Following is a review of the need for both internal and external support for the program.  Here, examples from several state experiences are given.  The final sections look at the experience of states in financing, allocating risk, the division of public and private sector roles, and the on-going relationship with private partners in the process.   Examples from several projects are given, including, for instance, Denver’s E-470 and Virginia’s Dulles Greenway projects.

Program highlights and lessons learned are drawn from in-depth research and interviews with states and project sponsors actively engaged in the P3 development process.  Interviews with representatives from ten states (Arizona, California, Delaware, Florida, Minnesota, Oregon, Puerto Rico, South Carolina, Virginia, Washington) form the basis of the majority of findings presented.  These states have developed and at least partially implemented a statewide process for solicitation, acceptance, and review of proposals from the private sector regarding surface transportation-related activities.  This section also draws on information gathered on several other states’ initiatives (for instance, Colorado, Maryland, Missouri, New Jersey, New York, Pennsylvania, Texas, and Utah) who are just beginning their own programs or considering program alternatives.  Finally, in-depth case studies of two programs (Virginia and Washington, and two individual projects—Denver’s E470 and the San Diego Expressway) provide further lessons.  Summaries of the state programs noted here are provided in the next section of this report.

# Scope and legislation

Two states have developed legislation that has already been used by other states as model legislation:  Washington State and Virginia.

The Washington State enabling legislation was basically sound and incorporated lessons learned in the early partnership efforts in other states.  In general, proposers liked the State’s design for the process and found the State receptive to different proposals and responsive to the needs of proposers.  The Washington State Department of Transportation (WSDOT) was successful in attracting bids from experienced teams with the financial and technical capability to fulfill their proposals.  Most observers felt that the selection process was fair, and resulted in selection of high-quality teams.  The proposed projects solved real problems still facing WSDOT, such as the build-out of Seattle's HOV system.

Similarly, DOTs and private proposers have remarked that Virginia’s legislation was sufficiently flexible and the accompanying guidance laid out a clear, logical evaluation and selection process.  Proposers initially liked the two-step proposal process as it limited cash outlays (by requiring an initial payment of $5,000 for a conceptual proposal submittal and $20,000 if the conceptual proposal was accepted and the team moved to a second phase of evaluation).

Most, but not all, P3 efforts have begun with general enabling legislation that has described a program scope and proposal process.  The success or failure of partnerships under different legislative structures suggests:

- Flexibility is needed to negotiate partnerships that meet the unique nature of individual proposals, specifically with respect to project selection, negotiation, and the overlay between the P3 legislation and existing laws and procedures for procurement of bids;

- States may wish to think carefully about whether to accept unsolicited proposals and under what conditions they are permitted as this structure affects other activities such as outreach and selection;

- The public partner does not necessarily need to be the state -- local governments can also play a role; and

- Some projects lend themselves better to a P3 approach than others and states may want to guide or dictate the nature of proposals submitted.

# Maximizing Legislative Flexibility For The DOT

Public-private partnership enabling legislation needs to satisfy two requirements.  First, it needs to create a process that does not loop back on itself -- such that a proposer invests a greater and greater effort and money into the process, only to have a ruling or veto late in the process virtually start the process over again.  Second, it needs to give the DOT flexibility with respect to making the final decision, the ability to determine its role (so that it can tailor its role to the needs of the project and proposing team), and the ability to enter into an agreement exempt from selected procurement rules and regulations.  While some state laws must still apply, P3 is not traditional procurement of services and it should not be thought of as such.  Enabling legislation also may serve to prevent or avoid potential dealbreakers by prohibiting certain types of projects or financial structure.  This is especially useful if public support is not yet fully secured.

# Loops and Potential Concerns

Following are a few examples of the adverse impact of procedural loops in the P3 development process:

- In California, planned integration of the San Miguel Connector into the design/build contract for SR-125 requires completion of an agreement between the private partner, CTV, and the public partners, San Diego Association of Governments and California Department of Transportation (cost-sharing responsibilities need to be spelled out).  These public bodies cannot make a definitive agreement until the road is approved, however.  At the same time, approval depends, in part, on the integration of the San Miguel Connector.  This kind of loop needs to be recognized and avoided.

- In South Carolina, while the P3 enabling legislation itself gave the DOT maximum flexibility from State Assembly oversight, it requires projects over $150 million to be approved by the affected local government.  In the case of the Conway Bypass, the selected proposer requested that subsequent legislation be passed to permit the affected local government to charge a one cent sales tax dedicated to the project.  This failed to pass, and there was concern that every new financial option would similarly be subject to local referendum.

- The Arizona Department of Transportation’s (ADOT) enacted process also contained an unintentional “feedback loop”.  Under Arizona’s legislation, both unsolicited and solicited proposals were permitted.  In the case of the former, upon receipt of an unsolicited proposal, the law required ADOT to issue an RFP for competing proposals that “responded” to the unsolicited proposal.  Proposers could respond to this RFP, and a single proposal would be selected.  Unsuccessful proposers could then submit their proposal on an unsolicited basis, forcing ADOT to respond, even if the proposed plan was not of any interest to ADOT.  Thus, the process could get trapped in a seemingly endless loop.

- In Minnesota, any affected community has veto power over any project for thirty days after contract negotiations are final, leaving the proposer with significant risk until the end of the process.

- The Virginia model, in contrast, progressively reduces proposer risk over time.

# DOT Discretion

Following are two sides of the coin with respect to the importance of DOT discretion in P3 program implementation:

- Virginia’s decision to require projects that are “compatible” with state and local transportation plans gives the private sector enough leeway to propose projects that may not have occurred to transportation planners, but also gives the Commonwealth the ability to go forward with projects that are in its best interests.

- In Florida, enabling legislation requires proposers to meet state procurement laws which proposers feel robs them of their proprietary rights and hampers their ability to capture efficiencies in service provision.

# Dealbreakers

Finally, enabling legislation can be used to prevent potential dealbreakers from the start.  In Virginia, for example, the law prohibits the tolling of existing roads unless the tolls will go to pay for major expansion or improvement of that facility; the state regarded these conditions as a major factor in gaining widespread support.  As a result, Virginia experienced no organized opposition to the statute.

# Solicited And Unsolicited Proposals And Open Scopes

Some states have permitted unsolicited proposals.  Others have issued a general solicitation with little or no constraints on scope.  Each structure has raised issues.

- In Washington, no mechanisms were in hand to assess whether the proposed projects were of interest to the individual county and regional jurisdictions.  Washington had general solicitation, but did not use specific RFPs for specific projects; it was an open scope structure.  The program may have received better local support if it had requested or required that proposed projects link directly to Metropolitan Planning Organization’s Transportation Improvement Plans.  For example, the Puget Sound MPO had not completed its regional plan before the six demonstration projects were accepted.

- Arizona has permitted unsolicited projects.  Upon reflection, ADOT felt the process would have worked better if private proposers had focused on smaller projects; initial proposals were too ambitious and comprehensive.  ADOT would also have preferred to have more control over project selection.  Although ADOT will continue to permit unsolicited proposals, it will attempt to screen them through a letter of intent process.

- In Virginia, several program issues arose that were related to Virginia’s decision to pursue a dual approach to P3, with respect to permitting solicited and unsolicited proposals and the latter's subsequent two-step selection process.  Permitting unsolicited proposals has caused the Department to rethink or alter the program regarding:

- Whether unsolicited proposals should be limited to certain types of projects (e.g. capital or DBOM);

- Using a two-step selection process for such proposals -- in terms of clearing up misunderstandings and revisiting the legislation pursuant to the selection process;

- Proposed schedule for action by VDOT; and

- Possible conflicts with Department outreach objectives.

Limiting Unsolicited Proposals to Capital Projects

If a program permits unsolicited proposals, it may cause less disruption to existing operation and maintenance (O&M) contracts with private providers if such proposals are limited to capital improvements.  O&M (asset management) proposals can then be solicited via RFP.  Alternatively, if a state program permits unsolicited proposals, and if the state will consider O&M proposals as part of design/build contracts (i.e., design-build-operate-maintain type of proposals), but does not wish to consider O&M proposals on their own, it simply needs to make that clear in the program guidelines.

# Using a Two-Step Selection Process for Unsolicited Proposals

Clearing Up Misunderstandings.  The Virginia Department of Transportation recognizes that if a state decides to implement a program that permits unsolicited as well as solicited proposals, the DOT needs to be very clear about what it wants and does not want in conceptual proposals.  While VDOT thought they were clear on this issue, events have demonstrated otherwise.  VDOT has received very long and technical “conceptual” proposals that, in their view, went much further than the conceptual proposal framework had intended, offsetting the time and cost savings the two-step process was supposed to provide to proposers.  One simple solution is to put in a page limit on conceptual proposals.  While crude, it could solve the problem VDOT has faced (VDOT also noted that this type of process is really only relevant for two-step programs, and DOTs pursuing only solicited responses may not gain very much from using a two-step process at all).

Re-visiting the Legislation Pursuant to the Selection Process.  VDOT realized that the Commonwealth’s Freedom of Information Act (FOIA) requirements made the two-step selection process awkward, and subsequently changed the legislation to exclude such proposals from the FOIA, subject to a series of tests.  VDOT advised that this type of problem can be avoided if a state’s P3 program development is considered simultaneously with the development of its legislation.

Schedule For Action

VDOT has learned that if a DOT pursues a dual proposal solicitation approach, it must develop an approach for proposal response.  Even if the timeframe established is long, the bidder must be kept informed of progress made regarding project selection and approval.  This may be as simple as regularly scheduled meetings upon initial selection.  Participants in the Virginia program have also suggested that states move away from the dual approach, and simply solicit proposals that addresses the state’s primary obejectives.

Unsolicited Approach Works at Cross Purposes To DOT Outreach

Virginia has been lauded for the extensive outreach carried out by the DOT both at the start of the program and over time.  Indeed, proposers praised the Department for being the only DOT to stand before local governments and state that the Commonwealth simply does not have the resources to fund all the projects its needs.  This honesty was strongly supported and deemed critical.

VDOT has noted, however, that pockets of local opposition remain. VDOT must, therefore, continue its efforts to educate the general public, as well as local governments.

At the same time, because Virginia’s program allows unsolicited proposals, VDOT has an incentive to reduce or stop outreach after a period of time, because the DOT has received more proposals than it could respond to, in a timely manner.  The Department has thus slowed its education and outreach efforts.  As a result, the solution used to resolve one problem thus prevents VDOT from achieving other program goals.

Washington State faced a similar problem with its open scope approach. In hindsight, broad competition with no defined project list meant WSDOT had to hold business proposals in confidence and restrict disclosure.  Yet, this left it open to the perception that the selection process was “behind closed doors,” with attendant implications.

Any “Responsible Public Entity” May Accept Or Solicit A Proposal

Enabling local governments or authorities to participate directly in a P3 program may overcome one of the biggest barriers to such programs -- local support.  However, some issues do arise.

Virginia permits local governments to solicit RFPs and enter into P3 agreements.  To date, only the City of Chesapeake has done so.  The relationship between Chesapeake and VDOT has been a good one, but VDOT was surprised at the level of support required on their part and reflected that other states may want to formalize roles and responsibilities more than Virginia has.  If a state program enables local governments or authorities to undertake P3 themselves, some consideration should be given as to how the DOT would work with the locality through the process.  This might include, for example, how (or whether) to value the DOT contribution as part of the public share in cost and risk sharing for the project.

VDOT also noted that, to date, no other locality has embarked on a P3 program.  While no one knows why, VDOT speculates that they do not understand the program well enough, possibly coupled with their fear of replicating some of the problems associated with the Dulles Greenway.  If a DOT wishes to enable local government entities to embark on a P3 program, it may, therefore, want to include education of such entities in its outreach program and offer upfront assistance to get them started.

In Colorado, the E-470 project was locally initiated, with little involvement by Colorado DOT.  To some extent, the E-470 Authority that sponsored the project was reluctant to approach the DOT as there was concern on the part of the Authority that the state would “take over”.  Again, if the process had created roles for both the Authority and CoDOT, the DOT could have stepped in and helped the process sooner.

In particular, while the E-470 example demonstrates the strengths and weaknesses of a project grown from local initiative, a clear and defined state role at the start may have helped secure financing and minimize costs.  As well, an increased state role may have helped to alleviate some of the political issues that arose and led to costly litigation motivated by angry developers.  At the same time, it could have been able to allay the Authority’s fears about being “taken over.”

Capital Vs. Operations And Maintenance Proposals: Suitability to P3

VDOT and participating proposers both reflected that some projects may be more suited to P3 programs and that there might be some benefit in identifying these projects at the beginning of the process.  In practice the issues arose in proposal evaluation, trying to determine whether a proposal provided sufficient value to the DOT.

With respect to capital projects, two issues arose.  First, one of the difficulties in evaluating new capital projects, if they are not already on the state Transportation Improvement Plan, or five year capital plan, is that these projects have not been considered and ranked in terms of their relative priority to the DOT.  Where the project is completely privately financed, this is not an issue, but increasingly, successful partnerships are seeking a contribution from the DOT, whether equity, a loan, or in-kind in nature.  This creates a situation that, at best, delays the evaluation, and can stop the process in its tracks.

A second problem that has been identified is the issue of “cherry picking”.  Several DOTs have expressed concern that the private sector is only interested in bidding on projects that can yield them a return, leaving the DOT with projects that are not viable from a stand-alone perspective.  This logic appears backward: private parties will always seek a return on their investment as profit motivated entities.  The DOT is not profit oriented, but provides a public service.  Given a basket of projects, some of which could be stand alone and others which could not, and scarce public dollars to meet transportation needs, many proposers suggested that the DOT should use its scarce resources to finance those that are not viable from a stand alone perspective, and use the private sector to develop those that can.  The P3 arrangement can be structured so that the DOT shares in the return, and uses its cash freed up to finance more projects than it otherwise could if the private sector had never gotten involved.

DOTs may wish to look carefully at their long term capital plans, as these typically represent a “wish list” of projects by local governments, MPOs, and the state.  While unsolicited proposals for creative new ideas need not be excluded from the process, bidders may be more interested and willing to respond if the DOT indicates the kinds of projects it is interested in receiving proposals for, using existing plans as a backdrop for that request.  In addition, in determining which projects might more logically lend themselves to P3, the DOT may wish to consider its projects from a market perspective -- which ones have or could have elements that would make them viable (or viable with some state assistance).  Given the discussion above, it may be more logical to solicit interest from the private sector for the latter group.

Also, DOTs may wish to identify P3 projects that are outside the scope of their core business.  For example, VDOT is considering proposals to, in effect, privatize a ferry service between Jamestown and Scotland, Virginia.  As long as core requirements for service are established, VDOT seems receptive to allowing private firms to explore the full commercialization of the service.  As facility operation will involve elements such as marine engineering, shipping, and related issues that are outside the core expertise of a traditional transportation project, VDOT identified the service as one that could benefit from a private firm’s resources.

This issue arose in Florida as well. Florida DOT attributed the lack of completed projects to date to the existence of the Turnpike and local Expressway Authorities which undertake the same types of projects, in effect capturing the potential projects away from the private sector.

Less seriously, with respect to O&M proposals, a similar issue arose.  Under O&M projects, the savings is typically based on expected efficiencies.  By definition, therefore, the DOT must be able to determine what that segment of road would have cost them to operate and maintain in the absence of private sector involvement.  In Virginia, the DOT did not calculate costs in a way that permitted them to isolate the costs of operations and maintenance of the pilot section interstate from overall costs.  While these calculations are being made now to permit evaluation after the pilot contract is completed, it was not anticipated.  This caused delay in the evaluation process.

Where a proposal is solicited, the DOT can prepare such benchmark cost information ahead of time.  The RFP for operations and maintenance of the Jamestown-Scotland Ferry is one such example where the DOT has separated out the costs of operating that facility.  This issue supported VDOT’s case for soliciting O&M projects.

Other Issues of Scope and Legislation

In Washington, the legislation did not limit the number of proposals or phase submission.  Fourteen proposals were submitted and six selected within the same timeframe.  This overwhelmed the DOT.  WSDOT had no experience with such a program.  Further, the proposals introduced tolls, which were new to the State.  Finally, the administrative costs were higher than anticipated.  These activities need a dedicated professional staff, and they continue for the life of the project.  WSDOT may have had a smoother experience if they had staged the submission or the selection process.

# public support and outreach

# Garnering Internal Support

Following are brief descriptions of three states’ experiences regarding ease with which intended support was achieved:

- In Washington, the program was initiated by the Transportation Commission and the DOT (through its leadership of the subcommittee on Public-Private Partnership).  This interest led to legislation, not the reverse.  While legislative initiatives can be successful, there have been many instances where the DOT did not support a legislatively driven program.

While, in Washington, initial internal support was achieved, public outreach needs to be a dynamic set of activities that keeps abreast of any changing conditions between proposal selection and final negotiated agreement.  The audience for outreach may thus change over time and cannot be prescribed beforehand.  Aside from reaching the general public and public officials in the DOT, WSDOT faced a change in the state legislature.  As opposition arose following the 1994 election results, and a new legislative leadership came into power, strong support from the Secretary and the Governor could have been critical. WSDOT needed to keep the new legislators informed and garner their support, which was not done.

- Delaware DOT would have preferred a process that gave them more control over project selection, but the political forces (that were behind the legislation that drove the entire process) "boxed" the DOT into an RFP that permitted toll roads -- the one type of project the DOT did not want to pursue.  Not surprisingly, the two proposals received (not surprising) called for acceleration of a partially built toll road.  Further, some miscommunication occurred between DelDOT and the State’s Trust Fund during the project selection process, which hampered the evaluation procedure.

- In Virginia, the DOT, the Governor’s office and the Legislature worked closely together to develop the program and to conduct outreach.  Virginia has been complemented extensively for its unified effort.

# Gaining External Support

Several programs have faced public opposition.  In Arizona, implementation was hampered by public opposition, which some private proposers attributed to inadequate public outreach in the initial program.  In particular, the public was subjected to a “bait and switch.”  The public had accepted a local sales tax increase on the premise that certain highway facilities would be built.  Sales tax revenues, however, fell short and those same highway facilities were now proposed as toll roads.  The public was not willing to pay tolls in addition to the tax increase.

Other types of “bait and switch” can take place.  If circumstances require a change after local support has been secured, it is imperative that the DOT walk the public through the change: why it occurred and what it means.  This concept applies more broadly as well.  In the event the P3 program is generated locally, it is just as important to explain from the beginning that a private partner is sought and why he is sought, so that the public is not “surprised” when a private partner appears.  The E-470 project in Colorado is an example.

In California, SANDAG (the MPO) faces a similar issue to that which arose in Arizona.  Here, SANDAG needs to explain why sales tax revenue must be diverted for the San Miguel Connector.  In general, the “bait and switch” issue needs to be anticipated, recognized, and avoided where possible or managed where inevitable.

South Carolina officials identified the biggest shortcoming of the process as a lack of outreach and involvement of local jurisdictions over the course of the process.  Residents, while aware that they would be paying for the new facilities through tolls or fees, wanted to be more a part of developing the project package, both in the RFP stage and in the final negotiations with the winning proposer.  County and city councils felt left out of the process, robbing the project of important local support which comes from a sense of local ownership.  The State now realizes there must be more of a team effort between the State and the affected localities throughout the solicitation and proposal process.  No one should be left outside the process because this allows them to criticize from the outside.  All stakeholders—even potential detractors-- must be brought into the circle through a partnering process, and they must be brought in at the outset according to the State.  Early on, communication must be established between proposers and the public.

In Minnesota, a July 1995 RFP deliberately separated the process of preparing the initial proposal and the community support proposal.  As the RFP states, “the purpose of allowing proposers the option of splitting their proposals into two parts is to permit the flexibility of developing an initial proposal -- an inherently competitive process among industry members -- without simultaneously requiring evidence of community support -- an inherently public process among community constituencies.”

In Oregon, extensive public outreach by ODOT resulted in less public opposition to toll roads than has been experienced in many other states.  The State is conducting its own outreach efforts, which will lay the groundwork for future P3 arrangements. In addition, consideration of alternative models of highway development and substantial study undertaken by ODOT will help gather support for whatever model is ultimately adopted.

In Washington, the program left much of the outreach to the proposers and the public at large was not adequately brought into the process (the new legislators to some extent reflected disgruntled constituents).  This was reflected in a Seattle newspaper from June 1994 which wrote: "[the] State may like transportation projects, but what about the public?"

As the Washington experience shows, without careful, extensive outreach, the public is unlikely to:

- Recognize the transportation problem. Before the public will find it acceptable to use tolls and P3 to solve a transportation problem, they have to believe that there is a transportation problem that needs to be solved.  In addition, the projects proposed should have no overwhelming impediments, such as environmental or ROW issues, that would interfere with project development.

- Understand the true costs of the needed transportation improvements and the funding problem.  Individual project needs were understood, but while the transportation fund is adequate for most individual projects taken one at a time, most of the public did not really understand the problems facing WSDOT to assemble funds to construct needed transportation projects.  Conveying the funding shortfall -- both by portraying the high costs of transportation improvements, and contrasting it with the inadequate revenues -- might have convinced voters of the real need (just as Secretary Martinez of Virginia later did to communities in Virginia).  WSDOT bonding is limited and gas tax increments have failed six years in a row.  If WSDOT had been able to convey the concept that project needs were so huge that they dwarf gas tax revenues, this recognition might have been heightened.

- Understand and support the fact that the private sector will seek a return on its investment in meeting public transportation needs.  This was especially true because, due to financial considerations, proposers had concentrated on bridges and other projects that lacked viable alternate routes.  This improved the financial feasibility of these projects, but worsened their acceptability.  The public (and the DOT) need to understand that “cherry picking” is an element of P3.  The perception that private firms might profiteer off public needs is easy to develop and hard to refute.  The key is to understand that the private sector, while it needs to make a return on its investment, can provide net benefits to the state.

- Understand WHY a public-private arrangement may be better than a public sector only arrangement.  Partnership projects differ from traditional public projects, which have a long planning period and are financed with allocations of existing funds.  It must be understood that the private sector can help enable investment to continue to meet growing transportation needs.

Financing, risk allocation, and the division of public and private sector roles

There are two types of issues related to risk sharing and definition of roles that need to be addressed:  (1) who plays what role within the public sector; and (2) how financing is shared between the public and private sectors.  Who plays what role will depend, among other things, on attitude and expectations regarding risk and reward and who has the economic advantage to secure low cost capital, and to access capital at critical times.  Further, the public partner’s role also depends on the risk profile of the project.  In early implementation, many states did not consider these issues carefully.  Following are a few state experiences:

- The process used in Colorado, for instance, did not formally involve CoDOT, but locally initiated programs should involve the state.  While the CoDOT offered its services on more than one occasion, the E-470 Public Highway Authority did not show much interest in accepting help. The Authority board was not familiar with the nuances of project finance, but fortunately trusted the private partner, Morrison Knudsen’s (MK) expertise and familiarity with project finance to engage them as financier. Once MK took a more formal role in arranging the financing, however, they quickly approached CoDOT for assistance.

MK realized that the commercial bond markets would look for state support of a large revenue bond issue, especially where there was no precedent for this kind of financing. Over the 1992-1993 period, MK secured a $20 million loan from CoDOT that required a $20 million local match. The value of the loan was not as important as the demonstration of state support for the project that the cash loan provided.  While providing less than 3 percent of project cost, the loan went a long way to reassure investors of the public sector’s commitment to E-470 and the viability of the endeavor.  This kind of state support is critical to re-assure investors that a project of this magnitude is both needed and encouraged by the administration.

- In Virginia’s Greenway project, since greenfield development costs may be higher relative to other types of projects, public sector assistance may be needed upfront.  No state support was to be drawn upon under legislative terms, however, requiring significant private equity at the outset.

Other greenfield projects may need special assistance, such as back-stopping credit support.  Toll revenue estimates for Virginia’s Greenway project were based on projected real estate development beyond Dulles which slowed in the recession.  A state line of credit might have helped.

- In South Carolina, on the Conway Bypass RFP, some outside private sector firms felt that the proposer was being asked to do what was really the state’s responsibility: identifying and implementing tax structures and revenue sources.

- Washington DOT had the foresight to make the maximum rate of return to the private partner negotiable; it was not established beforehand.  Within this rate of return, the developer was free to establish and modify tolls and fares.  Incentive rates of return could also be negotiated, allowing increments to the baseline maximum rate of return, if the developer met certain safety or demand management goals.

Washington was willing to engage in direct financial participation to “address risk private capital markets are unable to accept.”  A revolving fund of $25 million was established.  Both revolving fund loans and any additional state funds, however, would need to be appropriated by the legislature.  The State was also willing to deploy staff and facilities for development of the project, but expected to be fully reimbursed for all of these expenses from project generated revenues.  This permitted the DOT to share in the early risk period where political risk was highest.

Building a new road is a long-term process, with very uncertain results.  California’s SR-125 was granted its franchise under AB-680 in 1991, after 1-2 years of application effort.  In early 1997, this project is very near to financing and construction, but by no means are these steps assured.  While the private partner, CTV, has (along with the real estate developers who donated land) been willing and able to sink considerable equity into this venture, the long lead time inherent in a greenfield road has increased the risk to the private partners considerably.  This has several implications:

- Other firms in the same situation may not have been willing or financially strong enough to take such a position.  Risk sharing needs to consider the nature of the risks involved and the profile of risks over time.  Where a DOT or local government feels this type of project is very important, it can reduce the risk to the private party by sharing some of this upfront risk, or by recognizing it in negotiations over rate of return.  To some extent this has happened: SANDAG has recently decided to fund the San Miguel Connector up-front through direct reimbursement to CTV (instead of over time as initially proposed);

- The rate of return may need to be re-negotiated or structured as a function of different outcomes.  The rate negotiated between CTV/SDELP and Caltrans was 18.5 percent.  Based on today's risk/reward profile, this limited return permitted to CTV/SDELP under its franchise may not be adequate, compared to the continuing possibility (in 1997) of a complete loss of significant equity capital expended (since 1989).  Note that a portfolio investment in NYSE stocks has earned about 25-35% annually for the past two years.

- The state’s contribution may need to reflect the type of project.  Under AB-680, Caltrans cannot deploy state funds.  Given the project’s greenfield nature, this may have been an unrealistic restriction that precludes good projects from getting done.  Indeed, start-up financial assistance may be necessary to keep private players interested.  SR-125 has required major up-front equity over about eight years so far, with no revenues in sight before about 2001.

Where cash support is not possible, other kinds of support can be provided by the public partner, such as a promise not to build competing roadways, or in-kind contributions. One of the key issues that arose in Colorado during financial consideration of the E-470 project was related to land use jurisdiction and planning.  CoDOT’s assistance here was crucial to maintain objectivity between competing interests.

Requiring private ownership of land may impose unnecessary risks on the private party. The state can contribute to a project up-front by using its powers to acquire ROW.  Virginia land acquisition for the Greenway proved difficult to finalize without any “taking” authority.

The “non-compete” clause must be clear in setting local priorities.  California’s SANDAG recognizes the need for SR-125 when it states:  "The relocation of the commercial port of entry to Otay Mesa and the NAFTA-related traffic growth is overwhelming the existing border transportation infrastructure."  SANDAG has been supportive but it also has many competing priorities that make desert build-out of less than compelling urgency.  For example, the widening of Otay Mesa Road to six lanes by 1998 was recently scheduled, evidence that both SANDAG and Otay Mesa recognize the urgent need to upgrade the major East-West SR 905 to serve border traffic.  Otay Mesa Road currently serves as an extension of SR 905 and is feeding traffic to/from I-805 and I-5, the two major North-South Interstate roads through San Diego.  While this improvement could stimulate further area growth, SR-905 also provides a free, indirect route into/out of the border crossing area competitive with SR-125.  Caltrans is restricted from developing competitive facilities, but in fact CTV has only limited non-compete protection as SANDAG moves forward with this expansion of SR 905.

# Issues Regarding Public and Private Sector Role Definitions

Three additional issues related to the designation of appropriate roles relate to; (1) who should conduct outreach efforts; (2) the appropriateness of private partners carrying out EIS-realted activities; and (3) the potential role of 63-20 corporations.  Each are discussed below.

Outreach

Even before outreach can be conducted, a state must determine who will conduct it andwho will take the lead.  In Washington, some felt that the public outreach needed to be conducted entirely by public agencies.  Requiring proposers to conduct outreach as part of the RFP process created contradictory goals.  Proposers were competing with each other and did not want to share too much information about their plans and their features.  On the other hand, the proposers are trying to gather support.  The proposers were generally successful at gathering support from local leaders, but not the public.  When surveys, focus groups, etc., from the private sector were released, they were  perceived as biased, because they were conducted by the private entity that stood to gain from the project.

EIS-Related Activities and Studies

Experience has shown that there are some roles and risks that the public partner should take.  In Washington, when funding was provided to the State to conduct engineering and environmental studies on the Tacoma Narrows Bridge, the state hired the proposer -- United Infrastructure -- to perform the studies.  Some regarded this as a conflict of interest, because the company that stood to benefit from the project would be conducting the EIS and other critical studies, and might be tempted to change any negative results.  Others felt that having UI do the environmental and engineering work was logical, because they would be undergoing the risk of having the project development halted if the studies were inadequate.

In California too, there was some outcry over an initial suggestion that CTV undertake the EIS, as community residents felt that the EIS would be biased.  Caltrans is now undertaking the EIS.  CTV officials suggested that this is one area of risk and cost that the public partner can and should assume as the state has a natural advantage here: the value of the risk it saves the private partner is worth more to that partner than what it costs the state.  Thus it can be valued as a contribution in excess of what it actually costs the state to undertake (effectively capturing some or all of the rent for the state).

Finally, the state should take a broad view in seeking clearances.  Environmental clearances are difficult, lengthy in duration, costly, and often a stumbling block.  States and private entities should seek a way to minimize the possibility for local, state, or federal objections and seek to obtain the highest clearance possible if there is any chance federal funds will be used at any time in the process.

In California, for instance, participants had assumed SR-125 would be privately funded with some support from SANDAG’s TransNet program.  Once they realized federal border crossing funds (and possibly credit support) will be needed, Caltrans had to revisit the EIS effort.

# States may also want to include a calendar “cut-off” date to limit late-stage environmental challenges.

63-20 Corporations

Several project sponsors, including Chesapeake, Virginia, are considering using a so-called “63-20 corporation” to structure public-private financing.  Here, projects can be financed with tax-exempt bonds, while attempting to maximize the benefits for both public and private participants by establishing a not-for-profit corporation to issue the debt.  These corporations, named for Revenue Ruling 63-20, are not formally under the control of either the government entity or the private partner.  Therefore, it is essentially important that public-private partners keep their interests in mind when crafting 63-20 arrangements.  A fuller description of 63-20 corporations is included in the appendix of this report.

# Relations with the private sector

Related to the definition of project roles between public and private parties is the ongoing relationship with private partners.  Issues related to attracting, maintaining, and negotiating terms of private sector involvement are discussed below.

# Attracting Private Involvement

Proposal-related costs should be controlled and set with an understanding of associated risk.  The private sector appreciated DelDOT’s and Virginia's graduated fee structure, which reduced development costs.  In Florida, however, private proposers were asked to pay $50,000 upfront.

Time to prepare a proposal is a real cost too.  Virginia intentionally selected a 30-day period for competing proposers.  This allowed proposers to put together a proposal if they were already considering the same project, but not enough time for competing proposers to “steal” an original concept developed by another firm.

Finally, the DOT needs to show real commitment to the P3 process upfront.  Arizona's legislation required full reimbursement for public services, such as police.  Proposers felt this reflected a mixed level of commitment by the DOT.

# Maintaining Private Sector Interest

To date, in Florida, there have been six proposals, none of which have been approved.  Two are still pending completion.  In several cases, the proposals never went beyond the first step of the process, because they were never completed.  In some cases, this was because local support was lacking.  Other proposals have not made it past step two (usually when a more detailed proposal is submitted).  Sometimes, proposers were not willing to pay the additional costs incurred by the State to review their proposals, often because they sensed a lack of commitment by the state.  The State has thus lost some credibility because the process is so loosely defined and not adhered to.

One factor that helped California’s AB-680 process succeed was continued assurances of commitment by Caltrans and the Governor. Caltrans placed facilitators in each major urban district to facilitate proposal preparation.  Franchise agreements were negotiated by high-level state negotiators, who had the authority to approve contracts.  Individual projects were helped by demonstration of local commitment -- for example, the Orange County Transportation Authority’s financial commitment to SR-91 helped move the project forward.

# Negotiating With The Private Sector

The negotiations process can make the difference between a successful P3 initiative and one that is a complete failure.  Early procedural definition is a key supporting element as well.  Virginia, for instance, invested a significant amount of administrative time in developing its first agreement, but expects that future agreements will benefit from this investment.  Following are several key elements to effecting producing a productive negotiation framework.

# Establish A Framework For Evaluation and Selection

The key to negotiation appears to be flexibility: creating a framework that permits the private partner to achieve its goals, taking advantage of its ability to do things differently from the DOT.  Using performance standards allowed VDOT to establish a level of service required and minimizes the oversight necessary.  At the same time, it lets the private partner determine how it achieves required service levels.

The concept applies to Design/Build contracts as well.  Here too, it is critical to construct an agreement that evaluates the private party by its results, not the process or efforts employed to reach those results.  In practice, this means moving away from the traditional audit of activity during a billing period, where the private partner must demonstrate what was done to secure payment for services rendered.  It may be more helpful to spell out what results must be achieved by what dates, and to allow the private partner to determine the method by which it achieves those results.

In South Carolina, although the recommended proposal was identified during the selection process, the rank of the remaining three proposals was purposefully not revealed.  The goal was to eliminate the influence of politics in the Commission’s decision. If the negotiations were to fail, the panel would then re-present the remaining three to the Commission, with the original runner-up as the new recommended proposal.  This process gave the State negotiating power with the chosen team, because it allowed them to break off negotiations without abandoning the project.  Each of the remaining three teams believed that they were runner-up because the ranking was never revealed.  This kept the other teams prepared to re-enter the process if negotiations with the winner were to fail.

# Establishing A Fee Structure

It becomes important to negotiate a payment structure that provides stability to the private partner.  This can be done many ways, including partially divorcing the timing of payments from that activity of audit.

# Trust

Both sides must realize what is critical to the other party.  While there are no rules for establishing this trust, one private firm suggested that the initial negotiations take place privately between the DOT (and Attorney General’s office) and the team.  Once there is an initial agreement, each party should then turn to their respective legal teams to determine whether the agreement is satisfactory.  This clarifies the respective roles: the private partner and the DOT negotiate an agreement.  The legal counsel’s job is to make sure a negotiated contract is binding and fits within existing law.

Conclusion

This section highlighted key issues encountered with developing partnerships between the public and private sectors for the provision and maintenance of highway infrastructure.  Primarily, a wide base of support, effective coordination, and consistant communication are central to the success of P3 initiatives.  Without support from the affected locality, general public, and business sector, the project --even one that creates significant benefits under a P3 structure-- may not be able to overcome negative attacks initiated by internal or external forces.

With the necessary base of support, the ability to structure agreements between public entities and private parties codifying the basic framework of standards, assurances, warranties of performance, completion dates, and other commitments by either party becomes a more achievable challenge.  Achieving a workable agreement that is acceptable to all parties, stands the scrutiny of regulatory control, and survives the test of financial marketablility is the final hurdle for developing public-private partnerships.

# review of state p3 programs

# INTRODUCTION

Over the last several years, a number of state transportation agencies have established processes for soliciting and accepting proposals from private firms to develop, operate, maintain, and even own surface transportation projects and services.  As of this writing, ten states have developed and at least partially implemented a statewide process for solicitation, acceptance, and review of proposals from the private sector for provision of surface transportation related services:

- Arizona

- California

- Delaware

- Florida

- Minnesota

- Oregon

- Puerto Rico

- South Carolina

- Virginia

- Washington

This overview examines key aspects of these states’ processes, including:

- Legislative History;

- Types of Arrangements Permitted;

- Procedures for Project Initiation and Selection;

- Fee Structure;

- Assistance Available from the Sponsoring State;

- Rates of Return and Other Terms;

- Public Involvement Provisions; and

- Lessons Learned.

Following the state by state review is a series of flow diagrams that illustrates each of the ten states’ solicitation and review process.  Additional information was gathered about eight states that have not adopted a statewide process or are in the beginning stages of such a process:

- Colorado

- Maryland

- Missouri

- New Jersey

- New York

- Pennsylvania

- Texas

- Utah

Because the information gathered about these states’ processes was less detailed, these states are covered in an abbreviated format.  Also, by the fact that a number of these states are actively in the process of developing programs, the information presented here will become outdated but is still instructive.  Maryland, for instance, is now crafting a statewide program to accept non-highway proposals.

This section is followed by a summary table of recent or active P3 projects for the states included in this study.  The table includes a few projects not directly addressed in this report, but for which information was available and informative.

STATE BY STATE REVIEW

# ARIZONA

The State of Arizona initially passed enabling legislation in 1992, allowing ADOT to enter into partnerships with private entities for the identification and development of up to four toll-roads and other transportation projects.  In response to a 1992 RFP, the State received ten proposals from seven developer consortia, including a comprehensive proposal from the firm, HDR, Inc., for a series of planned highways around Phoenix.  Three of these proposals were selected for further development and negotiation; in response to significant public opposition, however, all three ultimately were canceled.  Another unsolicited toll road proposal  was also received from HDR in November, 1992, but ultimately was withdrawn by the developer after a dispute over whether the proposal met requirements established by the legislation and associated guidelines.

In February, 1996, ADOT issued an RFP for one of the projects in their long range plan, VUE-2000, for the South Mountain Freeway.  In addition, the State received another unsolicited proposal from HDR in August, 1996 for construction of automated high-occupancy toll lanes in eastern Phoenix (including most of the roadways from the earlier proposal, with the exclusion of the South Mountain Freeway).  The State is currently attempting to negotiate to develop the South Mountain Freeway project as a public-private partnership.

Legislative History:  Arizona in the 1980s was faced with rapid development in the Phoenix area.  Adding to the transportation funding gap was the fact that growth outpaced the collection of sales tax revenue, and sufficient funds were not available for construction of planned highway projects in Phoenix.  Arizona determined that private involvement, specifically in toll roads, would enable faster development of highway projects. The 1992 legislation was amended in 1995 to remove a provision that made the State responsible for any default on the part of the proposer, and to increase opportunities for local government and public involvement.  The amendments also permit the State to acquire the ROW on behalf of the private sector, and to fund construction of complementary highway interchanges.

Arrangements Permitted:  Under the revised enabling legislation, there are two separate tracks. Under Article 1, the transportation facility will be owned by the State.  Under Article 2, the facility may be privately-owned or State-owned, depending on the arrangement negotiated.

Initiation of P3 Proposals:  Under Article 1, the State must solicit proposals for private construction/operation of any transportation facility.  Under Article 2, the State may request proposals, or private operators may initiate proposals.

Selection Process & Selection Criteria:  Under both Article 1 and 2, the Arizona review process is two-tiered.  The first review is conducted by a panel of in-house technical experts from ADOT plus financial experts, citizens, and representatives from all affected jurisdictions.  Each proposal is reviewed for three basic criteria:  technical feasibility; financial feasibility; and political/social desirability (includes environmental and economic issues).  After reviewing the proposal, the panel makes its recommendation to the Management Review Committee (MRC).  The MRC, in turn, studies and accepts, rejects, or asks the proposer for additional information.  They, in turn, make the final recommendation to the State Transportation Board.  With Board approval, negotiations with the developer can begin.  Final Board approval, however, is contingent on public support.

Fee Structure:  No fees are specified in either the legislation or the RFPs issued by ADOT; however, under both Articles 1 and 2, applicants are required to reimburse ADOT for administrative expenses after a contract is signed.

Assistance Available from the State:  Under Article 1, the State may exercise eminent domain, undertake liability, and provide law enforcement and inspection services as with any other transportation facility.  Under Article 2, the State is not permitted to exercise eminent domain; the private entity must obtain local agreements and conduct public outreach on its own.  If the private entity owns the facility, it must also purchase its own insurance, and contract with state and local government for law enforcement services.

Rate of Return and Other Terms:  The State is not involved in setting rates of return, and plans to allow market forces to determine toll rates.  The State and the private partner will also negotiate the term of the agreement; no limitation is specified.  Under Article 1, no uses for excess toll revenue are specified: under Article 2, excess toll revenue must be used for improving roadways affected by the facility.

Public Involvement Provisions:  The process requires the proposer to consider public support from the beginning.  The RFP requires a broad, general public participation plan to be submitted with the proposal.  A public involvement strategy is then negotiated between ADOT and the proposer.  Concurrent with negotiations between the State and the developer, the developer must put into effect the negotiated public involvement strategy.  During this period, approvals from the affected jurisdictions must be obtained.  If public support is not forthcoming, the State Transportation Board approval of the project becomes null and void, terminating the project (each MPO also has the right to vote to concur or oppose, but their vote is advisory, not binding).

The legislation itself was also used to overcome public opposition.  It included a clause permitting any user of a toll facility developed under this process to seek a refund of gas taxes paid while using this facility.  It is not clear what impact this provision has had on potential P3 arrangements, but it appears to be unique.  ADOT’s legislation also includes a clause requiring any toll roads proposed to have a “reasonable free alternate route”.  While private respondents did not specifically mention this provision as a problem, it will likely reduce the financial feasibility of some roads because users inevitably would have access to alternate routes to avoid paying the tolls.

Lessons Learned:  Initially, implementation of P3 legislation in Arizona was hampered by public opposition, which some private proposers attributed to inadequate public outreach in the initial program.  Public opposition was also heightened by a shortfall in local sales tax revenues, which were initially intended to fund the construction of many of the highway facilities now proposed as toll roads.  The public had accepted the tax increase on the premise that the promised facilities would be built, and were not prepared to pay tolls in addition to the tax increase.  In addition, local contractors were concerned about projects being awarded to large, out-of-state firms.

ADOT felt the process would have worked better if private proposers had focused on smaller sections; initial proposals received from private developers were too ambitious and comprehensive.  ADOT would also have preferred to have more control over project selection.  Although ADOT will continue to permit unsolicited proposals, ADOT will attempt to screen them through a letter of intent process.  ADOT has also worked with the private sector to develop a set of guidelines clarifying expectations regarding proposals.  ADOT and private respondents also felt that proposers should be educated as to the extensive federal and state environmental and legal requirements, so that proposers will recognize the time and effort required to bring a proposal into reality.

The private sector found the local jurisdiction veto clause to be a “deal breaker” because it introduced a serious element of risk even after the final approval had been obtained at the state level.  Some proposers felt that ADOT’s process also contained an unintentional “feedback loop”.  Proposers could respond to an RFP, and one would be selected.  Unsuccessful proposers could then submit another unsolicited proposal, which the law would require ADOT to issue another RFP even if the DOT was not interested in the project.  ADOT would have preferred to have had the flexibility to initially evaluate the proposals before having to issue an RFP.

Private respondents also felt that the 60-day period allowed for responses to RFPs issued in response to unsolicited proposals was too short, although it is consistent with response periods for other RFPs issued by ADOT.  Finally, private respondents also felt that required reimbursement for public services, such as police, reduces the sense of commitment from the public sector.

# CALIFORNIA

The State of California passed enabling legislation in 1989 (Assembly Bill 680), one of the first such laws in the country, allowing the State to enter into partnerships with private firms for the development of privately financed transporation projects.  The stated purpose of AB 680 was to get private capital into public projects for highways, and to get roads built faster than could have been done with public funds.  Under the law, the State would allow no more than four P3 projects, and required at least one in both the northern and southern parts of the State.  As of December, 1996, one project was completed, and three are in various stages of development.

Legislative History:  The California Department of Transportation (Caltrans) was the major proponent of the AB 680 legislation which passed in July, 1989.  Although the legislation itself did not enjoy broad support, it was attached to a larger piece of legislation with strong backing, and thus passed easily.

Arrangements Permitted:  The legislation allows solely privately funded Build-Transfer-Operate  (BTO) projects.

Initiation of P3 Proposals:  AB 680 states that “the department may solicit proposals and enter into agreements with private entities . . .”  for the purpose of developing four demonstration P3 projects.  Caltrans issued Requests for Qualifications in order to solicit responses from the private sector. Private consortia came forward with projects that were unsolicited as opposed to identified by the State.

Review and Selection Process:  Project specifications are reviewed to ensure they comply with department  standards for state projects.  A project’s competitiveness will be enhanced by being responsive to the broadest set of relevant interests, such as commerce, transit, environmental, local land use, state-of-the-art traffic operations technology, and similar considerations.

Fee Structure:  All proposers were required to enclose a check for $50,000 with their proposals; however, only the checks for the four successful proposers were deposited after selection.  These funds are for administrative costs associated with proposal evaluation and development.

Selection Criteria and Negotiation:  Proposals were scored on criteria including innovation, environmental impact minimization, ease of implementation, local support, etc.  Eight proposals were received for seven projects (two proposers picked the same project).  A panel of Caltrans staff from various disciplines and one outside reviewer evaluated the applications.

Four proposals were chosen: the SR-91 Project, in operation since January 1996; the SR-57 project, which has experienced financing troubles in part because of the bankruptcy of Orange County; SR-125, for which the State took over the environmental review process following a community challenge and is nearing completion of the final EIR/EIS; and the Mid-State Tollway, a new roadway in the San Francisco Bay area, which has also experienced community opposition.

Final agreements between the State and the winners were signed before the new Governor entered office.  Both Caltrans and the proposers were concerned that the change of administration might alter the process.

Assistance Available from the State:  No State  funds can be used, and the State will not provide credit enhancements or risk sharing.  The private partner also must reimburse the State for initial development costs, such as design, engineering, and environmental review, as well as ongoing maintenance and policing costs.  However, the State did provide the private partner in the SR-91 project favorable lease terms for the median right-of-way.

Rate of Return and Other Terms:  All projects are to be Build-Transfer-Operate (BTO), meaning that the private firm will turn the facility over to the State upon completion, lease it back, and operate it for a maximum of 35 years.  Operators can set and collect tolls.  However, profit levels have beeen individually negotiated with Caltrans, and any toll revenue received in excess of operating costs, financing costs, and agreed private return, must be paid into the State Highway Account.

Public Involvement Provisions:  The AB 680 legislation does not articulate a specific process for public involvement.

Lessons Learned:  One factor that helped the AB 680 process succeed was continued assurances of commitment by Caltrans and the California Governor. Caltrans placed personnel in each major urban district to facilitate proposal preparation.  Franchise agreements were negotiated by high-level State negotiators, who had the authority to approve contracts.  Individual projects were helped by demonstration of local commitment -- for example, the Orange County Transportation Authority’s financial commitment to SR-91 in the form of subordinated debt helped move the project forward.

The State’s program was also successful because of the widespread public recognition of the need for improvements, as well as successful outreach to explain that traditional funding was not available.

# DELAWARE

The State of Delaware passed enabling legislation in 1995 (House Bill No. 177, April 13th, 1995)  permitting the DOT to solicit proposals for public-private partnerships in any form.  DelDOT issued an RFP in March, 1996, and received two responses.  Both proposals involved accelerating completion of a partially completed toll road, SR 1.  As of this report, no further RFPs have been issued, and no further proposals have been received.

Legislative History and Structure:  The catalyst behind the development and passage of P3 legislation was prompted by a group of developers who recognized the Department's desire to shift to full-cost pricing for transportation services.  DelDOT viewed these pricing policies as more equitable than existing funding means.  The State also sought to expand its financial capabilities over the long term, and provide critical transportation services in an efficient and timely manner.

Arrangements Permitted:  The legislation permits both Build-Operate-Transfer (BOT) and Build-Transfer-Operate (BTO) arrangements.  Under BTO, the State owns the project upon completion.  The private partner may then lease the project back from the State for up to 50 years.  Under BOT, the State retains ultimate ownership of the project and transfers at least some part of the risk of providing and/or operating the project to the private partner.  DelDOT also was prepared to consider other arrangements excluding full private ownership.

Initiation of P3 Proposals:  The Delaware legislation authorizes the DOT Secretary to “entertain, solicit, evaluate, negotiate, and administer innovative agreements with the private sector” for up to four demonstration projects, and requires the Secretary to issue an RFP requesting proposals for public-private partnerships.

Review and Selection Process:  The Delaware legislation requires that projects be selected by a Demonstration Project Committee consisting of the DOT Secretary, Director of Financial Management, Chief Engineer, and four other individuals designated by the DOT Secretary.  Each proposal is weighed on its own merits and ranked according to the selection criteria stipulated in the RFP.

Fee Structure:  Recognizing that private firms wanted to limit up-front development costs, DelDOT designed an incremental fee structure for the proposal process.  Under the fee structure, developers were to pay $5,000 to submit proposals, and an additional $10,000 if they were short-listed.  Another $35,000 would be required if a proposal was to be carried forward.

Selection Criteria and Negotiation:  In the March, 1996 RFP, criteria included: understanding the intent of the RFP; the proposal’s value to Delaware; the project approach; the firm and project team; management approach to the partnership with DelDOT; and financial strength of the project team.  After selection, proposals must be approved by the local Metropolitan Planning Organization and the Committee on Transportation, as well as the Joint Bond Bill Committee and the full General Assembly.

Assistance Available from the State: As part of a March 1996 solicitation, Delaware was willing to contribute $15 million in financial assistance.  DelDOT also stated that it would consider assisting with upfront, initial development efforts (via monetary and non-monetary contributions), assisting proposers with rating agency presentations, in-kind contributions, and high-risk activities such as environmental assessment or community participation and outreach.

Rate of Return and Other Terms:  The final agreement could include alternative rates of return, depending on the proposed partnership structure.  A maximum rate of return is to be negotiated under the agreement, which can last for up to 50 years.

Public Involvement Provisions:  Following project selection, a two-month outreach period occurs to allow DelDOT and the selected partner to build public support, and incorporate input from the general public as well as those directly affected by the project.  There is no specific public approval process; however, it is assumed that the vote in the General Assembly will reflect the opinions of the constituents represented by the members of the Assembly.

Lessons Learned:  DelDOT would have preferred a process that gave them more control over project selection.  The two proposals received called for accelerating the completion of a tolled commuter route, SR1, designed to shift through traffic off of routes 13 and 113.  The same political pressures that drove the legislation further drove the DOT to retain an open scope even though they feared they would simply receive proposals to complete SR1, which is exactly what happened. The DOT would have preferred to receive proposals related to managed development and transit.  Acceleration of SR1 did not provide sufficient value to the State relating to in-house development.  The requirement of private financial participation that was part of Delaware’s enabling legislation also limited the State’s willingness to structure the arrangement as a 63-20 corporation with access to tax-exempt debt.

In addition, the Secretary did not finalize the members of her selection committee until well into the process.  Earlier discussions between that group and the P3 working group in the Department may have facilitated a smoother process.

The private sector appreciated DelDOT’s graduated fee structure, which reduced development costs.

# FLORIDA

The State of Florida passed enabling legislation in 1991, and had received several proposals by the end of 1996.  For various reasons (including lack of local support and developer withdrawal), none of the projects had begun construction.  Under the 1991 legislation, FLDOT can accept proposals for all modes of transportation, and for many P3 arrangements, such as full private ownership, turnkey and design-build-operate, and contract operations and maintenance.

Legislative History:  Florida’s unprecedented growth has outpaced the State’s ability to keep up with infrastructure needs.  As a result of the need for local bodies to make sure available infrastructure allowed development and tax-base expansion, local authorities were formed to establish road financing and respond to other infrastructure needs and this system has worked well.  The 1991 legislation was a formalization of the process and an attempt to apply statewide rules to the roles of public authorities.  The State amended the legislation in 1994, allowing the investment of public funds, but only in a case of “overriding public interest.” In addition, the latitude for proposals was broadened to allow proposals for building, operating, owning, or financing a facility.

Arrangements Permitted:  Florida will accept private sector proposals for building, operating, owning, or financing any transportation facility.

Initiation of P3 Proposals:  In Florida, the private sector initiates all proposals.  Any proposer can propose anything at any time, as long as the complete proposal is received by FLDOT 180 days before the legislative session begins, for its consideration in that session.

Review and Selection Process:  The FLDOT rules establish a three part, open-ended, continuous process.  First, the FLDOT must accept a complete proposal.  Complete proposals must be received by FLDOT at least 180 days before the beginning of the state legislative session.  The review committee is made up of FLDOT staff and includes an eight-member technical review group, a financial review group, and a standing six-member Executive Review Team (comprised of the District Secretary and five senior staff from central office) which oversees the technical teams.

Proposals first undergo a preliminary review, for potential legal conflicts, proposal content, team qualifications, demand for the project, project benefits, general environmental impacts and mitigation measures.  The teams also review business and functional plans for the facility, and ensure that the proposal is consistent with state and local plans and contains letters of support from local jurisdictions.

Unlike many other states, which have exempted the P3 process from certain state laws, notably procurement laws, Florida requires proposers to meet the same legal requirements that the DOT would have to meet if it were building the facility, unless they can demonstrate that suspending specific laws in their particular case are “in the best interests of the public.”

The “compliance with all laws” rule includes competitive bidding for contracting jobs.  Pre-selected teams of designers-builders, etc. may or may not be acceptable, depending on the individual case.  Consortia are allowed, but pre-selected contractors are not. An iterative process results, in which the State informs the proposer what needs to be modified in order to meet legal requirements, and then the proposer must resubmit.  This process ends only when the State is satisfied that all laws are met or the proposer has made a convincing case as to why it is in the public’s best interest to suspend certain legal requirements for their particular case.

Once the DOT is satisfied with the completeness and legality of the proposal, detailed review begins to test feasibility and soundness of the project.  The basic test for the proposal is: “Is it in the public’s best interest?”  Proposals must not cause any additional cost to government or service disruptions which might be experienced by the traveling public.  If state funds are to be used in the project, it must have an “overriding public interest.”

The review teams (augmented by external financial and engineering consultants) make a recommendation to FLDOT’s Secretary.  After approval of the Secretary, the legislature must approve the project before it can go forward.

Fee Structure:  Proposing firms are required to pay a $50,000 fee to cover the expenses state and local governments may incur in reviewing the proposal.  If the costs to the governments exceed the $50,000, the proposer is required to pay the difference.

Selection Criteria and Negotiation:  Negotiations take place throughout the process.  In the proposal process, there is discussion between the DOT and the proposer about what is legal and what exemptions might be allowed.  There is also negotiation in the crafting of the legislation, between the proposer’s and the State’s lawyers.  Finally, the specific implementation negotiation takes place during the franchise agreement stage.

Assistance Available from the State:  Grants, assumption of liability risks, police and other public services may be provided if need is sufficient.  The law allows the State to put actual dollars into the project, even to take an equity stake, but there is no pool of money set aside specifically for this purpose.  Which party should assume liability is also negotiable, but policing costs must be reimbursed by the private entity unless they can prove the State has an “overriding state interest.”  The State is also willing to negotiate for the use of its power of eminent domain.

Rate of Return and Other Terms:  Rates of return are negotiated, and the State expects to have some control over the setting of tolls and fees by fixing them in the franchise agreement.  The State also expects to own the facility after 30 or 40 years or to negotiate a BTO arrangement.

Public Involvement Provisions:  In submitting a proposal, a private firm must provide documentation of public support for the project.  This section of the proposal is used in the evaluation and selection process.

Lessons Learned:  Three main lessons can be learned from Florida’s experience to date.  First, the $50,000 upfront fee was far too high.  Second, no proposals have been implemented to date.  The reasons given range from developer withdrawal to lack of public support.  In reality, the existence of the local authorities for transportation projects may mitigate the need or opportunity for private service provision.  Finally, the program’s "compliance with all laws" provision has acted as a disincentive and adds time and expense to the overall proposal process.

# MINNESOTA

The State of Minnesota, following the lead of larger states where transportation demand had exceeded supply -- and existing resources -- began considering private development of toll roads to attract private capital to the State and to provide needed infrastructure sooner, without relying on slower, more traditional pay-as-you go financing for roads.  At the close of 1996, four projects had been proposed, all of which were halted by political or public opposition.  One proposal, a tolled truck-only highway across the northern region of Minnesota, was rejected outright.  The three remaining projects were considered more feasible, and have been delayed by continuing negotiations.

Legislative History:  The State of Minnesota adopted P3 enabling legislation in 1993, creating the “Toll Facilities through Public-Private Initiative Program”.  The law established Minnesota DOT’s and other transportation authorities’ legal ability to form partnerships with the private sector.  Due to a strong opposition to tolls, the enabling bill passed in the House of Representatives by a slim, one vote majority.

Arrangements Permitted:  MNDOT is willing to consider tolling of new or existing highways, under any mode of ownership or operation, approved by the MNDOT Commissioner.  Ownership may be with or without reversion of title; operation may be under lease, management contract, or toll concession; and may involve Build-Operate-Transfer (BOT) or Build-Transfer-Operate (BTO) arrangements.

Initiation of P3 Proposals:  Proposals can be initiated by a public sector RFP or by the private sector, although to date no unsolicited proposals have been received.  Minnesota published an RFP in July, 1995 inviting firms to propose any kind of public-private arrangement (except contract operations and maintenance).  Five consortia responded (two for the same project), and one proposal by InterWest, for an 11-mile toll road from suburban Eden Prairie to southwest Minneapolis-St. Paul, was accepted for negotiation.  One was rejected outright, and as of this report three others were under consideration.

The proposer must engage in whatever public discourse and outreach they see fit in order to establish that their proposal is in the public interest and is supported by the public.  If necessary, technical proposals may be modified following the outreach process.  The proposer must prove public interest and public support to the DOT.  Then, the application will be complete and subsequently reviewed by the State.

The InterWest project, a BTO arrangement which would blend public equity and toll-backed revenue bonds, cleared the support hearings in three of the four communities.  The fourth community, Eden Prairie, vetoed the project.  The State and InterWest are working to modify the proposal to meet Eden Prairie’s approval.  Another project, Highway 212, will construct a new corridor that passes through largely undeveloped areas outside the twin cities.  Cost is estimated at $200 million.  Over 70 percent of the project financing will come from bonds and subordinated loans from the State.  The remainder may come from public equity.

Selection Criteria and Negotiation:  Projects are evaluated by a combination of criteria.  A community support proposal must be included in the project proposal before the State will consider it for negotiations.

Fee Structure:  Proposals for projects with anticipated total capital costs valued at or below $10 million must pay a fee of $7,500; proposals for projects with anticipated total capital costs valued above $10 million must pay $15,000.  Upon selection, all proposals must pay an additional fee of $20,000.

Assistance Available from the State:  The terms of Minnesota’s RFP did not detail the degree to which the State would assist the private firm.  Grants, lines of credit, assumption of liability risks, ROW acquisition, operations and maintenance, police and other services may all be negotiated.  No form of state assistance was prohibited by the RFP.  The RFP also did not specify a term for the arrangements.

Rate of Return and Other Terms:  The rate of return is subject to negotiation, but will be based on the relative risks and potential rewards of the project, current economic conditions, and other factors that MNDOT deems relevant.  The legislation specifically allows toll rates that vary by time of day, vehicle characteristics and other factors.

Public Involvement Provisions:  Any affected community has veto power over any project for thirty days after contract negotiations are final.

Lessons Learned:  First and foremost, the provision that allows for any affected community to have veto power is unacceptable to many firms because of the obvious risk involved.

In the July, 1995 RFP, MNDOT deliberately separated the process of preparing the initial proposal and the community support proposal, recognizing the need for a strong public role in the latter.  As the RFP states, “the purpose of allowing proposers the option of splitting their proposals into two parts is to permit the flexibility of developing an initial proposal -- an inherently competitive process among industry members -- without simultaneously requiring evidence of community support -- an inherently public process among community constituencies.”

# OREGON

Senate Bill 626, passed by the Oregon Legislature in 1995, creates the opportunity to fund transportation projects with new and innovative techniques, including public-private partnerships.  The legislation enables the Oregon Department of Transportation (ODOT) to combine local, state, federal, and private resources to advance projects that may take decades to complete with traditional funding.  It also allows the operation of tollway facilities as one means of generating revenue to finance the construction of new roads and bridges.

The legislation does not definitively indicate that the Department will issue an RFP to private sector respondents.  Instead,  the legislation dictates that ODOT will conduct several studies to determine an appropriate mix of public and private responsibilities and resources.  This analysis includes identification of revenue forecasts (based on anticipated traffic volumes), conceptual cost estimates based on facility types, financing options and potential revenue sources, needs for additional analysis, policies, and/or legislation, ways of using P3 to optimize transportation finance, and the relationship of P3 to the State’s decision-making process.  This is intended to help prepare the DOT to evaluate submitted proposals.

Legislative History:  Oregon’s P3 legislation identifies two projects for immediate consideration, the Newberg-Dundee Bypass and the Tualitan-Sherwood Connector.  ODOT will have to seek specific legislative approval to undertake any other projects.

Arrangements Permitted:  ODOT is considering a variety of institutional models, including traditional DOT development and operation; a public franchise, where the DOT enters into a design-build contract with 100 percent public financing; a private franchise, where the DOT enters into a design-build and operate agreement with a mix of public and private financing; or a private franchise with 100 percent private financing.

Initiation of P3 Proposals:  The legislation states “tollway projects may be initiated by the Department of Transportation, by a unit of government having an interest in the installation of a tollway, or by a private entity interested in constructing or operating a tollway project.”

Review and Selection Process:  Projects are reviewed by the DOT and governments having jurisdiction over the land the toll road crosses.  The legislation states, “the department may award any contract, franchise, license or agreement related to a tollway project. . . .” under a competitive process or by private negotiation.

Selection Criteria and Negotiation:  Factors that will consider in addition to the proposer’s estimate of project cost include quality of design (structural integrity, future maintenance cost), aesthetics, capacity, safety factors such as lane width, efficiency of toll collection, the extent to which small businesses will participate, financial stability of the proposer, and experience in similar projects.

Assistance Available from the State:  SB 626 authorizes the State to use funds in the tollway account to finance preliminary studies and reports, acquire land, make loans or provide credit enhancement to private entities, and to pay oversight and administrative costs.

Rate of Return and Other Terms:  Agreements will limit the tolls that may be collected by operators, but permit the operators to vary the tolls for different types of vehicles or users, or for travel during high or low use hours.  Forty years after completion of the tollway, title must revert to ODOT and tolls must be discontinued.

Public Involvement Provisions:  ODOT is required to adopt rules that consider the opinions of units of government encompassing or adjacent to the path of the proposed tollway project.

Lessons Learned:  Extensive public outreach by ODOT has resulted in less public opposition to toll roads than has been experienced in many other states.  The State is conducting its own outreach efforts, which will lay the groundwork for future P3 arrangements.

In addition, consideration of alternative models of highway development, and substantial study undertaken by ODOT will help gather support for whatever model is ultimately adopted.

# PUERTO RICO

In the 1980s, growth in the San Juan metropolitan area had exceeded the government’s ability to keep up with infrastructure required by the new development.  In particular, traffic between the Port of San Juan and the San Juan Airport presented serious congestion, inconvenience, delays, and hazards.  The need arose swiftly, and the Puerto Rico DOT was determined to respond quickly.  Instead of relying on the traditional process, a cumbersome and slow pay-as-you-go public financing, transportation officials set up a public-private partnership. The projects were initiated by the Puerto Rico planning board.  The planning board issued RFPs for specific projects.  Two partnerships had been proposed by the end of 1996.  One of the projects, a toll bridge in San Juan, opened to traffic in 1993.

Legislative History: Puerto Rico’s legislation was passed in 1990, after Puerto Rico had already issued project RFPs, when bond attorneys and others saw potential litigation barriers if the projects were to be undertaken without first establishing the legality of public-private partnerships.

Arrangements Permitted:  Puerto Rico legislation allows contracting with private entities to construct, operate, and maintain bridges, highways, avenues, and expressways, as well as for project financing.

Initiation of P3 Proposals:  The legislation does not specify whether proposals must be solicited; however, projects proposed to date have been in response to RFPs issued by the planning board.

Review and Selection Process:  The legislation calls for creation of an Adjudication Board to award contracts, assure compliance with regulations, procedures, laws and by-laws, and report to the Governor and Legislative Assembly on bids and contracts.

Selection Criteria and Negotiation:  The legislation does not specify criteria for the Adjudication Board.

Assistance Available from the State:  The Commonwealth of Puerto Rico will acquire right-of-way on behalf of the private partner.  Otherwise, no form of assistance is mentioned in the legislation.

Rate of Return and Other Terms:  The legislation does not specify restrictions on rates or return or tolls; however, the term of the contract is limited to 50 years.

Public Involvement Provisions:  No specific provision for public involvement is provided for in the legislation.  However, the public interest is represented by the Secretary of Transportation and Public Works, who must submit an annual report to the Governor of Puerto Rico and to the Legislative Assembly about the project.

Lessons Learned:  Puerto Rico passed enabling legislation after the P3 process had already begun, in order to quell investor fear of lawsuits and the potential of scaring off bond market investors.  This situation could have been avoided by passing enabling legislation prior to project implementation.

Tolls on the San Juan bridge were placed at $1.50.  Initially, there were concerns this was too high and would discourage motorists from using the new facility.  In the first years of the project, traffic was lower than projected by traffic forecasts used in project planning.  By the end of 1996, however, traffic had risen on the bridge and was generating expected levels of revenue.

# SOUTH CAROLINA

Faced with aging infrastructure, growing private sector interest in highway projects, and increased demand for roads, South Carolina began looking into the possibility of public-private partnerships.  The State was experiencing rapid growth, particularly in coastal areas where tourism was booming, and inland, where technology and manufacturing companies required greater infrastructure supply.

Transportation officials soon realized that the TIP contained several large projects that, while necessary to accommodate the continued rapid growth of the State, could not be readily financed with existing revenue sources.  They began to develop the P3 process because the size and imminent need for six identified projects (collectively worth $1.7 billion) made it necessary to go outside of the traditional highway program.  The State hoped that a design-build, or turnkey, approach would reduce the overall costs of developing these projects and result in faster economic development.  The legislation thus identified these six projects.

The State issued the first RFP for the Conway Bypass, one of six projects identified in the enabling legislation.  After a failed referendum to impose a one cent sales tax to fund the Bypass and other roads in the master plan, the project received funding through the State Infrastructure Bank (SIB) in January, 1998.  Ground was broken on January 19, 1998 for the 28.5-mile Conway Bypass project and it is expected to be completed by the year 2001.  This is the first major P3 project to be constructed in the State and it is also the first project to be funded by their SIB.

South Carolina also plans to pursue construction of a tolled, 17-mile Southern Connector loop linking two interstate roads south of Greenville under a P3 arrangement.  The project hopes to issue, using a nonprofit community development corporation, $192 million of tax-exempt debt.  The revenue bond financing would be the first by a private highway developer using a 63-20 corporation (see Appendix 2 for more information on 63-20s).  The State will pay $20 million for development costs as part of its commitment to the project.  Proceeds from the bond financing will cover the remainder of the project costs.

Legislative History:  The South Carolina Legislature passed enabling legislation for public-private partnerships in 1994.  The passage of the law resulted from the funding gap between what the State needed and what it could afford and the State Legislature's request to the DOT to consider tolling for new construction projects and some existing roads.  Legislators were generally receptive because the idea would help address needs through financial creativity, without requiring new taxes.

Arrangements Permitted:  The South Carolina DOT requested maximum latitude in the legislation to be able to respond to a wide variety of potential deals which might be offered by the private sector.  Although the projects themselves were pre-determined, the DOT wanted maximum flexibility for the private sector to be able to propose viable and creative solutions.  The DOT wanted to be able to make negotiation decisions internally, without having to go to the Legislature for approvals or accommodations.  The State recognized that a process which required legislative input at the proposal level would discourage the private sector from proposing.  The Legislature agreed to provide maximum negotiation power to the DOT, passing a broad law which even allowed the DOT to act as a banker, and to make deals with the private sector which might include a variety of financing ideas including tolls and development fees.   The State will consider design-build-operate and turnkey projects as potential P3 arrangements.

Initiation of P3 Proposals:  Proposals can only be initiated by a state-issued RFP.  South Carolina will not consider unsolicited proposals from the private sector.

Review and Selection Process:  A Committee selects proposing teams, based on financial feasibility, qualifications of management team, risks associated with the project, and quality assurances.  Projects are selected by merit, and the proposal selection process is designed to insulate the Committee from political influence.  Following approval of a recommended proposal by the Committee, an agreement is negotiated with the chosen team.

Selection Criteria and Negotiation:  The four proposals received in response to the Conway Bypass RFP were ranked using three criteria: 1) qualifications of the consortium, 2) relative value of the proposal (costs and benefits), and 3) speed of construction.  The latter was important because the need for the Conway Bypass was so acute.  Once the Committee had ranked the proposals, they were presented to the public and the Transportation Commission without revealing which proposals were made by which proposers.

The proposer selected for the Conway Bypass requested further specific legislation to allow the affected county to charge a one cent local option sales tax to be dedicated to the project.  The County and the proposer worked hard to push through the legislation.  Under the proposed legislation, any county would be able to charge a one cent sales tax as long as a specific transportation project is named by the County as the beneficiary of the funds, subject to local referendum.  The local referendum failed, however.

Assistance Available from the State:  All value added and risk sharing issues were open to negotiation, and the responsibility of the proposer to suggest. The State feels that it is better suited to acquire the right-of-way because it has the right of eminent domain, and has allowed the private sector to make use of this eminent domain through the P3 process.  A contingency fund, established by the developer, the DOT, and the County, will go to pay for any unforeseen problems (e.g., hurricanes, legal injunctions, etc.).  If the contingency fund is not exhausted upon completion of the project, the remaining funds will be redistributed among the contributing parties.  The State will not be liable for any damages above the contingency fund.  Instead, the road will be given to the State with a three year full warranty, under which the developer will assume all costs for any rebuilding or repair resulting from inadequate quality of construction or design.  The State may further agree to assume liability risks, assist with ROW acquisition, and help with police protection and other services.

In the case of the Conway Bypass, the State was able to contribute the EIS and various permits to the developer to add value.  The State will also police the completed facility.

Rate of Return and Other Terms:  No limitations on rate of return, toll rates, or term of agreement are specified in either the enabling legislation or the Conway Bypass RFP.

Public Involvement Provisions:  Any respondent to an RFP must comment on the public's reaction to the project outlined in the proposal.

Lessons Learned: Although the recommended proposal was identified during the process, the rank of the remaining three proposals was not revealed.  The goal was to eliminate the influence of politics in the Committee’s decision. If the negotiations were to fail, the panel would then re-present the remaining three to the Transportation Commission, with the original runner-up as the new recommended proposal.  This process gave the State negotiating power with the chosen team, because it allowed them to break off negotiations without abandoning the project.  Each of the remaining three teams believed that they were runner-up because the ranking was never revealed.  This kept the other teams prepared to re-enter the process if negotiations with the winner were to fail.

The private sector viewed the offer of in-kind contributions by the State as very important both because they indicate commitment, and because they increase the likelihood of success, thereby reducing risk for the proposer.  However, with regard to the Conway Bypass RFP, some outside private sector firms felt that the proposer was being asked to do what was really the State’s responsibility: identifying and implementing tax structures and revenue sources.  Other outside firms were concerned about the referendum process which accompanied the sales tax request.  As is the case with the failed referendum, these uncertainties were of great concern to private bidders.

Upon reflection, the DOT felt that the lack of outreach and involvement of local jurisdictions in the course of the process was the biggest shortcoming.  Individuals, while aware that they would be paying for the new facilities through tolls or fees, wanted to be more a part of developing the project package, both in the RFP stage and in the final negotiations with the winning proposer.  County and city councils felt left out of the process, robbing the project of important local support which comes from a sense of local ownership.

The State now realizes there must be more of a team effort between the State and the affected localities throughout the solicitation and proposal process.  No one should be left outside the process because this allows them to criticize from the outside.  All stakeholders, even the potential detractors must be brought into the circle through a partnering process, and they must be brought in at the beginning according to the State.  Early on, communication must be established between the proposers and the public.  The DOT suggests that proposers think like developers, not contractors.  The developer knows that they must build what the public wants or the project will not be a success.  This holds true for all transportation infrastructure.

South Carolina believes that the failure to build local support and bring all stakeholders into the process was one of the two basic mistakes made by Washington State.  The other was not identifying specific projects.  Unless there is a great need for a specific facility, there will be no sense of urgency among the public and there will be insufficient momentum for a successful P3 effort.  It is the State’s responsibility to know its needs and to identify which projects have the potential to be successful P3 efforts.

# VIRGINIA

Virginia passed statewide enabling legislation in 1995 (the Public-Private Transportation Act of 1995) establishing a procedure for entering into public-private partnerships for surface transportation.  To date, the Commonwealth has received at least 16 proposals, of which 11 are for outsourcing of maintenance or operations of facilities.

Legislative History: In 1994, an effort started concurrently in the DOT and the State Legislature to develop statewide transportation P3 legislation.  Although the Transportation Facilities Act of 1994 passed both houses, the effective date of the law was delayed by Governor George Allen until 1995 so that the incoming Transportation Commissioner and staff could review and revise the legislation.  Interested parties, including lawyers, investment bankers, engineers, construction firms and local government representatives, were all invited to provide input through public hearings, forums, and comments.  The 1995 legislation streamlined the P3 process, incorporated market forces, and allowed for non-toll road transportation projects.  It also included a requirement that projects be “compatible” with state and local transportation plans.  The redrafted legislation also eliminated the jurisdiction of the Corporation Commission over the projects.  The new law went into effect on July 1, 1995.

Initiation of P3 Proposals: Both solicited and unsolicited public-private partnership proposals may be accepted by any “Responsible Public Entity”, provided that that entity already would have the authority to construct the project under the standard process -- i.e., a city would not be able to accept a proposal to construct an interstate highway.  Virginia has an open structure that allows any private sector firm to propose anything to any level of government at any time.  It also allows any level of government to issue an RFP for a specific project or area, or to solicit ideas more formally and in a more competitive framework. When an unsolicited proposal is accepted, the Commonwealth posts a notice in major papers, on VDOT electronic bulletin boards, and in the State’s publications geared towards contractors.  A 30-day period follows, in which other firms can submit similar proposals in competition.

Review and Selection Process: Virginia’s review process consists of two steps.  First, the proposer submits a “Conceptual Proposal” and a $5,000 fee to a committee composed of the DOT’s Chief Engineer, Assistant Commissioner of Operations, and Assistant Commissioner of Finance. The initial review focuses on the proposer’s (and competitors, if any) qualifications and the proposal’s technical and financial feasibility.  Following initial review, the Commonwealth’s Transportation Board, may be asked to approve in concept one or more of the proposals.  A detailed proposal is then developed by the successful proposers and sent, along with a $20,000 fee, to the Public-Private Transportation Advisory Panel (PPTAP), which reviews the proposal in depth for viability and consistency with state and local goals.  The two-step process allows proposers to avoid giving detailed and proprietary information until a proposal has passed the conceptual stage, and has a greater chance of success.

Selection Criteria and Negotiation: Once the Public Private Transportation Advisory Panel makes a recommendation to the Commissioner on an approved proposal and upon selection by the Commissioner, negotiations for a comprehensive agreement between the Commissioner and the proposer can begin.  Nearly everything is open to negotiation.

Assistance Available from the State: Virginia’s position is that a proposer should not look to the Commonwealth to finance or share financing, but the State is willing to work hard to reduce the risk and add value to the process.  The Commonwealth is willing to negotiate the contribution of in-kind work, such as preliminary engineering, EIS analysis and approvals (if they have not already been obtained), and ROW acquisition.  The Commonwealth is also willing to negotiate how police costs would be covered.  Due to a large default of publicly backed toll roads in the early 1900s, the State’s constitution explicitly prohibits lending money or taking an equity stake in private ventures. VDOT is willing, however, to negotiate the loan of federal funds through the Virginia State Infrastructure Bank (SIB) which is part of the State’s Toll Facilities Revolving Account.

# Rate of Return and Other Terms: Rate of return, toll levels, and other issues are all open to negotiation.

Public Involvement Provisions: The initial conceptual proposals and detailed proposals must be sent by each proposer to all “affected jurisdictions”, which have a 60-day comment period after receipt of a detailed proposal in which to respond.  The general public is expected to comment through their local governments.

Lessons Learned: Virginia’s P3 law prohibits the tolling of existing roads unless the tolls will go to pay for major expansion or improvement of that facility.  The Commonwealth regarded these conditions as a major factor in gaining widespread support.  As a result, Virginia experienced no organized opposition to the statute.  Virginia’s decision to require projects that are “compatible” with state and local transportation plans gives the private sector enough leeway to propose projects that may not have occurred to transportation planners, but also gives the State the ability to go forward with projects that are in the best interests of the State.

Virginia intentionally selected a 30-day competitive period to give potential competing proposers enough time to put together a proposal if they were already considering the same project, but not enough time for competing proposers to “steal” an original concept developed by another firm.

Virginia invested a significant amount of administrative time in developing the first agreement under the new legislation, but expects that future agreements will benefit from this investment.

# WASHINGTON

Washington State was interested in engaging the private sector through a public-private partnership process in order to “provide the state with increased access to property development and project opportunities, [and] financial and development expertise, [while] allowing the state to use its limited resources for other needed projects [and] promot[ing] business and employment opportunities for Washington State residents.” The Washington Legislature unanimously approved a bill to make these recommendations law, and the bill was signed by the Governor on July 1, 1993.  Shortly following passage, a draft RFP was drawn up and distributed to 200 interested parties.  In January, 1994, the final RFP was issued concprrently with an extensipe national and international “solicitation of interest,” resulting in the issuance of the RFP to over 300 interested parties.  A pre-bid conference was held in February and attended by 200 private sector representatives.

The private sector formed consortia consisting of transportation, engineering, finance, marketing, environmental assessment and traffic analysis firms which explored many potential projects.  Fourteen projects were finally submitted on May 13, 1994.  WSDOT selected six of these projects for negotiation.  Of these six projects, two are no longer under consideration (S.R. 18 and Puget Sound Congestion Pricing); one (the Tacoma Narrows Bridge) is undergoing state-funded environmental and financial feasibility study; two (SR 520 and SR 522) are on hold until the Legislature appropriates funds for study; and one agreement has been signed for development of a series of Park-and-Ride lots in King County, Washington.

Legislative History:  Washington State began to consider private involvement as early as 1991, when the Transportation Policy Plan Steering Committee (an arm of the State Transportation Commission), set up a Subcommittee on Public Private Partnerships in Transportation.  The subcommittee suggested “the Legislature should authorize a program to allow the Secretary of the Department of Transportation to pursue and implement public-private initiatives for transportation capital improvements.”  It also suggested using community redevelopment financing to increase private sector investment, and the establishment of a revolving loan fund structured to take advantage of proposed public-private partnership provisions and funding opportunities under ISTEA.

The State Transportation Commission surveyed the general public and held public hearings, finding support for the idea.  Combined with the recommendations of the subcommittee, these findings encouraged the Commission to establish a second subcommittee to explore the legal, regulatory and administrative barriers to public private-partnerships.  This subcommittee recommended that WSDOT be “authorized to solicit proposals from the private sector and select up to six demonstration projects,” to be approved by the Commission and consistent with “plans, rules, regulations and statutes governing state transportation projects.”  The subcommittee also recommended “cooperation and consultation with affected jurisdictions,” and established the concepts of minimization of state liability and reimbursement for state services used to support the project.  Surveys and public forums following the efforts of this subcommittee identified continued public support.

A bill establishing the Transportation Revolving Fund passed both houses unanimously and was signed into law on March 30, 1994.

Initiation of P3 Proposals:  The law in Washington State directs the DOT to solicit proposals and develop six demonstration projects, but there was no guidance as to what the projects should be as long as they were “capital-related” and dealt with “the planning, construction, upgrading, or reconstruction of transportation systems and facilities.”  In fact, the law states, “proposals and demonstration projects may be selected by the public and private sectors at their discretion.”

The DOT developed an RFP process which solicited conceptual proposals, rather than full detailed proposals.  The process was designed to act as a funnel, attracting a number of proposals and narrowing them down to a few (six at the most) which would be approved for further consideration.

Review and Selection Process:  Each proposal first underwent a technical review by a review team of WSDOT technical experts.  Concurrently, a financial advisor was retained to review proposer financial qualifications and the proposed financial plans for each project.  The analyses by these two groups of each project became its Technical Evaluation Report.  All fourteen reports were submitted to the Project Review Board.

The Project Review Board consisted of the WSDOT Deputy Secretary, Deputy State Treasurer, Director of Revenue, and the Program Director.  They reviewed the 14 proposals, the attending Technical Evaluation Reports, and citizen letters submitted to WSDOT.  They also interviewed one proponent for each project.  Using all of this information, the Board ranked all 14 proposals and recommended 6 to the Secretary for approval.  Following the Secretary’s review of the Board’s report, the Transportation Commission was briefed on each of the 14 proposals, informed of the Secretary’s recommended six, and held public hearings.  In the end, the Commission approved the six recommended proposals and informed the DOT that they should engage the proposers in agreement negotiations.

The private sector was pleased with the coordinated state effort up to this point, but noted that supporters of P3 in the DOT, consumed with project negotiations, did not keep track of important legislative changes concerning the P3 program.  Many in the private sector believe that if supporters of P3 had briefed new legislators after the projects were selected to keep them informed and involved, the momentum might have been preserved.

Unlike many other states, in Washington the agreement between the State and the proposer is signed based on the conceptual proposal and “does not give developers a vested right to build and operate the proposed transportation facilities, [but rather] grants an opportunity to study and design the proposed facility and to complete the planning process required by law in order for WSDOT and other agencies to approve whether the facility should be built.”  In other words, agreements, and the final proposals which are subsequently drawn up, are contingent on various approvals through the normal state procedures for infrastructure projects.

The agreement does not bind the proposer to build the project, even after it has been through all approvals.  If the proposer wishes to pursue the proposal, it is at this point that they seek financing for right-of-way, final planning and specification for actual construction.  If project financing is secured, then construction can commence.

Selection Criteria and Negotiation:  Washington State’s RFP invited conceptual proposals, to be evaluated and ranked based on four basic criteria:  firm qualifications, including experience and financial capability to carry out the project (30 points); project characteristics, including concept, constructability, proposed financing, and compatibility with existing transportation systems and needs (30 points); community acceptability, including initial support and opposition, and plans to involve the public throughout project development (30 points); and finally, benefits to the state, including state transportation and economic development goals, and use of women and minority-owned firms (10 points).

Washington’s legislation provided a good deal of latitude to the DOT in negotiating agreements with project proposers, but established certain policy principles for the DOT to follow.  The State sought to minimize its liability, resulting in private ownership of the projects during the construction phase.  Ownership, however, would revert to the State upon completion of the project and would be leased back to the private concern for operations for up to fifty years.  There would be no guarantee in the agreements that the private firm would recoup its investment.

Assistance Available from the State: Unlike many states, Washington was willing to engage in direct financial participation to “address risk private capital markets are unable to accept.”  Any state funds, however, would need to be appropriated by the Legislature.  The State was also willing to negotiate the use of staff and facilities for development or operation of the project including maintenance, police, planning, traffic modeling, environmental study, design and right-of-way acquisition, but the State expected to be fully reimbursed for all of these expenses from project generated revenues.

To further a project, the DOT was authorized to “lease facilities, right-of-way, airspace, exercise its power of eminent domain, grant easements, permits, real property rights, negotiate the acquisition of right-of-way in excess of appraised value, etc.”  It was also authorized to “lease to the developer the airspace above or below their right-of-way of the transportation facility and grant the right of first refusal to undertake projects utilizing airspace owned by the State in the vicinity of the transportation facility.”  Non-competition clauses from other state transportation facilities could be negotiated provided they were not “unreasonable.”

Rate of Return and Other Terms:  Like most other states, a maximum rate of return was negotiated.  Within this rate of return, the developer was free to establish and modify tolls and fares.  The State would audit financial statements and appropriate any excess revenues collected above the negotiated rate of return.  Incentive rates of return could also be negotiated, allowing the developer to exceed the basic maximum rate of return.  The developer would be entitled to the higher rate if they met certain safety, performance, or transportation demand management goals which benefited the State or affected locality.

Public Involvement Provisions:  Public involvement was expected to take place under the normal public involvement process for state transportation project development.  Following the signing of agreements, the project must be adopted into Regional Transportation Plans, the Statewide Multimodal Transportation Plan, and for projects involving any federal funds, the State Transportation Improvement Program (TIP), as well as conform with the State Implementation Plan for Air Quality (SIP).  Normal EIS and permitting procedures follow.  All of these procedures involve normal public involvement and government approvals.

Lessons Learned:  In general, proposers liked the State’s design for the process, and found the State receptive to different proposals, and responsive to the needs of proposers.  WSDOT was successful at attracting bids from experienced teams with the financial and technical capability of fulfilling their proposals.  Most felt that the selection process was fair and unbiased, and resulted in selection of high-quality teams.

Some felt that the public outreach needed to be conducted entirely by public agencies.  Requiring proposers to conduct outreach as part of the RFP process created contradictory goals.  On the one hand, proposers were competing with each other and did not want to share too much information about their plans.  On the other hand, the proposers are trying to gather support.  The proposers were generally successful at gathering support from local leaders, but not the public.  When surveys and focus group results from the private sector were released, they were  perceived as biased, because they were conducted by the private entity that stood to gain from the project.

Many in the private sector believe that the State did not play an active enough role with the private sector in seeking public support or showing its own commitment to specific projects following project selection.  Washington relied on the standard public involvement process for an otherwise non-standard project process.  Many in the private sector believe that this resulted in public outreach which was too late, and too little public education overall.

According to one source, the public reaction could be explained by a combination of factors:

The public had not recognized the transportation problem: Before the public will find it acceptable to use tolls and a P3 structure to solve a transportation problem, they have to believe that there is a transportation problem that needs to be solved.  In addition, the projects proposed should have no overwhelming impediments, such as environmental or ROW issues, that would interfere with project development.

- The public did not understand the true costs of the needed transportation improvements.  Most of the public did not really understand the full costs of constructing the needed transportation projects.  Most of the public regard highways as free, and do not know what it really costs to construct, maintain, and operate highway facilities.

- The public had not recognized the funding problem.  In Washington, some voters had the perception that DOT was wasting its money, and did not really need to be seeking more revenue.  Conveying the funding shortfall -- both by portraying the high costs of transportation improvements, and contrasting it with the inadequate revenues -- might have convinced voters of the real need.

- The public had not accepted tolls as the correct revenue solution.  In Washington, the perception was “why don’t you just raise the gas tax,” even though increasing the gas tax would have met only a fraction of the needs.

Somehow, the public also did not fully acknowledge from the original legislation that it involved tolls (even though supporters claimed it was very clear). In a sense, residents supported the initiative in general but did not like the specifics.  The public also did not like the perception that the private sector was profiteering off of the public transportation needs.  This was especially true because, due to financial considerations, proposers had concentrated on bridges and other projects that lacked viable alternate routes.  This improved the financial feasibility of these projects, but worsened their acceptability, because voters disliked not having an option.

Another problem was that some perceived that no attempt was made to explain why a public-private arrangement was better than a public sector only arrangement.  Voters were not educated as to why these arrangements made good sense for the State -- whether the access to private capital was important, or greater private sector efficiency.  Some voters wondered, “if this is such a great idea, why doesn’t the DOT do it itself -- what added value are we receiving for the private sector involvement?”

Some Washington State voters also criticized the process because of the perception that it was begun “behind closed doors”, with WSDOT and proposers in collusion.  For example, the Puget MPO had not yet completed its regional plan before projects were accepted.  The MPO would have preferred a specific list of projects that could have been targeted to needs, rather than proposers’ interests .

Another issue for voters was that all of the projects were proposed in Western Washington.  Voters in this area perceived the process as unfair -- they did not understand why Western Washingtonians should pay tolls when the rest of the State gets gas tax money.  If WSDOT had been able to convey the concept that project needs were so huge that it would have dwarfed gas tax revenues, this perception potentially could have been lessened.

Finally, when funding was provided to the State to conduct engineering and environmental studies on the Tacoma Narrows Bridge, the State hired the proposer -- United Infrastructure -- to perform the studies.  Some regarded this as a conflict of interest, because the company that stood to benefit from the project would be conducting the EIS and other critical studies, and might be tempted to alter or minimize any negative results.  Others felt that having UI do the environmental and engineering work was logical, because they would be undergoing the risk of having the project development halted if the studies were inadequate.

# FLOW diagrams

Exhibits 1 through 9 present flow charts of the state processes reviewed in the preceding section.  Each chart presents the method for soliciting, reviewing, selecting, and negotiating proposals for public-private partnerships.  Because public outreach is such a critical issue in many P3 processes, the steps in which public outreach occurs are highlighted in each flow chart.

# OTHER STATES

# COLORADO

While Colorado is home to the E-470 beltway east of Denver, one of the most prominent P3 projects in 1996, the State DOT has not to date been active in P3 arrangements.  In 1987, Colorado passed the Public Highway Act.  This law was amended in 1993 to broaden the flexibility of public highway authority boundaries.  The Public Highway Act enabled municipalities to join together to create highway authorities within metropolitan regions of Colorado for the purpose of financing and constructing beltways and other transportation improvements.  Authorities may tax residents within a given boundary, in the form of tolls, highway expansion fees, and special assessment districts.  As is the case with E-470, authorities can enter into contracts with private companies for design-build contracts.

Under the Public Highway Act, public highway authorities can enter into agreements with private builders only after the State issues an RFP.  The RFP may be for highway projects or other kinds, such as rail or bus service.  Projects can be turnkey and design-build-operate or similar arrangements, and cannot be full private ownership or contract operations and maintenance.  The public sector may contribute loans or credit enhancement mechanisms to the financing of the project, may assume some liability risk, and assist with ROW acquisition.

Development consortia are chosen to execute a bid based on the strength of the firms.  Authorities consider financial condition, personnel qualifications, and the experience of the firms.

A referendum of citizens living within a given public highway authority district have the power to vote on certain tax issues.  A referendum is required for the levying of vehicle registration fees, but no vote is required before the authority levies expansion fees charged to developers within the highway district.

# Maryland

Under Maryland Code (COMAR) 11.07.0, the State allows private firms to finance, construct, or operate transportation projects that will enhance the State’s existing transportation system.  Eligible transportation facilities include a port, airport, railroad, or transit facility, and all incidental property rights, materials, structures, and other facilities related to these transportation facilities.  Highways have not been included for eligibility at this time.

The Maryland Transportation Authority (MdTA) administers the program on behalf of Maryland Department of Transportation (MdDOT) and related agencies.  Program guidelines specify a two-step selection process, with an initial review of conceptual proposals followed by a review of detailed proposals for selected projects.  Unsolicited proposals will be accepted with a provision for competing proposals as well.

# Missouri

In 1990, the Missouri Transportation Corporation Act and the Missouri Transportation Development District Act (Senate Bills 479 and 649) were enacted.  The acts enable a group of citizens to request authorization to establish a transportation corporation to develop a transportation facility.

# New Jersey

New Jersey adopted public-private legislation, P.L.1997c.136, on June 27, 1997.  The enabling legislation allows the Commissioner of Transportation to: (1) solicit private sector proposals to plan, design, construct, equip, operate, finance, improve and maintain, and any combination thereof; (2) select proposals for the negotiation of demonstration project agreements; and (3) enter into agreements to advance transportation projects.

A total of 7 projects may be negotiated, entered into, or solicited by the Commissioner.  The Department issued an RFP and program announcement in conjunction with passage of the legislation.  The submission deadline for the first round of proposals was September 30, 1997.

Prior to passage of the enabling legislation, New Jersey Transit, in cooperation with the State’s Transportation Trust Fund, participated in an innovative design-build-operate-manage (DBOM) process for construction of a new transit line.  The project, conducted under existing authority, may set a precedent for future partnerships. The Bergen-Hudson project is a $1.2 billion light-rail line that will be designed, built, operated, and managed by a consortium called the Twenty-First Century Rail Company, headed by Raytheon, a Lyndhurst, NJ-based engineering firm; Itochu of New York City, a Japanese trading firm; and KinkiSharyo of Boston, a Japanese railcar builder.

The project will be fully funded through an FTA grant and state matching funds (80/20 ratio).  Initially, the RFP for private consortia asked bidders to come up with construction financing.  Then, NJ Transit decided that they would be better off financing the project on their own, saving money through issuing tax-exempt short-term instruments, and also by speeding up the procurement and building process by not having to follow all federal regulations (because they are going to finance the initial construction on its own, and seek future reimbursement through advance construction).

# NEW YORK

The State of New York has not adopted any general enabling legislation permitting statewide P3 processes.  The State, however, has entered into numerous financial partnerships with local governments and developers, making use of impact fees, taxing districts, and other tools to innovatively finance transportation.

# Pennsylvania

In May, 1996, a bill was introduced in the Pennsylvania General assembly to enable public-private partnerships.  The legislation (Senate Bill #1521, The Privately-Operated Toll Road Act, May 2, 1996), would permit private operators to lease highways from the State for up to 35 years, and to charge tolls on existing highways.  As of this report, this legislation has not yet been passed.

# Texas

In 1991, the Texas Legislature passed enabling legislation (Section 17 of HB 749, Private Participation in Projects) allowing the Texas Turnpike Authority to enter into agreements with private entities for construction, maintenance, repair, or operation of turnpike projects.  The Authority may enter into exclusive development agreements with private entities, and has broad latitude to negotiat terms and conditions of financing.  The Authority may also allow franchises, leases, licenses, permits, and other devices to enable private development.

# Utah

In response to development pressure along Utah’s growth-heavy Wasatch Front, the Utah Department of Transportation issued an RFP for the largest design-build highway project ever undertaken in the United States.  The project calls for the reconstruction of 17 miles of Interstate 15 (I-15) in and around Salt Lake City.  Construction began in April, 1997.  Completion of the reconstructed I-15 corridor is planned for July, 2001.  The project includes widening of I-15 to 5 lanes in each direction, plus the addition of an HOV lane, along a 16-mile congested portion of the highway.  Additional I-15 improvements will be better lighting, aesthetic additions to bridges and walls, wetlands creation, and advanced traffic management systems (variable message signs, possible ramp metering).

The project’s $1.6 billion cost is mostly covered under one fixed-price contract awarded to a single contractor to both design and construct the project.  The project is the largest part of the State’s Centennial Highway Fund – a ten year, $2.6 billion fund for construction and reconstruction of highways in Utah.  In additon, the State has requested $970 million in Federal funds for the I-15 project as part of its $4.3 billion request for Federal funding for transportation projects related to the 2002 Winter Olympic Games.  As of October 1997, the State had received about $14 million in Federal funds for environmental studies and land acquisition.

Public-Private Project Experience (By State)

As a summary of the preceding sections and drawing on additional information available--from in-depth case studies and elsewhere--following is a table of public-private projects going on across the United States.  Projects are categorized in the following groups:

- Open or under construction;

- Pre-Construction: and

- Stalled or failed.

Project information is provided for all active projects discussed in this report and for a few additional projects in the states covered by the report.

# PUBLIC-PRIVATE PROJECT EXPERIENCE (BY STATE)

| State | project Name | Description | Cost | Project status | P3 Arrangement |
| --- | --- | --- | --- | --- | --- |
| Open or under construction |  |  |  |  |  |
| CA | Foothill/Eastern Toll Road | Design-build contract for 28.6 miles of express tollways linking the Riverside Freeway with I-5, I-405 in Orange County. Toll operations concessioned to private firm. | $1.5 billion | Construction 10/94. TCA secured investment ratings and sold $1.5 billion in fixed and variable-rate, tax-exempt toll revenue debt. | Turnkey Design-Build Sponsor is public toll authority |
| CA | San Joaquin Hills Toll Road | Turnkey private development and state operation and maintenance of new six-lane, divided, 15-mile automated toll road linking I-5 and I-405 freeways in Orange County. Toll operations concessioned to private firm. | $1.4 billion | Financed March 1993, construction to be completed 1997, segment already opened to traffic. | Turnkey Design-Build Sponsor is public toll authority |
| CA | SR 91 | 35-year, build-transfer-operate project to construct 10-mile all-AVI, four lane toll road in the Median of State Route 91, Orange County. Congestion pricing for SOV, transit and HOV are free. | $126 million, taxable debt and equity. | Opened to traffic in 1996. | Build-Transfer-Operate Design-Build Private equity |
| CO | E-470 | Design and construction of a circumferential highway around the eastern perimeter of Denver. | $694 million | Segment I opened to traffic and tolls in 1991. | Tolls Design-build |
| PR | Laguna San Jose Bridge | Commonwealth issued tax-exempt bonds and financed a consortium to build a stand-alone bridge and to operate and collect tolls for a lease period. | N/A | Opened to traffic in 1993. | Turnkey, Operations & Maintenance |
| SC | Conway Bypass | Design-build contract for a road linking I-95 and Myrtle Beach to carry mostly tourist traffic. | $360 million | Began construction January 1998. | Design-Build State Infrastructure Bank |
| UT | I-15 Project | Reconstruct 17 miles of Interstate Highway in and around Salt Lake City. | $1.6 billion | Construction began in April 1997. | Design-build |
| VA | Interstate Operations Contract | Unsolicited private proposal for a phased program to share savings below a guaranteed price for maintaining a portion of the Interstate highway in Virginia. | N/A | Negotiations complete. Work begins in 1997 and 1998. | Operations & Maintenance |
| VA | Dulles Greenway Toll Road Extension | A privately owned extension to an existing state-owned toll road. Virginia’s Corporation Commission approved the project's finances and has control over rates of return. | $326 million. | Opened to traffic in 1995. Due to lower-than-anticipated traffic, the Greenway is currently exploring financing options. | Full privatization (Build-Operate-Transfer) Considerable private equity |
| Pre Construction |  |  |  |  |  |
| SC | Southern Connector | Turnkey road: 16-mile toll bypass of Greenville between I-185 and I-385. | $177 million | Negotiations complete. | IRS 63-20 Corporation |
| WA | Park and Ride Expansions | Build-transfer-operate contract for single level parking decks at transit stations adding 7000 spaces, retail outlets at 23 existing park-ride lots in King County. | $70 million | MOU Agreement signed 3/96. Design-Build underway. | Build-Transfer-Operate Design-Build |
| WA | Tacoma Narrows toll bridge | New bridge to supplement existing bridge combined with demand management techniques. | $800 million | Preliminary negotiations completed. EIS and MIS underway. Regional vote scheduled for 1998. | Build-Operate-Transfer / Build-Transfer-Operate Private equity |
| Stalled or Failed |  |  |  |  |  |
| CA | AB 680 Mid-state tollway | 35-year BTO franchise to build new, four-lane toll road linking I580 with I-80 east of San Francisco Bay Area. | $700 million | Stalled due to lack of planning approval and financial feasibility. | Build-Operate-Transfer/Build-Transfer-Operate Private equity |
| CA | SR125 | 35-year, BTO project to construct 10 mile north-south toll road for trucks, tourists, and new residents of planned towns in southeastern San Diego county, starting from proposed border crossing at Otay Mesa. CalTrans does EIS on cost reimbursable basis. | $400 million | Franchise signed 1990, financing incomplete | Build-Operate-Transfer/Build-Transfer-Operate Design-Build Private equity |
| MN | Highway 212 | MNDOT negotiated with a private company to develop a toll road on a new section of highway outside beltway. A non-profit was formed to negotiate with DOT. | $100 million + | Agreement with State completed but project rejected by local community. | IRS 63-20 Corporation |
| VA | Route 58 Midtown Tunnel & Pinner’s Point Interchange, and Martin Luther King Freeway Extension | Design-build proposal for transportation facilities to benefit the cities of Norfolk and Portsmouth. | $600 million | Remains under review by VDOT’s Internal Review Committee | Design-build |
| VA | Route-895 Connector Tollroad | 8-mile connector road to I-895 near Richmond, includes bridge over James River. | $320 million | Negotiations ongoing, conceptual plan approved May 1996 | Design, build, operate |
| VA | Route-168 South Tollroad | A four-lane, divided roadway along limited access right-of-way in order to relieve a severely congested 10-mile section of highway. | $130 million | Negotiations ongoing. | 63-20 Corporation |
| WA | SR 522 improvements | Build-transfer-operate agreement. 10.5-mile, four-lane tollway expanding existing road. Prime motivation: safety. | $155 million | Preliminary negotiations completed by State, but local opposition has stalled project. | Build-Transfer-Operate with an IRS 63-20 Corporation. |

# case studies

# introduction

The survey of state public-private partnership (P3) programs, summarized in the previous chapter, provides a snapshot of state progress to date with P3, and some indication of strategies for success or areas for concern.  This section builds on the broad survey by taking a closer look at four state experiences, in order to understand the elements of such strategies and whether any one state’s efforts can, and/or should, be a model to other states considering such programs.

State experiences can be studied from the perspective of the state process used or, alternatively, from the perspective of an individual project within that effort.  Indeed, some states’ entire P3 experience centers around a single project.  The four cases presented in this section incorporate both methods of analysis.  While it prevents easy comparison across the cases, it may provide better insights overall regarding any critical path or key requirements for success of P3 programs.

Virginia and Washington State are examined from the state perspective.  Meanwhile, the E-470 project in Colorado and SR 125 in California are examined as projects undertaken as defining the P3 experience or within a P3 context, respectively.  Finally, the Virginia case study also contains a stand-alone consideration of the Dulles Greenway project, as it was undertaken outside the existing P3 program, and should therefore be considered separately, and because it is unique in structure and therefore merits a separate analysis in any case.

All of the case studies are based on interviews with state and local officials, participating private firms, and written materials where relevant.  Despite the two approaches used and the resulting split in the Virginia case, each case description is structured as follows:

- Background -- indicating program or project objectives and providing historical context;

- Process -- summarizing the state process used within which the project took place, or describing in detail the program developed and used;

- Project Description(s) -- where potential or existing projects are profiled and issues highlighted;

- Program and Project Status -- which indicates the current status of the program or the project within a program; and

- Lessons and Highlights -- that draws lessons that may be learned from that state’s or project’s experience.

# Virginia

# Overview

Virginia’s public-private partnership program passed, essentially, through two distinct phases.  First, the Commonwealth authorized development of the Dulles Greenway, under 1988 legislation enabling the (Virginia Department of Transportation (VDOT) to pursue this public-private partnership (Section 56-544 of the Virginia Highway Corporation Act).  VDOT and the State Legislature subsequently determined that a different approach was needed and, working together, developed new legislation in 1994.  This act, the Public-Private Transportation Act of 1995, forms the backdrop for current and expected public-private activity relating to all modes of transportation in Virginia.

Because the Commonwealth went through two very different experiences, and has learned important lessons from both, the two initiatives are profiled separately and sequentially.

# Dulles Greenway Public-Private Partnership

# Background/Scope and Legislation

Virginia enabling law was adopted in July 1988 for the Dulles-Leesburg toll road project under a “private corporation act.”  Section 56-544 of the Virginia Highway Corporation Act allowed private entities incorporated as public utility corporations to build, own, and operate toll roads upon receipt of a Certificate of Authority from the Virginia State Corporation Commission (a public utility commission).

# Process and Agreement

Toll Road Investment Partners II (TRIP II) applied under the Act and was selected to design, build, and operate the toll road  (Virginia already had built a toll road east of Dulles Airport to the Capital Beltway.  The extension runs west of the Airport to Leesburg).

Under the arrangement, TRIP II is regulated by the Virginia State Corporation Commission (SCC) and overseen by the Virginia Department of Transportation through the Commonwealth Transportation Board.  This structure treated the project very much like a public utility, giving the SCC the power to make unilateral decisions with respect to fixing the fee schedule and rates of return.  The project also required TRIP II to own the land, with all the attendant liabilities involved.

Under the initial plan, tolls were to be the main source of revenue.  The SCC would regulate tolls according to limits on the project’s rate of return on equity.  All assets of the toll road must revert to the State ten years after the debt is repaid.  VDOT monitored construction, operations, and maintenance as spelled out in the terms of a Comprehensive Agreement between the State and TRIP II.  Further, the project was required to comply with all local land use and zoning regulations.  The State also required that all land be acquired by donation or fee to assure use in perpetuity after turnover, and much of the right-of-way was donated by local land developers.

# Project Description

The Dulles Greenway is a 15-mile, limited-access four lane extension of the existing State-built Dulles Toll Road (Route 267), extending west from Route 28 near Dulles Airport to Leesburg, Virginia.

# Status

This project received all necessary State and local permits to commence construction and actively sought construction financing over a 5-year period.  The project overcame several barriers to finalize financing of over $300 million and break ground in the fall of 1993.  It opened for traffic in September 1995.

After about six months of operations, actual use of the Greenway was running about 10,000 to 12,000 vehicles per day, substantially below the forecast levels of 34,000 vehicles per day, and revenues were falling short by a comparable margin.  Net revenues proved inadequate to cover debt service, and reserves were drawn down.  Though the project was not performing on its debt, there were reports of a standstill among lenders to allow adjustments to be made by the equity investors.  Because the project was privately financed, without publicly marketed securities, detailed financial performance information is not available.

In the Spring of 1996, Greenway toll rates were reduced from $1.75 to $1.00, on a temporary basis, and remained at that level throughout the year.  Ridership expanded to about 20,000 vehicles per day, still well below projected volumes.

In addition, real estate development in the Greenway corridor and around Leesburg had stalled during roadway development, but has recently accelerated, in part because compatible electronic tolling devices have been installed on the Greenway and the State's connecting toll road.  Greenway developers have undertaken additional marketing efforts as well, so there are reasons to expect a continuation of traffic growth.

Operations continue without public evidence of major problems, but the project revenues are known to be insufficient to cover debt service and the financial position of the equity investors is known to be tenuous.  As of early 1998, VDOT gave TRIP II an additional six months to pay off a $2 million dollar debt to the State after it paid $500,000 of $2.5 million due and promised to pay the rest with interest by July 31, 1998.  TRIP II expects to reach a refinancing agreement with lenders by that time.

# Lessons and Highlights

Virginia and the private developers, TRIP II, learned several lessons from the experience with the Dulles Greenway and Virginia’s current program reflects many (if not all) of these lessons:

- Development costs may be higher for “greenfield” projects relative to other types of projects. Development costs associated with right-or-way acquisition and State and local interaction regarding underdeveloped areas required significant private equity from the outset.

- The state can contribute to a project up-front by using its powers to acquire ROW.  Land acquisition proved difficult to finalize without any “taking” authority.

- Projects servicing underdeveloped areas may need special assistance, such as credit support.  Toll revenue estimates were based on projected real estate development beyond Dulles which stalled in the recession.  The forecasts were overly optimistic, and appear to have been technically flawed in addition to the impact of stalled development in the area.

- The state may wish to retain land ownership as it faces a lower risk than the private partner does. Acquiring necessary right-of-way to complete transportation projects can be an expensive component of the overall financing of a project.  Any last minute alignment changes can be quite costly to private developers taking part in the joint development of a project.  Requiring private ownership of land may impose unnecessary operational risks on the private party.

- The contract must be clear on roles and responsibilities in the event of sponsor default.  Agreement on procedures in event of default proved difficult here.

- The final agreement between the private partner (i.e., Toll Road Investment Partnership II) and the State needs to recognize that the general public may view the arrangement differently.  To ease the transition between the two connecting toll roads, Greenway operators agreed to collect the State's toll.  This made the toll level paid on the Greenway visibly higher, even though a portion was simply being remitted to the State.

Public-Private Partnerships Under Virginia’s Public-Private Transportation Act of 1995

# Background

The Commonwealth sought several objectives in passing the Public-Private Transportation Act (PPTA) of 1995:

- Broad support from stakeholders (the Governor, VDOT, State Legislature, contractors, local communities);

- More flexible regulatory oversight requirements than were possible under the Greenway project;

- Increased capital (relieving the Commonwealth from having to increase its debt outstanding);

- A mechanism by which to encourage creative solutions to Virginia’s transportation problems; and

- Acceleration of important projects (across all modes).

VDOT worked with the Legislature and with significant input from interested parties to draft and re-draft the legislation, which was signed by Governor George Allen in 1995.  VDOT used public forums, written comments, and public hearings to secure feedback.  This activity also served as an initial education and outreach platform.

The Commonwealth has received 10 qualifying unsolicited proposals to date; one of which is in the negotiation phase. One contract has been negotiated with Virginia Maintenance Services, Inc. (VMS), to operate and maintain a portion of Virginia’s interstate under a fixed price pilot program.

# Process

# Program Development

Concurrent with passage of Legislation, VDOT developed guidance to direct potential proposers and to provide an internal framework for action.  Here too, VDOT solicited written comments from over 300 parties that had expressed interest in the program, of which about one third responded.  During this time and following publication of the final guidelines, the Secretary and Deputy Secretary gave several presentations around the State, introducing the program, explaining VDOT’s goals, and encouraging support.

# Scope and Legislation

The Virginia legislation is broad based and flexible in three respects.  It permits:

- solicited and unsolicited proposals;

- any “responsible public entity” to accept or solicit a proposal; and

- proposals across all modes for capital and/or operations and maintenance of a new or existing facility, with very few restrictions.

In addition, the legislation permits VDOT (or other responsible public entities) to negotiate nearly every aspect of the arrangement with the proposing team, including the partners’ respective roles, risk sharing, financial contribution, and return on investment.

# Selection

In response to written comments that expressed proposer concern over a steep fee, and the cost involved in developing detailed proposals, VDOT developed a two-step evaluation process, requiring a “conceptual” proposal and a $5,000 fee initially, with a $20,000 payment and a more detailed proposal if the initial submission is approved.  VDOT’s Chief Engineer, Assistant Commissioner of Operations, and Assistant Commissioner of Finance review each conceptual proposal.  If they accept one, the Chair of IRC takes the proposal to the Transportation Board for approval of the concept (This step also serves to keep the Board aware of projects being seriously considered as they will later be involved in making decisions regarding alignments, impacts on existing infrastructure, financing, etc.).

When an unsolicited proposal is accepted, the State posts a notice in major papers, on VDOT bulletin boards, and in the State’s publications geared towards contractors.  A 30-day period follows, in which other firms may submit similar proposals in competition.  The period is designed to prevent other firms from beginning similar complete proposals, but to provide ample time for firms already working on similar proposals sufficient time to complete and submit them.

The proposer must also send the conceptual proposal to all “Affected Local Jurisdictions.”  This forces the proposer to begin a public outreach and consensus building process.  Concurrent with and extending beyond the 30-day competition period after detailed proposals are received is a 60-day comment period during which local governments can formally respond to the proposals, but are not required to do so.  The State is aware that in some cases the requirement to inform all localities of the project can be difficult for the proposer, especially for projects which affect the whole state, but they feel the exercise is crucial to the success of any proposal. The general public is expected to comment through their local governments, and is not provided with a separate forum.  Local governments do not have veto power as part of the selection process.  However, local government support has an impact on the evaluation of the proposal.  Further, the proposal must be consistent with state and local plans.

Upon receipt of a detailed proposal, a Public-Private Transportation Advisory Panel (PPTAP) reviews the proposal in greater detail.  The PPTAP is comprised of the members of the Initial Review Committee, one member of the Transportation Board, one member of the academic community knowledgeable in transportation engineering, and chaired by the Deputy Secretary of Transportation.

While this creative two-step approach was undertaken to accommodate proposer concerns, it has not yet worked very well in practice.  Proposers have found that it does not really save them much in the way of time and money to develop a proposal, as they have to undertake a critical mass of effort to develop the conceptual proposal.  As a result, they expend effort that naturally would be reflected in the detailed proposal, to make the conceptual proposal make any sense.

VDOT has stated that it is receiving proposals for the “conceptual” submission that are too detailed and lengthy, and would prefer to receive less information as the IRC, however, only reviews the information to determine proposer qualifications, a project’s technical merits, and financial feasibility.  Thus, the review exercise, which was meant to be limited at this stage, has taken more department time and effort than was envisioned.  Moreover, it appears that proposers have started to consider it an unstated requirement that the conceptual proposal actually be very detailed, either because the research effort had to be undertaken anyway (so there is little additional effort involved in including detailed information in the proposal itself) because they believe it may give them an extra advantage.

The tendency toward overly detailed proposals concerns VDOT as it may discourage firms that would like to submit creative unsolicited proposals.  Unlike proposers responding to solicited RFPs, these proposers are taking the risk that the project is not of interest or importance to VDOT.  If they feel required to expend significant time and money developing a new idea, they may be discouraged from doing so, and lower their relative risk by selecting a project already on a long-range plan.  VDOT may not, therefore, achieve its program objectives relating to “creativity”.

# Disclosure Provisions

The two-step process also led to a 1996 revision in Virginia’s legislation related to information disclosure. Many states have Freedom of Information Act (FOIA) laws that determine the conditions under which materials submitted to a government body must be disclosed to anyone who asks to see those materials, even where the owner of the information considers their contents to be confidential and proprietary.  The Virginia legislation excludes proposals under PPTAP from standard procurement law in an effort to provide VDOT with flexibility on disclosure.

In a standard procurement, FOIA applies after a team is selected, so information is kept confidential until bidding is complete.  Under the public-private partnership program, however any competing team could ask to see a bidder’s submitted proposal during the 30-day period, and make use of that bidder’s confidential information in their proposal.

While this risk is clearly addressed in the guidelines, many original proposers were not aware of this possibility and simply stamped their information “confidential and proprietary”, not realizing that such action would not protect them.  Other early proposers split their proposal contents and left confidential chapters with their respective lawyers, who were not obligated to release that information to the public.  At the same time, VDOT could still look at the safeguarded materials as needed.  This solution was ad hoc at best, as it required continuous trips to the lawyers’ offices by VDOT personnel.

Virginia has since amended FOIA to explicitly exclude certain parts of proposals submitted under the P3 program.  Under the amended law, proposers need to meet three tests: (1) the proposer must ask that certain portions of the proposal be exempt from the FOIA requirements; (2) material deemed confidential and proprietary must be stamped as such; and (3) the proposer must explain why those materials should be exempt.  If VDOT accepts the proposer’s arguments, these materials are removed from the master copies VDOT keeps for FOIA requests.

# Schedule

VDOT provides a suggested schedule for decision-making in its partnership guidance.  Proposers have found that VDOT has not adhered to its “suggested” timetable laid out in the guidance, at great cost to the bidding teams.  From VDOT’s perspective, they have no control over when such proposals are submitted, and therefore cannot really plan or budget time or staff to accommodate a specific timeframe.  From bidders’ perspectives, however, the long delays are very costly.  VDOT recognizes that theirs is a new process, this issue is inherent to a process that accepts unsolicited proposals, and fully expects their turnaround time to speed up once more projects are in place.

# Project Descriptions

Under the new legislation, as of late 1997, Virginia has received six proposals that have been granted (at least) conceptual approval.  One of these has since been successfully negotiated; one was not recommended; and three were withdrawn from consideration by the proposer.  One proposal is still under consideration.  These proposals, including a project initiated by the City of Chesapeake, are shown in the table below and are summarized below (excluding the O&M proposal by Rebuild Inc.):

| Project | Type of Project | Solicited or Unsolicited? | Responsible Public Entity | Proposer | Estimated Cost |
| --- | --- | --- | --- | --- | --- |
| Operations & Maintenance for Dulles Toll Road | O&M | Unsolicited | VDOT | Rebuild Inc. | N/A |
| Interstate O&M | O&M | Unsolicited | VDOT | Virginia Maintenance Services (VMS) Louis Berger International Sverdrup Corp. Dyn Corp./CSC (withdrawn) | $132 million |
| Route-895 Connector Toll Road | Capital and O & M | Unsolicited | VDOT | Fluor Daniel & Morrison Knudsen | $320 million |
| Route 58 Midtown Tunnel, Pinner’s Point Interchange, and Martin Luther King Freeway Extension | Capital & O & M | Unsolicited | VDOT | Hampton Roads Public-Private Development, L.L.C. | $600 million |
| Route 168 South Toll Road | Capital & O & M | Solicited | City of Chesapeake | Parsons Brinckerhoff and J.A. Jones | $130 million |

Interstate System Ordinary Maintenance

Final agreement for this pilot program was reached in December 1996.  The proposal submitted by Virginia Maintenance Services (VMS), Inc. will provide total maintenance of certain portions of the interstate system, totaling about 250 miles.  The pilot program is Virginia’s first initiative to be implemented following enactment of the Public Private Partnership Act of 1995.

VDOT received the conceptual proposal on October 2, 1995.  Two competing proposals were received during the 30-day period that follows any accepted unsolicited proposal.  All were approved by the Initial Review Committee and accepted in concept by the Commonwealth’s Transportation Board for a pilot program only.  VMS and a second firm submitted detailed proposals in April 1996.

The Public-Private Transportation Advisory Panel recommended that the Commissioner negotiate with VMS and a comprehensive agreement was reached on December 19, 1996.  The pilot program negotiated with VMS includes 250 center lane-miles of interstate located in the southwest and southeastern sections of Virginia for a 5- year time period following an initial six-month transition period.  Full responsibility for all maintenance activities, including I-77 (except for tunnels)/ I-81 and snow removal, will take place in the later years. The total cost of the program is $131.6 million.

The evaluation process and subsequent negotiations were fairly smooth and uneventful.  VMS made several observations, however, that have wider applicability.  VMS recognized that the framework for evaluating the success of the partnership must be cognizant of where and how the private partner is able to achieve savings or efficiencies, and not be structured in a way that prevents the private party from achieving those efficiencies.  The private partner, in turn, has to accept that the public agency has to protect themselves in substance and perception.  VDOT did recognize the importance of doing so and the contract is structured in a way that permits VMS to achieve the efficiencies it proposed.

VDOT also established performance standards as an oversight tool.  The performance outcomes specify the level of compliance with maintenance standards for each maintainable asset.  This permitted VMS to take advantage of key opportunities possible under asset management, such as hiring labor as needed, rather than keeping maintenance staff on board the entire contract length.  While some staff is needed on a continual basis, VMS can determine peak labor periods over a planning horizon, and contract out during those periods.  In addition, instead of receiving an annual budget and applying that budget toward O&M needs the way VDOT has traditionally approached maintenance, VMS can take a more holistic view of the contract over the entire contract period.  It can then look at maintenance options at different time periods, and select a plan that combines cost efficiencies with safety factors.

VDOT negotiated a pilot program that permits these types of savings.  VDOT established a level of service required and will annually review outcomes to make sure this level is maintained.  How it is achieved, however, is left to the private partner.

VMS echoed many proposers in stating the importance to a private partner of a stable, predictable cashflow.  While there is a need to the DOT to verify that work is proceeding (whether construction or O&M) as agreed, it helps to partially divorce the timing of payments from the audit activity.  The VMS contract, for instance, spells out a total return over the period, split over the 5.5 years and declining in value each year.  While the overall return is the same as it would be if the fee were split evenly over the period, from a cashflow standpoint, the structure has the following advantages:

- It is beneficial to VDOT as it provides greater and greater savings each year relative to what it would have cost them in-house, given that their yearly payments to the contractor fall each year; and

- It provides an incentive to the contractor to improve efficiency each year, or annual bottom line performance and cashflow will suffer.

While, in both cases, the overall gains are the same, the cashflow difference can be important.  Finally, VMS again echoed many private firms who observed a deep-seated distrust that the public and private firms feel for one another.  Fortunately, VMS was able to build trust with VDOT.  VMS and VDOT began transitioning operations in February 1997.

# Route 895 Richmond Connector “Pocahontas Parkway” Project

This unsolicited, conceptual proposal calls for the design and construction of a Route-895 Connector linking I-95 with I-295 south of Richmond.  The project would serve the growing Henrico and Chesterfield Counties southeast of Richmond with improved airport access and regional traffic movement around the greater Richmond metropolitan area.  The proposal, which includes a bridge over the James River, had been under consideration by VDOT for some time but could not move forward to construction due to a lack of funding.

VDOT has already allocated $12 million for the design of a Route-895 Connector from the intersection of  I-95 (Richmond-Petersburg Turnpike) and Route 150 (Chippenham Parkway) to I-295.  As well, VDOT looked at three connector alignments and an environmental impact statement was approved by FWHA for a favored alignment that required a bridge crossing at the James River.  Proposers will incorporate this work in their project and perform additional design engineering before construction.

Under their proposal, the team of Fluor Daniel, Inc., and Morrison Knudsen Corporation propose to commit financial and human resources to a new company, FD/MK, for completion of the project.  Currently, the team is working together on the E-470 project in Denver.  FD/MK’s plan is to construct the Route-895 Connector as a user-pay facility (cars paying a maximum mainline toll of up to $2) and use the toll revenue as the security for non-recourse, tax exempt bond financing issued through a not-for-profit community benefit corporation.  VDOT will take ownership of the completed facility and FD/MK will serve as the contractor to operate the new highway.  The project is estimated to cost $320 million.  The not-for-profit entity will issue approximately $330 million in project-related debt and have requested a State Infrastructure Bank loan for the remaining $18 million.

The unsolicited Route-895 Connector proposal was submitted to VDOT on November 8, 1995. It was approved by the Initial Review Committee and in concept by the Commonwealth’s Transportation Board on March 21, 1996.  No competing proposals were received and proposers submitted a detailed proposal in July, 1996.  As of May 1997, VDOT, and FD/MK have been working to negotiate a comprehensive agreement for the project.

Route 58 Midtown Tunnel, Pinner’s Point Interchange, and Martin Luther King Freeway Extension

Eastern Virginia Public-Private Facilities Partners, L.L.C. and the Hampton Roads Infrastructure Development Group submitted design-build proposals for transportation facilities to benefit the cities of Norfolk and Portsmouth, Virginia.  The two firms have, subsequently, merged to form Hampton Roads Public-Private Development, L.L.C. The plan includes construction of limited access highway facilities at the Pinner’s Point Interchange in Portsmouth, improvements to a strategic interchange in Norfolk, and the addition of a second Midtown Tunnel facility to expand Route 58 in Norfolk to four lanes of traffic. Ownership and operation will rest with VDOT. These facilities are part of the existing regional transportation plan for improved east-west travel linking Route 58 and the Western Freeway (Route 164) in Portsmouth to a major interchange in Norfolk as well as improved north-south travel linking the Western Freeway to the Martin Luther King Freeway in Portsmouth.

The project team is a consortium of managers, engineers, financiers, legal advisors, and contract advisors with local and national experience.  Proposers estimate the total cost of the project -- including design, development, right-of-way, construction, and financing costs -- to be $420.8 million.  Since the project builds on existing (Pinner’s Point Interchange) and future (Midtown Tunnel widening/Brambleton Ave. Interchange) project improvements by VDOT, proposers reason that the value added by this proposal warrants VDOT’s financial participation in the project.  Proposers reason the project will provide a vital link across the Elizabeth River that will maximize the effectiveness of VDOT’s investment in the Pinner’s Point Interchange.  The plan requests that VDOT contribute $98.6 million (which is $19 million less than VDOT’s current commitment of $119 to construct the Pinner’s Point Interchange portion of the project).  Besides the contribution from VDOT, the plan calls for the issuance of long-term bonds supported by toll revenues from two plazas along the new facility as well as an initial loan from a private lender of $10 million.  The initial loan is to be repaid from the proceeds of the bond issuance.

This conceptual proposal was submitted to VDOT on October 18, 1996.  A competing proposal was received a month later and, to date, both remain under consideration by the Initial Review Committee.

# Route 168 South “Battlefield Boulevard Bypass” Toll Road

The City of Chesapeake would like to build a four-lane, divided roadway along limited access right-of-way in order to relieve a severely congested 10-mile section of highway (State Route 168).  The existing two-lane highway currently carries three times the traffic it was designed to handle.  Need for this new roadway is well demonstrated by strong local, regional, and state support.  The primary obstacle in completing the project has always been inadequate funding to complete a project of this magnitude.

Traffic build-up along this two-lane stretch of highway has severely constrained commerce between Virginia and North Carolina, especially in late Spring, Summer, and early Fall, as the bulk (80 percent) of the traffic on this route is travelers using the highway to reach the Outer Banks resort area of North Carolina.  This traffic competes with local residents.  The new road will be constructed at a new location leaving the existing roadway (with some improvements) free to serve local citizens.

Virginia is the only state to date that has explicitly permitted local governments to engage in P3 activities.  While VDOT does not require the local government or authority to follow VDOT guidance, it encourages them to establish some guidance to ensure a consistent, transparent process.

Pursuant to the PPTA of 1995 legislation, the City of Chesapeake developed a project RFP and guidelines allowing both solicited and unsolicited proposals to be submitted.  Overall, VDOT is pleased with the process Chesapeake has used.  One unexpected outcome has been the degree to which VDOT has been involved with Chesapeake’s program.  While this has worked, VDOT recognizes that it may have caused problems if several localities had moved forward with P3 efforts simultaneously and had all turned to VDOT for technical support.

A pre-proposal conference was held in March 1996 with approximately 50 people in attendance.  Two conceptual proposals were received and approved in April and, after oral interviews from the two proposers, the development team of Parsons Brinckerhoff and J.A. Jones (PB&J) was selected.  If a comprehensive agreement is negotiated and selected, PB&J will be responsible for program management, design, and construction of the project under a guaranteed price and guaranteed schedule.

The total cost of the Route 168 project is estimated at $130 million.  The plan of finance has yet to be finalized pending the outcome of a feasibility study.  However, it is intended that the highway will be a tolled facility using a two- or three-tiered fee structure.  The City plans to use $25 million of their State Urban Allocation grant money along with a $34 million loan from the Virginia Toll Facilities Revolving Account which will be repaid using toll revenue.

The proposal calls for the formation of the Chesapeake Expressway Corporation (CEC), a non-profit corporation that will be comprised of three members appointed by the City, one member each appointed by the Chairman of the Commonwealth Transportation Board and the Commonwealth Transportation Commissioner, two at-large members from the Circuit Courts of the City of Chesapeake, and one non-voting member appointed by PB&J.  The CEC will be authorized by the City to issue tax-exempt bonds secured by toll revenue in the amount of $50 million and will own and operate the facility upon completion.  It is anticipated that PB&J may provide a $5 million subordinated developer note and that $27 million in federal funds may get used to make up the shortfall in needed financing.

# Project and Program Status

To date, only the VMS contract has been signed with VDOT, although several are still under consideration and look promising.  Of the six proposals that passed the initial review, the Route 895 project is the only proposal currently in the negotiation phase.

Of greater significance has been VDOT’s moratorium on O&M proposals unless specifically solicited.  Several factors contributed to this decision.  In part, the Rebuild proposal illustrated a broader problem.  Because VDOT is currently expanding (widening) the Dulles toll road, it has more than its normal number of active contracts for various services on the road.  Most likely because of the visibility of this project, the Department realized that, although it did project savings, this proposal disrupted existing activities: contractors were concerned about contracts being canceled; existing workers were concerned about losing their jobs; and morale was generally low.

VDOT recognizes that the issue illustrates a problem inherent in O&M proposals: unless they are for a new facility, the proposals themselves can disrupt existing activities, often unnecessarily (as the proposal may not even be approved).  At the same time, VDOT realized that they wanted to steer the P3 program back toward capital projects, based on its original objectives.  VDOT thus has determined that the program should limit unsolicited proposals to capital improvements and permit O&M (asset management) proposals only under a solicited framework.

# Lessons and Highlights

# Program Scope and Legislation

# Solicited and Unsolicited Proposals

Several program issues arose that were related to Virginia’s decision to pursue a dual approach to P3, with respect to accepting unsolicited proposals and the subsequent two-step selection process applied to such proposals.  Allowing unsolicited proposals has caused the Department to rethink or alter the program regarding:

- Whether unsolicited proposals should be limited to certain types of projects (e.g. capital or operating);

- Proposed schedule for action by VDOT; and

- The concern that unsolicited approach works at cross-purposes to DOT outreach.

Limiting Unsolicited Proposals to Capital Projects. If a program permits unsolicited proposals, it may cause less disruption to existing O&M contracts if such proposals are limited to capital improvements.  O&M (asset management) proposals can then be solicited via RFP.  Alternatively, if a state program permits unsolicited proposals, and if the state will consider O&M proposals as part of design/build proposals, but does not wish to consider O&M proposals on their own, it simply needs to make that clear in its program guidelines.

Schedule For Action.  While the 2-step process was designed to help proposers as much as VDOT, they learned that if a DOT pursues a dual approach, it needs to develop an approach for proposal response.  Even if the timeframe established is long, the bidder must be kept informed of progress made regarding project selection and approval.  This may be as simple as regularly scheduled meetings upon initial selection.  Participants in the Virginia program have also suggested that states move away from the dual approach, and simply solicit proposals.

Unsolicited Approach Works at Cross-Purposes to DOT Outreach.  Virginia has been lauded for the extensive outreach carried out by the DOT, both at the start of the program, and over time.  Indeed, proposers praised the Department for being the only DOT to stand before local governments and state that the Commonwealth simply does not have the resources to fund all the projects its needs.  This honesty was strongly supported and deemed critical.

VDOT has noted, however, that pockets of local opposition remain. A Rt. 288 “freeway” group, for example, opposed tolls on the proposed Rt. 288.  VDOT must continue, therefore, its efforts to educate the general public as well as local governments.

At the same time, because Virginia’s program allows unsolicited proposals, VDOT has an incentive to reduce or stop outreach after a time, because the DOT has received more proposals than it could respond to in a timely manner.

# Any “Responsible Public Entity” To Accept Or Solicit A Proposal

Enabling local governments or authorities to participate directly in a P3 program may overcome one of the biggest barriers to such programs -- local support.  Some issues, however, do arise.  The relationship between Chesapeake and VDOT has been a good one, but suggests other states may want to formalize roles and responsibilities.  If a state program enables local governments or authorities to undertake P3 themselves, some consideration should be given as to how the DOT would work with the locality through the process.  This might include, for example, how (or whether) to value the DOT contribution as part of the public share in cost and risk sharing for the project.

No other Virginia locality has followed Chesapeake’s lead and initiated a P3 program for a major capital project under the PPTA of 1995 (although some Virginia localities have privatized transportation functions involving transit and road repair).  VDOT believes additional education of local government on the program and experience of P3 projects will increase the likelihood that local government entities will choose to pursue P3 programs of their own.

# Capital Vs. Operations And Maintenance Proposals: Relative and Absolute Suitability to P3

VDOT and participating proposers both reflected that some projects may be more suited to P3 programs and that there might be some benefit in identifying these projects at the beginning of the process.  In practice, the issues arose in proposal evaluation, trying to determine whether a proposal provided sufficient value to the DOT.

Several DOTs have expressed concern that the private sector is only interested in submitting proposals that are the most commercially viable, leaving the DOT with projects that are not viable from a stand-alone perspective.   Given a basket of projects, some of which could be stand alone and others which could not, and scarce public dollars to meet transportation needs, many proposers suggested that the DOT should use its scarce resources to finance those that are not viable from a stand alone perspective, and use the private sector to develop those that can.  The P3 arrangement can be structured so that the DOT shares in the return, and uses its cash freed up to finance more projects than it otherwise could if the private sector had never gotten involved.  This applies to both capital and operations and maintenance proposals.  In Virginia, eleven of sixteen proposals submitted under the Act were for operations and maintenance.  This result has led to VDOT issuing a moratorium on these types of proposals, henceforth restricting unsolicited proposals to construction of new transportation facilities only.

DOTs may wish to look carefully at their long term capital plans, as these typically represent a “wish list” of projects by local governments, MPOs, and the state.  While unsolicited proposals for creative new ideas need not be excluded from the process, bidders may be more interested and willing to respond if the DOT indicates the kinds of projects it is interested in receiving proposals for, using existing plans as a backdrop for that request.  In addition, in determining which projects might more logically lend themselves to P3, the DOT may wish to consider its projects from a market perspective -- which ones have or could have elements that would make them viable (or viable with some state assistance).  Given the discussion above, it may be more logical to solicit interest from the private sector for the latter group.

With respect to O&M proposals, the savings is typically based on expected efficiencies.  By definition, therefore, the DOT must be able to determine what that segment of road would have cost them to operate and maintain in the absence of private sector involvement.  In Virginia, the DOT did not isolate the costs of operations and maintenance of the pilot section interstate from overall costs in a comparable accounting framework.  While this exercise can and is being done to permit evaluation after the pilot contract is completed, it was not anticipated.  This caused delay in the evaluation process.

Where a proposal is solicited, the DOT can prepare such costs ahead of time.  The RFP for operations and maintenance of the Jamestown-Scotland Ferry is one such example where the VDOT has separated out the costs of operating that facility.  This issue supported VDOT’s case for soliciting O&M projects.

# Negotiations

The evaluation and negotiations with VMS illustrated three lessons that have broader application:

- Establish a framework for evaluation;

- Establish a fee structure that provides smooth cashflow for the private partner; and

- Build trust between public and private.

# Establish A Framework for Evaluation

The key appears to be flexibility: creating a framework that permits the private partner to achieve the goals as it chooses, taking advantage of its ability to do things differently from the DOT.  Using performance standards allowed VDOT to establish a level of service required and minimize the oversight necessary.  At the same time, it has allowed the private firm to determine how it achieves required service levels.

The concept applies to design-build contracts as well.  Here too, it is critical to construct an agreement that evaluates the private party by results, not the process or efforts employed to reach those results.  In practice, this means moving away from the traditional audit of activity during a billing period, where the private partner must demonstrate what was done to secure payment for services rendered.  It may be more helpful to spell out what results must be achieved by what dates, and to allow the private partner to determine the method by which those results are achieved.

# Establishing A Fee Structure

It becomes important to negotiate a payment structure that provides stability to the private partner.  This can be done many ways, including partially divorcing the timing of payments from audit activities.

# Build Trust

Both sides must reliably understand what is critical to the other party.  While there are no rules for establishing this trust, one private firm suggested that the initial negotiations take place privately between the DOT (and AG’s office) and the proposing team.  Once there is an initial agreement, each party should then turn to their respective legal teams to determine whether the agreement is satisfactory.  This clarifies the respective roles: the private partner and the DOT negotiate an agreement.  The legal counsel’s job is to make sure a negotiated contract is binding and complies with law.

# washington state: new partners initiative

# Background

Washington State embarked on their private partnership initiative in 1991, at least in part in response to ISTEA provisions encouraging public-private cost sharing.  Washington thus became one of the first states to design legislation that could incorporate ISTEA provisions and take advantage of lessons learned by other states, such as California and Virginia, that had moved ahead prior to ISTEA.

In 1991, Washington's Transportation Policy Plan Steering Committee (an arm of the State Transportation Commission) set up a Subcommittee on Public-Private Partnerships in Transportation. The Subcommittee suggested partnership enabling legislation, as follows:

“The Legislature should authorize a program to allow the Secretary of the Department of Transportation to pursue and implement public-private initiatives for transportation capital improvements.”

Among other subcommittee suggestions were the establishment of a revolving loan fund, structured to take advantage of proposed public-private partnership provisions and funding opportunities under ISTEA, and the use of community redevelopment financing to increase private sector investment.

The Transportation Commission (through the Subcommittee) sought several objectives in passing state legislation:

- Increased access to property development and project opportunities;

- Fostering of financial and development expertise; and

- A way to supplement state transportation revenues, allowing the State to use its limited resources for other needed projects.

# Process

# Program Development

Washington State’s public-private partnership program was initiated by a combined effort of the Transportation Commission and WSDOT.  Upon presentation by the Steering Committee, the full State Transportation Commission held public hearings and found support among the general public for the idea.  Combined with the recommendations of the Subcommittee, these findings encouraged the Commission to explore the legal, regulatory, and administrative barriers to public-private partnerships.  The Subcommittee recommended that WSDOT be “authorized to solicit proposals from the private sector and select up to six demonstration projects,” to be approved by the Commission and consistent with “plans, rules, regulations and statutes governing state transportation projects.”   The Subcommittee also recommended “cooperation and consultation with affected jurisdictions,” and established policies for minimization of state liability and reimbursement for state services used to support projects.  Surveys and public forums following the efforts of this subcommittee identified continued public support.

Over roughly the same time period, WSDOT was undertaking its regular two-year planning process for 1991-1992, and it became apparent that roadway system needs were outpacing funding resources.  As a key legislator said:  “we added up the needs and experienced sticker shock."

# Scope and Legislation

In early 1993, the Washington Legislature considered and unanimously approved a bill enabling implementation of the recommendations regarding public-private partnerships,  The bill, Substitute House Bill (SHB) 1006, was passed in April, by unanimous votes in both chambers, approved by the Governor in May, and became effective on July 1, 1993.  WSDOT established their New Partners in Transportation based on SHB 1006.

The Washington legislation permits:

- The WSDOT Secretary to select up to six demonstration projects;

- Solicited proposals (but without restriction on scope – projects are to be identified by the private sector);

- Proposers to use Federal, State, and local financing;

- WSDOT to assist the private entity, with respect to rights of way, airspace, eminent domain, development rights, permits, etc;

- Build-Transfer-Operate arrangements (Projects will be owned by the private sector during construction, turned over to the State after construction, then leased back for up to 50 years of revenue operations);

- Maximum rates of return to be established for each project, by negotiated agreement, with "incentive" rates of return allowed for beneficial actions; and

- The Secretary to continue to charge user fees after the private lease expires.

# Initiation of P3 Proposals

The enabling statute in Washington State directs WSDOT to solicit proposals and develop six demonstration projects, but there was no guidance as to what the projects should be as long as they were “capital-related” and dealt with “the planning, construction, upgrading, or reconstruction of transportation systems and facilities.”  In fact, the law states: “proposals and demonstration projects may be selected by the public and private sectors at their discretion.”

Shortly following passage of SHB 1006, a draft RFP was drawn up by WSDOT and distributed to 200 interested parties.  In January, 1994, the final RFP was issued concurrently with an extensive national and international “solicitation of interest,” resulting in the issuance of the RFP to over 300 interested parties.  A pre-bid conference was held in February, 1994, and attended by 200 private sector representatives.

WSDOT solicited conceptual proposals, rather than full detailed proposals, so that final designs and permits were not required.  The process was designed to act as a funnel, attracting a number of proposals and narrowing them down to a few (six at the most) which would be initially approved for further consideration.

# Selection

Each proposal underwent a two-step evaluation.  The conceptual proposals were submitted with a one time $35,000 check to help defray the cost of review and selection.  Each proposal was first evaluated by a team of WSDOT technical experts.  Concurrently, WSDOT retained a financial advisor to review proposer financial qualifications and the proposed financial plans for each project.  The analyses of each project by these two groups became a Technical Evaluation Report.  Reports were developed on all proposals and submitted to the Project Review Board.

Under the second step, the Project Review Board (consisting of the WSDOT Deputy Secretary, Deputy State Treasurer, Director of Revenue, a Professor of Civil Engineering, and the Program Director) reviewed the proposals, the attending Technical Evaluation Reports, citizen letters submitted to WSDOT, and interviewed one proponent for each project.  Using all of this information, the Board ranked all proposals and recommended up to six to the Secretary for approval.  Following the Secretary’s review of the Board’s report, the State Transportation Commission considered each proposal, after being informed of the Secretary’s recommendations.  Projects approved by the Commission advanced into agreement negotiations with WSDOT.

Conceptual proposals were evaluated and ranked based on four basic criteria:

- firm qualifications, including experience and financial capability to carry out the project (30 points);

- project characteristics, including concept, constructability, proposed financing, and compatibility with existing transportation systems and needs (30 points);

- community acceptability, including initial support and opposition, and plans to involve the public throughout project development (30 points); and finally,

- benefits to the State, including state transportation and economic development goals, and use of women and minority-owned firms (10 points).

An important characteristic of the WSDOT process was the treatment of proposals as proprietary in nature.  In order to protect the integrity of the evaluation process, and to provide commercial confidentiality for competing proposals, WSDOT kept the proposal details confidential until projects were selected by WSDOT and approved by the Transportation Commission.

# Finance

Under Washington’s program, selection is not based simply on a negotiated agreement following selection of conceptual proposals.  Instead, unlike other states, the post-selection agreement between the State and the proposer is based on the conceptual proposal and “does not give developers a vested right to build and operate the proposed transportation facilities, [but rather] grants an opportunity to study and design the proposed facility and to complete the planning process required by law in order for WSDOT and other agencies to determine whether the facility should be built.”

Implementation of project agreements, and subsequent approval of final proposals, are contingent on various approvals through the normal state procedures for infrastructure projects.  The franchise agreement would not bind the proposer to build the project, even after it had been through all approvals.

Only at this late point is it necessary for the proposer to seek financing for ROW and final specifications for actual construction.  If project financing is secured, then construction can commence.  Hence, detailed plans for project financing were not readily available during project review and selection.  WSDOT did report, however, that about $166 million in state funds would be required to implement the six projects.

# Project Descriptions

WSDOT received 14 proposals on May 13, 1994 from several consortia, of which six were ultimately selected for negotiations.  Consortia consisting of transportation, engineering, finance, marketing, environmental assessment and traffic analysis firms explored the Washington transportation system and identified numerous potential projects.  The 14 proposals included several bridge projects, including three competing improvement plans for the Tacoma Narrows Bridge (SR-16).  Also proposed were corridor and interchange improvements, a congestion pricing tolled HOV project, two transit-like projects involving ferry service and personal rapid transit, and two park-and-ride enhancements premised on feeding transit ridership.

# The selected projects are summarized below.

| SIX PROJECTS SELECTED BY WSDOT FOR NEGOTIATION |
| --- |
| Project Name | Project Type | Proposer | Estimated Cost | Project Status |
| King County Park-and-Ride Enhancements | Increased capacity at 23 park-and-ride lots | Perini Corp., with ABAM Engineers, et al. | $68 million | Active & agreement in place; study ongoing |
| Puget Sound Congestion Pricing | Toll SOV use of existing HOV lanes; build out HOV network | United Infrastructure (Bechtel/Kiewit joint venture) | $32.5 million for Phase I; $900 million for Phase II | Eliminated from further consideration |
| SR 522 Corridor Improvements | Design and construction of a 10.59 mile urban tollway | SR 522 Community Highway Association | $155 million for Phase I; other phases n/a | On hold pending legislative action/study |
| Tacoma Narrows Bridge and SR 16 | Several options to reduce congestion and add bridge capacity | United Infrastructure (Bechtel/Kiewit) | $216 million-$564 million for various options | Active; completing financial and environmental feasibility study |
| SR 18 Corridor Improvements | Construction of four lane tollway | National Transportation Authority (Perot Group & Greiner Engineering) | $256 million for Phase I; $220 million for Phase II | Eliminated from further consideration |
| SR 520 Corridor Improvement Project | Improvements to SR 520 corridor | Washington Transportation Partners (Parsons Brinckerhoff and Morrison Knudsen | $440 million total cost; $67.5 million for Phase I; $372 million for Phase II | On hold pending legislative action/study funding |

# Metro/King County Park-And-Ride Capacity Enhancement

In 1994, the Perini Corporation submitted a proposal to design, develop, finance, and construct single level parking decks over existing parking spaces at 23 park-and-ride lots located in King County, Washington. Though parking is currently free, discussions with potential users have indicated that patrons are willing to pay a fee for a parking location that provides the added amenities of security, convenience services, and clean attractive surroundings.  WSDOT and METRO benefit because all 23 lots are built at once. Perini offered to bring all 23 lots on line in two years.  Because the financing arrangement will build all 23 lots at once, Perini can take advantage of huge economies of scale which Perini estimates will reduce the cost per slot from $23,000 (the cost under the public construction plan) to $11,000.

Perini estimates that local construction cost will be $68 million.  In order to begin construction as soon as possible, Perini has agreed to pay all development and construction costs up-front while seeking reimbursement of the pre-construction development costs (approximately $2 million) from the State’s HB 2909 Transportation Revolving Loan Fund.  In addition, Perini has proposed to guarantee any revenue shortfalls (up to $3 million) for the first three years of operation.

Perini and the Revolving Loan Fund will be reimbursed for project costs through the sale of $68 million in 30-year tax-exempt certificates of participation backed by parking revenues.  METRO will operate the sites and collect parking revenues; revenues will be transferred to WSDOT who will use the revenues to repay the bonds issued on behalf of either a Special Purpose Entity (SPE) or a Public Development Authority (PDA) via a lease payment.  While operating costs will be subject to annual appropriations, it is anticipated that parking fees will generate sufficient revenues to cover debt service and operations.  Additional revenues from on-site commercial franchises are anticipated in the future.

Because Perini’s contract is strictly a flat fee for design/build, any excess revenues will be wholly available to WSDOT.  Once the bonds are repaid, the facilities will provide a long term source of revenue to WSDOT or METRO, even without extra concession lease income.  At the end of the project lease period, the facilities will be transferred to WSDOT or Metro.

# SR 522 Corridor Improvements

The SR 522 Community Highway Association, a nonprofit community-based corporation, submitted a proposal to provide a new transportation corridor between Woodville and Monroe.  The main benefit of this proposal is to improve safety and relieve congestion along the SR 522 corridor of northeast Seattle.  The proposal calls for work to be completed in three phases and only provides construction cost estimates and a financial plan for the first phase.

Phase I is to design, construct, and operate a 10 mile full access controlled, four lane tollway from the State Route 9 interchange to the US 2 interchange. Two new interchanges are to be constructed at Paradise Lake Road and Fales Road as well.  Phase II will include an additional toll plaza for a congestion pricing pilot program, installation of park-and-ride lots, and the modernization of approximately 2 miles of SR 522 between I-405 and SR 9.  The final phase would evaluate the feasibility of extending improvements across SR 2 and creating a bypass around Monroe.

Cost estimates are unavailable for the final stages, but the estimated total cost for Phase I is $155 million.  The financing for Phase I would be accomplished through the issuance of tax-exempt debt by the 522 Community Highway Association which expects to qualify for the issuance of debt under IRS ruling 63-20.  The size of the bond issue and the resulting toll service are dependent on any contribution made by the State.  These revenue bonds are backed solely by the pledge of toll revenues.  Interim funding is to be funded through a $4.6 million bank loan which would be repaid upon sale of the long term debt.  In addition, some form of credit enhancement (such as municipal bond insurance or letter of credit) may be used to strengthen the bond sale.

Proposers plan to seek federal designation for a Congestion Pricing Pilot Program along with federal financial assistance.  Currently, the proposal is on hold pending legislative approval.

# Tacoma Narrows

The Tacoma Narrows Bridge, located along SR 16 in the northwest section of Tacoma, is the primary link between the Seattle-Tacoma metropolitan area and the Olympic Peninsula.  The immense population growth of these areas has resulted in increased congestion on SR 16 and especially on the bridge.  United Infrastructure, a joint venture of Bechtel and Kiewit, proposed four distinct alternatives for improvements – two involving the construction of a new bridge, the construction of a new lower deck on the existing bridge, and an option for better management of the existing bridge.

The proposal includes project cost estimates for two of the alternatives.  Double decking the existing bridge is estimated at $564 million.  The Transportation Demand Management (TDM) option is estimated at $216 million.  WSDOT contributed a $1.4 million environmental/investment analysis in the SR 16 corridor to the project.  United Infrastructure expressed a willingness to provide $105 million in equity if a new bridge is built and $35 million for the TDM option.  Their investment would be recovered through the sale of taxable debt and repaid with tolls from the facility.

# SR 520 Corridor Improvement Projects

Washington Transportation Partners (WTP) proposed to improve the existing SR 520 corridor, which links downtown Seattle with Bellevue to the east, in two phases.  The first phase would connect the existing ramps from SR 520 to the I-5 express lanes, upgrade the elevated SR 520 structures, construct a toll facility, and provide some noise mitigation.  The project would construct covers with parks over the roadway at selected locations, add HOV lanes in each direction, and provide a bicycle and pedestrian path across Lake Washington.  The second phase will not proceed unless supported by the affected neighborhoods and relevant environmental studies.

WTP estimates total cost of the project including design, engineering, and construction to be approximately $440 million ($67.5 million for Phase I).  WTP plans to use $12.5 million of equity, $6 million from the HB 2909 Transportation Revolving Loan Fund, and $49 million from tolls to finance phase I of the project.  At a cost of $372 million for Phase II, WTP intends to use an additional $12.5 million of equity, $119 million from net toll revenue, and the remainder from permanent non-recourse financing.  Approximately $360 million of taxable revenue bonds will be issued to pay for construction costs, repay the Loan Fund, capitalize interest during construction, and pay financing fees and other costs.  The bonds will rely solely on tolls for repayment.

# Project and Program Status

In the fall of 1994, just after the six demonstration projects had been selected, Washington State experienced a major political change, and the majority party in the legislature swung to the Republicans.  While WSDOT's New Partners program was not a focus of the election campaigns, there was growing resistance to tolls in general.  New members were elected from the districts affected by projects, including the SR 18 corridor and SR 520 area, providing special focus on these issues.  Nevertheless, WSDOT proceeded to negotiate agreements with project sponsors.  Private participants later reflected that WSDOT did not pay sufficient attention to this change in the legislature.

The political upheaval in Washington State led to amendments to the New Partners program that cast doubt on all the projects and caused the demise of at least two.  A "repair" bill, SHB 1317, was introduced in January 1995, and hotly debated for the entire session, becoming one of the last bills to pass.  It required WSDOT to respond to petitions by 5,000 or more citizens, first determining communities affected by the proposed project, then conducting a local referendum in those communities (Any citizen could sign the petition).  All the roadway and bridge projects were significantly affected by negative petitions or other restraints; the King County Park-&-Ride was not subjected to a petition.

In February 1996, further revisions were made to the enabling legislation in SB 6753 that showed some degree of compromise.  This bill requires WSDOT to undertake environmental and financial feasibility studies itself, and only as funded by the Legislature, then select a preferred alternative before holding the referendum (Under the original legislation, the private proposer had to pay for these costs).  WSDOT points out that after holding the "advisory" election, the authority to enter into a franchise agreement with the sponsor still exists; it is not dependent on the outcome of the election and does not require further approval by the Legislature.

As of December 1996, of the six projects initially selected, two projects were no longer under consideration (SR 18 and Puget Sound Congestion Pricing); two (SR 520 and SR 522) are on hold indefinitely unless the Legislature appropriates funds for detailed feasibility studies.  Two projects are still alive:  the Tacoma Narrows Bridge project is undergoing a state-funded environmental and financial feasibility study; and the Park-and-Ride lots in King County have ongoing market studies under a development agreement between Perini and WSDOT. The Tacoma Narrows project could be approved after studies are completed and a referendum held, now planned for mid-1998 (SB 6753 also appropriated $10 million toward the environmental and feasibility studies.  If the project moves forward, then funds will be repaid to WSDOT from the project financing).

Public involvement was expected to take place under the normal public involvement process for state transportation project development.  Following the signing of project agreements, projects must be adopted into Regional Transportation Plans, the Statewide Multimodal Transportation Plan, and for projects involving any federal funds, the State Transportation Improvement Program (STIP), as well as conform with the State Implementation Plan for Air Quality (SIP).  Normal EIS and permitting procedures follow.  All of these procedures involve normal public involvement and government approvals.  These requirements leave open the prospect of another lengthy phase of project development, and may reflect a disbenefit of the stepwise process adopted by Washington.  In particular, the process does not provide a forum for public outreach by both the DOT and the proposer up-front.

The private sector was generally satisfied with the coordinated state effort up to the point of project approval, but noted that supporters of New Partners within WSDOT did not keep track of changes in the Legislature because they became consumed with the tight schedule of project negotiations across all six projects.  Meanwhile, a public revolt against tolls took shape.  Many in the private sector believe that if supporters had briefed legislators after project selection and again informed new members immediately after the election, the program momentum might have been preserved.  Unfortunately, this very promising New Partners program enacted in July 1993 has led to no infrastructure improvements as of March 1996, and appears unlikely to produce any before late 1998.

# Timeline

A timeline for Washington State’s public-private partnership initiative follows:

| WASHINGTON STATE PUBLIC-PRIVATE PARTNERSHIPS INITIATIVE TIMELINE |
| --- |
| DATE | EVENT | NOTES |
| Early 1991 | Establishment of Subcommittee on P3 in Transportation (part of Transportation Commission) | Birth of P3 initiative; parallels ISTEA |
| August 1992 | Report of Subcommittee Issued | Recommendation to pursue P3 |
| July 1993 | Passage of SHB 1006 | Enabling legislation unanimously approved |
| January 1994 | WSDOT issues Final RFP for demonstration projects | Extensive national and international solicitation of interest |
| March 1994 | Passage of Transportation Revolving Fund Legislation | Authorizes WSDOT to provide financial support; $25 million revolving fund. |
| May 1994 | Submittal of 14 conceptual proposals | WSDOT treats as confidential business plans |
| August 1994 | Six proposals selected by WSDOT and Commission | WSDOT began negotiating agreements in September 1994 |
| January 1995 | New legislative session convened after fall '94 elections | Majority changes to Republican; major revisions proposed to SHB 1006 statute |
| May 1995 | SHB 1317 passed; substantially weakens WSDOT authority to implement projects selected; prohibits further consideration of Puget Sound Congestion Pricing project | New limitations on P3 projects -- if petition with 5,000 signatures received, WSDOT must hold advisory election (referendum) after identifying affected communities; WSDOT may not negotiate a share of the user fees from the private projects, as originally permitted, nor continue to charge tolls after the privately-constructed projects revert to public control |
| February 1996 | SB 6753 passed; further revisions to P3 program | State selects preferred alternative before advisory vote taken; State must finance and undertake environmental and financial feasibility studies and define boundaries of affected communities; $10 million provided to study Tacoma Narrows Bridge project; local advisory votes to be taken on final project |

Lessons and Highlights

The Washington State enabling legislation was deemed to be basically sound and incorporated lessons learned in the early partnership efforts in other states.  In general, proposers liked the State’s design for the process, and found the State receptive to different proposals and responsive to the needs of proposers.  WSDOT was successful in attracting bids from experienced teams with the financial and technical capability to fulfill their proposals.  Most observers felt that the selection process was fair, and resulted in selection of high-quality teams.  The proposed projects solved real problems still facing WSDOT, such as the build-out of Seattle's HOV system.

Widespread Support in the DOT and in the General Public

The program was initiated by the Transportation Commission and the DOT (through leadership of the Subcommittee on Public-Private Partnership).  This interest led to legislation, not the reverse.  While legislative initiatives can be successful, there have been many instances where the DOT did not support a legislatively driven program.

Rate of Return was Regulated but Flexible

WSDOT had foresight to make the maximum rate of return negotiable; it was not established beforehand.  Within this rate of return, the developer was free to establish and modify tolls and fares.  Incentive rates of return could also be negotiated, allowing increments to the baseline maximum rate of return, if the developer met certain safety or demand management goals.

Financial Assistance was Available from the State

Washington was willing to engage in direct financial participation to “address risk private capital markets are unable to accept.”  A revolving fund of $25 million was established.  Both revolving fund loans and any additional state funds, however, would need to be appropriated by the Legislature.  The State was also willing to deploy staff and facilities for development of the project, but expected to be fully reimbursed for all of these expenses from project generated revenues.  This permitted the DOT to share in the early risk period where political risk was highest.

Outreach Should Be A Joint Responsibility

In Washington, the private developers had primary responsibility for gathering public support and were generally successful with local leaders, but not the public at large.  When surveys or focus groups results from the private sponsors were released, they were perceived as biased, because they were conducted by the private entity that stood to gain from the project.  This bias was strengthened because proposers were trying to gather support while competing with eachother for plan approval.

The public was seen as not understanding the true costs of transportation improvements.  Individual project needs were understood, but while the transportation fund is adequate for most individual projects taken one at a time, most of the public did not really understand the problems facing WSDOT to assemble funds to construct needed transportation projects.  Conveying the funding shortfall – both by portraying the high costs of transportation improvements and contrasting it with the inadequate revenues – might have convinced voters of the real need (just as Secretary Martinez of Virginia later did with communities in Virginia).  WSDOT bonding is limited and gas tax increments have failed six years in a row.  If WSDOT had been able to convey the concept that project needs were so huge that they dwarf gas tax revenues, this recognition might have been heightened.

In addition, although proponents of SHB 1006 felt that tolling was clearly identified when putting forth the New Partners program, somehow the public did not understand that the program  involved tolls.  In a sense, citizens supported the initiative in general but did not like the specifics.  Voters were not educated as to WHY public-private arrangements made good sense for the State and its citizens – whether the access to private capital was important, or greater private sector efficiency in road construction, etc.  Some voters wondered:  “if this program is such a great idea, why doesn’t the DOT do it itself -- what added value are we receiving for the private sector involvement?”

The public (and the DOT) also needs to understand that “cherry picking” is an element of P3.  The perception that private firms might profiteer off public needs is easy to develop and hard to refute.  The key is to understand that the private sector, while it needs to make a return on its investment, can provide net benefits to the State.

Public Outreach Efforts Must Use The Right People To Reach The Right People

Public outreach needs to be a dynamic set of activities that keeps abreast of any changing conditions between proposal selection and final negotiated agreement.  The audience for outreach may thus change over time and cannot be prescribed beforehand.  Aside from reaching the general public as well as public officials in the DOT, WSDOT needed to keep new legislators informed and garner their support, which was not done.  Indeed, by leaving much of the outreach to the proposers, the public at large was not adequately brought into the process.  This was reflected in a Seattle newspaper from June 1994 which wrote: "[the] state may like transportation projects, but what about the public?"

Furthermore, the key individuals required to conduct outreach may change depending on the intended audience.  Indeed, WSDOT's support was questioned by some participants.  As opposition arose, following the 1994 election results, and a new legislative leadership came into power, strong support from the Secretary and the Governor could have been critical for this otherwise non-standard approach.

Undertaking Six Partnership Projects From Scratch Overwhelmed The DOT

As WSDOT had no experience with such a program and the State had no tolls in place, several detailed negotiations went forward simultaneously, and large interests were at stake.  WSDOT may have had a smoother experience if they had staged the selection process.  In addition, administrative costs can be higher than anticipated, including the costs to design a program, issue RFPs, review submittals, select winners, oversee development and environmental processes, and eventually monitor toll collection and road maintenance.  These activities need a dedicated professional staff, and they continue for the life of the project or program.

Transparency Vs. Confidentiality

In hindsight, broad competition with no defined project list, meant WSDOT properly held business proposals in confidence and restricted disclosure, which left itself open to the perception that the selection process was “behind closed doors,” with attendant implications.

States May Wish To Guide Proposers To Projects Wanted By Regional Jurisdictions

No mechanisms were in hand to assess whether New Partner projects were highly sought by individual county and regional jurisdictions.  The program may have received better local support if it had linked directly to MPO TIPs.  For example, the Puget Sound MPO had not completed its regional plan before the six demonstration projects were accepted.  MPOs might prefer a specific list of projects targeted to their needs, rather than selected from private proposers.

E-470:  Public-Private Partnership in Denver Metropolitan Area

# Background

Colorado drew much of its public-private partnership experience from one major undertaking, the design and construction of a circumferential highway around the eastern perimeter of the Denver Metropolitan area.  This locally controlled initiative’s innovative blend of public and private finance made E-470 a success story among public-private partnerships.

The Denver Metropolitan area has grown rapidly since the 1970s.  The region, but for a brief recession in the mid 1980s, has become increasingly diversified in its economy and population.  A low cost of living, relatively high wages, and available employment attracted families from California and other, more crowded regions of the country.  Local governments in the southeast Denver Metropolitan Area embraced this growth and sought to make sure that communities provided the necessary infrastructure to meet demand.

The idea for a beltway around Denver had been discussed as early as 1958.  However, it was not until the late 1970s that federal funds were used to construct parts of a circumferential highway around the Denver area.  At that time, plans were made to construct both an Eastern segment (E-470) and a Western segment (W-470).  The Eastern segment was intended to connect Denver International Airport (DIA) and the northern parts of the City with the booming southeast Denver communities including Arapahoe, Adams, and Douglas Counties as well as the Cities of Aurora, Brighton, Parker, Thorton, and Commerce City.  Once complete, it is expected that commuters will save approximately 10 to 15 minutes over driving on existing roads to the airport.  E-470 will be the only high-speed, north-south corridor on the east side of Denver.

Even before the western section was completed in 1990, however, it became apparent that budget and political constraints on the Colorado Department of Transportation (CoDOT) would delay the extension of the beltway east of Denver.  Indeed, as early as 1985, due to the enormous cost of the beltway project, CoDOT felt pressure from other regions of the State to seek alternative options to complete the beltway, reserving scarce federal and state funds for areas beyond the Denver metropolitan area.  Under legislation passed in 1987, the aforementioned counties and cities created the E-470 Authority by intergovernmental agreement.  At that time, the Authority did not have the power to issue bonds or raise revenues.  In order to get the project moving, therefore, Arapahoe County offered to issue bonds for construction.

An Arapahoe County Commissioner, Tom Eggert, was one of the original backers of the project.  He believed in the road’s potential not only to relieve congestion and connect southeastern Denver to DIA, but to open the doors to economic development for Arapahoe County and the surrounding area.  Under Eggert’s leadership, Arapahoe County issued over $722 million in bonds in 1986 to finance the construction of E-470.  The project, however, was not ready to go to construction.  As a result, the bonds had to be deposited in escrow and were remarketed at 6-month intervals.  As they were intended to finance construction of a highway, it was not credible to issue them for periods longer than six months and still claim they were ultimately going to be used for project finance.  Once the project was ready for construction, the bonds could be re-issued for a longer period and the escrow account closed, as project revenues would be realized and used for debt service.  Arapahoe’s strategy to issue for deposit to escrow was feasible, however, because Arapahoe County issued before the 1986 Tax Reform Act took effect.  Thus, the County could use arbitrage earnings to repay the short term bonds plus interest and re-issue new bonds until such time as the project was ready to go to construction.

# PROCESS AND PROJECT DESCRIPTION

The process used to engage the private sector was secondary to the State’s intention of using a public authority structure to construct the road.  Indeed, much of the process developed in response to events that took place.  A detailed timeline for the project follows this section.

In 1987, Colorado passed the Public Highway Act, enabling municipalities to join together and create highway authorities within metropolitan regions of Colorado for the purposes of financing and constructing beltways and other transportation improvements.  The Act allowed the E-470 Authority to assess fees within their constituency in the form of tolls, highway expansion fees, and other special targeted assessments.  Under the Act, the State Legislature authorized the E-470 Authority to control the finance and construction of the project.  This included responsibility for the bonds as it now had the means to collect revenue for their repayment.

Once the E-470 Public Highway Authority had taken responsibility for the bonds it looked to establish revenue streams to begin construction and debt pay-down, as follows:

- Tolls -- paid by motorists who used the road for improved access to DIA;

- A $10 per year vehicle registration fee -- paid by local residents who would be beneficiaries of the road and the economic growth and development it would generate; and

- A highway expansion fee -- levied on developers who were similarly beneficiaries of the road and the increased mobility and access it provided their developments.

The vehicle registration fee required a majority approval from voters in the relevant districts.  The approval came by referendum in 1988 and the Authority began assessing the fee the following year.  No vote was required to implement the highway expansion fees.

The Authority retained the Union Bank of Switzerland (UBS), which had substantial international experience in these types of projects, to secure financing for all four segments of E-470, at a total cost of around $1 billion.  Using traditional methods of project finance, UBS tried to issue a letter of credit (LOC) backed by a consortium of commercial banks.  They were unsuccessful in this attempt.  However, UBS was able to issue a smaller LOC for $66 million to finance segment I of the road, where the LOC was backed by the vehicle registration fees.  Segment I was structured as a traditional design/bid/build contract.  After construction on segment I began, UBS attempted a second time to issue the larger LOC and failed a second time.

At the same time, the E-470 Authority determined that the remainder of the contract should be bid under a design-build structure, both to accelerate the rest of the project (it was now very delayed) and to allow partial financing of the design work.  Lacking an existing model for a design-build contract for highways, the E-470 Authority worked with prospective partners to design an RFP and contract agreement that would maximize public and private sector strengths.

The Authority issued the E-470 RFP for a design-build contract, with a fixed price and completion date. The RFP also stipulated a three-year warranty as well as early completion incentives.  Using a competitive bidding process, the Authority selected Morrison Knudsen (MK).

Realizing that UBS was having difficulty arranging the needed financing, MK signed a separate agreement that assigned the firm the formal role of financier in return for a success fee.  MK pursued two strategies in parallel: attempting to secure the traditional LOC with commercial banks as well as working with the various rating agencies to permit the project to issue revenue bonds.  The latter approach had no precedent as the rating agencies were uncomfortable with construction risk in a revenue-backed arrangement.

MK discovered at this time that the fourth segment of the project represented a “weak link” in terms of low traffic counts and high cost per mile.  Further, the selected alignment exacerbated the problem.  Pressured by the need to reduce the cost and scale of the project to make it financially feasible, planners modified a portion of the initial alignment of the proposed road.  By moving the alignment of Segment IV closer to Denver and utilizing an existing interchange with I-70, projected traffic volumes would improve and the reduction in the length of the road required would reduce costs by $100 million.  Unfortunately, this change strained the relationship between Arapahoe County, who had championed the project and issued the debt, and the Authority, which now had control over the project.

The realignment also angered developers who, relying on the road’s initial location, had begun purchasing land and planning businesses along the route.  Environmental interests raised additional complaints.  Moving the road in toward Denver, they argued, would aggravate an already serious air pollution problem in the metropolitan area.  Finally, residents of nearby affluent communities objected to the road’s proximity.

While the change in alignment offered an arena in which to fight an unrelated political battle for control over the project, this masked a real loss of support among some localities and the development community.  Arapahoe County Commissioner John Nicholl led opponents to the alignment change.  Nicholl agreed the communities would benefit from E-470, but he believed that residents of the area should have a chance to vote on the road’s new alignment.  Arguing that the public voted on vehicle registration fees under the initial alignment, Nicholl thought voters should be asked again whether a different alignment should be utilized.  His argument rested on the notion that the public had been subject to a “bait and switch” in that E-470 stakeholders had supported a tax based on one alignment and were asked to accept a different alignment for the road without a new vote.

Unfortunately, this issue also arose in the midst of a fight for control of the project and the commissioners engaged in this fight used the concern over the re-alignment to garner support for their case. In particular, two of three Arapahoe County Commissioners, including Nicholl, filed suit in 1993 stating among other claims that the Authority’s plan of finance to remarket the 1986 bonds violated the TABOR amendment, which requires any new bond issuance by a government entity be subject to a vote.  The Colorado Supreme Court, however, ruled that the E-470 Authority could proceed with the plan of finance without an election.

By doing this, the courts effectively over-ruled a County Commissioner, which may not be the best way to educate and garner local support.  Had these two issues been kept separate, the E-470 Authority and MK could have addressed the issue of needing to re-align the road head-on, and either gathered sufficient support to obviate the need for a re-vote or at least educate the stakeholders so they could cast an informed re-vote on the issue (In terms of setting precedent for further P3 initiatives, the way this was handled may be remembered).

During the interim period when the project was delayed due to litigation, the Authority was undertaking the re-issuance of the debt with MK playing the role of financier.  It became apparent that  MK was experiencing financial difficulties.  MK needed to select a partner that could support it financially.  MK selected Fluor Daniel, and the project went forward as a 51/49 (FD/MK) equity limited partnership, under the name Platte River Constructors.

The final financing consisted of a combination of debt and grants.  The City of Denver further agreed to construct an interchange over existing Route 70 near DIA,  worth about $7 million.  No direct federal highway aid has been made available for E-470 (See financing table below).

E-470 Project Financing

| Financing | Amount |
| --- | --- |
| Vehicle Registration Fee Bonds | $51 million |
| Senior Current Coupon Bonds | $406 million |
| Senior Deferred Interest | $181 million |
| State Loan and Local Match | $40 million |
| Contractor Investment | $16 million |
| Total Funds | $694 million |

E-470 Project Timeline

| DATE | EVENT |
| --- | --- |
| 1985 | E-470 created by IGA for express purpose of planning, designing, and constructing E470 |
| 1986 | $722 million in bonds issued by Arapaho County |
| 1987 | Passage of Public Highway Authority Act |
| 1988 | E-470 Public Highway Authority established Citizens of affected area approve $10/year vehicle registration fee |
| 1989 | $63 million of bonds released for segment I |
| 1991 | Segment I open to traffic and tolls |
| 1991-1993 | Financial plan for remainder of roadway using a $1 billion letter of credit eventually replaced by a fixed-rate long-term financing plan |
| 1993 | New alignment adopted by Authority Board |
| 1993-1995 | Litigation by opponents to the alignment change |
| 1995 | Supreme Court rules Authority’s financial plan could proceed with the 1986 bonds |
| 1995 | Bonds remarketed; project commences construction |

LESSONS and highlights

# Locally Initiated Programs Need To Involve The State

The process used in Colorado did not formally involve CoDOT.  While the DOT offered its services on more than one occasion, the Authority did not show much interest in accepting help. The Authority Board was not familiar with the nuances of project finance, but trusted MK’s expertise and familiarity with project finance to engage them as financier. Once MK took a more formal role in arranging the financing, however, they quickly approached CoDOT for assistance.

MK realized that the municipal bond market would look for state support of a large revenue bond issue, especially where there was no precedent for this kind of financing. Over the 1992-1993 period, MK secured a $20 million loan from CoDOT that required a $20 million local match. The value of the loan was not as important as the demonstration of state support for the project that the cash loan provided.  While providing less than 3 percent of project costs, the loan went a long way to reassure investors in the public sector’s commitment to E-470 and the viability of the endeavor.  This kind of state support is critical to re-assure investors that a project of this magnitude is both needed and encouraged by the administration.

Where cash support is not possible, other kinds of support can be provided, such as a promise not to build competing roadways or in-kind contributions. One of the key issues that arose during financial consideration of the E-470 project was related to land use jurisdiction and planning.  It was essential to the various parties that this planning report was unbiased.  CoDOT’s assistance here was crucial to maintain objectivity between competing interests.

At the same time, when a project is locally initiated, such as this one, there was concern on the part of the Authority that the state would “take over”.

While the E-470 example demonstrates the strengths and weaknesses of a project grown from local initiative, a clear and defined state role may have aided early on to secure financing and minimize costs.  As well, an increased state role may have been able to alleviate some of the political issues that arose that led to costly litigation motivated by angry developers.

Where a program permits local government entities to promulgate a P3 arrangement, the role of the state and the role of the local entity should be carefully identified and articulated at the start, probably in the guidance establishing the program.  This will allay fears on the part of the local entity, provide a framework for action by the state, permit each party to offer those services that take advantage of their respective strengths, and provide comfort to the bond market that the project has state support.

# Outreach Can Alleviate The Perception Of “Bait And Switch”

If circumstances require a change after local support has been secured, it is imperative that the DOT walk the public through the change: why it occurred and what it means.  This concept applies more broadly as well.  In the event the P3 program is generated locally, it is just as important to explain from the beginning that a private partner is sought and why, so that the public is not “surprised” when a private partner appears.

# California:  San Diego Expressway Project

# Background

The San Diego Expressway Project consists of constructing about 11 miles of new highway alignment from State Route 905 near the International Border to State Route 54 near the Sweetwater Reservoir. The project calls for the ultimate construction of an eight-lane highway plus possible future construction of carpool lanes and/or transit facilities in the median.

The San Diego area has a relatively diversified and prosperous economy and growth record and is experiencing a strong recovery from the recession of the early ninties.  Its location in Southern California, contiguous to the Mexican border, provides an international aspect to traffic patterns and an additional thrust to traffic growth.

In order to divert commercial traffic away from the congested San Ysidro border crossing to Tijuana, Mexico, the Federal government opened the Otay Mesa border crossing several miles to the east in 1984.  Sanyo NA became the first business to move into the Otay Mesa area.

For a number of reasons, cross-border commerce and trade have blossomed in the San Diego region.  The entire state of Baja (Mexico) contiguous to the California border  is designated as a Free Trade Zone by the Mexican government.  This is the underpinning of the Maquiladora (maquila) program in Mexico.  The maquila program permits duty-free transfer of parts into Mexico (from the US) for use in manufacturing.  The result has been to focus manufacturing in Mexico, using less expensive labor, but often reliant on US components:  management, sales and R&D tend to be housed on the US side of the border, creating the twin-plant concept.  An estimated 755 maquilas operated in Baja in 1995, with employment of 150,000; growth has continued despite the devaluation of the Mexican peso in the mid-1990s.  Tijuana, Mexico, directly adjacent to the border south of San Diego, has the greatest concentration of maquila operations and related employment.

Several domestic US actions have fueled economic growth of the twin plant industry, built around complementing the Maquiladora program in Mexico. The State of California designated Otay Mesa as an Enterprise Zone receiving special tax and other advantages.  In 1989, Otay Mesa was designated a US Foreign Trade Zone which conferred certain tax and other financial incentives to manufacturing and related industries.  As a result, twin plant activities grew rapidly.

# Effects of NAFTA

NAFTA gives preferential treatment, and complete tariff elimination to goods made or assembled in North America, with the probable result that a higher percentage of components will be sourced from North America (less from outside the NAFTA countries).  This provides additional incentive for maquilas to buy American, hence the likelihood of more trade flowing across the Mexican border.

In 1996, there were approximately 380 companies operating in Otay Mesa, employing about 10,000 people.  Thousands of acres are zoned for commercial/industrial use and ready for development.  Trade and maquila production, which was already growing strongly, were further strengthened by the passage of NAFTA.  Commercial traffic to/from the border area (all via Otay Mesa) has increased rapidly, coupled with employee travel to/from and through the border crossing.  This activity was aided by a duty free import program for goods moving back and forth in the production process.

In fact, the San Diego Association of Governments’ (SANDAG) land use plan showed a large heavy commercial zone along the border, endorsing the growth. San Diego County adopted its East Otay Mesa Plan to provide for additional commercial and industrial development east of the San Diego city limits. Six industrial parks are already established on the Mesa, containing more than two million square feet of building.  "There are more than 6,000 acres under the land use jurisdiction of either the City or County of San Diego, on the U.S. side Otay Mesa, planned for commercial and industrial use."  In addition, nearly 2,000 more people are employed at the several correction institutions in Otay Mesa and another 1,000 are employed by the federal inspection services at the border.

# TransNet Program

The San Diego region has a supplemental funding plan for transportation improvements administered by SANDAG.  The plan is funded by a 1/2 cent regional sales tax adopted in 1987 for 20 years, through April 2008.  When the sales tax was approved by voters, it was passed with the understanding that it would be used to fund these transportation improvements.  Parts of the TransNet program are bonded, issuing revenue bonds supported by the sales tax revenues.

The SANDAG Board of Directors administer the TransNet program.  One-third of the revenues are allocated to maintain and improve local streets using an agreed formula.  The other two-thirds are dedicated to highway and public transit improvements.  Every two years, a seven-year list of projects, the “TransNet Plan of Finance,” is updated which will use TransNet funds.  The revenues have been negatively affected by economic downturns in Southern California, and project costs have gradually inflated.  The estimated sales tax receipts will only cover approximately 70 percent of the costs.  Other traditional revenue sources will be needed to fully fund all projects.  Further, the program is unlikely to be renewed, because the statutory requirement now calls for a two-thrids majority to adopt an add-on sales tax and support is not there.

# Process:  AB 680

# Scope and Legislation

The SR-125 project was part of a larger statewide P3 initiative.  The State of California authorized four demonstration projects for development of transportation facilities by private entities under its AB 680 legislation enacted in July 1989.   Under AB 680, Caltrans was given broad, relatively autonomous authority to select four projects and enter into agreements with private parties, and it appears that the State chose projects under AB 680 with only limited input.  Geographic dispersion criterion for projects included in the statute required at least one project in Southern California and one in Northern California.

Major concession terms were relatively standard across the projects.  Firms would design, build, transfer, operate (BTO) for up to a maximum lease of 35 years and be responsible for maintenance and operating costs (the State may provide maintenance and the California Highway Patrol may perform policing services on a reimbursable basis).

Operators can set and collect tolls, can earn a "reasonable return on investment" net of ongoing expenses and debt service. Concession agreements are expected to inhibit Caltrans from building competing facilities, but exceptions were generally provided.  Finally, Caltrans is required to use its condemnation powers (eminent domain) on behalf of the project, if requested by the private operator.

The SR 125 project was one of four projects selected by Caltrans in September 1990.  The other projects were:  the SR-91 Express Lanes; the SR-57 extension in Orange County; and, the Mid-state Tollway (near San Francisco Bay).  Only one of four projects selected has become operational to date, the SR-91 Express Lanes.

California Transportation Ventures, Inc. (CTV) Rationale for Proposing San Diego Project Under AB 680

Caltrans had shown the general alignment of SR 125 South on San Diego area planning documents since the mid-1960s, and SANDAG had likewise identified a need for an eastern "outer loop" highway system in th Regional Transportation Plan since 1984, but constraints on public funding had precluded any construction activity.

California Transportation Ventures, Inc., a partnership between Parsons Brinckerhoff Infrastructure Development Co. and Transroute International, S.A., is the project sponsor.  CTV identified SR-125 South as appropriate and meeting the objectives of AB 680 to provide needed regional transportation facilities with private sector funding.  This area was characterized by:

- A dynamic environment in San Diego County, especially in the South Bay/Otay Mesa regions;

- Major land developments in and around the SR 125 South corridor, including residential developments at Otay Ranch (23,000 dwelling units alone), EastLake, and several others;

- Increasing trade and traffic across the US-Mexican border, with industries in Otay Mesa eventually at build out expected to employ 140,000; and

- Potential for an additional, northern segment from Route 52 to SR-56.

Most importantly, strong local support for completing the SR 125 project was demonstrated by the public funding of the connections to I-5 and I-805 to the west and I-8 to the north, and the initiation of environmental and route location process by SANDAG, the County of San Diego, the City of San Diego, and the City of Chula Vista under a 1989 Agreement with Caltrans.

# Project Description

The proposed State Route 125 South (SR 125) is designed to be a north-south highway corridor in southeast San Diego County traversing a partly developed region extending south to the Mexican border that will provide access to the Otay Mesa border area employment centers and adjacent border crossing.  The Southern segment of SR 125 is planned as an 11.2 mile controlled access highway running from State Route 54 south to Otay Mesa.    The southernmost 10-mile segment is planned as a privately-financed toll road built to freeway standards.

The northern-end segment (1.2 miles plus the interchange with SR 54), commonly referred to as the San Miguel Connector, will be built with public funds allocated by SANDAG.  Current plans are for CTV to construct the connector and be reimbursed by SANDAG under an extension to CTV’s franchise with Caltrans, requested by the SANDAG Board on February 28, 1997.

Additional northern segments of SR 125 are planned as freeways by SANDAG, and some are already under construction, as discussed below, with the result that this eastern corridor would connect with major east-west routes on the northern side of San Diego, as far north as SR 52, making an important contribution to traffic projections.   It is important to note that the entire segment of SR 125 from I-8 to the Otay Mesa border (including the tollway) has been designated as part of the National Highway System.

Land use to accommodate growth has been approved.  A large area is already zoned commercial, and there are extensive plans to move ahead.  In fact, SANDAG views the toll road as helpful for its land use plan, because it will serve planned developments in a manner consistent with the approved Regional Transportation Plan (the population within San Diego County is projected to grow from 2.7 million in 1995 to 3.8 million by 2015).  In addition, investments at the Otay Mesa Port of Entry will improve the flow of business traffic and commuters to/from the maquila plants in Mexico.  In particular, there is a new, dedicated commuter lane at the Otay Mesa Port of Entry.  Commuters returning to the US can obtain a permit, essentially represented by a smart card and vehicle transponder, to speed border clearance.  The card has a photo ID for quick checkup of auto drivers and passengers.

Finally, Chula Vista, in addition to being a major residential center, is also a shopping center for Mexican day-trips and a weekend home spot.  Both Chula Vista and Otay Mesa see heavy southbound commuter and commercial traffic, and sense that SR 125 will provide traffic relief by the time it is completed, since I-5 and I-805 (the other two north-south routes) are approaching capacity.

#### CTV’s Role

While CTV is the project sponsor (with financial contributions for the San Miguel Connector from SANDAG), the San Diego Expressway Limited Partnership (SDELP) actually holds the franchise, for whom CTV serves as managing partner.  CTV's franchise agreement provides for cooperative actions, assistance in obtaining permits and financing, and facilitation of local, State, and Federal roadways interconnecting with the tollway.  CTV is even given certain limited rights, subject to approval by SANDAG, to extend its tollway (discontinuously) in a northerly direction to connect with east-west routes 94, 52, and 56.

All parties have agreed that it makes sense for CTV to amalgamate the one-mile San Miguel Connector into its own construction project, concluding that a design/build arrangement integrated into CTV's construction contract would help realize economies of scale.

A recent projection of overall project costs for SR 125 South was approximately $315 million (as of late 1996).  In order to reach construction, CTV expects to have spent roughly $25 million for development and environmental costs, and another $40 million for ROW.  The ROW for the toll road requires about 730 acres, of which about 430 acres are expected to be donated by four major land developers, the Baldwin Company, EastLake Development Co., Trimark Ventures, and McMillin Companies. The final alignment recommendation has been made by Caltrans for the tollway and the connector.  One key cost has been controlled by virtue of CTV having contracted with Caltrans for environmental work in a fixed price contract.  CTV was originally supposed to do the EIS, but due to a request from the City of Chula Vista, Caltrans has agreed to complete the EIS under a fixed price contract with CTV.

SANDAG has committed $100 million out of the current seven-year TransNet program to support the San Miguel Connector and the interchange with State Route 54.  To program funds for the San Miguel Connector of SR 125 South, along with other complementary segments of SR 125, SANDAG had to commit its regional Federal funds that were intended to help border crossings under NAFTA.

The CTC was willing to reallocate, but some of this comes at the expense of "regular" priorities for the San Diego region.  Caltrans jointly with SANDAG proposed to the CTC to advance the San Miguel Connector and reprioritize the Sweetwater segment, using $132 million State and Federal dollars.  SANDAG further estimates that it has spent about $500,000 on environmental documents related to SR 125.  The Chula Vista and Otay Mesa Chambers of Commerce and several other local agencies were helpful also, urging SANDAG to provide financial support for the San Miguel Connector and other northern extensions that will complement the toll road.

CTV expects to issue taxable debt of about $220 million (including inflation, a total of $410 million, less $90 million equity and land contributions and $100 million more reimbursed for the San Miguel Connector from SANDAG).  This debt would be primarily financed by toll revenues on the facility, though some revenues from air rights, concessions, and impact fees are possible.  Chula Vista has Assessment Districts, and can provide incentive to donate ROW and also charge impact fees running $2,500 to $4,000 per DU for road improvements which supplement the SR 125 project.  The SDELP partnership has the right to sublets air rights on the SR 125 ROW.

CTV has actively pursued credit enhancement options, such as obtaining guarantees on their debt financing, possibly  through loan guarantees from a California State Infrastructure Bank (SIB).  CTV has also expressed interest in a Federal standby line of credit to serve as a traffic guarantee for the first 10 years of operation.

# Timeline for SR 125 Tollway

# The following chart shows key events in the SR 125 timeline.

| DATE | EVENT | COMMENT |
| --- | --- | --- |
| 1960s | Route adopted | Corridor protected, never funded, rescinded later in 1976 |
| 1984 | Otay Mesa Border Crossing | Northbound Commercial traffic diverted |
| 1987 | TransNet funding plan | County adopted 1/2 cent sales tax for TransNet program |
| 1989 | AB 680 enacted | Caltrans authorized to develop four roads by private partnership |
| 1984 | SR 125 reinstated into region's long-range plan | SANDAG agreed with Caltrans, recognized need, put SR 125 back into Long-term plan in March 1989 |
| February 1990 | AB 680 candidates chosen |  |
| July 1990 | Caltrans receives proposals | CTV and Bechtel submit proposal for SR 125 |
| September 1990 | Caltrans selects projects | SR 125 one of four selected projects |
| January 1991 | SR 125 franchise executed | CTV awarded franchise for SR 125 |

| DATE | EVENT | COMMENT |
| --- | --- | --- |
| June 1991 | Lawsuits filed protesting AB 680 process & SR 125 | State engineers protest outsourcing & Chula Vista challenges tollway development |
| 1992 | Lawsuits settled/dismissed | Engineers lost; Chula Vista settled |
| August 1992 | CTV/Caltrans agreement | Caltrans agrees to contract to perform environmental work |
| December 1992 | NAFTA signed by USA | NAFTA Treaty Effective Jan. 1994 |
| 1993 | Alignment studies | Ten alternative alignments selected and put under review |
| April 1994 | SANDAG supports connector & interchange | Public funding for San Miguel connector allocated |
| March 1995 | New alternative route added for study | Citizens Advisory Committee Alignment adds new study option |
| April 1996 | SR 125 Fanita section | Ground-breaking on segment |
| May 1996 | CTC allocates funds to SR 125 | State supports Sweetwater segment |
| July 1996 | DEIS circulated by Caltrans | Environmental study made public |
| August 1996 | SR 125 Sweetwater ground breaking |  |
| September 1996 | Comment period ends | Caltrans begins review of comments |
| August 1997 | Alignment recommendation | Caltrans assembles Final EIS |
| 1997 and 1998 | Seeking record of decision (ROD) & financing | CTV plans financing in late 1997; Construction to begin immediately |

project Status

CTV obtained an exclusive franchise to build a tolled expressway from Caltrans under the AB 680 program in 1991.  They are now seven years into project development.  Significant development expenditures have been incurred, two opposing law suits have been overcome.  The larger suit was a statewide challenge to AB 680 in which the Union of State engineers argued that the AB 680 process would simply outsource their engineering work.  As of the Fall of 1997, Caltrans is assembling the final Environmental Impact Report/Statement (FEIR/FEIS) and finishing the biological assessment necessary for Federal approval of the project.

While funding for the Connector had been secured through an agreement between CTV and SANDAG, long-term financing has yet to be arranged for the tollway segment.  As of now, financing seems likely to be private taxable debt of approximately $220 million, though several alternative options are available (such as SIB assistance), and tax-exempt status might be possible.  Finally, there is some precedent to using project-specific lines of credit and direct loans to enhance California projects.

CTV has not actually obtained ROW, but has agreements for land contributions from several developers.  AB 680 also provides access to condemnation via Caltrans.  Much of the residential build-out is planned for and approved, supported locally, and developers are apparently ready to go; Chula Vista seems especially eager to support residential construction and has a 23,000 unit development which began construction in the Fall of 1997.  Residential development is still prospective in nature, however, and depends on the overall growth of San Diego County, border trade, and the real estate market.

SANDAG commitment is positive, but there is a concern.  The San Miguel Connector is complicated and the Connector will feed directly into the toll road.  SANDAG has committed local sales tax revenues, intended for other projects, to this connector.  When local voters approved the sales tax, however, it was with the understanding that the funds would be used for free facilities.  In fact, the funds were only intended for the SR 125 connector and for other projects; there was not enough money to fund the SR 125 South segment as well (so it was never a question of asking for funds for a free facility only to then change that facility into a tolled facility).  Moreover, the connector itself is free; it simply links to the toll facility.  Voter perception, however, may be difficult to sway.

Another regional issue concerns funding for Route 905.  The SR 905 project is a key traffic link for the east/west corridor serving the Otay Mesa border area for truck traffic traveling to and from San Diego currently served only by the four-lane Otay Mesa road. It offers the only free alternative to move through traffic out of the border area.  It is crowded with commercial trucks and the CTC has already allocated $16 million to make the Otay Mesa Road section into a six-lane highway.

The Otay Mesa Chamber of Commerce has suggested that SANDAG is trying to have it both ways on SR 905, doing limited improvements now in 1997, reserving the ROW for a freeway, but holding major improvements until the year 2005, which Otay Mesa says is really 2020 because there will not be any funds left in 2005.  They feel this strategy will not get SR 905 built in a timely fashion unless specific federal funding is allocated.

Remaining next steps for CTV include:

- The final administrative hurdle, the FEIR/S, Section 404 Permit, and ROD;

- Selection of a design-build contractor; and

- Obtaining financing and moving to construction.

In order to finalize the EIS,  Caltrans needs to complete:

- A relocation study;

- A biological mitigation plan; and

- Finalize responses to all comments received.

By and large the private development of the road appears welcome, and the County entities have stated:

"The infusion of private funding for SR 125 South will ensure the timely completion of San Diego County's planned highway network and the provision of access vital to the economic success of the entire region."

# Lessons and Highlights

# Financial Arrangements Should Be A Function Of The Project’s Risk Profile

Building a new road is a long-term process, with very uncertain results.  SR 125 was granted its franchise under AB 680 in 1991, after one to two years of application effort.  While CTV has (along with the real estate developers who donated land) been willing and able to sink considerable equity into this venture, the long lead time inherent in a greenfield road has increased the risk to the private partners considerably.  This has several implications:

- Other firms in the same situation may not have been willing or financially strong enough to take such a position.  Risk sharing thus needs to consider the nature of the risks involved and the profile of risks over time.  Where a DOT or local government feels this type of project is very important, it can reduce this risk to the private party by sharing some of this upfront risk, or by recognizing it in negotiations over rate of return.  To some extent this has happened: SANDAG has recently decided to fund the San Miguel Connector up-front through direct reimbursement to CTV (instead of over time as initially proposed).

- The rate of return may need to be re-negotiated or structured as a function of different outcomes.  The rate negotiated between CTV/SDELP and Caltrans was 18.5 percent.  Based on today's risk/reward profile, this limited return permitted to CTV/SDELP under its franchise may not be adequate, compared to the continuing possibility (in 1997) of a complete loss of significant equity capital expended (since 1989).  Note that a portfolio investment in NYSE stocks has earned about 25-35 percent annually for the past two years.

- The state’s contribution may need to reflect the type of project.  Under AB 680, Caltrans cannot use State funds.  Given the project’s greenfield nature, this may have been an unrealistic restriction that precludes good projects from getting done.  Indeed, start-up financial assistance may be necessary to keep private players interested.  SR 125 has required major up-front equity over about eight years so far, with no revenues in sight before about 2000.

Environmental Clearances Should Be Sought To Maximize Flexibility and Minimize Objections

Environmental clearances are difficult, lengthy in duration, costly, and often a stumbling block.  States and private entities should seek a way to minimize the possibility for local, state, or federal objections and seek to obtain the highest clearance possible if there is any chance Federal funds will be used at any time in the process.

At the request of the City of Chula Vista, Caltrans undertook the EIS.  CTV officials suggested that this is one area of risk and cost that the public partner can and should assume as the state has a natural advantage here: the value of the risk it saves the private partner is worth more to that partner than it costs the state.  Thus, it can be valued as a contribution in excess of what it actually costs the state to undertake (effectively capturing some or all of the rent for the state).

Finally, it would facilitate such projects to include a calendar “cut-off” date to limit late-stage environmental challenges to the Federal  EIS.

# Any Non-Compete Clause Must Be Clear and Binding

The non-compete clause must be clear in setting local priorities.  SANDAG recognizes the need for SR 125 when it states:  "The relocation of the commercial port of entry to Otay Mesa and the NAFTA-related traffic growth is overwhelming the existing border transportation infrastructure."  SANDAG has been supportive despite having many competing priorities.

The widening of Otay Mesa Road to six lanes by 1998 was recently scheduled, evidence that both SANDAG and Otay Mesa recognize the urgent need to upgrade the major East-West SR 905 to serve border traffic.  Otay Mesa Road currently serves as an extension of SR 905 and is feeding traffic to/from I-805 and I-5, the two major north/south Interstate roads through San Diego.  While this improvement may seem to compete with SR 125, it actually will stimulate further area growth.  SR 905 also provides a free, direct route into and out of the border crossing area.   Caltrans is restricted from developing competitive facilities in a six mile wide corridor along SR 125, although SR 905 was specifically called out in the franchise as an exception to this restriction.

# Using Funds to Support Private Toll Road Projects

Opponents of the project have raised the issue of TransNet allocating the sales tax revenue for the San Miguel Connector that leads into the toll road.  In fact, the very concept of public-private partnerships is based upon both sectors providing funds or other non-monetary resources to complete necessary public infrastructure projects.

##### APPENDIX 1: INDIVIDUALS CONTACTED FOR THIS REPORT

Appendix 1: Individuals contacted for this Report

#### Arizona

Bill Hayden (ADOT)

Suzanne Sale (ADOT)

Bill Allen (Dewberry & Davis)

Robert Farris (Interwest)

# California

Roy Nagy (Caltrans)

Bill Allen (Dewberry & Davis)

Mike Schneider (Parsons Brinkerhoff)

Penny Allen (Allen & Company)

#### Colorado

Tom Eggert (Arapahoe County Commissioner)

John Nicholl(Arapahoe County Commissioner)

Pam Bailey (E-470 Authority)

Jeff May (DRCOG)

Frank Finlayson (Morrison Knudsen)

Jim Carroll (Fluor Daniel)

#### Florida

Nick Collins (Mngr. Public Private Trans Progr, FLDOT)

Brady Sneath (FLDOT)

Bill Allen (Dewberry & Davis)

Robert Farris (Interwest)

#### Minnesota

Adeel Lari (Dir. Alternative Transportation Financing, MinnDOT)

Jack Rizzo (Perini)

Robert Farris (Interwest)

#### New York

Michael McCarthy (NYDOT)

#### New Jersey

Robert James (NJDOT)

#### Oregon

Donald Wagner (ODOT)

#### Pennsylvania

Dennis Lebo (Assistant Deputy Sec. For Planning, Penn DOT)

#### Puerto Rico

Gabriel Rodriguez (Assistant Sec. For Planning)

#### South Carolina

Larry Duke (Dir.Fin. SCDOT)

Elizabeth Mabry (Deputy Chief Counsel, SCDOT)

Bill Allen (Dewberry & Davis)

Robert Farris (Interwest)

# Virginia

James Atwell (Assistant Commissioner for Finance, VDOT)

Rick Davis (Asst Admin. of Fin. Plng. VDOT)

Deborah Brown (VDOT)

Kevin Baron (VDOT)

Bill Allen (Dewberry & Davis)

Nici Masucci (VMS, Inc.)

Jim Carroll (Fluor Daniel)

John Milliken (Venable, Baetjer and Howard)

#### Washington

Rhonda Brooks (Program Mngr., Public Private Transportation Initiatives, WSDOT)

King Cushman (Puget Sound Regional Council)

Bill Allen (Dewberry & Davis)

Jack Rizzo (Perini)

Robert Farris (Interwest)

##### APPENDIX 2:”ROLE OF 63-20 NONPROFIT CORPORATIONS IN PUBLIC-PRIVATE INFRASTRUCTURE FINANCINGS”

###### By Karen J. Hedlund

Appendix 2: “Role of 63-20 Nonprofit Corporations in Public/Private Infrastructure Financings”

By Karen J. Hedlund

# Footnotes

Contribution of Highway Capital to Industry and National Productivity, research report prepared for US Federal Highway Administration, Ishaq Nadiri, 1996.

Minnesota Department of Transportation, Request for Proposals for Transmart: Minnesota’s Toll Facilities Public-Private Initiatives Program, July 26, 1995, p. 7.

Daily Journal of Commerce, Seattle, June 10, 1994

Washington State’s Role in Public Private Partnerships, WSDOT, p.11.

Minnesota Department of Transportation, Request for Proposals for Transmart: Minnesota’s Toll Facilities Public-Private Initiatives Program, July 26, 1995, p. 7.

Virginia passed specific enabling legislation in 1988 for the Dulles Greenway project; this project is further discussed in the Case Studies section of this report.  Because the 1988 legislation was project-specific, and not related to the current statewide process, it is discussed only within that case study.

One has been withdrawn and two did not qualify under the Act.

Substitute House Bill 1006, Sec.1.

Subcommittee on Public-Private Partnerships in Transportation.  “Subcommittee Report.”  Washington State Transportation Plan.  August 1992.

1993 Report to the Legislature: Transportation Policy Plan for Washington State.

Ibid.

Ibid, Sec.1 and 2.

Ibid, Sec.3.

Washington State’s Role in Public Private Partnerships, WSDOT, p.11.

Idem.

Ibid, 12.

The Washington Post, January 17, 1998.

Two conceptual proposals, one from Eastern Virginia Public-Private Facilities Partners, L.L.C. and one from Hampton Roads Infrastructure Development Group, were originally submitted.  The two have merged and a detailed proposal is expected from the new entity, Hampton Roads Public-Private Development, L.L.C.

Subcommittee on Public-Private Partnerships in Transportation.  “Subcommittee Report.”  Washington State Transportation Plan.  August 1992.

Substitute House Bill 1006, Sec.1.

1993 Report to the Legislature: Transportation Policy Plan for Washington State.

Ibid.

Ruth Fisher, (former) Chair of House Transportation Committee.

Ibid, Sec.1 and 2.

Ibid, Sec.3.

Washington State’s Role in Public Private Partnerships, WSDOT, p.11.

Ibid

Daily Journal of Commerce, Seattle, June 10, 1994.

Where all or part of the design work must be financed, a design/build approach is often necessary.  In order to issue stand-alone revenue bonds for construction (and design/engineering), the issuer must provide the markets with guarantees of the cost and completion date.  In practice, therefore, the project sponsor must already have the construction partner under contract, which in turn, necessitates the same firm or team undertaking the remaining design, engineering and construction work -- a design/build structure.

The Authority initially selected Brown & Root, but could not successfully negotiate an agreement.

Chula Vista is a rapidly growing residential community to the west of the proposed road.

San Diego Economic Development Corporation, Three Countries, Two Borders, One Market.