EIR Scope of Review ( 16 core review elements)

1.0 Work Breakdown Structure

- Assess Whether the WBS Incorporates All Project Work.

- Assess whether the Resource Loaded Schedule is consistent with the WBS for the project work scope

- Does the WBS represent a reasonable breakdown of the project work scope, and is it product oriented?

- 2.0 Resource Loaded Schedule ( BASIS of COST)

EXAMPLE: WBS 1.0  	$900,000

| Sub WBS element description | Estimated Cost $K | Basis of Cost estimate | EIR Team Assessment of Cost Basis | Finding / Observation if appropriate |
| --- | --- | --- | --- | --- |
| 1.1 | 250 | R.S. Means | EIR team was able to document R.S. Means estimate. Basis of estimate is reasonable. |  |
| 1.2 | 421 | Recent Vendor quote, August 12, 2005 | Description of equipment provided to the vendor was not specific to application No mention of need for NQA-1 compliance. | Costs for WBS 1.2 needs to confirmed with vendor to ensure that vendor is aware of NQA-1 requirements, and that cost incorporates this requirement |
| 1.3 | 229 | Vendor quote 3 years old, August 2003 | Three year old quote is not consistent with good cost estimation practice | Updated vendor quote is required |
| Total 1.0 | 900 |  |  |  |

2.0 RESOURCE LOADED SCHEDULE 	(BASIS of SCHEDULE ESTIMATE)

EXAMPLE: WBS 1.0	240 DAYS

| Sub WBS Element | Estimated Duration | Basis of Schedule Estimate | EIR Assessment of Schedule Basis | Finding/ Observation |
| --- | --- | --- | --- | --- |
| 1.1 | 50 days | Experience from recent project with similar activity | Conforms to good schedule estimating practice. Basis is reasonable. |  |
| 1.2 | 140 days | This element has not been performed previously for this material. Project team used best professional judgment. | No one on the IPT that helped with this estimate has any significant experience in the type of materials that will be used in construction | The EIR finds that there is not a sound basis for estimate. The Project needs to obtain additional expertise in the specialty area. |
| 1.3 | 50 days |  |  |  |
| Total | 240 days |  |  |  |

3.0 Key Project Cost and Schedule Assumptions

| COST / SCHEDULE ASSUMPTIONS (EXAMPLE ONLY) | BASIS of ASSUMPTION | EIR TEAM ASSESSMENT of the REASONABLENESS of the ASSUMPTIONS | FINDING/ OBSEVATION |
| --- | --- | --- | --- |
| Price of steel from now until project completion in 2012 will remain the same | Program Direction | EIR Team does not consider the assumption to be reasonable. Steel prices have increased considerably over the last several years, and the ENR predicts that cost will continue to increase significantly. | Finding: The EIR TEAM finds that the cost estimate is deficient as a result of the technical assumption concerning the price of steel. |
| Technical basis of the design is sound and start-up will not experience significant cost increases or schedule delays due to system not working as designed. | Program Direction | The EIR Team performed a limited review of the design basis. The Team found that the analysis supporting the design is flawed, and does not support the design criteria. | Finding: The EIR Team finds that the cost and estimate is deficient as a result of the likely need to perform re-design. |

4.0 Funding Profile

- Review and provide the basis for the Funding Profile (e.g. FY 05 Project Data Sheet)

- Compare the annual funding with the cost requirements, and provide an assessment of whether the costs and funding are reasonably linked.

- Identify any significant disconnects between the Performance Baseline requirements and funding.

5.0  Critical Path

- Assess whether the Critical Path is reasonably defined

- Assess whether the Critical Path reflects an integrated schedule and schedule durations are reasonable.

- Provide the duration between the Critical Path completion date and the Project Completion date (CD-4).  Is the schedule contingency (float) reasonable for this type of project?

6.0  Risk Management

- Describe the approach used to identify project risks and assess adequacy of this approach

- Assess whether all risks ( including site specific factors such as availability of contractors) have been quantified based on the probability and consequence of occurrence, and whether risks have been quantified as high, medium, and low risk

- Assess whether all appropriate risk mitigation actions  have been incorporated into the Performance Baseline to include cost and schedule contingency.

- Identify cost and schedule contingency, and provide an assessment of whether the basis of contingency is reasonable for this type of project.

7.0 Hazards Analysis

- Identify the functional make-up of the Hazards analysis IPT, and provide an assessment of the overall staffing mix and expertise of the team.

- Assess the Hazard analysis process, including the use of internal and external safety reviews.

- Review any Defense Nuclear Facilities Safety Board and/or Nuclear Regulatory Commission interface and discuss the status of their involvement.  Have DNFSB/ NRC issues been reasonably considered and addressed?

- Assess whether the Hazards identified and the accident scenarios represent a reasonably comprehensive list

- Assess whether all systems, structures, and components (SSCs) needed for worker and public safety have been incorporated into the Performance Baseline.

8.0   System Functions and Requirements

- Assess whether "design-to" functions are complete and have a sound technical basis (The review team should include safety and external requirements such as permits, licenses, and regulatory approvals).

- The EIR Team should assess whether system requirements are derived from and consistent with the Mission Need

- Assess whether the CD-4 (project completion) activities are clearly defined in the Requirements Document, and whether these activities are quantified and measurable, or can otherwise be reasonably determined as complete.

9.0 Basis of Preliminary Design

Review the Process Flowsheet and assess the reasonableness of the input and output parameters for each unit operation. Specifically, the EIR team shall complete the table below that provides a short description of the unit operation, the design parameters, the basis of the design parameters and an assessment of whether the design basis is reasonable.

EXAMPLE

| Unit Operation/ Short Description | Key Input parameters | Key Output Parameters | Describe Basis of Design | Is the composition of the Project feed similar? Explain | EIR team assessment of the basis of design for each unit operation |
| --- | --- | --- | --- | --- | --- |
| Unit Operation A |  |  |  |  |  |
| B |  |  |  |  |  |
| Etc. |  |  |  |  |  |

2.  Review the surrogate tests and provide an assessment of whether the surrogate composition reasonably represents the full range of feed streams for the aqueous polishing operation. Specifically, complete the table below:

| Description of the surrogate test/ surrogate composition | Purpose of the test/ success criteria | EIR team assessment of whether the “success criteria” were achieved |  | The EIR team assessment of the surrogate test |
| --- | --- | --- | --- | --- |
| Surrogate Test A | Assess whether component A can be effectively separated from feed material | Success criteria were not achieved |  | The surrogate test does not provide a sound technical basis for design. |

10.0 	Preliminary Design Review and Comment Disposition

- The EIR Team is to review the adequacy of the preliminary design including adequacy of the drawings and specifications, and assess whether they are consistent with system functions and requirements.

- The EIR Team is to review the disciplines and experience of the Project Design Review Team.  The EIR team is to provide an assessment of whether the Design Review team had appropriate experience and technical disciplines on the team.

- The EIR Team will review the Design Review comments and responses.  Based on a reasonable sample, the EIR team is to assess whether these comments have been incorporated into the Design, and whether the costs and schedule associated with design changes have been incorporated into the Performance   Baseline.

11.0	Start-Up Test Plan

- The EIR TEAM will review the start-up test plan and assess whether the plan identifies the acceptance and operational system tests required to demonstrate that the system meets design performance specifications and safety requirements.

- The EIR Team should review key tests to ensure that sufficient description is provided to estimate cost and schedule durations associated with these tests.

- The EIR team should ensure that the start-up test plan identifies how tests will be determined to be successful, and that associated equipment and instrumentation has been included in the preliminary design.

- The EIR team should assess whether adequate cost and schedule are included in the Performance Baseline to accomplish the required start-up activities.

- Finally, the EIR team should assess whether there is sufficient cost and schedule contingency for test and equipment failure during start-up testing.

12.0	Project Controls/Earned Value Management System.

- Assess whether the project control systems and reporting requirements are in place to correctly report Earned Value.

- Assess the capability to provide for timely and accurate transfer of actual cost information from the accounting system into the earned value management system.

- Discuss specifically whether accrual accounting will be used. If not, assess the adequacy of the EV system to acceptably report monthly cost and schedule information .

- Evaluate the control process whereby projects incorporate formal changes, conduct internal replanning, and adjust past, present and future information to accommodate changes.  Identify whether the process includes a system whereby such changes are documented, explained, and justified.  Asses whether these processes are reasonable.

13.0 Value Management/Engineering.

- Assess the applicability of Value Management/Engineering, and whether a Value Management/Engineering analysis has been performed with results being incorporated into the baseline.

- Provide an assessment of the Value Management/Engineering process for this project.  Include   whether the VM team had a reasonable skill mix and experience background.

- Assess whether Life cycle cost analysis was reasonably performed as part of the  trade-off studies and various alternatives reviewed.

14.0   Project Execution Plan.

- Review the Project Execution Plan and determine if it reflects and supports the way the project is being managed, is consistent with the other project documents, and establishes a plan for successful execution of the project.

15.0  Acquisition Strategy

- Review the Acquisition Strategy to determine if it is consistent with the way the project is being executed.

- The Review Team should evaluate any changes from CD-1 and assess whether the current AS still represents best value to the government.

16.0  Integrated Project Team

- Assess whether the project management staffing level is appropriate, and determine if appropriate disciplines are included in the Integrated Project Team.

- Identify any deficiencies in the Integrated Project Team that could hinder successful execution of the project.