U.S. DEPARTMENT OF TRANSPORTATION

FEDERAL AVIATION ADMINISTRATION

STATEMENT OF WORK

WIDE AREA AUGMENTATION SYSTEM (WAAS)

FULL LPV PERFORMANCE

VERSION 11

DATED

SEPTEMBER 17, 2004

Table of Contents

1.	Scope	1

1.1.	Applicable Documents	2

1.2.	FAA Specifications	2

1.3.	Military Specifications	2

1.4.	FAA Standards	2

1.5.	Military Standards	3

1.6.	Federal Standards	3

1.7.	Other FAA Documents	3

1.8.	Other Documents	4

2.	Contract Execution	5

2.1  Full LPV Performance Delivery	5

2.1.1.	Architecture Upgrade	5

2.1.2       Full LPV Performance Delivery	5

3.	Requirements	5

3.1.	Program Management	6

3.1.1.	Program Management	6

3.1.2.	Program Overview Meetings (POM)	9

3.2.	Systems Engineering Management	10

3.2.1.	Interface Design	10

3.2.2.	System Engineering Analyses	10

3.2.3.	System Engineering Working Group (SEWG)	11

3.3.	Hardware Engineering	11

3.4.	Software Engineering	11

3.4.1.	Operational Software Development	12

3.4.2.	Software Standards	12

3.4.3.	Software Development Plan	12

3.4.4.	Reserved	13

3.4.5.	Interface Requirements Specification(s)	13

3.4.6.	Software Requirements Specification(s)	13

3.4.7.	Interface Design Document(s)	13

3.4.8.	Software Design Document(s)	13

3.4.9.	Software Product Specification(s)	13

3.4.10.	Version Description Document(s)	13

3.4.11.	Software Test Plan(s)	14

3.4.12.	Software Test Description(s)	14

3.4.13.	Software Test Report(s)	14

3.4.14.	Software Accomplishment Summary	14

3.5.	Communications Engineering	14

3.5.1.	Terrestrial Communications Subsystem	14

3.5.2.	WTMS Terrestrial Communications Network	15

3.5.3.	WAAS Geostationary Communications Control Segment	15

3.6.	System Safety Program	15

3.6.1.	System Safety Program Plan	16

3.6.2.	System Safety Manager	16

3.6.3.	System Safety Working Group	16

3.6.4.	Hazard Tracking	17

3.6.5.	System Safety Program Progress Report	17

3.6.6.	Safety Analyses	18

3.6.7.	Test and Evaluation Safety	18

3.6.8.	Safety Review of Engineering Change Proposals, Specification Change Notices, Requests for Deviation/Waiver	19

3.6.9.	Safety Verification	19

3.6.10.	Software Program Safety Interface	19

3.6.11.	System Safety Architecture	19

3.7.	Human Engineering	19

3.7.1.	HE Program Planning	20

3.7.2.	HE Studies and Analyses	20

3.7.3.	HE Design Support	20

3.7.4.	HE Test and Evaluation	21

3.7.5.	WAAS HE Action Item List	21

3.7.6.	Human Factors Working Group	21

3.7.7.	WAAS Users Group	22

3.7.8.	HE Reviews	22

3.8.	Reliability and Maintainability	23

3.8.1.	Reliability and Maintainability Program	23

3.8.2.	Reliability and Maintainability Reports	24

3.9.	Reserved	24

3.10.	System Test and Evaluation	24

3.10.1.	Test and Evaluation Management	24

3.10.2.	Master Integration and Test Plan	24

3.10.3        Production Acceptance Test and Evaluation Plan	25

3.10.4        Test Procedures	25

3.10.5        Test Reports	25

3.10.6        Test Conduct	26

3.10.7        General Test Ground Rules	26

3.11.	Configuration Management	28

3.11.1.	Configuration Management Program	28

3.11.2.	Configuration Management Plan	28

3.11.3.	Configuration Identification	28

3.11.4.	Configuration Control	29

3.11.5.	Configuration Status Accounting	29

3.11.6.	Data Management	29

3.11.7.	Configuration Audits	29

3.11.8.	Interface Requirements/Control	30

3.11.9.	Retrofit Requirements	30

3.12.	Quality Control	30

3.12.1.	Quality System Plan	30

4.	National Airspace Integrated Logistics Support	30

4.1.	Contractor NAILS Program Management Responsibilities	30

4.1.1.	Planned FULL LPV PERFORMANCE Improvements	31

4.1.2.	Contractor Control	31

4.1.3.	Maintenance Planning	34

4.1.4.	Interim Contractor Depot Logistics Support	34

4.1.5.	Support Equipment	39

4.1.6.	Training, Training Support, and Personnel Skills	40

4.1.7.	Provisioning	41

4.1.8.	Site Spares	42

4.1.9.	Packaging, Handling, Storage And Transportation (PHS&T)	43

4.1.10.	Technical Data	43

5.	Site Implementation	44

5.1.	Site Surveys	45

5.1.1.	Reserved	45

5.1.2.	Materiel	45

5.1.3.	Power	46

5.2.	Implementation Planning	46

5.3.	Site Preparation	47

5.4.	Equipment Installation	47

5.5.	As-Built Drawings	47

5.6.	WAAS Disestablishment	47

6.	Government-Furnished Equipment	47

6.1.	Communications System	47

6.2.	Equipment and Support Space	48

6.2.1.	Equipment Space	48

6.2.2.	Support Space	48

6.3.	Environmental Control	48

6.4.	Electrical Power and Termination	48

6.5.	Ground Termination	48

6.6.	Documents	48

6.7.	Physical Security	49

6.7.1.	Points-of-Contact	49

6.8.	Telephones	49

6.9.	Ground Monuments	49

7.	Second Level Engineering Support	49

7.1.	Field Support	50

7.1.1.	Reserved	50

7.1.2.	Contract Award to FULL LPV PERFORMANCE	50

7.1.3.	On-Call and Onsite Support	50

7.2.	Performance Monitoring	51

7.2.1.	Monitoring and Reporting	51

7.2.2.	Monitored Performance Parameters	51

7.3.	Anomaly Investigation	52

7.4.	SLES Transition Support	52

7.4.1.	Contract Award to Full LPV Performance	52

7.4.2.	Asset Transfer to AOS	52

8.	Operational Baseline Management	53

8.1.	Scope Analysis	53

8.1.1.	Problem Re-Validation	53

8.1.2.	Impact Assessment	53

8.1.3.	Risk Assessment	53

8.1.4.	Alternatives/Options	54

8.1.5.	Initial Test Approach	54

8.1.6.	Implementation Estimate	54

8.1.7.	Scope Analysis Report	54

8.1.8.	WCRB – Initial Approval Support	54

8.2.	Detailed Design	55

8.3.	Operational Baseline Change Delivery	56

8.4.	Implementation Report	56

9.	Acronyms	58

# Scope

This Statement of Work (SOW) defines the requirements for the program management, engineering management, engineering development, production, test and evaluation, cutover of Full Lateral Precision with Vertical Guidance (LPV) Performance to the operational Wide Area Augmentation System (WAAS).  This SOW also includes provisions for the Contractor to provide Second Level Engineering Support (SLES) for the existing WAAS Initial Operational Capability (IOC) for the duration of the Full LPV Performance contract.

The Contractor must provide Full LPV Performance modifications and upgrades to the currently fielded and operational IOC WAAS as directed by the FAA, which will increase the coverage, continuity and availability of the WAAS over CONUS and Alaska. The Contractor must also provide SLES and system problem resolution as directed by the FAA and defined in this SOW during the period of Full LPV Performance capability development and cutover to the operational WAAS. The Contractor must ensure the WAAS meets the specific functional and performance requirements of the WAAS Specification, FAA-E-2892Bch2 as modified by the WAAS Procurement Specification Preplanned Product Improvements for Full Operational Capability, FAA-E-2976, dated March 18, 2004.  FAA-E-2976 is a delta specification that specifically addresses the requirements for the changes being implemented under the Full LPV Performance program. For requirements that are unchanged by the Full LPV Performance efforts, FAA-E-2892Bch2 will remain in effect.  For the remainder of this SOW the term “Full LPV Performance Specification" will be used to denote the combination of the FAA-E-2892Bch2 IOC and the FAA-E-2976 specifications.  Not all Full LPV Performance requirements changes must be unilaterally applied to existing WAAS installations.  The need to retrofit the Full LPV Performance changes into existing installations will be made by the FAA on a case-by-case basis.  The Contractor must provide the WAAS to the FAA in accordance with the requirements cited in this SOW.

The Contractor must implement upgrades to the IOC WAAS that meet FAA Full LPV Performance navigation requirements for domestic en route, non-precision approach, and precision approach phases of flight.  The Contractor must utilize the National Airspace System (NAS) Inter-facility Communications System (NICS) and other GFS communications capabilities to provide ground-ground communications between the various Contractor-provided Hardware Configurations Items.

The Contractor must provide, as a minimum, the following for the WAAS:

- System analysis and design using software, firmware, communications media, and Non-Developmental Item (NDI) hardware (referred to as equipment hereafter),

- Hardware and software as required to meet the requirements described in the WAAS Full LPV Performance Specification,

- Logistics support,

- System analysis and problem resolution of hardware, software and system issues and anomalies arising from the operation of WAAS,

- Technical and management support to the WAAS Change Review Board (WCRB).

The Contractor must provide equipment, personnel, and related services in support of the WAAS in the following areas:

- Project management,

- Full LPV Performance System engineering and system design,

- Full LPV Performance Software development,

- System development and installation in compliance with applicable Federal Regulations, including site surveys, site preparation, equipment installation, quality assurance, testing, and cutover support,

- Configuration management,

- Technical services required to support SLES and Full LPV Performance,

- Software development and integration services for the integration of Ground Communication and Control (GCCS) services with WAAS,

- Logistics support,

- Support services including contingency planning and support, conference attendance, and technical assistance.

## Applicable Documents

All specifications and standards are as of the issue date of this contract, unless mutually agreed otherwise.  Documents are applicable to the extent specified in Sections 2.0 through 8.0 of this Statement of Work.

## FAA Specifications

| FAA-E-2892Bch2 | WAAS Functional and Performance Specification |
| --- | --- |
| FAA-E-2976 | Wide Area Augmentation System Procurement Specification Preplanned Product Improvements for Full Operational Capability |
| FAA-G-1375C | Spare Parts-Peculiar for Electronic, Electrical and Mechanical Equipment |
| FAA-G-2100G | Electronic Equipment, General Requirements |

## Military Specifications

| MIL-DTL-31000B | Technical Data Packages, General Specification for |
| --- | --- |

## FAA Standards

| FAA-STD-005D | Preparation of Specification Documents |
| --- | --- |
| FAA-STD-019B | Lightning Protection, Grounding, Bonding, and Shielding Requirements for Facilities |
| FAA-STD-020B | Transient Protection, Grounding, Bonding, and Shielding Requirements for Equipment |
| FAA-STD-021A | Configuration Management |
| FAA-STD-025C | Preparation of Interface Control Documentation |
| FAA-STD-026A | NAS Software Development, June 1, 2001 |
| FAAD-STD-1293C | Servicing Standards and Test Requirements for Ground Electronic Equipment |

## Military Standards

| MIL-STD-129L | Marking for Shipment and Storage |
| --- | --- |
| MIL-STD-470B | Maintainability Program Requirements. (For Systems and Equipment) |
| MIL-STD-781D | Reliability, Design Qualification, and Production Acceptance Tests |
| MIL-STD-785B | Reliability Program for Systems and Equipment Development and Production |
| MIL-STD-881B | Work Breakdown Structures for Defense Material Items |
| MIL-STD-882C | System Safety Program Requirements |
| MIL-STD-973 | Configuration Management |
| MIL-STD-1390D | Level of Repair Analysis (LORA) |
| MIL-STD-1629A | Procedures for Performing a Failure Mode, Effects and Critically Analysis. |
| MIL-STD-2073-1B | DoD Material Procedures for Development and Application of Packaging Requirements |
| MIL-PRF-49506 | Performance Specification: Logistics Management Information |
| MIL-HDBK-46855 | Human Engineering Requirements for Military Systems, Equipment and Facilities |

## Federal Standards

| FED-STD-005D | Standard Guides for Preparation of Proposed Item Logistics Data Records |
| --- | --- |

## Other FAA Documents

| FAA Order 1370.82 | Information Systems Security Program June 9, 2000 |
| --- | --- |
| FAA Order 1800.58A | National Airspace Integrated Logistics Support Policy |
| FAA Order 4650.30 | Vendor Shipments of Nationally Furnished Project Material (In FAA Order 4650.30, reference made to DD Form 250 is changed to read FAA Form 256) |
| FAA Order 6950.2C | Electrical Power Policy Implementation at National Airspace System Facilities |
| FAA Order 6950.15B | Air Route Traffic Control Complex (ARTCC) Critical Load Circuits and Configuration |
| FAA Order 6000.30C | Policy for Maintenance of the National Airspace System |
| FAA Order 6030.45 | Facility Reference Data File (FRDF) |
| FAA Order 6650.9 | Requirements for Area Control Facility (ACF) Under the Floor Cabling |
| FAA AC 25.1309-1A | Subject: “System Design and Analysis” |
| DI-AFZ500-2003-005 | Asset Identification Contract Data Requirements List and Data Item Description (CDRL/DID) |
| DID-FAA-QA-003 | Quality System Plan (QSP) |
| DID-FAA-026-023 | Software Quality Assurance Plan (SQAP) |

## Other Documents

| MIL-HDBK-217 | Reliability Prediction of Electronic Equipment |
| --- | --- |
| MIL-HDBK-781 | Reliability Test Methods, Plans, and Environments for Engineering Development, Qualifications and Production |
| ANSI-STD-X3.159-1989 | C Programming Language |
| RTCA/DO-178B | Software Considerations in Airborne Systems and Equipment Certification |
| DoD Manual 4100.38M | DoD Provisioning and Other Preprocurement Screening Manual |
| Title 49, Section 172 | Code of Federal Regulations FAA Acquisition Management System dated April 1, 1996 |
| ARP 4754 ARP 4761 | Aeronautical Recommended Practices (ARPs) |
| ANSI/ISO/ASQ Q9001 2000 | Quality Management System - Requirements, Dec. 13, 2000 |

# Contract Execution

## Full LPV Performance Delivery

The WAAS System must have an architecture and performance upgrade which must consist of multiple phases of hardware and software enhancements.  The phases ensure WAAS continuous service throughout the upgrade to Full LPV Performance.  The Contractor is encouraged to propose hardware, software, and GFE communications system changes to integrate additional functional capabilities as necessary to sustain continuous service during the cutover.   The Contractor must ensure that all changes to the WAAS product baseline adhere to the processes described in SOW Section 8.0, Operational Baseline Management.

### Architecture Upgrade

The Architecture Upgrade is intended to focus primarily on increasing system capacity to support additional Wide-area Reference Stations (WRSs), a Wide-area Master Station (WMS), integration of a third and fourth GEO, and anticipated processing needs for software necessary to achieve Full LPV Performance requirements defined in the Full LPV Performance Specification.  However, when appropriate, the Contractor must propose hardware & software changes that also improve continuity, availability, coverage, and supportability at the earliest opportunity feasible.  As a minimum, the Contractor must upgrade the existing WAAS architecture to include the following:

- System engineering, hardware, software, and GFE communications changes necessary to host additional WRSs and WMSs per the requirements of the Full LPV Performance specification.

- System engineering, hardware, software, and GFE communications changes necessary to integrate up to 2 additional WAAS GEOs provided as part of the GCCS Contract DTFA01-03-C-00059.

- System engineering, hardware, software, and GFE communications changes necessary to install and integrate the additional WRSs being added to the WAAS system as part of the Full LPV Performance effort.  The Contractor must propose WRSs locations at FAA-approved locations based on maximum contribution to overall system performance.

### Full LPV Performance Delivery

The Contractor must complete all system engineering, hardware, software, and communications changes necessary to achieve all Full LPV Performance requirements specified in the Full LPV Performance Specification.

# Requirements

The Contractor must perform the effort described in this SOW and must comply with all the requirements set forth herein.  The Contractor must adhere to all plans developed in response to this SOW, when approved by the FAA.  The Contractor must deliver the data described in this SOW in accordance with the schedule and other requirements specified in the Contract Data Requirements List (CDRL).  The applicable CDRLs have been identified in parentheses at the end of the corresponding SOW paragraph and are detailed in Attachment C.

Unless otherwise specified in the following sections, the agenda for meetings (SEWG, WIPP, POM, NAILS, SLES, and ICDLS) must be provided to the Government for approval no later than 15 days prior to the start of the meeting and the minutes for meetings must be provided to the Government for approval no later than 14 days after the completion of the meeting.  The Government will respond to the Contractor with comments and/or approval for the submitted agenda within 5 days after receipt and within 30 days for the delivered meeting minutes.   The Contractor must incorporate comments and resubmit no later than 3 days after receipt of meeting agenda comments and no later than 15 days after receipt of meeting minute comments.  Contractor format for meeting agendas and meeting minutes is acceptable.

All PNBs identified in this SOW must be delivered in Contractor format, unless otherwise specified.   For PNBs requiring Government approval, the Contracting Officer will provide one consolidated set of comments to the Contractor, via email, and post the comments on the shared file server within 30 days of PNB receipt. The Contractor must incorporate comments and resubmit no later than 15 days after receipt. The Contracting Officer will respond, via email, within 15 days after receipt.

## Program Management

The Contractor must manage the effort described in this SOW.  A single Program Manager must be assigned the responsibility for control and coordination of all work performed under the WAAS contract.  The Program Manager must have sufficient experience and authority to ensure efficient and timely program execution and must be the single focal point within the Contractor's activity for all required program tasks performed under the contract.

### Program Management

#### Program Management Plan

The Contractor must update the existing Program Management Plan, as required, to identify the Contractor’s organization and procedures for administering the WAAS program.  These procedures must include (but not be limited to) monitoring program performance (cost, schedule and technical), contract administration, subcontract management, and integrated product teams.  (CDRL A001)

#### Contractor Work Breakdown Structure (CWBS)

The Contractor must establish and maintain a CWBS and dictionary in compliance with MIL-STD-881.  The summary CWBS must provide the basis for any further extension by the Contractor to lower levels during the performance of the contract.  The dictionary must include references to Contract Line Item Number (CLIN), Responsible Organization and Performing Organization, including any subcontractors’ performing work.  (CDRL A002)

#### Schedule Management

The Contractor must establish a single WAAS Master Integrated Network Program Schedule based on a logical and efficient sequence of events designed to accomplish the effort described in this contract.  The Contractor must develop and submit the Master Integrated Program Schedule (MIPS) using Primavera Project Planner for Windows, Version 1.1 or later.  The Contractor must comply with the following schedule requirements:

- Task IDs must be traceable to the CWBS.  Tasks that represent CDRL deliveries must use the CDRL number as the task identifier.

- Task names except Major Program Milestones must begin with a verb.  Task names must be specific enough to stand-alone and be understood apart from their Work Breakdown Structure (WBS) number by non-technical personnel.

- The MIPS file (CDRL A003) and subsequent Monthly Schedule Status Report (CDRL A004) must be electronically coded to enable the Contractor to provide Master, Intermediate, and Detail Level schedules.

- The Master Level Schedule must depict all Contractor Major Program Milestones.

- The Intermediate Level Schedule must depict work at the 4th level of the WBS.

- The Detail Level Schedule must depict all activities in the Master Integrated Program Schedule (MIPS) file.

- The Contractor must include an activity dictionary within the Log field for each activity in the MIPS and subsequent Monthly Updates.  Task definitions in this Log field must fully define the work to be performed.  In addition, the Contractor must include an acronym list with each delivery of the MIPS and Monthly Update.

- Schedule tasks, which depict work such as Level of Effort (LOE) longer than 5 months, subcontractor deliverables [i.e., Subcontract Data Requirements List (SDRL)], or tasks used simply as “placeholders” for financial traceability must not be included in the MIPS submission or subsequent Monthly Schedule Status Report Updates (CDRL A004).  Significant work performed by subcontractors must be included in the MIPS and Monthly Schedule Status Report Updates.  Significant work is defined as any work other than work to develop or deliver SDRLs or perform LOE work as defined above.  Subcontractor work must be logically integrated into prime Contractor work in all cases.  (CDRL A003) (CDRL A004)

- The Contractor must use a 5 working day calendar, unless otherwise specified, with both Contractor-specific holidays and government holidays as the only calendar for the MIPS.  The Contractor must provide the Contractor specific holidays to the FAA with the first submission of CDRL A003.  The FAA will recognize the standard published federal holidays.

- The Contractor must base any schedule submitted as a part of any other CDRL, plan, or technical document on the Master Integrated Program Schedule (MIPS) and subsequent Monthly Schedule Status Report Updates.  The Contractor’s Program Manager or designee must sign all schedules submitted in such documents, whether formal or informally delivered.  If a schedule submitted in a document as described above is at a more detailed level than is in the MIPS, the detailed activity must clearly track back (i.e., via a key) to its higher level MIPS activity ID.  The Contractor must include “Best guess work-around plans” for activities identified in Risk Abatement Plans in the Monthly Schedule Status Report (MSSR). (CDRL A004).

#### Cost Management

The Contractor must establish, maintain and use internal cost management control systems and provide the FAA with timely and auditable data on a monthly basis that determine product-oriented contract status. (CDRL A008)

#### Cost Management Reporting

The Contractor must use the Cost Performance Report (CPR).  The monthly reports of CPR data -- Budgeted Cost of Work Scheduled, Budgeted Cost of Work Performed, Actual Cost of Work Performed, Cost and Schedule Variances, for the current and cumulative to date work periods –   must be provided to at least WBS level 3 of the Contractor Work Breakdown Structure (CWBS), or to a lower level if deemed appropriate.  The FAA reserves the right to require reporting to a lower level of detail, down to the Work Package level.  (CDRL A008)

#### Earned Value Management

The Contractor must perform continuous contract management and contract performance assessment, in accordance with AMS clause 1.13-2, and the Earned Value Management Implementation Guide (DCMA), latest revision.  The Contractor must be diligent in addressing cost and schedule variances and provide specific information in their Cost Performance Report (CPR) regarding the disposition, overall impact, and plans of action (with projected dates of implementation) as part of the CPR.  The budgets agreed upon in the contract must reflect integration of schedule and cost projections. For the determination of earned value, as much work as possible must be defined in discrete Work Packages with well-defined products and milestones.  The Contractor’s use of Level-of-effort Work Packages must be minimized.  Work Packages are required to represent natural, logical subsets of the work described in the CWBS.

#### Technical Program Management

The Contractor must establish a Technical Program Metric (TPM) Program integrated with all other System Engineering and Risk Management activities as called out in this SOW.

##### Technical Program Metrics Status Report

The Contractor must post the monthly Technical Program Metrics (TPM) Status Report on the tenth of every month in PowerPoint format to the shared file server and inform the FAA via email.   The Contractor must describe each parameter being tracked and summarize the performance achievement along with current trends and discrepancies of actual versus expected performance in the TPM Status Report.  The Contractor must prepare and submit the TPM Status Report in Contractor format for review and approval.

##### Software Management Indicators

The Contractor must track and report on the following software management indicators for all operational Computer Software Configuration Items (CSCIs): software requirements stability, software size, computer resource utilization, software manpower, incremental software releases and software problem reports.  The Contractor must also track and report on management indicators for the test and support software on the following topics: software problem reports, and software size.  The tracking and reporting of the software management indicators must be performed via the Technical Program Metric (TPM) Status Report.

#### Risk Management

The Contractor must conduct risk management activities.  The Contractor must give full consideration to all factors, which could limit technical, schedule, cost, or operational performance of the program.  Risk management activities must identify "low," "moderate," and "high" risk items, track program performance on risk items, and implement risk abatement procedures as needed.  The risk assessment and abatement program tracking, evaluation, and direction must be an integral part of the Contractor 's system engineering and engineering management processes.

#### Contract Data Management

The Contractor must deliver all CDRLs, Correspondence, and other documentation in softcopy in Microsoft Office 2000 format, or other approved softcopy format, using agreed to communications media.

### Program Overview Meetings (POM)

The Contractor must conduct quarterly Program Overview Meetings (POMs) at the Fullerton facility unless otherwise directed by the Contracting Officer’s Technical Representative (COTR), to provide status on all program management activities.  The COTR may require monthly POMs if there are program (technical, schedule, or cost) issues that require increased FAA attention.  The Contractor must prepare and submit an agenda and meeting minutes IAW Section 3 of this SOW.

## Systems Engineering Management

The Contractor must establish, implement, and maintain a Systems Engineering Management Program.  The Contractor must submit and update as necessary a Systems Engineering Management Plan (SEMP) and a Metric Plan, which describe the Contractor's systems engineering organization, responsibilities, methodology and procedures for system engineering, technical planning and control, and systems integration.  The Contractor must ensure the SEMP provides an overall discussion of how change impact analysis will be accomplished for the WAAS and its constituent components (e.g., hardware, and software).  The Contractor must ensure this change impact analysis considers, at a minimum: effects on safety (including effects on integrity, availability, and continuity), effects on procedures, effects on system resources (e.g., throughput), and amount of reverification needed.  (CDRL A013) The Metric Plan may be prepared as a Program Notebook (PNB) and must be updated and delivered concurrent with the SEMP.

### Interface Design

The Contractor must update existing interface control documents (ICDs) as required for each change to the product baseline.    (CDRL A052)

The Contractor must also develop and deliver an ICD that defines functional and performance interface requirements between the Signal Generation Subsystem (SGS) and the WMS and WRS.  The ICD must be updated and delivered, as required, to incorporate changes introduced by Full LPV Performance development.  (CDRL A144)

### System Engineering Analyses

The Contractor must perform and submit the analyses and trade studies to determine the optimum allocation and apportionment of the requirements contained in the Full LPV Performance Specification to individual hardware and software configuration items (CIs).  The Contractor must perform the analysis, prototyping, modeling, etc. as required substantiating the rationale for all hardware, software, and GFE Subsystems selected for use in the system to meet the performance requirements. (CDRL A014)

#### Service Volume Model (SVM)

The Contractor must update and maintain the existing SVM, as required, to analyze and document availability and coverage performance for En Route, LNAV, LNAV/VNAV, and Lateral Precision with Vertical guidance (LPV) performance levels.  The Contractor must document the SVM algorithms and software requirements changes and present the results of the SVM model at the WIPP/SEWG.  The Contractor must present the results of the SVM Model to the WIPP and SEWG.

#### Probabilistic Continuity Analysis

The Contractor must provide WAAS performance data in Contractor format to the FAA on an as required basis for the purpose of verifying the allocation values used by the FAA models of WAAS continuity performance.  The first set of WAAS performance data must be submitted the first of the month following Full LPV Performance contract modification.

### System Engineering Working Group (SEWG)

The Contractor must continue the established System Engineering Working Group (SEWG) to provide a forum for technical review and resolution of all system development, improvement, and second level engineering support activities.  The SEWG will be co-chaired by the Contractor and a FAA WAAS representative.  The WAAS Integrity Performance Panel (WIPP) is a subgroup of the SEWG used to resolve issues associated with integrity, continuity, availability, safety, and performance.  The Contractor must prepare and submit an agenda and meeting minutes IAW Section 3 of this SOW.

## Hardware Engineering

Only hardware, needed to satisfy the requirements for the Full LPV Performance Specification must be procured.  The Contractor must provide hardware engineering to support the regression tests of the Common Reference Receiver (CRR). Specifically, test and debug and changes required during the Contractor integration and test of the receiver for the Alaska WRS racks.

## Software Engineering

The Contractor must design and develop upgrades to the WAAS software in accordance with FAA-STD-026A and RTCA/DO-178B, and meet the requirements of the Full LPV Performance Specification.  The Contractor must ensure the software life-cycle process used is compliant with RTCA/DO-178B for the software safety levels assigned to each CSCI.

The Contractor must provide support for software and test of the Common Reference Receiver (CRR). The Contractor must provide support to software and test efforts that arise from February to April 2004. Two specific tasks required to support hardware updates:

- Updates must be required to the boot code and firmware load to support the new SDRAM

- The Multipath Estimation Delay Lock Loop (MEDLL) reference functions will need to be re-measured on the new hardware to ensure optimal performance with the new RF deck design.

In addition, the Contractor must correct two minor issues found with the CRRs:

- Track all satellite ranges regardless of Almanac Health bit status

- Fix RX Commands log to indicate whether Binary or ASCII logs were requested by the user

### Operational Software Development

WAAS operational software and firmware must consist of all software, firmware and commercial off the shelf/non-developmental software (COTS/NDS) executed within the WAAS.  The Contractor must code all WAAS operational software developed under this contract in C.  The Contractor must obtain FAA approval for use of any language other than C.  Existing software used to monitor and control the GEO satellites is excluded provided that WAAS performance requirements in the Full LPV Performance Specification can be met and the hazard analysis shows there is no unacceptable safety hazards associated with the software.  The Contractor must ensure that embedded or existing COTS/NDS software, including complex logic devices (programmable logic arrays or equivalent), meet the objectives of RTCA/DO-178B for the software safety levels assigned to each CSCI.  The Contractor must secure all rights, including licenses and auditing of intellectual property, required for the Contractor and the FAA to verify compliance with RTCA/DO-178B objectives for the assigned software safety level for all COTS/NDS included in the WAAS.

### Software Standards

The Contractor must perform the planning, system requirements analysis, system engineering analysis, system design, system safety assessment, software safety assessment, requirements allocation, software design, software coding, software test, software integration, system integration and testing, configuration management, and documentation in accordance with FAA-STD-026A as tailored by this SOW.    The Contractor must comply with ANSI-STD-X3.159-1989 for computer languages.  The Contractor must use best commercial practices for hardware firmware.

#### Reserved

### Software Development Plan

The Contractor must update the Software Development Plan (SDP) as required.  The Contractor must comply with the SDP as required in FAA-STD-026A.  This plan governs all software development, software safety engineering, and human factors engineering activities necessary to support all development, which includes but is not limited to: micro-controller instructions, prototype software usage, COTS/NDS, and test and support software.  The Contractor must include processes to support informal peer reviews of documentation, algorithm development and prototyping activities by FAA personnel on an incremental basis in the SDP.  The Contractor must ensure the software safety level assigned to each CSCI in the SDP meets the objectives of RTCA/DO-178B.  The Contractor must include a section in the SDP describing a Plan for Software Aspects of Certification in accordance with RTCA/DO-178B, paragraph 11.1.  The Contractor must ensure the software configuration management section of the SDP meets the requirements of RTCA/DO-178B paragraph 11.4.  (CDRL A017)

### Reserved

### Interface Requirements Specification(s)

The Contractor must update as required the Interface Requirements Specification(s) (IRS) as prescribed in FAA-STD-026A for each change of the product baseline.  The Contractor must ensure IRS(s) meet the objectives in RTCA/DO-178B for the software safety level assigned to each CSCI.  (CDRL A019)

### Software Requirements Specification(s)

The Contractor must update as required the Software Requirements Specification(s) (SRS) as prescribed in FAA-STD-026A for each change of the product baseline.  The Contractor must ensure SRS(s) meet the objectives in RTCA/DO-178B for the software safety level assigned to each CSCI.  (CDRL A043)

### Interface Design Document(s)

The Contractor must update as required the Interface Design Document(s) (IDD) as prescribed in FAA-STD-026A for each change of the product baseline.  The Contractor must ensure IDD(s) meet the objectives in RTCA/DO-178B for the software safety level assigned to each CSCI.  (CDRL A020)

### Software Design Document(s)

The Contractor must update, as required, the Software Design Document(s) (SDD) as prescribed in FAA-STD-026A as an appendix to the Software Product Specification (SPS) in accordance with the approved Plan for Software Aspects for Certification (PSAC).   The Contractor must ensure SDD(s) meet the objectives in RTCA/DO-178B for the software safety level assigned to each CSCI. (CDRL A022)

### Software Product Specification(s)

The Contractor must update the Software Product Specification(s) (SPS) as prescribed in FAA-STD-026A for each change of the product software baseline in accordance with the approved PSAC.  (CDRL A022)

### Version Description Document(s)

The Contractor must update as required the Version Description Document(s) (VDD) as prescribed in FAA-STD-026A and FAA-STD-021A, Appendix XII for each change of the product baseline in accordance with the approved PSAC.  (CDRL A023)

### Software Test Plan(s)

The Contractor must include the software testing approach in the Software Development Plan (A017).  The Contractor must satisfy the requirements for a Software Verification Plan in accordance with RTCA/DO-178B for the software safety level assigned to each CSCI and must be consistent with the Master Integrated Test Plan (MITP)(CDRL A143).

### Software Test Description(s)

The Contractor must prepare or update software test descriptions as part of the Implementation Report (A142) for each applicable change to the product baseline.  The Contractor must ensure the software test descriptions satisfy the requirements for Software Verification Cases and Procedures in accordance with RTCA/DO-178B for the software safety level assigned to each CSCI.   The Contractor must deliver test descriptions to the FAA in accordance with Section 8.0 of this SOW.

### Software Test Report(s)

The Contractor must prepare software test reports as part of the Implementation Report (A142) for each applicable change to the product baseline.  The software test reports must satisfy the requirements for Software Verification Results in accordance with RTCA/DO-178B for the software safety level assigned to each CSCI.  The Contractor must deliver test reports to the FAA in accordance with Section 8.0 of this SOW.

### Software Accomplishment Summary

The Contractor must prepare and submit a Software Accomplishment Summary (SAS) as a PNB IAW the approved PSAC and Section 8.0 of this SOW.  The SAS will be evaluated and approved as part of the DO-178B audit process for each proposed change to the operational baseline.

## Communications Engineering

The Contractor must ensure the WAAS and WTMS communications systems support the transmission of data required to meet the Full LPV Performance Specification requirements.  The Contractor’s requests for GFE circuits must take into account the lead-time necessary to establish the service.

### Terrestrial Communications Subsystem

The Contractor must implement the WAAS Terrestrial Communications Network using the NAS Interfacility Communication System (NICS), and equivalent capabilities outside the United States (US), which will be provided as GFE.  The Contractor must design and integrate improvements into the Terrestrial Communications Network while meeting the overall system requirements specified in the Full LPV Performance Specification.    The Contractor must treat the Terrestrial Communications Network as a subsystem of the WAAS even though the Contractor is provided communication links as GFE.  The Contractor must update the existing WAAS Terrestrial Network Design Document. (CDRL A126)

### WTMS Terrestrial Communications Network

The WTMS Terrestrial Communications Network must include sufficient network connections and equipment required to simulate the operation of the WAAS as necessary to support training of WAAS operators and maintainers.

### WAAS Geostationary Communications Control Segment

All GEO satellites and associated subsystems will be provided to the Contractor as GFE.

#### WAAS/GCCS Integration

When any GCCS is provided as GFE, the Contractor must integrate the GCCS service into the WAAS while meeting the overall system requirements specified in the Full LPV Performance Specification.  Each GCCS is to be treated as a subsystem of the WAAS even though the Contractor is provided the subsystem as GFE.

## System Safety Program

The Contractor must maintain and update a System Safety Program (SSP) that provides assurance that architectural, performance and maintenance changes introduced into the WAAS do not result in a degradation in the WAAS Safety performance achieved in the Lateral Navigation (LNAV)/Vertical Navigation (VNAV) Phase.  The Contractor must ensure the activities defined in the SSP satisfy the requirements of this SOW and the FAA-developed Safety Assurance Process Requirements (SAPR), as specified in Attachment P of the contract.  The SAPR, based on Society of Automotive Engineering (SAE) Aeronautical Recommended Practices (ARPs) 4754 and 4761, together with hazard identification and analysis, risk assessment and tracking based on MIL-STD-882C, provides an acceptable approach to assuring the WAAS design.  The Contractor must ensure the SSP addresses hazards presented to the user as well as ground operations and maintenance safety.  Control of hazardous conditions is either elimination of the hazard or reducing the safety risk to acceptable levels as defined in the Contractor’s System Safety Program Plan (SSPP).  The Contractor must ensure the SSP addresses identification of impacts to the safety assurance (SA) baseline that were established during the LNAV/VNAV Phase.  The Contractor must ensure the SSP includes the identification of all artifacts in the Safety Assurance Configuration Item List (SACIL) (CDRL A014) that require an update based on WAAS changes to the operational product baseline.  The Contractor must notify the FAA when artifact updates are available for review.

The Contractor must ensure the SSP complies with the safety requirements specified in the Full LPV Performance Specification.

The Contractor must ensure the WAAS safety requirements and associated analyses consider the combined effects of hazards associated with hardware failures, software (including COTS/NDI) faults, algorithm trips, integrated system faults and/or failures, operator and/or maintainer procedures, and the WAAS operating environment.

The Contractor must identify an independent single point of contact in the SSPP to serve as the primary safety interface with the FAA.  The Contractor must consider all contract activities and all safety significant subcontracted efforts in the SSP.

### System Safety Program Plan

The Contractor must update the existing System Safety Program Plan.  The Contractor must include in the SSPP as a minimum:

- A description of an integrated program covering the hardware, software, and firmware.

- A description of the Contractor’s proposed safety organization and its relationship to the overall systems engineering process,

- A description of the hazard identification process proposed for both planned upgrades to the system and operation and test anomaly review,

- A comprehensive approach for WAAS design safety assurance in accordance with the SAPR,

- A description of the contents of the Safety CDRLs, and

- A proposed Hazard Tracking System (HTS) capable of distinguishing hazards identified by program phase and build.  The Contractor must maintain a HTS using Microsoft Access and contain the applicable existing LNAV/VNAV and Final Operating Capability ( Full LPV Performance) data.       (CDRL A062)

### System Safety Manager

The Contractor must task a single individual, the System Safety Manager (SSM), with the responsibility for the WAAS System Safety Program.  The SSM must be independent of the WAAS Technical Director.  This individual must be delegated responsibility for meeting the SSP and technical requirements.  The SSM’s responsibility must cover system and software design and analysis, equipment acquisition, and subcontractor SSP activities.  The Contractor must ensure the SSPP identifies the SSM and includes a summary of that individual’s system safety credentials and position in the WAAS Program and functional organization.

### System Safety Working Group

The Contractor must establish a System Safety Working Group (SSWG) composed of, as a minimum, safety representatives from the Contractor, appropriate subcontractors and the FAA.  The SSWG’s charter must address all safety assurance related issues. This includes issues involving hazards and those pertaining to safety analyses being conducted as part of the WAAS safety assessment.  The SSWG will meet, in conjunction with, System Engineering Working Group (SEWG) meetings or as directed by the FAA.  In addition, discussions will take place as required to discuss the disposition of hazards that the Contractor has recommended for closure.  The SSWG must be co-chaired by the SSM and a FAA WAAS representative.  Recommendations for system changes originated by the SSWG will be accomplished in accordance with Section 8.0 of this SOW.

### Hazard Tracking

The Contractor must maintain a closed loop Hazard Tracking System (HTS) for identification and control of hazards.  The Contractor must maintain the process definition in the SSPP for hazard submission, logging, adjudication, mitigation/control, and closure of hazard records (HRs).  The HTS process definition must include hazard criticality categories, Contractor management approval level authority necessary for each, and procedure for closing out the hazard or assuming the risk. The FAA is the final approval authority for the closing of hazards.

The Contractor must maintain a computerized hazard log containing all identified safety hazards that exceed the criteria established in the SSPP.  The Contractor must use this log to document proposed hazards and track hazards that exceed acceptable risk thresholds until they are either eliminated, controlled to an acceptable level, or the risk is assumed with FAA approval.  The Contractor must include the information in sufficient detail to permit WAAS system competent personnel to understand the nature and status of all included hazards.

The Contractor must use the hazard log as a permanent record of hazard control activity.  The computerized hazard log must include all safety hazard records identified for every delivery of the WAAS, including historical deliveries.  The computerized hazard log must provide the capability to associate hazard records to individual WAAS deliveries to support verification that hazards affecting the delivery have been appropriately controlled and closed or the associated risk has been assumed.

The Contractor must deliver the computerized hazard log to the FAA once per month for the period of the contract.  The delivered hazard log must be a Microsoft Access 2000 developed database. Alternate formats including .rtf report, Microsoft Access Viewer reports, and other database exports are not acceptable.  Delivery must be via posting on an FAA-accessible server or mutually agreed upon method.

### System Safety Program Progress Report

The Contractor must provide a System Safety Program Progress Report (SSPPR) in the format developed over the course of the WAAS LNAV/VNAV Phase. The Contractor must ensure the SSPPR includes newly recognized significant hazards and the source of those hazards (safety assessment activities conducted for planned product upgrades or anomaly/problem reporting of the current product baseline).  The Contractor must ensure the SSPPR identifies significant changes in the degree of control of the risk of known hazards and significant cost and schedule changes that impact the Program. The Contractor must include a Hazard Tracking Log summary in this report. (CDRL A063)

### Safety Analyses

The Contractor must perform the analyses listed in this paragraph to assess safety risk.  The Contractor must account for the combined effects of hazards associated with hardware failures, software (including COTS/NDI) faults, algorithm trips, integrated system faults and/or failures, operator and/or maintainer procedures, and the operating environment in these analyses.  Contribution of operator and/or maintainer procedures to minor hazards such as loss of function (LOF) may be addressed qualitatively.  The Contractor must ensure the risk assessment(s) address all phases of flight supported by WAAS, including oceanic and domestic en route positioning and navigation, terminal, non-precision approach, and precision approach operations.

The Contractor must include GCCS segment analyses generated by the GCCS Contractor, as provided by the FAA, into all appropriate System Safety Analyses

#### System Hazard Analysis

The Contractor must update the System Hazard Analysis (SHA), as required for each update of the product baseline.  The Contractor must ensure the SHA updates account for equipment upgrades and technology refreshment.  The Contractor must ensure the SHA is comprehensive and considers the sources of risk associated with both system integrity and continuity.  Results of those safety analyses conducted IAW the WAAS SAPR, including Fault Tree Analysis (FTA), Failure Modes and Effects Analyses (FMEAs), Failure Modes and Effects Summaries (FMESs), Common Cause Analysis (CCA), Safety Directed Analyses (SDAs), Qualitative Analyses (QAs), Safety Processor Input Analysis (SPIA), and Algorithm Probability of Hazardously Misleading Information (PHMI) Analysis, must be captured in the SHA.  The Contractor must ensure the SHA considers all Subsystem safety analyses (e.g., GCCS). (CDRL A067)

#### System Safety Assessment

The Contractor must maintain the baseline System Safety Assessment for each change to the operational system baseline.   The Contractor must determine the need to update the safety assessment for all other changes to be fielded through the conduct of a change impact analysis according to Section 8.0 of this SOW.  The Contractor must ensure the assessment provides a comprehensive evaluation of the residual risk being assumed prior to these major milestones.  In accomplishing this task, the Contractor must review all completed safety analyses and determine if and where additional system safety verification is required.   A final comprehensive System Safety Assessment must be delivered formally at the completion of the Contract. (CDRL A068)

### Test and Evaluation Safety

The Contractor must follow the requirements outlined in the SAPR for component and system level testing that demonstrates the component, series of integrated components or the system as a whole performs its intended function.  The Contractor must clearly flag safety critical procedures, training, and tasks.  The SSM must specify in the SSPP and appropriate test documentation any safety related information needed to be collected during the test program and provide support for analyzing safety related test data and results.

### Safety Review of Engineering Change Proposals, Specification Change Notices, Requests for Deviation/Waiver

The Contractor’s SSM must review all Engineering Change Proposals, Specification Change Notices, Software Problem Reports, and Requests for Deviation/Waiver for impact on safety. The SSM must approve all such proposed changes prior to submission to the FAA.

### Safety Verification

The Contractor must perform safety verification in accordance with the SAPR for all safety requirements.

### Software Program Safety Interface

The Contractor must ensure the SSP includes conduct of all safety analysis, hazard identification, and mitigation and verification activities required to support development of software according to the objectives of RTCA/DO-178B.  The Contractor must ensure software system safety, as a major element of the WAAS SSP, is addressed in the SSPP and the Software Development Plan.

### System Safety Architecture

The Contractor must review all changes authorized by the WAAS change process, including but not limited to the Full LPV Performance improvements, to determine all impacts to the WAAS Safety Architecture and Design.  The Contractor must update the WAAS Safety Architecture and Design as needed, according to Section 8.0 of this SOW.  The Contractor must ensure such updates address any necessary changes to the Safety Requirements Trace Matrix.  The Contractor must ensure the description identifies the allocation of System Safety Requirements to the system implementation and provides complete and traceable evidence of the full implementation of the System Safety Requirements and mitigation of identified safety threats.  The Contractor must ensure the description of the Safety Architecture addresses the hazards identified as a result of system hazard analyses and system development activities.  Where system safety is impacted, the Contractor must ensure the description of the safety architecture provides evidence that the mitigations developed for each threat operate as described and that the safety requirements have been met.  (CDRL A069)

## Human Engineering

The Contractor must implement a Human Engineering (HE) Program, in accordance with the guidelines contained in Section 4 of MIL-HDBK-46855.  The Contractor must ensure the HE program consists of planning, analysis, design support, and test and evaluation efforts to assure that the WAAS Full LPV Performance design changes are consistent with the capabilities and limitations of operators and maintainers in their operational environments.

### HE Program Planning

The Contractor must update the HE Program Plan (HEPP) in accordance with the guidelines contained in Section 4.1.2 of MIL-HDBK-46855, describing the activities, tasks, schedule, organization, levels of effort, design concepts, and test and evaluation.   (CDRL A133)

### HE Studies and Analyses

The Contractor must develop and maintain task inventories for WAAS Operators and Maintainers. The elements of those inventories must be subjected to a Criticality Analysis. A critical task is defined as a task: (1) which requires human performance which, if not accomplished in accordance with system requirements, is likely to result in the generation of Hazardously Misleading Information (HMI) or the Loss of Signal-In-Space (SIS); or (2) where equipment design characteristics demand human performance which approaches the limits of Operator or Maintainer capabilities.  The Contractor must further analyze tasks identified as system critical tasks in a Critical Task Analysis (CTA) in accordance with the guidelines contained in Section 4.2.1.3.2 of MIL-HDBK-46855A.  (CDRL A134)

The Contractor must solicit, analyze, and evaluate input from the WAAS Users Group (WUG) (see Section 3.7.7 below) as appropriate in support of studies and analytical efforts.

The Contractor must review the IOC design, evaluate and amalgamate data and information from HE studies and analyses to establish and define WAAS HE Critical Design Considerations (CDCs). A CDC is defined as an aspect or element of the WAAS system (including hardware, software, procedures, personnel, and environment), which will have a significant impact on human performance (and hence system performance) if not properly and adequately designed according to HE standards, guidance, and best practices. Resulting CDCs will be analyzed and described in a Critical Design Consideration Document PNB.  The CDC PNB must be delivered with each Scope Analysis Report (CDRL A140) for Government approval. A formal Critical Design Consideration Document will be delivered at the completion of the Contract.  (CDRL A135)

### HE Design Support

The results of HE guidance (i.e., DOT/FAA/CT-96/01), studies, analyses, test and evaluation, and WUG input must be applied to the Full LPV Performance design of system equipment, software, human-computer interfaces (HCI), and procedures.  Mockup, rapid prototyping, and simulation design evaluation must be employed as appropriate to assess the impact of design details on human performance and user acceptance.  Alternate design evaluations to determine effectiveness, usability, and user acceptance must be conducted as appropriate.

The Contractor must analyze, evaluate and prioritize action items documented on the WAAS HE Action Items List (WHAIL) (see Section 3.7.5). The Contractor must develop corrective actions for action items selected by the Human Factors Working Group (HFWG) (see Section 3.7.6) and those corrective actions, which are approved for implementation, must be validated and implemented.  The Contractor must revalidate and track the implemented corrective actions for long-term effectiveness.

The Contractor must monitor, evaluate and provide recommendations on Full LPV Performance proposed WAAS system design changes. The Contractor must ensure that proposed changes do not negatively impact human performance or negate/counter-act HE enhancements.

### HE Test and Evaluation

The Contractor must conduct a HE Test and Evaluation Program, which meet the following objectives:

- Demonstrates conformance of Full LPV Performance WAAS to the HE criteria established jointly between the Contractor and FAA; and

- Determines whether undesirable (Legal questions use of this word. Can we replace with unintended or unsuitable, or something else???) hardware, software, or procedural features have been introduced.

### WAAS HE Action Item List

Throughout Full LPV Performance, aspects of WAAS (including equipment, software, CHI, and procedures) that may adversely impact human performance (and subsequent system performance) must be identified by the Contractor (as coordinated with the Government) as HE Action Items.  The Contractor must maintain and track the HE Action Items on a WAAS HE Action Item List (WHAIL). Sources of HE Action Items must include (but not be limited to): (1) study and analysis results, (2) recommendations contained in WAAS Human Factors Phase 1 Assessment, dated 14 August 2000, (3) input from the WUG, and (4) other Human Factors Working Group (HFWG) activities.

The Contractor must document and maintain the identified HE Action Items in a tracking system.  The Contractor must ensure the HE Action Item documentation includes, as a minimum:

- A descriptive title;

- A complete description of the issue;

- Potential impacts of the issue if unresolved;

- Planned resolution strategy(ies);

- Implemented resolution solution; and

- Effects of resolution solution.

Contractor format may be used for the tracking system.  Upon Government request, the Contractor must provide access to information maintained in the tracking system.

### Human Factors Working Group

The Contractor must participate in the joint Government-Contractor Human Factors Working Group (HFWG). The Contractor Human Factors principal must co-chair the group, along with the Government Human Factors representative. The HFWG will consist of representatives from the following: Government and Contractor Human Factors personnel, System Engineering personnel, Safety and Training personnel, and, Operator and Maintainer personnel.  The HFWG is subordinate to the SEWG and will coordinate, provide overall direction, and decision-making to the WAAS HE effort.  Recommendations for system changes originated by the HFWG are presented to the WCRB for implementation in accordance with Section 8.0 of this SOW.

### WAAS Users Group

The Contractor must host a WAAS Users Group (WUG) consisting of Operators and Maintainers.  The WUG is chaired by FAA Operators and Maintainers representatives.  The primary purpose of the WUG is to provide a venue for soliciting input from WAAS users.

The WUG will participate, as a minimum, in the following activities:

- Task Inventory development,

- Criticality analysis,

- Critical Task Analysis,

- Critical Design Consideration development,

- WHAIL item identification and corrective item development,

- WHAIL item evaluation and prioritization,

- Prototype and simulation evaluation,

- Alternative design evaluations,

- Usability evaluations,

- Proposed design change evaluation,

### HE Reviews

Contractor HE representatives must participate in all technical and program reviews where human performance is a determinant of system operational and maintenance effectiveness.  In addition, the HE representatives must address the following as a minimum during the HE reviews:

- Principal Human Performance Requirements.  Summarize system operation and maintenance requirements, which depend on human performance. Identify tasks critical to system effectiveness. Review critical tasks in terms of the impact of various operational and environmental conditions on their performance.

- Human Engineering Design.  Present the compliance of items having a human interface with human performance and DOT/FAA/CT-96/01 requirements.

- HE Action Items.  Present and discuss the current content of the WHAIL, along with the status of on-going and implemented design changes

4.	Manpower, Personnel, and Training (MPT) Implications.  Describe MPT implications resulting from planned Full LPV Performance improvements.

## Reliability and Maintainability

### Reliability and Maintainability Program

The Contractor must maintain and update a reliability program in accordance with MIL-STD-785B and a maintainability program in accordance with MIL-STD-470B.  The Contractor must generate a Reliability and Maintainability (R&M) Program Plan by modifying, integrating, and updating as required, the existing Reliability and Maintainability program plans.  The reliability and maintainability programs must be planned, integrated, and executed to support the design, development, and testing efforts of the two planned major system upgrades (Architecture Upgrade and Full LPV Performance) to ensure that the requirements of the Full LPV Performance Specification, and this SOW are satisfied.

#### Reliability and Maintainability Program Plan

The Contractor must ensure the Reliability and Maintainability Program Plan describes how the RMA tasks in this SOW are addressed for the system changes accomplished under this SOW. The Contractor must include the organizational structure to accomplish these tasks in the Plan.

#### RMA Team Meetings

The RMA Team is comprised of FAA and Contractor RMA representatives and will meet quarterly as a sidebar in conjunction with System Engineering Working Group meetings or as directed by the FAA.  The RMA Team will review all proposed designs changes, current status of Reliability and Maintainability Modeling and Predictions for all proposed design changes and FMEA development in support of the Safety Program.  Wherever possible, the Contractor must use historical MTBF values for the new LRUs.

#### Failure Modes, Effects Analysis (FMEA)

The Contractor must document, in a PNB, the results of Failure Modes, Effects Analysis (FMEA) for all proposed Full LPV Performance Upgrades using MIL-STD-1629A as a guide.  The Contractor must ensure the FMEA covers hardware and firmware failures modes of the new and or modified LRUs.  The Contractor must tailor the FMEA with FMES to satisfy the Safety Assurance Process Requirements, including support to Fault Tree Analysis development.

#### Reliability and Maintainability Predictions

The Contractor must develop Reliability and Maintainability Predictions for all Full LPV Performance upgrades. The Contractor must establish the reliability and maintainability predictions based upon Vendor test results, fielded data and through analysis, using MIL-HDBK-217 and MIL-HDBK-781 as a guide. The Contractor must document LRU R&M Predictions in PNB format.

#### Failure Reporting and Corrective Action System

The Contractor must ensure failure reporting tracks new and modified LRUs, and provide a copy of all Vendor, i.e., prime and subcontractor, failure analysis reports that allow traceability to the root cause.  The Contractor must ensure these reports must cover hardware and firmware faults/failures.

### Reliability and Maintainability Reports

The Contractor must prepare and submit to the FAA a quarterly Reliability and Maintainability Status Report to include failure summary and analysis information.    (CDRL A033)

## Reserved

## System Test and Evaluation

The Contractor must establish a formal test program in accordance with Section 4 of FAA-E-2976.  The Contractor must be responsible for the conduct of hardware, software, and system level testing that must apply to the Full LPV Performance WAAS (Full LPV Performance Architecture Upgrade and Performance Upgrades).

The Contractor may write the test documentation in Contractor format.  The Contractor must design the test program to verify the requirements specified in Section 3 of the WAAS Specification.

### Test and Evaluation Management

The Contractor must assign a single Test Manager to interface with the FAA Test Director to coordinate integration of prime Contractor and subcontractor testing, and, support of FAA tests.  The Contractor must design the test program to minimize redundancy of effort or data.  The FAA Test Director may appoint a representative to observe formal and informal tests.  The FAA Test Director's or appointed representative’s authority is to ensure compliance with the approved test plans and procedures.

### Master Integration and Test Plan

The Contractor must develop a Master Integration and Test Plan (MITP) that provides the strategy for the integration and test of reported problems and enhancements to the LNAV/VNAV WAAS.  The MITP provides the groundwork for the detailed plans for each change due to a reported problem or planned enhancement.  The requirements for the detailed plans are contained in the Section 8.0 of this SOW.  The MITP may be prepared in Contractor format.  (CDRL A143)

The Contractor must include the following items in the MITP:

- Relationship between the system engineering process and integration and test activities

- General system integration strategy for each planned enhancement

- Cutover approach.  This includes the cutover approach for planned enhancements (algorithmic/software, new reference stations, new hardware, and changes to terrestrial communication design)

- Software enhancement strategy to show compliance with the objectives of RTCA DO-178B

- Strategy for requirements based testing for system, hardware, and software

- Integration and testing of terrestrial communication enhancements

- Regression test strategy

- Software test strategy

- Overall strategy for integration and test of reported problems with the operational WAAS

- Verification Requirements Traceability Matrix (VRTM)

- Factory Acceptance Test and Site Acceptance Test strategy

- Integration and test resources

- Integration and test management description

### 3.10.3 Production Acceptance Test and Evaluation Plan

The Contractor must update the Production Acceptance Test and Evaluation (PAT&E) Plan to include the new requirements identified in the Full LPV Performance Specification.  This Contractor must ensure the PAT&E Plan addresses requirements pertaining to Factory Acceptance Testing (FAT), for WAAS Program integrated Site Acceptance Testing (SAT) for new United States, Canada, and Mexico sites and the 3rd C&V.  The Contractor must support FAA SAT testing at each new WAAS site.  The Contractor must ensure the PAT&E Plan provides detail beyond that contained in the MITP on the testing and integration of new hardware into the operational system as well as detailed test descriptions for those requirements allocated to PAT&E.  The Contractor must ensure the PAT&E Plan includes sections on PAT&E test management, schedule, test configuration management, and a VRTM/ System Requirement Allocation Matrix (SRAM) for those requirements allocated to PAT&E.  The Contractor must ensure the SAT section of the PAT&E Plan addresses the requirements for the turnover of the data required to complete the Facility Reference Data File (FRDF).  The Contractor must ensure the content of the FRDF is in accordance with FAA Order 6030.45.  (CDRL A055)

### 3.10.4 Test Procedures

The Contractor must prepare and submit test procedures in Contractor format to cover all requirements based testing.  The Contractor must ensure these procedures contain step-by-step instructions for test conduct and the procedures clearly show which requirements are being verified during the testing.  The Contractor must not commence testing until the procedures have been reviewed and approved by the FAA.  (CDRL A056) (CDRL A057)

### 3.10.5 Test Reports

The Contractor must prepare and submit test reports documenting the results of all formal testing conducted. Use of Contractor format is authorized.  The FAA will approve all formal test reports.  (CDRL A058) (CDRL A059)

### 3.10.6 Test Conduct

The Contractor must notify the Government, via contract letter, 15 days in advance and receive formal approval to proceed to test prior to performing any formal testing.  The Contractor must perform all testing in accordance with FAA approved test documentation. The Contractor must maintain an official test log containing test identification, description of the Unit-under-test, date and time of test, procedures, test report(s), and any deviations or exceptions to the approved test procedures.  The Contractor must provide a list of any prior discrepancies or retests to be picked up as part of the current test to the FAA at least seven days prior to the start of testing.  The Contractor must not reallocate requirements from test to test without prior formal notification and approval by the FAA.

### 3.10.7 General Test Ground Rules

The Contractor must comply with the following ground rules for all testing conducted:

- The Contractor must design tests such that the success or failure of each test event is determined by measuring the results of the test against the required or expected results of the approved test documentation.  The FAA must make the determination of successful completion of test objectives and provide acceptance of test results in writing.

- Notification of test conduct includes assurance that all facilities and other support are available, the test configuration identified and under configuration control, the test equipment properly calibrated, and any prior deficiencies have been corrected and verified in accordance with the Contractor's quality assurance procedures.  Prior to the start of each formal test, the Contractor must brief the FAA representative(s), as a minimum, on the following topics:

- planned procedure and scenario changes that must be reflected in the procedure and scenario updates;

- quality assurance baseline testbed audit report including the status of all hardware, software, and documentation to be used in the test;

- test schedule;

- walk-through of the test conduct.

- The Contractor must make all changes to test procedures since the last submission to the FAA as "Red-lined Items."  If a work-around is required in one or more steps of the test procedures, the Contractor must explain the deviation and cause of this work-around.  The Red-lined test procedures must be submitted to the FAA in the DT&E and the PAT&E Reports.

- The Contractor must not interrupt the WAAS nor cause its performance to degrade during normal monitoring, testing, and validation operations.  The Contractor must obtain advance approval from the FAA to use any devices and procedures for monitoring, testing, trouble isolation, and related purposes.  The Contractor must obtain FAA approval prior to interruption of the WAAS.

- The Contractor must keep test logs to record all events that have occurred during the conduct of formal tests.  The Contractor must document all failures that occur during formal testing.  The Contractor and FAA will jointly conduct a scoring conference after the conclusion of each formal test and prior to the development of each formal test report.

- The Contractor must maintain a database of failure reports occurring during formal testing, and track individual corrective actions.  The FAA may choose to witness the closure of corrective actions and must be provided all updates to failure reports.  The FAA reserves the right to approve or disapprove the closure of failure reports.

- The Contractor must make test data and logs from formal tests available within two (2) working days after test completion upon FAA request and deliver a copy of FAA selected and requested data within five (5) working days.  The Contractor must provide at least two (2) working days notice to the FAA prior to the start of each unique formal test dry run, on a test-by-test basis.

- The Contractor must provide the FAA an opportunity to witness all Contractor conducted informal tests at the unit level and above.

- The Contractor must conduct a post-test briefing not later than one (1) day after the conduct of each unique formal test.  The Contractor must brief, at a minimum, the following topics: preliminary Contractor analysis of test responses and results; identification and preliminary analysis of anomalies discovered during test and post test analysis; planned and unplanned deviations and changes included in as-run test procedures; test procedures; test conduct log; and problem reports.

The Contractor must conduct retests when:

- The analysis of test data and the assessment of test results against pass/fail criteria indicate the item under test has failed to meet its applicable requirements, or when the analysis and assessment are inconclusive, or

- A review of changes to hardware, software, and firmware indicate that prior test results are invalid or that the impact on prior test results cannot be determined without repeating the test, or

- The Contractor deviates from the approved test plans or procedures without the prior approval from the FAA.

## Configuration Management

### Configuration Management Program

The Contractor must update and maintain the existing Configuration Management Program in accordance with FAA-STD-021A and MIL-STD-973 for hardware, FAA-STD-026A, FAA-STD-021A and MIL-STD-973 for software and Attachment P (Safety Assurance Process Requirements (SAPR) Document) for System Safety.  The Contractor must ensure the CM process for software meets the objectives in paragraph 7.0 and Table A-8 of RTCA/DO-178B for the software safety level assigned to each CSCI.  The Contractor must specify a single authority to serve as a focal point for all CM related issues.

### Configuration Management Plan

The Contractor must update, as required, the existing WAAS Configuration Management Plan (CMP), which describes the Contractor's Configuration Management Program, including responsibilities, methodology and procedures for baseline identification, configuration control, and audit and status accounting of software, hardware, documentation, support equipment, firmware, and data bases.  In addition the Contractor must ensure the CMP addresses the Contractor’s interface to the WAAS Change Control Process (Section 8.0).  The Contractor must use MIL-STD-973 with Notice 1, paragraph 5.2 and Appendix A and data item description DI-CMAN-80858A when updating the CM plan.  The Contractor must ensure the CMP addresses software development tools; the developmental configuration management process (MIL-STD-973, paragraph 5.3.3) required hardware and software necessary to read, write, or modify existing programs or data; requirements necessary to compile, assemble, link, and load source code to produce executable programs and test and debug program code.  The Contractor must ensure the engineering release system meets the requirements of Appendix C of MIL-STD-973.  (CDRL A039)

### Configuration Identification

The Contractor must follow a configuration identification program consistent with the LNAV/VNAV Phase of WAAS using MIL-STD-973 paragraph 5.3.  The Contractor must select, identify, label, serialize, and mark all Hardware Configuration Items (HWCI) and Computer Software Configuration Items (CSCI) in accordance with MIL-STD-973 paragraph 5.3.6 and develop and maintain configuration baselines in accordance with MIL-STD-973 paragraph 5.3.4.

#### System-Level Documentation

The Contractor must update the System Specification, consistent with each WCRB approved change to the product baseline.  (CDRL A121)

#### Configuration Item-Level Documentation

The Contractor must update the Configuration Item Development Specification for each HWCI in accordance with MIL-STD-490A, Appendix II, consistent with each WCRB approved change to the product baseline.  (CDRL A042)

#### System Configuration Load List

The Contractor must only maintain a load list for new Full LPV Performance sites until the FAA assumes maintenance responsibility. During Contractor maintenance, the Contractor must identify the location of all configuration item serial numbers for each location of the new Full LPV Performance sites.  The Contractor must integrate the load list with the hardware problem reporting systems and be available to the FAA, via the WAAS Shared Server.

### Configuration Control

The Contractor must maintain a system described in the CM plan, of configuration control in accordance MIL-STD-973 section 5.4.  The Contractor must establish an internal Configuration Control Board (CCB) and establish and implement procedures to accomplish change control in accordance with Section 8.0 of this SOW until the established baseline is updated to include the respective change.  The Contractor must submit changes to established baselines to the FAA in accordance with Section 8.0 of this SOW.  The Contractor must submit Requests for Deviations (RFD) and Requests for Waivers (RFW) as detailed in paragraphs 5.4.3, 5.4.4, 5.4.8.3, and 5.4.8.4 of MIL-STD-973.  The Contractor must prepare and submit specification change notices in accordance with Section 5.4.6 of MIL-STD-973.   (CDRL A048) (CDRL A049) (CDRL A122)

### Configuration Status Accounting

Configuration Status Accounting for the operational baseline (Reference Product Level Configuration Index (PLCI)) is accomplished by AOS.  The Contractor must implement and maintain a Configuration Status Accounting System in Contractor format, for activities covered by this SOW.  The Contractor must coordinate configuration status accounting with AOS as changes are accomplished in accordance with Section 8.0 of this SOW.  The Contractor must ensure the system documents the configuration identification for each serialized component and determines the status of change requests, deviations, and waivers by an automated means with a real-time capability whenever interrogated.  The Contractor must provide a Configuration Status Accounting Report(s) for each major operational baseline update.

(CDRL A050)

### Data Management

The Contractor must comply with the requirements of FAA-STD-021A and MIL-T-31000.

### Configuration Audits

A formal FCA/PCA will not be conducted for activities in support of this SOW; however, the Contractor must support activities intended to ensure all differences introduced to the operational baseline in each update are documented.  The Contractor must conduct an RTCA/DO-178B compliance conformity review for each operational baseline update in accordance with Section 8.3 of this SOW.

### Interface Requirements/Control

The Contractor must notify the FAA of impacts to GFE and NAS interfaces.  The Contractor must perform interface configuration management as stated in section 5.3.7.1 of MIL-STD-973.  The Contractor must prepare and submit Interface Control Documents for each major release to the product baseline in accordance with FAA-STD-025C.  (CDRL A052)

### Retrofit Requirements

The Contractor must comply with retrofit reporting requirements of paragraph 5.5.8 MIL-STD-973.

## Quality Control

The Contractor must maintain a Quality Assurance Program in accordance with the requirements of ANSI//ISO/ASQ Q9001-2000, DID-FAA-QA-003, FAA-STD-026A and DID-FAA-026-023.  The Contractor must comply with Software Quality Assurance objectives from Section 8.0 and A9 of RTCA/DO-178B. The Contractor may utilize certified operators where possible.

### Quality System Plan

The Contractor must maintain and update the Quality System Plan (QSP) as necessary.  The QSP describes the Contractor’s quality control program implemented in accordance with ANSI//ISO/ASQ Q9001-2000, DID-FAA-QA-003, FAA-STD-026A and DID-FAA-026-023.  (CDRL A030)

# National Airspace Integrated Logistics Support

## Contractor NAILS Program Management Responsibilities

The maintenance support concept for WAAS is Interim Contractor Depot Level Support (ICDLS). ICDLS will be provided by the Contractor prior to transitioning to full FAA depot maintenance for the duration of the contract. The Contractor must provide program management for the requirements contained herein. The Contractor must designate a single point of focus for the National Airspace Integrated Logistics Support (NAILS) Program.  The Contractor must execute a NAILS Program IAW the requirements contained herein.  The Contractor must ensure the NAILS Program consists of the total set of tasks required to accomplish the requirements stated in FAA Order 1800.58A, National Airspace Integrated Logistics Support Policy. The NAILS Program must support the following functions:

- Planned Full LPV Performance improvements

- ICDLS

- Second Level Engineering Support (SLES)

### Planned Full LPV Performance  Improvements

The Contractor must ensure NAILS activities continue to utilize the practices and procedures established during the IOC portion of the WAAS contract.

#### NAILS Program Planning

The Contractor must update the NAILS Integrated Support Plan (ISP) to include planned Full LPV Performance updates.  The ISP must contain updated descriptions of the procedures, actions, events, and organization the Contractor intends to employ in order to accomplish the NAILS program.    All updates of the NAILS ISP must be submitted for FAA approval.  (CDRL A070)

#### National Airspace Integrated Logistics Support Management Team            (NAILSMT)

The Contractor must host all NAILSMT meetings, the first of which will be held at the discretion of the FAA Associate Program Manager for Logistics (APML) and the FAA Program Office.  The APML will chair the NAILSMT.  The NAILSMT will monitor schedules and contract performance, and, review the adequacy, timeliness, and compliance with contract requirements.  The NAILSMT will meet semi-annually throughout the contract to review and assess the progress of the NAILS Program.  The NAILSMT meetings will be held at times and places mutually agreeable to the APML and the Contractor.  The Contractor must submit a proposed agenda to the chairperson no later than 15 days prior to the start of the meeting.  The agenda will provide for status reporting and analysis of problem areas.   Contractor format is acceptable.  The Contractor must provide meeting minutes IAW with Section 3 of this SOW.

#### Contractor Support of Meetings and Conferences

The Contractor will assist the FAA in providing support for conferences and

meetings, including facilities, office equipment, clerical personnel, mock-ups,

technical data, and subcontractor participation (when requested by the APML), in

accordance with the AMS policy. The Contractor must submit an agenda and meeting minutes IAW Section 3 of this SOW.

### Contractor Control

#### Subcontractor/Vendor Control

The Contractor must maintain, and be held responsible for accomplishment of subcontractor/vendor NAILS.  The Contractor must incorporate this requirement in all subcontracts exceeding $100,000.

#### Similar Work Efforts

The Contractor must make maximum use of analysis and documentation being procured under other or earlier provisions of this contract (i.e., subcontractor LSA data, Commercial-Off-The-Shelf (COTS) equipment data) and as applicable and available, data from other Government contracts and sources.  The Contractor must ensure the task analysis and equipment analysis do not duplicate the analysis, data collection, and decision-making that went into compiling the data contained in these other or earlier sources.  The Contractor must ensure these similar work efforts must be consolidated in such a way as to preclude duplication and ensure consistency.

#### Logistic Management Information (LMI)

The Contractor must maintain an LMI (Logistic Management Information) Program IAW the procedures MIL-PRF-49506 the Data Products in EXCEL format. See Attachment Q LMI Data Produce Definitions for layout of Excel spread sheet for the planned Full LPV Performance upgrades.  The Data Product must represent the physical system design configuration including: system, subsystems, support and test equipment, components, assemblies, subassemblies, and training equipment for the WAAS. The Contractor must adhere to the DATA Definitions, Edits and Data Formats as describe in CDRL A074.

As ordered by the Government, the Contractor must provide a top-down hardware breakdown structure to the component level except Commercial-Off-The-Shelf (COTS).  Any COTS or Non-developmental Item (NDI) item must only require LMI data to the Line Replaceable Unit (LRU) level.  Any modification to COTS item may disqualify it as COTS and may require LMI data to the component level.  The Government will determine the level of LMI data required for COTS modification.  The Contractor must ensure the LMI identifies logistics resources for support of the system at all levels of maintenance.

#### LMI Program Tasks

##### Reserved

##### Reserved

##### Reserved

##### Reserved

##### LMI Provisioning Guidance Data

The Contractor must support and host the LMI/delta Provisioning Update Meeting.  The Contractor must provide as part of a NAILSMT meeting/WCRB Provisioning/Supply Support data, in accordance with LMI (Mil-PRF-49506).  As determined by the FAA, the Contractor and subcontractors, must attend, participate in and contribute expertise in resolution of provisioning and supply support problems or issues.  The Contractor must document agreements reached in meeting minutes.

##### Reserved

##### LMI Data Base

The Contractor must establish and maintain an automated LMI database for equipment that is new to the WAAS baseline.  The Contractor must ensure the LMI software is a Logistics Support Activity (LOGSA) validated ADP system.  The Contractor must ensure the LMI is the central file of logistics data for the system.  The Contractor must prepare the LMI data in accordance with MIL-PRF-49506.  The Contractor must update LMI documentation to reflect changes in support requirements resulting from:

- Changes to equipment design, support or operational requirements as a result of logistic demonstrations, parts obsolescence, technical manual reviews, training results, and

- Contractor or FAA testing.

- Logistic support improvements or the correction of deficiencies discovered through analysis of test results or by Contractor’s verification of LSAR documentation.

- FAA reviews of LMI documentation and/or the result of provisioning data.

##### LMI Data Review

The Contractor must maintain internal procedures that provide for verification of the adequacy and technical accuracy of LMI documentation.  The FAA will review Contractor-produced LMI data, including LMI output summaries, drawings, mock-ups, specifications, and photographic reproductions.  The LMI review will be accomplished during and by members of the NAILSMT.  The Contractor must ensure availability of support materials and personnel for LMI data reviews.  Reviews will be held at the Contractor's facility.

##### LMI Delivery

The Contractor must prepare and submit for FAA approval, the required LMI data for each hardware change identified in each WCRB Detailed Design Report (A141). The Contractor must deliver the LMI data in electronic media format IAW the format provided in MIL-PRF-49506.  (CDRL A074)

##### Delivery Information

The Contractor must furnish the following information with the delivery of each electronic media:

- Tables contained on the media and their sequence.

- The approximate number of LCNs contained on the media.

- Person to contact.

### Maintenance Planning

#### Maintenance Concept

The Contractor must base the maintenance concept on FAA Order 6000.30C, Policy For Maintenance of The National Airspace System (NAS).  ICDLS will be used initially with ultimate transition of depot level maintenance, supply support, and second level engineering support to the FAA.  FAA Airway Facilities (AF) personnel will be responsible for WAAS site level operations and maintenance.

#### System Design for Maintenance

The Contractor must design Full LPV Performance upgrades to enhance system maintenance.  System status will be continuously monitored from the Operation and Maintenance (O & M) console. The Contractor must upgrade the WAAS so that system level verification, validation, and certification can continue to be accomplished at the O & M.  The Contractor must ensure WAAS upgrades incorporate modular design techniques to support two levels of maintenance.  On-site repair must be limited to the removal and replacement of the LRU to restore service.  Depot level maintenance will consist of repairing or replacing faulty LRUs.

#### Site Visits

The Contractor must ensure Full LPV Performance upgrades must support periodic and corrective maintenance that can be accomplished with site visits occurring no more frequently than in accordance with the Full LPV Performance Specification and FAA Order 6000.30C.

### Interim Contractor Depot Logistics Support

#### ICDLS Management

The Contractor must maintain a depot logistics support management program to effectively support the WAAS and to assist in the accountability of services rendered through Full LPV Performance.  The Contractor must maintain, in the ISP, a summary of procedures that must detail the Contractor's approach to depot maintenance.  That portion of the ISP may be in Contractor format, including the names and telephone numbers for points of contact associated with the depot maintenance effort.

The Contractor must provide bar code markings for deliverable WAAS Full LPV Performance equipment for all LRUs returned for repair to the Depot and Vendor.  Markings are to comply with Asset Identification Specification Version 2.4 dated November 18, 2003.  (A073)

#### Operations and On-site Maintenance

##### Interim Contractor Depot Level Support (ICDLS) - Supply                 Support

The Contractor must furnish facilities, labor, equipment, material and documentation necessary to provide for stocking, receipt, issue, inventory/management control, and repair service IAW the provisions set forth in this statement of work for all repairable/non-repairable LRUs of the WAAS, with the exception of the NAVSYS Signal Generator.

The Contractor must provide for the repair of selected repairable items to the extent not covered by the manufacturer's warranty.  The Contractor must include all labor, tools, test equipment, software, facilities, materials, documentation, training, a level of serviceable LRUs sufficient to maintain the level of service and any other technical and administrative support necessary to repair and restore service to the WAAS. The Contractor must provide to the Federal Aviation Administration (FAA) field sites those items as requested by the Government.  This entails complete supply support, which includes issuing expendable items and the issuing, receipting and repairing of exchange and repair (E&R) of Line Replaceable Unit (LRU) for the WAAS for the contract period of performance.  The Contractor must ensure an E&R item is repairable.  The Contractor must ensure sufficient stock is maintained to allow direct issue of the items listed for coverage under ICDLS and those items covered by warranty are repaired or replaced at no cost to the Government.  The Contractor must repair, or replace as required, all repairable E&R LRUs returned from FAA field sites and ensure the repair cost does not exceed sixty-five per cent (65%) of the cost of a new item, unless approved by the Contracting Officer or a designated representative.  The Contractor must furnish all labor, tools, test equipment, parts, software, and any other technical or administrative support necessary to provide the required depot level logistics support.

##### Reserved

##### E&R LRU Repair Procedure

The Contractor must repair E&R items to the extent necessary to restore it to a condition in which the item is capable of meeting all performance and functional requirements for which it was designed.  If the repaired item is part of a system, the Contractor must ensure it functions in a manner, which will allow the complete system to meet all operating tolerances.  Minor cosmetic defects, which do not affect the installation or operation of the item, do not require correction or repair.  The Contractor must clean, visually inspect, bench test, and isolate faults.  The Contractor must disassemble items to establish that the item is serviceable.  The Contractor must reassemble, calibrate, functionally test, perform acceptance inspection, and prepare for shipment of the item or component.  All methods and procedures used by the Contractor must be accomplished with the special tools and test equipment developed for that purpose.  The Contractor must ensure all repaired items comply with FAAD-STD-1293C and all other applicable specifications of the contract.  The Contractor must make any modification to items required by the contract and not previously accomplished at the time of repair.  Disposition of removed parts will be at the direction of the FAA Logistics Center (FAALC) Manager. The Contractor must conduct testing, inspection, and final acceptance of repair items in accordance with the production, test, inspection, and acceptance requirements of FAAD-STD-1293C and this SOW.  The Contractor must perform repairs using test equipment having traceability to the National Institute of Standards Technology in accordance with MIL-STD-45622, Calibration of System Requirements.  The Government reserves the right to inspect and verify all repairs in accordance with the terms of this contract.  Parts required to support the repair of E&R items will remain the property of the Contractor until used to restore failed items, at which time they become part of the LRU and Government property.  The Contractor may request additional inventory of parts from the Contracting Officer based upon the repair experience or analysis of this need.  The Contractor must have available an inventory consisting of a components/piece parts required for the supply support and repair of all items.  The Contractor must prepare for inventory an itemized list of all items required for support.  The Contractor must maintain an inventory listing to include, but not necessarily limited to, the following items:

- Part number and manufacturer’s cage code

- Nomenclature or description

- Quantity

- Unit of issue or Unit Ordering Quantity (UOQ)

- National Stock Number (if available)

- Unit Price

- Extended Price

The Contractor must maintain an Economic Ordering Quantity (EOQ) method (the same as presently established under the Contractor’s own ordering system) for replenishment.  Previously ordered spare parts peculiar by the Government will be maintained at the Contractor’s facility for use in the rotatable pool and all parts will remain at the Contractor’s bonded storage facility. For all vendor items requiring repair by the original equipment manufacturer (OEM), the Contractor must factor repair times into the stock requirements to meet exchange requirements for the LRUs.

###### Support Equipment

The Contractor must provide and maintain support equipment and test equipment to support the WAAS depot activities during the ICDLS period. The Contractor must certify that depot support and test equipment is calibrated and operating within the required tolerances.

###### Maintenance Support Facility Requirements

The Contractor must provide the necessary office and work space to effectively execute this contract during the period of performance.  The Contractor must be responsible for providing the necessary facilities for maintenance of WAAS hardware, for shipping and receiving, and to store system spares, piece parts, and support equipment required to maintain the system.

##### Supply Support

###### Spare And Piece Parts Support

The Contractor must be responsible for procuring and providing all required spares and piece parts, and replenishment thereof, for the duration of the ICDLS period of performance.  The Contractor must initiate and maintain inventory control for spares and piece parts and must maintain complete records of the inventory. The Contractor must house the spares and piece parts in a Government Bonded Storeroom to provide segregated storage of these spares. At the end of ICDLS (end of Full LPV Performance Contract) the spares and any piece parts in the bonded stock room will be transferred to the FAALC in two lots of approximately 50% each.  The first lot will be transferred 60 days prior to the end of the ICDLS.   The second lot will be transferred at the end of ICDLS.  Prior to the first shipment of parts from the Contractor, a team from FAALC will accomplish a physical inventory of assets stored in the bonded stockroom.

###### Consumption/Usage Report

The Contractor must maintain consumption usage reports on the WAAS spares and piece parts used or consumed.  Spares are the repairable and non-repairable circuit cards, removable modules, and LRUs. Piece parts are those items required to repair repairables.  The Contractor must submit consumption/usage reports to the FAA monthly no later than seven days following the last day of each month.  (CDRL A079) (CDRL A080)

###### Delivery Requirements

Order Priority

The Contractor must provide a 24-hour point of contact.  The Contractor must provide the name and telephone number of the point of contact.  Requisitions/orders will be submitted to the Contractor via Web-base LIS Interface Tool, or in some cases telephone or facsimile.  Telephone requisitions will be confirmed on Web-base LIS Interface Tool within 24 to 48 hours.

Web-base Requisition Interface Procedures

The Contractor must utilize the FAA Logistic Center Web-Based LIS Interface Tool to receive and process requisitions forwarded by the FAA Inventory Manager.  The Contractor must complete all appropriate Interface data fields; provide the required asset and asset return information, as well as any associated shipping information on a daily basis.

The Contractor must monitor the web-based tool for requisitions during standard working hours, defined as 08:00 a.m. - 14:30 p.m. PST (10:00 a.m. - 16:30 p.m. CST), Monday - Friday, excluding federal and Contractor holidays.

The Contractor will receive returned assemblies from WAAS sites and will record information regarding the returned item in the web-based requisition interface tool, to include originating site, LRU, and shipping information.

For all requisitions, the Contractor must utilize the FAA priority codes system:  This identifies priority of requisition placed by the user; indicates priority of Purchase Order on due-in; and priority of requisition on due-out.

- Priority 1- Requisition must be shipped within 24 hours of the Contractor having received the requisition request from the Government.

- Priority 2- Requisition must be shipped within 48 hours of the Contractor having received the requisition request from the Government.

- Priority 5- Requisition must be shipped within 7 business days of the Contractor having received the requisition request from the Government.

Shipment Of Items

Shipment of E&R Items

From Contractor Facility to Government Facility.  Upon request by the Government, the Contractor must ship a serviceable E&R item to the designated Government field facility. The assigned FAALC manager will furnish shipping instructions for those repaired items.  The assigned FAALC Manager will contact the Contractor's depot repair facility and provide a tracking number for each shipment repair action. The Contractor must use the assigned tracking number as the Return Material Authorization (RMA) for transportation charges to bill as a separate item on all invoices.   If the item’s shipping charges for any one destination exceed $100, the waybill must be marked as follows "THESE TRANSPORTATION CHARGES ARE TO BE PAID AS A SEPARATE AND DIRECT ITEM BY THE U.S. GOVERNMENT; THEREFORE, ANY SPECIAL U.S. GOVERNMENT TRANSPORTATION RATES MUST BE APPLIED."  Method of shipment will be commensurate with the designated priority of the requirements and may be specifically designated by the assigned FAALC Inventory Manager (IM).

From Government Facility to Contractor Facility.  Upon receipt of a serviceable item at the Government facility, a repairable item will be shipped using the prepaid return provided by the Contractor directly from the field facility.  The repairable item will be returned to the Contractor by traceable means within ten (10) calendar days. All shipments must be by traceable means.

Shipment of Expendable Consumable Items

Upon request by the Government, the Contractor must ship the specified quantity of the expendable consumable item to the designated Government field facility. The assigned FAALC Manager will furnish shipping instructions for the expendable consumable items.  The Contractor must bill transportation charges as a separate item on all invoices. If the items shipping charges for any one destination exceed $100, the Contractor must mark the waybill  "THESE TRANSPORTATION CHARGES ARE TO BE PAID AS A SEPARATE AND DIRECT ITEM BY THE U.S. GOVERNMENT; THEREFORE, ANY SPECIAL U.S. GOVERNMENT TRANSPORTATION RATES MUST BE APPLIED."  Method of shipment will be commensurate with the designated priority of the requirements and may be specifically designated by the assigned FAALC Manager.

### Support Equipment

Support equipment has been provided to support the LNAV/VNAV WAAS. To the extent possible, the Contractor must utilize LNAV/VNAV support equipment to satisfy requirements associated with Full LPV Performance.

#### Support And Test Equipment Identification

The Contractor must identify support and test equipment for site maintenance, depot maintenance, and depot software support.  The Contractor must justify requirements for special support and test equipment.  The Contractor must describe test equipment functions and parameters measured in sufficient detail to enable the FAA to determine the best method of satisfying the requirement.  Whenever possible, the Contractor must satisfy support and test equipment requirements with items currently in the FAA inventory.  The Contractor must identify the depot test equipment, test plans and procedures and associated documentation necessary for the FAA to conduct depot functions in the transition plan. (CDRL A078)

#### Automated Test Equipment (ATE) Identification

The Contractor must select from the list of WAAS ATE hardware listed in the transition plan.  The Contractor must document any decision for not selecting from the list of ATE; this rationale must be provided to the FAA.  The Contractor must require final approval by the FAA on ATE selection to prevent unnecessary proliferation of types and quantities of ATE in the FAA inventory.  The Contractor must justify, document, and describe requirements for ATE using the LSAR "E" data tables, Genrad 2272 (Bed of Nails, 1024 Pins), Factron 635 (Functional IC Tester), HP 3065 (Bed of Nails).

#### Development of ATE Software and Equipment

The Contractor must provide the Government all ATE software developed for the WAAS program.  This includes programs for both commercial ATE hardware and/or “bench” test fixtures where Personal Computers (PC’s) control the testing of individual modules connected to separate fixtures.  The Contractor must provide a copy of the operating procedure for the Test Program Set (TPS) software in sufficient detail that an experienced ATE operator can run the program.  (CDRL A105)

#### Development Of Test Program Sets (TPSs)

The Contractor must design all non-COTS/NDI LRUs in the WAAS to be compatible with, and facilitate testing by the Contractor-designated automatic test system.  The Contractor must provide all software, firmware, materials, instructions, and documented unit test programs compatible with the designated automatic test system(s) for each non-COTS/NDI LRUs.  If a particular unit under test (UUT) requires more than one ATE device for conducting its required tests, the Contractor must ensure the TPS for that UUT includes all hardware, software, procedures for isolation and troubleshooting, etc., for each ATE device which is involved in the test procedures.  The Contractor must ensure the test programs and the ATE are capable of isolating faults down to the piece part level for each LRU provided as part of the system as follows:

- Not less than 90% of all possible faults for each digital Printed Circuit Board (PCB)/LRU.

- As a design goal, not less than 90% of all possible faults for each analog PCB/LRU.

- The Contractor must provide updates/retrofits to the TPS, where the need for the change is generated by:

- A result of failure to isolate the required percentage of the total number of possible faults during the TPS acceptance tests.

- Hardware/firmware changes resulting from problems discovered in the repairable items and piece parts. (CDRL A106)

#### Automatic Test Equipment Requirements

The Contractor must deliver all software Test Program Sets and test fixtures required to test/repair LRUs all on proposed Automatic Test Equipment (ATE) hardware 6 months prior to the end of ICDLS.  The Contractor must install, debug, and demonstrate the capability of the software and test fixtures to test all LRUs as outlined in the transition plan.

### Training, Training Support, and Personnel Skills

#### Training

Training requirements associated with the procurement and deployment of the WAAS is provided by the FAA.

#### Access to Contractor’s Facilities and Data

The Contractor must permit FAA training personnel and/or their designated representatives full access to the Contractor facility for training development purposes, upon written or verbal notification from the COTR with at least 30 calendar days advance notice of any visit.  The Contractor must grant access to any training development organization under contract to the FAA to develop or assist in training program development.  The Contractor must provide FAA personnel or their designated representatives access to any data that is to become FAA property.  This access includes data on system and/or equipment hardware, software, and firmware.

#### Meetings/Conferences

The Contractor must provide facilities for meetings to support the FAA.  For estimating purposes, the Contractor must plan on six meetings at their facility.

#### WTMS Spare Parts

The Contractor must assign WTMS spare parts delivered under the LNAV/VNAV Phase to the WTMS to support FAA training activities. The Contractor must provide ICDLS support for the WTMS in accordance with SOW Section 4.1.4.2.1.  The Contractor must make recommendations to the FAA regarding the need to replenish the spare parts in to the depot that have been assigned to the WTMS.

### Provisioning

Provisioning has been performed to support the LNAV/VNAV WAAS. To the extent possible, the Contractor must utilize LNAV/VNAV provisioning to satisfy requirements associated with Full LPV Performance.  The Contractor must provide provisioning recommendations to the WCRB.

For baseline changes to the WAAS, the Contractor must provide the following data and service to the FAA (WCRB): The Contractor must support and host Delta Provisioning Update Meeting(s) as required.  The Meeting must be held not later then 30 day after the configuration audits performed in support of the detailed design review(s) and not more then 45 days after approval of the first increment of LMI.  The Contractor must provide the following Data and Service:

- The Contractor must have available for review one (1) complete set assembly and detail drawings for each item that appears on the Provisioning Part List (PPL) in PLISN with cross-reference list to part numbers in Technical Data Package (TDP).

- The Contractor must have copies of the Government approved configuration audit documentation available for use as reference.

- The Contractor must make available for the duration of the Meeting all equipment(s) on the contract.

- The Contractor must furnish personnel and tools necessary to disassemble the equipment(s) to the extent required by the Government Provisioning Team.

- The Contractor must ensure the participation of Contractor personnel with detailed knowledge of the subject mater they represent. E.g. provisioning documentation and technical documentation, hardware/software maintenance, engineering and system design, etc.

- The Contractor must provide facilities, office space, conference room access to telephone/facsimile, etc for the Government provisioning team and the Contractor personnel participant in the Meeting will be provided to the Contractor prior to the conference.

At any time during the terms of this contract or any extension thereof the Government reserves the right to order additional Delta Provisioning Update Meeting(s) and updates to the LMI data that will be required to support the provisioning process.

#### Spare Parts Peculiar

The Contractor must perform provisioning to identify, quantify, and deliver all items defined as parts peculiar in accordance with MIL-PRF-49506, Provisioning Requirements Statement.  The Contractor must document these items in the LMI database.

The Contractor must deliver additional spare parts peculiar as ordered by the FAA.  The Contractor must procure additional spare parts peculiar as a result of WCRB direction.  In the event that the FAA decides to procure additional spare parts peculiar, fair and reasonable prices and terms of delivery must be established by agreement between the Contractor and the Contracting Officer.  Such agreement will be set forth in a modification to the WAAS contract.

The Contractor must provide bar code markings for deliverable WAAS Full LPV Performance equipment for all spare LRUs.  Markings are to comply with Asset Identification Specification Version 2.4 dated November 18, 2003. (CDRL A073)

#### Prescreening

As ordered by the Government new equipment to the LNAV/VNAV baseline, must be screen through the Defense Logistics Information Services (DLIS) for National Stock Numbers (NSN) all information entered on the LMI data Base (Item Identification). The Contractor’s screening results must be documented in the LMI Data Worksheet Data Table and must be no more than 60 days old when the LMI data is delivered.  With Government approval, the Contractor may use current PC based parts list/software program for this requirement.  After completing DLIS screening, the Contractor must provide (contract option) data required by the Government for Item Identification (FED-STD-5) for item not cataloged and complete design change notices (DCNs) (A082).

Item identified as proprietary must be clearly marked and identified as PROPRIETARY.

### Site Spares

#### Site Spares

As ordered by the Government, the Contractor must prepare and deliver to the Government a list of recommended site replaceable spares, assemblies, and consumables for the WAAS Full LPV Performance configuration at each site.  The list must be in Contractor format and must include each LRU noun nomenclature, NSN, part number, manufacturer’s CAGE code, and the unit price will that will charged to the Government, Mean-Time-Between-Failure (MTBF) and recommended quantity for each LRU.  The Government reserves the right to order all, more than, less, than, or none of the items and quantities recommended. The Contractor must deliver the site spares ordered by Government with each LNAV/VNAV WAAS.

### Packaging, Handling, Storage And Transportation (PHS&T)

#### Storage Requirements

It is anticipated no items will require storage at the FAALC during the ICDLS period.

#### Hazardous Material Management Requirements

The atomic clock contains a small amount of cesium metal.  The cesium isotope used (cesium 133) is non-radioactive.  However, because of its reactive chemical properties, cesium is technically classified as a hazardous material by the U.S. Department of Transportation (USDOT) and the International Air Transport Association (IATA).  During normal handling, the atomic clock presents no danger since the cesium is encased within a vacuum-sealed metal enclosure.  However, the atomic clock is subject to certain shipping regulations under Title 49 of the Code of Federal Regulations (CFR), Section 172.101, which govern the shipping case as well as its labeling.  The Contractor must provide an atomic clock with a tested and certified shipping case along with the appropriate labels.  During installation of the equipment, the Contractor must be aware of the possibility of asbestos hazards in some of the FAA buildings.

### Technical Data

Technical Data has been provided to support WAAS LNAV/VNAV. The Contractor must provide additional technical data, to supplement LNAV/VNAV data, to support WAAS Full LPV Performance requirements.

#### Support/Test Equipment Manuals

The Contractor must provide commercial manuals for the operation, description, maintenance, and repair of the Contractor peculiar furnished support/test equipment.  In addition, the Contractor must provide all original documentation delivered with the support/test equipment,

#### Technical Data Package

##### Depot Level Repair Specifications

The Contractor must provide a copy of depot level limits and tolerances for each individual LRU.  These are criteria the Contractor uses to validate the satisfactory operation of each individual LRU.  (CDRL A107)

##### Technical Drawings and Associated Lists

The Contractor must provide commercial drawings and associated lists as a part of the WAAS technical data package.  (CDRL A108) (CDRL A109)

##### Technical Instruction Book

The FAA will update and maintain the Technical Instruction Book (TIB). The maintenance instructions contained in the TIB will be of sufficient detail to permit Government technicians to install, troubleshoot, and repair the equipment.  All tools, fixtures, and test equipment required for installation and maintenance will be listed.

With each baseline approved by the FAA WCRB, the Contractor must provide working data to support the FAA in updating the TIB after approval of the scope analysis package and no later than 60 days prior to the baseline cutover.

#### Contractor Support Transition Plan

The Contractor must prepare, submit for FAA review and approval, and subsequently implement a Contractor Support Transition Plan (CSTP).  The CSTP establishes the procedures and means for the orderly transfer of the system support activities from the Contractor to the FAA.  (CDRL A078).  The Contractor must ensure the CSTP details the activities the Contractor undertakes to assure a smooth transition from Contractor to FAA operations, and the preparations, facilities, and personnel that the FAA will require to assume responsibility for the conduct of all services provided under ICDLS and SLES.  The Contractor must ensure the CSTP recommends the time required to ensure a smooth transition with minimal interruption to repair activities.  The CSTP may be submitted in Contractor format.  The Contractor must ensure the CSTP includes, but is not limited to:

- Any formal/OJT training/familiarization required to support the repair functions;

- Activities, procedures and schedules for any necessary refurbishment, calibration, and acceptance of GFE/GFP/Contractor Acquired Property (CAP) prior to return to the FAA;

- The detailed plan for shipment, installation, and checkout of any GFE/GFP/CAP at the designated FAA facility;

- The duration and type of Contractor support required, if any, at the FAALC facilities during the depot repair startup;

- The disposition and physical inventory of lay-in stock, to include all accounting records;

- Operating methods to be employed to assure repair services during the transition period;

- Method or procedure of transitioning management of the Vendor/OEM repair contracts to the FAA;

- An estimated cost (based on the Contractor's prior experience) of managing vendor repair subcontracts for the life cycle of the system;

- Post Production Support Analysis

- Any recommendations for additional equipment, processes, and documentation which would be beneficial to the FAALC operation of the transitioned ICDLS;

- Software support environment (SSE), system test facility (STF), and related documentation; and tools required to support and maintain the WAAS.

# Site Implementation

The Contractor must use the FAA designated Full LPV Performance sites (as referenced in Section F of the contract) for the ground-based equipment.

The Contractor must perform work according to the following table:

| EQUIPMENT | SITE SURVEYS | SITE IMPLEMENTATION PLANS | SITE PREPARATION | EQUIPMENT INSTALLATION |
| --- | --- | --- | --- | --- |
| Alaska WRS Sites | FAA | FAA | FAA | FAA |
| Mexico WRS Sites | Contractor | Contractor | FAA | FAA |
| Canada WRS Sites | FAA | FAA | FAA | FAA |
| C&V (WMS) | Contractor | Contractor | Contractor | Contractor |
| TCS | Contractor | Contractor | Contractor | Contractor |

The Contractor must supply the documentation, ground-based equipment, equipment used to interface to the NICS or equivalent non-US communications capabilities that will be provided as Government-Furnished Service (GFS) for sites external to the US and related resources to implement the Full LPV Performance WAAS.  The Contractor must provide, install, test, and support cutover of the new equipment required for each operational update of the baseline of WAAS.  The Contractor must provide any tools and test equipment needed for installing, testing, operating and maintaining the WAAS.  The Contractor must be responsible for compliance with applicable Federal Regulations including but not limited to FCC Rules and Regulations and International Rules and Regulations, concerning frequency coordination, licensing actions, and related matters. All matters concerning coordination, approval, and authorizations etc. with agencies external to the US will be handled by the FAA.

## Site Surveys

Facility Site Surveys and FAA Surveys may be conducted at the same time to facilitate communications and a common understanding of the background environment.  The results of the Site Survey must be submitted as a PNB for approval IAW Section 3 of this SOW.

The Contractor must complete a facility Site Survey for each site as directed in the table above, in order to acquire site-specific information required for performance of the system implementation activities.

### Reserved

### Materiel

The Contractor must provide all materiel required for the installation of all WAAS Full LPV Performance components.  Such materiel must consist of but not be limited to antennas (and mounts), racks, cabinets, circuit conditioning, cables, and connectors. For facilities where the Contractor will be installing equipment, the Contractor must also furnish any equipment or electronics enclosures (including any associated heating, ventilation, and air conditioning equipment) required for any WAAS equipment that is to be installed outdoors (outside of FAA facilities) and for any WAAS equipment that is to be installed within FAA facilities that do not provide the environmental conditions required by this WAAS equipment.

### Power

#### Cable and Connectors

The Contractor must determine, select, and provide cables and connectors necessary to connect the WAAS equipment to the FAA-designated power sources. For the equipment being installed by the Contractor, the Contractor must install cables and connectors and ensure cable marking, labeling, tracer indications and protection for unused power and radio frequency (RF) outlets or receptacles is consistent with LNAV/VNAV capability.  The Contractor must ensure initial power installation is to the building service power bus.  Upon certification that the system meets the AC power constraints in FAA-G-2100G, paragraph 3.1.1, the FAA will switch the power connection to the critical power bus.

#### Standby Power

For equipment being installed by the Contractor, the Contractor must provide standby power for the WAAS.  The Contractor must provide WAAS standby power for equipment, which includes but is not limited to units such as uninterruptible power supplies, power conditioners, batteries, and battery-backup power.  The Contractor must ensure standby power is available immediately (without interruption) upon failure of the primary power source and must support operation for a period of at least four hours.

#### Grounding

For equipment being installed by the Contractor, the Contractor must ensure that all grounding is in accordance with FAA-STD-019B, FAA-STD-020B, and the Full LPV Performance Specification.  The Contractor must ensure the ground wires utilize the same green wire tracer indication for single and multipoint grounding as used in the LNAV/VNAV Phase.

## Implementation Planning

The Contractor must prepare and submit a Site Implementation Plan (SIP) for approval in PNB format for each new site, as described in the Table included in Section 5, or any significant redesign of existing sites for Full LPV Performance.  The PNB must be delivered to the FAA, IAW Section 3 of this SOW, 60 days after approval of the Site Survey.   For SIPs produced external to the Contractor, the Contractor must review and provide comments to the FAA no later than 14 days after receipt via email to the Contracting Officer.

## Site Preparation

For new sites where the Contractor must perform site preparation work, the work must be in accordance with the applicable FAA approved Site Implementation Plans

## Equipment Installation

For equipment being installed by the Contractor, the Contractor must install WAAS equipment in accordance with the approved Site Implementation Plans.  Upon completion of the Contractor installation activities at each FAA site, the Contractor must be responsible for clean-up and disposal at each applicable site of any shipping crates, packing materials and related items not required for WAAS operation.

The Contractor must provide bar code marking for deliverable WAAS Full LPV Performance equipment for all newly installed LRUs.  Markings are to comply with Asset Identification Specification Version 2.4 dated November 18, 2003.  (CDRL A073)

## As-Built Drawings

The Contractor must provide As-Built Drawings, for approval,  90 days after SAT in PNB, IAW Section 3 of this SOW.  For each new site added where the Contractor performs the installation, the Contractor must update the Government facility drawings to show the installed WAAS Full LPV Performance configuration, including the Subsystems within all WAAS sites.  The Contractor must update the existing National Operations Control Center (NOCC) as built documentation in WAAS PNB 107-1-3-2 including a review of the existing NOCC as built data, conduct a site survey to gather data on current configuration, and update and release a PNB updating the NOCC As-Built documentation.

## WAAS Disestablishment

If the WAAS contract is terminated without the election by the FAA to purchase some or all of the WAAS equipment, the Contractor must be responsible for the removal from FAA sites of any WAAS equipment and related items not purchased by the FAA including but not limited to receivers, processors, antennas, equipment enclosures, and Contractor work-area furnishings.

# Government-Furnished Equipment

The FAA will provide the Contractor the GFE in accordance with Section H.4 of the contract.

## Communications System

Government furnished communications systems are listed in paragraph 3.5.1 of this SOW.

## Equipment and Support Space

### Equipment Space

The FAA will provide up to fifty square feet for the installation of WAAS equipment at WRS sites.  The FAA will provide up to 150 square feet for the installation of WAAS equipment at WMS sites.  The FAA will provide up to 100 square feet for the installation of the SGS equipment.  Internal facility space available for installation of WAAS equipment at FAA facilities must be determined during Full LPV Performance facility site surveys and will be subject to FAA coordination and approval via NAS Change Proposals (NCPs)

### Support Space

At each facility at which WAAS equipment will be installed, the FAA will provide up to sixty-five square feet of internal floor space for use in on-site maintenance activities, storage of spare parts as well as support and test equipment, and related purposes.  Internal space available for the Contractor's WAAS support activities will be determined during facility site surveys and are subject to FAA coordination and approval.  The Contractor must be responsible for the security of spare parts, support and test equipment, and related items as long as the Contractor retains sole custody of said items.  In cases, if any, where physical security capabilities in excess of those normally provided by the FAA are required, such as storage cabinets with locks, the Contractor must provide these capabilities and furnishings.

## Environmental Control

Government facilities in which WAAS equipment may be installed will be controlled to environmental condition I as specified in, FAA-G-2100G paragraph 3.2.1.1.2 for outdoor equipment and paragraph 3.2.1.1.3 for indoor equipment.

## Electrical Power and Termination

The FAA will provide normal alternating current (AC) electrical power.  Primary power will generally be available at FAA-provided power panels in the form of 60 Hz three- phase 120/208V power or 60 Hz single-phase 120V power.

## Ground Termination

The FAA will provide access to the required facility power ground and signal power ground buses for the Contractor-provided WAAS equipment.

## Documents

The FAA will provide available site documentation (e.g., site drawings and building blueprints, geodetic survey information) to facilitate the installation and operation of the WAAS upon written request from the Contractor.

## Physical Security

The FAA will provide or coordinate security at Government sites and will coordinate access to such through existing local security channels and procedures (e.g., building passes). However, the FAA will not provide physical security external to those sites (e.g., conduits or lines routed from Government buildings to Commercially owned power or telephone poles).

### Points-of-Contact

The FAA will identify a point-of-contact at each affected Government facility for the coordination of activities related to the WAAS.

## Telephones

The FAA will provide access to existing Government telephones for use by the Contractor personnel while on-site for the conduct of activities related to the WAAS.

## Ground Monuments

The FAA will provide National Geodetic Survey (NGS) benchmarks or suitable alternatives for each Full LPV Performance site.

# Second Level Engineering Support

This section defines the Contractor's technical and management support to the FAA in the Contractor's role of providing second level engineering support (SLES) for the Wide Area Augmentation System (WAAS).  This includes engineering services to detect, investigate, verify, and correct problems within the WAAS, and support the analysis, design, and deployment of enhancements to the system as authorized or directed by the FAA.  The services described herein are provided to facilitate a smooth transition of WAAS from development to Contractor-provided second level engineering support to unassisted FAA support.

SLES excludes direct Contractor support to WAAS Operators and any associated training unless associated with AOS coordinated Field Support.  Contractor depot repair, supply support, and coverage of NAILS work scope are provided in Section 4.0 of the SOW and are not part of SLES.

The Contractor's support to the FAA must include engineering services to maintain the operational integrity of WAAS and provide an engineering infrastructure to support the investigation and correction of problems, and implementation of enhancements. The Contractor must provide engineering services which include various layers of on-call and on-site field support, detection and investigation of anomalous system behavior or potential field problems, system performance monitoring, assessment, and design, development, and test of modifications to repair or enhance the system, and delivery of verified modifications consistent with the processes described in Section 3.10 of the SOW.

The Contractor must ensure the engineering infrastructure includes provision of the engineering and management expertise to assist the FAA in maintaining and enhancing the WAAS, including the maintenance and extension of laboratory assets, test environments, and associated administrative services.

## Field Support

### Reserved

### Contract Award to Full LPV Performance

The Contractor must ensure that complete and accurate contact information for the second-level engineering support field personnel is made available to the AOS for both on-call and administrative hours.

The Contractor must designate specific personnel to ensure that second level engineering support is available to the AOS 24 hours a day, 7 days a week.

The Contractor must provide engineering services when requested by the AOS to support the SLES efforts at FAA field sites, the Contractor's plant, or elsewhere, with skills in specific areas including, but not limited to:

- Anomaly Investigation / Analysis

- Satellite navigation principles;

- Telecommunications network applications, engineering, and operation;

- WAAS equipment (hardware, software, and firmware);

- WAAS system operational, support modes, and procedures; and

- Testing support.

### On-Call and Onsite Support

#### Administrative Support

The Contractor must provide engineering support during administrative hours on a full time basis.  Administrative hours are defined as weekdays, 8:00 AM to 5:00PM PST, excluding Contractor published holiday schedules.

#### On-call Support

The Contractor must respond to AOS within two (2) hours of the initial request for engineering support.

The Contractor must render the necessary support to restore the system to operation.

#### Onsite

The Contractor must provide onsite field assistance when requested by AOS.

The Contractor must ensure that onsite assistance for high priority problems is rendered within 24 hours.  A problem categorized as high priority typically will involve loss of Signal In Space (SIS) or a significant loss or risk of loss of redundancy.  Note: A longer response time may be allowable, but must be coordinated with the FAA on a per occurrence basis.

## Performance Monitoring

### Monitoring and Reporting

The Contractor must perform event and trend analysis of WAAS performance parameters.

The Contractor must define other monitoring activities as needed to fully characterize WAAS performance.

The Contractor must document, investigate, track, and disposition all anomalies found in the course of monitoring WAAS performance.

The Contractor must report WAAS system performance including any anomaly investigation activity weekly to the FAA (AOS).  The format of this report will be mutually agreed upon between the Contractor and the FAA (AOS).

The Contractor must maintain the anomaly database and make the database available to the FAA.  The Contractor and the FAA will mutually agree on the level of detail provided in the database for each anomaly.

The Contractor must define the performance monitoring during and immediately following cutovers to new operational baselines including new site installation, maintenance activities, and system upgrades.

The Contractor must make available all performance monitoring plans, procedures, and devices to the FAA.

### Monitored Performance Parameters

The Contractor must monitor WAAS signal accuracy performance.

The Contractor must monitor WAAS integrity performance.

The Contractor must monitor WAAS availability performance.

The Contractor must monitor WAAS continuity performance.

The Contractor must monitor WAAS terrestrial communication circuit performance.

## Anomaly Investigation

The Contractor must investigate the root cause of WAAS events, or anomalies, that occur outside of expected system behavior or performance, even if WAAS performance remains within specification tolerances.

The Contractor must notify the FAA if an anomaly cannot be recreated.  In these cases, the Contractor may recommend closure of an anomaly report due to lack of evidence.  Such closures will be at the discretion of the FAA.

The Contractor must report any anomalies to the FAA that are believed to be a result of problems in GFE equipment (e.g. leased communication lines, certain GUS components, etc.).

The Contractor must support the FAA in coordinating activities with other GFE providers to resolve system anomalies.

## SLES Transition Support

### Contract Award to Full LPV Performance

The Contractor must provide On-The-Job Training (OJT) for no more than six FAA personnel at the Contractor’s facility.  This OJT must include, but not be limited to: familiarization with WAAS procedures and processes including activities involved with identification and recognition of anomalous conditions, validation of anomalies, root cause troubleshooting, corrective action tradeoffs/impact assessment, interface to the WCRB, retesting, documentation updates, on-site maintenance, configuration management practices, identification of items requiring safety review and/or update, and performance monitoring.

The Contractor must provide a list of minimum WAAS job skill qualifications for the start of OJT at the Contractor’s facility.

The Contractor must ensure that OJT positions are available for AOS personnel in key process areas to ensure the overall training needs of AOS are satisfied.

The Contractor must also assist AOS in developing a recommended staffing structure of engineering and administrative disciplines to perform and manage these activities.

### Asset Transfer to AOS

The Contractor must transfer FAA-owned assets (e.g., support and maintenance environment) used by the Contractor to support SLES from the Contractor's facility to AOS in Oklahoma City prior to Full LPV Performance in accordance with Section 4.1.10.3 of this SOW.

# Operational Baseline Management

The Contractor must adhere to the WAAS Change Control Process as administered by the WCRB when modifying the WAAS operational baseline.

For modifications requiring equipment installations, the Contractor must complete a facility survey of each WMS, WRS, and GUS location as required in order to acquire site-specific information for system implementation activities according to Section 5.0 of this SOW.

## Scope Analysis

The Contractor must perform a scope analysis, as directed by the FAA (AOS), for each proposed change as initiated by contracts letter.  (CDRL A140)

### Problem Re-Validation

The Contractor must perform the activities to re-validate the reported problem and that a need for change exists.  The Contractor must notify AOS if the reported problem and/or need for change cannot be revalidated.

### Impact Assessment

The Contractor must perform a change impact analysis to determine what elements within the system will be affected by the proposed change and what supporting documentation will need to be updated.  Such analysis should identify the specific sections of system documentation that are affected and provide a suggested approach for incorporating the changes.  Upon request, the Contractor must also provide written technical input to support development of FAA Change Directives (e.g., System Support Directives).  Documents that may be affected include but are not limited to those identified in the Product-Level Baseline.  The Contractor must identify the affected Computer Software Configuration Items (CSCIs), Computer Software Components (CSCs), hardware components, and firmware that require change and recommend how changes will be accomplished.

### Risk Assessment

The Contractor must assess the risk of implementing and fielding modifications in the context of planned WAAS changes and the priority of change implementation.  If the change is part of an identified package of changes, the Contractor must evaluate the implementation and fielding risk given the other changes identified in the change package.

The Contractor must assess the potential for functional conflicts that the change may introduce, examining each affected function or operation, and adjust the implementation approach for risk avoidance or mitigation.  Where risks are unavoidable without excessive schedule or cost impact, the risk factors must be clearly documented in the Scope Analysis for consideration by the FAA.

The Contractor must rate the severity, likelihood, and overall risk of each change package using criteria agreed upon by the Contractor and FAA.

### Alternatives/Options

Where appropriate, the Contractor must develop solution alternatives or options including an option for not implementing any solution.  These options must include all aspects of the Scope Analysis described herein.

The Contractor must also provide a recommendation that specifies a preferred option and rationale for selecting it.

### Initial Test Approach

The Contractor must identify the initial approach to testing the change prior to release according to the master integrated test plan (reference Section 3.10 of this SOW).  The test approach may be further refined or modified during development and implementation.  The approach must also include identification of functionality that cannot be fully exercised or tested within the Contractor's test facility.  Risk associated with not fully exercising functionality must be described in the Risk Assessment portion of the analysis.

### Implementation Estimate

The Contractor must provide an estimate of the manpower, material, and schedule to develop the change or enhancement.

The Contractor must identify any impacts to manpower, material, and schedule - both positive and negative, associated with bundling a particular change with other changes currently being considered.

The Contractor must provide a preliminary cost estimates and ESLOCs for SLES changes by WPR and a mapping to WBS elements for Full LPV Performance changes by WPR.

### Scope Analysis Report

The outputs of all scope analysis activities (Sections 8.1.1-8.1.6 of this SOW) must be delivered to the FAA for consideration by the WCRB.  The specific format and details of this report must be delineated in the CDRL.    (CDRL A140)

### WCRB – Initial Approval Support

The Contractor must present the findings of the scope analysis to the WCRB.

## Detailed Design

For each change approved through the WCRB and as directed by the Contracting officer, the Contractor must:

- Perform all change development activity utilizing the product-level baseline obtained from the FAA.

- Design changes for hardware and software for all changes approved by the WCRB.  The Contractor must update product baseline documents for all changes approved by the WCRB.

- Provide engineering support and information associated with user document changes resulting from approved WCRB changes.

- Perform regression analysis and develop a verification/test approach for all changes including the development of modification acceptance criteria.

- Develop a cutover approach and identify risks for fielding.  The Cutover approach must identify any and all special requirements for deploying the new baseline.  When determining these requirements, the Contractor must take into account at least the following items:  (a) upgrades must be accomplished with minimal risk to SIS interruption, (b) minimize the number of restarts of subsystems to reduce the risk of loss of SIS or availability, (c) avoid operator overload, and (d) minimize the impact on additional TCS bandwidth during the cutover transition.  The Contractor must ensure the cutover approach has an appropriate and complete mechanism for rollback to an earlier baseline in the event of a problem.

- Verify/test where possible all hardware and software modifications and the associated cutover procedures.  Where modifications and cutover procedures cannot be verified in the laboratory environment, the Contractor must identify residual risks for fielding.

- Conduct retests when a review of changes to hardware, software, and firmware indicate that prior test results are invalid or the impact on prior test results cannot be determined without repeating the test.  The Contractor must conduct regression testing on those items and associated items that have previously been tested successfully and are subsequently modified.

- Provide documentation for each approved change to the product baseline according to Section 3.10.2 (Master Integrated Test Plan) of this SOW.

- Analyze and plan for the specific needs for implementing changes at each site affected by the change.

The Contractor, upon completion of the above change implementation activities, must provide a completed WAAS Detailed Design Report to the FAA for review and approval.  This report must include, as a minimum, the results of the change impact analyses; detailed information on the changes made, and detailed information on the verification activities associated with the changes. The specific format and details of this report must be agreed upon jointly between the Contractor and the FAA.  (CDRL A141)

## Operational Baseline Change Delivery

The Contractor must conduct an RTCA/DO-178B compliance conformity review for each update of the software product baseline.

The Contractor must support implementation of changes as requested by the FAA.  Support may include travel on-site to monitor or assist in change installation.

The modified product baseline must be documented by the Contractor and maintained in soft copy form on a shared file server for FAA access.  Updated baseline documentation must be made available to the FAA as defined in the Contract Data Requirements List, and according to Major or Minor upgrades as defined below:

Major Upgrade - Two major upgrades are defined for WAAS Full LPV Performance:  (a) the Architecture Upgrade, as described in paragraph 2.1.1, and (b) the Full LPV Performance Delivery, described in paragraph 2.1.2.

Minor Upgrade - Minor Upgrades provide for the deployment of field problem corrections and enhancements, as approved by the WCRB and as directed by the Contracting Officer, and serve as an incremental approach to achieving higher levels of Full LPV Performance functionality in support of Major Upgrades.  The number and frequency of minor upgrades must be mutually decided between the FAA and Contractor during the course of Full LPV Performance.  With the exception of software deliverable media, all applicable documentation updates for minor upgrades must be made available to the FAA in soft copy document, format (PNB or other) to be agreed to by the FAA via a shared file server to support timely review by the FAA.  The Contractor must incorporate FAA comments and post the updated document on the shared file server.  The Contractor must notify the FAA via email when the documents are posted on the shared file server.

## Implementation Report

The Contractor must submit an Implementation Report to the FAA that documents the first article, modified baseline (including all affected product-level baseline documentation), reason for modifications, required equipment, modification kit contents (if applicable), installation instructions, and test after installation procedures as delineated in the CDRL.  (CDRL A142)

The Contractor must deliver the updated product baseline on a Compact Disc that includes all products and artifacts for WCRB approved changes concurrent with each delivery of A142.

# Acronyms

AC	Alternating Current

ACF	Area Control Facility

AF	Airway Facilities

AMS	Acquisition Management System

AOR-W	Atlantic Ocean Region – West (INMARSAT)

AOS	Operational Support Service

APML	Associate Program Manager for Logistics

ARP	Aeronautical Recommended Practice

ARTCC	Air Route Traffic Control Complex

ATE	Automated Test Equipment

C&V	Corrections and Verification processor

CAP	Contractor Acquired Property

CCA	Common Cause Analysis

CCB	Configuration Control Board

CDC	Critical Design Considerations

CDRL	Contract Data Requirements List

CFR	Code of Federal Regulations

CI	Configuration Item

CLIN	Contract Line Item Number

CM	Configuration Management

CMP	Configuration Management Plan

COTS	Commercial Off the Shelf

CRR	Common Reference Receiver

CSC	Computer Software Components

CSCI	Computer Software Configuration Item

CPR	Cost Performance Report

CSTP	Contractor Support Transition Plan

CTA	Critical Task Analysis

CWBS	Contract Work Breakdown Structure

DID	Data Item Description

DLIS	Defense Logistics Information Services

DLSC	Defense Logistics Services Center

DoD	Department of Defense

DT&E	Development Test and Evaluation

E&R	Exchange and Repair

ECP	Engineering Change Proposal

EOQ	Economic Ordering Quantity

FAA	Federal Aviation Administration

FAALC	FAA Logistics Center

FAT	Factory Acceptance Test

FCA	Functional Configuration Audit

FCC	Federal Communications Commission

FMEA	Failure Modes and Effects Analysis

FMES	Failure Modes and Effects Summary

FRDF	Facility Reference Data File

FTA	Fault Tree Analysis

GCCS	Ground Communication and Control Segment

GEO	Geostationary Earth Orbit

GFE	Government Furnished Equipment

GFS	Government Furnished Service

GPS	Global Positioning System

GUS	Geostationary Uplink Subsystem

HCI	Human Computer Interface

HE	Human Engineering

HEPP	Human Engineering Program Plan

HFWG	Human Factors Working Group

HMI	Hazardously Misleading Information

HRs	Hazard Records

HWCI	Hardware Configuration Items

HTS	Hazard Tracking System

IATA	International Air Transport Association

IAW	In Accordance With

ICD	Interface Control Document

ICDLS	Interim Contractor Depot Level Support

IDD	Interface Design Documents

INMARSAT	International Maritime Satellite

IOC	Initial Operational Capability

IRS	Interface Requirements Specification

ISP	Integrated Support Plan

kbps	Kilobits per second

L1	Radio Frequency Link 1 (GPS)

L2	Radio Frequency Link 2 (GPS)

L2C	Radio Frequency Link 2 - Civilian (GPS)

L5	Radio Frequency Link 5 (GPS) LCN	LSA Control Number

LNAV/VNAV	Lateral Navigation/Vertical Navigation

LOF	Loss of Function

LOGSA	Logistics Support Activity

LORA	Level of Repair Analysis

LPV	Lateral Precision with Vertical Guidance

LRU	Line Replaceable Unit

LSA	Logistics Support Analysis

LSAR	Logistics Support Analysis Record

MEDLL	Multipath Estimation Delay Lock Loop

MIPS	Master Integrated Program Schedule

MITP	Master Integrated Test Plan

MOP	Minimum Operating Procedure

MPT	Manpower, Personnel, and Training

MSSR	Monthly Schedule Status Report

MTBF	Mean Time Between Failure

NAILS	National Airspace Integrated Logistics Support

NAILSMT	National Airspace Integrated Logistics Support Management Team

NAS	National Airspace System

NCP	NAS Change Proposal

NDI	Non-Developmental Items

NDS	Non-Developmental Software

NGS	National Geodetic Survey

NICS	NAS Interfacility Communications System

NSN	National Stock Numbers

O&M	Operations and Maintenance

OEM	Original Equipment Manufacturer

OJT	On-the-Job Training

PAT&E	Production Acceptance Test and Evaluation

PC	Personal Computer

PCA	Physical Configuration Audit

PCB	Printed Circuit Board

PHMI	Probability of Hazardously Misleading Information

PHS&T	Packaging, Handling, Storage And Transportation

PLCI	Product Level Configuration Index

PM	Periodic Maintenance

PMO	Program Management Office

PNB	Program Notebook

POM	Program Overview Meeting

POR	Pacific Ocean Region (INMARSAT)

PPL	Provisioning Part List

PSAC	Plan for Software Aspects of Certification

QA	Quality Assurance

QA	Qualitative Analysis

QSP	Quality System Plan

R&M	Reliability and Maintainability

RF	Radio Frequency

RFD	Request for Deviation

RFU	Radio Frequency Uplink

RFW	Request for Waiver

RMA	Reliability, Maintainability and Availability

SAE	Society of Automotive Engineering

SACIL	Safety Assurance Configuration Item List

SAPR	Safety Assurance Process Requirements

SAS	Software Accomplishment Summary

SAT	Site Acceptance Test

SCN	Specification Change Notice

SDA	Safety Directed Analysis

SDD	Software Design Documents

SDP	Software Development Plan

SDR	System Design Review

SDRAM	Synchronous Dynamic Random Access Memory

SDRL	Subcontract Data Requirements List

SEMP	System Engineering Master Plan

SEWG	System Engineering Working Group

SGS	Signal Generator Subsystem

SHA	System Hazard Analysis

SIS	Signal in Space

SLES	Second-Level Engineering Support

SOW	Statement of Work

SPIA	Safety Process Input Analysis

SPR	Software Problem Report

SPS	Software Product Specification

SQAP	Software Quality Assurance Plan

SPTD	Supplementary Provisioning Technical Data

SRS	Software Requirements Specification

SSE	Software Support Environment

SSM	System Safety Manager

SSP	System Safety Program

SSPP	System Safety Program Plan

SSPPR	System Safety Program Progress Report

SSWG	System Safety Working Group

STF	Software Test Facility

STP	Software Test Plan

TCN	Terrestrial Communications Network

TIB	Technical Instruction Book

T&E	Test and Evaluation

TPM	Technical Performance Measurement

TPS	Test Program Set

TSO	Technical Standard Order

UOQ	Unit Ordering Quantity

U.S.	United States

USDOT	US Department of Transportation

UTC	Universal Time Coordinated

UUT	Unit Under Test

VDD	Version Description Document

VRTM	Verification Requirements Traceability Matrix

WAAS	Wide Area Augmentation System

WBS	Work Breakdown Structure

WCR	WAAS Change Request

WCRB	WAAS Change Review Board

WHAIL	WAAS HE Action Items List

WIPP	WAAS Integrity Performance Panel

WMS	WAAS Master Station

WRS	WAAS Reference Station

WTMS	WAAS Training and Maintenance System

WUG	WAAS Users Group