## Sheet1
WBS # | Task Name | Person In Charge | Duration (workdays) | Start Date | Predecessor(s) Number (Linked to any other tasks (or start/end of shutdown) | WBS Dictionary (Needed for Level 4 only) | Resources (List Name and % of time) | M&S Costs
1 | Run II Upgrades | Jeff Spalding
1.3 | Stacking and Cooling | Dave McGinnis
1.3.6 | Rapid Transfers | Elvin Harms
1.3.6.1 | Document Fast Transfer scheme |  | 10 |  |  |  | Harms, 20%
1.3.6.2 | Beam Line Regulation
1.3.6.2.1 | Determine magnetic field tolerance |  | 5 |  |  |  | 1 Physicist, 50%
1.3.6.2.2 | Measure power supply regulation |  | 2 |  |  |  | Obie, 80%
1.3.6.2.3 | Improve power supply regulation |  | 20 |  | 1.3.6.2.2 |  | Wolff or Peterson, 30% Obie, 40% Wisner, 60% Bair, 60%
1.3.6.2.4 | Ramp waveform control of AP1
1.3.6.2.4.1 | Build new 465 cards |  | 10 |  |  |  | Electrical Tech., 100% | 16166.6667 | 12000
1.3.6.2.4.2 | Install and commission new 465 cards |  | 5 |  | 1.3.6.2.4.1 |  | 3 Pbar Study Shifts 1 Physicist 1 Electrical Tech.
1.3.6.3 | Software
1.3.6.3.1 | Streamline Sequencer |  | 10 |  |  |  | Harms, 15%
1.3.6.3.2 | 465 card application |  | 60 |  |  |  | 1 Computer Professional
1.3.6.3.3 | Orbit Correction |  | 90 |  |  |  | 1 Physicist, 20% 1 Computer professional, 75%
1.3.6.3.4 | Lattice measurement |  | 90 |  |  |  | 1 Physicist, 30% 1 Computer professional, 100%
1.3.6.3.5 | TBT correction |  | 90 |  |  |  | 1 Physicist, 30% 1 Computer professional, 100%
1.3.6.3.6 | other software |  | 240 |  |  |  | 2 Computer professionals, 50%
1.3.6.4 | Oscillation Feedback and Control
1.3.6.4.1 | MI Injection Damper
1.3.6.4.1.1 | Specify necessary damper voltage |  | 20 |  |  |  | 1 Physicist, 20%
1.3.6.4.1.2 | Determine scope of work |  | 20 |  |  |  | 1 Physicist or 1 Engineer, 100%
1.3.6.4.1.3 | Purchase load switches/power amps | [5 empty] | 1 Engineer
1.3.6.4.1.4 | Specify and fabricate damper pickups |  | 180 |  |  |  | 1 Physicist 1 Engineer 3 techs
1.3.6.4.1.5 | Specify, design, and build low level |  | 240 |  |  |  | 1 Engineer 1 Physicist 1 Electrical tech 1 Computer professional
1.3.6.4.1.6 | Install damper system |  | 20 |  |  |  | 1 Engineer 4 mechanical techs
1.3.6.4.1.7 | Test low level |  | 10 |  |  |  | 1 Engineer 1 electrical tech
1.3.6.4.1.8 | Commission full system |  | 40 |  |  |  | 1 Physicist 1 Engineer 1 technician
1.3.6.4.2 | Accumulator Quad pickup | Nagaslaev |  |  |  |  | 1 Physicist
1.3.6.5 | Commission Fast Transfers |  | 40 |  |  |  | 10 Pbar Study Shifts 10 MI Study Shifts 10 Recycler Study Shifts |  | 1/week for 2 months
1.3.6.5.1 | Diagnostics
1.3.6.5.1.1 | P1, P2, AP1, AP3 53 MHz BPM's |  | 240 |  |  |  | 1 Electrical Engineer, 100% 1 Computer Professional, 100% 2 Electrical techs., 100% |  | $4000/BPM

## Resource list
RESOURCE NAMES
Study Shift Names | Booster Study Shifts
MI Study Shifts
Pbar Study Shifts
Recycler Study Shifts
Tevatron Study Shifts
Generic Resource Types | Administrative Specialist
Computer Professional
Cryo Engineer
Cryo Tech.
Drafter/Designer
Electrical Engineer
Electrical Tech.
ES&H Specialist
Mechanical Engineer
Mechanical Tech.
Operations Specialist
Physicist
Survey Crew
People Names | Adamus M.
Ader C.
Ahn S.
Albergo A.
Albertus M.
Alexahin Y.
Allcorn P.
Allen D.
Allen L.
Anderson J.
Anderson K.
Anderson L.
Anderson T.
Andrews M.
Angelus J.
Ankenbrandt C.
Annala G.
Aponte E.
Arveson D.
Asher T.
Ashmanskas W.
Augustine D.
Averett M.
Baddorf D.
Baginski S.
Bair C.
Balbekov V.
Ball M.
Baller B.
Baltes L.
Barbor M.
Barnes B.
Barnes T.
Bartelson B.
Bauer P.
Becker R.
Benson L.
Berenc T.
Bessert B.
Beutler A.
Bhat C.
Biggs J.
Billenstein B.
Bishofberger K.
Bock G.
Boehnlein D.
Bogert D.
Bohn C.
Bolek B.
Bollinger D.
Bolshakov T.
Bonkalski M.
Bossert R.
Bourkland K.
Boyd D.
Bradley L.
Briegel C.
Broemmelsiek D.
Brooker B.
Brown B.
Brown C.
Brown G.
Brown John W.
Brown Josph D.
Brown R.
Buckley J.
Budlong J.
Bulmahn D.
Burov A.
Busch T.
Butler J.
Butler T.
Cadorna A.
Cahill K.
Cai J.
Cai Y.
Callaghan R.
Camarena B.
Capista D.
Carey D.
Carlson K.
Carmichael L.
Carrier R.
Carrigan R.
Carter M.
Castro C.
Cathey D.
Chamberlain J.
Chase B.
Chaurize S.
Chemiakine A.
Chen D.
Chen Z.
Chester N.
Cheung H.
Childress S.
Chou W.
Choudhary B.
Church M.
Clark E.
Claypool B.
Clemons J.
Cobb D.
Coburn M.
Coleman R.
Compton J.
Conlon S.
Cortez E.
Crabtree P.
Crawford A. C.
Crawford D. J.
Crawford J. L.
Crayton M.
Crisp J.
Cross T.
Cross W.
Crouch R.
Crowell G.
Cullerton E.
Czarapata P.
Darimont D.
Darve C.
DeGraff B.
DeJerld R.
DeRoo L.
Derwent P.
Desler K.
Devoy J.
Dey J.
Dick D.
Dick H.
Dilday M.
Dillow K.
Divelbiss R.
Domann K.
Dombeck T.
Domeier M.
Douglas D.
Doyle R.
Drendel B.
Drozhdin A.
Du Q.
Ducar R.
Durando D.
Dwyer D.
Dymond W.
Edstrom D.
Edwards D.
Edwards H.
Eighnor A.
Erdelyi B.
Evanger B.
Falconer B.
Featherstone J.
Federwitz G.
Feld A.
Felix I.
Fellenz B.
Feyereisen P.
Finstrom D.
Firebaugh J.
Fischler M.
Fisher Q.
Fitzgerald J.
Flora R.
Flores C.
Flores J.
Florian R.
Foley M.
Fomusa J.
Ford R. D.
Ford R. E.
Forester P.
Foster C.
Foster G. W.
Fowler W.
Franck A.
Freeman D.
Frett M.
Fritz B.
Fulgham J.
Ganster G.
Garbincius P.
Gattuso C.
Gelfand N.
Genser K.
Gentry P.
Gerardi M.
Germain Jr. A.
Geynisman M.
Gierhart T.
Giese G.
Glenn R.
Gloor R.
Gollwitzer K.
Gomilar J.
Gonzales A.
Goodwin R.
Gordon M.
Gordon T.
Gounder K.
Gramly K.
Grossman N.
Gurley N.
Gusler H.
Hagler R.
Hamerla T.
Hanna B.
Harcharick S.
Harms E.
Harris D.
Hartman K.
Hauser R.
Hays S.
Heath R.
Heidemann J.
Heikkinen D.
Heinz M.
Hendricks B.
Hendricks T.
Hentges Michael
Hentges Michele
Hibbard R.
Hickey R.
Higgins W.
Hill E.
Hively R.
Holm J.
Holub J.
Howe J.
Hren R.
Hu M.
Hughes W.
Hurd D.
Hurh P.
Hylen J.
Ifversen D.
Ingram V.
Irvin J
Ivanov I.
Ivanov P.
Jach C.
Jackson G.
James C.
Janosi M.
Jarocki S.
Jensen C.
Jensen D.
Johnson Daniel A.
Johnson David E.
Johnson Glenn A.
Johnson Gregory S.
Johnson S.
Johnson T.
Johnstone C.
Johnstone J.
Joireman P.
Juarez F.
Juneau J.
Jurkiw O.
Kallenbach J.
Karns P.
Kasley P.
Kasper P.
Keil E.
Kellett R.
Kellogg K.
Kellogg W.
Kelly F.
Khabibullin T.
Kiemschies O.
Kihlken D.
Kindelberger D.
King C.
Kissel W.
Klebaner A.
Klecka R.
Klen J.
Klepec D.
Koba K.
Kobilarcik T.
Koch K.
Kohler M.
Koizumi G.
Kostin M.
Kourbanis I.
Kowalik C.
Krafczyk G.
Kramper B.
Kriss M.
Kroc T.
Kucera M.
Kuchnir M.
Kufer M.
Kulyavtsev A.
Kuplic M.
Kuropatkine N.
Kurylo P.
Kuznetsov G.
Lackey J.
Lackey S.
Lambertz P.
Landers H.
Lange F.
Langford T.
Larson A.
Larson J.
Lassiter T.
Laughton C.
Lautenschlager G.
Lawrence G.
Lazzara J.
Le H.
LeBeau R.
Lebedev V.
Lebrun P.
Legan A.
Leibfritz J.
Lennox A.
Lentz J.
Lesiak P.
Leveling F.
Lewis R.
Lindenmeyer C.
Linton F.
Lopez L.
Lorman E.
Lucas P.
MacLachlan J.
Makara J.
Malamud E.
Malo C.
Marchionni A.
Marquardt R.
Marriner J.
Marsh W.
Martens M.
Martin E.
Martin K.
Martin W.
Martinez A.
Mau R.
May M.
McClure C.
McCormack J.
McCormick S.
McCrory E.
McCusker-Whiting M.
McDonough K.
McDowell D.
McDowell J.
McGee M.
McGinnis D.
Meadowcroft R.
Meisner J.
Meisner K.
Meyer G.
Meyer T.
Meyhoefer M.
Michals R.
Michelotti L.
Milholland R.
Miller D.
Misek J.
Mishra C. S.
Mitchell F.
Moehs D.
Mohns J.
Mokhov N.
Monningh M.
Moore C.
Moore R. L.
Moore R. S.
Moretti A.
Morfin J.
Morgan J.
Morris D.
Morrison T.
Mraz R.
Mueller W.
Munger R.
Muranyi W.
Murphy M.
Nagaitsev S.
Nagaslaev V.
Nelson J.
Nestander A.
Neswold R.
Neuffer D.
Newhart D.
Nezrick F.
Ng K.
Nicklaus D.
Nicolas L.
Nobrega L.
Norris B.
Nowlin R.
Nylund M.
O’Brien K.
O’Connell J.
Oberholtzer R.
Obrycki M.
Ogert B.
Olesen K.
Olsen C.
Olson M.
Oplt S.
Ostiguy J.
Ostrowski D.
Padilla R.
Panacek S.
Parker A.
Pasquinelli R.
Patrick J.
Payne O.
Pei L.
Pellico W.
Perez R.
Peterman G.
Peterson D.
Petkus M.
Petravik D.
Petrov A.
Pfeffer H.
Piccoli L.
Piekarz H.
Pierce R.
Pirtle E.
Pischalnikov Y.
Plant D. A.
Plant D. R.
Plant Derek
Poll D.
Popovic M.
Popper B.
Pordes S.
Prebys E.
Prieto P.
Pruss S.
Qian Z.
Quinn K.
Raji M.
Rakhno I.
Ranson J.
Rauchmiller M.
Read A.L.
Rebstock R.
Rechenmacher R.
Reehal J.
Reeves S.
Reid J.
Reilly R.
Richardson Darryl S.
Richardson David W.
Riordan J.
Rios F.
Roberts T.
Rock J.
Rohde D.
Romanov G.
Roon K.
Ross G.
Rowe A.
Rucinski F.
Ruffin J.
Russell A.
Rychenkov V.
Sabo J.
Saewert G.
Santucci J.
Sasse M.
Scala R.
Scarpine V.
Schappert W.
Schlabach P.
Schmidt C.
Schmitt D.
Schneider F.
Schoo D.
Schuett J.
Schultz R.
Schupbach B.
Schwartz J.
Secora W.
Sedory P.
Seifrid P.
Seino K.
Semenov A.
Sen T.
Seraphin J.
Shiltsev V.
Shvets G.
Sidorov V.
Sievert K.
Sigmon D.
Simmons J.
Simpson D.
Slaughter A.
Slazyk R.
Sliczniak M.
Smart W.
Smedinghoff J.
Snee D.
Snyder J.
Sondgeroth A.
Soyars W.
Spalding W.
Spencer J.
Stanzil B.
Staples C.
Stazak V.
Stefanski R.
Steimel J.
Stenman D.
Stern J.
Stewart R.
Still D.
Stitts W.
Striganov S.
Sullivan J.
Sullivan T.
Sun D.
Sutherland J.
Syphers M.
Szabo G.
Tan C.
Tariq S.
Tassotto G.
Tennis B.
Theilacker J.
Thompson J.
Ticku J.
Tinsley D.
Todd J.
Tokarek R.
Tollestrup A.
Tomlin R.
Triplett A. K.
Tupikov V.
Urban J.
Valerio L.
Valverde J.
Van Bogaert J.
VanderMeulen D.
VanGinneken A.
Varghese P.
Vargo R.
Villarreal D.
Vincent M.
Vogel G.
Voit C.
Volk J.
Voy D.
Wahl L.
Walker R.
Wallace D.
Waller A.
Walters J.
Walton J.
Wang J.
Warner A.
Waver G.
Webber R.
Weber K.
Wehmann A.
Wendt J.
Werkema S.
Wesseln S.
West R.
White F.
White H.
Wickenberg R.
Wildman D.
Williams K.
Williams T.
Wilson B.
Wilson J.
Wilson P.
Wilson S.
Winterowd L.
Wisner B.
Wolff D.
Worel C.
Worthel B.
Wredling N.
Wu G.
Wu V.
Xiao A.
Xiao M.
Yang M.
Yang Xi
You J.
Yousif A.
Yuan Z.
Zagel J.
Zhang X.
Zifko R. A.
Zifko R. M.
Zimmermann R.
Zingelman T.
Ziomek D.
Ziomek M.
Zuchnik T.
Zuk J.