SESSION: Community Assessments & Rural Resource Teams

(TX Rural Partners, WY Rural Development Council, WA Rural Development Council, NV Rural Development Council)

- Rural resource teams:  Partnerships of trained volunteers that work together to help rural communities identify resources and strategies for locally-executed community development.

  - Potential team members are from:

    - Economic development organizations

    - Health organizations

    - Federal government

    - State government

    - Educational institutions

    - Private sector

    - Non-profit organizations

    - Rural development organizations

  - Past team members have been very positive about the experience!

- Resource team community assessment:  “A community-based planning & assessment process consisting of interviewing a large number of people in the community, recording their suggestions and having a team of specialists write up implementation plans for community use.” –as defined by TX Rural Partners, Inc.

- Someone in the community must serve as the catalyst to set the process in motion.

  - To requests a resource team:

    - In Wyoming for example, the Wyoming Rural Development Council requires a letter signed by the community leader (Mayor, Executive, other) which serves as a contract with the Council.  The letter must include the name & contact information for the community contact, and state that the community:

      - Understands it must provide meals and lodging,

      - Understands it must do all publicity for Listening Sessions, Town Meeting, etc.,

      - Understands it must develop agenda with help of Team Leader,

      - Will plan tour for the team members, and

      - Will provide all arrangements for Listening Sessions

- Benefits of a resource team assessment to community:

  - Affordable assessment process (usually costs ~$1,500 per community; would cost $50K – $75K if contracted to other professional companies)

  - Provides a “mirror look” at a community

  - Beginning steps to strategic planning

  - In-kind contribution can be used as a match for grant applications

  - Report contains a wealth of resources and opportunities for a community

- Resource team planning for a community assessment takes 2 – 3 months.

- The assessment team process:

  - Team of 5-7 resource specialists,

  - Spend 1.5 days in a community,

  - Listening to the community members & asking the 3 questions,

  - (About 20% of the community usually participates in listening sessions and/or interviews)

  - Recording community answers, and

  - Developing major themes.

  - On the last day, the team hosts a town meeting, and

  - Facilitates priority-setting session.

  - The 3 Questions (for all interviews):

- What are the major problems and challenges in your community?

- What are the major strengths and assets of your community?

- What projects would you like to see implemented in your community in the next 2, 5, 10, or 20 years?

- Everyone is asked these questions.  And because some people are not comfortable with responding immediately or orally, people may also submit written questions and comments.

  - Example Agenda:

First Day

10am – 12pm		Team orientation

12pm – 1pm 		Lunch with community team

1pm – 3pm		Community tour

4pm – 5pm		Topic 1 Listening Session

5pm – 6pm 		Topic 2 Listening Session

6pm – 7:30pm		Dinner

8pm – 9pm 		Topic 3 Listening Session

Second Day

6:30 – 7:30am		Breakfast

8am – 9am		Topic 4 Listening Session

Etc…

  - Community determines sectors/ issues for Listening Sessions

- Recommended sectors/ issues

    - Youth

    - Seniors

- Other common sectors/ issues

    - Agriculture

    - Churches

    - Retail

    - Banking

    - Civic Groups

- After all Listening Sessions are complete, the resource team develops the major themes (economic development, housing, aesthetics, youth concerns, zoning, etc.)

- Host Town Meeting

  - Held the last evening of the visit

  - Everyone is invited back

  - Opportunity to thank community

  - Team presents “What was said”

  - Team presents major themes – “What was heard”

  - Discuss “next steps” and stress importance of priority setting meeting

- Final Report

  - Must be original document!

  - Presented to the community 4 – 6 weeks after the visit.

  - Contains Executive Summary, Agenda, Team Members, “What was said”, “What was heard”, and team member reports

- Next Step: Priority Setting

  - After community has had time to read report (approximately 1 month), Team Leader will contact Community Leader to set date for follow-up meeting.

- Some Facts from SRDCs

- Texas Rural Partners:

  - 57 community assessments completed since 1993 (49 completed since 1997).

  - Assessments work for large range of community sizes.  So far community populations have ranged from 595 to 28,562.

- Wyoming Rural Development Council:

  - Assessments began in 2000.

  - 53 community assessments completed with a goal of 60 in 5 years.

  - 285 volunteers have been trained in Wyoming for resource teams.

  - Completed training for 150 volunteers in Montana.

  - Completed training for 120 volunteers in Washington State.

- Washington State Rural Development Council:

  - Assessments began in 2002.

  - Completed 4 team trainings and have scheduled 5th for December 2003 (120 volunteers).

  - Populations range from 4,000 – 12,000.

  - Completed 3 assessments, 4th in Fall 2003, 5th has been requested.

  - Signs of success from 1st community.

- Nevada Rural Development Council:

  - Council formed within last one year.

  - Board planned 19 Listening Sessions for assessment across rural Nevada, and identified site coordinators in each community.

  - Community assessment team traveled over 2500 miles total to 19 communities (3 trips) in 7 days.

  - 424 people attended the meetings (averaging 22 per meeting)