###### ASU-200-03

6/99

QUALITY/RELIABILITY OFFICER

GUIDEBOOK

FEDERAL AVIATION ADMINISTRATION

THIS DOCUMENT IS CONTROLLED ON THE FAA ASU-200 WEB SITE.

IF PRINTED OR COPIED, IT BECOMES UNCONTROLLED AND MAY BE

USED ONLY IF THE USER ASSURES IT CONTAINS THE LATEST  REVISIONS.

TABLE OF CONTENTS

FOREWORD

CHAPTER 1.  GENERAL

SECTION 1  QUALITY STANDARDS

CHAPTER 2.  QRO INITIAL OPERATIONS

SECTION 1  DUTIES

SECTION 2.  REVIEW OF CONTRACTUAL DOCUMENTS

SECTION 3.  DEVELOPMENT OF THE QRO CONTRACT PLAN

SECTION 4.  REVIEW OF CONTRACTOR'S DOCUMENTS

SECTION 5.  DEVELOPMENT OF AUDIT GUIDELINES

FIGURE 1.  TYPICAL KEY EVENTS AND MILESTONES

CHAPTER 3.  RECURRING OPERATIONS

SECTION 1.  AUDITS

SECTION 2.  INSPECTION/TEST WITNESSING

SECTION 3.  OPERATIONS UNDER QUALITY SYSTEMS

SECTION 4.  QUALITY RECORDS AND INDICATORS

SECTION 5.  CORRECTIVE ACTION

SECTION 6.  PROCESSING OF NONCONFORMING SUPPLIES

SECTION 7.  QUALITY RECORDS

CHAPTER 4.  ADMINISTRATIVE DUTIES

SECTION 1.  FIELD CONTRACT FILE

SECTION 2.  CONTRACT PROGRESS REPORTS

SECTION 3.  ACCEPTANCE

FIGURE 2.  INSPECTION REPORT OF MATERIAL AND/OR SERVICES (FORM-FAA-256)

SECTION 4.  PROGRESS PAYMENT REQUESTS

SECTION 5.  CLOSEOUT OF FIELD CONTRACT FILE

SECTION 6.  CONTRACTOR PERFORMANCE EVALUATION

CHAPTER 5.  COLLATERAL DUTIES

SECTION 1.  PROVISIONING CONFERENCES

SECTION 2.  POST-AWARD CONFERENCE

SECTION 3.  FAA TEST AND EVALUATION

SECTION 4.  SUPPORT FOR THE PRODUCT TEAM

SECTION 5.  CONTRACT PROPERTY ADMINISTRATION SUPPORT

SECTION 6.  STRIKES/LABOR PROBLEMS

SECTION 7.  SITE OPERATION

SECTION 8.  DATA COLLECTION/METRICS REPORTING

SECTION 9.  GIDEP SUPPORT

APPENDIX A  Forward

APPENDIX A  Software Quality Assurance (SQA) Model

APPENDIX B  SQA Procedures for Implementing the Model

# FOREWORD

Purpose:  This document is issued to provide guidance to FAA Quality Assurance personnel involved in all quality-related aspects of FAA procurements for material and services.  It is specifically directed to Quality and Reliability Officers and Associate (Alternate) Quality and Reliability Officers of the Quality Assurance Division (ASU-200).

Applicability:  The broad guidelines herein are intended to be applied to a contract to which FAA quality representatives are assigned, regardless of the specific quality system requirements or the material or services procured.  These guidelines are intended to be illustrative/descriptive of the best available practices rather than regimental in content.  This will facilitate an evolving approach to the administration of Quality Assurance within the Quality Assurance Division, (ASU-200) and the Federal Aviation Administration.

Obligation:  In the detailed procedures that follow, actions which are considered essential by the FAA Quality Representatives are distinguished by the use of words of direction, such as “shall” or “is required”.  However, none of the information presented shall be used to impose any requirement on a contractor that is outside the scope, terms or conditions of the contract.  The varied contractual requirements and Integrated Product Team methodologies may require the QRO to tailor his/her methods accordingly.

Distribution:  The document is distributed to each employee of the Quality Assurance Division (ASU-200).  Copies are also available to all FAA Product Team members and FAA Contractors upon request to the Quality and Reliability Officer assigned to the contract involved or to the Manager of the Branch to which the Quality and Reliability Officer reports.

Request for Information and Changes:  Requests for further information or questions relating to this document should be addressed to the Manager, Quality Assurance Division, ASU-200.  Recommended corrections, additions, or deletions should also be sent to ASU-200.

# CHAPTER 1.  GENERAL

## SECTION 1  QUALITY STANDARDS

1.1.1  Background.  As of April 1, 1996, the FAA Acquisition Management System (AMS) was officially initiated to replace the existing Federal Acquisition Regulation (FAR) for future procurements in the FAA.  Under this reformed acquisition system, the general quality policy as stated in FAA Order 4630.8 remains unchanged, i.e., that a quality program/system shall be provided for, and included in, the documentation for National Airspace System (NAS) acquisition, of all systems, equipment, material and services.  Almost concurrent with the planning for the reformed Acquisition Management System, the Office of Acquisitions initiated the use of international quality system standards published by the Office of International Standards (ISO) to replace the prior FAA quality system/program standards considered high level contract quality requirements under the FAR, e.g. FAA-STDs -013, -016, -018.

The ISO standards, referred to in the U.S. as ANSI/ISO/ASQC standards, are applicable as follows:

1.  ISO 9001.  For contracts involving design, development, production, installation and servicing, ANSI/ISO/ASQC Q9001 (or ISO 9001) is applied.

2.  ISO 9002.  For contracts involving production, installation and servicing ANSI/ISO/ASQC Q9002 (or ISO 9002) is applied.

3.  ISO 9003.  For contracts that specify conformance to requirements may be assured by the supplier via final inspection and test alone, ANSI/ISO/ASQC Q9003 (or ISO 9003) is applied.

In addition to the above ISO standards, the FAA will continue to invoke “contractor inspection” system requirements and “standard inspection” system requirements as follows:

4.  Contractor Inspection.  This is the minimum level requirement.  It assigns total responsibility to the contractor for all aspects of product or service quality delivered, with no Government commitment to verify acceptability.  It normally is applied for relatively simple products and/or services that are not critical and which are almost always procured per the contractor’s design.

5.  Standard Inspection.  This is the next higher level requirement.  It requires that a contractor provide an inspection system acceptable to the Government and it provides an opportunity for Government inspection at the source.  It is normally used for equipment and services that are sufficiently complex and/or critical to require more control and confidence regarding the delivered quality than that used for “contractor inspection”.  This quality level is above that expected for the “contractor inspection” system, but less than that required by the “higher level” quality system requirements (ISO 9000 series).

Under this quality requirement, the Quality and Reliability Officer (QRO) assigned to evaluate the contractor’s inspection system for acceptability should select the relevant quality elements from ISO 9001, 9002, or 9003, (e.g., quality records, control and calibration of measuring and test equipment, control of non-conforming material, etc.) appropriate to the operations and technical requirements involved.

1.1.2  Quality Standard Selection.  The initial recommendation regarding the quality standard to be applied to an acquisition contract is provided by ASU-250 SOFTWARE QUALITY and INDUSTRIAL EVALUATION BRANCH, to the Product Team PT in the early planning stages for a program.

1.1.3  Existing FAA Contracts.  All existing contracts shall be monitored for compliance with the existing quality system standard specified in the contract.  Only formal contract changes can impose newer quality standards (e.g., ANSI/ISO/ASQC Q9001).  The contractor may, however, provide a quality system “better than” the quality system specified in the contract provided there is no cost to the Government, and the new quality standard is reviewed by the QRO, PT and approved by the FAA Contracting Officer (CO).

1.1.4  Quality Standard Differences.  There are some significant differences between the FAA Quality System Standards (FAA-STD-013, -016, -018) and ANSI/ISO/ASQC (ISO) Quality Standards worthy of note, as follows:

1.  The control of content to the ISO standards is totally within the purview of the ISO organization, and revision may be expected more frequently than FAA standards.

2.  There is currently no separate ISO software quality system standard.  Rather, it is considered that the total quality system document (e.g., ISO 9001, 9002) covers all products and processes including computer software.  There is, however, an ISO standard, 9000-3, which is designed as a guide for application of the 9001 standard to development of computer software.

3.  The differences between the three ISO quality standards (9001, 9002, 9003) do not depend on complexity or criticality, but rather on the scope of the activities to be provided.  For example, (a) ISO 9001 applies when design and development are involved; (b) ISO 9002 applies for production, installation and servicing (with no design effort involved); (c) ISO 9003 applies when only final inspection and test are required.

4.  The ISO standards are subject to relatively frequent review and revision.  Since revisions are normally identified by date only, it is important to be aware of the revision date of the contractually applicable standard.

5.  The ISO standards, as well as most, if not all, other industry standards are copyrighted.  Accordingly, it is illegal to reproduce them for any reason, without appropriate legal authority.  Copies should be obtained via the CO or the Quality Assurance (QA) Branch Manager.  Contractors or PT members who request copies should be directed to the CO.

# CHAPTER 2.  QRO INITIAL OPERATIONS

## SECTION 1  DUTIES

2.1.1  GENERAL.  The QRO is required to perform the following operations during the initial or "set-up" phase of a contract:

1.  Review contractual documents.

2.  Develop QRO contract plan.

3.  Review contractor documents.

4.  Develop audit guides (where applicable) and related records.

2.1.2  SUPPORT FOR THE PRODUCT TEAM.  A recent FAA restructuring involved the establishment of an Integrated Product Team (IPT) structure that includes PTs within an IPT.  Accordingly, the role of the QRO and Associate QROs may be broadly defined as “the eyes and ears of the PT” in a contractor’s facility.  While the specific QRO duties are identified in this document, the following guidelines clarify the ASU-200 management expectations of this relationship:

1.  The QRO becomes a member of the PT upon being assigned to the contract, which normally occurs immediately after contract award.  Prior to that time, a representative of the ASU-250 SOFTWARE QUALITY and INDUSTRIAL EVALUATION BRANCH, fills that role.

2.  Each member of the PT is a “prime customer” of the QRO staff, with particular emphasis on the CO, Technical Officer (TO) and Product Team Lead (PTL).  All services within the guidelines herein should be provided in the most effective and efficient manner.

3.  Requests for services outside the scope of the Quality function as described herein, should be discussed with the QA Branch Manager and should be provided to the maximum degree possible without detracting from the QRO’s prime responsibilities.

4.  The QRO is required to plan activities based on information provided by the contract and the PT representatives, including the PT representative from ASU-250.

2.1.3  QRO Support/Assistance.  In the event that the QRO requires additional support or assistance, the QRO shall submit a request to the Branch Manager or appropriate support organization.

## SECTION 2.  REVIEW OF CONTRACTUAL DOCUMENTS

2.2.1  GENERAL.  Upon assignment as the QRO to a contract, the QRO will receive from his/her Branch Manager a copy of the basic contract.  The Branch Manager should also identify key support personnel  (e.g., software, hardware, property administration, etc.).  The QRO shall be responsible for obtaining the remaining relevant specifications and documents.  These documents will normally consist of:

1.  The contract schedule.

2.  The equipment specification.

3.  General specifications referenced, e.g., FAA-G-2100 or equivalent.

4.  Technical Proposal (if applicable).

5.  The contractor's quality plans.

6.  Pre-award survey or summary, if available.

7.  Drawings, test procedures, plans and other relevant information.

2.2.2  REVIEW.  Upon receipt of these documents, the QRO shall perform a detailed review for the purpose of verifying their completeness, understanding the requirements, and detecting obvious technical or administrative deficiencies.

1.  Completeness.  The QRO should ensure that the contract package contains relevant documents referenced in the contract.  Documents that are not included should be obtained from the contractor or Government sources listed in the contract.

2.  Understanding.  The primary purpose of the review is for the QRO to gain complete understanding of all requirements of the contract including:

(1)  Equipment and service requirements including site installation and maintenance operations where applicable.

(2)  Type of quality requirements.

(3)  Requirements for documentation and support, such as, instruction books, provisioning documents, and spare parts.

(4)  Delivery Schedule.

(5)  Special provisions included in the contract.

(6)  Provisions for Government-Furnished Property (GFP).

(7)  Contract terms and conditions.

3.  Deficiencies.  Any deficiencies in contractual, design, or technical requirements that are noted during the QROs review should be forwarded to the CO, PTL, TO and the ASU-200 Branch Manager in a timely manner.  Comments should include a full explanation of the deficiencies as well as recommendations.

## SECTION 3.  DEVELOPMENT OF THE QRO CONTRACT PLAN

2.3.1  GENERAL.  After the contractual documents have been thoroughly reviewed, the QRO shall develop a "QRO Contract Plan".  This plan, as a minimum, shall consist of two parts.  One part shall be entitled "Contract Review Record" (CRR) and the other part shall be entitled "QA Plan".  A copy of the contract plan shall be submitted to the Branch Manager; also to PT members (if requested).  A copy of the contract plan shall be retained in the field contract file.

2.3.2  CONTRACT REVIEW RECORD (CRR).  The CRR shall, as a minimum, consist of the following items:

1.  Contractor's name, address, and telephone number.

2.  Contract number, date of award, type, current contract modification number, and current dollar value.

3.  Equipment name and description.

4.  Names and routing symbol information of FAA personnel who participate in the contract, including functions and responsibilities (e.g. TO, CO, Transportation Officer, and other PT members).

5.  Names and other identifying information of the contractor's personnel, including functions and responsibilities, particularly the company official(s) with authority and responsibility for final decisions (e.g., Program Manager, QA Manager, Contract Manager).

6.  Distribution list, including frequency and distribution of quality-generated documents, and the type of correspondence required for the contract (i.e., progress reports, Form FAA-256, etc.).

7.  Delivery and inspection/acceptance information (i.e., FOB point, place of inspection and acceptance, and other related information).

8.  List of major applicable specifications including revision level and date.

9.  List of deliverable contract line items including provisioning requirements with quantities and delivery schedules, as well as documentation which is not a contract item but is required by specification.

10.  Progress payment and contractor's progress report information.

11.  Special packing, marking, and shipping instructions, if applicable.

12.  A milestone schedule or chart that indicates the key activities and milestones of the contract.  The level of detail of this chart will be proportional to the magnitude or nature of the contract.  For relatively simple contracts such as those for commercial off-the-shelf items, the milestone chart may be limited to such events as equipment delivery dates and submission of test procedures.  On more complex procurements the key events may consist of such items as:  beginning and completion of design; procurement (order and receipt) of parts and materials; fabrication of initial units; submission of test procedures and other documents; beginning and completion of test required by contract; beginning of production and shipments of equipment and other deliverable items.  Figure 1 is a relatively complete listing of possible events that may be used as a guide for selecting milestones.  It should be noted that the contractor may have prepared a milestone chart.  If available and adequate, this may be used or supplemented by the QRO.  Other planning documents prepared by the contractor such as flow charts, PERT charts, narrative plans, and production schedules should be obtained if available, and used to prepare the milestone chart.  Depending on their volume and significance, these documents may also be included in the CRR at the discretion of the QRO.

13.  Other relevant information as deemed appropriate by the QRO (e.g. information requested by Product Team members or the Branch Manager).

2.3.3  QA PLAN.  This document shall describe the QRO's overall plan for fulfilling his/her responsibilities.  It shall include, as a minimum, the following sections.  If any of the following elements are not directly applicable to a specific contract, a notation of "not applicable" should be used.

1.  Program overview.  This section shall consist of a brief narrative description of the QA program.

2.  Description of major phases and QRO activities.  This section shall describe the major phases of the contract as shown on the milestone chart (contained in CRR) and shall describe the planned activities that the QRO anticipates related to those phases.  This section should address the QRO’s approach to monitoring the contractor’s performance.  Certain activities, such as development of audit guidelines that are pertinent to the contractor's internal operations should also be addressed.

3.  Audit guides, schedules, and other records.  In this section, the QRO shall describe the planned use of audit guides, schedules, and other types of guidance records.  A listing shall be included of the operations for which the QRO plans to develop audit guides (e.g., receiving inspection, calibration system, PCB flow, packing and shipping, etc.).  The generation of the audit guides shall be prioritized such that the earliest required events (e.g., design, purchasing, etc.) are generated first.  A schedule shall also be included describing the planned frequency for conducting audits.  This section shall also describe any other type of records and forms that the QRO intends to use, such as deficiency reports and rejection notices.  In addition, the QRO shall include the projected schedule for the generation of the audit guides, schedules, and other records.

4.  Special Provisions.  This section should include a description of any special or unusual activities/actions that will be required of the QRO (e.g., site acceptance activities if required by contract).

5.  Manpower Estimates.  This segment shall describe the manpower requirements needed to efficiently implement the QA Plan.  The basic method and assumptions used for this estimation should be detailed.  It is suggested that the estimate be keyed to the milestone chart, though other methods may be utilized if they relate the manpower requirements to specific time frames and activities (e.g., first article and type test witness/monitoring).

2.3.4  SUBMISSION OF QRO CONTRACT PLAN.  The Contract Plan, as described in this section, shall be developed as soon as possible after assignment to a contract, but not later than sixty (60) days unless approved by the Branch Manager.  It is recognized that some portions of the plan will change during the life of the contract (e.g., delivery schedules, manpower estimates).  Accordingly, the QRO Contract Plan should be reviewed annually and updated as appropriate.  Copies of plan updates should be forwarded to the original recipients.

## SECTION 4.  REVIEW OF CONTRACTOR'S DOCUMENTS

2.4.1  REVIEW OF CONTRACTOR'S DOCUMENTS.  After (or concurrent with) the review of the contractual documents and the development of the QRO's contract plan, the QRO shall review a sufficient number of the contractor's documents in sufficient detail to develop a clear understanding of the contractor's operations.  The term "contractor's documents" may include operation procedures, work instructions, quality instructions, workmanship standards, etc., which are applicable to the contract.  The purpose of this review is to develop an understanding, by the QRO, of the contractor's operations, to assure that the contractor's documents do not conflict with the requirements of the contract, and to enable the QRO to develop the necessary audit guides and other records for implementation of the QRO QA Plan.

2.4.2  SPECIFIC DOCUMENTS.  The specific documents that are to be reviewed will depend upon the nature of the contract and the organization of the contractor's operations.  In general, the documents will be evaluated for their adequacy and accuracy in describing those operations, controls, and actions to be performed by the contractor to meet all contract provisions.  The procedures to be evaluated will cover various items such as:  (a) nonconforming materials; (b) government furnished property; (c) complete items inspection and test; (d) corrective action; (e) drawings, documentation, and change control; (f) government source inspection; (g) handling, storage, and delivery; (h) indication of inspection status; (i) materials and material control; (j) measuring and testing equipment; (k) process control; (I) organization, including individuals responsible for the various elements; (m) supplier material; (n) records, and; (o) work instructions.  At a minimum, they should describe the controls provided for all elements described in the applicable quality system standard (e.g., ISO 9001).

2.4.3  GUIDELINES.  The following guidelines apply to procedures review:

1.  The contractor's written procedures need not be contained in a single publication.  They may be in quality or inspection manuals, workmanship standards manuals, test procedures, inspection instructions, work orders or instructions, operating procedures, technical/quality agreements with vendors/subcontractors, engineering manuals, or other documents.  The QRO shall make arrangements with the contractor to obtain copies of the procedures that are deemed relevant.

2.  Upon completion of a document review, it may be disapproved, notifying the contractor in writing of the reasons for disapproval.  For acceptable documents the QRO may issue a letter to the contract file indicating the specific documents reviewed and found acceptable.  Since disapproval is based on a conflict with a valid requirement, any disapproved document must be corrected and resubmitted prior to use on the contract.

3.  Changes to the contractor's written procedures shall be reviewed in the same manner prescribed for the original procedures.

## SECTION 5.  DEVELOPMENT OF AUDIT GUIDELINES

2.5.1  GENERAL.  Audit guidelines shall be developed by the QRO for all contracts, regardless of which quality standard(s) are included.  Development and use of these guidelines is mandatory.  The contractor’s quality plans, procedures and standards should be used as a basis for developing the guidelines.

2.5.2  PROCEDURES.  The QRO shall break down the requirements in the contractor's quality plan (e.g., Quality Control Program Plan (QCPP), Quality Control System Plan (QCSP), Computer Software Quality Program Plan (CSQPP), or Quality System Plan (QSP)) into the form of guidelines.  These guidelines shall be in the form of checklists of characteristics that describe each of the contractor's specific commitments to be verified by the QRO.

1.  The characteristics shall be defined to the degree necessary to confirm acceptability of the contractor's process and to adequately describe the process for evaluating each operation, and each area to be audited.

2.  When appropriate, the plant location(s) at which the characteristics in the guideline will be observed shall be selected, and such locations shall be recorded on the guidelines.  For this purpose a detailed plant layout should be obtained from the contractor for each of the facilities involved.

3.  The audit frequency shall be identified for each guideline.

4.  A Quality Deficiency Report (QDR) should be used as a vehicle of notification to the contractor of any discrepancies found during the performance of scheduled or unscheduled audits.  Other comparable means may also be used.  These reports will be sequentially numbered for reference.

### FIGURE 1.  TYPICAL KEY EVENTS AND MILESTONES

DESIGN

Preliminary System Design	Interface Requirements

Electrical/electronic Design	Design Data

Mechanical Design	Design Review

Printed Circuit Board (PCB) Design	Site Design

Unit Design	Design Specifications for Subcontractors

Final System Design

FIRST UNIT PROTOTYPE PRODUCTION

Breadboards	Parts/Materials

PCB Fabrication & Assembly	Long-Lead Items

Unit Fabrication & Assembly	Subcontracted Items

Assembly Fabrication & Assembly	System Integration

System Fabrication & Assembly

DOCUMENTATION

QC Plan	Final Instruction Book Review

Test Plan	Printed Instruction Books Available

Design Qualification Test Procedures	Provisioning Documentation

Production Test Procedures	PERT Reports

Type Test Procedures	Management Reports (Status, Cost, etc.)

Reliability Demonstration Procedures	Installation Drawings

Maintainability Demonstration Procedures	Construction Drawings

Site Test Procedures	Reliability Plan/Reports

Factory Acceptance Test Procedures	Maintainability Plan/Reports

Instruction Book Manuscript Plan	Training Manuals

Instruction Book Validation Plan	Specifications

Instruction Book Draft Manuscript	As-Built Drawings

Instruction Book Camera Copy	Interface Documents

TEST

Design Qualification Tests 	Factory Acceptance Tests

Production Tests	Site Acceptance Tests

Type Tests	Unit Tests

Contractor Preliminary Tests	Assembly Tests

Reliability Demonstration	System Tests

Maintainability Demonstration	Vendor Tests

FIGURE 1.  TYPICAL KEY EVENTS AND MILESTONES continued

PRODUCTION (AFTER FIRST UNIT PROTOTYPE)

Pre-Production Planning	Test of Production Units

Design Release to Production	Acceptance of Production Units

Parts/Material	Delivery of Production Units

Fabrication of Production Units	Site Installation

Assembly of Production Units	Delivery of Spares

Subcontract Items

OTHER

Provisioning Conference	Training

Site Preparation	Government Furnished Property

Support after Delivery (Engineering/maintainability)

COMPUTER SOFTWARE

System Development Plan	Integration Testing

Computer Program Functional Specification	Acceptance Testing

Program Design Specification	Computer Software Quality Program Plan

Software Coding	System Testing

System Test Plan	Software Testing

Module Testing	Software/Hardware Integration

Subsystem Testing	Software Programs (Tapes, Cards and Listings)

Software Design Data (Flow Charts, Table Design, etc.)

SOFTWARE INSTRUCTION BOOKS

Operator’s Manual	Programmer’s Reference Manual

User's Manual	Utility, Test & Maintenance Manual

# CHAPTER 3.  RECURRING OPERATIONS

## SECTION 1.  AUDITS

3.1.1  GENERAL.  Audits are scheduled formal reviews, examinations, and verifications of activities and operations, which affect the quality of products, processes or services.  They provide a means for assuring compliance with contractual requirements.  Audits also provide a means for evaluating the effectiveness of the overall program, identifying areas in need of improvement, and verifying the results of improvements instituted.  The scope of auditing required varies with the stage of the contract, type of contract and level of confidence developed from previous audits.

3.1.2  AUDIT PERFORMANCE.  The QRO shall perform audits in accordance with the schedule and audit guidelines developed for inclusion in the QRO QA Plan and the following guidelines:

The QRO should verify that:

1.  The audit schedule and details are documented.

2.  Audits are scheduled at an adequate frequency.

3.  Records reflect compliance with schedules.

4.  Records/reports of audits are appropriately documented.

5.  Description of complete corrective action is documented.

6.  Corrective action is effective.

7.  Follow-up audits are accomplished to verify effectiveness of corrective action.

8.  Reports are distributed to appropriate personnel.

3.1.3  AUDIT LOCATIONS.  Audit locations shall be established to verify the implementation of the Contractor’s Quality Program and to evaluate the acceptability of the product and processes.  The number of audits and audit locations shall be adequate to separate the contractor’s activities into manageable increments.  The locations selected should provide the opportunity to verify contractor performance for compliance with all contractual requirements.

3.1.4  AUDIT FREQUENCY.  The frequency of audits shall be determined by the QRO and should depend on the activity of the affected area and the findings of previous audits.  Areas found to have major discrepancies or numerous minor discrepancies, may be audited more frequently and in greater depth, and then should be re-audited to verify the effectiveness of contractor corrective action.  The frequency and/or depth of an audit may be reduced in areas where the findings warrant such.

3.1.5  AUDIT RESULTS.  When contractor corrective action is found to be ineffective, the QRO may, as FAA program interests warrant, increase the amount of surveillance over the contractor’s quality operations and also increase the amount and intensity of direct inspection and test witnessing.  Conversely, the amount and intensity of FAA’s verification operations should be reduced when quantitative and qualitative data warrants.  They may also be temporarily terminated and/or acceptance withheld when the contractor is particularly deficient in taking required corrective and/or preventive action.

## SECTION 2.  INSPECTION/TEST WITNESSING

3.2.1  GENERAL.  The primary responsibility for inspection and test of equipment, material and services rests with the contractor.  However, it is necessary for the QRO to verify and validate the effectiveness of the contractor’s quality system, operations, and the acceptability of the products being submitted by performing some degree of inspection and test witnessing.

3.2.2  INSPECTION.  Inspection is the examination of supplies or services (including when appropriate, raw materials, components, intermediate assemblies, software products, etc.) to determine whether they conform to contract requirements.  It is used in conjunction with testing and auditing to evaluate overall contractor performance on a contract.  The QRO shall select those characteristics to be inspected depending on importance, previous findings, and/or specific contract requirements.

3.2.3  TESTING.  Testing is a means of determining the performance of a product (software or hardware) in relation to requirements.  When a contract requires the use of FAA approved test procedures the QRO shall verify that the tests are conducted in accordance with the approved procedures.  The QRO shall examine the test equipment that is used during contractually required testing and ascertain that the test equipment is calibrated in accordance with contract requirements.  Additionally, the QRO should assure that the test equipment is in accordance with, or equivalent to, that specified in the proper revision of the test procedure.  The QRO will determine whether a test has been successfully completed (i.e., the hardware/software under test has either passed or failed).  The QRO may allow a test to be resumed at an intermediate point, rather than being restarted, depending on the circumstances of the test, the test discrepancy, and/or the contractor's corrective action.  In every case however, the contractor may continue unofficial testing at his own risk.  The Test Director (TD), and/or TO, and the CO, should be advised of the status of tests and the contractor's actions resulting from a test failure, when requested.

3.2.4  CLASSIFICATION OF TESTS.  There are five general categories of tests identified in specification FAA-G-2100.  The test categories that apply will be as stated in the contract and/or specifications.  The categories are as follows:  Contractor's Preliminary Tests, Design Qualification Tests, Type Tests, Production Tests, and Federal Communications Commission (FCC) Type Acceptance and Registration Procedures.  When specified, Reliability and/or Maintainability Demonstration Tests shall also be conducted.

1.  Contractor's Preliminary Tests.  Preliminary tests shall be performed on one production equipment or on one prototype model as specified in the contract.  The contractor's preliminary test does not satisfy the requirement for performing the other classes of tests required by the contract, equipment specification or general specifications, and are not normally witnessed by the QRO.  Reliability, Maintainability, and FCC Type Acceptance and Registration Procedures are not normally required to be performed as part of the contractor's preliminary test program.  Before notifying the Government that the initial production items are ready for inspection and official test, the contractor shall have completed all required contract requirements associated with preliminary testing.

2.  Design Qualification Tests.  Design qualification tests, as required by contract and/or specification, shall be made on one of the first regular production units normally selected by the QRO.  These tests generally include rating verification on parts and materials, other general specification tests, and design qualification tests required by the equipment specification.  These tests shall be performed in accordance with FAA approved test procedures.

3.  Type Tests.  Those tests specified as type tests in the equipment specification shall be made on selected regular production units.  The equipment to be delivered shall be assigned numbers, as required by the contract, in the order of reaching the stage of completion and readiness for testing.  Using these numbers, the equipment will be divided into groups.  The quantity of equipment within each type test group is determined by the contract.  Selection of equipment for type test within the group shall be made by the QRO.  When selecting the type test unit, the QRO shall consider all pertinent information.  These tests shall be performed in accordance with FAA approved test procedures.  Release for delivery of units in each type test group shall be in accordance with contract requirements.  This issue is normally covered in general specifications, e.g., FAA-G-2100.

4.  Production Tests.  Production tests, as specified in the contract, shall be performed on each production item.

5.  Federal Communications Commission (FCC) Type Acceptance Procedures.  Where contractually applicable (typically RF radiating equipment), the first production equipment shall be subjected to FCC Type Acceptance procedures in accordance with FCC rules and regulations.  In addition, during the life of the contract, the contractor shall comply with FCC regulations in connection with any approved changes made to production items that are relevant to the FCC Type Acceptance.

3.2.5  QRO COTS/NDI CONSIDERATIONS.  The contractors Software QA program must also ensure the quality of non-developmental software (NDI).  This is software that may or may not be developed under the current contract.  The following definitions apply to this paragraph:

1.  Commercial-off-the-shelf (COTS).  Items or equipment, which can be purchased through commercial retail or wholesale distributors as is (for example, equipment that is available as a cataloged item).  Within this document, COTS equipment is a subset of Non-developmental Item (NDI), but is excluded from performance requirements specified herein.

2.  Developmental Item.  Item of supply, not previously available, developed uniquely to meet the requirements of a specific procurement contract and/or equipment specification.

3.  Modified COTS.  COTS equipment that has been modified to meet functional requirements.  Within this document, Modified COTS equipment is a subset of Non-developmental Item (NDI) and shall meet the performance requirements for NDI.

4.  Non-developmental Item (NDI).  NDI equipment can be COTS, modified COTS, or previously developed.  NDI shall be defined as any one of the following:

(a).  Item of supply that is available in the commercial marketplace (COTS).

(b).  Previously developed item of supply that is in use by a department or agency of the United States, a state or local Government, or a foreign Government with which the United States has a mutual defense cooperation agreement.

(c).  Item described above that requires only minor modification to meet the procuring agency's requirements (includes Modified COTS).

(d).  Item currently being produced that does not meet the above requirements solely because it is not yet in use, or not yet available in the commercial marketplace.

# 3.2.5.1  QRO Surveillance Guidance.  The responsibility for assuring that NDI software meets requirements is assumed by the organization that furnishes it.  When the government furnishes NDI software, unless otherwise specified in the contract, the contractor has no responsibility to assure the functionality of the furnished software.

When government furnished software is involved, the QRO should perform a visual inspection and examination of the software package and documentation upon receipt.  This inspection should consist of kind, count, and condition, or any other criteria that would insure the item specified is received in acceptable condition

The quality of all software must be verified.  At a minimum, the QRO should raise any concerns or issues with the PT and stress the importance of verifying the functionality of the software.  Abnormally high failure rates determined during operation and/or use will require an in-plant quality evaluation and report by the QRO.

When the contractor furnishes COTS/NDI software, the responsibility for the quality of the software lies with the contractor.  When monitoring contractor furnished COTS/NDI software, the QRO should consider the following points.  The COTS/NDI software may be susceptible to lower quality from “rush-to-market” pressures.  In addition, there may not be any source code or test documentation available for inspection.  Therefore, COTS/NDI software must be verified to show that it works in accordance with the requirements.  If COTS/NDI software is integrated with developed software, the contractor sometimes develops code to integrate or interface the COTS/NDI software with the developmental software.  This integration code is sometimes referred to as glue code.  Glue code should be developed to the same standards as the current developmental software.

Software that is re-used without modification (i.e., developed for an earlier contract) may have been developed under different standards or documented in a different manner or to a different Data Item Description (DID).  Therefore, it is important for the QRO to assure that this software is controlled in accordance with current contract requirements.  If reuse software requires modification, it should be documented and controlled by current contract requirements for developmental software.

Whether furnished by the contractor or government, if COTS/NDI products are intended to be used as part of a developed item or in an environment different from that for which it was designed, the contractor shall demonstrate that the COTS/NDI products operate as part of the developed item.  This product must be demonstrated to operate in the environment specified for use as required by the contract.  Modified COTS/NDI shall also be demonstrated to comply with the specified performance criteria in the contract.  These demonstrations should be included in the test plan and test procedures for the contract.

3.2.6  CONTRACTOR INSPECTION.  This condition places total responsibility for delivery of acceptable product or services on the contractor and normally does not require QRO involvement.

3.2.7  STANDARD INSPECTION OF FAA PRODUCTS.  Under “standard inspection”, the QRO is required to verify that the contractor has an inspection system acceptable to the Government.  In this situation, the QRO shall use some of the same tools and techniques used for a “high level” quality program, i.e., audits, inspection, test witnessing, to verify the acceptability of the inspection system and the products and services provided.  When this requirement is applied to “Off-the-Shelf” equipment, documents used for inspection/test will be those developed by the manufacturer, e.g., manufacturer’s catalogs and instruction books.

SECTION 3.  OPERATIONS UNDER QUALITY SYSTEMS

3.3.1  GENERAL.  The following methods shall be used for contracts specifying ISO-9001 Quality System Plan (QSP) or FAA-STD-016 Quality Control System Plan (QCSP) type requirements.  The QRO shall assure that the detailed procedures, including all changes thereto, which are released to implement the QSP/QCSP, do not conflict with the requirements and commitments in the contract.  This will necessitate a review of these documents before or after release.  Arrangements for these reviews should be made between the QRO and the contractor’s QA Manager.

3.3.2  METHODS.  The following methods apply:

1.  The QRO shall perform independent audits of the Contractor's compliance with his own systems and procedures.

2.  The QRO's own product verification operations (inspection and test witnessing) shall be utilized as a final means of evaluating the effectiveness of the contractor's quality system and its implementation by the personnel assigned.  This operation is vital for the QRO since it is possible that the system and records may be acceptable, but if the personnel or equipment involved are ineffective, the product could be unacceptable.  In this regard, any product defect may be considered as a possible "system" failure in that it was not prevented, nor detected by the contractor's organization.  In this case, the contractor's corrective action must include:

(a)  Correction of the product involved.

(b)  Screening of all products potentially defective in a similar manner.

(c)  Action to prevent recurrence of the deficiency, including detection if it does exist.

3.  The QRO should take advantage of contractor collected data, such as quality indicators, detailed inspection records, and audit reports, to the extent practicable.  This data, along with QRO collected data, will be used to determine which areas or operations indicate unsatisfactory conditions or trends and, therefore, are in need of corrective action.

4.  After identifying those conditions requiring correction, the QRO should review the contractor's recorded actions to evaluate their logic and effectiveness.  Action to preclude repetition as well as screening action (inspection and/or test) for products that may have passed through with undetected defects should be indicated in the records.

5.  In addition to reviewing the records of action taken, the QRO should make independent observations to verify that the action was implemented as recorded.  The QRO should also verify whether the action was effective in precluding further deficiencies and recovering those that may have passed improperly before the screening.

3.3.3  TECHNIQUES.  The following techniques apply:

1.  The QRO shall start with sufficient observations to verify that the Contractor is complying with the documented system and procedures.  This may initially involve a review of relatively large numbers of such items as drawings, purchase orders, standard repairs, or the first run of printed circuit boards.  The QRO should then reduce the amount of direct verification observations as confidence is developed, based on the QRO's and the contractor's quality records.

2.  Regardless of the level or amount of verification performed by the QRO, most of that effort shall be devoted to verifying the acceptability of the major characteristics of the system, procedure, product or test involved.

3.  The QRO shall maintain sufficient records necessary to make objective decisions regarding quality and variations in the amount and intensity of future FAA observations and inspections.  These records shall include corrective action requests and responses.

3.3.4  OBSERVATIONS.  Consistent with the methods and techniques described above, the QRO may use sampling techniques in making observations for verification purposes.  For this purpose, reference may be made to ANSI/ASQC 21.4-1993, or other reference documents.  The Acceptable Quality Level (AQL) shall reflect considerations of the criticality of the items/ characteristics involved.  Any defective items/defects found using a sampling plan, even those within the acceptance number, must be repaired or replaced in accordance with procedures for non-conforming material.  When the number of defective items/defects in the sample exceeds the acceptance number, the entire lot should be rejected and returned to the Contractor for appropriate corrective action.  In those cases where sampling inspection is contractually required, action shall be taken as prescribed by the contract.

3.3.5  DESIGN REVIEW MEETING ATTENDANCE.  The QRO should attend design review meetings to the extent that the QRO workload permits, in order to understand design concepts and intentions, and to be aware of and evaluate commitments (i.e., action items, etc.).  As a minimum, the QRO should review the minutes of the meetings.  The attendance/review is intended to monitor timeliness of action taken by both the FAA and contractor.

3.3.6  OPERATIONS UNDER COMPUTER SOFTWARE QUALITY PROGRAM PLAN.  The basis for the QRO’s software quality program is the ASU-200 “Software Quality Assurance (SQA) Model” (reference Appendix A), and its associated procedures for implementation (reference Appendix B).  The QRO shall describe in the QA Plan section of the QRO Contract Plan the methods to be employed in assuring the goals of the Model will be met.  These methods include QRO activities such as:  auditing of the contractor software development and SQA practices, evaluation of contractor processes, review of software documentation, inspection of software products, and the evaluation of metrics as they relate to the Process Area (PA) of the Model.

The phased approach to the development of computer software should be considered when developing the software quality program.  The QRO QA Plan will specify the activities to be accomplished for each phase of the development effort (requirements, design, coding, test) as described by the Model Process Areas.  It should be noted that many of the Model Process Areas are phase independent and apply to the entire development life cycle.

1.  Software vs. Hardware Operations.  In-process evaluation of computer software involves a variety of QRO activities and contractor products.  The development of quality computer software is dependent largely on the contractor’s internal processes.  The QRO activities should primarily focus on process adequacy and compliance, preventive action and corrective action.

2.  Terminology.  In order to assure a common understanding of terms used in computer software, it is necessary that a common reference be used.  IEEE, STD 729, entitled “A Glossary of Software Engineering Terminology” is the standard prescribed, unless otherwise specified in the contract.

3.3.6.1  SUPPLEMENTAL GUIDELINES FOR SOFTWARE QUALITY ASSURANCE (SQA) PROCESSES.  Detailed instructions, sample work products and generic audit guides are located in the ASU-250 Toolbox.  The Toolbox will be maintained and updated to include current information.  To access the ASU-250 Toolbox on the Internet website go to the ASU Home Page and select ASU-200, then select ASU-250 Toolbox.  Contact the ASU-250 SOFTWARE QUALITY and INDUSTRIAL EVALUATION BRANCH for more information on Software Quality Assurance and the Toolbox.

## SECTION 4.  QUALITY RECORDS AND INDICATORS

3.4.1  GENERAL.  Quality indicators are data items that can be used as input for decisions pertaining to the acceptability of the product and the quality system.  These can take the form of, but are not limited to, QRO and/or contractor data such as audit reports, trend charts, and records of inspections and test witnessing.

3.4.2  AUDIT RECORDS.  As a quality indicator, audits should provide an evaluation of an area, operation, process, or product.  Audits are intended to determine the degree to which the contractor is complying with quality or other applicable procedures.  The number and severity of the discrepancies should be recorded with sufficient descriptive detail and should be considered when evaluating the effectiveness of contractor control.

3.4.3  TREND CHARTS.  Trend charts provide a graphic presentation for evaluating the effectiveness of the contractor's quality program.  Trend charts should provide an indication of the present quality level in comparison with past periods.  A continuous and/or significant increase in the number of defects indicates that the quality of a process or product is deteriorating.  A steady, but unacceptable level indicates that the contractor's process may be out of control and/or their corrective action may be ineffective.

3.4.4  RECORDS OF TESTS OR INSPECTIONS.  Records of contractor and/or QRO tests or inspections provide a database for evaluation of the contractor's overall control of operations, processes, or product characteristics.  Effective control generally dictates that items should not reach inspection or test with existing discrepancies.  Items reaching this stage with discrepancies may indicate inadequate or ineffective control.

3.4.5  FIELD FAILURE REPORTS.  Upon receipt of a field report, the QRO shall ensure that the contractor takes appropriate steps to investigate the cause of failure and take appropriate corrective action.  The QRO may need to perform an audit, review, examine, or reevaluate the cause of the failure, to ensure the removal of all existing deficiencies and prevention of future ones.

## SECTION 5.  CORRECTIVE ACTION

3.5.1  GENERAL.  Any breakdown in the contractor's quality system requires the QRO to assure that product quality is not compromised.  The contractor is then required to correct defects and deficiencies as well as eliminate the root cause(s) in the system.  Corrective action shall be requested by one or more of the following methods and normally in the sequence listed, depending upon the frequency and significance of the defect or deficiency:

1.  On-the-spot corrective action requesting the responsible contractor’s personnel to eliminate the deficiency(ies) and cause(s).  A written record of these requests shall be maintained in the QRO file.

2.  A Quality Deficiency Report (QDR) initiated to notify the contractor’s quality management in writing of the deficiency(ies) found and the requirement for corrective action.

3.  A written notification escalated to the contractor's management requesting immediate correction of causes for documented deficiencies.

4.  Recommendation made to the Contracting Officer (in coordination with the PT) that the contractor be notified that, pending receipt and acceptance of contractor's proposed corrective action, acceptance of end items of the contract may or will be withheld.  The QRO shall inform his/her Branch Manager before proceeding with this step.

3.5.2  SUBCONTRACTS.  Subcontractors are considered an extension of the prime contractor.  Accordingly, when deficiencies are detected in subcontractor products or processes, the QRO shall inform the prime contractor of the circumstances and request the prime contractor to take immediate action with the subcontractor.

3.5.3  NONCONFORMING SUPPLIES.  Contracts establish technical requirements for supplies through reference to plans, drawings, specifications, purchase descriptions, etc..  Supplies that depart from these requirements are termed "nonconforming".  During the manufacture of supplies for sale to the Government, the contractor is permitted to establish dimensions, tolerances, test limits, and process or other controls which are either more stringent than required by contract or not specifically covered by contract.

1.  The contractor is solely responsible for the control of nonconforming supplies intended for use on Government contracts.  This control involves adequate identification, segregation (to prevent unintended use), and disposition by authorized personnel.

2.  Repeated offering of nonconforming supplies, including those with minor defects, should be discouraged decisively by appropriate actions such as requiring corrective action and/or rejecting the supplies.

## SECTION 6.  PROCESSING OF NONCONFORMING SUPPLIES

3.6.1  GENERAL.  The final decision regarding acceptance of nonconforming supplies is solely the prerogative of the Government.

1.  Major Nonconformances.  Major nonconformances (includes all nonconformances except those defined under minor nonconformances) are those which are likely to result in failure, or to reduce materially the usability of the items or services.  Major nonconformances may be accepted by the CO, in coordination with the PT.  Such acceptance will be based upon information furnished by the contractor, by the TO and, as appropriate, by the QRO.  The submission of a formal request to the CO, with appropriate recommendations by the QRO, will be as prescribed in the contract and related documents.

2.  Minor Nonconformances.  Minor nonconformances are nonconformances that do not adversely affect safety, durability, reliability, performance, interchangeability of parts or assemblies, maintainability, weight (where weight is of significance), or any other significant objective of the items or services, and do not increase price or affect delivery under the contract.  This shall be made clear to the contractor at the time that minor nonconformances are accepted.  Minor nonconformances may be approved by the QRO in accordance with the contract clause and/or letter of designation.  Prudent judgment shall be exercised when accepting a minor nonconformance.  If in doubt about its significance, the matter should be coordinated with the CO, and/or other members of the PT as appropriate.  The approval/disapproval action shall be documented.

3.6.2  PARTICIPATION IN MATERIAL REVIEW BOARD.  Normally the QRO does not participate as a member of the MRB.  However, when considered to be in the best interest of the Government, the QRO may participate as a non-voting member of the group.

3.6.3  MATERIAL REVIEW BOARD (MRB).

1.  The results of MRB actions will be processed by the QRO when:

(a)  it is considered to be in the best interest of the Government as determined by the CO, in coordination with the PT,

(b)  nonconforming materials are processed in the format prescribed by the contract (e.g., deviations/waivers),

(c)  the contractor establishes and implements the written MRB procedures acceptable to the QRO,

(d)  the contractor provides complete supporting documentation of the MRB action,

(e)  the contractor's personnel are fully knowledgeable of product technical and quality requirements when participating in the MRB.

2.  MRB actions should not be used by the contractor as a procedure for continued and repetitive submission of nonconforming supplies.  The QRO shall discourage the repeated tender of nonconforming supplies or services, including those with only minor nonconformances, by taking the appropriate action, such as rejecting the nonconforming supplies or services, documenting the contractor's performance record and requiring appropriate corrective action.

3.  The QRO shall periodically audit the MRB corrective action and disposition system for nonconforming material for compliance with contract requirements and to ensure system effectiveness, in the normal QRO audit process.

3.6.4  SUBCONTRACT OR SUPPLIERS NONCONFORMANCE.  Unless otherwise specifically authorized by contract, subcontractors' and other suppliers' requests for acceptance of nonconformance must be submitted to the FAA after approval by the prime contractor.

3.6.5  REQUEST FOR DEVIATION WAIVER.  It is the contractor's prerogative to submit requests for deviation/waiver to the CO.  The contractor must furnish a copy of the request to the QRO.  Pertinent comments or recommendations to the CO, concerning the request shall be made by the QRO.  In unusual circumstances, it may be to the Government's best interest to consider acceptance of nonconforming supplies even though the contractor has not elected to submit a request for  their acceptance.  For example, if the raw material is Government furnished and is highly expensive, and the contract is Cost-Plus-Fixed-Fee (CPFF), the contractor may have little incentive to submit a Request for Deviation/Waiver.  In such cases, the QRO should notify the CO and request appropriate instructions.

3.6.6  PREPARATION OF REQUEST FOR DEVIATION/WAIVER.  A request for acceptance of a nonconformance is prepared by the contractor on his own form or letterhead, unless specific forms are prescribed for use in the contract documents.  A subcontractor-initiated request must be thoroughly evaluated and approved by the prime contractor.  Only authorized prime contractor personnel are permitted to formally submit a copy of the request to the QRO.  If the request format is not included in the contract requirements, the QRO should recommend to the CO the following information, as a minimum, be requested from the contractor.

1.  Name and address of contractor, or if applicable, subcontractor.

2.  A request number, such as a serial number starting with "1" on each contract, preceded by contract number (i.e., FA70WA-0000-1).

3.  Complete identification information, such as:  (a) contract number; (b) part name and number including revision date; (c) specification or drawing number including revision date; and (d) lot, model, and/or serial numbers.

4.  Quantity of nonconforming items.

5.  Details of each deficiency with respect to the technical requirements, including a statement of the effect on other areas of consideration.  Recurrence data for each deficiency also should be provided.  If appropriate, marked drawings should also be included.

6.  Reason for submission of request.

7.  Corrective action taken to prevent recurrence, including effective date and/or serial number of equipment, whichever is applicable.  If prevention is impossible, state reasons, including action taken to reduce the probability of recurrence.

8.  Effect on contract price, delivery schedule, and other contract requirements.

9.  If initiated by a subcontractor or other supplier, a statement by the prime contractor agreeing to the need of the deviation/waiver.

10.  Signature and title of authorized contractor representative.

3.6.7  PROCESSING OF REQUEST FOR DEVIATION/WAIVER.  Upon receipt of requests for deviation/waiver from a contractor, the QRO shall:

1.  Assure that nonconforming supplies have been properly identified and segregated.

2.  Review the request for deviation/waiver to assure all prescribed information is complete and accurate.

3.  Assure that the reported corrective action has been, or will be taken to correct and prevent recurrence of conditions causing the need for deviation/waiver.

4.  Contact the CO by telephone when expediting of the request is considered to be in the best interest of the Government.  If verbal approval is received, the CO must subsequently confirm such approval in writing.  Pending receipt of the written confirmation, the details, including the name(s) of individual(s) authorizing the approval, shall be documented on the request and later in the Progress Report.

## SECTION 7.  QUALITY RECORDS

3.7.1  GENERAL.  The QRO QA Program should provide for the accumulation and maintenance of documented objective evidence gathered during inspection, test witnessing and audits of the contractor's quality system and the product.  Maintenance of adequate records is necessary in order to provide for continuity in the day-to-day operations, and to provide a database upon which quality decisions can be made.

3.7.2  TYPES.  Records can include, but are not limited to, test results, audit data, QDRs, inspection data, and any other information deemed necessary by the QRO.

3.7.3  MAINTENANCE.  Normally, records will be maintained until the CO officially closes out the contract.

3.7.4  AUDIT RECORDS.  Audit records should include:

1.  The area or quality control system element to be checked.

2.  The audit guide identification.

3.  The frequency and schedule for making observations with the audit guide.

4.  The facility(ies) at which the observations will be made.

5.  The facility layout location(s) at which the audit guide will be used.

6.  An indication of completion, including the name of auditor and date.

7.  The number of observations and discrepancies observed.

8.  The number and date of "QDRs" on which the deficiencies observed were reported to the Contractor and a report of corrective action.

3.7.5  ADDITIONAL RECORDS.  Additional records desired by the QRO may be developed and utilized.  These records should be described in the QRO Contract Plan.  All records must be maintained including records with negative findings.

3.7.6  DISPOSITION.  Upon closeout of the contract, the QRO shall request disposition in accordance with Chapter 4, Section 5.

# CHAPTER 4.  ADMINISTRATIVE DUTIES

## SECTION 1.  FIELD CONTRACT FILE

4.1.1  GENERAL.  The FAA QRO shall establish a contract file upon receipt of the contract package.  Initially, the file shall contain, as a minimum, a copy of the contract with all modifications, drawings, applicable specifications, relevant correspondence, etc..  Subsequently, throughout the contract administration phase, the field contract file will be maintained current to clearly reflect:

1.  The QRO developed "QRO Contract Plan", as prescribed in Chapter 2.

2.  Historical objective evidence relative to the application of the QRO QA Plan.

3.  Copies of relevant correspondence, (Form FAA-256, progress reports, telephone conversation records, minutes of in-plant FAA/contractor meeting, and recommendations to CO and TO).

4.  Audit guidelines and related records.

5.  Other relevant material as dictated by good management practices.

4.1.2  COMMUNICATION INTERCHANGES.  Copies of relevant correspondence from the Contracting Officer to the contractor will be forwarded to the QRO through prescribed channels.  Likewise, all correspondence generated by the QRO will be prepared and distributed in accordance with instruction prescribed herein.  Typical correspondence generated by the QRO is discussed in detail in subsequent parts of this chapter.  This correspondence includes:

1.  Progress reports.

2.  Special reports, interim reports, information/alert bulletins.

3.  Trip reports.

4.  Acceptance/rejection reports, Form FAA-256.

5.  Telephone conversation records.

6.  In-plant conference records.

7.  Progress payment recommendations.

8.  Technical document recommendations.

9.  Audit Reports.

4.1.3  CORRESPONDENCE CONTROL.  A control system should be established which identifies all incoming/outgoing correspondence.  Responses should be made in a timely manner.  If this is not practical, an interim reply should be made.

## SECTION 2.  CONTRACT PROGRESS REPORTS

4.2.1  GENERAL.  This section establishes requirements for progress reports, trip reports, interim reports, and special reports (also see Section 5 for final report).  Based on QRO observation and knowledge, these reports give COs, engineers, QA Division Management, and other acquisition and PT personnel first-hand information about the contractor's progress on each contract, the status of QRO and quality assurance operations, and those items which affect contract technical requirements and delivery schedule.  These reports document observations made and action taken during manufacture, inspection and testing, and acceptance or rejection of contractor's offered equipment and material.  These reports must also describe those actions which, in the QRO's opinion, should be taken by FAA to alleviate actual or potential problems.

1.  Progress Reports.  A separate progress report is required on each contract from the resident QRO.  These reports shall be submitted monthly unless otherwise approved by the Branch Manager.

2.  Special Reports.  Special reports are used to report unusual situations or actions (e.g., waste/fraud/abuse/mismanagement) which, in the QRO's opinion, warrant action by the Branch Manager.  These reports shall be submitted to the Branch Manager with no other distribution.

3.  Trip Reports.  A trip report is required on every itinerant contract assignment even if activities such as:  audits of processes, system/procedure compliance, inspection, test, and acceptance of the material or equipment are completed within a working day.  If no items are ready for inspection, the contract status or progress shall be reported.  Reports describing the status shall be submitted at least monthly, even if no trip was made.

4.  Interim Reports.  Interim reports are used to inform management of planned scheduled events that have not been completed because of significant problems encountered, and may be made during the period between normal progress reports.  This report documents specific problems and does not replace the normal progress report.  The document should be identified as an interim report, the subject stated and the contents written in a clear concise narrative form.

5.  Information/Alert Bulletins.  These bulletins should be forwarded by email  to the QA Branch Manager, CO, TO and PT to inform or alert management about significant events that occur within the company to which the QRO is assigned.  These reports should be used to transmit such items as:  significant changes in company management/organization; impending strikes; major financial issues; etc..  The Branch Manager will then forward the information to other levels of ASU management, as warranted.

4.2.2  FORMAT OF PROGRESS AND TRIP REPORTS.  Reports shall be numbered consecutively.  The subject shall identify the contract number, name of contractor, and city and state of contractor.  Major items on the contract should be described directly below the address portion of the letter in the following format:

1.  Contract Line Item Number(s) and item description(s).

2.  Contract delivery dates:  First _______________; Last __________________.

3.  Contract is behind schedule (days/weeks); or contract is on schedule, as appropriate.

4.  Total quantity on order.

5.  Total quantity accepted to date.

6.  Balance remaining.

NOTE:  When a number of items are listed in the contract schedule, only the major items are to be listed in the format depicted above.  Major items are to be described in narrative form immediately below the major item.  Major items are defined as systems, subsystems, and integral units, such as receivers and transmitters.  Minor items are defined as spare parts, provisioning parts lists, instruction manuals, and item identification lists.  Minor items should be treated as major items if they become pacing items affecting, or likely to affect, delivery.

4.2.3  NARRATIVE PORTION OF REPORT.  The narrative portion of the report must be informative, factual, concise and based on firsthand observations.  Predictions, opinions or secondhand information should be identified as such.

1.  Contract Progress.  The contractor's progress should be described in terms of production quantity, quality and schedule.  If the contract is behind schedule or it is anticipated the contract will become delinquent, the reasons shall be reported together with the forecast as to when the problem should be resolved and delivery made.  If a technical, production or process problem exists, the problem and the contractor's efforts to resolve the problem should be described.

When a contractor attributes the delinquency to vendor delays, the vendor's name, location, and item produced should be added to the above information.  If the contractor attributes the delinquency to another cause, the cause as well as the contractor's reasons should also be added to the above information.

2.  Contract Quality Status.  This paragraph should discuss any quality functions, issues, concerns or problems that could effect product quality and/or schedule.  A brief description of the status, disposition and/or resolution should be included.  Also list any audits, inspections, or testing performed and the results.  Any QDRs issued should be identified along with the status of the requested corrective action(s).

3.  Action Recommended.  In this paragraph of the report, describe clearly those actions to be taken by the FAA to alleviate problems and the date when a decision is necessary to avoid delay in production and timely delivery.  To the extent possible, identify the cognizant FAA segment responsible for taking action.  Examples:

(a)  Technical Officer.  A decision on contractor's request for or review and approval of test procedures and instruction books is required by (day, month, and year) to avoid delaying start of production or production tests or environmental tests, etc..

(b)  Contracting Officer.  A decision on issuance of contract modifications, issuance of shipping instructions, or delivery of GFP is required by (day, month, and year) to avoid delaying shipment for first system, etc..

4.2.4  DlSTRlBUTlON.  Progress reports, trip reports, and interim reports shall be addressed to the CO with copies distributed as follows:

1.  Original to the CO.

2.  Copy to the cognizant PTL and TO.

3.  Copy to QRO's Branch Manager.

4.  Copy to QRO contract field file.

5.  Copies of contract progress reports affecting initial provisioning actions and schedules should be furnished to the FAA Logistic Center, Attention:  NAS Project and Provisioning Section.

4.2.5  TIMELINESS.  When feasible, each progress report should be submitted on the same day of the week.  Monthly reports should be submitted within 3 workdays of the same date each month.  Trip reports should be submitted within 3 workdays after completion of the trip.  Branch Managers may designate specific days to submit reports in order to meet deadlines for submitting reports to higher levels.

## SECTION 3.  ACCEPTANCE

4.3.1  GENERAL.  Acceptance (or rejection) of supplies or services under FAA contract shall be made by the QRO on Form FAA-256, Inspection Report of Material and/or Services, unless the contract specifies otherwise.  Under Inspection Interchange Agreements, the QA Division may be requested to administer, inspect, and accept supplies or services for other Department of Transportation agencies, or for other Government departments.  Acceptance under these contracts will be made as prescribed, using the forms specified therein.

4.3.2  SHIPMENTS.

1.  The QRO shall ensure that the contractor preserves, packages, packs, and marks the equipment and materials in accordance with specified contractual requirements and that shipping instructions are followed.

2.  The QRO will also ensure that the contractor properly executes Government Bills-of-Lading, FAA Form 4500-1 and other related shipping documents, and accomplishes forwarding action in accordance with contractual requirements.

4.3.3  SECURITY CLASSIFICATION.  Classified information shall not be included on Form FAA-256 or any other prescribed acceptance form.  When classified material is to be shipped and the contract description of the material is classified, enter only a general description which does not require security classification, for example, "Standard Materials", "Electronic Equipment", or the like.  When information other than the description of the contract item is classified by the contract, the applicable space of the form shall be left blank.

4.3.4  CERTIFICATES OF COMPLIANCE (COC).

1.  When a COC is permitted by a contract and the QRO deems its use warranted, the QRO shall coordinate with the TO and CO, as appropriate, through his/her Branch Manager for the advisability of using the contractor's COC as a basis for acceptance of supplies and services.  The following should be considered in making the determination:

(a)  Nature of the supplies and intended use.

(b)  Administrative costs associated with accomplishment of required quality assurance functions.

(c)  Risk of receiving defective material in the FAA based on the contractor’s past record, current quality system, and other relevant factors.

2.  If the COC clause contained in the contract is considered inappropriate, the CO shall be notified accordingly.

3. The COC statement required by the contract shall be prepared by the contractor and submitted to the QRO.  Copies will be attached to all completed copies of Form FAA-256.

4.3.5  INSPECTION REPORT OF MATERIAL AND/OR SERVICES, FORM FAA-256.  The following instructions apply when Form FAA-256, Figure 2, is issued as the official inspection/acceptance record.  The QRO shall ascertain that all information, including signature is legible on all copies.

1.  Block No. 1 - Report Number.  Generally, report numbers will be in sequence, starting with No. 1, for each line item of the contract.  Rejection reports will be part of the sequence.  However, items may be combined on a single report form for one-time inspection/acceptance where all, or nearly all, items are accepted the same day or where there are so few reports that there can be no confusion.  If it becomes necessary to correct Form FAA-256, a new form will be issued using the same report number as the original with addition of the word "Amended" in block number 1.  The reason for the amendment shall be entered in block number 23.

2.  Block No. 2 - Date.  Enter the date of the report.  This is the date the report is filled out (which might be later than the acceptance date which is shown in Block No. 14).

3.  Block No. 3 - Order Number.  When applicable, enter the purchase order number covering equipment or services on a contract or on an open market purchase.

4.  Block No. 4 - Contract Number.  Enter the contract number.  On small purchases (purchase orders), this block does not apply and will not be completed.

5.  Block No. 5 - Item Number.  Enter the number(s) of the contract line item(s) covered by the report.  All-encompassing figures may be used as "1 through 39" or "1 through 22, except Item 17".  Where sample units are inspected in accordance with a clause of the contract and held at the Contractor's plant for delivery at a future date, mark after the item number "Clause ______________of the contract" and indicate that the item was inspected in accordance with a special clause of the contract and that it is not final acceptance of a production unit of the line item.  When one report covers the entire contract, Blocks 16, 17, 19, and 21 should show "all units and items".  Individual line item(s) with quantities and serial numbers will be listed on the continuation sheet, Form FAA-256a.

6.  Block No. 6 - Material and/or Services Inspected.  Enter the contract nomenclature for the line item(s) covered by the report.  In the event several line items are covered, use terminology of all, such as "instruments", "tools", "spare parts", or the like.

7.  Block No. 7 - Contractor.  Enter name and address of Contractor awarded the contract.

8.  Block No. 8 - Manufacturer.  Enter name and address of company presenting material for inspection/acceptance.

9.  Block No. 9 - Place of Inspection.  Enter the name and address of the company where inspection/acceptance is performed.  If the same as Block No. 8, enter the words "same as above".

10.  Block No. 10 - Serial No(s).  When the line item has subassemblies containing several serial numbers, list only the number on the governing nameplate, except where special equipment requires more than one serial number because it is an assembly of two or more major assemblies.  In that case, the two or more significant serial numbers should be identified and recorded.  Serial numbers of all items, differentiating between rejections and/or acceptance will be entered.  The total number of serial numbers entered should equal the sum of the quantities shown in Blocks 15 and 16.

11.  Block No. 11 - Date notice Received.  Leave Blank.

12.  Block No. 12 - Date Ready.  Enter the actual date material (contract line item) is presented for inspection/acceptance.

13.  Block No. 13 - Date Started.  Self-explanatory.

14.  Block No. 14 - Date Completed.  Enter the date the inspection was completed.  Final inspection and acceptance is not completed until packing and marking has been observed.  In cases where packing and marking are separate line items on the contract and may be witnessed by another representative, or the time between acceptance of the material and packing and marking is three working days or more, so state in Block No. 23 "Remarks".

15.  Block No. 15 - Rejected.  Ordinarily, when a unit is found to be defective, then corrected, resubmitted, and accepted before the lot inspection is complete, the unit will not be classified as a reject nor will it be entered in Block No. 15 as such.  In special cases, such as the contractor's repeated submission of unacceptable units, it is proper to issue an Form FAA-256 rejection.  An Form FAA-256 rejection will be issued on a non-resident facility, when the QRO visits the Contractor's facility and finds the submitted material is not acceptable.  A failure of type or environmental test may also be rejected on an Form FAA-256.  Specific reasons for rejection will be entered in Block No. 23, "Remarks".

16.  Block No. 16 - Accepted.  Self-explanatory.

17.  Block No. 17 - Submitted.  Self-explanatory.

18.  Block No. 18 - Rejected.  Self-explanatory.

19.  Block No. 19 - Total of units accepted.  Where sample units are inspected/accepted under a clause of the contract as described in Block 5 above, the totals are not to reflect final acceptance of those units until accepted as production items.

20.  Block No. 20 - Quantity.  Self-explanatory.

21.  Block No. 21 - Accepted to date.  Self-explanatory.

22.  Block No. 22 - Balance remaining.  Self-explanatory.

23.  Block No. 23 - Remarks.  This block is for pertinent information for which no other space is provided on the form, e.g., conditional acceptance, destinations of direct shipments, GBL numbers, carriers, total weights, quantity, and cubic contents of shipment.  Explanations such as "Sample Unit to be retained at Contractor's plant and shipped with final item on the contract", "Markings conform to telegrams, CO, 6 July 95" or "Instruction books packed behind door of control panel" are properly entered in this space.

24.  Block No. 24 - Inspected by.  Type the name and title of the QRO inspecting the material or services.

25.  Block No. 25.  The QRO who accepts the material or services signs here.  No one should sign for another.  The person signing is responsible for assuring that the material or services described on the Form FAA-256 meet(s) the contract requirements.  The date of signature is the date of acceptance.

26.  Notes.

(1)  When a contract provides that inspection shall be performed at the contractor's facility but that final acceptance shall be made at destination, the words "as accepted" in the statement following block 24 shall be crossed out either by typewriter or in ink, and the following entry shall be made in Block No. 23:  "Factory test and inspection satisfactory; acceptance is at destination."

(2)  Conditional acceptance can only be authorized by the Contracting officer.  This must be noted in the remarks section, block 23, and the condition(s) must be described.

4.3.6  DISTRIBUTION OF COMPLETED FORM FAA-256.  The QRO prepares and distributes signed copies of the report as follows:

1.  The original to the CO.

2.  Copy to the accounting office (ABA-220 for headquarters contracts, AMZ-300 for FAA Logistics Center contracts).

3.  Copy to the contractor.

4.  Copy to the PTL and the TO.

5.  Copy to the QRO contract field file.

6.  Additional copies distributed as approved by the QA Branch Manager.

### FIGURE 2.  INSPECTION REPORT OF MATERIAL AND/OR SERVICES (FORM FAA-256)

| DEPARTMENT OF TRANSPORTATION FEDERAL AVIATION ADMINISTRATION INSPECTION REPORT OF MATERIAL AND/OR SERVICES |
| --- |
| 1. REPORT NO. | 3. ORDER NO. |
| 2. DATE | 4. CONTRACT NO. |
|  | 5. ITEM NO. |
| 6. MATERIAL AND/OR SERVICES INSPECTED |
| 7. CONTRACTOR |
| 8. MANUFACTURER |
| 9. PLACE OF INSPECTION |
| 10. SERIAL NO/S | INSPECTION | QUANTITY |
| (If Applicable) | 11. DATE NOTICE REC'D | 12. DATE READY | 13. DATE STARTED | 14. DATE COMPLETED | 15. REJECTED | 16. ACCEPTED |
|  | PREVIOUS REPORT/S | THIS REPORT | TOTAL TO DATE |  |  |
| 17. SUBMITTED |  |  |  | 20. QUANTITY ON ORDER |  |
| 18. REJECTED |  |  |  | 21. ACCEPTED TO DATE |  |
| 19. ACCEPTED |  |  |  | 22. BALANCE REMAINING |  |
| 23. REMARKS |
| 24. INSPECTED BY | TITLE |
| THE MATERIALS AND/OR SERVICES LISTED HEREIN HAVE BEEN INSPECTED, OR CERTIFIED TEST DATA HAS BEEN EXAMINED, BY ME OR UNDER MY SUPERVISION. THE MATERIALS AND/OR SERVICES LISTED ABOVE AS ACCEPTED CONFORM TO CONTRACT REQUIREMENTS. THOSE LISTED AS REJECTED DO NOT CONFORM AND MAY NOT BE DELIVERED, EXCEPT AS AUTHORIZED UNDER "REMARKS." |
| 25. | TITLE | DATE |
| (Use Form 256a for Continuation Sheet) | PAGE ____ OF ____ PAGES |

Form FAA-256(3-61)										Rev. B (3/03/95)

4.3.7  PROJECT MATERIAL SHIPPING NOTICE/RECEIVING REPORT FORM 4500-1.

1.  FAA Order 4650.30, Vendor Shipment of nationally Furnished Project Material, describes the activities associated with FAA Form 4500-1 in detail.

2.  The contractor is responsible for notifying the CO of upcoming shipments (and requesting shipping instructions on non turnkey shipments) at least 30 days prior to anticipated shipping date, or as soon as shipping availability is known if it is less than 30 days from date of contract or order.  The notification and request for instruction must include the name and telephone number of the shipper, number of pieces, weight, and dimensions to be shipped in each shipment, any material handling equipment which may be necessary as well as any storage requirements.  If the weight and dimensions are unknown, "estimates for rate" and "routing purpose" must be provided on the request for shipping instructions.  Lack of required information may delay issuance of FAA Form 4500-1.

3.  The QRO at the contractor's plant is responsible for ensuring contractor compliance with contractual requirements pertaining to packaging and shipping of material.  The QRO shall verify that the shipping information supplied by the contractor is accurate and complete.  The QRO is also responsible for preparing and distributing Form FAA-256, Inspection Report for Material and/or Services, as well as signing copy 1 of the FAA Form 4500-1 on Free on Board (FOB) Origin shipments and returning it to the paying office.

4.  If the equipment is conditionally accepted, i.e. not in full compliance with contract requirements, for shipment (conditional acceptance must be approved by the CO) on FOB origin shipments, the QRO will notify the transportation officer (by telephone), sign copy 1 of FAA Form 4500-1, and insert thereon a notation as to the exceptions and other condition(s) of acceptance.  In lieu of this notation and if approved by the PTL or CO, a copy of the Form FAA-256 with exceptions may be attached.  The annotated, signed copy 1 of FAA Form 4500-1 is then forwarded to the accounting officer as indicated in paragraph c above.  If there is an error or change on number 1 copy, the QRO will not sign it, but inform the transportation officer.

5.  In all cases of FOB origin, the QRO receives copies 1, 3, and 4 of FAA Form 4500-1 from the transportation officer.  Copies 1 and 3 are to be signed no later than the next workday after acceptance of the material.  Copy 1 is to sent to the paying office, and copy 3 to the consignee’s servicing accounting office.  If the consignee is not an FAA facility, copy 3 should go to the consignee.  Copy 4 is for the QRO file.  See Order 4650.30, Appendix 4, for a listing of FAA Accounting offices.  If the FAA Form 4500-1 has not been received by the time QRO accepts the shipment for the Government, the QRO shall immediately notify the program management office.

6.  FOB destination shipments are those shipments for which the contractor is liable for both the cost of the shipment and the material while in transit until delivered to the Government specified location.  Government takes title to equipment at time of receipt and acceptance.  FAA Form 4500-1 copy 2 is forwarded by the transportation officer to the contractor as shipping instructions.

7.  Normal execution of FAA Form 4500-1 as indicated above might be impractical in some instances such as, site unavailability, production problems, or the like.  These circumstances could possibly result in unavoidable changes in the delivery instructions, (i.e., changes in quantities to be delivered, changes in destinations, or prices).  In these circumstances, the QRO should coordinate with the transportation officer, PT, and the CO.

8.  When the QRO can anticipate that the quantity being produced differs from the quantity specified in the contract delivery schedule, the QRO should advise the transportation officer, PT, and the CO requesting guidance.

9.  To the extent practicable, the QRO should confirm shipping addresses prior to shipping of project material on both FOB origin and FOB destination shipments.  On Headquarters' contracts, the QRO will notify the appropriate Regional Material Manager, the date shipped and if known, the estimated date of arrival.  This paragraph does not apply to shipments to the FAA Logistic Center.

10.  The QRO shall discuss the requirements for FAA Form 4500-1 in accordance with Contract clause "Contractor Request for Shipping Instructions" with the contractor.  Particularly, the "shipments shall not be made by the contractor unless (and until) FAA Form 4500-1 has been received."

Note:  FAA Form 4500-1 is used on all contracts for project material (installation or modification under Facilities and Equipment (F&E) funds).  It is not used on contracts for maintenance material under Operations appropriation funding (OPS).

4.3.8  GOVERNMENT BILLS OF LADING (GBL).  The QRO should, to the extent possible, verify that the GBL includes the following information:

1.  Exact quantity, dimensions, and weight of articles shipped.

2.  Individual weights for each piece when pieces are listed separately.

3.  When exclusive use or specialized carriage (e.g. heavy hauler) is required, type and size of vehicle ordered and furnished.

4.  Carrier's agent signature on the original and all copies at time shipment is tended to carrier.

After the carrier's agent has signed, the contractor should mail one yellow copy to the Transportation Officer, one to the Accounting Office, and retain one.  The blue copy should be forwarded to the consignee.  The original and all other copies should be given to the original carrier's agent.  No one, QRO or contractor, is authorized to make any changes to a GBL without specific approval from the Transportation Officer.

## SECTION 4.  PROGRESS PAYMENT REQUESTS

4.4.1  BACKGROUND.  To be applicable, progress payments must be authorized by the contract.  They apply only to fixed price contracts and are generally used when there is a long lead time between the beginning of work and the first delivery, and the necessary outlay of moneys prior to first delivery time will have a marked impact on the contractor's working funds.  Progress payments are granted as the contractor performs work under these conditions and if he (1) has an adequate system of accounting and financial control, (2) is financially responsible, and (3) is an otherwise competent contractor.  Progress payments for the majority of FAA procurements are based on incurred costs and are related to actual progress.  Incurred costs are those costs identified through the use of the accrual method of accounting and reporting.

1.  As to invoices, incurred costs include only invoices for (a) completed work to which the prime contractor has acquired title, (b) material delivered (to which the prime contractor has acquired title), (c) services rendered, (d) costs billed under cost reimbursement of time and material subcontracts for work to which the prime contractor has acquired title, and (e) invoices for progress payments to subcontractors which have been paid or approved for current payment in the ordinary course of business (as specified in the prime contract), all properly recorded on the books of the contractor and identified with the contract.

2.  Costs incurred also include costs of direct labor, direct material, and direct service(s) identified with, and necessary for, the performance of the contract, and also all properly allocated and allowable overhead (indirect) costs as shown by the books of the contractor.

4.4.2  RESPONSIBILITY.  The QRO will review contractor's requests for such payments and provide a recommendation to the CO for approval or disapproval of the request.  This will be accomplished by (1) equating the evidence of actual progress against the amount of money requested, (2) determining if the dollar value of the request is substantiated by satisfactory evidence of incurred costs, and (3) equating actual progress against the delivery requirement stipulated in the contract.  It is important that the QRO maintain awareness as to the contractor's overall financial stability.  Should he/she become aware of mechanic liens, difficulty in getting financing, "cash on delivery" requirements from vendors, a pending merger with another company, possible bankruptcy or the like, these developments should be immediately reported to the CO and the QRO’s Branch Manager (see guidance on Information/Alert bulletins, 4.2.1, subparagraph 5).

4.4.3  GUIDANCE.  Basically, the QRO is concerned with entries on the Request for Progress Payment which pertain to direct elements such as hours, personnel and material and need not be concerned with General and Administrative Expenses (G&A), other overhead entries, or cost computations.

1.  One of the better methods of evaluating progress payment requests is to request a copy of the contractor's planned performance schedule on the contract.  Most contractors do this by using a bar chart, or similar method which shows the number of days and planned manpower loading for each phase (i.e., design, engineering mock-up, purchasing, short-and long-lead items, production releases, material availability, manufacturing and so forth).  Evaluator should consider the planned progress versus the actual; these in turn versus the contract-delivery requirements versus moneys requested.  More simply stated, when the physical progress is reasonable, the contractor is maintaining good effort, and delivery requirements are not impaired, then recommendation for approval of the progress payment is in order.  Conversely, should the evaluation conclude the contractor is not maintaining a good effort, and delivery requirements of the contracts are in jeopardy or will not be met, then recommendation for disapproving the progress payment usually is in order.

2.  Keep in mind that the QRO is not a cost auditor and shall not perform an accounting "audit" of costs incurred.  Substantive reasoning and good judgment is sufficient to arrive at a timely recommendation for approval or non-approval.  Normally, problem(s) of sufficient magnitude to warrant recommendation of non-approval should have been identified and reported to the CO prior to the progress payment request being submitted.

3.  Upon completion of the review, the QRO shall submit a written statement to the CO and TO recommending approval or disapproval of the payment.  This statement should reference the contract number, the request for progress payment number, and the date of the request.  In order to assist the CO in determining approval or non-approval, the statement must include a summary of the facts germane to the approval or non-approval of the request.  The statement must conclude with a specific recommendation that the progress payment be approved or disapproved.  In the case of a recommendation for disapproval, a copy should be sent to the QRO’s Branch Manager.

## SECTION 5.  CLOSEOUT OF FIELD CONTRACT FILE

4.5.1  GENERAL.  After delivery of the final contract item, the QRO shall:  (1) conduct a final contract review, (2) submit final progress report, (3) submit Contractor Performance Evaluation Form, and (4) submit notification of intent to closeout files.  These actions shall be in accordance with the following paragraphs.

4.5.2  FINAL CONTRACT REVIEW.  The final review should focus on a verification by the QRO that all actions, which are his/her responsibility, have been consummated and that these actions have been documented to the extent practicable.  When the review indicates that there are incomplete actions, the surrounding circumstances should be investigated and resolved to a satisfactory conclusion.  The following three paragraphs are intended as a guide and represent significant items that should be considered during the final review:

1.  Examine the Field Contract File to ensure the receipt of all documentation, inspection and acceptance of all contract items, and that all corrections and/or exceptions have been accomplished.

2.  Ensure that correspondence related to the items listed in paragraph 4.5.2.1 above have been distributed to the responsible personnel such as CO, PTL, TO, etc.

3.  Verify that proper disposition has been made of Government-Furnished Property including the documentation and its distribution.

4.5.3  FINAL PROGRESS REPORT.  The final progress report shall indicate that no further progress reports will be submitted on this contract.  It shall also document all significant actions not previously documented or those previously reported as incomplete.

## SECTION 6.  CONTRACTOR PERFORMANCE EVALUATION

4.6.1  GENERAL.  A Contract Performance Evaluation Form, Form 3458, is to be executed upon completion (final shipment) of each contract.  To obtain maximum standardization, the following guidelines for completion of the form are supplied.

1.  Block 1 - Quality of End Product or Services.  The fact that the products (or services) were accepted establishes that the products (or services) were satisfactory.  However, this does not preclude a rating of “outstanding” or “unsatisfactory”.  If the quality of the products was clearly and consistently outstanding, that adjective rating should be used; however, a brief specific narrative evaluation should be included.  If the contractor required unusually burdensome assistance to obtain an acceptable (i.e., satisfactory) product, if numerous defects were encountered and these facts are documented in the files, the adjective "unsatisfactory" should be used.  Include a brief, specific narrative statement of the facts as documented, to substantiate this rating.

2.  Block 2 - Timeliness of Performance.  Deliveries made in accordance with contract requirements should be rated as "satisfactory".  If satisfactory deliveries were made ahead of contract schedule, or, if the contractor accepted a tight delivery schedule and delivered on time, a rating of "outstanding" should be considered.  A major factor to consider is the amount of time ahead of schedule as compared to overall time for delivery.

One week ahead of schedule within 90 days after award of contract may be more or less significant than one week ahead of schedule 360 days after contract award.  If deliveries were frequently late, a rating of "unsatisfactory" should be considered.  When a rating of "unsatisfactory" is used, include under "remarks" a statement such as the following:  "Delivery was due on (Date) and was one month delinquent.  Review of the Field Contract File discloses that the Government did not significantly contribute to this late delivery."  A rating of "unsatisfactory" should be used only when all of the following conditions prevail:

(a)  Deliveries were frequently and/or significantly late.

(b)  The Government did not contribute to the late deliveries.

(c)  The above conditions were documented in the field contract file.

3.  Blocks 3, 4, and 5.  These blocks should be left blank unless there is specific information having a significant bearing on one of these items.  In that case, describe briefly the facts bearing on these items.  Do not check any of the adjective ratings.

4.  Distribution.  Five copies of these reports should be prepared and signed in the "Prepared by" block.  In this block, cross out "contract specialist" and insert your title and routing symbol.  Send one copy each to the CO, TO, PTL, ASU 210 and the Branch Manager.

4.6.2  NOTIFICATION OF INTENT TO CLOSEOUT FIELD CONTRACT FILE.  At the time determination to closeout the file is made, the QRO shall address a memo to the CO with copies to the PTL, QRO Branch Manager, the TO, and any other agency personnel having an intimate interest in the contract.  This memo shall request disposition instructions for data sheets, test procedures and if applicable, extra copies of instruction books, manuscripts, and drawings and advise the recipients of the intent to closeout the Field Contract File.  The memo shall also indicate that the contract files will be disposed of after 60 days unless otherwise notified.

Upon receipt of a reply, or the lack of a reply, from the CO, and with concurrence from the QRO Branch Manager, the QRO shall make disposition.

# CHAPTER 5.  COLLATERAL DUTIES

## SECTION 1.  PROVISIONING CONFERENCES

5.1.1  GENERAL.  The purpose of a provisioning conference is to identify those parts or items that need to be stocked at the FAA Logistic Center to support the equipment when it becomes field operational.  The QRO has first hand knowledge of the equipment.  This knowledge can be invaluable to the provisioner and PT in making decisions on which items need to be supported.

5.1.2  ACTIONS PRIOR TO PROVISIONING CONFERENCE.  In preparation for the provisioning conference, the QRO should review the provisioning documentation.  The documentation review may consist of review for proper part numbers, for identification of spare parts peculiar, and for completeness.  The QRO, if requested, should provide coordination between the provisioner and the contractor as to availability of the equipment, of the drawings (if required), and of the pertinent personnel for the scheduling of the conference.

5.1.3  PROVISIONING CONFERENCE ACTIONS.  The QRO should attend the provisioning conference.  During the conference, the QRO provides technical guidance about the equipment being procured, assists with clarification of part numbers, and advises the provisioner of any history of part failures that could affect equipment support.

## SECTION 2.  POST-AWARD CONFERENCE

5.2.1  GENERAL.  A post-award orientation conference should be held on all contracts as soon as possible, but generally not later than thirty (30) days after award, to clarify contract requirements, resolve misunderstandings, and ensure that the contractor understands and plans to meet all contract requirements.  The need for a formal post-award orientation conference will normally be established by the CO as a result of substantive review and analysis of the contract and related reports.  When a formal post-award conference is not scheduled by the CO, the QRO should coordinate with the PTL, CO and TO scheduling an "informal" post-award meeting with the contractor to discuss quality assurance program issues.  On small contracts, particularly those with small contractors, this meeting may be attended by only the QRO and one or two contractor personnel.  However, the goals of the "informal" meeting should be the same as that of a formal conference.  During this "informal" meeting the QRO must avoid any actions that indicate the provisions of the contract are being, or will be, changed.  Any misunderstanding of the rights and obligations, or of the technical requirement, should immediately be referred to the PT and the CO.

1.  Although the remainder of this section is addressed primarily to the formal post-award conference, it should be used as guidance for the conduct of an informal post-award meeting.

2.  The complexity of the contract will determine the agenda items for the conference; an extremely complex contract may require participation of specialists from the Contractor’s Quality, Production, Engineering, Legal, Provisioning, and Contract Administration organization.

3.  The Government's contribution to the post-award conference should be the result of a well-planned, coordinated, and informed team effort.  Consequently, it might be necessary to hold one or more in-house meetings prior to meeting with the contractor.  The conference, therefore, will be planned and coordinated to the degree commensurate with the complexity of the contractual requirements, and conducted in accordance with current applicable policy and directives.

4.  If a proposed program schedule (milestone chart) was not submitted by the contractor as part of the proposal in response to the Screening Information Request (SIR), Invitation For Bid (IFB) or Request For Proposal (RFP), the QRO will request such a schedule as soon as possible after award and prior to the conference.  Milestones and events listed therein should be verified for conformance with requirements e.g., (a) all contract line items, (b) parts procurement, (c) provisioning parts list, (d) breadboard design, (e) subassembly design verification, (f) total system design review, (g) drawing release, (h) submission of proposed test procedures and test data sheet, (i) production release, (j) submission of contractor's quality plan; and (k) other relevant scheduled dates and events.  The foregoing plus related items listed in the Contract Review Record may be used in the generation of Government agenda items, as a minimum, for the post-award.

5.  Items of particular interest to the QRO are:  contractor’s submittal procedures, organizational responsibilities including those responsible for interface with the QRO, contractor’s requirement for requesting or providing information, e.g., FAA Form 4500-1 and certification requirements of FAA-G-2100.

6.  Contractual QA elements and QRO responsibilities should be presented and discussed at the post-award conference.

7.  A copy of the post award conference record shall become part of he QRO contract file.

8.  If, at the time of pre-post award and/or post-award meeting the QRO has not been selected, the QRO will be represented by the Branch Manager or designee.

## SECTION 3.  FAA TEST AND EVALUATION

5.3.1  GENERAL.  The QA Division will provide support services during each stage of the Test and Evaluation (T&E) program, as required by the contract.

## SECTION 4.  SUPPORT FOR THE PRODUCT TEAM

5.4.1  PRODUCT TEAM REPRESENTATION.  As the PT’s representative, the QRO shall keep the PT advised of the status of all pertinent contract items.  The PT should be made aware of all contractor actions that could adversely affect product quality, schedule, or price, and should be advised of any areas where Government inaction could have an adverse effect on contract performance.  The PT may request that the QRO investigate specific technical problems, review documents, or perform other duties that can best be performed in the contractor’s plant.  To the extent practicable, and as time and workload permit, the QRO should perform these tasks as requested.  Caution must be exercised to avoid actions that exceed the authority delegated to the QRO.  When the contract requires Government approval of specific documents, such as test procedures, test data sheets, name plate drawings, instruction book manuscripts, and Provisioning Parts Lists, the QRO should provide written comments to the PT in a timely manner.

## SECTION 5.  CONTRACT PROPERTY ADMINISTRATION SUPPORT

5.5.1  GENERAL.  The ASU-210 Contract Support Team is responsible for property administration in ASU-200.  As part of the audit process, each QRO is expected to provide in-plant support to this activity by monitoring the contractor’s operations.

5.5.2  CONTRACT PROPERTY ADMINISTRATION.  The QRO will verify that:

1.  The contractor has delegated or assigned a specific person as “Property Custodian” responsible for management of Government property accountable to a specific contract.

2.  The contractor complies with the documented property control process.

5.5.3  ACQUISITION.  The QRO will verify that:

1.  All property is recorded and controlled in the contractor’s property management records.

2.  The contractor obtains TO prior approval and reports all acquisitions of Contractor Acquired Property (CAP) to the FAA Property Administrator (PA).

5.5.4  RECEIPT PROCESSING,  The QRO will verify that:

1.  For Contractor Acquired Property, the contractor maintains appropriate records of incoming receipts per their approved written property control procedures.

2.  For Government Furnished Property (GFP), the contractor appropriately identifies and records discrepancies on FAA Form 4650-12, and returns completed original to the FAA PA.

3.  The contractor notifies the FAA PA when overages, shortages, damages and/or other relevant information are discovered upon receipt of GFP.

4.  The contractor has and complies with procedures for identifying and segregating hazardous materials.

5.5.5  WAREHOUSING.  The QRO will verify that:

1.  The contractor segregates Government property from contractor owned property and safeguards it from damage and deterioration.

2.  The contractor takes appropriate action and notifies the FAA PA regarding lost, destruction or damage to Government property while in storage.

5.5.6  INVENTORY CONTROL RECORDS.  The QRO will verify that:

1.  The contractor has and complies with contractually required inventory controls.

2.  The contractor has and complies with contractually required procedures and policies governing supply support of spares.

5.5.7  RECEIPT AND ISSUE FILES.  The QRO will verify that:

1.  The contractor provides for, and complies with, contractually required receipt and issue records and controls.

2.  The contractor maintains and reports to the FAA PA any material/equipment established as scrap or salvage.

5.5.8  PROPERTY USE.  The QRO will verify that:

1.  The contractor uses Government property only as authorized.

2.  The contractor reports to the FAA PA all plant equipment no longer justified.

3.  The contractor monitors subcontractor compliance with property provisions requiring safeguarding, care and use of Government property.

5.5.9  MAINTENANCE.  The QRO will verify that the contractor performs and records the scheduled maintenance, including preventive maintenance, as required by procedure.

5.5.10  CAPITAL-TYPE REHABILITATION.  The QRO will verify that the contractor complies with contract requirements regarding maintenance and reporting of capital equipment, including such action as inspection of buildings and other capital equipment and reports to the FAA Property Administrator.

5.5.11  PHYSICAL INVENTORY.  The QRO will verify that the contractor performs physical inventories in accordance with approved procedures and schedules.

5.5.12  RECORDING OF INVENTORY.  The QRO will verify that the contractor develops and maintains inventory records as required by contract and internal procedures.

5.5.13  REPORTING.  The QRO will verify that the contractor provides timely and appropriate contractually required reports (including annual and financial reports) to the FAA PA.

5.5.14  PROPERTY DISPOSAL.  The QRO will verify that:

1.  The contractor assures that Government identification and/or markings are removed prior to disposal of the GFP.

2.  The contractor’s description of Government property on inventory schedules for disposal is accurate, i.e., description, quantity, condition, etc.

3.  The contractor’s disposal actions are completed and that excess property is shipped within a reasonable time after receipt of disposal instructions from the FAA PA; and that surplus property is screened against ongoing contracts for possible need.

## SECTION 6.  STRIKES/LABOR PROBLEMS

5.6.1  GENERAL.  The QRO should immediately notify the PTL , the CO and the QRO’s Branch Manager of any strikes, impending strikes, or labor problems at the contractor’s facility.  Specific information that should be reported includes the notification of the impact of the strike on progress of the contract, the date(s) of votes to end the strike, possible expansion of the strike to include additional contract personnel, and the like.  In the event of picketing, the QRO should not attempt to cross the picket line, but should request instructions from the Branch Manager.

## SECTION 7.  SITE OPERATION

5.7.1  GENERAL.  On contracts that provide for Contractor installation, the Contractor's quality plan should include on-site quality operations as well as appropriate implementing procedures.

1.  The QRO should refer to Chapter 3 of this guidebook for the initial operation and related installation/on-site requirements of the contract.  Other chapters should be used as guidance to the extent practicable.

2.  Prior to each trip to a site, the QRO should coordinate with the PT, regional personnel and the QRO's Branch Manager, identifying the purpose of the trip and schedule.  In those cases where site acceptance of a turnkey installation is delegated by the CO to the Field TO/Resident Engineer, the QRO shall provide him/her with information regarding the contractor’s quality system commitments.  This information shall include appropriate copies of contractor procedures, organization, etc., and shall provide for feedback of deficiencies to the PT.  When the QRO is assigned the responsibility for formal acceptance of site installation, he/she shall use the relevant tools and techniques used in the factory.

## SECTION 8.  DATA COLLECTION/METRICS REPORTING

5.8.1  GENERAL.  The QRO shall collect, report, and maintain data on all contracts assigned responsibility as follows:

1.  QRO QA Plan Measures.  For each project, the QRO shall develop a set of measures that will show the implementation and status of QRO operations identified in the Plan.  Data for these measures should be refreshed on a monthly basis.  The measures should be formatted as metric charts, and included in the progress report.  Ideas and sample metrics can be found in the ASU-250 Toolbox.  To access the ASU-250 Toolbox on the Internet website go to the ASU Home Page and select ASU-200, then select ASU-250 Toolbox.  Contact the ASU-250 SOFTWARE QUALITY and INDUSTRIAL EVALUATION BRANCH for more information on Metrics and the Toolbox.

2.  Contract Data.  For each contract for which the QRO has primary QA responsibility, the QRO shall maintain:  (i) Contractor Name, (ii) Contract Number, (iii) IPT and PT being supported.

3.  Form FAA-256.  The QRO shall maintain an accurate count of the number of FORM 256 documents executed on each contract and the dollar value of each Form FAA-256 executed for each contract separately.

5.8.2  REPORTING.  The QRO shall furnish the Branch Manager the data specified above as follows:

1.  QRO QA Plan Measures – via the Progress Report

2.  Contract Data and Form FAA 256 – a report by contract within five (5) working days after September 30 of each year

## SECTION 9.  GIDEP SUPPORT

5.9.1  GENERAL.  The QRO should monitor contractor operations regarding the Government and Industry Data Exchange Program (GIDEP) requirements as follows:

1.  For contracts that specifically require the contractor to participate in the GIDEP process, the QRO should verify compliance with all detailed requirements, e.g., reviewing, preparing and distributing appropriate reports, etc..

2.  Where no specific contract requirement exists, the QRO should periodically check the GIDEP data base for “Alerts” and “Safe-Alerts” to assure that the contractor is aware of relevant information and takes appropriate action regarding equipment and/or services provided (reference FAA Order 4470.2).

# FORWARD

The SQA Model was developed as a framework for implementing quality assurance programs on software intensive projects.  The model provides a reference for comparing actual activities against model best practices and can be used as a guide for implementing new SQA programs.  The model is intended to cover the full life cycle from pre-award through fielding and includes SQA activities directly associated with the pre-award phase and with supporting product teams.

The SQA model is intended for use as a lower level supplement to the FAA integrated capability maturity model (FAA-iCMM) , which covers all of the essential elements of acquisition, engineering, and program management.

PURPOSE:  The SQA Model is intended for use for the following purposes:

Documenting SQA processes.

A reference model of what constitutes a good SQA program.

A process improvement tool for meeting CMM levels.

Identifying competencies.

Aid in determining potential workload.

New employee guide.

Management tool for determining SQA effectiveness.

MODEL ORGANIZATION and FORMAT:  The model is organized by process areas, which in turn relate to specific SQA objectives.  Each process area has specific goals and activities designed to meet those goals.  Activities have been applied to the major life cycle of the development process.  Procedures for each process area provide additional guidance on implementing model practices.

PROCESS AREA:  Process areas represent a set of related activities, which when performed collectively, can achieve a defined goal or goals.  The SQA process areas are specifically intended to provide the essential elements for conducting SQA.

- GOAL:  The outcome or product of the Process Area.

- ACTIVITY:  Base Practice or sequence of activities that are employed to meet a goal.

PROCEDURE REFERENCE:  Refers to procedures (not physically contained in the model) that provide guidance on how to accomplish an activity.

LIFE CYCLE:  In order to provide a better understanding as to when activities should be performed in the software development life cycle, activities are mapped to major phases.

These phases are:

Conceptual (Pre-contract award)

Software Requirements Analysis

Preliminary Design

Detailed design

Code & Unit Test

Computer Software Integration & Test

Computer Software Configuration Item Integration & Test

Systems Integration & Test

It should be understood that not all activities begin and end in a single phase and some activities will extend beyond the phases listed above (e.g., beyond Systems Integration & Test).

GENERIC PROCESS AREAS:  During the development of the SQA model, several process areas were determined to be generic and not unique to the area of SQA.  These have been left out of the actual model but should still be considered as important and should be addressed when establishing or measuring an SQA program:

Ability to work as a team.  Establishing and conducting value added quality assurance (software or hardware) requires working closely with product team, contractor and other QA personnel.

Communication.  Effective verbal and written communication to management, product team members and contractor personnel both formal and informal is a vital process in a good quality assurance program.

Providing Formal and OJT Training.  Assisting junior level SQA personnel or other QA members with SQA activities is an important part of any quality assurance program.  The goal for this process area involves maintaining the organizations ability to increase needed skill areas where required.

REFERENCES:

1. FAA integrated Capability Maturity Model (FAA-iCMM).

2.  Quality/Reliability Officer Guidebook ASU-200.

POLICY:  This model constitutes a guide for conducting effective SQA and should be considered as the SQA portion of the QRO Guidebook with ASU management endorsement.