AMS-02 Weekly Activity Report, December 2, 2006

Upcoming Events:

- AMS Integration Meeting at CERN January 25 – 26, 2006

- AMS General Technical Interchange Meeting (TIM) at CERN January 30 – February 3, 2006.

- AMS-02 Phase II Safety Review – Date TBD (Schedule under review) – JSC

Upcoming Tests:

- Interface Plate Static Test – Date TBD – Location TBD

- Lower Joint Static Test – Date TBD – Location TBD

- STA Sine Sweep Test – August 2006 – INFN, Terni, Italy

- STA Acoustic Test – October 2006 – ESTEC, Noordwijk, Netherlands

- Full Assembly Modal & Static Tests – January 2007 – IABG, Munich, Germany

AMS-02 Design

- EVA Foldable Remotely Operated Electrical Umbilical (ROEU) Bracket model design primarily is complete.  Detail and Assembly Drawings are in work.  The usual tolerance work and drawing review is in order.  The space qualified Pip Pin specification has been identified and price and availability information is forth coming once we are satisfied with the detail design.

- The two thermal blanket bracket drawings are completed but not uploaded.

- The Thermal blanket assembly drawing for the VC Outer Cylinder and Inner Conical Flange is at 95 percent complete.

- The Inner Conical Flange thermal blanket template has been changed to include shielding material from the tracker.

- Primary Support Stand (PSS) top level drawing is currently in check.

- USS-02 build-up drawing, decals drawing, Upper USS-02 drawing, and Lower USS-02 drawing are checked and ready to be uploaded into EDRS.

- USS-02 Keel Assembly drawing is uploaded into EDRS and waiting to be signed and released.

- Thirty five (35) PSS drawings were released from EDRS.

- The drawings for the VC Shipping Fixture modifications have been submitted to checking.

AMS-02 Flight and GSE Manufacturing:

- The Sill Joints are being held up at the vendor due to nickel plating problems.  The final machining operations peeled up some of the plating out of the Trunnion hole.  It was determined by engineering that the original plating thickness was too thin.  A DR was generated and approved to fix the problem by removing the remaining plating, enlarging the hole, re-plating and final machining the bore (if necessary).  This may affect schedule.  We will not know the extent until time estimates are received back from the vendor performing the work (Metalex).

- Riveting of the Lower USS-02 Center Body Assembly is complete.

- Assembly of the PSS is to commence Monday 12/5/05.

- The USS-02 Keel has been assembled on the assembly fixture.  It is currently being aligned with the rest of the hardware.

- The Primary Support Stand subcomponents are being finalized for assembly.

GSE & STE

- An analyst is currently working on the Primary Support Stand (PSS) medium level configuration stress analysis.  Analyst received the set of nonlinear runs from the Loads group and the analyst ran NASPOST.  The NASPOST raw data was then processed using MathCAD.  MathCAD files were created for both Air Transportation and Truck Transportation scenarios.   The beams that compose the PSS were all analyzed and preliminary results were reviewed by the analyst and the lead engineer.  Analyst will now analyze the fasteners in the PSS.

- Checking redlines for the X-Y sine sweep transition frame drawings were incorporated.

- The top level assembly drawing for the assembly of the mass simulator into the Vacuum Case Test Fixture (VCTF) has been completed and submitted to checking.  In addition, the drawings have been supplied to stress for analysis.

Vacuum Case

- The UT inspection of the Vacuum Case closeout welds has been completed.  The final report is in work and will determine which areas need to be repaired.  Repairs and inspection are expected to take 1-2 days.

- DRs for the STA Vacuum Case are being worked.

- The drawings for the VC Shipping Fixture modifications have been submitted to checking.

Modal & Static Tests

- Work is progressing on generating STEP and IGES models of the AMS-02 Payload for delivery to IABG.  The STEP model has been successfully created but the IGES model conversion process is currently crashing due to the limitation of the PC.  The conversion process is being resubmitted with a lower resolution on parts to see if the PC can handle the translation.  In addition, the model is being submitted to a server for translation by the Unigraphics system administrator.  Problems are still being encountered with the translation and it will be allowed to run over the weekend to determine if the conversion will work.

Avionics

- Continued efforts in resolving Uninterruptible Power Supply (UPS) cable integration issues so that manufacture of the UPS can begin.

- Continued efforts in resolving CDD thermal test issues so that manufacture of the CDD test article can begin.

- Continued efforts to publish Revision B to the Uninterruptible Power Supply (UPS) State of Work.

- Resolved bonding and grounding requirements definition for the AMS-02 MLI specification, and provided revised text with these changes to EC.  The AMS-02 MLI blankets must be compliant with ISS requirements found in SSP-30245 and with SSP requirements, as documented in NASA/TP-1999-209263.  The revised text was reviewed with the local Boeing co-chairman of the ISS Electromagnetic Effects Panel (EMEP), and who concurred with the wording.

- Began reviewing the drawings for the flight article integration cables.  Following drawing review, PRs will be placed to procure materials for flight cable assembly.

- Inspected the Flight Remotely Operated Electrical Umbilical (ROEU) Payload Disconnect Assembly (PDA), and several discrepant items were found.  These were identified to SSP, USA and Boeing engineers and QA, who will submit rectifying instructions via E-mail.  The AMS-02 team will be responsible for implementing these steps.

- Successfully resolved an issue with fault path bonding (Class H bond) via riveted joints on the Lower USS.  This issue was identified when it was determined that EM can only perform Class 1A (not Class 3) touch-up chem-film alodining.  The concern was that the Class 1A alodine would have greater electrical resistance that the Class 3 alodine, and that the resistance values might exceed the requirement for Class H bond.  A milli-ohm meter was used to measure the resistance across several Lower USS riveted joints, and these values are several orders of magnitude lower, or better, than the requirement.  Additionally, the approach to effecting fault path bonding over riveted joints was reviewed with the local Boeing co-chairman of the ISS Electromagnetic Effects Panel (EMEP), and who concurred with the design.

Experiment Mentoring (ECAL)

- Meetings were held with NASA ES representatives twice this week to discuss ECAL bolt analysis issues.  The ECAL bolts were reanalyzed to show compliance with NSTS 08307 requirements.  Negative margins of safety for the gapping of the bolts attaching the Bracket to Side Panel interface was discussed at length.  Actions were given to prove that gapping would not cause a shift in the fundamental frequency of the ECAL assembly and show that the gapping would not result in any fatigue problems in the bolts themselves.  The additional analysis was completed and the results were presented to NASA ES representatives.  The ES representatives were satisfied with the analysis results and agree that we have satisfactorily proven that joint separation for the ECAL is not an issue.  These analysis results will be documented and issued as a separate report to be sent to both the ECAL developers and NASA.  Replacement bolts for the ECAL will be ordered this coming week.