# Implementation Plan: Deployment of Caribbean Broadband Stations for Improved Earthquake Monitoring and Tsunami Warning

Draft: June 11, 2005

I. Introduction

The USGS will deploy by September 2006 nine new seismic stations to support U.S. efforts to improve tsunami warnings in the Atlantic and Caribbean region. Destructive earthquakes and tsunamis are known to be a threat in the Caribbean causing damage, not only from inundation and strong ground shaking, but also from liquefaction and extensive land sliding. Installation of the new seismic stations will be a collaborative effort involving member institutions of the Middle America Seismograph Consortium (MIDAS) including: the United States Geological Survey (USGS), the Puerto Rico Seismic Network (PRSN), Seismic Research Unit of the University of the West Indies, The Departamento de Fisica, Universidad Nacional Autonoma de Honduras, Instituto de Geociencias,Universidad de Panama and other institutions in the region. The following implementation plan outlines the roles and responsibilities of the USGS and its collaborators as well as a time-table for project completion by September 2006.

##### Summary of Proposed Stations

This following is a summary of the nine proposed station locations. For planning purposes stations are divided into two groups, based on two parameters: 1) local cooperating partner, which roughly correlates to geographic region and, 2) the level of development required for installation of the site. At this time the options are considered either reoccupation and upgrade of an existing regional seismic station or, a complete new build. We hope to reoccupy as many as seven existing regional network short-period stations and thereby install as few as two complete new stations. New stations will require more resources than an upgrade of an existing station. This list is preliminary and is subject to change depending on issues such as local site conditions, the quality of existing and planned broadband stations, partner considerations and local infrastructure. Detailed information is outlined below and mapped in Figure 1.

Trinidad/Tebago (lat: 10.350 lon: -61.241) Figure 1

Partner: Seismic Research Unit of the University of the West Indies in Trinidad.

Development: equipment upgrade of existing short-period station.

Barbados (lat: 13.166 lon: -59.556) Figure 1

Partner: Seismic Research Unit of the University of the West Indies in Trinidad.

Development: equipment upgrade of existing short-period station.

Antigua (lat: 1 7.566 lon: -61.795) Figure 1

Partner: Seismic Research Unit of the University of the West Indies in Trinidad.

Development: equipment upgrade of existing short-period station.

Dominican Republic (lat: 19.016 lon: -71.145 15) Figure 1

Partner: Puerto Rico Seismic Network (PRSN)

Development: equipment upgrade of existing short-period station.

Cuba, Guatnanamo Bay (lat: 19.983 lon: -75.196) Figure 1

Partner: USGS International Programs office

Development: complete new station build.

Grand Cayman Islands (lat: 19.283 lon: -81.234) Figure 1

Partner University of the West Indies, Mona

Development: equipment upgrade of existing short-period station.

Honduras (lat: 14.616 lon: -87.347) Figure 1

Partner: The Departamento de Fisica, Universidad Nacional Autonoma de Honduras

Development: equipment upgrade of existing short-period station.

Panama (lat: 9.183 lon: -79.0769) Figure 1

Partner: Instituto de Geociencias,Universidad de Panama

Development: equipment upgrade of existing short-period station.

Turks and Caicos Islands (lat: 21.883 lon: -71.942) Figure 1

Partner: Puerto Rico Seismic Network (PRSN)

Development: complete new station build

Figure 1: Planned installations of the Caribbean Seismic project. (map by A. Tarr)

II. Identification of the Roles and Responsibilities of Participating Organizations

The upgrade and expansion of seismic monitoring in the Caribbean will be a collaborative, international, multi-institutional effort led by the USGS that will leverage existing network capabilities and infrastructure in the region. A description of each participating institution, areas of interest and/or responsibility, potential roles and detailed contact information is provided.

1. Caribbean Partners

Puerto Rico Seismic Network, University of Puerto Rico

The 30-station Puerto Rico Seismic Network (PRSN) was originally established by the USGS in 1974.  In 1987, the short period network was transferred to the Department of Geology, University of Puerto Rico at Mayaguez. PRSN will help in coordinating the siting and installation of a seismic station in the Dominican Republic (DRP Figure 1) and TKC in the Turks and Caicos Islands (TKC Figure 1). The PRSN will play a critical role in identifying local partners at least two stations and evaluating the upgrading of at least three existing sites in the eastern Caribbean in collaboration with the Seismic Research Unit of the University of West Indies in Trinidad. The PRSN will be a major partner in the project with significant involvement in at least five stations.

Contact: 	Christa G. von Hillebrandt-Andrade, Director of PRSN

email: christa@midas.uprm.edu

http://redsismica.uprm.edu

Seismic Research Unit of the University of the West Indies in Trinidad.

The Seismic Research Unit (SRU) is the governmental agency responsible for monitoring earthquakes and volcanoes for the islands of the Eastern Caribbean. SRU, in coordination with the USGS and PRSN, will evaluate siting and upgrade-options for seismic stations on the Islands of Antigua, Barbados and Trinidad/Tobago (ANT, BAR, TTB Figure 1).

Contact: 	Dr. Richard Robertson, Head of the SRU

email: richie_robertson@uwiseismic.com

phone: (868) 662-4659

Lloyd Lynch, seismic engineer

http://www.uwiseismic.com/index.html

#### Jamaican Seismic Network: University of the West Indies

Since the late 1960's, the University of the West Indies has operated the Jamaican Seismograph Network (JSN) on Jamaica and Grand Cayman Island.  The USGS will pursue the identification, siting and permitting of a station on either Grand Cayman or Jamaica with full coordination with the JSN.

Contact: 	Margaret Wiggins-Grandison (Earthquake Unit, University of the West Indies, Mona Campus)

wwwlibrary.uwimona.edu.jm:1104/research%20day%202005/Earthquake%20Monitoring.doc

Honduras

To ensure comprehensive seismic monitoring coverage of the Caribbean basin, the USGS plans to deploy seismic stations in Honduras and Panama.  These stations provide improved coverage of the Central America subduction zone and western most Caribbean, and these new stations are strategically located to compliment existing GSN stations in Mexico (TEIG) and Costa Rico (JTS).  The Departamento de Fisica, Universidad Nacional Autonoma de Honduras presently operates five stations.  The intent is to coordinate with the Department on the possibility of upgrading an existing station in the Tecucigalpa area.

Contact:	Gonzalo Cruz-Calderon

Departamento de Fisic, Universidad Nacional Autonoma de Honduras

http://www.unah.hn

#### Panama

Instituto de Geociencias Universidad de Panama (UPAN) is a member of the MIDAS consortium and operates a small number of stations in Panama. The intent is to coordinate with the Department on the possibility of upgrading an existing station in the Panama City area.

Contact: 	Eduardo Camacho

INSTITUTO DE GEOCIENCIAS UNIVERSIDAD DE PANAMA

Cel  675-0410 Fax 263-7671

http://www.igc.up.ac.pa

#### Cuba – US military, Guantanamo Bay Naval Base

There are no existing seismic monitoring stations at Guantanamo Bay Naval Base.  The USGS will assume the primary role of siting and installation of a station within the U.S. controlled portion of Cuba.  Coordination for the permitting and siting of the station will be done through the USGS International Programs office and installation will be done through one of the USGS Earthquake Hazards Program field offices.

Contact:	Jean Weaver, USGS International Program Office, Reston, VA

jweaver@usgs.gov

2. USGS Participants

This is a collaborative, multi-institutional effort led by the USGS GHT in Golden, CO with participants from several different USGS offices. Due to the rapid deployment requirements and funding limitations, we will combine the resources of three USGS groups. By identifying USGS expertise and utilizing properly we will maximize the efficiency and productivity of this project. This is a unique approach in the USGS and should be a good model for future inter-office collaborations.

USGS Headquarters, Reston, VA

The USGS International Programs Office will serve in a coordinating role, facilitating interaction between USGS and host countries in the Caribbean.  These coordination activities will be focused both in the Caribbean and in Washington D.C. to ensure wide-spread communication.  The International Programs Office will also help in the coordination with U.S. agencies such as Department of State, NOAA, and Department of Defense.

Personnel:	Jean Weaver – USGS International Programs

Regional Specialist for Central America/ South America/Caribbean

Geologic Hazards Team (GHT)

The USGS Geologic Hazards Team will take lead responsibility on the U.S. side for site identification, permitting, instrument procurement, station installation, and station operation.  To accomplish these tasks, staff members from both the Golden, Colorado and Albuquerque, New Mexico offices will participate.  Responsibilities will be as follows:  siting, permitting, and instrument procurement will be the principal responsibility of staff in Golden.  Albuquerque and Golden field engineers will both participate in station configuration, testing, installation, and station operator training. Once the new stations are installed, data will be telemetered to GHT’s National Earthquake Information Center (NEIC) in Golden, CO, where network architects will reroute it to participating institutions and the NOAA tsunami warning centers.  Long-term operations and maintenance of the new stations will fall under the responsibility of the Albuquerque Seismic Lab, which also provides support for other Global Seismograph Stations (GSN) operating in the region (e.g., TEIG, SDV, Figure 1); the nine new stations will be managed as part of the GSN inventory.

Personnel: 	Dan McNamara – Project Coordinator/procurement

Jack Odum – station siting and permitting

Bob Hutt – ASL Coordinator

Mark Sharratt – Honeywell, Field and Telecommunications Engineer

### USGS Western Region, Menlo Park, CA

We anticipate that the deployment/installation phase of this project will require working on multiple stations simultaneously.  For this reason we will be dependent on the contributions of field engineers from other USGS offices. The USGS office in Menlo Park, CA will contribute field staff for the system integration and deployment of the Caribbean network project.

Personnel - 	David Oppenheimer – Northern California Seismic Network Coordinator

Dave Croker – Field Engineer

3. Additional U.S. Government and International Partners.

The seismic station deployment in the Caribbean is an international effort led by the USGS with significant contribution required from numerous network host nations and international institutions. The USGS will coordinate planning with numerous institutions that have an interest in the success of the Caribbean project. The following is a list of U.S. government and international organizations that will be included in all project coordination and planning.

###### National Oceanic and Atmospheric Administration – NOAA

NOAA is responsible for the oceanic portion of the planned tsunami warning and will be a major recipient user of the seismic data generated from the planned nine stations in the Caribbean region. The Pacific Tsunami Warning Center will act as the regional tsunami warning center for the Caribbean and is consequently a critical partner. The primary NOAA contact for USGS communications on the Caribbean will be Jeff LaDouce.

Intergovernmental Oceanographic Commission- IOC of UNESCO

IOCARIBE – sub-commission for the Caribbean

The IOC has been planning for a Caribbean Tsunami warning system for several years. The USGS will coordinate high level planning with IOCARIBE and it’s member institutions through international meetings and scientific presentations.

Middle America Seismograph Consortium (MIDAS)

The umbrella organization for seismology in the Caribbean region is the Mid America Seismology Consortium (MIDAS). The USGS has a 10-year partnership with MIDAS. Installation of the new seismic stations is a collaborative effort that will involve coordination with and contributions from several MIDAS member institutions.

###### Global Seismographic Network (GSN) Standing Committee

The standing committee of the Global Seismographic Network (GSN) has presided over the installation of hundreds of high-quality broadband seismic stations globally. The nine new Caribbean stations will be affiliated with the existing GSN and all planning will be coordinated through the GSN standing committee.

III. Project Timeline and Tasking

In this section we describe a number of tasks and subtasks required to complete the implementation by the end of September 2006. The dates are preliminary and subject to change depending on the schedules of individuals involved in the specifically identified subtasks.  Some tasks of each phase will be active concurrently.

Phase I:  Pre-Deployment Planning and Coordination: May-August 2005

Subtask 1: Identification of Participants – May-July 2005. Network operators from participating institutions in the region will be solicited to work closely with USGS staff to identify qualified individuals who can contribute to the deployment of the Caribbean stations.

Subtask 2: Organizing Meetings with Local Partners – May-July 2005. A critical objective for the Caribbean deployment is to develop a strong, shared partnership with host countries in the region.  To accomplish this, the USGS must engage senior government officials from the Caribbean nations and local seismic network operators very early in the planning stages.  To this end, USGS will either organize or participate in a series of meetings to brief participating governments, meet local contacts and participants, discuss deployment plans and solicit expertise.  The following is a list of meetings that are currently identified.  Representatives will be sent from the NEIC in Golden and/or USGS headquarters in Reston, VA.  Briefing materials will also be prepared to facilitate these meetings. Currently identified meetings are listed below.

Department of State Briefing – May 17, 2005

Jean Weaver, USGS

IOC-UNESCO, Mexico City Mexico, June 1-3, 2005

Jim Dewey and Jean Weaver, USGS

Washington D.C. Embassy Representative Meetings – May-July 2005

Jean Weaver, USGS

George Dragnet – Oceans Environment and State

Ambassadors and/or representatives from partner nations

Caribbean Geologic Conference, San Juan, Puerto Rico, July 17-21 2005

The USGS will coordinate with members of the PRSN and SRU to organize a Special Interest Group meeting to discuss planning and deployment of the proposed Caribbean stations. The purpose of this meeting will be to meet potential collaborators, present preliminary deployment plans, and to solicit ideas.

Subtask 3: Public Relations and Information Dissemination

Prepare Fact sheet – June 2005

An informal USGS information fact sheet will be prepared that provides an overview of the earthquake and tsunami hazards in the region, the rational for expanded seismic coverage, the opportunity to add or upgrade nine stations in the Caribbean basin, and the need for region-wide cooperation and coordination in the effort.  A draft version will be available for review by May 25, 2005. Dan McNamara, GHT. We will work with David Green at NOAA to create a joint statement on the project.

Prepare Website – July 2005

The USGS in Golden will lead in the creation of a project website. The website will be used to communicate the efforts of the group to interested parties, disseminate relevant information to all participants in the project, coordinate operations, and maintain the equipment inventory database.

Phase II.  Station Siting and Permitting.  Station location selection will be based on numerous requirements  including the type of development required, as outlined by the separate subtasks below. All stations will be evaluated on the following criteria:

- Vehicle accessibility.

2.   Site conditions such as proximity to bedrock and drainage.

- Security.

- Infrastructure (e.g., enclosure requirements, power, cultural noise sources).

- Availability of telecommunications, and satellite view.

- Availability of reliable AC power.

- Local contacts and maintenance personnel.

Subtask 1: Existing Station Identification and Evaluation: May-September 2005

In several cases we hope to reoccupy existing sites with upgraded equipment and communications. Each existing site will undergo a thorough evaluation based on the criteria discussed above. In several cases we have real-time data and can review spectral plots and telemetry statistics.

(see http://geohazards.cr.usgs.gov/staffweb/mcnamara/Projects/Caribbean.html)

Subtask 2: New Station Characterization and Evaluation: August. 2005-Feb. 2006

In several cases we will be required to build new broadband seismic stations. The sites will be evaluated and chosen based on the criteria discussed above. Responsible USGS personnel will be Jack Odum and Dan McNamara.

Subtask 3: Obtain permits for sites. Review memoranda of understanding (MOU) for esisting agreements with participating institutions. Responsible USGS personnel will be Jack Odum and Jean Weaver.

Phase III.  Procurement of Equipment/Hardware.  The USGS Geologic Hazards Team will have responsibility for identifying the major components for each station and purchasing of all of the equipment necessary to deploy the Caribbean stations.  Based on USGS equipment specifications and procurement authority, each of the nine stations will have the following major pieces of equipment:

Datalogger:			Quanterra Q330HR with Baler

Broadband Sensor:		Streckeisen STS-2 Low gain Seismometer

Strong-motion Sensor:	Episensor ES-T Force Balance Accelerometer

Power System:

Primary:	1000-2000 Watt Photovoltaic Solar Panel system with a bank of 5-10 deep-cycle, 12V, 60-100 amp-hour batteris , and a generator.

Secondary:		Local AC power and UPS

Procurement vehicles are currently in place for all of the above equipment due to ongoing contracts for the ANSS backbone upgrade.  Accordingly, orders will be placed for all equipment by July 30, 2005.  Approximately six months will be required before receipt of equipment (December 31, 2005).

Telecommunications options for the new stations must be researched.  Mark Sherrat (GHT, Albuquerque) will research options with SkyCasters and LibiSat. Concurrently, Alena Leeds (GHT, Golden) will explore options with Hughes.  These individuals, together with ASL and ANSS managers and Project Coordinator will determine preferred strategy for service.  This research should be completed by September 30, 2005.

Phase IV.  Equipment Testing and Configuration: Testing and system integration will occur at appropriate USGS facilities (either ASL or Golden).  Lab testing and integration is expected to take two months.  Assuming all equipment is delivered by December 31, 2005, testing and configuration should be completed by February 28, 2006. Instrument testing will take place with coordination between the ANSS NOC in Golden (Leeds, McNamara and ASL (Hutt).

Phase V: Training of Network Operators.  Operation and maintenance of the Caribbean stations will involve participants from a number of organizations in the U.S. and Caribbean region.  The USGS is committed to providing training assistance and technology transfer to all participants.  Training is designed to provide network operators with the knowledge and skills necessary to construct vaults and operate stations in the Caribbean.  Training will be conducted at appropriate USGS facilities and will involve the following activities:

- Training in the use of the appropriate computer software needed for configuring seismic digitizers, telecommunications equipment and acquisition computers,

- Training on the installation and trouble shooting of all components of a station that includes power systems, telecommunication equipment, sensors, and digitizers,

- Basic training in the operation and installation of seismic instruments (as a preamble to establishing seismograph stations in the Caribbean) and,

- Training in the construction of high-quality vaults to optimize performance of the Streckheisen STS2 broadband seismometer.

Basic training to take place with visits by appropriate staff to a workshop in the winter of 2006 (Jan.-Feb. 2006). Caribbean network operators must work closely with USGS staff to identify qualified individuals who will be responsible for coordination on the operation and maintenance of the stations. Scheduling should be coordinated so that selected engineers arrive in the United States during the equipment testing period.  The workshop will involve overview on installation and operation procedures of individual equipment components (sensors, dataloggers, telecommunications, power systems), conducting cultural noise surveys, testing of the equipment that will be deployed, and a field trip to a USGS operated station to view USGS engineer plans, operations and procedures.

Phase VI: Network Deployment: December 2005-September 2006.  Following the equipment testing, site evaluation, site selection and engineer training in the United States, all of the station equipment will be packaged and shipped to the local contacts.  We anticipate that a team of two USGS personnel will be sufficient for initial site evaluation. We also anticipate that 2-3 teams of 2 USGS personnel each will be required for site installation. If the USGS cannot provide the required number of field technicians, we will draw from the human resources pool of the ANSS. The USGS field teams will meet with local participants (1-2 person team), construct a vault and shelter then deploy the equipment.

Subtask 1. Reoccupation and Upgrade of existing Short-period Stations:  Where possible, USGS will seek to upgrade an existing station rather than deploy a new station.  This determination will be based on availability of stations in regions of interest, as well as station quality.  We estimate approximately 10-12 days for each upgraded station, including shipping, reassembly of equipment, and installation.

Subtask 2. New Station Development

In some cases stations will be built from scratch. New stations will require site preparation, including construction of the vault.  Where feasible, new vaults will be based on ANSS/EarthScope design criteria, which is under re-evaluation at ASL.  The time required to construct a new station is estimated to be approximately 12-20 days per site, including vault construction, station configuration, and station installation.

Preliminary estimates are that two crews of two people each will be required to install the stations by the end of September 2006.  Each crew requires a minimum of one USGS person on site during the installation.  USGS personnel are required because they are certified installers of Hughes, SkyCasters and LibiSat telecommunications equipment and they are needed for initial configuration of dataloggers and commissioning of the station into the NEIC processing system.   When possible, the USGS would like to partner one of their personnel with trained technician(s) or assistants from participating institutions.

Phase VII: Network System Integration: September 2006.  Data will be telemetered directly to the NEIC in Golden, CO.  Data will then be integrated into the NEIC processing system for global earthquake monitoring and distributed in real-time to interested organizations and agencies of the U.S. government.

The USGS will provide the real-time data to participating institutions in either Earthworm format or as a LISS service.   Alternatively, the USGS will provide all of the data to the PRSN and PRSN will provide customized data services to individual networks in the region.

The USGS will provide data from these new stations to the NOAA tsunami warning centers via established mechanisms of data exchange.  If the existing dedicated links between NEIC and the NOAA tsunami warning centers cannot accommodate the increased data volume, the USGS will work with NOAA to increase the bandwidth necessary or provide the data to them via the public internet.

Phase VIII: Long-Term Operations and Maintenance.  The USGS will work with ASL GSN and Caribbean region partners to develop a plan for ongoing operations and maintenance.  The plan will include specifics on required staff support (e.g. field engineers, analysts, computer system administration) and associated salary costs and other operational costs (e.g. costs for power and supplies) that are needed to maintain the seismograph station reliably.  In addition, the groups need to assign appropriate staff to operational roles that involve maintenance of field systems, telecommunications, computer systems, and data processing.

IV.  Refinement of Tasking and Implementation Plans

Following initial activities specified in Phases I and II more detailed timelines will be provide on a station by station basis.  At this time, station specific implementation plans will be submitted for review by the USGS and participating institutions.  These plans will following the guidelines outlined in the Roles and Responsibility Memo dated May 7(?), 2005 (see attached).

V. Data Management

Waveform data will be telemetered in real-time to the ANSS NOC for processing and initial earthquake locations. Processing will include automated and manual QC procedures performed by the USGS ASL Data Collection Center (DCC). Data will also be transmitted from the ANSS NEIC other interested organizations over public and dedicated internet. Existing data links from the ANSS NEIC may require upgrades to handle the increased data load to the tsunami warning centers. Internet connections to local partners may also require upgrades to utilize the real-tome data feeds. Recipients of real-time data include:

- The local host institution,

- NOAA tsunami warning centers,

- IRIS DMC.

VI. Summary of Proposed Schedule and Assignments

- Fact Sheet: June, 2005, Dan McNamara

- Implementation Plan, June 2005, Dan McNamara

- Identification of Participants: May-July 2005

    - Jean Weaver, Dan McNamara. Bruce Presgrave, Jim Dewey

- Meetings with Local Partners (Identify local operators) : May-July 2005

    - Dan McNamara, Jean Weaver

- Evaluate Proposed upgrades of existing stations: May-Sept. 2005

    - Trinidad, Barbados, Antigua, Dominican republic, Grand Cayman Honduras Panama

    - Jack Odum, Dan McNamara

- Research Possible New stations: Aug.-Sept. 2005

    - Cuba, Turks and Caicos

    - Jack Odum, Dan McNamara

- Apply for Permits and determine MOU status: June-Oct. 2005

    - Jean Weaver, John Derr

- Purchase New equipment: June 2005

    - Barbara Bogaert, Dan McNamara

- Determine VSAT needs: June 2005

    - Alena Leeds, Mark Sharrat

- Equipment Delivery: by Dec. 31, 2005

- Equipment Configuration and testing: Jan.-Feb. 2006

    - Leeds, McNamara, Hutt

- Training: Jan.-Feb. 2006

    - Dan McNamara

- Station Deployment: March-Sept. 2006

    - Dan McNamara coordinator

- Data Integration into real-time systems: March-Sept. 2006

    - Dan McNamara coordinator