United States Department of Agriculture (USDA) eGovernment Program

Management and Planning Profile – Project Plan

eLearning Business Case

Final

February 2003

Table of Contents

Revision History	iii

Previous Change History	iii

Document Sign-off	iii

1	Introduction	1

2	Staffing Plan	2

2.1	Purpose	2

2.2	Contracting vs. USDA Employees	3

2.3	eLearning Program Team	4

2.3.1	Advisory Team	5

2.3.2	eGovernment Program Management Office	6

2.3.3	eLearning Project Team	7

3	Quality Assurance Plan	10

3.1	Purpose	10

3.2	Application Standards and Policies	10

3.3	Configuration Management	11

3.4	Testing	12

3.4.1	Component (Unit) Testing	13

3.4.2	Assembly Testing	13

3.4.3	Product (System) Testing	14

3.4.4	Test Plan Quality Assurance	14

3.5	Reviews, Walkthroughs, and Audits	15

3.5.1	Reviews	15

3.5.2	Walkthroughs	15

3.5.3	Audits	15

3.6	Verification and Validation	16

3.7	Issue Tracking Process	16

4	Project Schedule	17

4.1	Purpose	17

4.2	eLearning Project Tasks	18

4.2.1	eLearning Overall Tasks	18

4.2.2	eLearning Implementation Tasks	18

4.3	Plan for Progress Updates	23

4.4	Assessing and Managing Schedule Changes	23

5	Costs	24

5.1	Overview	24

5.2	Cost Detail	24

6	Project Deliverables	25

7	Assumptions	26

8	Appendix A – eGovernment Advisory Team	27

8.1	eGovernment Executive Council	27

8.2	eGovernment Working Group	27

8.3	eGovernment Steering Committee	27

8.4	Agency eGovernment Teams	28

9	Appendix B – Project Plan Deliverables	29

# Revision History

## Previous Change History

Table a – Previous Change History

| Version | Date | Author | Comment |
| --- | --- | --- | --- |
| 0.1 | 10/30/2002 | Amanda R. Plummer | Initial Draft |
| 0.2 | 11/04/2002 | Amanda R. Plummer | Updated with team comments |
| 0.3 | 11/12/2002 | Amanda R. Plummer | Updated with team comments |
| 1.0 | 11/18/2002 | Elaine K. Turville | Updated with team comments |
| 1.1 | 11/20/2002 | Amanda R. Plummer | Updates to project schedule and staffing plan |
| 1.2 | 11/22/2002 | Amanda R. Plummer | Updated with team comments, costs, and assumptions |
| 1.3 | 11/22/2002 | Sara Q. Tyndall | Updated formatting |
| 1.4 | 11/23/2002 | Amanda R. Plummer | Updated with team comments |
| 1.5 | 11/24/2002 | Elaine K. Turville | Updated with team comments |
| 1.6 | 11/25/2002 | Elaine K. Turville | Updated with team comments |
| 1.7 | 12/03/2002 | Sara Q. Tyndall | Updated formatting |
| 1.8 | 12/09/2002 | Elaine K. Turville | Updated Naming |
| 1.9 | 02/03/2003 | Liesl M. Awalt | Updated with team comments |
| 2.0 | 02/05/2003 | Liesl M. Awalt | Added reference to early adopters |
| 2.1 | 07/25/2003 | Gregory A. Zanowski | Updated to read “Final” |

## Document Sign-off

Table b – Document Sign-off

| Date | Name | Title |
| --- | --- | --- |

# Introduction

The Project Plan is the comprehensive plan for delivering the eLearning solution. It delineates the who, what, why, when, where, and how aspects of the project. It is the road map for achieving the program objectives and realizing the project benefits.  The Project Plan is a critical communication tool and is at the heart of the planning and management processes.

Ongoing project planning is crucial to a successful investment.  The Project Plan provides the starting position for project mobilization.  It provides a baseline work plan and identifies the key components of the project such as the project team, the tasks that will be completed, and the timeframe for completing the tasks.  The Project Plan will guide eLearning team members, management, and stakeholders throughout the phases of the project.  During the course of the project, it may be necessary to update the plan to accommodate approved change requests.

The Project Plan for eLearning includes the following sections:

- Staffing Plan:  Describes the project team’s organizational structure and their respective roles, responsibilities, and desired skills.

- Quality Assurance Plan:  Addresses the quality management activities for the duration of the project.

- Project Schedule:  Identifies the timeline the project will follow to achieve its stated objectives.

- Costs:  Describes the estimated cost to complete project tasks.

- Deliverables:  Defines all deliverables that will be created during the project.

Assumptions:  Identifies assumptions made while writing the project plan, which may affect the estimates in each section of the Project Plan.

# Staffing Plan

## Purpose

Managing staff resources properly is critical to the success of all eLearning initiatives.  The staffing plan will give an overview of the teams, roles, and responsibilities that will be required during various phases of the project to implement and operate eLearning.

It is critical that the staffing plan is flexible.  It is written to allow for changes in the number and type of staff and/or contracted resources, depending on the project phase and the types of tasks being conducted.  For example, early phases of the project will require a large number of implementation resources such as designers, developers, and testers.  During later phases of the project, the team composition will shift to more heavily favor operational roles such as maintenance, administration, support, etc.

The staffing plan will address the following components:

- Government vs. Contracted Resources; and

- eLearning Project Team.

## Contracting vs. USDA Employees

The recommended project team will be a mixture of USDA employees and contracted resources.  Personnel resources will be scaled according to project demands at a given phase.  Initial phases of the project will require a high number of contractors while USDA employees undergo the pre-requisite training and exposure to new technologies.  As the organization’s familiarity and knowledge of the technologies becomes integral to daily business operations, the ratio of contractors to USDA employees will decrease.

It is anticipated that USDA employees will focus in the following areas:

- Coordinating with USDA eGovernment initiatives on an ongoing basis;

- Documenting roles and responsibilities;

- Conducting business process re-engineering efforts;

- Defining workflows and associated rules, roles, and responsibilities;

- Identifying USDA customers and analyzing their needs;

- Creating educational and marketing materials; and

- Promoting enterprise-wide and Agency communications.

Contracted resources will likely focus in the following areas:

- Assisting with system integrations;

- Providing program and project management;

- Developing UI standards and associated templates;

- Providing communications support;

- Assisting with training content conversion activities; and

- Facilitating vendor relationships and procurement activities.

## eLearning Program Team

The eLearning program team will be comprised of resources with a variety of skill sets.  Throughout the lifecycle of the project, the resources on the project team will fluctuate depending on the skill set that is needed at the current time.  The eLearning program team is founded based on some fundamental tenets, including the following:

- Focus on cross-agency participation to continuously and correctly represent requirements from Agencies;

- Focus on a structure that provides governance due to executive sponsorship;

- Apply dedicated USDA full-time resources to run the initiative;

- Embody a mixed structure of both contractor and Federal government employee staff;

- Manage the eLearning application service provider to ensure delivery of services according the Service Level Agreement (SLA) provisions; and

- Address the need for business expertise to ensure technology correctly supports the initiative.

The Advisory level of the Program Team will consist of Agency liaisons to the eGovernment team and Agency business managers. Their responsibilities include the following:

- Ensuring that USDA receives regular reports on the implementation of the initiative;

- Ensuring that Agencies adhere to existing laws, regulations, and standards;

- Ensuring that any requests for additional resources are made according to existing rules;

- Ensuring that requests for cross-agency services (such as portal services or B-to-B extranets with Agency or USDA partners) are managed; and

- Overseeing all efforts are coordinated internally with Agency management, including CIOs and Agency administrators.

Once the Program Team develops further within the Agencies, the roles will become more diverse. These roles will include technical, business, and other more specialized roles.  Figure 2.3 – eLearning Program Team displays the organizational chart for the eLearning initiative.

Figure 2.3 – eLearning Program Team

### Advisory Team

The eGovernment Advisory Team, led by USDA’s OCIO eGovernment Executive and supported by the Program Management Office, will consist of the following groups:

- eGovernment Executive Council;

- eGovernment Working Group;

- eGovernment Steering Committee; and

- Agency eGovernment Team.

The Advisory Team will be responsible for periodically monitoring Agency initiatives for adherence to USDA’s Strategic Plan, existing laws and regulations, OMB requirements, and business requirements. They will also be responsible for mediating any conflicts that arise among the Agencies and resolving them in the best interest of USDA in upholding or modifying existing standards.  Please see Appendix A:  Advisory Team for a detailed description of all advisory groups.

### eGovernment Program Management Office

An eGovernment Program Management Office (PMO) will provide overall strategic planning and project management for the eGovernment initiatives including eLearning, eAuthentication, and eDeployment.  This will ensure that all eGovernment initiatives are planned and implemented in a consistent manner under the auspices of the eGovernment executive leadership and advisory team.  The Program Management Office will require the following skills:

- Project management;

- Financial management;

- Contract management;

- Asset management; and

- Documentation management.

Members of the Program Management Office require the skills to work effectively with others and provide both leadership and support to the team in their respective areas.

- Project Managers ensure that all areas of the project match the scope, schedule, and resources identified at the beginning of the project and establish an accurate and efficient workflow. If issues arise that affect these areas, they manage the risks by working with staff and management to resolve the issues efficiently and effectively. Ideally, these risks are either avoided with a well-developed project plan and timely and effective communication with staff about deliverables and schedules, or seen very early and mitigated with the lowest impact on the project. They also serve as liaisons with the application service provider’s management team.

- Training Managers are experienced in training development and management and fully understand the business requirements of both USDA and its Agencies. They lead the planning and execution of Agencies’ eLearning initiatives by coordinating with all training areas within and outside of the organization.

- Contract Managers oversee all aspects of vendor contracts, including budget, staffing, work quality, and schedule. They ensure that the contract is managed according to all Government and industry standards.

### eLearning Project Team

The eLearning Project Team will be an integrated team, consisting of USDA employees representative of multiple organizations, in addition to contractors.  The primary objective of this team is to ensure that the eLearning solution will meet the needs of all of its users.

The Project Team will require employees and contractors with specific skill sets to fill technical, functional, and other more specialized roles.  These roles are described in greater detail in the following section.  Full-time individuals will coordinate and perform eLearning tasks, especially working with the application service provider to coordinate the USDA side of the implementation activities.  Additional resources will be added to the team as need.

#### Technical Implementation Team Roles

Since the solution is being contracted to an application service provider, the provider will have final determination of the staffing for the Technical Team.  The following roles are included as guidelines.

- Technology Architects are responsible for defining and planning technology infrastructure aspects of the business capability and for translating technical requirements into the architecture/design of the technology infrastructure. The technology architect becomes involved in the project during the early planning stages and stays involved.

- Database Administrators develop and maintain information databases and data mining initiatives, ensure data integrity, and maintain their functionality with customers and business partners.

- Application Developers/Programmers develop and maintain web-based applications and maintain their functionality with customers and business partners.

- System Integrators ensure that the selected systems work with current approved Agency systems, including legacy systems and applications.

- Technical Quality Assurance (QA) Analysts and Testers ensure that the systems work properly and that the data/content they produce are error-free and output into the proper formats. They also ensure that the systems operate under all configurations.

#### Functional Team Roles

The application service provider along with USDA employees and contractors will have joint responsibility for the Functional Team Roles.

- Requirements Analysts capture the requirements in use case models, use cases, and supplementary specifications. Facilitating the definition of the scope and details of the requirements, how the requirements relate to and depend on each other, and promoting a common vocabulary, are this role's most important activities.  This role also ensures that the stakeholders agree to the written requirements.

- Business Analysts develop and follow all levels of the business strategy, including strategic plans, existing Federal laws and regulations, OMB requirements, and other Agency-specific business requirements. They see the big picture of how these systems fit into the overall strategy of the organization, identify and manage project sponsors, preside over the project mandate process, devise an overall workload and budget strategy, and work with the project teams to ensure that the project mandate is fully integrated into the organization. They understand the business, know how to negotiate, understand the concepts and complexities of the initiatives, and can motivate staff and management.

- Human Factors/User Interface (UI) Specialists ensure that applications, forms, and content comply with Section 508 guidance and follow industry usability standards and audience analysis for interface design. They run page usability and portability user tests to document how usable and navigable a page is, as well as resolve any issues associated with the integration of text, media, graphic design, and branding with the UI. These specialists must use all available methods to understand the identified audience’s needs, including what types of information they want and how they want to receive the information, such as the format, display.

- Training and Documentation Specialists will ensure that all system users are properly and adequately trained, including follow-on training as the system is upgraded. Although the initial training will be provided to the lead staff by the software vendors and system integrators, future training, including hand-on training and online training, will need to be developed for system users and technical staff. Documentation will likely be a combination of material provided by the software vendors and system integrators and material developed about USDA and Agencies systems and any custom processes developed.

- Training Content Analysts analyze USDA/Agency content submitted by Training Content Authors and Editors and recommend which training content should be included within the new solution. They also recommend which new training content needs to be designed, based on need.

- Training Content Authors/Subject-Area Specialists are USDA/Agency staff with experience in and responsibility for developing media and/or writing training content specific to their areas of expertise for targeted or general audiences.

# Quality Assurance Plan

## Purpose

The Quality Assurance Plan for eLearning outlines the methods and procedures that will ensure that stakeholder expectations and performance objectives are met, that project staff and business partners perform in accordance with metrics set forth in the requirements documents, and that measurable indicators are systematically tracked to assess progress and promote accountability.  It helps to ensure that the project is focused on improving delivery capability in terms of people, processes, and technology.

Although the approach for the Quality Assurance Plan is created in the early stages of the project, it will be updated and managed throughout the project lifecycle.  The Quality Assurance Plan describes quality assurance at the system level, software level, and data level.  It also identifies the type of quality assurance support that is necessary for effective project management.

## Application Standards and Policies

Application standards and policies consist of the standards, rules, and guidelines to be followed during the application development process for programming and documenting programs. Application standards and policies are not meant to be used for training purpose, but rather, as a reference manual for the standards set by the development architecture.

Application standards and policies will provide a consistent way of designing, documenting, and programming over the different areas of work, such as user interface design, database design, and application development.  Quality reviews may be derived from these standards and policies.

The application standards and polices will consist of the following:

- Programming standards;

- Performance design guidelines;

- File/Directory naming standards;

- Application program interface (API) description and use;

- Procedures for using the development architecture and its operations support components (e.g., checking in and out code, when backups occur and how to retrieve archived files, compiling programs);

- Data standards; and

- User interface (UI) standards.

## Configuration Management

Configuration management is the process for controlling changes that occur during the project.  This includes managing changes to several types of project deliverables, including the work agreement/ arrangement letter, project plan, design documents, application modules, and other components of the business capability.

Configuration management relies on a systematic approach for controlling the changes that occur during the project.   The process defines the configuration management activities are to be completed, how they are to be accomplished, who is responsible for performing specific activities, when the activities are to happen, and what resources are required.

The configuration management process is determined during project planning.  The process enforces the integrity of the project’s work products throughout all stages of development and maintenance.  The cornerstone of configuration management is the change control process to manage and track changes to all work products.  The change control process will be coordinated with issue tracking processes.

## Testing

Testing is the primary step for evaluating compliance with requirements and ensuring overall quality.  Testing for the eLearning initiative will be conducted at several levels.  There are three generic test phases, which will be conducted for both application development and technology infrastructure delivery.  These phases include:

- Component or Unit Testing;

- Assembly Testing; and

- Product or System Testing.

The same basic steps are followed for each phase of testing. The driver of every test phase is a specification, and the output of every test phase is an executed test model that includes test conditions and expected results, a cycle control sheet, test scripts, and actual results. This allows the testing activities to be described generically throughout this section of the Quality Assurance Plan, with unique considerations or techniques listed in the tasks related to each test phase.

Specifically, the activities common to all phases of testing in the application and architecture segments are as follows:

- Develop test approach: Provide the objectives, schedule, environment requirements, and entry and exit criteria for the test stage.

- Plan test: Identify test conditions and test cycles for the test stage.

- Prepare test: Define input data and expected results, scripts the test cycles, defines stubs and job streams, and prepares the cycle control calendar.

- Establish test environment: Ensure the environment is established and tested before test execution.

- Execute test: Perform the scripts contained in the test model, compares the actual results to the expected results, and identifies and resolves discrepancies.

### Component (Unit) Testing

A component test is the test of an individual component of the solution. The objective of a component test is to ensure that the component correctly implements the design specifications.

All components of a business capability including technology infrastructure, application programs, conversion programs, input/output (I/O) modules, and job control language are subject to component test. Some human performance and business process components may need to be tested with other components of the business capability.  All of the capabilities of the component should be exercised during component test to ensure that the component meets the functional and quality requirements of the specification.

It is important that the driver of a component test be the detailed design specification documents and not the component itself. If, for instance, one sets out to exercise all of the paths through a particular component as written, the component may pass the tests successfully and yet not implement the specifications from which it was supposed to be created.

### Assembly Testing

The assembly test verifies the interaction of related components to ensure that the components function properly when integrated. As in the case of component testing, this can occur at different levels depending upon ones perspective. Considering the business capability as a whole, assembly testing occurs when all of the business capability elements are brought together for the first time in the business capability release test. Within each business capability element (business process, technology and application), the assembly tests are a function of integrating individually developed components and making sure they work together properly.

In testing either the technology infrastructure or applications, assembly test ensures data is passed correctly between screens in a conversation or batch process and messages are passed correctly between a client and a server(s). The application flow diagram within the application architecture will depict the assemblies—either online conversations or batch assemblies—that will be assembly tested.

By the completion of assembly testing, the object of the test should be technically sound and the information flow throughout should be correct. Component and assembly testing ensures that all transactions, database updates, and conversation flows function accurately.

### Product (System) Testing

The product or system test ensures that all requirements have been met. Like the aforementioned tests, product testing may also occur at multiple levels. However, within these multiple levels, the purpose of testing is the same: to ascertain that the requirements have been met.

The product test verifies the actual functionality of the solution as it supports the various cycles of transactions, the resolution of suspense items, the workflow within organizational units and among these units. The specification against which the product test is run is the specification of all applicable requirements.

User Acceptance Testing, or focused user verification of capabilities, is accomplished through a final iteration of product (system) test execution.  In this test, users execute a sub-set of the system test scenarios that represent more end-to-end capabilities. A simulated production environment with production data is used for this iteration of testing.

### Test Plan Quality Assurance

Designated reviewers will participate in all formal testing and qualification activities.  These activities include the following verifications:

- Ensure that test plans adequately verify the software requirements;

- Confirm test environment has a controlled configuration;

- Validate that test data supports all test cases;

- Maintain the integrity of and adherence to test plans during testing; and

- Ensure accurate documentation of test results.

## Reviews, Walkthroughs, and Audits

The goal of the Quality Assurance Program is to deliver an error-free system that meets all requirements and satisfies the needs of the stakeholders and users.  As part of that goal, the quality of the project will be subjected to review, audits, and walkthroughs.  Both processes and technical solutions will be reviewed for quality assurance.  Within the Quality Assurance Plan, objective measures of quality will be used to:

- Monitor compliance;

- Identify deficiencies;

- Correct problems; and

- Avoid repetition of errors by identifying and eliminating their causes.

All reviews, walkthroughs, and audits will be documented.   If an issue is identified, it will be entered into the issue management process and formal project documentation will be updated.

### Reviews

Full reviews will be conducted to verify eLearning system functionality.  To comply with the issue management process, any issues that are identified will initiate the creation of a system change order.  Functionality reviews will begin at the end of the development phase and any issues or concerns will be identified and corrected during the product test phase.

### Walkthroughs

The eLearning Technical Implementation team will be responsible for conducting walkthroughs to support the development and change process.  Walkthroughs consist of a structured series of peer reviews to enforce standards, detect errors, and improve system quality.  The final responsibility of the walkthroughs lies with the eLearning project management.

### Audits

A technical advisor or other designated technical auditor may be requested to conduct internal audits of the processes for development, issue management, and integration activities to verify compliance with USDA standards.  The project management will create an audit schedule and coordinate the schedule with the auditor.  Detailed results will be reported to management and appropriate team members in a written report.

## Verification and Validation

Verification and validation are performed to ensure that the total collection of deliverables is consistent with the specifications.  The deliverables are verified against the requirements, facilitating stakeholder sign-off. This process helps ensure that the current and future design work products are produced as planned.  In some cases, a separate contract for independent verification and validation may be considered.

The outcomes of this process are:

- Reconciled gaps between design and intent;

- Documented stakeholder buy-in; and

- Verified and validated application design.

## Issue Tracking Process

The issue tracking process documents any issues, open points, or decisions that will have a significant effect on the project. It also records design rationale for later stages of development, particularly maintenance.

An issue tracking process along with issue management is used to ensure that all issues are tracked and resolved.  This deliverable provides a framework to structure discussion of project issues from assessment to resolution. It also helps provide an audit trail of discussion and decisions on all project issues.

A separate issue entry will be created for each issue. These entries will be used as a reference for use by those working and reviewing issues. When creating an issue entry, the following information should be incorporated:

- A general description of the problem to be resolved. A brief and a full description, the issue class (e.g., management), and the items and areas of the project affected by the issue are all included here. Also noted are those groups and individuals that have a stake in the solution of this problem: management, development teams, and business representatives. Other information defined includes the issue's priority, status, date created, author, date due for resolution, and the responsible party for resolving the issue.

- A list of possible, proposed, and final solutions to the problem. In the sample, the process by which the staffing shortfall issue was resolved has been documented. Listed here are several possible alternative solutions to the problem and a brief description of the final resolution of the problem. A brief timeline of the resolution process is also provided.

# Project Schedule

## Purpose

The Project Schedule details the significant milestones over the life of the project.  The Project Schedule will support and allow for the tracking of project activities.

The Project Schedule shows the target start and stop dates for the activities associated with the accomplishment of project milestones.   It is a task-oriented decomposition of the total work scope of the project from planning through implementation.

The Project Schedule contains a listing of implementation and management tasks, the technical approach, configuration management, deliverables and milestones, and quality control tasks.  The Project Schedule provides the following:

- Identification of all the tasks required for accomplishing project objectives and satisfying requirements;

- Identification of task packages for estimating and assigning work responsibilities;

- Clarification of the responsibilities of team members and management;

- Creation of worksheets to track and control cost, schedule, effort, and deliverables; and

- Introduction of a process for maintaining the project schedule.

The Project Schedule is a key component of the Project Plan as it serves as a basis for performance measurement, analysis, and reporting process.  It will be updated continually throughout the project to reflect any changes.

## eLearning Project Tasks

### eLearning Overall Tasks

Overall eLearning Project Tasks consist primarily of project management tasks that will be applied consistently to the eLearning initiative throughout the lifecycle of the project.  Project management will originate and be coordinated from the eGovernment Program Management Office (PMO).  Ongoing tasks are displayed in Table 4.2a.

### eLearning Implementation Tasks

The Project Tasks for eLearning have been projected based on a release schedule.  Because of the aggressive timeframe, complex functionality will not be available during the first release.  During the eLearning lifecycle, two additional releases will be made which introduce new functionality to the solution.

Throughout the business case process existing learning management capabilities have been identified within USDA.  Some Agencies are already using these capabilities, other Agencies are ready to implement a new eLearning solution, and still other Agencies are not yet prepared to implement eLearning.  Therefore, a phased approach to adding Agencies to the new eLearning solution will accommodate all Agencies by first implementing the solution for “early adopters” and later implementing the solution across Agencies without any current capabilities as well as others migrating Agencies from existing training-related systems.

Therefore, two separate phases will implement Release 1 functionality as shown in Table 4.2b.  The project schedule estimates early adopter Agencies will have completed implementation of eLearning services by the fourth quarter (Q4) of fiscal year (FY) 2003.  This timeframe is challenging, but many early adopter Agencies already have a head start on conducting pre-implementation tasks.  Detailed information on the early adopter process and the specific approach for early adopter implementation is available in the Risk Profile – Early Adopter Plan business case document.

Remaining Agencies that do not participate in the early adopter implementation activities are expected to implement eLearning during FY2004.  It is estimated that Department-wide implementation of eLearning will be complete by FY2004 with new functionality released throughout the period from FY2005 to FY2006.

The eLearning implementation is broken into four task phases:

- eLearning Pre-Implementation Tasks  – Pre-implementation tasks consists of the tasks that must be performed prior to implementation.  These initial tasks include the vendor analysis and selection process as well as creating and configuring the technology infrastructure and the physical network required for implementation.  These tasks begin and end in Q2 of FY03.  These tasks are depicted in Table 4.2b.

- eLearning Early Adopter Implementation – The Early Adopter Implementation consists of a full implementation of eLearning services for early adopter Agencies.  This implementation includes project planning, design, conversion, and workforce transition activities.  Phase 2 begins in Q2 of FY03 and some tasks extend through Q1 of FY04.  However, a fully functional implementation of Release 1 functionality will be ready during Q4 of FY03.  These tasks are depicted in Table 4.2c.

- eLearning Department-wide Implementation – The Department-wide Implementation consists of similar set of tasks as the Early Adopter Implementation and with the same Release 1 functionality.  During this time, remaining USDA Agencies will conduct full implementation of eLearning services.  These tasks begin in Q1 of FY04 and some conversion tasks may extends through Q2 of FY05.  These tasks are depicted in Table 4.2c.

- Additional Functionality Releases – The final task grouping consists of tasks required to bring additional future functionality to the eLearning solution on a yearly basis.  After refining application requirements during Q4 of the previous year, additional functionality will be added to the system.  These additional functionality releases are called Release 2 and Release 3 and will be implemented for Agency use during FY05 and FY06 respectively.  These tasks are depicted in Table 4.2d.

The following timeline shows the project tasks outlined in phases against a quarterly schedule:

Table 4.2a – Overall eLearning Project Tasks

Table 4.2b – eLearning Pre-implementation Tasks

Table 4.2c – eLearning Implementation Tasks for Release 1 Functionality

Table 4.2d – eLearning Implementation Tasks for Release 2 and Release 3 Functionality

## Plan for Progress Updates

All members of the eLearning Implementation Team will be responsible for providing weekly status reports to document their progress against the schedule.  Progress on all tasks will be monitored, documented on the overall project schedule, distributed to the team members and communicated to executive stakeholders.  USDA project managers will remain in constant communication with the application service provider to ensure their tasks are on schedule as well.

## Assessing and Managing Schedule Changes

Deviations from the schedule will be assessed on a weekly basis by the eLearning Project Management to determine impact on the project.  If there is a delay, management will assess its potential impact and decide on a process to address and correct the issue.

Once agreed upon, the project schedule at the beginning of the project will represent the baseline against which progress will be measured.  Weekly updates to the baseline will be made based on the process discussed in the previous section.

# Costs

## Overview

Under a service arrangement, the application service provider assumes most of the implementation and ongoing costs with a yearly fee charged to the purchaser for the lifecycle of the arrangement. Although most of the costs are included within the application service provider agreement, USDA project teams as described above are still necessary.  The cost of those resources is also included in this cost estimate.

## Cost Detail

Considering the requirements outlined in this business case, the costs for contracting to an application service provider are estimated at $45 per person per year. Assuming all 100,000 employees will utilize eLearning, the arrangement will cost approximately $4,500,000 per year.

A Program Management Office (PMO) team will be responsible for overseeing the activities of the application service provider.  The estimated yearly cost for those resources will be $353,998.  Additionally, a project team will perform eLearning tasks, such as process reengineering and workforce transition with decreasing effort as the system is fully implemented.

Table 5.2 – Cost Assessment

| Task Description | Schedule | Cost |
| --- | --- | --- |
|  | Start date | End Date |  |
| Application Service Provider Fees – Year 1 | 2003 Q3 | 2003 Q4 | $ 2,250,000 |
| Project Management & Oversight – Year 1 | 2003 Q2 | 2003 Q4 | $ 265,491 |
| Project Team Activities – Year 1 | 2003 Q2 | 2003 Q4 | $ 330,000 |
| Application Service Provider Fees – Year 2 | 2004 Q1 | 2004 Q4 | $ 4,500,000 |
| Project Management & Oversight – Year 2 | 2004 Q1 | 2004 Q4 | $ 353,988 |
| Project Team Activities – Year 2 | 2004 Q1 | 2004 Q4 | $ 660,000 |
| Application Service Provider Fees – Year 3 | 2005 Q1 | 2005 Q4 | $ 4,500,000 |
| Project Management & Oversight – Year 3 | 2005 Q1 | 2005 Q4 | $ 353,988 |
| Project Team Activities – Year 3 | 2005 Q1 | 2005 Q4 | $ 220,000 |
| Application Service Provider Fees – Year 4 | 2006 Q1 | 2006 Q4 | $ 4,500,000 |
| Project Management & Oversight – Year 4 | 2006 Q1 | 2006 Q4 | $ 353,988 |
| Project Team Activities – Year 4 | 2006 Q1 | 2006 Q4 | $ 220,000 |
| Application Service Provider Fees – Year 5 | 2007 Q1 | 2007 Q4 | $ 4,500,000 |
| Project Management & Oversight – Year 5 | 2007 Q1 | 2007 Q4 | $ 353,988 |
| Project Team Activities – Year 5 | 2007 Q1 | 2007 Q4 | $ 220,000 |
| Total Lifecycle Project Costs | $ 23,581,441 |

# Project Deliverables

A deliverable reflects the documented information and knowledge produced as a result of executing the project.  The major project deliverables have been identified in the table below.  For more information about a particular deliverable, please review Appendix B – Project Plan Deliverables.

Scheduled dates have been associated to each of the deliverables with respect to the pre-implementation and early adopter implementation tasks.  Some of the deliverables will be continuously updated throughout the project lifecycle and many will be delivered for each implementation of the solution.

Table 6 – eLearning Project Deliverables

| Deliverable Description | Scheduled Dates | Responsible |
| --- | --- | --- |
| Request for Proposal | Pre-Implementation | PMO |
| Current Business Capability Assessment | Pre-Implementation | Functional Team |
| Project Plan | Pre-Implementation | PMO |
| Vendor Evaluation | Pre-Implementation | PMO |
| Cost and Benefit Analysis of Vendor Finalists | Pre-Implementation | PMO |
| Vendor Comparison Matrix | Pre-Implementation | PMO |
| Project Plan | Release 1, 2, 3 | PMO |
| Capability Release Delivery Approach | Release 1, 2, 3 | Functional Team |
| Functional Requirements | Release 1, 2, 3 | Functional Team |
| Business Performance Model | Release 1, 2, 3 | Functional Team |
| Business Process Design | Release 1, 2, 3 | Functional Team |
| Capability Interaction Model | Release 1, 2, 3 | Functional Team |
| Data Conversion Design | Release 1, 2, 3 | PMO |
| User Interaction Model | Release 1 | Functional Team |
| User Interface Standards and Guidelines | Release 1 | Functional Team |

# Assumptions

Assumptions made within the Project Plan regard the scope and approach to be taken for a project. The assumptions should be used to review the estimate with management and as a basis for understanding when to re-estimate.

Assumptions should continue to be documented throughout the development of the Project Plan; management will review the assumptions during the Project Plan approval process. The assumptions apply to all projects, including those that address the management functions, such as quality management or configuration management.

Table 7 – Project Plan Assumptions

| Number | Assumption |
| --- | --- |
| 1 | An application service provider can be selected during Q2 of FY2003. |
| 2 | The application service provider can accomplish the implementation tasks during the proposed time schedule. |
| 3 | The application service provider will adhere to desired levels of quality and support created in the Service Level Agreement (SLA). |
| 4 | Costs are calculated based on information and assumptions from the Cost Benefit Analysis Select-phase Business Case document. |
| 5 | Resources are available based on the needs of the Staffing Plan. |
| 6 | Resources have the skills required by the Staffing Plan. |
| 7 | The Project Management Office will be shared across the eGovernment project teams. 25% of the resources will be devoted to the eLearning project team. |
| 8 | The eLearning initiative is able to maintain executive sponsorship both within OCIO as well as across all Agencies. |
| 9 | The eLearning initiative is able to utilize the security created by the eAuthentication initiative. |
| 10 | Existing USDA course content can be migrated into the new system. |
| 11 | USDA legacy systems can be integrated with the proposed solution. |
| 12 | Agency employees who already utilize a system with learning management capabilities will migrate to the new system when it is prepared. |

# Appendix A – eGovernment Advisory Team

This section describes the groups that make up the eGovernment Advisory Team.

## eGovernment Executive Council

The eGovernment Executive Council is an interagency management structure established to lead USDA’s transformation to a citizen-centric electronic service delivery provider in accordance with customer and industry expectations.  It is also intended to provide guidance delineated in mandates such as the Federal Records Act, the Paperwork Reduction Act, the Government Performance and Results Act, the Clinger-Cohen Act, Government Paperwork Elimination Act, Freedom to E-File Act of 2000, OMB Circular A-130, and President Bush’s Management Agenda.  The Council strives to champion the use of eGovernment technologies as an enabler for delivering enhanced USDA products and services more effectively and efficiently.

The eGovernment Executive Council is comprised of Senior Executive Program Leaders representing each USDA Mission Area.  The Council is chaired by USDA’s eGovernment Executive.

## eGovernment Working Group

The eGovernment Working Group represents individuals who will coordinate activities related to eGovernment on behalf of their respective agencies.  The members of the eGovernment Working Group are Executive Sponsors, designated by an Agency Head, from either the business or information technology area of each Agency.  The Working Group is chaired by USDA’s eGovernment Executive.

Members from the eGovernment Working Group will serve as liaisons to other working groups in USDA such as the Cyber-Security and Telecommunications Advisory Councils and the USDA Webmasters group as well as external committees such as those connected to the Federal CIO Council eGovernment Committee.

## eGovernment Steering Committee

The USDA eGovernment Steering Committee will undertake the task of providing organization-wide guidance and coordination of Agency activities necessary to implement an enterprise-wide eLearning solution. The eGovernment Steering Committee will make every effort to support interoperability among the USDA agencies as well as among other Federal government agencies taking part in the overall eGovernment initiative.

The eGovernment Steering Committee is comprised of initiative leads that represent each of the eGovernment strategic and enabling initiatives.

## Agency eGovernment Teams

Each Agency will form an internal Agency eGovernment Team, chaired by the Agency’s eGovernment Working Group member, to work in conjunction with and support of the broader enterprise Working Group and to develop agency-specific initiatives.  The Agency eGovernment Teams will be comprised of program or business leaders as well as specialists who represent the Web team, capital planning and investment control, public affairs, information technology, security, privacy, forms management, and records management.  The Agency Head and associated eGovernment Executive Council member will also serve as ex-officio members on the Agency eGovernment Teams.

# Appendix B – Project Plan Deliverables

This section includes explanations of the eLearning Project Plan deliverables that are delineated in Table 6a.

- Business Performance Model:  The Business Performance Model contains the performance targets and indicators for the business architecture and for each business capability. The model includes the definitions of metrics as well as the methods of measurement, presentation, and communication that monitor the performance of each business capability during implementation.  The Business Performance Model is an iterative document that can be updated and refined as the delivery effort progresses through planning and analysis, to designing, building, deployment, and eventually operation.

- Business Process Design:  This deliverable contains all supporting information for Business Process Designs including workflow diagrams and other related information.

- Capability Interaction Model:  This deliverable is based on work object deliverables that produce different "views" of the business process designs, based on information required for each of the business capability elements (for example, a view of the business process from a role "view" or from an application interaction "view").  The different views are then combined to produce an overall integrated picture of the business capability and will provide a starting point for the various design teams (human performance, technology infrastructure, applications) to begin work.

- Capability Release Delivery Approach:  This composite deliverable documents critical decisions regarding the development, evaluation/testing, procurement, piloting, and deployment of a specific business capability release.

- Cost and Benefit Analysis of Packaged Software Finalists:  This deliverable contains a comparison of the costs and benefits associated with all of the packaged software finalists.  It is created after collecting vendor information regarding packaged software capabilities and contract terms.  The document is used as input for selecting one packaged software finalist.  It ensures that important costs and benefits, both economical and intangible, are considered in the finalist decision.

- Current Business Capability Assessment:  This document is a detailed analysis of the existing capability in terms of human performance, business processes, physical environment, application, and technology infrastructure.  The objective of the analysis is to establish a detailed understanding of not only the boundaries, operational implications, and rationale behind the current capability, but also the stimuli for change.  This type of analysis is applicable when specific requirements and the impact of the proposed changes need to be defined before detailed design begins.

- Data Conversion Design:  This deliverable defines the issues and resolutions involved in converting the data from the current application (if applicable) to the new application. It is useful for documenting the requirements, manual and automatic procedures, and programs needed to extract data from the current application(s), cleanse it, and load it into the new application.

- Functional Requirements:  Functional Requirements detail what the application must do to satisfy the business needs of the customers and stakeholders, including details such as categorization, importance, and clear descriptions.  Functional requirements do not include specific technical details related to implementation that are determined through the design process.

- Project Plan:  The Project Plan is a detailed schedule that documents the baselines mutually agreed to by the program and project managers.  It is an inherently flexible document that can accommodate any modifications to the schedule as the project progresses.  It consists of all project-planning documents needed to effectively perform and control project activity, such as the Project Schedule and Milestones, the Project Work Plan, the Project Resource Plan, etc.

- Request for Proposal:  This deliverable prepares a request to submit a quote or proposal for providing goods or services to a candidate supplier.  The request describes the item(s) being procured and all associated requirements (e.g., quantities, delivery dates, packaging and shipping instructions, warranties, etc.). Quotes are typically requested for procurement of goods, while proposals are requested for procurement of services, or a combination of goods and services.

- User Interaction Model:  This deliverable describes how the users will interact with the future application and how the application will be integrated into their work.  This deliverable is used to support decisions on how the users will interact with the application by designing the high-level user interface and primary methods for interaction.

- User Interface Standards and Guidelines:  This deliverable is used to document the user interface standards that must be followed, and the less strict user interface guidelines. The guidelines are general design principles that should be followed by user interaction designers, based on the user population and their tasks. Their main purpose is to provide an appropriate level of user interface consistency throughout the application. Develop initial user interface standards and guidelines early in the project, but be careful to provide a process for updating them as the project learns more about the business representatives and the tasks they perform.

- Vendor Comparison Matrix:  This deliverable compares how each vendor scores on each of the requirements groupings.  This deliverable can be used to summarize and compare the vendors' responses to screening criteria and to select two to three finalists.  Refer to it again when selecting one packaged software finalist and while negotiating contract terms.

- Vendor Evaluation:  A Packaged Software Evaluation documents the packaged software selection process and its resulting decisions, including any recommendations for installation and contract negotiations.  This deliverable addresses vendor performance, packaged software references, costs, benefits, risks, and the strategy for packaged software contract negotiations.

# Text boxes

Team

Project

Team

eAuthentication

Secretary

Deputy

CIO

eGovernment

ACIO,

Office

Management

eGov Program

Team

Team

Implementation

Technical

Advisory Team

Other eGovernment Project Teams

Team

Project

eDeployment

Team

Project

eAuthentication

eLearning Project Team

Secretary

Deputy

CIO

eGovernment

ACIO,

Office

Management

eGov Program

Team

Functional

Team

Technical

Advisory Team

Executive Leadership and Advisory Team

eLearning Project Team