U.S. Department of Transportation

Federal Aviation Administration

GUIDE FOR PREPARING THE

FEDERAL AVIATION ADMINISTRATION PROGRAM BASELINE AND OMB

EXHIBIT 300 REPORTS

Version 2.5.4

April 2006

| Version Number | Version Date | Changes |
| --- | --- | --- |
| Version 1.0 Final | 01/25/2005 | Exhibit 300 guidance (FY2006). |
| Version 2.2 Preliminary Draft | 11/04/2005 | Initial draft with updates to Exhibit 300 guidance (FY2007). |
| Version 2.3 Draft | 11/09/2005 | Complete draft with updates to Exhibit 300 guidance (FY2007). |
| Version 2.4 Draft | 11/09/2005 | Completed draft with updates to Exhibit 300 guidance (FY2007) and highlighted comments |
| Version 2.5.1 Draft | 11/30/2005 | FAA comments from 11/22/05 meeting and inputs were incorporated. |
| Version 2.5.2 Advanced Draft – for ASAG meeting on 12/07/05 | 12/5/2005 | Added comments from K. Kepchar, T. Burke and Terminal. |
| Version 2.5.3 Draft for ASAG review | 12/9/2005 | Incorporated additional comments received after ASAG meeting on 12/7/05. |
| Version 2.5.4 Draft | 1/6/2006 | Incorporates Additional comments from Brandi Ingargiola, Darren Ash and Dave Woodson and some editorial clarifications. |
| Version 2.5.4 Final Draft | 2/7/2006 | Incorporates SoS revisions from Sue Fedor and corrected URLs. |
| Version 2.5.4 Final Draft | 2/16/2006 | Added new screening question (User Type). |

Note:  This guide is a living document.  Several sections of this guide are subject to change prior to the end of the fiscal year to incorporate changes due to Budget Year 2008 OMB and other government wide guidance as well as any changes in FAA guidelines and processes.

Table of Contents

1.   Exhibit 300 Preparation Overview	1-1

1.1   Introduction	1-1

1.2   Purpose	1-1

1.3   Acquisition Management System	1-2

1.4   The Exhibit 300 Program Baseline vs. the OMB Exhibit 300 Report	1-2

1.4.1   The Exhibit 300 Program Baseline (PB)	1-3

1.4.2   OMB Exhibit 300 Report	1-4

1.4.3   Differences between the Exhibit 300 PB and the OMB Exhibit 300 Report	1-6

1.5   Organization of the Guide	1-6

1.6   Scoring Criteria	1-7

1.7   General Writing Rules	1-8

1.8   Lifecycle and Useful Segment Terminology	1-10

2.  Screening Questions and Summary of Spending	2-1

2.1   Introduction	2-1

2.2   Scoring Criteria	2-1

2.3   Part I: Screening Questions	2-1

2.4  Part I: Summary of Spending Table	2-7

2.4.1   General Guidance for Completing the Summary of Spending Table	2-7

3.  Sections I.A and I.B - PMA	3-1

3.1   Introduction	3-1

3.2   Scoring Criteria	3-1

3.3   Section I.A – Project Description Guidance	3-1

3.4   Section I.B – Justification Guidance	3-3

4.  Section I.C – Performance Goals	4-1

4.1   Introduction	4-1

4.2   Scoring Criteria	4-1

4.3   FAA-Specific Guidance	4-2

4.3.1   Helpful Tips	4-2

4.3.2   Creating the “Line of Sight”	4-3

5.  Section I.D - Program Management	5-1

5.1   Introduction	5-1

5.2   Scoring Criteria	5-1

5.3   Guidance	5-1

6.  Section I.E - Alternative Analysis	6-1

6.1   Introduction	6-1

6.2   Scoring Criteria	6-1

6.3   Guidance	6-1

7.  Section I.F - Risk Inventory and Assessment	7-1

7.1   Introduction	7-1

7.2   Scoring Criteria	7-1

7.3   Guidance	7-1

8.  Section I.G - Acquisition Strategy	8-1

8.1   Introduction	8-1

8.2   Scoring Criteria	8-1

8.3   Guidance	8-2

9.  Section I.H - Project and Funding Plan	9-1

9.1   Introduction	9-1

9.2   Scoring Criteria	9-2

9.3   Guidance	9-3

10. Section II.A – Enterprise Architecture	10-1

10.1   Introduction	10-1

10.2   Scoring Criteria	10-1

10.3   Guidance – Part II.A.1: Business	10-2

10.4   Guidance – Part II.A.3: Applications, Components and Technology	10-4

11.  Section II.B - Security and Privacy	11-1

11.1   Introduction	11-1

11.2   Scoring Criteria	11-2

11.3   Guidance	11-2

12. Abbreviated Exhibit 300 Program Baseline Overview	12-1

12.1   Introduction	12-1

12.2   Scoring	12-1

12.3   Guidance	12-1

APPENDIX A - CROSSWALK OF THE EXHIBIT 300 SECTIONS	A-1

APPENDIX B – USEFUL WEB LOCATIONS	B-1

APPENDIX C - E-GOV STRATEGY REVIEW SAMPLE	C-1

APPENDIX D – FAA RISK MANAGEMENT GUIDANCE	D-1

APPENDIX E – ADDITIONAL 508 GUIDANCE	E-1

APPENDIX F – GLOSSARY OF ESSENTIAL TERMS	F-1

# 1.   Exhibit 300 Preparation Overview

(NOTE:  This section is under review and subject to change.)

## 1.1   Introduction

As stated in OMB Circular A-11, Federal agencies must annually submit to OMB and Congress the Exhibit 300 Report as an appendix to their budgets.  In order to receive Congressional program funding each year, the Federal Aviation Administration (FAA) must show through the Exhibit 300’s that investments are managed using the best available practices.  The FAA Acquisition Management System (AMS) calls for the use of Exhibit 300 Program Baselines (PBs) as the JRC approval document for agency investments.  Each OMB Exhibit 300 Report that is submitted to OMB must be consistent with, and show the baseline, that was most recently approved by the JRC.  Section 1.3 describes the relationship and differences between the Exhibit 300 PB version and the OMB Exhibit 300 Report version that is submitted to OMB.

The Exhibit 300 also serves as FAA’s opportunity to demonstrate to budget decision makers why FAA’s investments are critical to the Air Traffic community.  It is important to remember that the primary purpose of the Exhibit 300 is to effectively convey accurate information about the investment, including its impact on the business, its status, and the management processes used to execute it and monitor its performance.  Understanding and complying with the information requirements of the Exhibit 300 are key not only to ensuring that the correct information is reported, but also to ensuring that lifecycle management and investment selection, control and evaluation processes are performed correctly to enable the best investment decisions.

Each year OMB raises the bar regarding the information presented in the Exhibit 300 therefore it’s important not to become complacent.  It’s the responsibility of each program to ensure their business case demonstrates continuous improvements and contains current information.

## 1.2   Purpose

The purpose of this guide is to provide guidance for preparing the Exhibit 300 PB documents and the OMB Exhibit 300 reports.  As the cornerstone of key investment decisions, the Exhibit 300s must be filled out completely, clearly, and concisely.  In the past FAA has risked reduced funding for major NAS F&E investments by as much as $300 million because of poor or not so compelling business cases.  In referring to this, Administrator Marion Blakey stated in the BY2005 Exhibit 300 kickoff meeting, “the inability to tell the story of why these investments are important cost us dearly."

Each year, OMB raises their expectations for the content of Exhibit 300’s – requiring the FAA to proactively improve its Exhibit 300 preparation process – thus improving program management that produced the required information.  This guide addresses common issues that arise during both the writing and scoring process of the Exhibit 300.  In addition to general guidance, detailed information is provided for each section of the Exhibit 300.  If additional information or clarification is needed, the FAA Value Management Office (VMO) maintains an updated list with contact information for the Subject Matter Experts (SMEs) and other Exhibit 300 contacts that can provide additional assistance.  The list can be found in the Exhibit 300 portal:  https://nase.amc.faa.gov.  Note: This URL will not work from outside the FAA intranet without a valid FAA userid and password.  To obtain access to this URL contact Anona Day at Anona.Day@faa.gov.

## 1.3   Acquisition Management System

The AMS establishes policy and guidance for all aspects of lifecycle acquisition management for the FAA.  It defines how the FAA manages its resources - money / people / assets - to fulfill its mission. The objectives of the policy are to increase the quality, reduce the time, manage the risk, and minimize the cost of delivering safe and secure services to the aviation community and flying public.  Acquisition management policy promotes these objectives through partnership among service providers and customers to ensure FAA plans, programs, and budgets address priority aviation needs.

The FAA AMS consists of numerous policies and guidelines that describe investment management and lifecycle management requirements, responsibilities, processes, and documentation, including those for investment analysis and decisions.  The AMS also includes criteria for determining which investments must complete the different types of Exhibits 300 and policies for which office(s) reviews each one.  Electronic copies of the AMS policies and guidelines are available on http://fast.faa.gov.

OMB uses the terms “Planning, Acquisition, and Maintenance” to define life-cycle funding phases in the Summary of Spending (SoS) Table and other sections of the Exhibit 300.  The table below maps OMB CPIC and Funding Phases to FAA AMS Lifecycle Phases.

| OMB CPIC Phase | Summary of Spending Funding Phase | FAA AMS Lifecycle Phase |
| --- | --- | --- |
| Select | Planning | Mission Analysis Investment Analysis |
| Control | Acquisition (DME) | Solution Implementation |
| Evaluate | Maintenance (Steady-state) | In-service |

Table 1: CPIC/AMS Mapping

All sections of the Exhibit 300 must be completed prior to submitting an Exhibit 300 Report to OMB.  The level of detail provided for investments that are in the initial planning phases will be less than for investments in later phases of the lifecycle.  It is very important that investments in the initial planning phases that have not completed an initial investment analysis or obtained a final investment decision by the Joint Resources Council (JRC) clearly state throughout the OMB Exhibit 300 Report that the information is preliminary.  For new investments it’s important that the funding for the phase or segment that covers that budget year be approved by the JRC prior to the OMB Exhibit 300 being submitted to OMB; otherwise, the funding may not be approved.

## 1.4   The Exhibit 300 Program Baseline vs. the OMB Exhibit 300 Report

The format and types of information required for the Exhibit 300 Program Baseline (PB) and the OMB Exhibit 300 Report are essentially the same but there are differences in their purposes and timing.  This section outlines the major purposes, relationships, and differences pertaining to these two documents.  Subsequent sections of this guide will outline any additional differences pertinent to that section.

### 1.4.1   The Exhibit 300 Program Baseline (PB)

The Exhibit 300 PB is prepared for JRC investment decision meetings.  The JRC is the FAA executive investment review board that makes all the investment decisions for investments that are required to submit Exhibit 300s to OMB and for other investments designated for JRC review based on agency specific criteria.

An Exhibit 300 PB becomes the official baseline document for an investment once it is approved by the JRC.  This baseline cannot be changed without JRC approval.  Prior to the AMS changes that established the Exhibit 300 PB as the official JRC approved baseline, the FAA used the Acquisition Program Baseline (APB) as the official baseline for an investment.  For those investments that do not have a more current JRC approved baseline, use the APB in lieu of the Exhibit 300 PB as the current official baseline.

The JRC has several investment review responsibilities, depending on the lifecycle phase of the project.  Figure 1 illustrates the investment analysis phases and decision points which are conducted to ensure FAA's critical needs, are satisfied by practical and affordable solutions.

Figure 1: JRC Decisions during the FAA Lifecycle Management Process

The AMS guidance found in the FAST web site provides detailed guidance on investment analysis processes, decisions, and documentation.   The AMS also explains who is responsible for the different investment decisions.

The cover sheet that includes a list of required signatures for the Exhibit 300 PB is included in Appendix B of the AMS policy which can be found on the FAST web page at:  http://fast.faa.gov/docs/exhibit300.doc.

### 1.4.2   OMB Exhibit 300 Report

As part of the annual budget process FAA submits to OMB and Congress an annual OMB Exhibit 300 report for each of its major investments.  The list of which specific FAA investments must submit an Exhibit 300 Report is coordinated with and agreed to annually with OMB.  As part of the annual submission process FAA, in coordination with DOT, has implemented a process to assist FAA investment programs in preparing Exhibit 300s that provide comprehensive and up-to-date information about their investments.  The FAA Value Management Office (VMO) and Subject Matter Experts (SMEs) are available to provide guidance in specific areas of the Exhibit 300.  The VMO maintains an updated list of Exhibit 300 SMEs and other contacts on the FAA Exhibit 300 portal located at - https://nase.amc.faa.gov.  The VMO also provides annual training and internal independent scoring of the completed exhibits 300.  Prior to being submitted to OMB, Exhibit 300 reports are submitted for internal FAA scoring, review, and approval.  The cover sheet that includes a list of required signatures for the OMB Exhibit 300 report will be available on the FAA Exhibit 300 portal or by contacting the VMO office.  The table below depicts the annual sequence of events for the Exhibit 300 preparation and submission for Budget Year (BY08).

| Month | Exhibit 300 Activities |
| --- | --- |
| December-January | Program areas start updating Exhibit 300s from previous year to incorporate OMB Passback, SME, and VMO guidance |
| February | First Exhibit 300 training session |
| March | NASE Portal Training (This is the FAA portal where information and guidance related to the Exhibit 300 can be found) |
|  | Administrator Kick-off Ceremony |
| April | eCPIC Training (eCPIC is the tool that is used to enter Exhibit 300 information) |
|  | Second Exhibit 300 Training Session |
|  | First drafts of OMB Exhibit 300 reports are due to the Value Management Office (VMO) for initial evaluation and scoring |
| May | Revising and rescoring of business cases (Exhibit 300s) |
| June | Draft OMB Exhibit 300s are submitted to DOT |
|  | DOT provides comments for remediation Draft SoS table is entered in eCPIC |
|  | Third Exhibit 300 Session |
|  | Briefings on changes to OMB Exhibit 300 guidance and reporting requirements |
| July | Programs wishing to re-baseline before their Exhibit 300 is submitted to OMB must obtain JRC approval no later than July |
|  | OMB Exhibit 300 reports are submitted to VMO for final scoring |
| August | Summary of Spending table is entered in eCPIC |
|  | Exhibit 300 information is entered in eCPIC |
|  | Emergency rescoring of specific business cases and areas |
|  | OMB Exhibit 300 reports obtain required FAA PM, Director Level, and Executive approvals |
| September | OMB Exhibit 300 reports are submitted to DOT |
|  | OMB Exhibit 300 reports are submitted to OMB |
| November | OMB issues Passback, including scores on OMB Exhibit 300 reports |

Table 2: Annual OMB Exhibit 300 Preparation Events

### 1.4.3   Differences between the Exhibit 300 PB and the OMB Exhibit 300 Report

The relationships and differences are summarized below:

- The Exhibit 300 PB stands in force and cannot be changed without JRC approval.  In contrast the OMB Exhibit 300 report must be updated at least annually to depict upcoming near term activities identified in the program baseline (Exhibit 300 PB) and report the status of these activities prior to submission of the Exhibit 300 report to OMB.  However, in the OMB Exhibit 300 report, the current Program Baseline information must be consistent with and within the latest JRC approved baseline shown in the Exhibit 300 PB.  Changes cannot be made to the OMB Exhibit 300 report baseline information without first having a revised Exhibit 300 PB whose baseline changes have been approved by the JRC.

- The OMB Exhibit 300 report version would need to be updated to incorporate the results of any JRC decision that has taken place since the last annual or official submission to OMB.

- Neither the Exhibit 300 PB nor the OMB Exhibit 300 report will be required to report any information in Section I.H.4 if the investment is new and no costs have been, or will be, incurred before the Exhibit 300s are submitted to the JRC or OMB.  There may be instances however where a new investment will have incurred no expenses when it is submitted to the JRC for approval but will have incurred expenses by the time the OMB Exhibit 300 report is submitted to OMB.  In such cases Section I.H.4 will not need to be completed for the Exhibit 300 PB but it will need to be completed in the OMB Exhibit 300 report.  In cases where an Exhibit 300 is being completed for the first time for an ongoing investment that is already incurring costs, Section I.H.4 must be completed for both the Exhibit 300 PB and the OMB Exhibit 300 report.

- The Exhibit 300 PB going to the JRC would need to document all performance goals (Section I.C) and milestones (Section I.H) that will cover the period that includes all the segments/phases being proposed to the JRC for funding approval.  Normally OMB Exhibit 300 report goals should cover the period of the current useful segments being reported in Section I.H or at least through the budget year and one year beyond.

- The Summary of Spending in the OMB Exhibit 300 report may be updated to reflect the CIP and may not be consistent with the SOS in the Exhibit 300 PB if the CIP was updated after the Exhibit 300 PB was approved by the JRC.

Throughout this guide, when the term Exhibit 300 is used, both documents have the same content.  Any differences between the two documents are discussed where applicable.

## 1.5   Organization of the Guide

The Exhibit 300 consists of some screening questions followed by ten sections, each covering a different topic. The first section of this guide provides overview information and general guidance related to the Exhibit 300 and this document.  Sections 2 through 11 of this guide cover the topics of the Exhibit 300 in the same order as the Exhibit 300 sections.  Section 12 addresses the Abbreviated Exhibit 300.   The appendices at the end of this guide include a table that summarizes the relationships between the section and a list of useful web sites and references as well as more detailed information and guidance on some Exhibit 300 topics.

## 1.6   Scoring Criteria

The Exhibit 300 is scored on a 5-point rating, where 1 is the lowest score and 5 is the highest score and a 3 is passing.  OMB will only recommend programs that score a 3 or above for each Exhibit 300 section to Congress for funding.  However OMB may designate some specific sections as requiring a 4 in order for the Exhibit 300 business case to pass.  For example, the security section requires a 4 and OMB may designate additional sections as requiring a 4.  As an agency, the FAA has set a goal to achieve a score of 4 or 5 for each Exhibit 300 section.

An overall score of three, meaning that the Exhibit 300 scores for all sections total to 30 or less, means an investment has not passed and therefore OMB will not approve funding.  Consequently some modifications will need to be made to the Exhibit 300 and a program may need to take some additional corrective actions before OMB will approve funding for the investment.  Investments with a total score that does not pass are placed on the OMB Management Watchlist.  OMB, however, may place an investment on the Management Watchlist even if it has a total passing score (31 or higher) due to concerns OMB may have about the investment’s performance in a particular area(s) such as security scoring a 3, large negative cost or schedule variances, or the failure to obtain JRC approval to a baseline or baseline change before the Exhibit 300 was submitted to OMB.

Scoring for the Exhibit 300 business case (BC) is as follows:

| Score | Points | Description |
| --- | --- | --- |
| 5 | 41-50 | Strong documented business cases (including all sections as appropriate). |
| 4 | 31-40 | Very few weak points within the BC but still needs strengthening. |
| 3 | 21-30 | Much work remains to solidify and quantify BC. BC has the opportunity to either improve or degrade very quickly. |
| 2 | 11-20 | Significant gaps in the required categories of the BC. |
| 1 | 1-10 | Inadequate in every category of the required BC. |

It should be noted that the scoring is based on OMB’s perception of the strength of the IT project management, rather than simply the writing of the Exhibit 300.  The results of audits, reviews, and other evaluations will therefore often contribute to an investment’s score.  Also, an investment that is being submitted to OMB with an initial or revised baseline is not likely to get a passing score in some scoring areas if that baseline has not received official agency approval through the FAA JRC.

Each year OMB raises the bar.  It is therefore important not to get complacent and to ensure Exhibits 300 demonstrate continuous improvements and properly updated information.

There are ten scoring areas for each Exhibit 300, thus making the business case worth a total of up to 50 points.  Each scoring area is associated with specific sections of the Exhibit 300.  The following table lists each of the 10 scoring areas with the associated Exhibit 300 sections.

| Scoring Area Title | Related Exhibit 300 Section |
| --- | --- |
| Supports the President's Management Agenda Items (AI) | Multiple sections – including Part I, Section I.A. and Section I.B. |
| Performance Goals (PG) | Part I, Section I.C |
| Project Investment Management (PM) | Part I, Sections I.D and I.H, and overall business case |
| Alternative Analysis (AA) | Part I, Section I.E |
| Risk Management (RM) | Part I, Section I.F |
| Acquisition Strategy (AS) | Part I, Section I.G |
| Performance Based Management Systems (PB) | Part I, Section I.H |
| Enterprise Architecture (EA) | Part II, Section II.A |
| Security and Privacy (SE) | Part II, Section II.B |
| Life-Cycle Costs (LC) Formulation | Multiple Sections – including Screening Questions, SoS Table, Section I.H |

## 1.7   General Writing Rules

The best investment may score lower if the reviewer cannot understand the text in its Exhibit 300.  The following are simple grammar and format rules that need to be followed to produce an effective business case.

- Remember Your Audience – Each year the FAA may get a new Exhibit 300 OMB examiner who comes from outside the FAA (and possibly outside of DOT), so it is important to ensure that documents not filled with “FAA-ese.”  Here are some tips:

  - Avoid FAA jargon and overly technical explanations- Reviewers main focus is to determine how well projects are being managed.  Limit the amount of technical explanations, and when you do need to go into further details – try to translate functions into common, everyday language.

  - Limit use of multiple abbreviations- Reviewers will be familiar with common Federal abbreviations such as FAA, DOT, DoD, and OMB.  For each sentence, use one or at most two common abbreviations – the first referring to the major subject of the sentence and the second referring to a related program or sub-set of said major subject.  For FAA internal abbreviations, write out the full term; if repeatedly referred to, a short-form or “nickname” can be used after it is first spelled out (example – Joint Resources Council can be referred to as “the Council” and not JRC).  Remember to remain consistent with how you refer to each term.

- Keep it simple – Like any government document, the Exhibit 300 must follow the rules of Plain Language.  The goal of Plain Language is to make documents clear and concise.  These guidelines include:

  - Avoid repetition- When repetition occurs, there is a good chance that the repeated piece of information may be used inappropriately in some places.

  - Use active verbs- Use no more, if not less, than 15% passive verbs.

  - Keep sentences short- Try to keep sentences to 20 words or less, but if a sentence needs to be longer, use no more than 40 words.  The longer a sentence, the more likely there will be a grammatical error.  If needed, split up sentences into lists or bullets.

  - Experiment with using bullets before submission- The automated tool for submitting data to OMB, eCPIC, does not always reliably capture bullet formatting.  Experiment with numbering and or tabs in a text editor like Notepad (not Word) to determine what works best visually.  A common recommendation is skip a line between each bullet item.

In order to make sure that Exhibit 300 has employed Plain Language, run the document through an editing program such as StyleWriter (a requirement this year).

- Only answer the question asked- When asked a question, directly and fully answer the question asked first before elaborating, and if elaborating, use only absolutely pertinent information.  Before adding additional information, check to make sure it is not asked for in a later part of the Exhibit 300.  For example, when asked “Is the project baselined?”, the answer should “Yes” or “No” and then could be followed up with “It was baselined in 2001” but should not include what the baseline amount is, how long it took to baseline, or how the baseline was determined.  It is highly probable that this extra information will be asked for later.

- Ensure your Exhibit 300 is current- Programs who have submitted the Exhibit 300 in the past often use the previous years version as a jumping off point.  If this is done, double check each response to make sure you update all of it appropriately (i.e. use current year where appropriate).   In some cases, questions have been broken into smaller parts – so make sure your previous answer has been broken down appropriately.

- Keep section answers consistent- Often times the responses in one section will refer to responses in others.  Make sure that these responses are consistent with one another.  Appendix A includes a crosswalk that compares each question to one another and points out where these tie-ins exist.  The answers in the Exhibit 300 must also be consistent with what is reported in the Agency’s Exhibit 53, IT Portfolio.

- Avoid using “Not Applicable”, “Not Available”, or leaving questions blank- If a question cannot be answered because data is not available, explain why the question cannot be answered.  If the data will be available in the future – clearly state when the data will become available.

- Do not “cut-and-paste” answers between different questions- Although many questions are related to another, the same answer will not satisfy two different questions.  Do not cut-and-paste examples from this guide.

## 1.8   Lifecycle and Useful Segment Terminology

It is very important to clearly identify the investment phase and useful segments for which funding is being requested.  In both Sections I.A.1 and I.H of the Exhibit 300, investments need to clearly identify the phase, useful segment(s), duration and scope for which funding is being requested.

Lifecycle:  An investment’s total lifecycle is the duration of the investment encompassing the planning, acquisition, and maintenance phases until the investment is discontinued, disposed of, and/or replaced.

Phase:  A part of the investment that usually reflects its current lifecycle phase, such as planning, acquisition/development/modernization/enhancement, maintenance, or mixed lifecycle.

Useful Segment:  A useful segment is an economically and programmatically separate component of an investment, as narrow in scope and brief in duration as practicable.  It provides a measurable performance outcome for which the benefits are derived independently and separately of other useful segments.  A phase can consist of just one useful segment or can include several useful segments.

Milestones:  Milestones are specific activities or tasks that have a beginning and an end and are part of a useful segment.

Below is a depiction of the relationship between an investment total lifecycle, its phases, useful segments, and milestones.

| Investment’s Complete Lifecycle |
| --- |
| Planning Phase | Acquisition (DME) Phase | Maintenance (Steady-State) Phase |
| Planning Useful Segment #1A: 10/01/2004-05/30/2005 | Acquisition/Development Useful Segment #1B: 06/01/2005-09/30/2008 Milestone 1 Milestone 2 Milestone 3 Milestone 4 | Steady-state Useful Segment #1C: 01/15/2007-09/30/2012 |
| Planning Useful Segment #2A: 04/01/2004-09/30/2005 | Acquisition/Development Useful Segment # 2B: 10/01/2005-05/30/2007 Milestone 1 Milestone 2 | Steady-state Useful Segment #2C: 06/01/2007-12/30/2010 |
| Planning Useful Segment #3A: 10/01/2005- 06/30/2006 | Acquisition/Development Useful Segment #3B, 07/01/2006-09/30/2010 Milestone 1 Milestone 2 Milestone 3 | Steady-state Useful Segment #3C, 10/01/2010-09/30/2012 |

Table 3: Sample Life-Cycle Phase, Segment, and Phase Relationships

# 2.  Screening Questions and Summary of Spending

## 2.1   Introduction

The numbering and organization of this section reflects the numbering and organization of the screening questions and Summary of Spending (SOS) table in the Exhibit 300.  Guidance is provided for each question.

## 2.2   Scoring Criteria

The screening questions and SoS table are not scored.

## 2.3   Part I: Screening Questions

Date of this Submission [update each year]:

Enter the date submitted to DOT.

Agency:

Enter “Department of Transportation (DOT)”

Bureau:

Enter “Federal Aviation Administration (FAA)”

Budget Account Number:

Programs should use one of two account numbers: Operations account or the Facilities and Equipment account.  ECPIC lists the treasury code for these numbers, starting with a “69” which represents the FAA; however, for the purpose of the Exhibit 300, programs should use the OMB code.

| OMB Budget Codes: |  |
| --- | --- |
| Operations | 021-12–1301–0–1–402 |
| Funding and Equipment | 021-12–8107–0–7–402 |

The first three digits of the code “021” stand for the DOT Agency and the next two digits “12” are the FAA’s Bureau code.  For the operations budget, “1301” means that this is a general fund, the transmittal code “0” means this is part of the regular budget, and the “1” is the fund code related to general funds.  For the Funding and Equipment budget, “8107” stands for Trust, non-revolving fund, the “0” once again refers to being a part of the regular budget, and the “7” is a fund code related to Trusts, non-revolving.  The account name will be listed after the account number.

Account Name:

Account number of any other budget accounts funding this investment.

Program Name:

This may sometimes be different from the “Name of Investment”

Name of Investment:

Use the full name of the investment followed by its acronym in parentheses.  Please note that if this investment was submitted as part of the previous budget year’s portfolio, the name of the investment should NOT change, per OMB direction.

Unique Project (Investment) Identifier (UPI):

The instructions for completing the UPI can be found in OMB circular A-11, Exhibit 53.  The UPI depends on the investment’s primary strategic goal mapping, the type of IT investment (i.e., financial, infrastructure, grants management, Enterprise Architecture, or other, and the primary line of business and sub-function.  As such, the code is based on, and must be consistent with, your responses to several specific Exhibit 300 sections.  The Business Reference Model (BRM) mapping in section II.A.1 determines the information to be placed in the last six digits of the UPI.  Contact the Value Management Office to have a UPI code assigned to your project or to check the existing code.

The Department's eCPIC tool automatically generates the UPI code based on responses to several of the screening questions as well as the mapping of the investment to the Federal Enterprise Architecture Business Reference Model (FEABRM) in Section II.A.1.

Investment Initiation Date:

Provide the month and year for the project’s beginning.

Investment Planned Completion Date:

The completion date shown here should be consistent with the completion, or end, of life date shown in the Alternatives Analysis (Section I.E) and should represent the entire life of the investment until it is discontinued or disposed of.

This Investment is: Initial Concept, Planning, Full Acquisition, Steady-State, Mixed Lifecycle

Make sure your response is consistent with the budget resources documented in the budget year column of the Summary of Spending table.  For example, if “Maintenance” has been selected OMB would not expect to see any budget resources in the “Full Acquisition” category in the Summary of Spending table.  Investments showing maintenance costs as well as planning and/or acquisition costs in the Summary of Spending table would normally be categorized as “mixed.”

Remember, this question should be answered for the budget year for which you are requesting funding.  The following is an explanation of the terms.

- Initial Concept: Early concept development and scoping, assessment of functional needs, etc.

- Planning: Funds are being expended for preparing, developing or acquiring the information to design and evaluate the project (e.g., market research, engineering or design studies, prototypes, full cost-benefit studies, accessibility studies, security studies). Planning can be a useful segment of a capital project. Depending on the nature of the project, one or more planning segments may be necessary.

- Full Acquisition: Funds are being expended on assets and/or personnel for implementation.

- Steady-state: Funds are being expended for the maintenance of an operational system or module (system has been through at least one full budget cycle).

- Mixed Lifecycle: Mixed lifecycle investment means an investment that has development, modernization, and/or enhancement (DME) aspects as well as steady-state aspects. For example, a mixed lifecycle investment could include a prototype or module of a system that is operational with the remainder of the system in DME stages; or, a service contract for steady-state on the current system with a DME requirement for system upgrade or replacement.  At a minimum, if 25% or more of the budget you are requesting in the budget year will be spent on development, modernization, and/or enhancements, the investment is considered mixed.

Useful Segment is Funded: Incrementally or Fully

“Incremental Funding” means that a useful segment is not funded in its entirety, thus creating risk associated with uncertainty of future funding (loss of sunk costs, higher acquisition costs, etc.) This is not viewed positively by OMB and not a good way of funding investments.  The preferred response is “Full Funding” which means the budget authority request covers the amount required to complete the current useful segment(s) described in Section I.H of the business case.  Most or all of FAA projects are “Fully” funded.   Please note that “Full Funding” does not refer to funding the entire life of the investment.

The “Full Funding” policy requires that each useful segment (or module) of a capital project be fully funded with either regular annual appropriations or advance appropriations.  Some further FAA-specific clarifications are:

- Full funding means the budget request in the budget year is sufficient to complete all of the useful segments identified in I.H.  (Previous useful segments would be funded with authority from previous years.  In the Facilities and Equipment (F&E) fund FAA has three-year authority to obligate/outlay money.

- Full funding also means that your budget request should be sufficient to obligate for any and all contracts that cover your investment’s current useful segment(s).

- It is acceptable to define a useful segment in F&E with up to three years worth of activities, but then for that useful segment to be fully funded means that the budget year request covers the costs not just for the budget year but for the additional two years needed to complete the useful segment (s).

- Full funding does NOT mean that a budget year request only covers the Section I.H milestones that take place during that budget year.

- Development projects funded solely by Operational funds will have trouble fully funding useful segments that last longer than one year since the Ops fund only has a one year authority.  These investments will therefore probably be categorized as incremental.

Was this investment approved by OMB for Previous Year Budget Cycle?

If an Exhibit 300 went to OMB and was approved for the previous budget year, then the answer is “Yes.”  If this project did not submit an Exhibit 300 to OMB last year, then the answer is “No.”

Note:	 New initiatives that are in the planning stages and have not completed an initial investment analysis and JRC review would answer “No” to this question.

Did the Executive/Investment Review Committee approve the funding for this investment this year?

The answer is “Yes” for all projects that have JRC or JRC subordinate Board approval (if delegated by the JRC), and were given authorization to proceed to the next phase.

Did the CFO review the cost goal?

By the time the Exhibit 300s are due to OMB in September the answer will be yes, so enter “Yes.”

Did the Procurement Executive review the acquisition strategy?

By the time the Exhibit 300s are due to OMB in September the answer will be “yes,” so enter “yes.”

Note:	 The FAA Procurement Executive is the FAA Acquisition Executive.

Did the Project (Investment) Manager identified in Section I.D. review this exhibit?

The Project Manager (PM) must review the Exhibit 300 business case, and then respond “Yes.”  Project Managers are responsible for fully understanding the content of the Exhibit 300 and the project itself.  The PM name and phone number must be included in the Exhibit 300, Section I.D.

Is this investment included in your Agency’s annual performance plan or multiple annual performance plans?

The FAA Flight Plan and annual business plan should be reviewed in relation to this question.  Contact the Value Management Office regarding questions.

Does this investment support homeland security?

Answer ‘Yes’ or ‘No’.  If yes, complete the next question.

If this investment supports homeland security, indicate by corresponding number which homeland security mission area(s) this investment supports?

Review the Department of Homeland Security (DHS) Strategic Plan at www.dhs.gov to see if any homeland security mission areas apply to your program.  If one or more mission areas have been selected, use Section I.A.3, Supporting Information, to elaborate.

Is this investment information technology (IT)?

Information Technology, as defined by the Clinger-Cohen Act of 1996, Sections 5002, 5141, and 5142, means any equipment or interconnected system or subsystem of equipment that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange transmission, or reception of data or information.  For purposes of this definition, equipment is “used” by an agency whether the agency uses the equipment directly or it is used by a contractor under a contract with the agency that (1) requires the use of such equipment or (2) requires the use, to a significant extent, of such equipment in the performance of a service of the furnishing of a product.  Information Technology includes computers, ancillary equipment, software, firmware and similar procedures, services (including support services), and related resources.  It does not include any equipment that is acquired by a Federal contractor incidental to a Federal contract.  An FAA investment that is part of the NAS is usually considered IT.  For example, the En Route Automation Program (ERAM) is categorized as an IT investment, whereas the Power Systems Sustained Support (PSSS) is not.

User Type?

All FAA investments are required to indicate whether they are NAS or non-NAS.

Is this Project a Financial Management System?

Financial Management Systems are financial systems and the financial portion of mixed systems that support the interrelationships and interdependencies between budget, cost and management functions, and the information associated with business activities.  Financial systems are comprised of one or more applications that are used for any of the following:

- Collecting, processing, maintaining, transmitting, and reporting data about financial events;

- Supporting financial planning or budgeting activities;

- Accumulating and reporting cost information; or

- Supporting the preparation of financial statements.

If so, does this project address a FFMIA compliance area?  If so, which compliance area?

The Federal Managers Financial Integrity Act of 1982, Chief Financial Officers Act of 1990 and Federal Financial Management Improvement Act of 1996 require accountability of financial and program managers for financial results of actions taken, control over the Federal government's financial resources, and protection of Federal assets.  The Office of the CFO prepares the FFMIA compliance reporting for financial management systems.  Contact the VMO regarding questions.

Was a privacy impact assessment performed for this project?

The E-Government Act require agencies to conduct, and submit to OMB, Privacy Impact Assessments (PIAs) for all new IT investments administering information in identifiable form collected from, or about, members of the public.  This question should be reviewed each year.

More detailed guidance on PIAs is provided in this guide in the section on the responses for Section II.B.4.  The response to this question should be consistent with the guidance and response for Section II.B.4.

Federal Information Security Management Act (FISMA) questions:

This question is updated each year.  The answer should be "Yes" if your project is required to undergo the security self-assessment process managed by the Information Technology Security Staff.  All major investments (Agency general support systems and major applications) are required to be assessed in accordance with FISMA.  Weaknesses identified as part of the security self-assessment process generate Plans of Action and Milestones (POA&Ms) and are incorporated into the Agency's comprehensive security action plan.

The response to this question should be consistent with the guidance and responses for Section II.B.

Critical Operation or Mission Critical:

Has this investment been identified as a national critical operation or asset by a Project Matrix review or other agency determination?

If no, is this an agency mission critical or essential service, system, operation, or asset (such as those documented in the agency’s COOP Plan), other than those identified as above as national critical infrastructures?

Refer to Value Management Office for further guidance on this question.

PART Questions (These questions apply to all investments, IT and non-IT):

On July 16, 2002, OMB issued a memo to the heads of federal department and agencies describing a new approach being used by OMB to assess program performance.   OMB is now using a Program Assessment Rating Tool (PART) to complete a formal evaluation of federal programs and plans to apply this detailed analysis to a percentage of federal programs every year.  The OMB memo describes the purposes of the PART as:  “The program assessment effort presents an opportunity to inform and improve agency GPRA plans and reports, and establish a meaningful systematic link between GPRA and the budget process.  The memo defines the PART approach as follows, “The PART is a diagnostic tool that relies on objective data to inform evidence-based judgments to assess and evaluate programs across the wide range of issues related to performance.”

If an investment was included in a PART review the response to both PART screening questions f and f.2 should be “Yes”.  The name of the program (not just the investment) that was reviewed should be provided in the “PARTed Program” box

All investments included in PART reviews must demonstrate strong links to the PART process and how the investment will improve the program’s rating, or how the investment affects or is affected by the PART rating process.  PART-related improvement goals would normally be discussed in Sections I.B and I.C.

If the PART review did not result in any findings or action items that apply specifically to the investment, then a brief explanation should be included in Section I.A.2 (Assumptions) briefly naming the PART review that included the investment within its scope, but explaining that there were no findings or action items specific to the investment.

So far the OMB PART has covered four FAA program areas:

1)  The RED account – in 2003

2)  The Airport Improvement Grants – in 2002

3)  Air Traffic Services Operations (OPS funded only) – in 2003

4)  Facilities and Equipment (F&E) – in 2004.

The FAA portfolio is predominantly funded under F&E.  Investments with F&E funding therefore need to answer “YES” to (f).

OPS-funded investments in ATO should answer “YES” to this question.

If you are unsure whether your system/investment supports a program reviewed under PART, contact the Value Management Office.

Will you use a Share-In Savings contracts to support this investment? (This question applies to all investments, IT and non-IT):

These are IT contracts in which the Government, under the authority of Section 210 of the E-Government Act of 2002, awards a contract to improve mission-related or administrative processes, or to accelerate the achievement of its mission and share with the contractor in savings achieved through contract performance.  For help in determining whether a share-in-savings project should be pursued go to www.gsa.gov/shareinsavings.  Acquisitions using the share-in-savings authority in Section 210 must be funded from the funds that would have been appropriated for operations and maintenance of the legacy system the new system is replacing.

Is this investment for construction or retrofit of a federal building or facility? (This question applies to non-IT investments):

The Energy Policy Act 1992, which establishes an energy management requirement for Federal agencies that states not later than January 1, 2005, each agency shall, to the maximum extent practicable, install in Federal buildings owned by the United States all energy and water conservations measures with payback periods of less than 10 years.  A Utility energy efficiency service contract (UESC) means that a local utility provides up-front project funding and Federal agencies pay for the services over time, either on their utility bill, or through a separate demand-side management agreement.  See FAR Part 41 for more information.

## 2.4  Part I: Summary of Spending Table

(NOTE:  This section is under review and subject to change.)

The SoS table represents all the costs for the investment for the full estimated lifecycle of the selected alternative, regardless of source of funding or budget account.

### 2.4.1   General Guidance for Completing the Summary of Spending Table

| Column 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Life-Cycle Stage | PY-1 and Earlier | Prior Year (PY) 20YX-2 (Op Plan) | Current Year (CY) 20YX-1 (Pres Bud) | Budget Year (BY) 20YX OMB Sub | BY+1 20YX+1 | BY+2 20YX+2 | BY+3 20YX+3 | BY+4 & Beyond | Total |
| Planning: |  |  |  |  |  |  |  |  |  |
| Budgetary Resources |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |
| Full Acquisition/ Development: |  |  |  |  |  |  |  |  |  |
| Budgetary Resources |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |
| Total, sum of stages (Planning + Full Acquisition): |  |  |  |  |  |  |  |  |  |
| Budgetary Resources |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |
| Maintenance Total (Steady-state): |  |  |  |  |  |  |  |  |  |
| Budgetary Resources |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |
| Total, All Stages: |  |  |  |  |  |  |  |  |  |
| Budgetary Resources |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |
| Government FTE Costs: |  |  |  |  |  |  |  |  |  |

Table 5: Example of FY07 Summary of Spending Table

Budgetary Resources

In the Summary of Spending table, "Budgetary Resources" means an amount available to enter into new obligations and to liquidate them, including direct spending and obligation limitations (see OMB A-11 or contact Budget Office if the project line item is subject to statutory limitations on obligations).

For the Past Year and Prior always refer to the appropriated amounts received by the program. During the period the Exhibit 300 is being developed for OMB, the Current Year will equal the President's Budget request until an appropriations bill is enacted and signed by the President.  Past year F&E appropriation amounts by project can be found in the Capital Investment Plan.

The Budget Year amount should be consistent with the budget request FAA makes to the Department and OMB.  ATO Finance develops the F&E budget within the framework of the Capital Investment Plan.  Project teams should keep in touch with ATO Finance and the CFO Budget Office to ensure they have the latest figures.

F&E resources beyond the Budget Year should be consistent with amounts found in the Capital Investment Plan, which should adjust out year amounts for current or past year resource changes in order to maintain consistency with the JRC approved baseline.

The Operations budget is developed within each line of business.  Operations funding should be also be consistent with request levels to OMB.

Any project collaborating with another agency or agencies (such as E-Gov projects) should include the funding from those collaborators.  See OMB A-11 Section 300 for more guidance on collaborative projects.

Outlays

Outlays are payments to liquidate an obligation. Outlays generally are equal to cash disbursements but also are recorded for cash-equivalent transactions, such as Federal employee salaries. Outlays are the measure of Government spending.  Outlays should not be confused with obligations, which binding agreements that result in future outlays.

Outlay information must be provided for past, current and future years.  Outlays for past years should be consistent with actual project costs/expenditures.  Current year outlays should reflect actual expenditures to date plus estimated outlays for the remainder of the fiscal year.  Outlay amounts for future years should reflect the outlay rates as agreed upon with the budget office and OMB.   Outlays should equal its counterpart in Table I.H.4, Actual Costs.

Government FTE Costs:

For the Government FTE Costs, use a cost-per-FTE commensurate with the grade level of the government employee(s) performing the work. The budget office has cost per FTE for each Line of Business organization and other inflation rates for formulating payroll resources.  Multi-agency initiatives must include FTE costs for all partnering agencies.  Government FTE Costs in the Summary of Spending include:

- All government personnel considered direct and indirect labor in support of the investment.

- The investment management IPT (service team) and any other government effort (e.g., programming effort for part of the overall investment, development effort) that contributes to the success of the investment.

- Salary costs plus the fringe benefit rate of 32.8%.

- Costs of internal FTE supporting the IT investment, at a minimum including in FTE estimates the costs of anyone spending more than 50% of their time supporting the investment. Persons working on more than one investment, whose contributions over all investments would exceed 50% of their overall time, should have their specific time allocated to each investment.

# Relationship to Costs in Table I.H.4

Outlays in the Summary of Spending should equal Actual Costs for the activities listed in Table I.H.4 for any given budget year.  As time goes on, a project may not appropriated the entire amount planned for any given year’s activities.  Project teams should discuss cost variances in terms of schedule delays or performance shortfalls, if any result, in Section I.H. 4 sections C and D.

Life-Cycle Phase Costs:

- Planning costs include costs for mission analysis and investment analysis.  At FAA, planning comprises all efforts leading up to the final investment decision by the JRC.  It generally includes all activity that occurs prior to the contract award for development.

- Full Acquisition costs include costs for solution implementation (development, testing and deployment).

- Maintenance costs are steady-state costs, which include costs for routine maintenance and technology refresh.

- Mixed Lifecycle projects have costs in multiple phases.

# 3.  Sections I.A and I.B - PMA

## 3.1   Introduction

This section gives the OMB reviewers their first impression of the program.  The goal is to provide OMB with a management summary of the program.  Answers should be structured in the same order as the elements in the question.  Keep descriptions short and to the point.

## 3.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | This is a collaborative investment that includes industry, multiple agencies, State, local, or tribal governments, uses e-business technologies, and is governed by citizen needs. If the investment is a steady-state investment, then an E-Gov strategy review is underway and includes all of the necessary elements. If appropriate, this investment is fully aligned with one or more of the Presidential Initiatives. |
| 4 | This is a collaborative investment that includes industry, multiple agencies, State, local, or tribal governments, uses e-business technologies though work remains to solidify these relationships. If investment is in steady-state, then an E-Gov strategy review is underway but needs work in order to strengthen the analysis. If appropriate, investment supports one or more of the Presidential Initiatives but is not yet fully aligned. |
| 3 | This is not a collaborative investment though it could be and much work remains to strengthen the ties to the President's Management Agenda. If this is a steady-state investment and no E-Gov strategy is evident, this investment will have a difficult time securing continued or new funding from OMB. If appropriate, this investment supports one or more of the Presidential Initiatives but alignment is not demonstrated. |
| 2 | This is not a collaborative investment and it is difficult to ascertain support for the AI. If this is a steady-state investment, then no E-Gov strategy was performed or is planned. |
| 1 | There seems to be no link to the AI and E-Gov strategy. |

## 3.3   Section I.A – Project Description Guidance

Question I.A.1:  Provide a brief description of this investment and its status through your capital planning and investment control (CPIC) or capital programming “control” review for the current cycle.

Start with a brief, concise description of the program and the performance gap it addresses. Describe the useful segments including the CPIC and lifecycle phase of each segment.  Identify which useful segments are covered by this year’s funding request.

The response should include the following:

- Briefly describe the investment scope and activities (planning, acquisition, development, and maintenance) that have occurred in the past, are occurring at the present time and are planned for the future.  Particular emphasis should be placed on the activities that will occur during the time for which funding is being requested.

- Briefly describe the performance gap the investment is addressing or will address and the related benefits.  This information should be consistent with the answers provided in Sections I.B.1 and I.B.8, but not as detailed.  When describing benefits to be, or being, realized as a result of this investment, clearly differentiate those benefits that will result from the phase for which funding is being requested from longer term benefits that are expected in the later years of the investment’s life (and which may not be as easily quantifiable presently).  Don’t forget to include the impact on agency mission performance if the investment were not allowed to start or continue.

- Cite any laws required for the investment as well as reasons why the investment may have been determined to be critical to the agency mission, to homeland security, or a national critical operation.

- Include the CPIC phase(s) (Select, Control, and/or Evaluate) applicable to the investment during the budget year, and the related most recent JRC baseline funding approval decisions.   This section should include a brief but complete description of the governance processes that are being followed, investment review boards that are involved, and decisions that have been, or will be, made regarding the investment’s funding, schedule, risks, and performance.

- If JRC decision dates are discussed, make sure that these dates remain consistent throughout the document.  In the past, reviewers have been confused about whether a project has been re-baselined due to different JRC discussions scattered throughout the Exhibit with no clear linkage between them.

- For fully operational projects in the maintenance phase state the number of years it has been in this phase.

Note: 	For investments in the early planning phases that have not yet completed a final investment JRC decision, the following text, tailored appropriately for the investment, should be inserted at the beginning of Section I.A.1.

“This investment is in the planning phase of the FAA’s Acquisition Management System (equivalent to the Select Phase of CPIC).  The information contained in this Exhibit 300 is considered preliminary because this investment is undergoing internal capital investment reviews.  The team will be performing further analysis and planning.  The JRC is tentatively scheduled to review this investment on <date>, at which time the investment is expected to be baselined.  Once the JRC baselines this investment, the Exhibit 300 will be updated to reflect the JRC decisions.”

Question I.A.2:  What assumptions are made about this investment and why.

Summarize the key business process, strategic, technical or other assumptions related to the investment’s purpose and direction.  Do not include statements such as “the program assumes funding will be approved for this investment.”  Rather, the assumptions should be tied to how the investment links to Agency or organizational strategies for ensuring the investment’s success and barriers that need to be overcome.  Assumptions that specifically affect the investment’s cost/benefit analysis or expected performance goals should be described here, such as, number of air travelers, weather conditions, etc.  Include any technical assumptions that are critical to the success of the program.  When assumptions cite specific figures, these assumptions should be accompanied by an official citation of where those figures can be found.

Question I.A.3:  Provide any other supporting information derived from research, interviews, and other documentation.

Summarize the background information gathering process and research that occurred to determine this investment’s necessity and feasibility.  This information is generally the baseline from which your organization decided whether a new system or a re-engineering of the current system is warranted.  This section re-states the “problem” the agency is trying to solve with the proposed investment and lists documentation and studies that substantiate information on the performance gap and benefits.

## 3.4   Section I.B – Justification Guidance

To improve the score in this area, the Exhibit 300 responses need to demonstrate collaboration with other Federal, State, Tribal, and local governments, business/industry, and private-citizen organizations.  There is an expectation that investments will collaborate with other agencies and/or industry and OMB expects this to be articulated in the Exhibit 300.  A true multi-agency investment involves a partnering relationship with another agency/organization outside of the Department of Transportation.  Partners are those agencies actively involved in the development, operation and change management of the investment and may/may not be providing part of its funding.

Collaboration with customers and stakeholders should also be discussed to demonstrate customer/stakeholder-centered programs.  One example of collaboration might be to reference FAA participation and interaction with the RTCA Inc.  If program requirements were developed through work with the RTCA this information can be included in question 1.B.7.  Additional references to the roles of the IPT (service team) or its members in participating in RTCA committees in Section 1.D and reference to RTCA documents/reports in Section I.A.3 would also help support the business case.

Don’t include benefits in Sections I.B and I.E for which there are no associated performance goals and measures - or plans to include such measures - in Section I.C.  Include narrative in Section I.B.8 that clearly maps the benefits described in I.B to the performance goals in Section I.C.  If there are plans to include additional performance goals in the future because information is not available now, such plans should be described in Section I.B.8 and the related goals would be included in Section I.C, Table 2, and dates provided when the baseline and expected improvement information will be provided.  Include narrative in Section 1.B.1 that describes the line of sight to demonstrate linkage of technology, process, and customer-related improvement goals to mission-outcome goals such as increased safety/reduced accidents, and reduced delays when the portion of a specific investment’s contribution cannot be determined or measured.  Include the name of the related DOT and FAA strategic and performance goals in the Table 2 improvement description to clarify the link between the investment’s performance goals and measures and the DOT and FAA (outcome) goals.

Question I.B.1:  How does this investment support your agency’s mission and strategic goals and objectives?

In accordance with the latest DOT Strategic and FAA Flight Plan, identify in detail, which strategic and performance goal(s), objective(s) this investment supports. Specifically link the relationship between this investment and furthering the goal(s) and objective(s).  Explain how the flight plan goal/objective won’t be achieved if the performance gap (or problem) is not closed.  Information in this section should be consistent with the goals and benefits information provided in Section I.C of the business case.  For most programs, FAA’s Operational Evolution Plan (OEP) and strategic mapping process (SMP) details how the program works into the FAA Flight Plan, including the metrics in some cases.

The Flight Plan is located at http://www.faa.gov/about/plans_reports, DOT’s strategic plan is at http://www.dot.gov/stratplan2008/strategic_plan.htm, the OEP can be found at

http://www.faa.gov/programs/oep

Question I.B.2:  How does it support the strategic goals from the President’s Management Agenda?

The goal of the 2002 Presidential Management Agenda is to create a more efficient government that better serves the citizens needs.  The Agenda established a set of 8 agency-specific goals and five government-wide initiatives, which apply to FAA.  These five government-wide initiatives are as follows:

- Strategic Management of Human Capital

- Competitive Sourcing

- Improved Financial Performance

- Expanded E-Government

- Budget and Performance Integration

The response should demonstrate that the project is a collaborative project that includes multiple agencies, State, local, or Tribal governments, uses e-business technologies and/or the project is governed by citizen needs.   If appropriate, demonstrate that this project is fully aligned with one or more of the President's e-Gov initiatives.  Only map to those PMA goals that the investment clearly and directly supports.  The President’s Management Agenda is located at http://www.whitehouse.gov/omb/budget/fy2002/mgmt.pdf

If the investment is steady-state, or has portions that are steady-state, demonstrate that an E-Gov Strategy Review was completed.  In the FAA, briefings of post implementation reviews (PIRs) and operational assessment data included in semi annual service level reviews (SLRs) can be used to satisfy part of the E-Gov strategy review requirements as long as all the necessary E-Gov strategy review topics are addressed.  The PIR guidance is at:

http://fast.faa.gov/post_implementation/index.htm.  SLR guidance is at:

http://fast.faa.gov/index.htm

The findings of the E-Gov Strategy Review and resulting planned activities or changes should then be discussed in the appropriate sections of the business case, to include Sections I.A and I.B (in relation to performance gap and expected benefits), I.C,  I.E and II.A.  Unfortunately, most FAA business cases either don’t mention E-Gov Strategy Reviews or mention them very briefly.  It’s very important to develop and implement approaches for completing E-Gov Strategy Reviews and integrating this information into the business case development process.  This would include integrating this process into the Alternatives Analyses, Operational Analysis/Assessments, and Post Implementation Review processes.  An individual E-Gov Strategy Review is not required for each investment.   It may be beneficial at times to conduct an E-Gov strategy review of several investments that support similar functions and have similar performance gaps.   The SLR serves as the review for all the programs for which operational assessment and/or post implementation review data has been presented to the JRC.

SLRs can be used as part of an investment’s operational analysis or E-Gov strategy review process but they will normally not be sufficiently broad in scope or detailed to satisfy operational analysis or E-Gov Strategy review requirements in themselves.

An E-Gov Strategy Review is a comprehensive review and analysis that determines whether the investment is continuing to meet agency needs in a cost-effective manner or should be modernized and replaced.  Information from the investment’s most current FAA semi-annual Service Level Review can be used as input to this question.  Appendix C provides additional information on approaches for completing e-Gov strategy reviews and the type of information that should be reported from these reviews.

Please note that Non-IT investments are more supportive of the Human Capital PMA goal by enabling greater efficiency of pilots and other users/customers whose efficiency in performing their functions is disrupted by power outages.

Question I.B.3:  Are there any alternative sources in the public or private sectors that could perform this function?

If there are alternative public or private sector sources that could perform the same function as the investment, describe in detail the analysis conducted and the results that indicated the investment was still required.  New initiatives in the planning stages and preparing for an initial investment JRC decision may need to answer that this is being researched and determined as part of the planning activities.

Question I.B.4:  If so, explain why your agency did not select one of these alternatives.

Use objective or quantifiable reasons when answering this question, supported with documentation (e.g., studies, analyses, research, etc.).

Question I.B.5:  Who are the customers for this investment?

Typically, customers are defined as people/groups who are direct users of the system.  The public, pilots and airlines can be defined as customers of an investment if they are direct users of the system or its data and/or there are goals in Section I.C, Table 2 (Customer Results) that clearly relate to them.  This is also true of infrastructure systems that are internal to the agency and interface primarily with other systems.

For cases where the public, pilots and airlines are not direct users, nor are there any Section I.C, Table 2 customer results goals identifying them as customers, then they would be identified as stakeholders and the following explanatory statement would be included:

“The flying public and pilots, and aviation companies/airlines, as indirect customers of Investment-X, are also stakeholders.”

This statement would be followed by a brief explanation of how the investment indirectly affects/benefits these indirect customers (the public, airlines, pilots).  This approach would categorize pilots/the public as stakeholders but also define them as indirect customers of the particular investment.

Question I.B.6:  Who are the stakeholders of this investment?

Identify all principle groups or individuals who are affected by the investment’s outcome (success or failure).  Include those with business processes that interact with the business process supported by this investment.  For investments where the flying public is not a direct user and customer, the public would be a stakeholder.

Question I.B.7:  If this is a multi-agency initiative, identify the agencies and organizations affected by this initiative.

Collaborative and multi-agency are synonymous terms.  To be considered collaborative an investment will partner with other Federal agencies (outside DOT), state governments, and/or private industry.  This would include sharing the funding and/or work associated with the planning, development and deployment of the investment.  Shared funding usually means that other agencies participate in the funding of the investment and the lead agency that completes the Exhibit 300 shows their contributions in Section I.H.  In the case of FAA, there are some investments that are collaborative with DOD since DOD is currently paying part of the costs.  However DOD does its own separate reporting of the funds it provides for certain investments.  In such cases the investment can be considered collaborative, but it is strongly recommended that the program areas obtain the UPI from DOD (or other partnering agencies) and provide that UPI in Section I.B.7 of the business case.  Investments should also provide an explanation that the costs are reported separately and whether the DOD UPI includes other investments as well.

OMB will expect to see team members from the other agencies included in Section I.D as part of the investment Integrated Project Team (IPT).  Please note that in ATO and AMS policy, ‘IPT’ has been replaced with ‘service team’.

Question I.B.7a:  If this is a multi-agency initiative, discuss the partnering strategies you are implementing with the participating agencies and organizations.

Be very specific with examples of planning or implementing strategies for this investment.  For example, if there is a Memorandum of Understanding (MOU) that documents the partnership, then reference it and summarize its general partnering content.  If members from partnering agencies are included in the investment’s IPT, clearly identify them in Section I.D along with their roles and responsibilities.

OMB has issued additional instructions for the Presidential e-Gov initiatives to providing additional guidance for the preparation of Exhibit 300 and Exhibit 53.  The following information is included in the guidance.

In preparing an Exhibit 300 as a Migrating Agency:

- Reflect all costs associated with the investment, including migration costs incurred by the Migrating Agency.  This includes identifying and documenting the risks associated with the migration.

- Identify and quantify any budgeted cost savings to be realized as a result of the migration including the performance improvements that will be realized.

- Describe the migration schedule and associated major milestones included in that schedule.

- Describe the interagency work group and associated management processes.

In preparing an Exhibit 300 for an e-Gov initiative, Managing Partners:

- Reflect all costs associated with the initiative, including but not limited to program management costs, migration costs, risk-adjusted costs, etc.

- Identify Partner Agencies and describe the funding algorithm used to determine partner contributions.

- Identify and quantify any budgeted cost savings realized as a result of the initiative.

- Include the migration schedule for agencies, including which agency investments are migrating and when.

- Identify the agencies that have signed, or are expected to sign, fee-for-service agreements, including the fees associated with those agreements (where applicable).

Question I.B.8:  How will this investment reduce costs or improve efficiencies?

Describe how the investment will reduce costs and improve efficiencies.  Include business process changes related to the investment that will make the outcome successful.  Benefits identified in this section should be consistent with those identified in Sections I.B.1 and I.E and should be clearly linked to the performance improvement goals described in Section I.C.  Avoid describing benefits that cannot be measured in Section I.C.

Please note that when describing benefits clearly differentiate those benefits that will result from the phase for which funding is being requested from longer-term benefits that are expected in the later years of the investment’s life.  For future benefits for which there are no performance goals in Section I.C, describe plans to determine baselines and establish such goals in the future.

Describe efficiencies in relation to improving business functions and processes more efficiently as opposed to eliminating FTEs.  The Processes and Activities measurement area of the PRM specifically deals with cost savings, cost avoidance, and productivity/efficiency.

Question I.B.9:  List all other assets that interface with this asset.  Have these assets been re-engineered as part of this investment? (Yes/No)

Describe any systems that are interfacing, or will interface, with this asset.  State whether they have been re-engineered as part of this project.

Respond with a “Yes” or “No” for each asset as the second part of the question.

# 4.  Section I.C – Performance Goals

## 4.1   Introduction

In order to successfully address this area of the Exhibit 300, performance goals must be provided for the investment and linked to the Agency’s annual performance plan and mission/strategic goals.  These goals need to map to the gap in the Agency's strategic goals and objectives that this investment is designed to fill.  They are the internal and external performance benefits this project is expected to deliver to the agency (e.g., improve efficiency by 60%, increase citizen participation by 300% a year to achieve an overall citizen participation rate of 75% by FY XXXX, etc.).

Goals must be clearly measurable project outcomes, and if applicable, project outputs.  They do not include the completion date of the module or project, or general goals, such as, significant, better, improved that do not have a quantitative or qualitative measure.

There are two tables in this section, Table 1 and Table 2.  The guidance for which table should be used is as follows:

- Existing investments that were initiated prior to FY 2005: Table 1 must be used to document goals prior to FY 2005 and may be used for goals covering FY2005 and later.  Table 2 must be used for all DME activities starting FY 2005.

- Investments that started during FY 2005 or later: Table 2 must be used.

- Non-IT investments: Table 1 must be used.

## 4.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Performance goals are provided for the agency and are linked to the annual performance plan. The investment discusses the agency’s mission and strategic goals, and performance measures are provided. |
| 4 | Performance goals are provided for the agency and are linked to the annual performance plan. The investment discusses the agency’s mission and strategic goals, and performance measures are provided. Some work remains to strengthen the PG. |
| 3 | Performance goals exist but the linkage to the agency’s mission and strategic goals is weak. |
| 2 | Performance goals are in their initial stages and are not appropriate for the type of investment. Much work remains to strengthen the PG. |
| 1 | There is no evidence of PG for this investment. |

## 4.3   FAA-Specific Guidance

FAA as a whole needs to improve its performance measurement indicators and the linkage between IT investments and program’s performance goals.  For future years, offices are encouraged to develop performance goals and measures that demonstrate support for the Agency’s mission and particularly strategic outcomes.  In cases where more than one investment contributes to an outcome (such as increased safety or reduced delays), it is important to attribute the appropriate portion of the outcome improvement to each contributing investment.

The Exhibit 300 PB version of the business case should show performance goals and measures for all the years covering the duration of the phase that has been or will be approved by the JRC.

At a minimum, OMB Exhibit 300 reports should include goals and measures up to and including one year beyond the budget year; they may provide goals for the entire phase or useful segments for which JRC funding has been approved.

In general, performance improvement goals previously reported to OMB must be included in subsequent OMB Exhibit 300 submissions and not eliminated or changed unless such changes are part of a JRC-approved re-baseline.  If they are approved as part of a re-baseline, the reasons (such as risk adjustments) for the change and the fact that the change is part of an approved re-baseline need to be clearly reported in appropriate sections of the Exhibit 300, including Sections I.C, I.F, and I.H.4.  Goals from past years should not be deleted until the actual performance results have been reported to OMB at least once in the OMB Exhibit 300 Report submitted officially in September.

### 4.3.1   Helpful Tips

The Baseline indicates “where you are today” (for new investments) or “where you were when you first began” (for steady-state investments).  This is the basis for determining increases or decreases in performance.  Planned is the targeted performance level expressed in a metric that can be measured and compared to the actual performance.  Actual is tangible performance results that occurred as the system was used.

Table 1

- Column #1 Fiscal Year: Develop and report performance goals through at least FY 2005.  Performance goals should not be dropped from the table unless the actual performance has been reported to OMB at least once in a prior year’s submission.

- Column #2 Strategic Goal(s) Supported: Indicate which DOT Strategic Plan and FAA’s Flight Plan goals the investment supports.  Include a brief statement explaining how this investment supports the strategic plan goal(s) and objective(s).

- Column #3 Existing Baseline: Enter the baseline for each performance goal.  This is the metric that will measure planned versus actual performance for each performance goal.  To the maximum extent practicable, this should be a quantitative metric for the units that are being measured (for example: the number of delays per year, the number of accidents per year, the number of errors per year, customer complaints per year, hours required to complete an activity/task, or cost of something in dollars, etc).

- Column #4 Planned Performance Improvement Goal: Enter the performance improvement goal(s) that were planned for the investment through 2005.  Performance goals should be expressed in outcomes, using quantifiable metrics which will be used to measure the results. Improvement goals are usually expressed in terms of percentages (for example % reduction in delays, errors, or customer complaints)

- Column #5 Actual Performance Improvement Results: Enter the actual result as compared to the planned goal.  For the current year, state the mid-year progress (if available), progress projected to the end-of-year, or when performance will be measured.  For future years, when the information is not known, provide an estimated date for when it will be available.  Actual performance improvements are often expressed in terms of the % improvement actually achieved.  Actual results are not required for the Exhibit 300 PB unless a previous phase or useful segment for the investment has been completed.

- Column #6 Planned Metric Performance: Enter the quantitative performance metric that will use to measure progress (for example: number of errors per year, number of customer complaints per year, number of hours required for an activity, etc).  This can be an output that is directly tied to achieving the strategic outcome.

- Column #7 Actual Performance Metric Results: For the current year, state the mid-year progress (if available), progress projected to the end-of-year, or state when performance will be measured.  For future years, when the information is not known, provide an estimated date for when it will be available.

Table 2

All new IT investments that include DME activities for 2005 and beyond must use Table 2 and are required to map to the Federal Enterprise Architecture (FEA) Performance Reference Model (PRM).  The PRM includes detailed guidance about how to incorporate PRM Indicators into the performance goals and measures table.  Use the Table 2 and the PRM to identify the performance information that pertains to the major IT Investment. Ensure there is a complete tie-in to the strategic goals and objectives described in Sections I.B.1 and I.B.8.

A key concept of the PRM is a term called “operationalized indicators”.  Operationalized indicators explain how IT investments support business functions of the Business Reference Model (BRM). These business functions can be Services to Citizens or they can be functions that Support Delivery of Services or improved Management of Government Resources.  In other words, the operationalized indicators are the actual metrics that are used to measure progress towards achieving the goal.  For example, a generic indicator from the BRM would be “Air Transportation.”  The operationalized indicator, or specific metric to be used, could be “Hours of Passenger Delay.”

### 4.3.2   Creating the “Line of Sight”

The line of sight referred to in the PRM is a logical set of cause-and-effect relationships, laid out for each year that show how Technology supports improved Processes or Activities to create program outputs that in turn support Customer Results and Mission and Business Results.  In other words, for each year in Table 2, there is a line of sight (a story line) that traces how improvements related to technology improve business activities, which in turn improve customer satisfaction and mission results.  The line of sight is typically four lines in Table 2 for each year, each line containing an operationalized indicator, or specific metric.

Start with the desired outcome at the “top” of the line of sight, then trace back to the outputs and inputs. According to the PRM, the outcome can be at any of the three levels of the BRM (Services for Citizens, Support Delivery of Services, or Management of Government Resources), as appropriate to the individual investment.

An example of a line of sight follows:

Figure 2: Line of Sight from Output to Outcome Goals

- The line of sight should be based on the primary BRM mapping.

- All major IT investments requesting new DME funding for FY 2005 and beyond must identify at least one indicator in each of the four Measurement Areas: Mission and Business Results, Customer Results, Processes and Activities, and Technology Measurement Areas.

- For Table 2 identify at least one indicator for each of the measurement areas specified in the PRM.  Use the same indicators each year to demonstrate the intended value of the investment over time.

- Table 2 should include all goals beginning with FY 2005 that were reported in last year’s submission, plus goals for future years up through one year beyond the budget year.

- Mission goals listed in the DOT Strategic Plan and FAA flight plan are the ultimate strategic outcome that investments support, yet it may be appropriate to name some subsidiary or lesser mission objective or sub-objective that the investment supports. Build on what you have from last year and review the DOT Strategic Plan and FAA Flight Plan for the appropriate outcomes your investment supports.

- Goals related to Support Delivery of Services or Management of Government Resources are also legitimate outcomes at the top of the line of sight.  If your investment is an administrative or support system that is not directly tied to FAA mission and Flight Plan results, your line-of-sight outcome can support these other levels of the BRM (e.g., “reduce cost of grant processing,” “provide more efficient legislative tracking”).  Again, build on what you have from last year.  If you want to take a further step in the line of sight and link a support or administrative process to the DOT Strategic Goals and the FAA Flight Plan Goals, do so. This will allow you to ensure there is a complete tie-in to the Goals described in I.B.1 and I.B.8.

- Include the Generic Measurement Indicator Grouping as well as the operationalized indicator in the “Measurement Indicator” column.  The operationalized indicator must be consistent with the selected Generic Measurement Indictor Grouping in FEA PRM.

- In Table 2, “Baseline,” “Planned Improvement to Baseline,” and “Actual Results” should contain numerical data showing the status of the indicator at the beginning of the fiscal year, the desired target level, and the indicator at the end of the fiscal year, respectively.

- In Table 2, if there is no data for the measurement, indicate in the data field why the data is not yet collected, explain how the data will be collected over the course of the upcoming fiscal year, and provide an estimated date by which the required data will be available.

- It is expected that in many cases, benefits and their related performance goals will not be realized until an investment is at least partly operational.

Please note that new investments that have not yet completed a final JRC investment decision need only provide estimated goals.  In most cases it will be difficult during the preliminary planning phases of these new initiatives to quantify these goals.  Therefore, Table 2 should show the types of performance improvements that are expected and provide an estimated date for when the information to quantify baselines and performance improvements will become available.

To demonstrate linkage of specific performance improvement goals to the DOT Strategic and FAA Flight Plan goals, the names of the appropriate DOT/FAA goals that are supported by a performance improvement may be included in the “Planned Improvement to the Baseline” Column.

# 5.  Section I.D - Program Management

## 5.1   Introduction

The OMB Circular A-11, Part 7, Capital Programming Guide, and the OPM Project Management Guidance “Interpretive Guidance for Project Manager Positions,” discuss project management structures, responsibilities, and qualifications that contribute to successful achievement of cost, schedule, and performance goals.

The score in this section is directly related to other sections of the business case such as Performance Goals, Risk Management, Acquisition Strategy, Alternatives Analysis, and Performance Based Management (PBM)/EVM.  The business case needs to ensure that the management strategies described in these sections is consistent.  Additionally, manager and IPT roles in EVM, Operational Analysis and CPIC governance processes should be included in question I.D.1.A.  A more detailed description of FAA IPTs based on FAA guidelines would also be helpful.

Please note that in ATO and AMS policy, ‘IPT’ has been replaced with ‘service team’.

## 5.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Project is very strong and has resources in place to manage it. |
| 4 | Project has few weak points in the area of PM and agency is working to strengthen PM. |
| 3 | Much work remains in order for PM to manage the risks of this project. |
| 2 | There is some understanding of PM for this project but understanding is rudimentary. |
| 1 | There is no evidence of PM. |

## 5.3   Guidance

Question I.D.1:  Is there a project (investment) manager assigned to the investment? (Yes/No) If so, what is his or her name?

Each program must have a program manager and the program manager name must be entered here.  There can only be one government program manager for each investment; however, there can be more than one contract manager.  In the case of multiple contract managers, they should be listed under question I.D.1.A.   Make sure the person listed in this response has read and concurs with all information in the Exhibit 300.  Be sure to provide contact information (at least the telephone number) for each of the managers listed below in Section I.D.1.A.

Question I.D.1.A:  Identify the members, roles, qualifications, and contact information of the in-house and contract project (investment) managers for this project.

The response should be in alignment with the Capital Programming Guide (A-11, Part 7).  If there are qualification gaps, then state the gaps and briefly describe the Corrective Action Plan (CAP) to eliminate them.

OMB published a policy (OMB Memorandum M-04-19, dated July 21, 2004) regarding project managers.  Paragraph 3 asks that Exhibit 300s explain the following: (1) The required PM level for this investment; (2) Whether the assigned PMs qualifications have been validated against Federal CIO Council guidance; and (3) If applicable explain when the validation will be completed.  New PMs must be validated against the CIO Council guidance within 180 days of appointment.  Status of appointments and validation should be coordinated with the AIO Value Management Office.

The following statements should be included the opening paragraph in Part 1.D.1.A, as appropriate:

1.   For projects that have a PMI PMP-certified PM and whose qualifications have been validated against the CIOC guidance:

“According to the criteria provided in the Federal IT Project Management Matrix, the (project acronym) investment requires project management level ( 1 / 2 / 3 ) support.  Mr./Ms. (Project Manager), the FAA’s project manager for the (project acronym) project, is a Project Management Institute (PMI) certified Project Management Professional (PMP) and has been certified to this level.  He/She has satisfied the IT project management competency requirements identified in the Federal CIOC Council guidance.  Mr. / Ms. (Project Manager / Team Member) can be contacted at (phone number with area code).”

2.   If the PM is supported by a team member such as an IT Lead who has completed PMI PMP certification add:

“Mr./Ms. (Project Manager) is supported by an Mr. / Ms. (IT Lead) who has satisfied the required IT project management requirements.”

Following the initial statement of qualifications above, the PM and project management team members individual qualifications and project management roles should be described.  Qualification statements should include degrees and other relevant certifications held, years of project management and acquisition experience with projects of similar size and complexity, years experience with the investment that is the subject of the OMB Exhibit 300 submission.  In cases where the PM is certified by an assessment process rather than a training program certification (e.g. PMI PMP), include a summary of significant project management experience and coursework such as Fundamentals of the AMS.

This section should also describe the project managers’ roles in the investment’s governance, lifecycle management, and performance monitoring processes, including participation in investment review boards and coordination with the IPT.

The following information should be added to this question to reflect the Agency's approach to risk management:

"The service team's risk management strategy is based on FAA's Systems Engineering Manual, Section 4.10, Risk Management Guidance.  It provides that all members and stakeholders supporting the <insert program name> meet periodically to report on and discuss status of identified medium or high program risks; and, present and or identify any potential new risks to the team for discussion, assignment of an owner, and mitigation.  Evidence of the meeting dates can be seen in some of the listed risks below under "Current Status."  The FAA risk guidance was updated in April 2004, to address OMB's 19 categories as a standard activity in risk management planning and reporting."

For new investments that have not yet completed a final JRC investment decision, this section should provide available information and state that additional management personnel may be identified as the project completes its planning phase and provide an estimated date for when the additional information will be available.

Question I.D.2:  Is there a contracting officer assigned to this project (investment)? (Yes/No)  If so, what is his/her name?

Enter the name of the contracting officer.  If there are multiple contracting officers, enter the one who is responsible for the largest contract.

Question I.D.3:  Is there an Integrated Project Team? (Yes, No)

IPT means a multi-disciplinary team led by a program manager responsible and accountable for planning, budgeting, procurement and lifecycle management of the investment to achieve its cost, schedule and performance goals.  Team skills include: budget, financial, capital planning, procurement, users, requirements analysis, quality assurance, configuration management, earned value management, operational analysis, security, Enterprise Architecture, testing and other staff as appropriate.

For new initiatives/investments that have not yet completed an initial JRC investment decision, this section should provide available information and existing team membership.  This section should state that IPT membership and needed skills will be identified when the planning phase is completed and provide an estimated date when that information will be available.

Question I.D.3.A:  If so, list the skill set represented.

Refer to the guidance in I.D.3 above.  Mention any certifications (such as project management, security, and technical) pertinent to the investment that have been completed by managers and IPT members or that are planned for completion (include the planned completion date).    It is very important to identify IPT members with Earned Value Management (EVM) and operational analysis experience.  Also, clearly identity IPT members from partnering agencies and describe how they participate in IPT activities.

Question I.D.4:  Is there a sponsor/owner for this investment?  (Yes/No)

Choose the person with developmental and execution authority for an investment/project who manages the funding for a project, once allocated, as well as securing additional funding.  The owner appoints the project manager and manages the people supporting the project.  This individual is accountable for ensuring the project is developed on time, within budget, and adheres to performance and security requirements.  The sponsor coordinates the System Development Lifecycle (SDLC) activities with those of the FAA Investment Management process and Enterprise Architecture effort. This is a long-term position that should ideally be maintained by the same individual over the life of the investment.

The FAA executive responsible for the investment should be listed as the sponsor.  If the investment is in the steady-state mode, then the sponsor should be the FAA executive responsible for its operation and maintenance.

Question I.D.4.A:  If so, identify the sponsor/owner by name and title and provide contact information.

Refer to the guidance above.

# 6.  Section I.E - Alternative Analysis

## 6.1   Introduction

In order to successfully address this area of the business case, the program must include three viable alternatives that were compared consistently.  The Agency must identify all viable alternatives and then select and report details on the top three alternatives.  The Clinger Cohen Act and OMB Circular A-94 include minimum criteria to be applied in considering whether to undertake a particular investment, including criteria related to the quantitatively expressed projected net, risk-adjusted return on investment and specific quantitative and qualitative criteria for comparing and prioritizing alternative investments.  For IT investments, agencies should use the Federal Enterprise Architecture (FEA) to identify potential partnerships or joint solutions that may be used to close the identified performance gap.  Appendix B includes the web location for the Federal Architecture Management System (FEAMS), a web-based management system designed to provide agencies with access to initiatives aligned to the FEA and the associated reference models

Information in this section should be consistent with the Business Case Analysis Report (BCAR).  If the investment alternative analysis is more than 5 years old it is considered outdated and must be updated.  This usually means that JRC approval will be needed for new phases of an existing investment or for changes to previously approved program baselines.

For investments that are past the original alternative analysis and/or didn’t have three viable alternatives, the program must schedule a new alternatives analysis (which includes a Cost Benefit Analysis) and show this as a milestone in Section I.H.

## 6.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | AA includes three viable alternatives, alternatives were compared consistently, and reasons and benefits were provided for the alternative chosen. |
| 4 | AA includes three viable alternatives, however work needs to continue to show alternatives comparison, and support must be provided for the chosen alternative. |
| 3 | AA includes fewer than three alternatives and overall analysis needs strengthening. |
| 2 | AA includes weak AA information and significant weaknesses exist. |
| 1 | There is no evidence that an AA was performed. |

## 6.3   Guidance

Question I.E.1:  Describe the alternative solutions you considered for accomplishing the agency strategic goals or for closing the performance gap that this investment was expected to address.  Describe the results of the feasibility/performance/benefits analysis.  Provide comparisons of the returns (financial and other) for each alternative.

Describe the research and methodology used to determine the need for this investment.  Describe the criteria used to choose this investment versus other investments.  Describe how closing any FAA performance gap was part of the analysis and decision-making process.  If this is a steady-state investment, mention if this alternatives analysis is part of, or a follow-on to, an E-Gov Strategy Review.  Describe the results of the E-Gov Strategy Review.  See the guidance for Section I.B. for ore information on E-Gov Strategy Reviews.

For new initiatives and/or when the AA cannot be completed before submission of the business case, include a discussion of alternatives that will be, or are being, considered and some rough order magnitude (ROM) estimates of alternative costs, benefits, and net present value.  Include the planned completion date for the Alternative Analysis, Cost-Benefit Analysis, etc. and include these as milestones in Section I.H.

- Planning/Beginning of Full Acquisition: At this point in the lifecycle the program is describing the alternatives considered to meet a mission need or close a performance gap.

- Full Acquisition/Beginning of Maintenance:  At this point in the lifecycle the program should be validating that the previously selected alternative is still the best alternative versus other possible alternatives, and continues to meet the specified cost, schedule, and performance goals.

- Steady-state:  Once the investment has reached the maintenance and operations phase the program should periodically validate that it continues to meet the specified cost, schedule and performance goals, and that it’s performing well.  The alternative analysis should discuss the performance benefits versus other alternatives such as replacement or upgrade.  If the investment is not meeting performance goals or needs, the alternatives analysis is looking at future alternatives for replacement or upgrade.

Question I.E.1.A:  Discuss the market research that was done to identify innovative solutions for this project (e.g., used an RFI to obtain 4 different solutions to evaluate, held open meetings with contractors to discuss project scope, etc.).  Also describe what data was used to make estimates:  past or current contract prices for similar work, contractor provided estimates from RFIs or meetings, general market publications, etc.

| Alternative | Description |
| --- | --- |
| Alternative #1 | Summary of findings: |
| Alternative #2: | Summary of findings: |
| Alternative #3 | Summary of findings: |

Using the Alternatives Table make sure the alternatives are all viable.  Do not list an alternative you examined if your analysis showed it was not a feasible or viable alternative.  List a very short title of the alternative in the first column, and provide summary information in the description column.

Question I.E.2:  Summarize the results of your life-cycle cost analysis performed for each investment and the underlying assumptions.

| Cost Elements | Alternative 1 | Alternative 2 | Alternative 3 |
| --- | --- | --- | --- |
| Element 1 |  |  |  |
| Element 2 |  |  |  |
| Element 3 |  |  |  |
| Element 4 |  |  |  |
| Element 5 |  |  |  |
| Total |  |  |  |

For each alternative, use the table in this section to list the cost elements used for comparison purposes when conducting the analysis, and summarize the associated resources and findings from your analysis.  Make sure the elements are consistently compared, per OMB scoring criteria.  New projects should include security costs and considerations with each alternative.  At a minimum the cost elements should include hardware, software, contractor labor, and government labor (FTE) costs for each project phase (planning, development/implementation, and maintenance.  State whether dollars are in thousands or millions.  State whether costs shown are in constant dollars of inflated dollars.  (Constant dollars should normally be used for the alternatives and cost benefit analysis).

Describe how the project risk-adjusted the benefits, milestone and schedule costs or explain how the program plans to risk-adjust these costs.  Use Section I.E.3 to provide this information if the CPIC tool does not allow narrative text in this section.  This narrative should include information on whether/how costs of mitigation strategies shown in the risk table are included in the Section I.H costs.

The updated alternatives analysis should not include sunk costs in questions I.E.2 or I.E.3.  All alternatives should be based on the best way of closing the performance gap from this point forward.  However, if the CBA was done within the last five years and is still valid (assumptions still hold true and there are no major changes in the program environment), then the cost estimates of the original or most recent AA would continue to be reported and these would include the sunk costs that have been incurred to date since the last AA update.

Question I.E.3:  Which alternative was chosen and why?

Identify the alternative from the above analysis that was selected and explain why.  This section should include a summary comparison of the total ROI and NPV of the alternatives and other considerations such as differences in costs, benefits, and risks that explain why one alternative is preferred over the others.  If agency funding decisions/constraints have resulted in the selection or implementation of an alternative that was not the preferred one, this should be explained in this section.

Explain how the program defined the ROI (is it measured by cost savings, improved efficiency in specific processes, decreased error rates, etc.) and what that return is expected to be for each of the three alternatives.  Describe how the estimated returns provided by each alternative compare to one another.  Also discuss the payback period and the NPV at investment completion/end for all three alternatives.

It is important to have consistency between the lifecycle costs for the selected alternative in this section, the SoS table and Section I.H.  There are reasons however why the costs shown in Section I.E will not match the costs shown in the SoS table or Section I.H.  Below are some reasons why these costs may not match that can be included as appropriate in this section:

- The SoS table should show the investment’s inflated costs and total lifecycle costs, from beginning until it is discontinued or replaced.

- The AA table in I.E.2 showing the total costs of all three alternatives should be consistent with whether they used constant or inflated dollars in their analysis of costs and benefits and in the NPV table in I.E.3.B.  Normally the analysis should be based on constant/real dollars instead of inflated.  The cost table in I.E.2 would normally not include sunk costs (i.e. it would include only those costs from the latest AA update and the costs would include only those years shown in the NPV table).

- The AA NPV table in I.E.3.B would normally use non-inflated constant/real dollars.  It would not include sunk costs prior to the latest update to the AA.  The narrative in Section I.E.3 should include a brief explanation of the rates used, the reasons and if inflated dollars were used for their analysis, and an explanation of the reason.

- The costs shown in Section I.E should include government labor (FTE) costs, however if FTE costs were not included in the planning, acquisition and maintenance rows of the SoS table, this should be explained in Section I.E.

- The FAA CIP (approved budget) in the SoS table may not be the same as the total costs for the preferred alternative or the related approved program baseline.

Question I.E.3.A:  Are there any quantitative benefits that will be achieved though this investment (e.g., systems savings, cost avoidance, stakeholder benefits, etc.)? Define the Return on Investment (ROI).

Discuss the quantitative benefits used to make up the expected yearly costs and benefits used in the NPV calculations.

The benefits described in this section should be consistent with those described in Sections I.A and I.B.8 and should be measurable by the performance goals and measures in Section I.C.  Benefits that cannot be measured now or in the future should not be included in this section.

Benefits to be considered should include increased safety, accuracy, availability, and efficiency and related cost savings or avoidances.

Question I.E.3.B:  For the alternative selected, provide the financial summary, including Net Present Value by Year and Payback Period Calculations.

| Year = | FY | FY | FY | FY | FY | FY | FY | FY | FY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual Cost |  |  |  |  |  |  |  |  |  |
| Annual Benefit |  |  |  |  |  |  |  |  |  |
| Discount Factor |  |  |  |  |  |  |  |  |  |
| Discounted Benefit |  |  |  |  |  |  |  |  |  |
| Net Present Value (NPV) |  |  |  |  |  |  |  |  |  |
| Payback Period (Cumulative NPV) |  |  |  |  |  |  |  |  |  |

Net Present Value by Year:  For the selected alternative, start with the first fiscal year used in the analysis, and continue through the last fiscal year used in the analysis.

Indicate whether constant or inflated dollars are being used.  (Constant dollars are usually used in a cost-benefit analysis).  State the discount rate that is being used (for example, 7%).

The number of years included on the NPV table should include all years from the date of the last update to the analysis through the last year of the estimated total life of the investment.  The last year of the expected investment life should be consistent with the date shown in response to the “investment completion date” screening question.

To calculate the pay back period, add the individual yearly estimates from the Expected Yearly Benefit row and compare it to the Expected Yearly Costs total for that row.  The year when the sum of your expected yearly benefits exceeds your total costs is the beginning of the investment pay back period.

When an analysis is updated, sunk costs should not be included in the updated NPV table.

Question I.E.4:  What is the date of your cost-benefit analysis?

Provide the month and year of the last time it was updated.

# 7.  Section I.F - Risk Inventory and Assessment

## 7.1   Introduction

In order to successfully address this section of the Exhibit 300 the program must have performed a Risk Assessment and developed a Risk Management Plan at initial concept, addressed the mandatory risk elements defined below and demonstrate active risk management throughout the life-cycle of the investment.  For all investments, both IT and non-IT, the program must discuss risks in the pertinent risk areas listed below and discuss plans to mitigate the risk.  If there is no risk to report for the investment achieving its goals from a risk category, say this.  Only a subset of a project’s active risks are required – sufficient to demonstrate that all 19 aspects have been considered.  If there are additional risks, current E-CPIC capabilities require arrangements to be made to include these in a separate attachment.

Risk assessments for all investments must include reporting for: 1) schedule, 2) initial costs, 3) life-cycle costs), 4) technical obsolescence, 5) feasibility, 6) reliability of systems, 7) dependencies and interoperability between this investment and others, 8) surety (asset protection) considerations, 9) risk of creating a monopoly for future procurements, 10) capability of agency to manage the investment, and 11) overall risk of project failure.

In addition, for IT investments, risk must be discussed in the following categories: 12) Organizational and Change Management, 13) Business, 14) Data/Info, 15) Technology, 16) Strategic, 17) Security, 18) Privacy and 19) Project Resources.  For all risks, identify under the probability of occurrence column the level of risk as high, medium, or basic based on the assessment criteria defined in the approved Risk Management Plan.  Note that OMB uses the term “basic” for “low” risks.   For security risks, what aspect of security determines the level of risk (i.e., the need for confidentiality of information, availability of information or system, reliability of the information or system)?

## 7.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Risk assessment was performed for all mandatory elements and risk is managed throughout the investment. |
| 4 | Risk assessment addresses some of the risk, but not all that should be addressed for this investment. |
| 3 | Risk management is very weak and does not seem to address or manage most of the risk associated with the investment. |
| 2 | Risk assessment was performed at the outset of the investment but does not seem to be part of the program management. |
| 1 | There is no evidence of a risk assessment plan or strategy. |

## 7.3   Guidance

The following table lists and defines the risk areas to report risks against and which programs must address them:

| Area of Risk | Risk Area Description | Must be addressed by: |
| --- | --- | --- |
| 1 – Schedule | The risk that the project will not be completed within the schedule specified | All programs |
| 2 – Initial Costs | The risk of exceeding the initial cost estimate figures | All programs |
| 3 – Life-cycle Costs | The risk that the project will not be completed within the budget specified | All programs |
| 4 – Technical Obsolescence | The ability to adequately maintain the system after deployment | All programs |
| 5 – Feasibility | The risks associated with adequately developing, fielding, and maintaining the resulting systems | All programs |
| 6 – Reliability of Systems | The risk that the system availability/downtime will have a negative effect on field operations. | All programs |
| 7 – Dependencies and Interoperability Between This and Other Investments | How well the system or program produced operates with other internal or external organizations’ systems | All programs |
| 8 – Surety (Asset Protection) Considerations | The risk of an organization not to protect fixed, intellectual, and human assets from harm – related to Continuity of Operations Plans | All programs |
| 9 - Risk of Creating a Monopoly for Future Procurements | The unavailability of several different sources for procurement of goods and services | All programs |
| 10 – Capability of Agency to Manage the Investment | The risk to program success from the complexity of the project (e.g., number of subtasks and/or number of performing organizations). Risks associated with obtaining and using applicable resources and activities, which may be outside the project’s control but can affect the project’s outcome | All programs |
| 11 – Overall Risk of Investment Failure | The risks to the project from a holistic view that considers project management, technology, contract, cost, schedule, performance, requirements as well as the other risk categories | All programs |
| 12 – Organizational and Change Management | The risk associated with various stakeholders supporting the development, implementation, and operation of the project, such as Congress, users, senior business executives, and business organizations | IT programs only |
| 13 – Business | The risk inherent in system operation, including the probability of failure, external influences, organizational or management structure, change management, and availability of project resources (labor, materials, services) | IT programs only |
| 14 – Data/Info | The risk that input data and information is of substandard quality and integrity or the possibility that data is managed or used incorrectly | IT programs only |
| 15 – Technology | The risk associated with (1) developing a new or extending an existing technology to provide a greater level of performance than previously demonstrated, (2) achieving an existing level of performance subject to new constraints, or (3) how well the system operates to design or safety specifications | IT programs only |
| 16 – Strategic | The negative effect of changes in the strategic goals of an organization on the project | IT programs only |
| 17 – Security | The risk that IT and physical security is not sufficient to protect an organization’s fixed, intellectual, and human assets. Level of risk, determined primarily by confidentiality, availability, or reliability, is “basic” | IT programs only |
| 18 – Privacy | The risk that the privacy of the public or of the organization’s workers is compromised | IT programs only |
| 19 – Project Resources | The risk of unavailability of funds, staff, and contractual resources when they’re needed and confidence in management and Congress that these resources will continue to be provided | IT programs only |

Table 6: OMB Risk Reporting Categories

Indicate any mitigation risk or strategies whose costs have been included in the Section I.H milestones, regardless of whether they are shown as individual milestones or included as part of other milestones.  Clearly identify in the Strategy for Mitigation or in the Current Status columns if the risks and/or mitigation strategy have been used to adjust the cost and schedule goals shown in Section I.H, including whether management reserve is included.

Please note that this section is to be updated at least once a year, or as often as your Risk Management Plan is updated to reflect risk management updates.

Date Identified: Provide the date when the risk was first identified.  Every program must perform some kind of risk assessment during the initial concept/planning stage, therefore at a minimum the date of the initial risk assessment should be entered in this column.  However, risks are not static; therefore as risks are mitigated and replaced by new ones, the “Date Identified” should change to reflect the new risks.  A risk assessment should normally be updated at least when an investment enters a new lifecycle phase.

Description of Risk:  Briefly describe the specific risk that was identified for each risk area.  Also describe the seriousness and level (low, medium, or high) of the impact an occurrence of this risk would have on agency missions. The risk statement should be clearly stated in the “if – then” format to clearly explain the specific risk and its consequences/impact.  This column should also be used to indicate the date when the risk information was last reviewed or updated.  Do not simply put N/A in a risk category.  Instead use the risk description and risk mitigation columns to describe why the risk is negligible.  The risk description and impact should be updated to reflect the current phase and status of the investment.

Probability of Occurrence: Using the criteria established in the approved Risk Management Plan, develop a method for determining whether the magnitude of the risk is rated as High, Medium, and Basic (low).  This field should reflect the current risk level based on the status of mitigation actions.

Strategy for Mitigation: Briefly describe the preventative methods or plan for addressing the risk and discuss if mitigating this risk resulted in adjusting your return on investment in question I.E.3.B.

Current Status: Briefly describe the status of your mitigation activities, to include identifying any mitigation actions that have been completed and the status of ongoing ones. Provide specific milestones and dates as appropriate, rather than stating that mitigation activities are on-going.   On-going projects should be sure to update any outstanding status commitments from last year’s Exhibit.  If a specific risk mitigation results is reflected in the (risk adjusted) cost or schedule baseline(s), indicate so.

As a quality check on the entries made, read the entries for each category to see if they’re coherent.  Does the risk statement describe the risk, its root cause, and the impact to success of this investment?  Does the strategy actually address the risk described?  Does the status demonstrate how the strategy is being implemented and whether the risk is being reduced as a result?

Question I.F.1:  What is the date of your risk management plan? (MM/DD/YYYY)

This response should reflect the date when the governing Risk Management Plan was last approved.  An Exhibit 300 cannot score a 5 if it does not demonstrate in the Risk Management (RM) section that risk is being managed consistently throughout a program’s life.   An indication that an investment is effectively managing risk is to read the Exhibit 300 from front to back.  Are the risks discussed in the other sections of this business case reflected in the risk section?  If not, the Exhibit is NOT presenting strong evidence that risks are being proactively managed.  Appendix D to this document contains additional guidance on consistency.

# 8.  Section I.G - Acquisition Strategy

## 8.1   Introduction

In order to adequately address the questions in this section OMB wants to see programs employ a strong acquisition strategy that mitigates risk to the federal government, accommodates Section 508 as needed, and uses performance based contracts.  If an investment is not using performance based contracts and Statements of Works (SOWs), the acquisition strategy should clearly state the reasons that prompted use of other than performance based contracts and SOWs and how the risk to the government will be mitigated.  Implementation of the acquisition strategy must also be clearly defined.

Information in this section should be consistent with the Information Strategy and Planning (ISP) document.

Finally, this section should map the contract CLINs to the useful segments and milestones that are documented in Section I.H.

## 8.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Strong Acquisition Strategy that mitigates risk to the Federal Government, accommodates Section 508 as needed, and uses contracts and statements of work (SOWs) that are performance based. Implementation of the Acquisition Strategy is clearly defined. |
| 4 | Strong Acquisition Strategy that mitigates risk to the Federal Government, accommodates Section 508 as needed, uses contracts and SOWs that are performance based. Acquisition strategy has very few weak points which agency is working to strengthen, and the implementation of AS is clearly defined. |
| 3 | Acquisition strategy does not appear to successfully mitigate risk to the Federal Government, accommodates Section 508 as needed, much work remains to solidify and quantify the AS, and contracts and SOWs do not appear to be performance based. |
| 2 | Acquisition strategy does not appear to successfully mitigate risk to the Federal Government, does not accommodate Section 508, does not appear to use performance based contracts and SOWs, and there is no clear implementation of the acquisition strategy. |
| 1 | There is no evidence of an AS. |

## 8.3   Guidance

Question I.G.1:  Will you use a single contract or several contracts to accomplish this investment?

Question I.G.1 is followed by two other questions that go into more detail about single versus multiple contracts.  When answering these questions, keep in mind that FAA is moving towards Firm Fixed Price (FFP), performance based contracts.  These are contracts in which the Government specifies the end requirement and allows the contractor to provide the solution at a specific price.

In addition to listing each of the contracting vehicle(s) for the investment and how they interrelate, please specify what agency “owns” the contract.  For example:  GSA Schedule 70, Company ABC.

Question I.G.1.A:  What type of contract/task order if a single contract is used?

Specify the type of contract; Firm Fixed Price (FFP), Cost Plus Fixed Fee (CPFF), Time and Materials (T&M), etc.  Also specify if the contract is a performance-based contract.  All contracts or task orders must be performance-based.  Specify any plans to use FFP and performance based contracts in the future if they are not currently being used.

If multiple contracts are being used then enter N/A and go to question I.G.1.B

Question I.G.1.B:   If multiple contract/task orders will be used, discuss the type, how they relate to each other to reach investment outcomes, and how much each contributes to the achievement of the project cost, schedule and performance goals.  Also discuss the contract/task order solicitation or contract provisions that allow the contractor to provide innovative, transformational solutions.

Specify the type of contract; FFP, CPFF, T&M, etc.  Also specify if the contract is a performance-based contract.  All contracts or task orders must be performance-based.  Specify any plans to use FFP and performance based contracts in the future if they are not currently being used.

In addition, describe any contract clauses that allow the contractor to achieve performance of the contract in the manner it determines will result in better, faster, cheaper results to the Government.  OMB’s guidance is that programs should use FFP contracts for the DME phase of an investment.

Additionally, map the various contracts to the Exhibit 300 PB and useful segments in Section I.H.  For example, contract A covers useful segments A and B and includes the following CLINs.  Contract B covers useful segment C and includes the following CLINs.

Question I.G.2:  For other than firm-fixed price, performance-based contracts, define the risk not sufficiently mitigated in the risk mitigation plan, for that contract/task order, that requires Government to assume the risk of contract achievement of cost, schedule and performance goals.  Explain the amount of the risk the government will assume.

FAA is working to move away from cost-reimbursement contracts in which the Government assumes the risks associated with cost, schedule and performance goals.  Cost reimbursement contracts are those in which the Government cannot fully define all its requirements at the beginning of the contract.  This opens the Government to greater risk in that the contractor will get paid for good faith effort even though the Government’s requirements may not be fully realized

OMB’s guidance is that FFP contracts should be used for the DME phase of an investment.  If a program has contracted services under a non-FFP contract, the program should list them and explain the rationale for using these types of contracts.  Discuss what and how much risk to the government exists due to the contract structure, what strategies and actions that will or have been implemented to mitigate these risks, and what risks remain.  Information on risks and mitigation activities should be consistent with and included in the information provided in Section I.F Risk Management (RM).   The program should also describe how contractors will use Earned Value Management (EVM) to help identify, manage, and mitigate project risks.  If additional performance incentives and other methods of reducing the government’s risks have been added into non-FFP contracts, mention them here but leave the details for question I.G.3.

Question I.G.3:  Will you use financial incentives to motivate contractor performance (e.g. incentive fee, award fee, etc.)?

FAA is working to increase the use of contracts that reward contractors for using innovative solutions to meeting the Government’s requirements.  Describe any level of incentives (fees) instituted into contracts to motivate the contractor.

An example of incentives is the Share-in-Savings contracts.  These are IT contracts in which the Government, under the authority of Section 210 of the E-Government Act of 2002, awards a contract to improve mission related or administrative processes, or to accelerate the achievement of its mission and share with the contractor in savings achieved through contract performance.  Acquisitions using the share-in-savings authority in section 210 must be funded from the funds that would have been appropriated for operations and maintenance of the legacy system the new system is replacing, and this must be reflected in lifecycle costs.  If a Share-in-Savings contact was used, the preparer must also answer “Yes” to Screening Question g.  More information on Share-in Savings contracts can be found at http://www.gsa.gov/shareinsavings.

Question I.G.4:  Discuss the competition process used for each contract/task order, including the use of RFP’s, schedules or other multiple agency contracts, etc.

Programs should work with their contracting officer to determine how competition was, or will be, obtained.  Programs should discuss contracts outside of FAA (such as the GSA Schedules Program or other Government-Wide Acquisition Contracts [GWACs]), with their contact in the sponsoring office.  While these contracts have typically been subject to competition prior to their award, this section is strongest when it addresses any additional competition that was done for each individual contract/task order.  Information that should be included is primary source selection factors, how vendors were/are compared, and how past vendor performance and process improvements are factored in.  If procurements are software intensive, explain how the Capability Maturity Model is used in contract determination.

The answer for this question should be consistent with the contents of the “Procurement Strategy” section of the Implementation Strategy and Planning (ISP) document that is completed when establishing baselines in the investment analysis process.  More information can be found at FAST website

Question I.G.5:  Will you use commercially available commercial off-the-shelf (COTS) products for this investment?

For the first part of the question, list all commercial off-the-shelf products that are being used for this program, including software and hardware.  The FAA is working to utilize COTS products as much as possible.  This allows for greater compatibility across offices and agencies as well as reduces development costs.  Highlight any agency wide procurement contracts/ licensing agreements used to purchase COTS products.

If no COTS products were used, the preparer should state as such and then explain why in Question I.G.5.B.

Question I.G.5.A:  To what extent will these items be modified to meet the unique requirements of this investment?

Again, OMB is looking for all agencies to utilize COTS products as much as possible.  If an investment is using a COTS product that has to be modified extensively, or the investment requires software development, please explain in question I.G.5.A.  The explanation should include what changes are being done to the product and who is performing the changes (is done by the product’s manufacturer, an outside contractor, or in house).  Be sure to address how modifications impact cost, schedule, and performance goals reflected Section I.H.

Question I.G.5.B:  What prevented the use of COTS without modification?

This section will need to provide a very persuasive argument as to why an investment could not use a COTS product.  If an investment was unable to utilize COTS products, a detailed response will be required.  Cost/benefit information would be helpful here to show empirically why a non-COTS solution was chosen.

Question I.G.6:  What is the date of your acquisition plan?

For FAA, the Implementation Strategy and Planning (ISP) document, which is required as part of the FAA AMS, is the acquisition plan.  Even if a project is using multiple contracts, as part of good project management the ISP lays out the project’s contracting needs, how they are being met, the types of contracts being used, etc.  The ISP should be used as a reference point for all the questions in the Acquisition Strategy (AS) section of the Exhibit 300.  The date of a program’s most recent ISP will be the answer to this question.

If an acquisition plan is over 5 years old, it should be reviewed to determine if it needs updating.  If it will be or is being updated provide a completion date for the update, in the narrative at the beginning of Section I.G.  If the plan is still relevant and needs no update, explain this and the date of your review, in the narrative at the beginning of Section I.G. When a new/updated plan has been approved, the date of its approval should be provided in this section.

Question I.G.7:  How will you ensure Section 508 compliance?

For each proposed investment, the response must include an explanation as to how (i.e. what steps will be taken) the program will ensure this compliance.  A system must comply with the Section 508 standards if it is classified as electronic information technology (EIT).  All EIT procured, developed, maintained or used by FAA lines of business must comply with the Section 508 EIT accessibility standards.  A list of standards and additional Section 508 guidance is included in Appendix E.

If program requirements were contracted out or ordered under a task order subsequent to 6/21/01, then insert one of the following responses to respond to this question (choose one).

Response #1:

“In accordance with FAA's Section 508 Procurement Standard Operating Procedures, (insert name of program) will determine which of the Section 508 standards apply to the program and comply with each applicable standard.”

Response #2:

“In accordance with FAA's Section 508 Procurement Standard Operating Procedures, (insert name of program) has determined that the following Section 508 standards apply to the program and will comply with each applicable standard.”

Be sure to include standards as appropriate.

This section should also state whether 508 compliance is required in the contract and how compliance is verified.  For example, state whether inspections or tests are conducted to help ensure compliance.  Due to the nature of some jobs in the FAA (e.g. Air Traffic Control Series 2152), certain jobs cannot be fulfilled by people unless they meet strict medical qualifications.  For example, Air Traffic Controllers cannot be blind or deaf.  Therefore, many 508 compliance actions are superfluous to the needs of EIT users and add unnecessary costs.  If a program manager believes this situation applies to their program, they should arrange for Section 508 exemption with the FAA Section508 Coordinator and SME.  The answer to question I.G.7 should state that exemption was given and why.  Additionally, the program will need to include the Section 508 Exemption document with their submission.

Section I.G.8:  Acquisition Costs:

Acquisition costs entail all the costs shown in the SoS, except for government FTEs.  For the budget year, if at all possible, use information from DELPHI to formulate an estimate of how much will be spent.  The percentages shown in response to questions I.G.8.A, B, and C should total 100%.

Question I.G.8.A:  For budget year, what percentage of the total investment is for hardware acquisition?

These costs include any hardware items such as servers or PCs dedicated to the system/investment.  These costs usually do not include contractor labor.

Question I.G.8.B:  For budget year, what percentage of the total investment is for software acquisition?

Examples include purchasing COTS, or custom developed software. These costs usually do not include contractor labor.

Question I.G.8.C:  For budget year, what percentage of the total investment is for services acquisition?

These costs include contractor labor.

# 9.  Section I.H - Project and Funding Plan

(NOTE:  This section is under review and subject to change.)

## 9.1   Introduction

OMB and AMS policies require development, modernization, and enhancement (DME) programs to use Earned Value Management (EVM) based on the guidelines in the American National Standard ANSI/EIA-748.  FAA programs are required to apply EVM methodologies to the total program effort, including both government and contractor work, to better manage complex, high-risk, high-cost, or high-visibility efforts.  While DME programs primarily occur during solution implementation, the work, as approved, may start during final investment analysis and may continue during in-service management.

Program managers responsible for FAA capital investment programs that involve DME activities are required to develop and implement an EVM system consistent with guidance in ANSI/EIA 748, FAA AMS Policy (Section 4.16) and the FAA EVM Guide. Capital investment programs required to use an EVM system in accordance with AMS Section 4.16.1 must be certified as meeting the guidelines of ANSI/EIA-748.  The EVM Focal Point (ATO-A) assesses and validates EVM implementation and monitors application to ensure compliance.  The AIO Value Management Office (AIO) certifies program EVM systems.

In order to successfully complete this section of the Exhibit 300, the program manager must describe how the program is integrating all related management disciplines (e.g., systems engineering, cost estimating, procurement, scheduling, and risk management) using earned value management to effectively support program execution.  Earned value management provides the FAA with timely, accurate, and integrated cost, schedule, and technical performance information for both the total investment program and individual supporting contracts.  It continuously measures the quantity and value of completed work and enables the program to forecast reliable estimates of future performance.

In this section the program manager is also required to show how well the investment is meeting the approved cost, schedule and performance goals for each DME activity.  DME programs must apply EVM to the total program effort, including both government and contractor work, according to the following table.

The VMO office and the EVM SME coordinates with OMB and programs to determine which investments are categorized as “major”, “non-major”, or “other”.

For those projects in the Maintenance (Steady-State) phase the program must perform an Operational Analysis (Operational Assessments for FAA) as defined in the Capital Programming Guide to demonstrate that the investment is continuing to close the performance gap and achieve the expected performance goals.

Additional EVM guidance can be found in the EVM Guide on FAST.  The EVM Guide provides program managers, contracting officers, executives, executive committees, and review boards with a further understanding of the application of E VM concepts in support of program management practices in FAA that will contribute to improved program performance.

Note:  Contact the VMO office to obtain the correct language and current status for agency-wide EVM efforts.  Also, more detailed guidance on EVM processes will be included in the training sessions.

## 9.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Agency will use, or uses an Earned Value Management System (EVMS) that meets ANSI/EIA Standard 748 and investment is earning the value as planned for costs, schedule, and performance goals. |
| 4 | Agency uses the required EVMS and is within the variance levels for two of the three criteria. Work is needed on the third issue. |
| 3 | Agency uses the required EVMS but the process within the agency is either very new, not fully implemented, or there are weaknesses in this investment's EVMS information. |
| 2 | Agency seems to re-baseline rather than report variances. |
| 1 | There is no evidence of PB. |

## 9.3   Guidance

Question I.H.1:  Description of performance-based management system (PBMS):

Start this section with a discussion of the methodology and relevant agency-wide EVM policies and tools being used to manage the program.  Describe the process used to verify that the contractor's project management system follows the ANSI/EIA Standard 748-A.

If the project is in the Maintenance (Steady-State) phase, define the Operational Analysis system that will be used to evaluate that the investment is continuing to close the performance gap and meet the expected goals.  If this is a mixed lifecycle project with both Maintenance and DME activities earned value must be used on the DME portions of the contract and Operational Analysis on the maintenance portions.

An operational analysis “system” includes the processes, documentation, and automated tools that are used to track and measure performance.  An Operational Analysis will focus on four key factors per the requirements of the OMB Capital Planning Guide:  Customer/User Satisfaction; Internal Business; Strategic Impact; and Innovation.

- Customer Satisfaction – the investment continues to meet ongoing customer and stakeholder needs, particularly with respect to providing enterprise-wide tools and applications.

- Internal Business – the investment continues to evolve and grow.

- Strategic Impact – the investment continues to meet or exceed the majority of its performance goals and expectations as outlined in Tables I.C and I.H.

- Innovation – the investment continues to take a leading role among business and technical initiatives.

Within the above categories or in addition to them it is important to track performance, obsolescence, and the trend of maintenance and operating costs as well as any other indicators that are critical to the investment’s ability to support FAA missions and strategic goals as well as its own performance improvement goals.

If the investment/project is in planning, full acquisition, or mixed –

Briefly describe how the program:

- Meets the management control system guidelines in ANSI/EIA-748;

- Creates an integrated performance measurement baseline (resource-loaded schedule of work to be performed at the lowest level required for performance measurement);

- Establishes a work authorization system that assigns responsibility for and controls changes to the performance measurement baseline;

- Tracks earned value for planned budgets as work is completed;

- Provides status against the baseline plan and identifies significant schedule and cost variances.  If the program baseline in Table I.H.2 has been modified or replaced explain what modifications were made, why, and when the new useful segment(s) start.  Indicate if the project baseline, including all the milestones and costs shown in Table I.H.2, have been approved by the JRC.  If not, indicate what portion or useful segment of the investment still needs to be approved and any planned dates for obtaining JRC or other approval.  If the program needs to re-baseline, explain the reasons for re-baselining, whether the re-baseline has been approved by the JRC, and ensure the proposed new baseline is entered into Table I.H.3.  Once OMB has reviewed and approved the new baseline it can be removed from Table I.H.3 and moved to Table I.H.4.

- Analyzes variances for early warning signs and take corrective action as necessary;

- Estimates final cost and schedule outcomes.

- Reconciles the cost values represented in Section I.H to the cost values represented in the Summary of Spending (SoS) table in Section I.A.

- Defines a useful segment(s).  Describe how the useful segments map or are represented in the program WBS.  References to lifecycle phase and duration should also be included.

- Makes risk adjustments to program schedule and costs.  Describe the process and tools that were used and how mitigation costs in Section I.H milestones associated with risks outlined in Sections I.F and II.B are included in the cost and scheduled dates shown in Section I.H.  Explain how unmitigated risks are reflected as part of the program’s management reserve.

- Decides what portion of the program’s contracts use an EVMS.  What is the contract percentage for each useful segment or phase shown in I.H?  This should be consistent with the information in Section I.G, although it does not need to be as detailed.

- Verifies the contractor’s EVMS system is compliant with ANSI-EIA standard 748-A.  This would include Integrated Baseline Reviews (IBRs).

- Uses management tools, processes, and disciplines to analyze the earned value performance data to track and manage the project’s performance.  Describe the processes the program uses to track and manage the project’s performance.  This would include regular periodic status meetings involving IPT members, status and other reports generated for and reviewed by whom, and governance processes such as periodic reviews by the capital planning/investment review boards/committees, EA committee, etc.  This information should be consistent with the management processes described in Section I.D.

- Plans to enhance program and contractor EVMS performance.  Provide a timeline. For the portion of your contracts that do not use EVMS, what milestones do these contracts cover?  This should be consistent with the information in Section I.G, although it does not need to be as detailed.

For steady-state investments  –

These are projects that are operational and performing routine operational maintenance/technology refresh.

- Describe the Operational Analysis (Assessment) system and procedures that are being used to track project performance.  Include information from the latest semi-annual SLR reports.

- Have Post-Implementation Reviews (PIRs) been conducted?  If so, when and what was addressed by the reviews?  If not, has a PIR been planned?  Include the date of the planned PIR.

- Have PIRs or other review processes addressed e-Gov strategy issues such as whether the project is still meeting performance goals, and is it meeting current agency strategic and performance goals?  Is it aligned with the agency’s EA?  Is there a current Alternatives Analysis that can be cited as evidence that current alternatives were looked at and that the existing investment is still the best solution?  Include results from the latest SLR.

Applicability of Section I.H Tables

If the investment is new and no costs have been or will be incurred before the Exhibit 300s are submitted to the JRC or OMB, then only Table I.H.2 needs to be completed.  There may be instances however where a new investment will have incurred no expenses when it is submitted to the JRC for approval but will have incurred expenses by the time the Exhibit 300 is submitted to OMB.  In such cases Section I.H.4 will not need to be completed for the Exhibit 300 PB but it will need to be completed in the OMB Exhibit 300 Report.  In cases where an Exhibit 300 is being completed for the first time for an ongoing investment that is already incurring costs, Section I.H.4 must be completed for both the Exhibit 300 PB and the OMB Exhibit 300 report

Question I.H.2:  Original baseline (OMB-approved at investment outset):

What are the cost and schedule goals for this phase or useful segment of the investment?  Also identify the funding agency for each useful segment and milestone if this is a multi-agency investment.  For projects, or portions of projects, that have reached steady-state enter one line for each fiscal year of this phase.  If the project is mixed life-cycle there will be two parts to the baseline; one for the O&M portion and one for the DME portion using EVMS.  Please note that this original baseline must be included in all subsequent versions of the Exhibit 300, even when there are OMB-approved baseline changes shown in Table I.H.3.

For on-going projects, this baseline is the original baseline first submitted to OMB in an Exhibit 300; any proposed changes to the baseline should be entered in Table I.H.3.  If the existing JRC approved baseline shown in the latest Exhibit 300 PB needs to be decomposed into more detail but there are no changes to the total cost or planned completion date of the original useful segment higher level milestone dates and costs, then these changes do not constitute a re-baseline and there would be no need to request a re-baseline in Table I.H.3.

For new projects Table I.H.2 will be the starting point for reporting cost, schedule and performance goal information.  The FAA considers the useful segments and associated milestones presented in this section preliminary at this point in time, as this investment has not yet been baselined by the JRC. The Exhibit 300 PB must include at least annual milestones for the entire useful segment or phase for which JRC funding approval is being requested.  Once this investment has been baselined by the JRC, this section will be updated to reflect JRC baselining decisions and will become the JRC approved baseline reflected in the Exhibit 300 PB.  Table I.H.2 will show the milestones and costs for all the useful segments and phases that are part of the JRC approved baseline.

If a new useful segment needs to be added to the Exhibit 300, but the original I.H.2 baseline remains unchanged, then the new useful segment would be added to Table I.H.2.  Table I.H.3 would be completed showing the previous segments plus the new segment that is being added. Table I.H.3 would be completed even if no changes were being proposed to the previously approved program baseline.   In this way the new segment baseline will remain identified as an original baseline in Table 1.H.2 but it will also be part of the overall revised baseline shown in Table I.H.3.  Clearly explain in Section I.H.1 and via headings on the tables that this is a new segment that does not change the previous approved baseline and clearly identify where you are inserting it in Table I.H.2 and I.H.3.  Any addition of useful segments (which have not already been approved for funding by the JRC) or changes to existing previously approved baselines should be approved by the JRC prior to being submitted to OMB.

If a project re-baselines in Table I.H.3, past milestones from the beginning of the current phase and useful segment(s) would need to be included in the re-baseline, and their actual performance would need to be reported in Table I.H.4 to ensure that cumulative costs are tracked for the entire useful segment.

For the OMB Exhibit 300 report, annual updates to Section I.H will be required including entering updated actual cost and schedule performance information in Table I.H.4.  Internal FAA reprogramming of funds that have not been approved by the JRC as a new baseline, will be reflected in the actual cost and schedule performance status and variances reported in I.H.4 and will not be shown as a proposed new baseline in I.H.3.

For new projects in the upcoming budget process, be sure to include security planning milestones and significant risk mitigation actions with your overall project planning; security planning is a part of each phase of the system’s life-cycle.

Milestones for the DME phase of an investment should be detailed, with each milestone lasting less than one year.   The milestones should consist of activities/tasks that are reflected in the WBS and where possible should show detail to the fourth level of the WBS.

Include security milestones such as the completion of security plans, risk assessments, and certification and accreditations (C&As) either separately or as part of the other DME milestones (in which case, the milestone description should clearly state that they are included as part of that milestone).

Include all the types (planning, acquisition/DME, maintenance) of costs reflected in the spending summary for the years covered by the current useful segment/phase described in I.H

- Include risk costs/adjustments both in terms of extra $ to include risk mitigation actions and/or longer schedule (Milestone descriptions should show if they include risk mitigation activities).

- Do not subtract the risk reserve either from section I.H or the spending summary.

- Include estimate of FTE costs of government personnel.  The preferred approach and long term goal is that the milestone costs in I.H should incorporate government labor (FTE) costs.  Since at present it has been difficult to incorporate FTE costs at the milestone level, for now at FAA, at a minimum,  FTE costs should be shown for each useful segment, and year of O&M.

Section I.H.3:  Proposed baseline (applicable only if agency intends to propose a baseline modification):

Programs will enter a proposed change to the original or current baseline or an OMB-approved baseline change in Table I.H.3.  What are the new cost and schedule goals for the project (e.g., what are the major project milestones or events; when will each occur; and what is the estimated cost to accomplish each one)?  Also identify the funding agency for each milestone or event if this is a multi-agency project.

Milestones scheduled to begin or finish in the past cannot be changed unless there is a JRC approved re-baseline in which case they would be changed to reflect actual cost and schedule performance.  Any changes to previously JRC approved baselines must be approved by the JRC prior to being submitted to OMB for approval.  On the OMB Exhibit 300 report, JRC approved revisions to the previously OMB approved baseline, will be categorized as “proposed” until OMB approves them.  Once OMB approves the proposed baseline revision, subsequent updates to the OMB Exhibit 300 report will reflect the planned milestone dates and costs of the most recent/current OMB approved baseline in Table I.H.4 and remove this information from Table I.H.3.

Section I.H.4:  Actual performance and variance from OMB-approved baseline (original or current):

Question I.H.4.A:  This section is always filled in to reflect current status of the project.  It compares the OMB approved baseline and actual results for this phase, segment, or module of the project.  Show for each major project milestones or events you planned (scheduled) to accomplish and the cost and what work was actually done and the cost.  If the project is in the operational or steady-state phase complete one line on the chart for each year.  For these projects complete paragraphs C, D, F and G as appropriate.  If this is a new investment in the FY 2006 budget year, this section will be blank for your initial submission.  OMB may ask for latest information during the budget review process.

All investments (except new projects that have not previously submitted an Exhibit 300 to OMB and have no ongoing or past costs) must complete Table I.H.4, regardless of life-cycle phase.  Table I.H.4 is updated each year and projects in preliminary design, development or mixed life-cycle phases should enter cumulative actual performance information for the entire current useful segment(s).  Projects in full maintenance with no development dollars report annual actual performance against the annual base lined maintenance cost goals.

This table should reflect the useful segments/milestone dates and planned costs of the most recent JRC approved baseline that is part of the current Exhibit 300 PB and that was approved by OMB.  Proposed baselines (that have not been approved by OMB) cannot be entered in Table I.H.4.  In some cases, Section I.H may have the original JRC and OMB approved baseline in Table I.H.2, a new proposed baseline in Table I.H.3, and the latest JRC and OMB approved baseline in Table I.H.4.

At FAA, for purposes of the variance calculations, the EVM system should provide the actual costs incurred to date.  Otherwise an approved invoice is considered an actual expenditure (as opposed to waiting until the contractor actually receives the payment).  Any contractor hours must have been billed and the invoice must have been approved before they can be included in the actual costs.

EVM data, starting with question I.H.4.B below must be provided for all projects with resources allocated to DME activities.  EVM calculations must include all the costs of the non-steady-state activities for a useful segment, including FTE costs.  EVM calculations must also include the costs of the entire current non-steady-state useful segments, not just those of the contracts using EVM

All projects must provide information starting with Question I.H.4.C and continuing to the end of the section.  If questions are not applicable to an investment, state why the question is not applicable.  Steady-state projects are not required to complete the EVM calculations in I.H.4.B nor respond to Section I.H.4.E.  Also, the calculations in Sections I.H.4.B and E should not include the costs for any steady-state portions of the investment.  However responses should be provided to all the other questions in I.H.4 by including  information about the actual performance of the steady-state portion of the project and clearly identifying the steady-state information to distinguish it from the planning or development/acquisition aspects of the investment.

B. Provide the following project summary information from your EVMS data

(as of date):  This section should not be completed for the steady-state/operational portion of projects.

B.1. Show the budgeted (planned) cost of work scheduled (BCWS):

B.2. Show budgeted (planned) cost of work performed (BCWP):

B.3. Show the actual cost of work performed (ACWP):

B.4. Provide a cost curve graph plotting BCWS, BCWP and ACWP on a monthly basis from inception of this phase or segment/module through the latest report.  In addition, plot the ACWP curve to the estimated cost at completion (EAC) value, and provide the following EVMS variance analysis.

C. 	If cost and/or schedule variance are a negative 10 percent or more at the time of this report or EAC is projected to be 10 percent or more, explain the reason(s) for the variance(s).

If more than one useful segment in Table I.H.4 is shown with a 10% slippage, it should be reported in this section.  If this is due to funding cuts, this should be clearly explained, including whether additional funding will be provided in future years to eliminate or minimize the schedule variance/slippage.

- Provide performance variance.  Explain whether, based on work accomplished to date, you still expect to achieve your performance goals.  If not, explain the reasons for the variance.  For steady-state projects, in addition to a discussion on whether or not the system is meeting the program objectives, discuss whether the needs of the owners and users are still being met.

Explain whether IPT still expects to achieve performance goals in Section I.C.  If not, explain why.  Also explain, if any slippages in actual performance in relation to the Section I.C performance goals is due to funding cuts, and if goals have been risk adjusted to address the cuts and as part of a re-baseline.

For steady-state projects, in addition to a discussion on whether or not the system is meeting the program objectives, discuss whether the needs of the owners and users are still being met.

- For investments using EVMS, discuss the contractor, government, and at least the two EAC index formulas in I.H.4.B, current estimates at completion.  Explain the differences and the IPT’s selected EAC for budgeting purposes.  This paragraph is not applicable to operations/steady-state projects.

A response to I.H.4.E should only be provided for investments or parts of investments that are not steady-state.

- Discuss the corrective actions that will be taken to correct the variances, the risk associated with the actions, and how close the planned actions will bring the project to the original baseline.  Define the baseline changes, if necessary.

Corrective actions resulting from IG audits and other reviews should be included as well as any corrective actions that have been included in corrective action plans sent to OMB.  Discuss the following:

- The risks associated with the actions

- How close planned actions will bring the investment to the original baseline

- Any proposed baseline changes

Below is a sample list of corrective actions that should be considered and used (as appropriate) to answer I.H.4.F of the Exhibit 300:

- Requiring additional EVM training/certifications for IPT members and/or PMs.

- Implementing additional EVMS and other tools and processes to better monitor and manage project performance.

- Short term or long term actions that can be taken to modify contracts or issue new contracts to convert to FFP and performance based management, specifically requiring the use of ANSI 748-A compliant EVMS, and/or add incentives or penalties.

- Implementing more pro-active oversight using more frequent status reports and/or meetings to more quickly detect and respond to potential problems.

- Redefining or more clearly defining a project into smaller more manageable useful segments, each of which will be managed individually and whose success does not depend on other segments.  This information would need to be entered into Table I.H.3 as a proposed re-baseline.

- Re-baseline by revising milestones to incorporate cost and schedule risk adjustments to minimize the need for future re-baselining.  This information would need to be entered into Table I.H.3 as a proposed re-baseline.

- Adding people to increase the speed with which tasks/milestones are completed.  (This may not always work and is likely to result in cost overruns).

- Establishing clear milestones for when to determine/check if corrective actions are succeeding in mitigating the cost and schedule variances

- Identifying whether the risks/losses of not completing the project outweigh the delays and/or cost overruns.

- Determining what viable alternate solutions are available at this point if the project has to come to a halt.

- If the investment cost, schedule or performance variances are 10% or greater, has the Agency Head concurred in the need to continue the program at the new baseline?

Select “Yes” or “No” as appropriate.

# 10. Section II.A – Enterprise Architecture

(NOTE:  This section is under review and subject to change.)

## 10.1   Introduction

OMB requires that Exhibit 300s demonstrate conformance to business, data, application, and technology layers of the Federal Enterprise Architecture (FEA) and Agency EA. It requires federal agencies to map the capital investments to the federal reference models to ensure that the investments support the Federal Enterprise Architecture.

The FAA EA includes a National Airspace System (NAS) Operations section as well as an administrative section.  The NAS covers all of FAA’s operational systems whereas the administrative section covers financial, human resources and other administrative systems.  A matrix is available from the FAA EA SMEs that maps the specific FAA operations systems to the proper sections of the NAS.

## 10.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | This investment is included in the Agency EA and CPIC process. Investment is mapped to and supports the FEA and is clearly linked to the following FEA reference models: Business Reference Model (BRM), Performance Reference Model (PRM), Service Component Reference Model (SRM), and Technical Reference Model (TRM). BC demonstrates the relationship of the investment to the business, data, application, and technology layers of the EA. |
| 4 | This investment is included in the agency’s EA and CPIC process. Investment is mapped to and supports the FEA. Investment is clearly linked to the BRM but work is continuing to map the investment to the PRM, SRM, and TRM. BC is weak in demonstrating the relationship of the investment to the business, data, and application, and technology layers of the EA. |
| 3 | This investment is not included in the agency’s EA and CPIC process, was not approved by the agency EA committee, or does not link to the FEA. BC demonstrates a lack of understanding on the layers of the EA (business, data, application, and technology). |
| 2 | While the agency has an EA framework, it is not implemented in the agency and does not include this investment. |
| 1 | There is no evidence of a comprehensive EA in the agency. |

## 10.3   Guidance – Part II.A.1: Business

Question A:  Is this investment identified in your agency’s enterprise architecture?  If not, why?

Elaborate by stating how, and address the DOT as well as the FAA EA.  This answer should briefly explain the structure and relationship of the DOT and FAA EA.

Question A.1:  Will this investment be consistent with your agency’s target architecture?

One of the following responses should be selected as appropriate.

- No. This investment is currently in the operations and maintenance phase and is not scheduled to be modernized before it is retired and replaced.

- Yes. This investment is scheduled to be consistent with DOT and FAA’s “to be” modernization blueprint by aligning itself with the appropriate principle components of FAA’s Target Applications Architecture. Describe how the investment is to be consistent with the target components, and how it links to the Target Architecture as appropriate.

Question B:  Was this investment approved through the EA Review committee at your agency?

Answer “yes” or “no” as appropriate, and provide the date of the review.  If the investment has completed a NAS or Non-NAS architectural assessment, the answer to this question should be yes.  Also, if the investment has received a final investment decision by the JRC, then the answer would be ‘Yes’.  Also, if the investment has received a final investment decision by the JRC, then the answer would be ‘Yes’.

Question C:  What are the major process simplification/reengineering/design projects that are required as part of this IT investment?

Identify any major business process simplifications, business process reengineering efforts, or business design projects that will be required to reach the full business functionality of the investment.  Consider all of the major process simplifications/reengineering/ design projects that must take place in order for the investment to be in compliance with FAA’s target architecture.  The response to this question should show that the CPIC process has not focused solely on a system engineering perspective, but has taken non-IT elements of the investment into account. For example, a current business process that the investment supports may be required to change in order for the investment to function according to its identified target.  This would require the process to be reengineered or simplified in order for the investment to function properly and efficiently in the future.

Question D:	What are the major organization restructuring, training, and change management projects that are required?

Consider all of the organization restructuring, training, and change management projects that must take place for the investment to comply with FAA’s target enterprise architecture. Be specific. Examples are:

- Organization Restructuring – The investment provides new efficiencies that allow existing human resources to be deployed elsewhere. Another example is, Process X has been reengineered for greater efficiency; Organization A is being reorganized accordingly, and this investment will support the new organizational functions.

- Training – The investment requires training because of the new business processes or new technology.

- Change Management – Deployment of the investment will require a planned change management process to ensure smooth implementation across the organization.

Question E:  Please list up to three non-primary Business Reference Model (BRM) mappings to describe the functions that this IT investment supports.  A BRM mapping consists of a mapping to a Line of Business and an associated Sub-Function from the FEA BRM.  The primary BRM mapping for this initiative should have been identified with the last six digits of the unique project (investment) identifier in Section 300 Part 1 and in Section 53.8, and it should not be reentered here.  The BRM has been updated since last year.  For a list of the updated BRM Lines of Business and Sub-Functions, go to www.egov.com.  (Note: The Services for Citizens area and the Mode of Delivery area should be thought of collectively.  If you identified your primary Line of Business and Sub-Function in Section 53.8 as a Service for Citizen, at a minimum you should identify the corresponding Mode of Delivery that applies in this section).

Check the latest guidance to determine if there are additions and deletions to the FEA BRM each year. Do not map to any deleted sub-business functions.

- Ensure that there is consistency between the LOBs shown in the BRM table and the Performance Reference Model (PRM) Mission and Business results Measurement Category and Measurement Grouping fields, shown in Section I.C, Table 2.  This is especially important in relation to “transportation” versus “management of government resources” as it applies to infrastructure investments.  It is not logical for an infrastructure investment to map only to the “Transportation” LOB in the BRM and then only map to the “Information and Technology Management” Mission and Business Results area of the PRM (Section I.C, Table 2).

- Agencies should map investments to the FEA BRM based on the function of the investment, not the function of the program or mission of the agency.  FAA investments that map to the NAS are in the “Services for Citizens” business area and would map to the “Transportation” LOB, and “Air Transportation sub-function” of the BRM for their primary mapping.  However, FEA guidance no longer requires investments to identify the primary mapping in the BRM table because it is identified by the numbers in the unique project identifier (UPI) number that is shown at the beginning of the Exhibit 300.  The UPI numbers that correspond to the Transportation LOB and Air Transportation sub-function are 118 and 060.  Administrative investments are in the Management of Government Resources business are and would usually have a primary mapping to the “Human Resources Management” (#403) or “Financial Management” (#402) LOBs and the appropriate associated sub-functions.

- Mode of Delivery is no longer a primary business area in the FEA BRM.  Map the primary relationship to Services for Citizens Area, Support Delivery of Services Area, or Management of Government Resources Area. No primary mapping is allowed to Mode of Delivery.

- For a primary relationship mapped to Services for Citizens, a secondary mapping to Mode of Delivery is required.  This means that the investments mapping to the “Transportation” LOB must map to at least one Mode of Delivery LOB and sub-function in the BRM table.  FAA investments often map to the “Direct Services for Citizens” (#201) LOB and “Civilian Operations” (#068) sub-function.  However some of the other LOBs such as “Knowledge Creation and Management” (#202”) or “Regulatory Compliance” (#204) may be more appropriate for FAA investments that do not directly interface with the public as customers.

- The Information and Technology Line of Business is limited to infrastructure-related investments only.  Infrastructure investments/projects are those investments that provide communications, networking or other IT support internal to FAA and supporting other FAA systems that interface more directly with the customer.  Infrastructure investments are included in the “Management of Government Resources” business area and would therefore map to the “Information Technology Management” (#404) LOB and appropriate sub-function(s).   FAA infrastructure investments should include a mapping to the “Information and Technology Management” LOB to avoid being penalized in the scoring.

- OMB allows a maximum of three secondary (non-primary) FEA BRM mappings. Do not map to more than three secondary BRM LOBs.

- A primary LOB mapping must be identified for all investments – “100,” “200,” “300,” and “400” will not be acceptable 3 digit codes or the 18th, 19th, and 20th digits of the unique ID (UPI) number unless an agency receives prior OMB approval by their published deadline.

- A primary Sub-function mapping must be identified for ALL investments therefore, “999” will not be an acceptable 3 digit code for the 21st, 22nd, and 23rd digits of the unique ID number unless an agency receives prior OMB approval by their published deadline.

- The primary LOB and sub function mapping should be included in the UPI that is provided in response to the screening questions and not re-entered in the BRM table of Section II.A.

## 10.4   Guidance – Part II.A.3: Applications, Components and Technology

Question A:  To demonstrate how this investment aligns with the FEA Service Reference Model (SRM), list the Service Domains, Types, and Components supporting this IT investment.  Include the component description and indicate whether this is a new component (i.e. not currently identified in the SRM).  If this is a new Service component, agencies should also leave the “Component “ field blank and provide a name and description in the “Relation to SRM” field.  The SRM has been updated since last year.  For more information on the SRM go to www.egov.gov.

FAA investments that are part of the NAS map to the appropriate NAS elements in the SRM table instead of to the FEA SRM.  FAA administrative or non-NAS systems must map to the FEA SRM.

The FAA Enterprise Architecture portal application shows the links between FEA Reference Models and FAA processes, applications, data, and technology for non-NAS investments. A matrix is also available from the FAA EA SMEs that maps the NAS systems to the appropriate parts of the NAS.  Contact the FAA EA SME for access to the FAA EA portal or for mapping guidance for a specific investment.

Question C:  To demonstrate how the investment aligns with the FEA Technical Reference Model. (TRM), list the Service Areas, Categories, and Standards supporting this IT investment.  Also, the “Relation to TRM” field should be the “Relation to SRM” field, and agencies should indicate the SRM Service Component to which the TRM service standard is linked.  In additional, because the “Service Specification” layer was removed from the TRM, agencies should not provide a Service Specification mapping.  Instead, agencies should provide information on the vendor and product mapped to the Service Standard in the “Service Specification” field only for those products that have already been acquired.  For more information on the TRM, go to www.egov.gov.

If the eCPIC tool allows text in this section, elaborate on the response by stating how the investment is included in FAA TRM.  For example:

“Yes, all of the hardware, applications, components, and web technology requirements for this investment are covered in the Agency’s Technical Reference Model. The above table identifies the relevant Service Domain, Service Type, and Service Components. The standards have been reviewed by the Agency’s Chief Information Officer and Chief Architect. We have also collaborated with federal e-Gov initiative X and are adopting the use of standard based technology components.”

Use the TRM table to discuss the relationship of the investment to FEA TRM.  The first column, “Relation to SRM” should show which SRM component that is supported by the TRM item in each row of the TRM table.  It may be necessary to repeat a TRM component, if it supports more than one SRM component.   All SRM components should have a supporting TRM component and vice versa.  For those mapping to the NAS, it is recommended this column of the TRM table map to the appropriate NAS component shown on the SRM table rather than only showing “NAS” in this column.

Question D:  Will the application leverage existing components and/or applications across the Government (i.e., FirstGov, Pay.Gov etc.)?  If so, please describe.

If yes, list the current or future applications that the investment will be leveraging and describe the process for doing so.  The functionality and information available from these application catalogs can be found at http://www.FirstGov.gov, http://www.Pay.gov, and http://www.e-gov.gov.  For a list of the federal e-Gov initiatives, please visit this link: http://www.whitehouse.gov/omb/egov/downloads/e-Gov_Initiatives.pdf. If no, explain why.

Question E:  Financial Management Systems and Projects, as indicated in Part One, must be mapped to the agency’s financial management system inventory provided annually to OMB.  Please identify the system name(s) and system acronym(s) as reported in the most recent systems inventory required by Circular A-11 Section 52.4.

Coordinate with the FAA Budget Subject Matter Expert and organization to ensure consistency in which FAA investments are categorized as financial in the Section 52.4 inventory and the Exhibit 300.

# 11.  Section II.B - Security and Privacy

## 11.1   Introduction

In order to successfully address this area of the Exhibit 300, each question below must be answered at the investment (system/application) level, not at a program or agency level.  Simply referring to security plans or other documents is not an acceptable response.  For IT investments under development, security planning must proceed in parallel with the development of the system to ensure that IT security requirements and life-cycle costs for the investment are identified and validated.  All IT investments must have up-to-date security plans and be fully certified and accredited prior to becoming operational.  Anything short of a full certification and accreditation indicates that identified IT security weaknesses remain and need to be remedied and is therefore not adequate to ensure funding for the investment.  Additionally, to ensure that requests for increased IT security funding are appropriately addressed and prioritized, the agency must identify: 1) current costs; 2) current IT security performance gaps; and 3) how the funding request will close the performance gaps.  This information must be provided to OMB through the agencies’ plan of action and milestone developed for the system and tied to the IT Exhibit 300 through the unique project identifier.

Programs must ensure their FISMA review and POAM information and the Exhibit 300 are consistent and state clearly that there is adequate funding to implement corrective actions.  C&As must be completed in a timely manner and wherever possible identified in Section I.H as a planned milestone.

New initiatives that have not receive a final investment decision by the JRC should address each question by providing information about future plans to complete security activities and documentation, which regulations will be complied with, and which methodologies will be used as appropriate.  If exact dates for completion of security activities or documentation cannot be provided, an estimated date for when the information will be available should at a minimum be provided.

When planned completion dates for the activities and/or documentation described in this section are known they should be provided in this section as well as in Section I.H.

The FAA ISS Program policy is contained in FAA Order 1370.82 (intranet.faa.gov/aio), as amended. This order supersedes FAA Order 1600.54B (FAA Automated Information Systems Security Handbook).  For some of the questions in this section some “Information Systems Security (ISS) Common Language” is provided.  This is security language that is common to all FAA and can be used to answer the questions in this section.  However, the responses should not be limited to the common language, but rather they should be augmented and tailored with information specific to the investment.  The following clarifications are provided in relation to the security section to help ensure some of the information provided in the business cases is not interpreted as being too generic, incomplete, or not addressing the correct time frame.

The emphasis of section II.B is on security processes and controls that are specific to the investment/system discussed in the business case.  It is good to mention infrastructure controls/security processes (like vulnerability scans) that are done at the network/ infrastructure level, or agency-wide security controls such as annual security training.  However, the descriptions of security controls should make it clear what security controls are in place that apply to the specific system.  This is true of any general discussion of how compliance is ensured as well as the responses to specific questions about security training, incident reporting, operational testing, and contractor controls.

The questions about specific security processes and controls do not just request information about whether an activity has been completed but also whether it will be completed/planned for the future, including the budget year and/or on a periodic basis.

## 11.2   Scoring Criteria

| Score | Description |
| --- | --- |
| 5 | Security and privacy issues for the investment are addressed, all questions are answered, and a privacy impact assessment is provided in appropriate circumstances. Security/privacy detail is provided about the individual investment throughout the life-cycle to include budgeting for SE. |
| 4 | Security and privacy information for the investment is provided but there are weaknesses in the information that need to be addressed. |
| 3 | Security and privacy information for the investment is provided but fails to address the minimum requirements. |
| 2 | Security and privacy information points to an overall Agency Security Process with little or no detail at this investment level. |
| 1 | There is no security or privacy information provided for the investment. |

Since security is very important, and investments must receive a 4 in this area, programs must ensure their FISMA review and POAM information and the OMB Exhibit 300 Report information are consistent and that they make it clear that they have adequate funding to implement corrective actions and that their C&As are completed in a timely manner and wherever possible future C&A activities are identified in I.H.

## 11.3   Guidance

Question II.B.1:  How is security provided and funded for this investment (e.g., by the program office or by the CIO through the general support system/network)?

The answer to this question should focus on the organization structure in place to support security and privacy protection for an investment.  The following should be considered when preparing an answer:

- Which organization is responsible for providing security for this investment?

- Who is the Designated Approving Authority?

- Is there a system security officer assigned to this investment/project?

- Who funds the security for this investment and how?  (For example, are there any parts funded centrally?)

- If any IT interacts with other program IT systems, how is security handled between them?

Security funding should include key security personnel that are included in the IPT response in Section I.D.3.  If any special skills applicable to security and privacy were mentioned in Question I.D.3.A, describe how they are being used here.

Question II.B.1.A:  What is the total dollar amount allocated to IT security for this project in the budget year?  Please indicate whether an increase in IT security funding is requested to remediate IT security weaknesses, specifying the amount and a general description of the weaknesses.

Identify the costs (in thousands) planned by your Office for the system.  This amount should represent the % security of your budget year total identified on the cover sheet of this Exhibit, using the total dollar amount identified in the budget year (BY) column of the SoS Table.

The total dollar amount allocated for IT Security should come from the Department of Transportation IT Security Cost Estimation tool (CETIS).  The CETIS tool helps programs understand where IT security weaknesses may be found, and based on industry best practices – helps formulate a cost estimate for remediation and maintenance.  Any dollar amount reported here should also be reflected in the Section I.H milestones and costs.   Programs send a copy of the final CETIS report to DOT, so it is important that CETIS be the source of the total dollar amount.  The CETIS tool can be found in the KSN Exhibit 300 community under the Reference tab.

Costs should be provided in the thousands of dollars (label it as such), and will also be referenced in terms of total percent of a program’s budget on the cover page of the Exhibit 300.

IT security includes such costs as: security architecture development, determination of sensitivity level of information; development of risk assessments; revisions, review and testing of security plans; disaster recovery plans, continuity of support plans, and contingency plans; implementation of technical management and operational controls, including security-related hardware and software; testing of effectiveness of controls, including technical vulnerability assessments and penetration testing; development of information, security policies, security training; security program assessment; physical security if specifically for IT assets; and background checks for Federal and contract IT personnel.

For increased IT Security funding please give the dollar amount and clearly mark it as “increased IT security funding”.  You must also describe the weakness, using the same phraseology as the POA&Ms, that the increased funding is slated to address and the corrective measures for which the funding is being requested.  It is a good idea in this section to describe any additional security controls and studies that are being funded.   If there are security weaknesses - regardless of whether additional funding is being requested – a brief explanation should be provided of how the weaknesses are being addressed and/or what additional controls have been or are being implemented.  This should be consistent with responses in the risk assessment section (I.F) and the FISMA screening question.

IT security costs will cover security architecture development, determination of sensitivity level of information; development of risk assessments; revisions, review and testing of security plans; disaster recovery plans, continuity of support plans, and contingency plans; implementation of technical management and operational controls, including security-related hardware and software; testing of effectiveness of controls, including technical vulnerability assessments and penetration testing; development of information, security policies, security training; security program assessment; physical security if specifically for IT assets; and background checks for Federal and contract IT personnel.

Section II.B.2:  Please describe how the investment (system/application) meets the following security requirements of the Federal Information Security Management Act, OMB policy, and NIST guidance.

There are several policies that outline what agencies’ need to cover when coming up with IT Security and Privacy strategies.  These include the Federal Information Security Management Act (2002), the E-Government Act (2002), OMB Circular A-130 – Appendix III, and various National Institute of Standards and Technology policies (including NIST 800-65).  Links to these policies can be found at the KSN Exhibit 300 community under the Reference tab.

The response to this question should address the following types of questions:  What are the major FAA and government-wide guidelines (NIST, OMB, etc) that are being followed and what are the overall security processes implemented/planned for accreditation and certification? What are the significant security controls and processes that are implemented and/or planned now and particularly in the budget year in relation to these regulations.

Question II.B.2A:   Does the investment (system/application) have an up-to-date security plan that meets the requirements of OMB policy and NIST guidance?  What is the date of that plan?

FAA’s Subject Matter Experts on IT Security and Privacy recommend that programs use some “Information Systems Security (ISS) Common Language” to form the backbone for this question.  For this question, the ISS Common Language would be:

“The Security Plan was developed in accordance with FAA Order 1370.82, Information Systems Security Program, and the FAA ISS Handbook, which are based on NIST 800-18, Guide for Developing Security Plans for Information Technology Systems.”

Provide the date of the latest plan update.  Following the Common Language, preparers should elaborate on how these guidelines are influencing security plans.  What are the major FAA and government-wide guidelines (NIST, OMB, etc) that are being followed and what are the overall security processes implemented/planned for accreditation and certification?

OMB, FISMA, and NIST Policy require investments to address the following security issues in Security plans:

- Security Awareness Training

- Periodic Security Review/Audit

- Planning and Reporting on Remedial Action

- Incident Detection

- Configuration Management

- Continuity of Operations and Contingency Plan and Procedures

- Major System Inventories

- Senior Security Officers

- Rules of System

- Official Authorization

Parts B-F allow the preparer to elaborate on some of the topics addressed in the investment’s overall security plan.

Question II.B.2.B:  Has the investment been certified and accredited (C&A)?  Note: Certification and accreditation refers to a full C&A and does not mean interim authority to operate.  Additionally, specify the C&A methodology used (e.g., NIST guidelines) and the date of the last review.

According to NIST Pub 800-12, “Certification is a formal process for testing components or systems against a specified set of security requirements.  Certification is normally performed by an independent reviewer, rather than the system builder.”

NIST Pub 800-12 states that “System security accreditation is the formal authorization by the accrediting (management) official for system operation and an explicit acceptance of risk.”

If a C&A process were completed, the response should address the following questions:  For FAA a C&A consists of the Security Certification and Accreditation Plan (SCAP) process. When was the latest C&A/SCAP completed and when will the C&A/SCAP be updated next?  With what NIST/OMB or other guidance were these processes and documentation compliant?  What processes were/will be completed as part of the C&A/SCAP (for example risk assessment, security plan update, security testing)?  Are/will the investment’s security controls and processes implemented in a manner consistent with their security plan and SCAP?

Any program that has completed a SCAP should answer this question using the following format: (making the necessary investment-specific adjustments, where applicable):

“Yes.  The system was Certified and Authorized in accordance with FAA Order 1370.82, Information Systems Security Program, and the FAA ISS Handbook, which are based on OMB Policy and NIST guidance.

Certification was completed on <insert date> and accreditation was completed on (insert date).  FAA’s Certification and Accreditation (C&A) process is based on a risk assessment and testing of controls commensurate with the importance and sensitivity of the system.  Mitigation of weaknesses identified through the testing are centrally tracked through the Agency’s POA&M system. The results of the risk assessment and testing, as well as risk management activities, are described in the system security plan.  The system is certified by <enter name>). The accreditation is done by a management official who has the authority to accept the risks of the system and to authorize the system for operation. The signature of the DAA <insert date> constitute the authority to operate /accreditation.”

If a program is still in the planning phase, this section should describe plans for completing a full C&A prior to becoming operational and provide an approximate date for SCAP approval.

Completion of a SCAP or SCAP update should be included in the milestones tables in the Section I.H tables.

Question II.B.2.C:  Have the management, operational, and technical security controls been tested for effectiveness?  When were the most recent tests performed?

If a formal risk assessment was performed on your application/system, your answer to this question should be “yes” and the date on the final assessment document should be cited.  Describe any other types of testing that has been or will be completed, including security tests and evaluations, vulnerability scans, and penetration testing.  Briefly sum up the results of these tests.  Indicate if there are any tests planned for the near future and give the estimated date of completion.

Question II.B.2.D:  Have all system users been appropriately trained in the past year, including rules of behavior and consequences for violating the rules?

The answer to this question should start with the ISS Common Language, “Yes, every employee undergoes mandatory security awareness training annually as part of the agency security training and awareness program,” before moving onto program specific training.  Give the date(s) when user training was last provided.  If the last training session took place more than a year ago, then give the planned/scheduled date(s) for upcoming training session(s).  Should verification be needed, be certain that training documentation includes: training dates, users’ names, organization, telephone numbers, etc. and a clear indication that the rules of behavior and the consequences for violation were discussed.  Be sure to include give a brief overview on what was contained in the training and how it addressed the rules of the system.

Question II.B.2.E:  How has incident handling capability been incorporated into the system or investment, including intrusion detection monitoring and audit log reviews?  Are incidents reported to DHS’ FedCIRC?

The answer should begin by describing how incident handling in general is handled by the FAA, as specified by the ISS Common Language:

“All incidents are reported to the FAA Computer Security Incident Response Center (CSIRC),   CSIRC in turn reports incidents to the Department of Transportation, Transportation Incident Response Center (TSIRC), TSIRC reports incidents to the Federal Computer Security Incident Center (FedCirc).  This is in addition to the specific procedures followed by the system or program.”

A description of how incident handling for the specific program should follow.  If a program relies partially or totally on the central infrastructure for incident handling, then describe how staff interacts/responds when an incident occurs or how the system managers are notified of an incident the system is involved in.

Questions that should be addressed in this section include:

- To whom do the incidents/suspicious activities get reported initially and to whom do these individuals report?

- Are these procedures documented in the security plan or elsewhere?

- Are there plans to develop incident reporting procedures in the future that are specific to the investment?

- Are intrusion detection systems and audit trails used to protect the investment or are there plans to use them.  Are audit trails reviewed?

- If these controls do not exist are there plans to implement them in the future – when?

Question II.B.2.F:  Is the system operated by contractors either on-site or at a contractor facility?  If yes, does any such contract include specific security requirements required by law and policy?  How are contractor security procedures monitored, verified, and validated by the agency?

If you respond “Yes” to this question, then you should refer to the specific contract clause(s) that clearly show all of the security requirements specified by law and policy are covered.

Things to consider when answering this question are:

- Are contractor facilities inspected periodically?

- When was the last inspection?

- Are security requirements for contractors, including background investigations, security training participation, and protection of sensitive government information included in SOWs and contracts?

ISS Common Language:

“All personnel must undergo the appropriate background investigation, as specified in FAA Order 1600.1D, Personnel Security Program, prior to being granted access to the program or system.”

If this language is in the contract, please specify that it is in the contract.

In addition to the Common Language, the preparer should refer to any specific contract clause(s) that clearly show all of the security requirements specified by law and policy are covered.  The contract clauses that contain requirements for contractor security procedures are as follows:

      - Security Requirements – Classified Contracts (Jul 2002)

3.14-1/alt 1	Security Requirements – Classified Contracts Alternate I (Jul 2002)

3.14-1/alt 2	Security Requirements – Classified Contracts Alternate II (Jul 2002)

3.14-2		Contractor Personnel Suitability Requirements (Apr 2004)

3.14-3		Foreign Nationals as Contractor Employees (Jul 2002)

3.14-4		Government-Issued Keys, Identification Badges, and Vehicle Decals (Jul 2002)

3.14-5		Sensitive Unclassified Information (SUI) (Apr 2003)

Describe how the program monitors, verifies, and validates the contractor security procedures (i.e., periodic reviews, independent third party assessments, scheduled and unscheduled site visits, etc.)

Question II.B.3:  How does the Agency ensure the effective use of security controls and authentication tools to protect privacy for those systems that promote public access?

Address the policies and controls that are in place at FAA and specifically for your investment, if your investment is accessible to the public.  Identify security policies and procedures and technical security access and authentication controls used to ensure sensitive data is protected from unauthorized access.  Another thing that can be discussed here are general user rules.  If a program is not accessible to the general public, state as such.  Additional information on protecting sensitive data is found in Orders 1600.75, Protecting Sensitive Unclassified Information (SUI) and 1600.2D, Safeguarding Controls and Procedures for Classified National Security Information and Sensitive Unclassified Information.  If you have questions on these orders, contact your security servicing organization.

Question II.B.4:  How does the agency ensure that the handling of personal information is consistent with relevant government-wide and agency policies?

If the investment processes/accesses privacy data, start the response to this question by describing DOT and FAA Privacy policies and system specific controls implemented for your investment.  For a listing of government policies applicable to safe handling of personal information, see Order 1600.75, Appendices B, C and F.  For clarification on DOT or FAA security policy, contact your security servicing organization.

Also, the E-Government Act require agencies to conduct, and submit to OMB, privacy impact assessments (PIAs) for all new IT investments administering information in identifiable form collected from, or about, members of the public.  PIA’s should be updated on a regular basis and the date of the latest PIA should be included.

Do not send any PIAs directly to OMB.

The Security and Privacy SME’s have developed five different ways to discuss privacy using ISS Common Security Language.  Choose the appropriate statement from the five listed below.

Example 1

The <insert name of Operating Administration (OA)> Privacy Officer and <insert system name> subject matter experts completed an initial privacy identification, assessing whether <insert system name> requires a PIA. As an existing system with no changes that affect privacy, <insert system name> does not require a PIA.

Example 2

The <insert name of OA> Privacy Officer and <insert system name> subject matter experts completed an initial privacy identification, assessing whether <insert system name> requires a PIA. As a new system that contains public Personal Identifiable Information (PII), <insert system name> does require a PIA. OMB will receive a PIA for this system on or before the <insert year> deadline.

Example 3

The <insert name of OA> Privacy Officer and <insert system name> subject matter experts completed an initial privacy identification, assessing whether <insert system name> requires a PIA. As a new system that does not contain PII of the public, <insert system name> does not require a PIA.

Example 4

The <insert name of OA> Privacy Officer and <insert system name> subject matter experts completed an initial privacy identification, assessing whether <insert system name> requires a PIA. As an existing system that does not contain public PII, <insert system name> does not require a PIA.

Example 5

The <insert name of OA> Privacy Officer and <insert system name> subject matter experts completed an initial privacy identification, assessing whether <insert system name> requires a PIA. As an existing system that contains PII of the public, <insert system name> does require a PIA. OMB will receive a PIA for this system on or before the <insert year> deadline.

To help you determine if your investment requires a PIA or if there are any questions on the sample text above, contact the VMO to obtain the name of the PIA subject matter expert (SME).

# 12. Abbreviated Exhibit 300 Program Baseline Overview

(Note for reviewers:  The Abbreviated Exhibit 300 Program Baseline is intended to provide a consistent format for presenting the minimum information needed to make and investment baseline decision, regardless of the FAA organization to which the decision has been delegated by the JRC.   Having a standard format that is a subset of the Exhibit 300 will facilitate the investment analysis process and preparation of a full Exhibit 300 in those cases where the JRC and/or OMB may require a full Exhibit 300 for an investment that was not previously required to complete one.

The abbreviated Exhibit 300 information requirements can be tailored to address the specific needs of each investment decision organization by adding information where desired.  Please comment on any further streamlining you think is necessary or possible.

## 12.1   Introduction

For investments that are delegated by the JRC to a JRC subordinate board for approval and are not required to submit an Exhibit 300 to OMB, an abbreviated version of the baseline document is required for internal use at FAA.  The Abbreviated Exhibit 300 Program Baseline (PB) is more thorough than the Resource Planning Document (RPD).  The Abbreviated Exhibit 300 PB is a streamlined version of the Exhibit 300 that provides essential FAA investment analysis information but does not include all the information or sections required for the Full Exhibit 300.  This section outlines the differences.  Except for those areas where differences are identified, the guidance and instructions found in the previous sections will apply, although the responses may not need to contain as much detail.  All references to the Joint Resources Council (JRC) in the previous sections of the guide would be replaced by the appropriate JRC subordinate board for the investment completing the abbreviated Exhibit 300.

It should be noted that program should be ready to switch over to a full Exhibit 300 if so required by OMB for a specific investment.

## 12.2   Scoring

Abbreviated Exhibits 300 Program Baselines (PB) do not require scoring.

## 12.3   Guidance

The information provided in this section outlines the major differences between which sections are needed to complete the Full vs. the Abbreviated Exhibit 300.  Also remember that less detail will normally be expected for an investment completing an Abbreviated Exhibit 300.  This is especially true for investments in the planning phases.  Less detailed information will be expected for those investments that are in the planning phase and have not completed all the investment analyses processes needed to finalize the Abbreviated Exhibit 300.

### 12.3.1    Screening Questions

Only the following Screening questions must be answered for Abbreviated Exhibits 300 PB:

- Name of Investment (Project)

- Investment Initiation Date

- Investment Planned Completion Date

- This Investment is: Initial Concept, Planning, Full Acquisition, Steady-state, Mixed Lifecycle

- Did the Project (Investment) Manager identified in Section I.D. review this exhibit?

- Is this investment included in your Agency’s annual performance plan or multiple annual performance plans?

- Is this investment IT?

In addition to the SoS table, the abbreviated Exhibit 300 PB includes the table below to show the costs of only the phase or segments for which JRC baseline funding approval is being sought.

| F&E | First FY | FY+1 | FY+2 | FY+3 | FY+4 | Total EAC |
| --- | --- | --- | --- | --- | --- | --- |
| Baseline requested for funding |  |  |  |  |  |  |
| OPS |  |  |  |  |  |  |
| Baseline requested for funding |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |
| Baseline requested for funding |  |  |  |  |  |  |

Table 7: Standard format for financial information (Then-Year $$)

This table, along with the other investment analysis and decision documentation can be found in the JRC briefing template in the JRC guidance in the FAST web page.

### 12.3.2    Section I.A – Description

A response is not required for Section I.A.3, Supporting Documentation.

### 12.3.3    Section I.B – Justification

A response is not required for Section I.B.7, Multi Agency Initiative.

### 12.3.4    Section I.C – Performance Goals and Measures

Only Table 2 must be completed.  Table 1 is not required regardless of when the investment was initiated.

### 12.3.5   Section I.D – Program Management

Responses must be provided to all of the Exhibit 300 questions in Section I.D.

### 12.3.6   Section I.E – Alternatives Analysis

Responses must be provided to all of the Exhibit 300 PB questions in Section I.E

### 12.3.7.   Section I.F – Risk Inventory and Assessment

The Abbreviated Exhibit 300 should focus on the schedule, cost, technical, security/privacy, and strategic risk areas.  This section should also address any other risk that is not included in those risk areas but is rated as being High and is applicable and specific to an investment.

### 12.3.8   Section I.G – Acquisition Strategy

Responses must be provided only for the following sections:

- Question I.G.1:   Will you use a single contract or several contracts to accomplish this investment?

- Question I.G.1.A:   What type of contract/task order if a single contract is used?

- Question I.G.1.B:   If multiple contract/task orders will be used, discuss the type, how they relate to each other to reach investment outcomes, and how much each contributes to the achievement of the investment cost, schedule and performance goals.  Also discuss the contract/task order solicitation or contract provisions that allow the contractor to provide innovative, transformational solutions.

- Question I.G.2:   For other than firm-fixed price, performance-based contracts, define the risk not sufficiently mitigated in the risk mitigation plan, for that contract/task order, that requires Government to assume the risk of contract achievement of cost, schedule and performance goals.  Explain the amount of the risk the government will assume.

- Question I.G.4:   Discuss the competition process used for each contract/task order, including the use of RFP’s, schedules or other multiple agency contracts, etc.

- Question I.G.5:   Will you use commercially available commercial off-the-shelf (COTS) products for this investment?

- Question I.G.5.A:   To what extent will these items be modified to meet the unique requirements of this investment?

- Question I.G.7:   How will you ensure Section 508 compliance?

### 12.3.9   Section I.H – Project (Investment) and Funding Plan

Responses must be provided to all parts of this section.  However the response need not include information about Earned Value Management (EVM) assessments, their results, and the status or recommended actions, if this type of assessment has not been completed for the specific investment.

### 12.3.10   Section II.A – Enterprise Architecture (EA)

Responses must be provided only to the questions in Section II.A.1, Business.

### 12.3.11   Security and Privacy (Required for IT Investments Only)

Responses must be provided only for the following Sections:

Question II.B.1:   How is security provided and funded for this investment (e.g., at the program office level or by the CIO through a general support system/network)?

Question II.B.1.A: What is the total dollar amount allocated to IT security for this project in the budget year?  Please indicate whether an increase in IT security funding is requested to remediate IT security weaknesses, specifying the amount and a general description of the weaknesses.

Section II.B.2:   Please describe how the investment (system/application) meets the following security requirements of the Federal Information Security Management Act, OMB policy, and NIST guidance

Question II.B.2A:   Does the investment (system/application) have an up-to-date security plan that meets the requirements of OMB policy and NIST guidance?  What is the date of that plan?

Question II.B.2.B:   Has the investment been certified and accredited (C&A)?

Note: Certification and accreditation refers to a full C&A and does not mean interim authority to operate.  Additionally, specify the C&A methodology used (e.g., NIST guidelines) and the date of the last review.  C&As are to be performed prior to the system becoming operational.  If the system(s) described in the business case are in the initial concept, planning, or development phase, the agency needs to state that a C&A will be conducted prior to the system becoming operational.  Please include the planned date for any system not yet operational.  FAA uses the Security Certification and Accreditation Plan (SCAP) process for C&A.  Refer to this section for the full Exhibit 300 for more information on the C&A and SCAP.

Question II.B.2.C:   Have the management, operational, and technical security controls been tested for effectiveness?  When were the most recent tests performed?

Question II.B.4.  How does the agency ensure that the handling of personal information is consistent with relevant government-wide and agency policies?

Note:	The response to this question needs to focus primarily on the information about the PIA, for which instructions are included in Section 11.3 of this guide.

# APPENDIX A - CROSSWALK OF THE EXHIBIT 300 SECTIONS

Screening Questions

Please note that several of these questions need to be cross checked with other sections of the business case.

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | Unique Project Identifier (UPI) | Guidance for this number is found in OMB Circular A-11 Exhibit 53. The number includes the primary BRM mapping information from section II.A of the Exhibit 300. The UPI shown for this project/investment on the Exhibit 300 should be consistent with the UPI shown in the Exhibit 53 and in the Plan of Action and Milestone (POAM), if there is a POAM for this project. |
|  | Investment Initiation Date and Planned Completion Date | These dates should reflect the life of the project/investment, from its conceptual/initiation phases up to its disposal and/or replacement by another system. The duration should be consistent with the duration of costs shown in the spending summary. |
|  | System Phase (Initial concept, planning, full acquisition, steady-state, mixed lifecycle) | The phase of the investment during the budget year should be indicated. If the investment reflects costs for more than one phase or will be transitioning phases, “mixed” would normally be the most accurate response. Make sure that the phase selected correctly reflects the costs and milestones shown in the spending summary and section I.H. For example, if the spending summary and/or section I.H show costs in either planning or acquisition, as well as maintenance, the phase should be defined as mixed, not steady-state. |
|  | Security Percentage | Make sure that the same security costs have been included in the spending summary, section I.H, and section II.B. Zero percent is normally not an acceptable answer. If other organizations are paying for large parts of the security for this project, this should be explained in section II.B. |
|  | Does this investment support homeland security? | This is determined both by whether the department of homeland security is a user of the project/system and the mission supported by the investment itself. If you check off yes for any of the Homeland Security items, use section IA.3 (supporting information) to elaborate. |
|  | c. Was a Privacy Impact Assessment (PIA) submitted via PIA@omb.eop.gov | The information provided in this section should be consistent with the information provided in section II.B. |
|  | d. Was this investment reviewed as part of the Federal Information Security Management Act (FISMA) review process? d.1 If yes, were any weaknesses found? d.2 Have the weaknesses been incorporated into the agency’s corrective action plans? | The answers in this section should be consistent with information provided in section I.F and II.B in terms of the security risk level of the system and the status of FISMA weaknesses. If weaknesses were found but not included in the POAM, this should be explained in section II.B. If a system has undergone certification and/or has had a NIST 800-26 self-assessment performed, then the answer is yes. Weaknesses found during the certification process and/or the self-assessment must be identified in a Plan of Action and Milestone for that system and if so, then you can say yes, they have been incorporated into the Agency's corrective action plan. |
|  | Has this investment been identified as a national critical operation or asset by a Project Matrix review or other agency determination? E.1. If no, is this an agency mission critical or essential service, system operation, or asset other than those identified as above as national infrastructures. | Review of the list of Ex 300 programs by AIS indicates the following: - CAS is considered essential - ASCM, ASKME, SWIFT and SASO are non-critical (Note: In fiscal year 2005, ASCM, ASKME, and SWIFT were not required to submit Exhibits 300 to OMB for Budget Year 2007.) - the remaining programs are considered mission critical |
|  | Was this investment included in a Performance Assessment Rating Tool (PART) Review? Does the investment address a weakness found during the PART review? | All projects with F&E funding should answer YES in section I (f.) If a PART review was completed but no weaknesses were identified that pertained to the specific investment, then the answer to I.(f1) should be yes but section I.A.2 should clearly explain that there were no weaknesses nor action items that pertained to the investment. AVR projects should answer YES in section I (f) and I (f1). |
|  | Spending Summary | The spending summary reflects the total lifecycle costs of the project. The spending summary costs should be consistent with the costs shown in Section I.H for the duration of the useful segment. Summary costs should also be consistent with the chosen alternative in section I.E (for the years covered by the alternative analysis). Differences, such as CIP changes reflected in the Summary of Spending should be explained in Sections I.E and II.H as appropriate. FAA shows Government FTE costs in a separate line at the bottom of the chart (Planning / Acquisition / O&M Phase costs at the moment do not include FTE costs). If there is spending in two or more phases (Planning / Acquisition / O&M), the answer to the screening question “This investment is” would normally be mixed lifecycle. |

President’s Management Agenda (PMA)

| Section | Topic | What to check |
| --- | --- | --- |
| I.A.1 | Investment Description | The description of the investment should state what it does and its purpose. The “what” should include the scope, functionality, data captured and the purposes and use of that data in program operations, components (such as software, hardware, databases, etc.), user community and interfaces. The description should make it explicitly clear which specific system components are being funded (requested), and the scope of any upgrade or modernization components. The “purpose” part should include a brief description of the performance gap or business need and major function of the investment, including any legal requirements/regulations satisfied by the investment, the investment’s objectives, and why this investment is (still) the best way to achieve the business requirements. The discussion of the why this investment is still the best way to achieve the business requirements and benefits expected from it should reflect the chosen alternative in section I.E. |
| I.A.3 | Provide supporting information derived from research | This should reflect research, interviews and other documentation about the chosen alternative in section I.E. In this section, an agency can provide links or the titles and dates of supporting studies and other documents. Each website or document reference, however, should include a brief description of the kind of information that is provided by the web site or document that relates to the investment, as well as how that information supports the business case. Documents should not be attached to the 300. |
| I.B.1 | Investment support of agency’s mission and strategic goals | Include and ensure consistency with the information and major benefits that are measured in section I.C, and are consistent with benefits discussed in section I.E in relation to the chosen alternative. |
| I.B.3 | Alternative sources | If there are alternative sources, they should be included in the Alternatives Analysis section I.E. If the private sector/contractors are currently being used as part of the solution, this should be mentioned. |
| I.B.7 | Multi-agency initiative | This is not just about funding from different agencies, but if there is funding, this should be reflected in section I.H. as milestones each agency is responsible for. Plans for partnering in the future should also be discussed where applicable. It would strengthen the business case if the different agencies were reflected in the Integration Project Team in section I.D. |
| I.B.8. | How will this investment reduce costs or improve efficiencies | These benefits should be the same things (only addressed in less detail) that are measured in section I.C. AND analyzed in section I.E. There may be a number of clear benefits, which have either not yet been measured or that may be considered “intangible” benefits that are not listed in I.C but should be mentioned in I.B.1. If such benefits are listed, they should be specific and concrete examples or an explanation. For example, if the investment somehow contributes the improvement in the agency’s image, the response should explain exactly how. |

Performance Goals, Section I.C

| Section | Topic | What to check |
| --- | --- | --- |
| I.B.1 | Justification – Support of Agency’s mission and strategic goals | Is the mapping described in this section and the information shown in Section I.C, Table 1 and/or 2 consistent with the discussion on support of the agency’s mission and strategic goals that is provided in section I.B.1? |
| 1.B.8 | Justification – Reduction in costs/or improvement in efficiency | Are the planned performance improvements identified in section I.C consistent with the benefits described in sections I.B.8? If there are additional benefits (maybe intangible) described in section I.B for which there are no performance goals and measures in section I. C, is an explanation provided? |
| I.E | Alternatives Analysis | Are the planned Performance improvements identified in section I.C consistent with the benefits described in section I.E? |
| II.A | Enterprise Architecture | Are the measurement areas in Table 2 consistent with the Business Reference Model information in section II.A? |

Project Management – Section I.D

The project management area does not get scored just based on the questions in Section I. D.  It is important to show an overall understanding of the business case and consistency with other sections, especially sections dealing with project costs, risks, and performance.

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | System Phase (Initial concept, planning, full acquisition, steady-state, mixed lifecycle) | The phase identified in Part I should correctly reflects the costs and milestones shown in the spending summary and section I.H. For example, if the spending summary and/or section I.H show costs in either planning or acquisition, as well as maintenance, the phase should be defined as mixed, not steady-state. |
|  | Security Percentage | Make sure that the same security costs have been included in the spending summary, section I.H, and section II.B. Zero percent is not an acceptable answer. |
|  | Spending Summary | The spending summary costs should be consistent with the costs shown in Section I.H for the duration of the useful segment. The spending summary reflects the total lifecycle costs of the project. Section I.H covers the current useful segment and/or phase. Differences should be explained. |
| Part I.B.8 | Justification | This section should demonstrate an understanding of the whole business case by showing consistency with other sections of the investment, especially in terms of the performance gap, expected benefits, and alternatives. |
| Part I.C. | Performance Goals and Measures | Demonstrate linkage with the descriptions of expected improvements/benefits in section I.B (justification), with planned / expected improvements in section I.C (Performance Goals) and I.E (Alternatives Analysis). The business case should also show consistency and linkage among sections I.C, I.H and I.G, in that the contracts that are being tracked for schedule and cost are also being tracked for the quality of their deliverables (as specified by performance goals in I.C). |
| Part I.E | Alternatives Analysis | The lifecycle costs included in section E of the alternatives analysis (AA) should be consistent with the costs shown in the spending summary. (The costs should reflect the same lifecycle phases for the period covered by the AA for the selected alternatives. Differences should be explained) Benefits discussed in I.E should be consistent with the benefits (performance improvement goals, cost savings and avoidances, etc) discussed in I.B and I.C. |
| I.F | Risk Inventory and Assessment | The risk table must be completely filled out and kept up to date. The costs shown in the spending summary, alternative analysis and Section I.H have been risk adjusted. The risk levels shown are consistent with the schedule, cost, and security performance/status and other information in the business case. |
| I.G | Acquisition Strategy | Contracts should have an EVMS clause requiring the contractor to implement a program management system that meets the criteria in ANSI/EIA Standard 748-A. EVMS is required for all contracts for DME efforts, including tests and prototypes that may be part of the planning phase and upgrades/modifications to an operational/steady-state system. OMB wants to see consistency and a connection between sections I.C, I.H and I.G, in that the contracts that are being tracked for schedule and cost are also being tracked for the quality of their deliverables (as specified by performance goals in I.C). |
| I.H. | Project and Funding Plan | IPT skills and training are discussed in section I.D. Section I.H should address the project management and governance processes being used by the project managers, and IPT to mange project cost, schedule and performance goals. The roles of the IPT in these processes should be described in section I.H. |
| II.A | Enterprise Architecture (EA) | Information in this section should indicate the project is consistent with the agency's EA and there is a process to help ensure that consistency. Information should also demonstrate and understanding of the business missions being supported by the investment, as well as the technology supporting it. The information about the system should be consistent with section II.B as well as the system description in I.A, and the performance goals in I.C. |
| II.B | Security | Security cost and status information should be consistent with the screening questions, spending summary, the project and funding plan (I.H), and the risk assessment (I.F). Security should be represented in the IPT. |

Alternatives Analysis, Lifecycle Costs Formulation, and related sections.

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | Spending Summary | The costs in the Alternatives Analysis should be consistent with the costs in the Summary of Spending for the time period of the alternatives analysis. The Summary of Spending table represents the total investment cost for the full estimated lifecycle of the selected alternative. Consequently, the summary of spending will include all the projects past costs as well as its present and future ones, whereas an alternatives analysis will normally address the remaining life of the project (not including sunk costs) from the time of the latest alternatives analysis update or completion. |
| I.B I.C I.H | Justification Performance Goals and Measures Project and Funding Plan | Describe alternatives considered keeping in context of agency strategic goals, closing performance gap, providing a service, or performing a function, rather than how to build to a technical specification in different way. Provide comparison of returns for each alternative and demonstrate thoroughness, using well-grounded, consistent estimates for the ROIs. Do not cite benefits in I.E. that are not mentioned in sections I.B and I.C. For steady-state, especially legacy systems, where an e-Gov strategy review is needed, planned or underway, sections I.B, I.E, and I.H should address e-Gov strategy issues consistently and in relation to the specific sections. For examples in relation to explaining whether the project still meets the agency and PMA goals addressed in section I.B, whether updates to the alternatives analysis (section I.E) are or will address e-Gov strategy issues, and whether post-implementation reviews and other operational analysis processes take into account e-Gov strategy issues. |

Risk Management I.F

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | Spending Summary | The costs shown in the spending summary should be risk adjusted. |
| I.H. | Project and Funding Plan | Must have a plan, with milestones and completion dates, to eliminate, mitigate, or manage the risks. Section I.H should clearly state if and how the milestones shown in the section I.H tables have been adjusted to address the project’s schedule, cost and performance risks, as well as risk mitigation actions. If there are significant risk mitigation actions, section I.H should either show these as separate milestones or describe if they have been included as part of other project milestones. |
| II.B | Security | Section I.F descriptions and probability levels for security related risks (such as 17 and 18) should be consistent with the findings in FISMA assessments, other security assessments and tests, and with the information in section II.B. If certifications and accreditations have not been completed on operational systems and/or many of the controls mentioned in section II.B are not in place, a basic security risk rating may not be justified. |

Acquisition Strategy, Section I.G.

| Section | Topic | What to check |
| --- | --- | --- |
| I.C and I.H | Performance Goals and Project and Funding Plan | Performance-based acquisition management means you have a documented, systematic process for program management, which includes: Integrating program scope, schedule and cost objectives; Establishing a baseline plan for accomplishment of program objectives; and Using earned value techniques for performance measurement during execution of the program. This means that your contracts are integrally tied to your performance, including: cost/schedule performance reported in section I.H. and; technical/project performance reported in section I.C. The information on expected performance provided in section I.C and the types of contracts that are used and their relationship should be consistent with the EVM information provided in Section I.H. |

Performance Based Management and Lifecycle Costs Formulation, Section I.H. and Related Sections

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | Spending Summary | The spending summary reflects the total lifecycle costs of the project. The spending summary costs should be consistent with the costs shown in Section I.H for the duration of the useful segment. The phases covered in I.H for the duration of the segments depicted in the tables should be consistent with the phases in the summary of spending for the same duration. Cost differences due to CIP or other funding changes should be explained. FAA shows Government FTE costs in a separate line at the bottom of the chart (Planning/Acquisition/O&M Phase costs at the moment do not include FTE costs). FTE costs however should be shown at least as a separate line for each useful segment in the Section I.H tables. |
|  | System Phase (Initial concept, planning, full acquisition, steady-state, mixed lifecycle) | The phase selected should correctly reflect the costs and milestones shown in the spending summary and section I.H. For example, if the spending summary and/or section I.H show costs in either planning or acquisition, as well as maintenance, the phase should be defined as mixed, not steady-state. |
|  | Security Percentage | Make sure that the same security costs have been included in the spending summary, section I.H, and section II.B. |
| Part I.B.7 | Justification | If this is a multi-agency initiative and other agencies/ organizations are paying for part of this investment, these agencies should be identified in the funding agency column of the tables in section I.H. |
| Part I.C | Performance Goals and Measures | Ensure section I.H.1 describes how these measures will be tracked by the operational analysis system and any other management processes. OMB wants to see consistency and a connection between sections I.C, I.H and I.G, in that the contracts that are being tracked for schedule and cost are also being tracked for the quality of their deliverables (as specified by performance goals in I.C). |
| I.D.3.a | Project Management/ Skill Set | Section I.H should address the project management as well as governance processes being used by the project managers and IPT to mange project cost, schedule and performance goals. The roles of the IPT in these processes should be described in section I.H. |
| Part I.E | Alternatives Analysis (AA) | The costs shown in section I.E should encompass the whole life of the project (not including sunk costs – except in cases where they are still relevant to that phase/useful segment because the AA does not yet need to be updated) and be consistent with the costs covering the same time span in the spending summary and well as the useful segment of section I.H. The alternative costs should include all the risk adjustments and risk mitigation strategies that are included in the spending summary and section I.H. If section I.H.3 is used to re-baseline a useful segment/phase of a project, the AA cost information should be updated to reflect the new cost and milestone information, but may not need to be completely redone. If the AA is out of date, a new one must be completed regardless of whether section I.H has been re-baselined. |
| Part I.F | Risk Inventory and Assessment | Section I.H costs and dates must incorporate risk adjustments and the risk reserve. The cost of risk mitigation actions identified in section I.F (including security risk mitigation actions identified in more detail in the POAM) should be included in the mitigation costs and milestones described in section I.H. |
| Part I.G | Acquisition Strategy | Contracts should have an EVMS clause requiring the contractor to implement a program management system that meets the criteria in ANSI/EIA Standard 748. This includes all contract types including firm fixed price (except for contracts when there is no DME or integration work). Contracts need to specify schedule and performance goals. EVMS is required for all contracts for DME efforts, including tests and prototypes that may be part of the planning phase and upgrades/modifications to an operational/steady-state system. Section I.G, I.H.1 and I.H.4 need to clearly and consistently identify what portion of the contracts and which milestones are covered by EVM. OMB wants to see consistency and a connection between sections I.C, I.H, and I.G, in that the contracts that are being tracked for schedule and cost are also being tracked for the quality of their deliverables (as specified by performance goals in I.C). Section I.H.1 should clearly explain what portion of the project costs shown in section I.H use EVM and which do not. It should also clearly explain which of the milestones shown in section I.H are ones belonging to EVM contracts and being tracked using EVM in section I.4. Section I.H.1 should also explain how those contracts that do not use EVMS are being managed and how project performance is being tracked for those portions of the project. |
| II.A.1C | Was this investment approved through the EA review committee at your agency? | If reviews by the EA committee are mentioned as part of the investment governance process in section I.H, the information should be consistent with that provided in this section of the Exhibit 300. If an operational analysis or e-Gov strategy review is being conducted on an existing operational system, it should address adherence to the agency’s EA. |
| II.A.3.C | Technical Reference Model | Costs attributable to technology described in the TRM that supports this project should be included in the costs that are reflected in section I.H and the spending summary. |
| II.B.1 | Security Costs | If there is a security milestone identified in the tables in I.H, then make sure the $$ are consistent with the security % and the security $$ mentioned II.B.1.A. Significant security actions/activities should be clearly included security as independent milestones or as part of the description of other milestones. It is important to show that C&A and other security actions are being scheduled, budgeted for, and completed. |

Enterprise Architecture II.A

| Section | Topic | What to check |
| --- | --- | --- |
| Part I screening questions | Unique Project Identifier (UPI) | The number includes the primary BRM mapping information from section II.A of the Exhibit 300, if the BRM for that Exhibit 300 still includes the primary BRM mapping , which is no longer required. |
| I.C | Performance Goals | The measurement area in Table 2 of Section I.C should be consistent with the business areas described in the BRM. |
| I.H | Project and Funding Plan | The Operational Analysis and e-Gov strategy reviews discussed in section I.H for existing operational systems should address compliance with the EA and modernization blueprint. |
| II.B | Security | The security aspects/controls pertinent to this project/investment should be reflected in the Service Reference Model (SRM) and the Technical Reference Model (TRM) information and mappings provided in section II.A (See Security section for an example.). |

Security, Section II.B

| Section | Topic | What to check |
| --- | --- | --- |
| Part I Screening Questions | d. Was this part of a FY03 FISMA review? d1: Were weaknesses identified? d2: Have the weaknesses been incorporated into the agency’s corrective action plan? | Make sure that these are consistent answers with II.B.1.A – that is, if you say there are weaknesses up front, there should be weaknesses discussed here. The discussion of weaknesses in section II.B does not have to be detailed but it should be consistent with the information in the POAM. |
| Part I Screening Questions | Security Percentage | Make sure that these are consistent answers with II.B.1.A ($$ vs. %). |
| Part I.B | Justification | If the security benefits in terms of satisfying a security performance gap are significant they need to be consistently addressed in sections I.B (justification), I.C (performance goals), and I.E. (alternatives and cost benefit analysis). However, security activities such as the completion of security plans or C&As should normally be included in section I.H milestones. |
| Part I.C | Performance Goals and Measures | If the security benefits in terms of satisfying a security performance gap are significant they need to be consistently addressed in sections I.B (justification), I.C (performance goals) and I.E (alternatives and cost benefit analysis). However, security activities such as the completion of security plans or C&As should normally be included in section I.H milestones. |
| I.D.3.a | Project management/ skill set | This section must include a statement about security skills being part of the project team. If the IPT does not currently include individuals with security skills, the planned date for including such individuals should be provided. Example: “Other functional areas, such as quality assurance and information security, are readily available and accessible from within the Terminal Business Unit. These areas are called in to advise and consult on specific issues as they arise. In so doing, we are able to manage the program effectively and efficiently while save the cost of dedicated functional support that we may not need full-time.” |
| Part I.E | Alternatives Analysis | If security considerations are a significant part of your criteria for selecting an alternative, this should be mentioned in the business case. The security benefits of one alternative may outweigh its higher costs. If the security benefits are significant, they need to be consistently addressed in sections I.B (justification), I.C (performance goals) and I.E (alternatives and cost benefit analysis). |
| Part I.F Risk Table | Risk #17-Security Risk #18-Privacy | # 17. The level of risk indicated in the table must be consistent with the weaknesses described in section II.B.1.A. The current status column for this risk (milestones remaining to mitigate the risk) should be consistent with the description of security activities in II.B.2 (especially II.B.2.A,B and C – results of FISMA review, risk assessments, and security tests or the need to complete security plan and C&A activities). #18. The level of risk and its description should be consistent with findings of the PIA if one was conducted and with the screening question, section II.A.2.F and section II.B, especially II.B.3, II.B.4, and II.B.5. |
| Part I.G | Acquisition Strategy | Contracts used for security support should be mentioned and their relationship to other contracts should be described. For example, the contractor responsible for providing security risk assessment and security test and evaluation support should be independent of the contractor providing development or operational support. |
| Part I.H. | Cost and Schedule Goals | If there is a security milestone identified in the table, then make sure the $$ are consistent with the security % and the security $$ mentioned II.B.1.A. Security milestones should include security activities either as independent milestones or as part of the description. It is important to show that C&A and other security actions are being scheduled and budgeted for. |
| II.A.3.A | Service Reference Model | The project should address its relationship to the security portion of the service component reference model. Example: Relation to SRM (Component Description): Air Navigation Services: (6) Infrastructure-Information Management. Support subsystem requires identification and authorization for users to access the system. Service: Support Services Service Type: Security Management Service Component: Identification and Authentication |
| II.A.3.C | Technical Reference Model | The project should address their relationship to the security aspects of the TRM. Examples: Relation to SRM (SRM service component): NAS OR Identification and Authentication Service Area/Area Name: Component Framework Service Category: Security Service Standard: Certificates/Digital Signature Product Name: Provide Name of the specific product being used Vendor Name: Provide the name of the Vendor Relation to SRM (SRM service component): NAS or Intrusion Detection Service Area/Area Name: Component Framework Service Category/Category Name: Security Service Standard/ Standard Name: Supporting Security Services Product Name: Network Virus Scan Vendor: Provide the name of the vendor. |

# APPENDIX B – USEFUL WEB LOCATIONS

FAA’s Exhibit 300 portal - https://nase.amc.faa.gov

FAA Acquisition Management System FAST URL - http://fast.faa.gov/index.htm

FAA Contract Writing Toolbox URL -   http://204.108.10.60/conwrite/

FAA Policies, Regulations, and Guidelines -   http://www.faa.gov/regulations/

FAA Flight Plan - http://www.faa.gov/AboutFAA/Plans.cfm

DOT Strategic Plan -  http://www.dot.state.tx.us/insdtdot/geninfo.htm?pg=stratplan

DOT Publications -  http://www.dot.state.tx.us/business/manuals_publications.htm

DOT Departmental Information Resource Management Manual (DIRMM -   http://cio.ost.dot.gov/policy/dirmm.html

DOT Capital Planning and Investment Control Guidelines - http://cio.ost.dot.gov/capital_programming/index.html

Department of Homeland Security (DHS) Strategic Plan -   http://www.dhs.gov/dhspublic/theme_home1.jsp

OMB URLs important for Capital Planning processes and documentation:

- OMB Circular A-11, Section 300, Planning, Budgeting, acquisition, and management of Capital Assets, The most recent official and final version of the Exhibit 300 reporting instructions and format document are on OMB’s website.  Section 300 includes OMB’s 5-Point Scoring Criteria for IT Investments (also used by FAA):  OMB Circulars are located on OMB’s website at: http://www.whitehouse.gov/omb/circulars/index.html.  Please note again that scoring is based on OMB’s perception of the strength of the IT project management, rather than simply the writing of the Exhibit 300.

- OMB Circular A-11, Section 53, Information Technology and E-Government.  This section or exhibit shows all of an agency’s IT and e-Gov spending, and lists major as well as non-major projects individually and using a unique project identifier (UPI).  This section of Circular A-11 is also found at:  http://www.whitehouse.gov/omb/circulars/index.html.

- OMB Circular A-94: Guidelines and Discount Rates for Benefit-Cost Analysis of Federal Programs:  This circular provides general guidance for conducting benefit-cost and cost-effectiveness analyses. It also provides specific guidance on the discount rates to be used in evaluating Federal programs whose benefits and costs are distributed over time. Located on OMB’s website: 
http://www.whitehouse.gov/omb/circulars/a094/a094.html#1

- The OMB Circular A-11, Part 7, Capital Programming Guide:  The document’s purpose is to provide guidance for a disciplined capital programming process for capital assets.  Located on OMB’s website: http://www.whitehouse.gov/omb/circulars/a11/cpgtoc.html

- Implementing the President’s Management Agenda for E-Government:  This document describes the E-Government achievements since February 2002, the challenges facing E-Government leaders in 2003 and 2004, and the strategy to address these challenges. Located on OMB’s website: http://www.whitehouse.gov/omb/egov/2003egov_strat.pdf

- The President’s Management Agenda is located at:  http://www.whitehouse.gov/omb/budget/fy2002/mgmt.pdf.

- The FEA reference models can be found on www.egov.gov, This URL includes the PRM with detailed guidance about how to incorporate PRM Indicators into the performance goals and measures in Table 2 of the Exhibit 300 and on how to incorporate the PRM into agencies’ performance goals and measures.

- The Federal Architecture Management System (FEAMS) is a web-based management system designed to provide agencies with access to initiatives aligned to the FEA and the associated reference models.  FEAMS should be checked to help identify other government initiatives that might be alternatives to addressing a performance gap.   FEAMS is located on:  https://www.feams.gov

- Information on EVMS is available at http://www.acq.osd.mil/pm.

# APPENDIX C - E-GOV STRATEGY REVIEW SAMPLE

Government agencies are using technology to enhance the access to and the delivery of government services for the benefit of citizens, business partners and employees. To achieve these overall goals an adequate E-Government Strategy has to be developed which will determine the success or failure of the ensuing E-Government Projects. E-Government is not only about technology but impacts every aspect of an organization involved.

The purpose of an E-Government Strategy at the Agency or organization-wide level is to foster the use of information technology aimed at helping people make better- decisions and enhancing their ability to achieve the Agency’s mission.  The Agency/organization E-Government Strategy will follow Agency-wide guidance and further augment this effort through specific E-Government Strategies and Initiatives.

As an enterprise pursues a commitment to e-business, it must include all the IT and business process re-engineering implications or it will not meet performance expectations for fulfillment and service.

Agency senior business management and IT governance must ensure that the business and IT operate from a common strategy, with common short- and long-term objectives. In particular, enterprises must synchronize the development of the Web-based and incumbent IT infrastructure with the business commitment to an e-business strategy.

To develop an effective agency/organization-wide e-Government Strategy a review process should be implemented that addresses agency-wide issues as well as individual investments.

The development of an agency E-Government strategy or approach refocuses attention on:  how to collaborate more effectively across agencies to address complex, shared problems; how to enhance customer focus; and how to build relationships with private sector partners.

The mission and objectives of an agency’s E-Government Strategy should include:

- Simplifying delivery of services to citizens,

- Minimizing the burden to the public,

- Collecting information only once and reusing it,

- Simplifying business processes, and

- Utilizing information technologies to reduce costs through integrating and eliminating redundant systems.

The development and implementation of an agency-wide E-Government strategy normally should involve the following activities.

E-GOVERNMENT FRAMEWORK

An organization’s E-Government strategy needs to allow the organization to implement an E-Government Framework that allows it to make progress in the following four areas simultaneously and in an integrated manner.

  - Customer Relationship Management

  - Organizational Capability

  - Enterprise Architecture

  - Security & Privacy

  - E-Government Strategy Activities

The following activities are part of the e-Government strategy development and review processes.

    - Develop awareness of E-Government within the organization, with citizens, business partners, customers, and employees and an understanding of the services E-Government can provide.  This includes reviewing agency processes and systems to identify opportunities for:

    - Partnering with other federal, state, and local agencies and many of our stakeholders.

    - Harnessing the power and capacity of new information technologies.

    - Providing secure, reliable access to scientifically-sound data and information.

    - Integrating data that pertains to the same topic, facility, place, or resource.

- Gain the support of the Agency/organization executive management in the development and subsequent implementation of E-Government strategy and review processes within the Agency/organization.

- Identify and incorporate best practices in the public and private sector for similar IT organizations.

- Conduct interviews of the appropriate senior management and project managers in the organization to gather their vision for the implementation and development of an E-Government framework within their organization.

- Build upon the Government Paperwork Elimination Act (GPEA) which serves as an official driver to ensure that E-Government continues to evolve, provides specific technology options that must be explored, and establishes guidelines to develop fully electronic transactions.

- Follow OMB’s Federal E-Government and ensure the overall goals of the President’s “Expanding E-Government Initiatives”, listed below, are incorporated into the Agency/organization E-Government Strategy.

  - Make it easy for citizens to obtain service and interact with the Federal Government;

  - Improve government efficiency and effectiveness; and

  - Improve government’s responsiveness to citizens.

- The Federal E-Government Strategy identifies 24 Presidential Priority Initiatives (PPIs) designed to significantly improve customer service in an 18 to 24 month period.

  - Determine which of the 24 PPIs your organization aligns against.

  - Review existing agency investments to determine Agency’s Current alignment or involvement with the PPIs.

- Review the agency’s or organization's existing Mission, Goals, and Vision Statements strategic and performance plans to ensure consistency between the E-Government Strategic Plan, the organization and the Agency Strategic Plans.

  - Link IT and E-Government initiatives to the Agency Strategic Plan.  Clearly demonstrate that IT investments are being planned and implemented to successfully deliver the benefits of increased effectiveness and efficiency to the business lines and programs of the Agency/organization.

  - Develop E-Government Goals – describing how each can be achieved to fulfill the E-Government mission.

  - Break the goals into distinct objectives with defined targeted outcomes, project initiatives, and high-level performance measures (ensure these performance measures are incorporated into the Exhibit 300 process).

  - Each objective should highlight current E-Government capabilities and prospective short- and long-term initiatives.

- Ensure consistency with the President’s Management Agenda (PMA).  The five elements or Government-wide initiatives of the PMA are:

  - Strategic Management of Human Capital

  - Competitive Sourcing

  - Improved Financial Performance

  - Expanded Electronic Government

  - Budget and Performance Integration

- Strengthen IT Management of the Agency/organization by reviewing ALL elements of the business case(s) (Exhibit 300s) to identify any performance gaps.

- Identify and document existing E-Government initiatives underway.

- Analyze existing systems and applications against OMB E-Government guidance and criteria.

  - Obtain listing of all systems and applications with the Organization.

  - Identify any redundant systems and possible cross-cutting agency applications.

  - Identify opportunities for reducing redundancies of effort.

  - Identify opportunities to provide cost savings through streamlining of activities.

  - Identify organizational realignments to maximize efficiencies.

- Identify enterprise level opportunities (the agency, other federal, state, and local agencies) collaborative efforts.

- Review the Agency’s Modernization Blueprint and the Agency/organization’s alignment with the Agency’s Enterprise Architecture (EA).  Review potential opportunities for aligning with the Federal Enterprise Architecture (FEA) and using the FEA to model the future business.

- Review THE Agency’s and the organization’s Security and Privacy framework and implement a unified approach for developing and implementing security policies, procedures, analyses and risk mitigation plans.

- Identify Challenges facing the implementation of the E-Government Strategy.  In every E-Government Strategy, Organizational, Change Management, and Governance issues are major challenges that need to be addressed.

- Identify the E-Government Initiatives of the organization and develop an Implementation Plan or Timeline for accomplishing the Initiatives.  Monitor and evaluate the progress of implementing The Agency/organization’s E-Government Initiatives.

- Incorporate and document E-Government Strategy review and planning activities and their results of into the appropriate sections of the Exhibit 300 and update the status each budget cycle.

E-GOV STRATEGY REVIEW AND PLANNING ACTIVITIES REPORT OUTLINE

EXECUTIVE SUMMARY

INTRODUCTION

OFFICE OF MANAGEMENT AND BUDGET (OMB) and PRESIDENTIAL MANAGEMENT AGENDA (PMA) GUIDANCE

THE AGENCY & ORGANIZATION E-GOVERNMENT FRAMEWORK

The ORGANIZATION & THE AGENCY STRATEGIC OVERVIEW

THE AGENCY & ORGANIZATION E-GOVERNMENT GOALS

DESCRIPTION OF RESULTS OF GAP ANALYSIS OF BUSINESS CASE(S)

ENTERPRISE OPPORTUNITIES & OTHER COLLABORATIVE EFFORTS

Describe potential alignments within The Agency/organization (per review of all systems and applications identified on Exhibit 53) and external collaboration opportunities

DESCRIPTION OF THE AGENCY & ORGANIZATION E-GOVERNMENT INITIATIVES

CHALLENGES OF IMPLEMENTING E-GOVERNMENT AND RELATED ACTION PLAN(S)

# APPENDIX D – FAA RISK MANAGEMENT GUIDANCE

For each of the OMB risk areas, program managers need to document specific program risks, to include the level of risk and any planned mitigation for reducing the risk.  The mitigation strategy selected should be tied to the root cause and consequence of the risk.

The results stemming from Section I.F become key links to several other sections of the Exhibit 300 (it is important to note that risk needs to be reflected consistently throughout the Exhibit 300):

- Section I.G (Acquisition Strategy) requires that the program describe the investments’ cost risk and mitigation strategy.

- Section I.H (Performance-Based Management) requires a brief explanation of where and how risk is being included in the program’s costs and milestones (define the operational analysis system/process that will be used).  Mitigation activities identified in Section I.F must be linked with individual useful segment milestones in this section (milestone descriptions should show if they include risk mitigation).  In addition, lifecycle costs identified in this section need to be adjusted for risk.  For any negative actual performance and variance metrics, there should be the relevant lifecycle risks.

- Section I.E (Alternatives Analysis) requires that lifecycle costs shown for each alternative reflect risk-adjusted values found in Section I.H (Performance-Based Management).

- Risk is an aspect in I.B.7.a, I.C, II.B, I.D.4.A, and 3.3 also.  These sections must be consistent with the items listed in Section I.F.

A subsequent requirement of Section I.F consists of the reporting of a program’s risk reserve.  The process the FAA uses to account for risk reserve within program estimates is outlined in Section I.E (Alternatives Analysis).  This or any other method for addressing risk reserves is to be outlined within this section.

Mapping of IA Risk Facets to OMB Exhibit 300 Risk Elements:

The FAA System Engineering Manual (Section 4.10) and the AMS contain guidance for implementing Risk Management across an investment’s lifecycle.  Specific investment phases may use a tailored approach to the basic guidance found in the FAA SEM.  For example, In the AMS guidance the risk facets currently used in the risk assessment phase of the Investment Analysis (IA) process include the following:  technical, operability, information security, supportability, cost estimate, funding, human factors, stakeholder, producibility, management, schedule, benefits estimate, safety, and architecture.  Other risk sources considered include: political, interdependencies, requirements, and equipage.  These facets capture the sources of risk that the FAA has determined over the years to be the most relevant to the success of its investment decisions.  Risks identified via the facet areas outlined above can be mapped directly to the OMB Exhibit 300 (seeTable 2.0).

Table 1: FAA Investment Analysis Risk Sources Mapped to OMB Risk Areas

The above table demonstrates a notional mapping of the FAA’s IA risk facets to the OMB risk areas.  It should be noted, that depending on your program type, (i.e. system modernization, new concept implementation, or system reengineering) the nature of the risks identified during the pre-investment analysis may impact the actual mapping to the Exhibit 300 and analysts should use their best judgment.

General Risk Guidance:

The FAA System Engineering Manual (Section 4.10) provides detailed information for implementing the FAA’s risk management process.  The data generated during the risk management process is compiled into a risk table/database, as a means to satisfy continued FAA programmatic risk management requirements.  This data can easily be summarized, sorted by OMB category, and incorporated into section I.F of the Exhibit 300.

Relationship of Risk Management to other Exhibit 300 sections.

It is important to reflect risks and risk management processes consistently throughout the Exhibit 300, and especially in relation to the sections described below.

- Section I.E– Alternatives Analysis Section (from an FAA perspective)

The FAA’s approach to Alternatives Analysis, as performed for an Initial Investment Decision is consistent with the OMB Exhibit 300 Section I.E reporting.  The presentation of alternatives and lifecycle cost estimates in this section should accurately reflect risk and any associated mitigations. When the FAA performs an alternatives analysis, it reflects risk in three ways:

- adjusting schedule assumptions to reflect schedule risk

- addition of costs for mitigations identified in the risk definition phase

- assignment of risk ranges to cost estimates where there is uncertainty about the exact magnitude of costs.

The FAA develops its estimates under the AMS, by starting with point estimates for the schedule, cost and benefits.  For each of the models, the FAA then evaluates key risk drivers and areas of uncertainty and applies ranges of estimates based on best, most likely, and worst case scenarios.  The schedule, using critical path analysis is adjusted to reflect an 80% confidence level schedule.  For all programs arising from the FAA’s IA or Re-base lining processes, the 80% confidence cost estimate (i.e. the cost estimate that has an 80% probability of being under run in actual program execution) will be used for both budgeting (e.g., CIP financial baseline) and  the Exhibit 300 Program Baseline costs.  Only this cost baseline will be recorded in the Exhibit 300 PB.  This cost baseline includes “contingency” or “risk reserve” funds in each of the relevant Work Breakdown Structure (WBS) elements that require reporting in section I.F.

It is important to note that when cost estimates are developed at the 80% confidence level (risk adjusted), each of the FAA’s relevant WBS elements accounts for “contingency” or “risk reserve” as necessary.

- Section I.H – Performance-Based Management

Section I.H requires a brief explanation of where and how risk is being included in the program’s costs and milestones (define the operational analysis system/process that will be used).  Mitigation activities identified in section I.F (Risk Management) must be linked with individual useful segment milestones (milestone descriptions should show if they include risk mitigation).  In addition, lifecycle costs identified in this section should be adjusted for risk, especially for those investments that involve COTS (with or without modification).

Section I.G – Acquisition Strategy

Section I.G requires that you describe your cost risk (e.g., contract type) and mitigation strategy (e.g., EVMS, utilization of COTS products).  Within your acquisition strategy description, it is important to tie it back to your risk section, ensuring consistency of approach.  It should be noted that it is important to employ a strong acquisition strategy that mitigates risk to the Federal Government, particularly in response to question 1.G.2.

# APPENDIX E – ADDITIONAL 508 GUIDANCE

A program/system must comply with the Section 508 standards if it is classified as electronic information technology (EIT).  All EIT procured, developed, maintained or used by FAA lines of business must comply with the Section 508 EIT accessibility standards.

EIT is any equipment or interconnected system or subsystem of equipment, that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information.  Specifically, EIT includes:

- telecommunication products, such as telephones

- Information kiosks

- Transaction machines

- World Wide Web sites (Intranet and Internet)

- Multimedia (including videotapes)

- Office equipment, such as copiers, fax machines, printers, calculators

- Computers

- Ancillary equipment

- Software

- Firmware and similar procedures

- Services (including support services)

- Related resources

The Access Board Section 508 EIT Accessibility Standards are as follows:

- CFR 1194.21-Software Applications and Operating Systems

- CFR 1194.22-Web Based Information and Applications

- CFR 1194.23-Telecommunication Product

- CFR 1194.24-Video and Multimedia Products

- CFR 1194.25-Self-Contained, Closed Products

- CFR 1194.26-Desktop and Portable Computers

- CFR 1194.31-Functional Performance Criteria

- CFR 1194.41-Information, Documentation, and Support

During the procurement process, the requiring official must indicate which of the Access Board Section 508 EIT Accessibility Standards are applicable to the procurement.  It may be necessary to consult with procurement officials, Legal, and/or FAA’s Section 508 Coordinator and Technical Support to determine which Section 508 EIT Accessibility Standards may apply.

For additional information about FAA’s Section 508 Program go to http://intranet.faa.gov/aio/e-government/section_508/index.htm.

A program/system complies with the Section 508 standards when it uses and follows FAA’s Section 508 Procurement Standard Operating Procedures when procuring Section 508.

Step 1:  During the procurement process, the first question one would ask is, “Does the EIT standards apply”?  If they do not apply, then you can disregard the Section 508 requirement.

Step 2:  If the answer is yes, then you would ask, “Is the procurement eligible for exception?”  Additional detail is provided on exceptions in the Section 508 Procurement Standard Operating Procedures under Section 4.  There are four exceptions which are (1)  EIT acquired by a contractor incidental to a contract, (2)  Systems used for military command, weaponry, intelligence, and crypto logic activities (National Security System), (3) “Back Office” equipment used by service personnel for maintenance, repair or occasional monitoring of equipment, and (4) EIT that would impose an undue burden (significant difficulty of expense) on the agency.

After you identify the exception, you submit your write-up and support documentation to the Contracting Officer and FAA Legal, which is General Counsel.  This documentation will be maintained in the COs contract file.

Step 3:  If the answer is No, and no exception applies, then you would proceed to identify the applicable Access Board Section 508 EIT Accessibility standard.   The requiring official selects the EIT standards that will apply to the procurement.  He/she would have to select from 1194.21 thru 1194.41 or he/she may select then all depending on the procurement requirements.  The requiring official may have to consult other technical personnel, the Section 508 Program Office, and/or persons in the procurement office to assist in identifying the EIT standards.

Step 4:  After you select the applicable EIT standard or standards, you would conduct the market research.  For example, you could query Government databases, review on-line catalogs and product literature, hold pre-solicitation conferences, use technical analysis publications and review Government-managed web sites.  For more specifics, on the methods of market research that are available, please consult Exhibit B in the Section 508 Procurement Standard Operating Procedures.

After you have completed the market research, you would decide whether the electronic information technology is available in the marketplace.

Step 5:  If the answer is no, then the requiring official would document to the file that the EIT was not available in the marketplace and submit to the Contracting Officer and FAA Legal, which is General Counsel.  This documentation will be maintained in the Contracting Officer’s contract file.

Step 6:  If the answer were yes, then the Contracting Officer would initiate all the Pre-award Process tools to purchase the EIT product.  For more specifics, on the Pre-award Process tools, consult Exhibit E in your Section 508 Procurement Standard Operating Procedures.

If the program/system is not electronic information technology (EIT) then it does not have to comply with the standards.  Also, there are four exceptions that are as follows:

- EIT acquired by a contractor incidental to a contract

- Systems used for military command, weaponry, intelligence, and crypto logic activities (National Security System)

- “Back Office” equipment used by service personnel for maintenance, repair or occasional monitoring of equipment

- EIT that would impose an undue burden (significant difficulty or expense) on the agency.

Additional detail is provided on exceptions in the Section 508 Standard Operating Procedures under Section 4.

All exceptions, with write-up and support documentation must be submitted to the Contracting Officer and FAA Legal, which is General Counsel.

How could I respond to the OMB question, “How will you ensure Section 508 compliance?”  My program/system is in the planning stages and I am unfamiliar with the Section 508 requirements.

Programmatic Condition

If your program requirements were contracted out or ordered under a task order subsequent to 6/21/01, then Insert one of the following responses in Section I.G  Acquisition Strategy after question Number 7, "How will you ensure Section 508 compliance?"

Standard Response--(Please choose one)

In accordance with FAA's Section 508 Procurement Standard Operating Procedures, (insert name of program) will determine which of the Section 508 standards apply to the program and comply with each applicable standard.

OR

In accordance with FAA's Section 508 Procurement Standard Operating Procedures, (insert name of program) has determined that the following Section 508 standards apply to the program and will comply with each applicable standard.

List standards that apply:

- 1194.21 Software Applications and Operating Systems

- 1194.22 Web-based Information or applications

- 1194.23 Telecommunication Products

- 1194.24  Video and Multimedia Products

# APPENDIX F – GLOSSARY OF ESSENTIAL TERMS

Appropriation

An appropriation is an act of Congress that enables Federal agencies to spend money for specific purposes. Congress must then pass appropriations bills to provide money to carry out government programs for that year. Appropriations bills divided up by type of program and agency into thirteen separate bills: Agriculture; Commerce/Justice/State; Defense; District of Columbia; Energy and Water; Foreign Operations; Interior; Labor/Health and Human Services/Education; Legislative Branch; Military Construction; Transportation; Treasury/Postal Service; and Veterans Affairs/Housing and Urban Development.

Authorization

An authorization is an act of Congress that establishes or continues a federal program or agency, and sets forth the guidelines to which it must adhere.

Balanced Budget

A balanced budget occurs when total receipts equal total outlays for a fiscal year.

Budget Authority (BA): The authority provided by law to incur financial obligations that will result in outlays.  Specific forms of budget authority include appropriations, borrowing authority, contract authority, and spending authority from offsetting collections.

Budget Resolution

The budget resolution is the annual framework within which Congress makes its decisions about spending and taxes. This framework includes targets for total spending, total revenues, and the deficit, as well as allocations, within the spending target, for discretionary and mandatory spending.

“Cap”

A “cap” is a legal limit on annual discretionary spending.

Capital Planning and Investment Control

A decision-making process for ensuring that information technology (IT) investments integrate strategic planning, budgeting, procurement, and the management of IT in support of agency missions and business needs. A Capital Planning and Investment Control cycle typically includes three major strategies: Select (investments are selected), Control (investments are controlled and monitored as they are implemented), and Evaluate (investments are evaluated after they have reached full operating capacity).

Clinger-Cohen Act

The Clinger-Cohen Act is also known as the Information Technology Management Reform Act of 1996. The act supplements the Paperwork Reduction Act of 1980 by establishing a comprehensive approach for executive agencies to improve the acquisition and management of their information resources (IT).

Cost Benefit Analysis

A systematic, quantitative method to assess the desirability of government projects or policies when it is important to take a long view of future effects and a broad view of possible side-effects.

Deficit

The deficit is the difference produced when spending exceeds revenues within a fiscal year.

Discount Factor

The factor that translates expected benefits or costs in any given future year into present value terms. The discount factor is equal to

1/(1 + i)t

where i is the interest rate and t is the number of years from the date of initiation for the program or policy until the given future year.

Discretionary Spending

Discretionary spending is what the President and Congress decide to spend through the 13 annual appropriations bills. Examples include money for such activities as the FBI and the Coast Guard, housing and education, space exploration and highway construction, and defense and foreign aid. See Mandatory Spending.

E-Government

E-Government (electronic government) refers to the federal government’s use of information technologies (such as Wide Area Networks, the Internet, and mobile computing) to exchange information and services with citizens, businesses, and other arms of government. Refers to the use by the Government of web-based Internet applications and other information technologies, combined with processes that implement these technologies, to enhance the access to and delivery of Government information and services to the public, other agencies, and other Government entities; or to bring about improvements in Government operations that may include effectiveness, efficiency, service quality, or transformation.

Entitlement

An entitlement program is one in which the federal government is legally obligated to make payments or provide aid to any person who meets the legal criteria for eligibility. Examples include Social Security, Medicare, Medicaid, and Food Stamps.

Fiscal year

The fiscal year is the federal government’s accounting period. It begins on October 1 and ends up September 30. For example, fiscal year 2003 began on October 1, 2002 and will end on September 30, 2003.

Full-time Equivalents (FTEs)

Civilian employment in the Executive Branch is measured on the basis of full-time equivalents. One FTE is equal to one work year or 2,080 non-overtime hours. For example, one full-time employee counts as one FTE, and two half-time employees also count as one FTE.

Lifecycle Costs

The overall estimated cost, both government and contractor, for a particular program alternative over the time period corresponding to the life of the program, including direct and indirect initial costs plus any periodic or continuing costs of operation and maintenance.

Major IT Investment (Investments that are required to be reported to OMB):  A Major IT investment means a system or investment that requires special management attention because of its importance to an agency’s mission; was a major investment in the FY 2005 submission and is continuing; is for financial management and spends more than $500,000; is directly tied to the top two layers of the Federal Enterprise Architecture (Services to Citizens and Mode of Delivery); is an integral part of the agency’s modernization blueprint (EA); has significant program or policy implications; has high executive visibility; and is defined as major by the agency’s capital planning and investment control process. OMB may work with the agency to declare other investments as major investments. Investments that are E-Government in nature or use e-business technologies must be identified as major investments regardless of the costs.

Mandatory Spending

Mandatory spending is authorized by permanent law rather than annual appropriations. An example is Social Security. The President and the Congress can change the law to change the eligibility criteria and thus the level of spending on mandatory programs, but they do not have to take annual action to ensure the continuation of spending.

Mixed Lifecycle Investment

An investment that has both development/modernization/enhancement (DME) and steady-state aspects. For example, a mixed lifecycle investment could include a prototype or module of a system that is operational with the remainder of the system in DME stages; or, a service contract for steady-state on the current system with a DME requirement for system upgrade or replacement.

Net Present Value/NPV

The difference between the discounted present value of benefits and the discounted present value of costs

Obligations: A binding agreement that will result in outlays, immediately or in the future.  Budgetary resources must be available before obligations can be incurred legally.

“Off-Budget”

By law, the Government must distinguish “off-budget” programs separate from the budget totals. Social Security and the Postal Service are “off-budget.”

“On-Budget”

Those programs not legally designated as off-budget.

Outlays: A payment to liquidate an obligation (other than the repayment of debt principal).  Outlays generally equal to cash disbursements, but also are recorded for cash-equivalent transactions, such as the subsidy cost of direct loans and loan guarantees, and interest accrued on public issues of the public debt.  Outlays are the measure of Government spending.

ROI

Return on Investment

Risk Adjusted Lifecycle Costs

The overall estimated cost for a particular investment alternative over the time period corresponding to the life of the investment, including direct and indirect initial costs plus any periodic or continuing costs of operation and maintenance that has been adjusted to accommodate any risk identified in the risk management plans.

Sunk Cost

A cost incurred in the past that will not be affected by any present or future decision. Sunk costs should be ignored in determining whether a new investment is worthwhile.

Useful Segment/Module

An economically and programmatically separate component of a capital investment that provides a measurable performance outcome for which the benefits exceed the costs, even if no further funding is appropriated.

Budget Authority and Outlays

Spending levels in the President’s Budget and in congressional budget resolutions are measured in dollars in two ways: budget authority and outlays. Outlays represent actual disbursements by the Treasury. When the Treasury issues a check in fiscal year 1998, that is a fiscal year 1998 outlay. Budget authority, on the other hand, is the legal authority for an agency to enter into obligations of dollars in a certain amount that will result in outlays. When Congress appropriates (appropriations bills) funds for a particular program, it is enacting budget authority – not outlays.

Earned Value Management (EVM) Terms

- Planned Value (PV) = Budgeted Cost of Work Scheduled (BCWS): The sum of the budgets for all work packages, planning packages, etc., scheduled to be accomplished (including in-process work packages), plus the amount of level of effort and apportioned effort scheduled to be accomplished within a given time period.

- Earned Value (EV) = Budgeted Cost for Work Performed (BCWP): The sum of the budgets for completed work packages and completed portions of open work packages, plus the applicable portion of the budgets for level of effort and apportioned effort.  This is value earned to date.

- Actual Cost (AC) = Actual Cost of Work Performed (ACWP):  The costs actually incurred and recorded in accomplishing the work performed within a given time period.

- Variance – The difference (in $$) between your plan and your actuals

  - Cost Variance – the numerical difference between value earned (BCWP) and actual cost (ACWP)

  - Schedule Variance – The numerical difference between value earned (BCWP) and the planned budget (BCWS)

- Either one may be positive or negative

  - A negative value normally denotes either having accomplished less than scheduled or spent more than planned for the work accomplished.

  - A positive value normally denotes having accomplished more than what had been scheduled or spent less than planned for the amount of work that was accomplished.

- Performance Index – A measure of the efficiency of work performed to date

  - Cost Performance Index – cost efficiency factor achieved by relating value earned (BCWP) to the dollars actually spent (ACWP):  CPI = BCWP/ACWP

  - Schedule Performance Index – schedule efficiency factor achieved by relating value earned (BCWP) to the scheduled work (BCWS):  SPI = BCWP/BCWS

- Budget at Completion (BAC) – The sum of all budgets (BCWS) on the project.

- Estimate at Completion (EAC) – The sum of all actual costs to date plus the estimate of costs for authorized work remaining: EAC = ACWP + Estimate To Complete

  - This should be updated periodically

- Estimate to Complete (ETC) – That portion of the EAC that addresses total expected costs for all work remaining

# Text boxes

Security

Operability

Technical

Supportability

Cost Estimate

Funding

Human Factors

Stakeholder

Producibility

Management

Schedule

Benefit Estimate

Safety

A: Political

A: Interdependencies

A: Requirements

A: Architecture

A: Equipage

Exhibit 300 Risk Reporting Category

IA: Cross

Reference

V5, V6

V5, V6

V1, V2, V4, V9

V5, V7, V12, V17

V1, V2, V4, V7, V13, V15, V17

V2, V11, V12, V13, V15, V17, V18

V3, V13, V17

V9

V10

V8,  V10, V12, V13

V7, V8

V8, V14, V18

V3, V7, V15, V17, V18

V1, V4, V9, V15, V17, V18

V14, V16, V17, V18

V3

V3, V7, V8

Schedule

Initial costs

Life-cycle costs

Technical Obsolescence

Feasibility

Reliability of systems

Dependencies / interop.

Surety (asset protection)

Risk of Monopoly

Management Capability

Risk of investment failure

IT: Org. & change mgmt.

IT: Business

IT: Data/info

IT: Technology

IT: Strategic

IT: Security

IT: Privacy

IT: Project resources

IA Risk Areas

V11

V1

V2

V3

V4

V5

V6

V7

V8

V9

V10

V11

V12

V13

V14

V15

V16

V17

V18

O1

O2

O3

O4

O5

O6

O7

O8

O9

O10

O11

O12

O13

O14

O15

O16

O17

O18

O19

V9, V11