United States Department of Agriculture (USDA) eGovernment Program

Risk Profile – Risk Management Plan

eLearning Business Case

Draft

February 2003

Table of Contents

Revision History	ii

Previous Change History	ii

Document Sign-off	ii

1	Introduction	1

2	Identify Risks	2

2.1	Financial Risks	2

2.2	Technical Risks	2

2.3	Operational or Business Risks	3

2.4	Schedule or Project Resources Risks	3

2.5	Legal and Contractual or Strategic Risks	3

2.6	Organizational and Change Management Risks	3

2.7	Data/Information Risks	4

2.8	Security Risks	4

2.9	Privacy Risks	4

2.10	Risks Associated with Contracting to an Application Service Provider	4

3	Analyze Risks	5

3.1	Risk Probability	5

3.2	Percent Occurring	6

3.3	Risk Priority	7

3.4	Cost of Risk	8

3.5	Risk Adjusted Cost	9

3.6	Risk Score	9

4	Mitigate Risks	10

4.1	Strategy and Methodology	10

5	Track Risks	13

6	Appendix A	14

6.1	Risk Management Table	14

# Revision History

## Previous Change History

Table a – Previous Change History

| Version | Date | Author | Comment |
| --- | --- | --- | --- |
| 1.0 | 10/24/2002 | Amanda R. Plummer | Initial Draft |
| 2.0 | 11/04/2002 | Elaine K. Turville | Updated with comments |
| 2.1 | 11/06/2002 | Elaine K. Turville | Updated with comments |
| 2.2 | 11/11/2002 | Elaine K. Turville | Updated with comments |
| 2.3 | 11/12/2002 | Elaine K. Turville | Updated bullet lists |
| 2.4 | 11/20/2002 | Amanda R. Plummer | Updated with Risks Associated with Contracting to an Application Service Provider, Risk Costs |
| 2.5 | 11/20/2002 | Elaine K. Turville | Updated with team comments |
| 2.6 | 11/21/2002 | Elaine K. Turville | Updated with risk score |
| 2.7 | 12/03/2002 | Sara Q. Tyndall | Updated formatting |
| 2.8 | 12/09/2002 | Elaine K. Turville | Updated Naming |
| 2.9 | 01/17/2003 | Elaine K. Turville | Updated with team comments |
| 3.0 | 01/22/2003 | Elaine K. Turville | Updated with team comments |
| 3.1 | 02/03/2003 | Liesl M. Awalt | Updated with team comments |
| 3.2 | 02/25/2003 | Liesl M. Awalt | Updated with CyberSecurity comments |

## Document Sign-off

Table b – Document Sign-off

| Date | Name | Title |
| --- | --- | --- |

# Introduction

Risk is the possibility that an uncertain circumstance or event that could stand in the way of achieving the objectives of an investment.  Risks are distinct from issues in that they reflect things that might happen in the future.  Issues on the other hand are things that are current occurring.  Issues can be thought of as the outcomes of risks.  This document primarily focuses on addressing and preparing for eLearning risks before they become issues.

Risk is inevitable and all investments incur a certain amount of risk.  Risk is to be expected in any situation and therefore must be considered when approaching new investments.  The downfall of risks is not that they exist or even occur, but that many times they are not recognized.  Most project problems arise when there is no plan in place for dealing with risks when they become issues.

Risk Management has been identified as the systematic approach for identifying, analyzing, and mitigating risks that could be encountered by an initiative.  Risk Management is not about being 'risk averse'; rather, it is based on informed decisions and analyses of potential outcomes.

Since it is possible that some risks identified for the eLearning initiative will eventually become realities, it is important to begin identifying and planning for these risks in the early stages of the project.  This document addresses and discusses risks associated with the recommended eLearning approach.  Reviewing and outlining risks during this phase will help to better prepare the project team to manage risks in a timely and effective manner.

To ensure added effectiveness, this plan is designed such that identified risks and controls can be continuously updated over the entire project lifecycle.  Through continuous evaluation of the potential risks and the creation of plans to manage them, adjustments can be made to prevent or reduce many of the damages that result when risks occur.

The following sections of this document discuss the steps that will be followed to manage relevant eLearning risks.  These include:

- Identify Risks;

- Analyze Risks;

- Mitigate Risks; and

- Track Risks.

# Identify Risks

Risk identification involves determining and documenting risks that could potentially impact the eLearning initiative.  These have been identified in the following areas:

- Financial Risks;

- Technical Risks;

- Operational or Business Risks;

- Schedule or Project Resources Risks;

- Legal and Contractual or Strategic Risks;

- Organizational and Change Management Risks;

- Data/Information Risks;

- Security Risks;

- Privacy Risks; and

- Risks Associated with Contracting to an Application Service Provider.

Each of these risk areas relevant to the eLearning initiative are discussed in the following subsections and are further detailed in Table 6.1a in Appendix A.

## Financial Risks

Financial risks have a purely financial outcome.  The financial risks identified for the eLearning initiative include threats such as:

- Proper funding not being acquired to continue moving forward;

- System procurement costs exceeding the estimated amount;

- Technical support costs exceeding the estimated amount; and

- Deployment/Operational costs could exceed estimated amount.

## Technical Risks

The technical risks center around the selection, implementation and deployment of a technology solution.  The relevant technical risks identified for the eLearning initiative include:

- Project team lacks technical expertise required for successful implementation;

- Solutions are out of date when delivered due to advances in technology or delay in funding;

- The solution doe not deliver usable and useful services;

- Underestimating the complexity of interfaces with other systems; and

- Complexity of interfaces with other systems in underestimated.

## Operational or Business Risks

Operational or business risks are the most common risks.  These occur during the life of the project and include risks like:

- Users are not able to use the system proficiently; and

- Inadequate estimation of maintenance and/or enhancement resources required to operate the solution.

## Schedule or Project Resources Risks

Schedule or project resource risks involve the degree to which the expected completion dates for all major investment activities meet organizational deadlines and constraints for affecting change.  The eLearning risks related to the project schedule or project resources include:

- Time required for business process re-engineering could exceed estimates;

- Time required to rollout the solution could exceed estimates;

- Generic processes common to all agencies and unique agency processes not; and clearly identified and compared to delivered vendor product.

## Legal and Contractual or Strategic Risks

Legal and contractual risks relate to events to which USDA could be held liable.  The eLearning legal and contractual risks include:

- Improper information may be published to the public; and

- Discussions with the Unions may lead to delays in the process or necessary changes.

## Organizational and Change Management Risks

Large projects impact many people and processes.  The relevant eLearning organizational and change management risks involve:

- Redistribution of power occurring within the Department; and

- Agencies or individual employees are resistant to adopt proposed solutions.

## Data/Information Risks

Data and information risks relate to the loss of data or information.  The eLearning data and information risks include:

- Loss of content due to an accident, fire, or other disaster; and

- Erroneous deletion or destruction of content.

## Security Risks

Security is paramount for any system to prevent unauthorized access.  The eLearning security risks include:

- Roles and responsibilities related to solution are improperly administered; and

- Unauthorized users gain access to data or content stored in the solution.

## Privacy Risks

In accordance with the Privacy Act of 1974 and related legislation, privacy of data and information must be maintained.  The eLearning risks related to privacy include:

- Unauthorized users access, use, or disclose private information that is stored in the system.

## Risks Associated with Contracting to an Application Service Provider

If the choice is made to contract the eLearning solution to an application service provider, some additional risks will be incurred:

- Inability to transfer assets, such as equipment, facilities, and licenses, from USDA to the application service provider;

- Inability to acquire the skills or resources necessary to manage the provisions of the service contract;

- Lack of control over skills and resources as well as quality and performance of the application service provider; and

- Issue identification and resolution are not achieved in a timely manner due to unresponsiveness of the application service provider.

# Analyze Risks

Identified risks are analyzed based on an assessment of their likelihood of occurrence and the impact that could result if they occur.  During the risk analysis process, numerous activities are conducted to aid in the development of the risk management and control strategies.  The activities for examining the potential eLearning risks include:

- Determining Risk Probability:

- Calculating Percent Occurrence;

- Assigned Risk Priority;

- Calculating the Cost of Risk;

- Determining the Risk Adjusted Cost; and

- Assigning the Risk Score.

## Risk Probability

Probability of occurrence is the likelihood that a particular risk will occur.  Risk probabilities have been assigned to each of the potential eLearning risks by estimating the likelihood that the risk would actually be recognized based on the scale identified in Table 3.1a.  Risks that will exist for the duration of the project have been assigned a higher probability of occurrence than risks that do not span the whole lifecycle.  Probabilities are also higher for common risks that occur frequently within USDA.

Table 3.1 – Probability of Occurrence Scale

| Assessment of Risk Probability | Clarifying Remarks | Figure for Calculation |
| --- | --- | --- |
| Highly Likely | Likelihood of occurrence > 75% | 88% |
| Somewhat Likely | Likelihood of occurrence between 50% and 75% | 63% |
| 50/50 Chance | Likelihood of occurrence 50% | 50% |
| Somewhat Unlikely | Likelihood of occurrence between 25% and 50% | 38% |
| Highly Unlikely | Likelihood of occurrence < 25% | 13% |

Risk probability is recorded in Tables 6.1a in Appendix A for each of the risks identified for the eLearning initiative.  The risks with the highest probability of occurrence include:

- Underestimating the complexity of interfaces with other systems;

- Inability to migrate existing Agency content and documents into the solution; and

- Inability to acquire the skills or resources necessary to manage the provisions of the service contract.

## Percent Occurring

The percent occurring refers to the impact or estimated percent of Agencies, users, systems and/or processes that could be affected by each risk.  The impact each risk could have on the eLearning initiative or the entire Department has been determined based on the scale identified in Table 3.2a.

Table 3.2 – Percent Occurring Scale

| Assessment of Percent Occurring | Clarifying Remarks |
| --- | --- |
| Critical Impact | 66% to 100% Impact |
| Moderate Impact | 33% to 66% Impact |
| Low Impact | Less than 33% Impact |

The percent occurring for each of the potential eLearning risks are estimated in Appendix A.  The following risks have been identified to have critical risk:

- Proper funding may not be secured to continue moving forward with the initiative;

- Complexity of interfaces with other systems is underestimated;

- Users are not able to use the system proficiently;

- Improper information may be published to the public;

- Discussions with the Unions may lead to delays in the process or necessary changes;

- Agencies or individual employees are resistant to adopt proposed solutions;

- Unauthorized users gain access to data or content stored in the solution;

- Unauthorized users gain access to sensitive content because they are not properly identified in the system;

- Inability to transfer assets, such as equipment, facilities, and licenses, from USDA to the application service provider; and

- Inability to acquire the skills or resources necessary to manage the provisions of the service contract.

## Risk Priority

After the list of risks is qualified according to the risk probability and percent of occurrence, the risks are prioritized.  This process helps to determine which risks are most critical and should be addressed first, as well as the least significant risks that may not be as critical to the project’s success.  Risks have been prioritized into three main groups based on combinations of likelihood and impact as identified in Table 3.3a, below.

Table 3.3 – Risk Priority Rating Scale

| Priority | Risk Probability | Percent Occurring |
| --- | --- | --- |
| 1 | Highly Likely | Critical |
|  | Highly Likely | Moderate |
|  | Somewhat Likely | Critical |
|  | Somewhat Likely | Moderate |
|  | 50/50 Chance | Critical |
| 2 | Highly Likely | Low |
|  | Somewhat Likely | Low |
|  | 50/50 Chance | Critical |
|  | 50/50 Chance | Moderate |
|  | Somewhat Unlikely | Critical |
| 3 | 50/50 Chance | Low |
|  | Somewhat Unlikely | Moderate |
|  | Somewhat Unlikely | Low |
|  | Highly Unlikely | Moderate |
|  | Highly Unlikely | Low |

As evident from the table above, priority 1 risks are most crucial and priority 3 risks are least crucial.  Risk priorities have been identified for the eLearning risks and are also included in the risk management table in the appendix.  Some of the more crucial risks include:

- Proper funding may not be secured to continue moving forward with the initiative;

- Complexity of interfaces with other systems is underestimated;

- Users are not able to use the system proficiently;

- Agencies or individual employees are resistant to adopt proposed solutions;

- Inability to transfer assets, such as equipment, facilities, and licenses, from USDA to the application service provider; and

- Inability to acquire the skills or resources necessary to manage the provisions of the service contract.

## Cost of Risk

Most risks, financial or other, have a cost associated to them.  The cost of risk relates to the financial setbacks that would be encountered as a result of the risk.  Estimated costs for the identified eLearning risks are detailed in Table 6.1a in Appendix A.  The more costly risks include:

- System procurement costs (software & related hardware) could exceed estimated amount;

- Proper funding may not be secured to continue moving forward with the initiative;

- Deployment and/or Operations costs could exceed the estimated amount;

- Technical support costs could exceed the estimated amount;

- Solutions are out of date when delivered due to advances in technology or delay in funding;

- The solution does not deliver usable and useful services;

- Complexity of interfaces with other systems is underestimated;

- Time required to rollout the solution could exceed estimates;

- Discussions with the Unions may lead to delays in the process or necessary changes;

- Agencies or individual employees are resistant to adopt proposed solutions;

- Loss of content due to an accident, fire, or other disaster;

- Roles and responsibilities related to the solution are improperly administered;

- Unauthorized users gain access to data or content stored in the solution;

- Unauthorized users gain access to sensitive content because they are not properly identified in the system; and

- Inability to transfer assets, such as equipment, facilities, and licenses, from USDA to the application service provider.

Costs for risk could be incurred due to legal penalties for failure to properly identify and protect official records or legal penalties for destruction of official record material without proper disposition authority.  Another cost of risk could include legal penalties for destruction of evidence based upon inconsistent handling of official record material.

Table 3.4 – Estimated Risk Cost Ranges

| Category | Range | Figure for Calculation |
| --- | --- | --- |
| A | Less than $5,000 | $2500 |
| B | $5,000 to <$25,000 | $15,000 |
| C | $25,000 to <$100,000 | $62,500 |
| D | $100,000 to <$2.5 million | $1.3 million |
| E | $2.5 to <$5 million | $3.75 million |

## Risk Adjusted Cost

Risk adjusted cost is measured by multiplying the risk cost (in dollars) by the percentage risk probability.  Risk adjusted costs have been calculated for each potential eLearning risks and are also included in the risk management table in the appendix.

The investment’s overall risk adjusted cost or risk exposure has been determined to be $8,149,900 by taking a sum of each of the eLearning risk factors.

## Risk Score

Finally, a risk score is assigned to the initiative to provide a more accurate picture of the overall investment risk.  Risk score is measured by dividing the investment’s overall risk factor by the total number of identified risks.  Since 28 eLearning risks have been identified and the investment’s risk score is $8,149,900, the eLearning risk score calculates to $313,458. The eLearning  – Financial Profile - Cost Benefit Analysis accounts for the risk cost in the lifecycle costs for each of the alternatives by assuming that approximately 10% of this cost will occur each year

# Mitigate Risks

## Strategy and Methodology

Risk mitigation includes the strategy and methodology for controlling risks when they become issues.  The main objective of risk mitigation is to define the approach for dealing with risks to ensure that the eLearning initiative is completed on time and on budget.  This section of the document addresses this strategy and methodology for mitigating risks.

The method begins by determining the techniques or risk strategies, through identifying and utilizing the level of control for each risk.  Table 4.1a defines the risk strategies that have been identified for controlling eLearning risks.

Table 4.1a – eLearning Risk Mitigation Strategies

| Strategy | Definition |
| --- | --- |
| Avoidance | Avoidance is any action that completely eliminates the risk. |
| Transfer | Transfer moves the responsibility for the risk to the party best placed to respond to it. |
| Control | Control identifies an action or product that becomes part of the work plan. It is monitored and reported as part of the regular performance analysis and progress reporting. Control will reduce the likelihood of a risk materializing, or if it does materialized it will reduce the potential impact. |
| Acceptance | Acceptance is taking on the risk without putting into place a risk mitigation pan. This occurs when implementing a risk mitigation plan is impossible or not cost effective. |
| Investigation | Investigation is recommended when no clear solution can be identified. Investigation involves undertaking further research to more accurately define the level of risk and developing a contingency plan until a mitigation plan can be developed. |

To assist in selecting an appropriate mitigation strategy for risks, the level of control is determined for each risk.  Level of control can be external, internal, or both.  External control levels utilize the avoidance, transfer, acceptance, or investigation mitigation strategies.  Internal control levels utilize the control, acceptance, or investigation mitigation strategies.  If the level of control is both external and internal, avoidance, transfer, control, acceptance, or investigation mitigation strategies are applied.  This methodology is further depicted in Table 4.1b, below.

Table 4.1b – Levels of Control

| Level of Control | Mitigation Strategy | Explanation |
| --- | --- | --- |
| External | Avoidance, Transfer, Acceptance, Investigation | Transfer or avoid these risks. If the risk can neither be transferred nor avoided, consider accepting it. By their nature, these risks are not within our control. Accepting these risks could result in exposure to potentially costly liabilities. Whenever risk is accepted, a contingency plan should be developed to respond if/when the risk becomes a reality. If more information is needed to select a technique, investigate. |
| Internal | Control, Acceptance, Investigation | Develop risk mitigation responses to control these risks. If risk mitigation techniques are unavailable or cost prohibitive, or if the risk priority is low (priority 3), consider accepting the risk. Whenever risk is accepted, a contingency plan should be developed to respond if/when the risk becomes a reality. If more information is needed to select a technique, investigate. |
| Both | Avoidance, Transfer, Control, Acceptance, Investigation | Transfer or avoid these risks if possible, especially where control is indirect or minimal. If the risks can neither be transferred nor avoided, develop risk mitigation responses to control them. If risk mitigation techniques are unavailable or cost prohibitive, or the risk priority is low (priority 3), consider accepting it. Whenever accepting a risk, a contingency plan should be developed to respond if/when the risk becomes a reality. If more information is needed to select a technique, investigate. |

Risk mitigation strategies have been assigned to the identified eLearning risks.  These are displayed in the Mitigation Strategy column of Table 6.1a in Appendix A.

Following the identification of the control level and risk mitigation strategy, detailed descriptions of the risk mitigation techniques are developed.  Since the initial response may prove to be unsuccessful in this Risk Management Plan, multiple risk mitigation techniques are detailed for each area of risk.  The inclusion of multiple techniques allows the project team to implement the most appropriate risk mitigation techniques.  It also supports back-up plans.

As previously mentioned, the Risk Management Plan should be continually updated throughout the life of the project.  The tool should house any identified risks and mitigation strategies.  If or when risks become issues, the risk management plan should be referenced as a resource for potential solutions.  Since mitigation could also impact schedules and resources, it is important to note that the responses assigned to these risks may require modifications to the project plan.  The tracking of risks is further mentioned in the Track Risks section of the document.

A future step in the risk mitigation methodology is the assignment of responsibility.  Individuals, not groups, should be assigned to risks during the phase the risk could occur. Responsibility should be allocated across the project team to ensure that risks will be managed and monitored more closely.

The project manager should be responsible for overseeing the risk management process and periodically reconvening the project team to determine if new risks have surfaced.  The project team should continue to revisit the plan, and use the process described throughout this document to add new risks and update the team’s progress on existing risk mitigation responses.

# Track Risks

As issues begin to arise and the identified responses are put into action, an important component of any risk mitigation plan is ongoing monitoring and communication of risk.

A Risk Management table has been identified as the appropriate tool for tracking and updating the eLearning risks.  This table, included in Appendix A, details the following:

- Date Identified;

- Area of Risk;

- Description;

- Risk Priority;

- Risk Probability;

- Occurrence;

- Cost of Risk;

- Level of Control;

- Mitigation Strategy; and

- Current Status.

As previously mentioned, risk management is an iterative and continuous process.  Therefore, this table will serve the purpose of tracking the eLearning risks as they evolve and as additional risks are identified.

During the design, build, and implementation phases, the Risk Management Plan will be reviewed, updated, and republished to ensure that all risks are documented and tracked.

# Appendix A

## Risk Management Table

Table 6.1 – Risk Management

| Date Identified | Area of Risk | Description | Risk Priority | Risk Probability | Occurrence | Cost of Risk | Risk Adjusted Cost | Level of Control | Mitigation Strategy & Detailed Description | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10/28/02 | Financial | System procurement costs (software & related hardware) could exceed estimated amount | 2 | 50/50 Chance | Moderate | D | $650,000 | Internal and External | Avoidance Select software & hardware to be within budget amounts through thorough planning & contingency funding Control Conduct market research on costs and incorporate into the funding request | Identified |
| 10/28/02 | Financial | Proper funding may not be secured to continue moving forward with the initiative | 1 | 50/50 Chance | Critical | D | $650,000 | Internal and External | Avoidance Present OMB with a concise and thorough business case that fully supports the vision Control Implement in phases Assess and reassess the cost of implementation Create a contingency plan for going forward | Identified |
| 10/28/02 | Financial | Deployment and/or Operations costs could exceed the estimated amount | 2 | 50/50 Chance | Moderate | D | $650,000 | Internal and External | Control Conduct periodic and timely project monitoring according to milestones Tracking time and expenses Perform thorough planning Implement iterative development processes Schedule independent quality control audits | Identified |
| 10/28/02 | Financial | Technical support costs could exceed estimated amount | 2 | 50/50 Chance | Moderate | D | $650,000 | Internal and External | Avoidance Select and task resources to be within budget amounts Control Utilize a project manager to ensure that timeframes and timelines are met Adopt a cohesive, agreed-upon technical support strategy | Identified |
| 10/28/02 | Technical | Project team lacks technical expertise required for successful implementation | 3 | Somewhat Unlikely | Moderate | C | $23,750 | Internal and External | Avoidance Define technical expertise in advance of determining team Screen and select deployment staff with expertise in all functional areas Provide training Select staff with prior experience in similar project Use resources with overlapping expertise Select vendor with good technical support | Identified |
| 10/28/02 | Technical | Solutions are out of date when delivered due to advances in technology or delay in funding | 3 | Highly Unlikely | Moderate | D | $169,000 | External | Acceptance Incorporate technology upgrades/“just-in-time technology” as available and keep close watch on standards and other changes in industry Control Conduct impact analysis of technologies Select a solution that incorporates industry open standards | Identified |
| 10/28/02 | Technical | The solution does not deliver usable and useful services | 3 | Highly Unlikely | Moderate | D | $169,000 | Internal and External | Control Document lessons learned from early adopters Conduct iterative user acceptance and usability testing Ensure solid and concise business requirements Provide a system to collect and track concerns and ensure that these are addressed Conduct a prototype implementation | Identified |
| 10/28/02 | Technical | Complexity of interfaces with other systems is underestimated | 1 | Somewhat Likely | Critical | D | $819,000 | Internal and External | Control Predefine interface protocols that work between disparate systems Leverage early adopters of systems we select Define standards using industry protocols Define integration requirements Ongoing assessment and evaluation based on early adopters Prove solution would integrate through ‘Proof of Concept’ | Identified |
| 10/28/02 | Operational | Agencies are unable to migrate existing content (within scope of the project) into the solution. | 1 | Somewhat Likely | Moderate | C | $39,375 | Internal and External | Investigate Investigate conversion tools Control Ensure the solution supports native and open standards Ensure Agencies prioritize content for inclusion into the solution | Identified |
| 10/28/02 | Operational | Users are not able to use the system proficiently | 1 | 50/50 Chance | Critical | C | $31,250 | Internal and External | Control Ensure system is flexible and customizable Ensure the system is integrated with existing suite of tools to decrease user learning curve Conduct usability and user acceptance testing as products are developed Provide timely and modularized training and extensive education (both online and in person) Conduct marketing effort to educate both internal and external users Choose a solution that provides FAQ, help centers, and online real-time customer support | Identified |
| 10/28/02 | Operational | Inadequate estimation of maintenance and/or enhancement resources required to operate the solution | 2 | 50/50 Chance | Moderate | C | $31,250 | Internal and External | Control Use early adopters to predict required maintenance and/or enhancements Account for extra maintenance time in the schedule Utilize other agency experience Avoidance Utilize fixed cost contracts with selected vendors | Identified |
| 10/28/02 | Schedule | Time required for business process re-engineering could exceed estimates | 2 | 50/50 Chance | Moderate | C | $31,250 | Internal and External | Control Incorporate business process changes early in the project plan Conduct project monitoring and identification of potential schedule impacts so that corrective measures can be taken Prioritize the processes that will be implemented in order of importance | Identified |
| 10/28/02 | Schedule | Time required to rollout the solution could exceed estimates | 2 | 50/50 Chance | Moderate | D | $650,000 | Internal and External | Control Set realistic expectations and manage those expectations Conduct periodic review and reevaluation of the project plan Offer incentives (and penalties) to ensure timely completion | Identified |
| 11/04/02 | Schedule | Generic processes common to all agencies and unique agency processes not clearly identified and compared to delivered vendor product | 2 | 50/50 Chance | Moderate | C | $31,250 | Internal and External | Control Careful analysis of: Training administration processes of all Agencies Identification of common process and unique Agency processes Careful analysis of vendor delivered processes Identification of processes where custom solutions are required. Define common workflow and training process. | Identified |
| 10/28/02 | Legal | Improper information may be published to the public | 2 | Somewhat Unlikely | Critical | B | $5,700 | Internal | Control Use staging servers to keep information separate Follow Quality of Information Guidelines Utilize established agency processes for the quality assurance of information Instill accountability to Project Managers for the content that is provided to the public | Identified |
| 11/6/2002 | Legal | Discussions with the Unions may lead to delays in the process or necessary changes. | 2 | Somewhat Unlikely | Critical | D | $494,000 | Internal | Control Begin the Union discussions early n the process in order to allow for needed changes. | Identified |
| 10/28/02 | Organizational | Redistribution of power within the Department | 2 | 50/50 Chance | Moderate | A | $2,250 | External | Acceptance Accept this risk Avoidance Ensure that a change management component is included in the implementation and rollout | Identified |
| 10/28/02 | Organizational | Agencies or individual employees are resistant to adopt proposed solutions | 1 | 50/50 Chance | Critical | D | $650,000 | External | Control Create and implement a change management plan Ensure compliance with established communication plan to promote and market the benefits of the solution to agencies and employees Include as a part of the Performance Elements | Identified |
| 10/28/02 | Data | Loss of content due to an accident, fire, or other disaster | 3 | Highly Unlikely | Moderate | D | $169,000 | Internal | Avoidance Create backups for content and documents | Identified |
| 10/28/02 | Data | Erroneous deletion or destruction of content | 3 | Somewhat Unlikely | Moderate | A | $950 | Internal | Control Select solution with valid workflow processes and standards for deletion or destruction of content or documents | Identified |
| 10/28/02 | Security | Roles and responsibilities related to the solution are improperly administered | 3 | Somewhat Unlikely | Moderate | D | $494,000 | Internal | Control Involve USDA Cyber Security Office and agency level security office in design and review of solutions Continuously review and update the Security plan Instill accountability to Program Managers | Identified |
| 10/28/02 | Security | Unauthorized users gain access to data or content stored in the solution | 2 | Somewhat Unlikely | Critical | D | $494,000 | Internal and External | Control Involve USDA Cyber Security Office and agency level security office in design and review of solutions Continuously review and update the Security plan Instill accountability to Program Managers Implement sound security plan that includes appropriate firewalls | Identified |
| 10/28/02 | Privacy | Unauthorized users access, use, or disclose private information that is stored in the system. | 2 | Somewhat Unlikely | Critical | D | $494,000 | Internal and External | Avoidance Ensure that the proper policies and practices concerning the protection of privacy information have been implemented through Certification and Accreditation Conduct a Privacy Impact Assessment Identify and register a system of records Control Perform extensive review of content and documents to identify time-sensitive and market-sensitive materials Instill accountability for Program Managers to assign metadata | Identified |
| 11/15/02 | Risks Associated with Contracting to an Application Service Provider | Inability to transfer assets, such as equipment, facilities, and licenses, from USDA to the application service provider | 1 | 50/50 Chance | Critical | D | $650,000 | Internal and External | Control Jointly define a migration plan to estimate the time and costs associated with preparing the environment | Identified |
| 11/15/02 | Risks Associated with Contracting to an Application Service Provider | Inability to acquire the skills or resources necessary to manage the provisions of the service contract | 1 | Somewhat Likely | Critical | C | $39,375 | Internal | Control Develop and implement a Service Level Agreement (SLA) with the application service provider to ensure expectations are met. Include penalties to the provider for non-compliance. Create a group specifically responsible for vendor management activities. | Identified |
| 11/15/02 | Risks Associated with Contracting to an Application Service Provider | Lack of control over skills and resources as well as quality and performance of the application service provider | 2 | 50/50 Chance | Moderate | C | $31,250 | External | Avoid Develop and implement a Service Level Agreement (SLA) with the application service provider to ensure quality expectations are met. The SLA should explicitly state the number of resources required to support operations. | Identified |
| 11/15/02 | Risks Associated with Contracting to an Application Service Provider | Issue identification and resolution are not achieved in a timely manner due to unresponsiveness of the application service provider | 2 | 50/50 Chance | Moderate | C | $31,250 | External | Avoid Develop and implement a Service Level Agreement (SLA) with the application service provider that includes issue management policies and procedures as well as provider penalties for non-compliance. | Identified |