MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 17-21, 2003

Date:	March 21, 2003

Highlights:

Highlights for the week included:  (1) conditioning of the gun ceramic stack assembly up to

430 kV; (2) qualification and installation prep for 3 of the remaining 5 dipole magnets in the 2nd recirculation arc; and (3) successful turn-around of the injector cryounit by the SRF crew after last week’s warm window problems.

Commissioning Activities:

Electron Beam Transport:

Two GQ’s and 1 GX are ready for installation on Monday.  The 2nd GX magnet and the last magnet to complete the 2nd recirculation arc (GY) are both on the measurement stands.

Optical Systems:

Commissioning of the optical cavity assemblies continues. The diagnostic system that monitors the outcoupler optical cavity was moved into place.

Instrumentation and Controls:

All trim magnet power supply systems for all installed magnet systems were exercised.  A problem in the gun HVPS was diagnosed as a beating problem between the two 5 mA stacks.

One stack was disconnected to allow the successful high voltage conditioning of the gun ceramic stack assembly.

Photoelectron Gun:

Successful conditioning of the ceramic stack assembly and high voltage transmission line of the gun to 430 kV.

Special Meeting Notices:

FEL Upgrade Cost and Schedule Teleconference:  March 24, 2003 : 0800

(ONR invitees only)

FEL IR/UV Upgrade Semiannual Review:  April 9-10, 2003

At Jefferson Lab (ONR/AFRL/DOE invitees only)

Management:

This week we hosted our annual FEL Users Meeting and Laser Processing Consortium Workshop on March 19-20.  It was a successful and well attended meeting.  We had 113 registrants (71 from universities, 28 from the National labs and 13 from industry).  The program is listed on our web site and we will be adding copies of the presentations.  In parallel with this meeting, the joint UVA/NSU/JLab IGERT program sponsored by NSF was held.  This brought more than 20 student posters to the meeting on laser-materials related science and technology.

We also held meetings of the FEL Program Advisory Committee and the Jefferson Lab Industrial Advisory Board during the User meeting.

We prepared a project status report and financial reports for the ONR, NAVSEA and DOE Program Offices as background material for a conference call scheduled for Monday morning.

WBS 4 (Injector):

The support electrode is ready for re-installation.  The ball electrode is on its final polish step and will be ready next week when we begin final step of the electrode re-assembly.  The internal parts of the electrode structure have all been re-cleaned, and the complicated structure behind the stalk assembly has been re-assembled in a separate vacuum test stand so that the high surface area bellows and wire assemblies can be partially outgassed before the final assembly.  While this electrode preparation has been going on, we have been voltage conditioning the remainder of the gun assembly after a full bakeout cycle was completed last week, and have brought this assembly up to 430 kV as of this writing (1715hrs, March 21), which is the required overhead for operation at our nominal gun voltage of 350 kV At this point we are projecting bakeout of the full gun assembly with the electrode structure during the first week of April and re-start of gun commissioning by mid- April.

WBS 6 (RF):

In the process of testing the injector cryounit last week, we developed a leak in one of the warm rf windows.  The cryounit has since been warmed up, both windows replaced, and the cryounit cooled down to 4K.  We are coordinating cool down to 2K with a needed cool-down of a cryomodule in the main accelerator next week, and then this system will be returned to operability.

WBS 8 (Instrumentation):

Effort continued on the shunt hookup for the Wiggler and Optical Chicane magnets. Communication cabling for the transport system shunts have been pulled in and are being terminated.  The last trim rack (3F region ) is in commissioning.  Wiring of the 896 power supplies continues.

Beam viewers 3F04 - 3F09 have been re-aligned for use with Max Video.  A half rack has been installed next to the High Reflector which will house instrumentation and controls ports for Optics use.

The final punch list for the 4F vacuum region is underway.  This includes installing the three position mirror assembly for the Happek device.  The Happek is used for optimizing (minimizing) bunch length at the wiggler.

The firmware programming for the duty-factor calculation board [for the dlpc/mps system] is ready to be embedded and tested.  The duty factor calculation board has been built and is ready to be programmed and tested.

A Quarterly EH & S inspection was conducted on Tuesday.  With few exceptions, we came through with flying colors.  A list of items being tracked will be available early next week.  One noted problem is the ongoing water leaks at both ends of the tunnel.  Repeated attempts by Plant Services to plug the leaks have been unsuccessful.  Also repeated attempts to keep one of the safety system doors from sticking and preventing the maglock from energizing, have failed.  We need to elevate our concerns for these two annoying problems.

WBS 9 (Transport):

Work Arounds

Substitution of IR Demo 180° Bend (DY) for the Upgrade 180° Bend (GY) in the First Arc and installation of a GW beyond the Optical Klystron as a diverter-to-the-dump magnet

•	In order to add more resistance to the circuit, we are working to connect two of the IR Demo’s DU, Injector dipoles in series with the temporary diversion dipole at the end of the optical cavity.  This will allow the magnet power supply to deliver the required 100 A.

Dipoles

Optical Chicane Dipoles (GW)

•	No progress.

Injector Dipoles (DU/DV)

•	No progress

Arc 180 Degree Dipoles (GY)

•	The machinists of the JLab Shop continued their very competent job as they commissioned the measurement apparatus for the GY dipole.  They refurbished the probe motion mechanism that allows both circular (through the arc) and straight (for measuring the ends) motion.  They aligned the apparatus to the magnet within .003 inches.

•	The machinists made a new probe holder for the two NMR and two Hall probes that move to seven positions across the width of the good field region.  These readings will match the series of readings taken on the similar, one meter radius, Pi Bend (DY) dipoles of the IR Demo.  The transverse distance between readings will be 50 % larger in order to accommodate the wider 8 inch wide good field region.  Fortunately this pattern of readings allows the use of the spreadsheet developed for the DY measurement.  Ken Baggett, who is on loan from the Alignment Group, finished massaging the spreadsheet to bring it up to date for GY measurements.

•	Measurement of the GY started.  After battling control problems and safety paperwork, Bill Merz, Kevin Jordan and Tom Hiatt got the newly installed 66 KW power supply to respond to control commands.  This supply has the current and voltage capability to fully test the GY.

•	Wang NMR continued potting the coils for the second dipole.

Arc Bend & Reverse Bend Dipoles (GQ, GX)

•	The second last GX magnet passed preliminary qualification measurements with core field matching the first GX to 1.5 parts in 10,000.  Specification is 10 parts in 10,000.

•	Tests of the final GX Dipole started this week.  We were able to do this because replacement GX coil from Wang NMR arrived in time.  The JLab Shop machinists again helped us out, taking the GX dipole apart and replacing the leaking coil and putting the magnet back together.  Note, because the coil was partially made from recycled copper from the first GY coil its dimensions were 0.25 inches too wide.  In a very quick maneuver, the machinists removed that amount of material from the inside of the small return leg and replaced it with a shim plate on the outside of the return leg.  This should have no effect on field quality.

•	Installation of the two GQ dipoles and one GX could have started on Thursday but a combination of heavy rain and critical work in bringing the CEBAF accelerator back up from the down period prevented Neil Wilson’s crew from doing this work.  Installation is scheduled for Monday.

Quadrupoles

Trim Quad (QT)

•	The vertical corrector function (GC) in the two Trim Quadrupoles (QTs) for the second arc was verified.  They will be installed on Monday.

Sextupole (SF)

•	No news.

Octupole (OT)

•	The order is ready to be placed anticipating the next batch of commissioning money.

Correctors

•	The coils for the horizontal optical chicane corrector (GZ) were made by Hiroyuki Toyokawa and he installed them in the third Optical Chicane Dipole (GW).  He is working on the connection of the series of parallel wires into form the coils on the magnet.

•	Jeff Dail of the JLab Shop completed the fixtures for making the GA vertical corrector and will start winding as soon as we get the epoxy.

WBS 11 (Optics):

We worked late last Friday to install a motor with a working encoder and pumped down the vacuum vessel over the weekend.  This put us back on track to run the leadscrews of both the HR and OC, so as to initiate the in-vacuo lubrication process we previously demonstrated on the HR assembly.  In the process, we discovered that some of the stepper motor drivers had been changed, and certain parameters didn't match what the software was indicating.  The I&C group swung into action and helped get that straightened out.  We then found that the drag torque on the OC was quite high, and finally resulted in the stepper motor shaft slipping on the flexible bellows coupling clamp.  We had a fixture made to measure the torque in-situ(without venting the vacuum vessel), and we'll use it to determine what's wrong and fix it.  We also made plans to modify the flexible bellows coupling and the motor shaft to accept a pin to make the coupling more robust.   We worked to get the ultraviewer mounted near the HR assembly aligned and working.  By midweek, we were aligned to the OC.  In the process, we confirmed that the clips that retained the mirror on the ultraviewer were pressing too hard on it, and we were aberrating the beam.  New clips have been designed and submitted for fabrication.  We'll have them early next week, and will install them while vacuum work is being conducted on the beamline. The OCMMS optical assembly that monitors the OC was moved into position.  The HR OCMMS optical assembly is being assembled and aligned, and will be moved into the vault next week.

We received word that the oscillator for the advanced drive laser, a custom system built by Time-Bandwidth Products, will be delivered and installed in the beginning of April.  The laser appears to be exceeding the specified output by almost a factor of two.  Once it is installed and qualified, we look forward to receiving follow-on funding to purchase the amplifiers for the laser in order to complete the laser system.  Several of us gave presentations at the LPC meeting.  We assisted the Hall C installation staff by loaning them a 6" gate valve.