MEMORANDUM

To:	Distribution

From:	F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 24-28, 2003

Date:	March 28, 2003

Highlights:

Three of the four second arc vacuum chambers were set in the magnets with the fourth scheduled for early next week.

A test of 800 MeV energy recovery is proceeding well on the CEBAF accelerator.  This test is complimentary to the high current energy recovery demonstration on the FEL and will establish a strong case for ERLs.

First light diagnostics installation punch list was completed with the installation of viewers in both the optical chicane and the first pi bend.

Special Meeting Notices:

FEL IR/UV Upgrade Semiannual Review:  April 9-10, 2003

At Jefferson Lab (ONR/AFRL/DOE invitees only)

Management:

We held a teleconference with ONR to review technical progress and financial status and resolve any issues which might be holding up signature of our MOU and release of remaining FY03 funds.  Commissioning is meeting the schedule presented at the last review with the exception of a 2 week delay in the installation of the final arc magnet and the delay in gun startup which is now expected around April 15.  The budget is exactly on track with our projections.

Adm. Cohen presented the ONR FY04 plan to the House Armed Services Committee.  Our JLab poster was one of three displayed for the committee.  In attendance were technical heads of all the branch services.

A Statement of Work, cost, and schedule were prepared for ONR/Dahlgren for a follow-on effort for the laser materials damage tests by establishing an effects lab with a wind tunnel.

An agenda for our Semiannual Review on April 9-10 was prepared and circulated to the speakers and program office.  We began reviewing the team's presentations for that review.

WBS 4 (Injector):

The ceramic stack was run up to 400 kV with the running resistor completing the check out of the dual resistor transmission line.  The ball cathode and support tube have been repolished to 1um and are being cleaned.  A preassembly bake of gun subassembly parts is being done after solvent cleaning.

Gun HVPS - Operated the Gun's HVPS to 572 kV.  The Conditioning Resistor was operated to 450 kV.  Its resistance has dropped to 144 M Ohms.  The Running Resistor was operated to 400 kV.  These parameters are sufficient for first light operations.  Noise was also noted on the current measure and voltage ripple monitor ports.  The current noise was about 300 uamps for 2 stack operation.  Two stacks are required for operations above 5 ma of e-beam current.  Discussions are ongoing with the vendor concerning this noise.

WBS 6 (RF):

Zone 1 - Completed the tuning and started the re-checkout of the Quarter.

WBS 8 (Instrumentation):

A pair each of the demo DU magnets have been placed at the Injection, Extraction and temporary dump magnet strings to increase the load on the 5kW power supplies.  Water, power and thermal interlock installation has been completed.  The 8 floating trim power supplies are being built up.  They will initially run with a 12 bit, MVME 628 DAC, when the new "Analog Block" is complete they will be reworked and achieve higher accuracy.  The high voltage power supply was characterized for current vs. voltage for operation with a single stack and with both HV stacks connected.  The new analog control card was also installed and calibrated.

Final checkout of the vacuum system is being done.  This includes operating the valves both locally and through EPICS.  The NEGs on the differential pumping station downstream from the cryomodule is being reactivated (region recirc dump).

Video Selection System - Documentation of the current system configuration and the plans to upgrade the system with the vault patch panels has been updated.  The vault patch panels are essentially copies of the patching system we currently use in each user lab except that they have three video monitoring points. There are currently four of these I & C stations with video patch panels being implemented.  One in the Injector area and three for the optical transport regions, namely the high reflector mirror assembly, the output coupler assembly and the wiggler region. These control stations are essential for the routine diagnostics of the machine.  Upstairs, all the new video cables currently installed are terminated and are being dressed in to the main video system (FL02B09).  The I & C stations will also hold the Radiation Rapid Access Control hardware and an assortment of analog I/O for general purpose use.

MPS/DLPC Integration - The digital integrator module for upgrading the drive laser's duty factor interlock is running in the test crate (IOCFELT2) in Lab 5.  It is communicating properly with the IOC and the duty factor permit function is being checked-out.

Additional beamviewer cameras have been built to support installation of the paddle viewers in the arc.  Lab stock is being sorted and organized so we are ready for maintenance when the time comes.

The following drawings were completed this week: F0117 VME Interface Board, F0119 8 Channel Digital Interface Module, F0190 HV Interlock Analog I/O, F0191 MPS Comparator Module, F0193 (RevA) User Lab Patch Panel, F0182 (RevA) HV Interlock Chassis Rear Panel Fabrication.  Again, thanks to EECAD for their support in getting these drawings done and to Document Control.

WBS 9 (Transport):

Work Arounds

Substitution of IR Demo 180° Bend (DY) for the Upgrade 180° Bend (GY) in the First Arc and installation of a GW beyond the Optical Klystron as a diverter-to-the-dump magnet

•	We added more resistance to the circuit, of the temporary diversion dipole at the end of the optical cavity. We tested the power supply and it is qualified for full current.

Dipoles

Optical Chicane Dipoles (GW)

•	No progress.

Injector Dipoles (DU/DV)

•	We added resistance (using two IR Demo DU magnets) to this circuit.  The injection circuit qualified for full current.

Arc 180 Degree Dipoles (GY)

•	The machinists of the JLab Shop finished commissioning the measurement apparatus for the GY dipole and did some of the measurement at the 145 MeV/c level.

•	Preliminary data indicates field uniformity at 145 MeV/c of ± 2 parts in 10,000 and a core field that needs only 0.5% shunting to match the GQ/GX family.  Core field at 80 MeV/c needs about 1.6 % shunting to match.  All these values better than or adequately close to specification.  80 MeV/c measurements are being taken as this is written.

•	Wang NMR is having difficulty potting the first coil of the second dipole.  The mold was not vacuum tight and had to be disassembled and resealed.  They plan to pot as this is being written.

Arc Bend & Reverse Bend Dipoles (GQ, GX)

•	The last GX magnet passed preliminary qualification measurements at 145 and 80 MeV/c in the IR configuration. Specification is 10 parts in 10,000.  Readings are being taken of the UV configuration as I write.

•	Late last Friday, the preliminary data showing core field 0.75 % low led us to take resistance readings that discovered the new, lower coil indicates one shorted turn.  We replaced the coil with the original coil after testing for and finding no leaks, even at 500 psi.  We are puzzled by the finding but decided to use the coil anyhow.  This enabled the reading above.

•	A 1.5 day delay in testing the last GX was caused by the same phase mismatch trips we have had in the power supply throughout the testing period.  Fortunately, these trips were not intermittent as they had been in the past and the power supply group had diagnostics in place.  They appear to have finally fixed the problem.

•	We installed the two GQ dipoles and one GX with two of the vacuum chambers.

Quadrupoles

Trim Quad (QT)

•	The QTs were hooked to their power supplies.

Sextupole (SF)

•	No news.

Octupole (OT)

•	The order is ready to be placed anticipating the next batch of commissioning money.

Correctors

•	Hiroyuki Toyokawa is still working on the connection of the series of parallel wires into form the coils of the GZ horizontal corrector within the third GW dipole of the Optical Chicane.

•	Jeff Dail of the JLab Shop started winding the coils of the GA vertical corrector of the Optical Chicane.

WBS 11 (Optics):

We found the problem with the OC leadscrew (a loose fastener had caused binding in the leadscrew) and fixed it.  We pulled a vacuum on the OC vacuum vessel and verified that a) it as running correctly in both directions and b) that the Vespel nut was lubricating, and thus reducing the drag torque.  We received new mirror retaining clips for the thicker ultraviewer mirrors we're using, and verified they can be installed in such a way as to not affect mirror figure.  We quickly changed out the ultraviewer mirror and clips, however we still have some problems to resolve.  Nevertheless, it is improved, allowing us to begin optical cavity alignment in earnest; first aligning an external HeNe through the outcoupler and the center wiggler viewer.  Using that, we roughly (to a few 100 urad) aligned the 3" and 2" OC mirrors.  We then used the ultraviewer next to the HR assembly to align the 2" OC mirror.  By early pm Friday, we were working on aligning the 3" OC mirror, and will then align the OC OCMMS optics.  We've also been running repeatability tests and LVDT calibrations when the vault is locked up, or at night, so we've made a lot of progress this week.  All this work on the OC assembly required the help of the staff member working on the HR OCMMS optical assembly, so it's progress had to be slowed.  We anticipate installing it in the vault next week.

Other activities:

We began preparing presentations for the Navy semi-annual review.