## Equipment Spending 4-00
EQUIPMENT SPENDING THROUGH END APRIL '00
|  | COST | YTD | PRIOR YRS | CONTRIB | PROJECT |  | Committee | ETC +
WBS | DESCRIPTION | EST | OBLIG | OBLIG | (NON-DoE) | BALANCE | D0 cont | Cont | Cont
1 | TOTAL DZERO UPGRADE EQUIPMENT | 41593169.962 | 3077365.095 | 33989153.7102 | 1441946 | 3104705.1568 | 528000 | 728050 | 0
1.1 | TRACKING DETECTORS | 20097606.54 | 2136695.24 | 16773014.511 | 20000 | 1187896.789 | 435000 | 484000 | 0
1.1.1 | SILICON TRACKER | 7857073.3 | 1106995.56 | 6166133.568 | 20000 | 583944.172 | 230000 | 231000 | 0
1.1.1.1 | Engineering & Design | 525541 | 4959.52 | 504478.356 | 20000 | 16103.124 | 0 | 0 | 0
1.1.1.1.1 | SVX II engineering | 157500 | 0 | 157500 |  | 0
1.1.1.1.2 | MOSIS submission | 55000 | 0 | 55000 |  | 0
1.1.1.1.3 | UTMC submission | 113600 | 0 | 113600 |  | 0
1.1.1.1.4 | HDI engineering | 0 | 0 | 0 |  | 0
1.1.1.1.5 | Test readout system | 199441 | 4959.52 | 178378.356 | 20000 | 16103.124
1.1.1.2 | Disks | 1407507 | 62726.94 | 1353291.584 | 0 | -8511.524 | 0 | 36000 | 0
1.1.1.2.1 | F disk | 859485 | 43206.61 | 829143.904 | 0 | -12865.514 | 0 | 36000 | 0
1.1.1.2.1.1 | F wedge detectors | 539365 | 0 | 539365 |  | 0
1.1.1.2.1.2 | F wedge berylium | 24580 | 0 | 24580.24 |  | -0.24
1.1.1.2.1.3 | Probe testing | 51904 | 31275 | 36908.2 |  | -16279.2
1.1.1.2.1.4 | F disk fixtures | 25695 | 2591.91 | 25033.26 |  | -1930.17
1.1.1.2.1.5 | F wedge fabrication | 23604 | 5517.62 | 12435.844 |  | 5650.536
1.1.1.2.1.6 | F Disk Support | 128292 | 3822.08 | 124776.36 |  | -306.44
1.1.1.2.1.7 | F wedge det. spares | 66045 | 0 | 66045 |  | 0
1.1.1.2.2 | H disk | 460986 | 19520.33 | 437112.13 | 0 | 4353.54 | 0 | 0 | 0
1.1.1.2.2.1 | H wedge detectors | 278950 | 14750 | 264200 |  | 0
1.1.1.2.2.2 | Probe testing | 12000 | 0 | 12000 |  | 0
1.1.1.2.2.3 | H wedge substrate | 43061 | 350 | 42711.25 |  | -0.25
1.1.1.2.2.4 | H disk fixtures | 19740 | 873.41 | 17251.61 |  | 1614.98
1.1.1.2.2.5 | H wedge fabrication | 44026 | 3285.92 | 37740.14 |  | 2999.94
1.1.1.2.2.6 | H Disk Support | 63209 | 261 | 63209.13 |  | -261.13
1.1.1.2.3 | Spares | 87036 | 0 | 87035.55 |  | 0.45
1.1.1.3 | Barrels | 2567736.3 | 168844.39 | 2370906.21 | 0 | 27985.7 | 0 | 175000 | 0
1.1.1.3.1 | Single Sided | 218162 | 0 | 218162 |  | 0
1.1.1.3.2 | Single Sided Spares | 284803 | 14000 | 270802.7 |  | 0.3
1.1.1.3.3 | 2 Degree | 1034747 | 141296.71 | 907546.74 |  | -14096.45
1.1.1.3.5 | 90 Degree | 395307 | 2000 | 373307 |  | 20000 |  | 175000
1.1.1.3.7 | Probe Testing | 209647 | 237 | 206542.06 |  | 2867.94
1.1.1.3.8 | Berylium substrates | 138450 | 0 | 138449.7 |  | 0.3
1.1.1.3.9 | Ladder Fixtures | 47028 | 9428.68 | 36975.72 |  | 623.6
1.1.1.3.10 | Barrel assembly fixtures | 23523 | 456 | 8509.5 |  | 14557.5
1.1.1.3.11 | Ladder fabrication | 38791 | 1426 | 33332.49 |  | 4032.51
1.1.1.3.12 | Bulkheads | 177278.3 | 0 | 177278.3 |  | 0
1.1.1.4 | Readout IC's | 578724 | 39741.25 | 526868.6 | 0 | 12114.15 | 0 | 0 | 0
1.1.1.4.1 | F disk | 155957 | 655.25 | 155302 |  | -0.25
1.1.1.4.2 | H disk | 88744 | 0 | 88744 |  | 0
1.1.1.4.3 | Layer 1 | 27733 | 0 | 27733 |  | 0
1.1.1.4.4 | Layer 2 | 49919 | 0 | 49919 |  | 0
1.1.1.4.5 | Layer 3 | 55465 | 0 | 55465 |  | 0
1.1.1.4.6 | Layer 4 | 99837 | 0 | 99837 |  | 0
1.1.1.4.7 | Chip testing | 37869 | 3086 | 22868.6 |  | 11914.4
1.1.1.4.8 | Spares | 63200 | 36000 | 27000 |  | 200
1.1.1.5 | Readout System (Detector to Port Card) | 2622983 | 789062.11 | 1366222.238 | 0 | 467698.652 | 180000 | 20000 | 0
1.1.1.5.1 | Disk HDI | 150419 | 20535 | 129883.85 |  | 0.15
1.1.1.5.2 | Barrel HDI | 347449 | 33845 | 309453.66 |  | 4150.34 |  | 10000
1.1.1.5.3 | HDI assembly and test | 344216 | 85124.86 | 250216.398 |  | 8874.742 |  | 10000
1.1.1.5.4 | Low Mass Cables | 682034 | 559316.2 | 121673.13 |  | 1044.67 | 80000
1.1.1.5.5 | High Mass Cables | 425736 | 30506.8 | 363885.14 |  | 31344.06
1.1.1.5.6 | Transition Card | 113460 | 16579.22 | 7460 |  | 89420.78 | 20000
1.1.1.5.7 | Bias Voltage System | 80669 | 468 | 35669.06 |  | 44531.94
1.1.1.5.8 | Interface board | 479000 | 42687.03 | 147981 |  | 288331.97 | 80000
1.1.1.6 | Mechanical Support, Services | 114582 | 39341.75 | 44366.58 | 0 | 30873.67 | 20000 | 0 | 0
1.1.1.6.1 | Half-cylinder | 32000 | 8471.05 | 11520 |  | 12008.95
1.1.1.6.2 | Installation fixtures | 10000 | 0 | 0 |  | 10000
1.1.1.6.3 | Cooling system | 42582 | 14274.99 | 27581.58 |  | 725.43
1.1.1.6.4 | Air system | 10000 | 4857.21 | 0 |  | 5142.79
1.1.1.6.5 | Monitoring system | 20000 | 11738.5 | 5265 |  | 2996.5
1.1.1.7 | Detector Assembly, Installation | 40000 | 2319.6 | 0 | 0 | 37680.4 | 30000 | 0 | 0
1.1.1.7.1 | Silicon install fixturing | 15000 | 0 | 0 |  | 15000
1.1.1.7.2 | Silicon Supports | 15000 | 2319.6 | 0 |  | 12680.4
1.1.1.7.3 | Installation services | 10000 | 0 | 0 |  | 10000
1.1.2 | FIBER TRACKER | 7774348.1 | 594913.29 | 6976329.418 | 0 | 203105.392 | 100000 | 253000 | 0
1.1.2.2 | Scintillating Fiber Ribbons | 996398.5 | 132494.84 | 860418.44 | 0 | 3485.22 | 0 | 3000
1.1.2.2.1 | Scintillating Fibers | 443449 | 0 | 443449 | 0 | 0
1.1.2.2.1.1 | Scintillating Fibers | 433449 | 0 | 433449 |  | 0
1.1.2.2.1.2 | Scintillating Fiber QC | 10000 | 0 | 10000 |  | 0
1.1.2.2.2 | Ribbons | 6000 | 0 | 2990.26 |  | 3009.74 |  | 3000
1.1.2.2.3 | Connectors | 255995 | 123848.75 | 134036.81 |  | -1890.56
1.1.2.2.4 | Aluminization | 12308 | 3035.88 | 9272 |  | 0.12
1.1.2.2.5 | Ribbon Machine/molds | 121857.5 | 0 | 121857.5 |  | 0
1.1.2.2.6 | Ribbon QC test box | 23244 | 0 | 23243.85 |  | 0.15
1.1.2.2.7 | Ribbon laying & fixturing | 116063 | 2290.21 | 111407.02 | 0 | 2365.77
1.1.2.2.7.1 | Ribbon Laying Fixturing | 116063 | 2290.21 | 111407.02 | 0 | 2365.77
1.1.2.2.7.1.1 | Ribbon Laying Fixturing Parts | 96823 | 2290.21 | 94533.02 |  | -0.23
1.1.2.2.7.1.2 | Ribbon Laying Fixturing Shop Chrgs | 19240 | 0 | 16874 |  | 2366
1.1.2.2.8 | Ribbon/Waveguide Connectorization | 17482 | 3320 | 14162 |  | 0
1.1.2.3 | Clear Waveguides | 1145142 | 167585 | 973837.93 | 0 | 3719.07 | 25000 | 0
1.1.2.3.1 | Clear Fiber | 798563 | 95000 | 703563 |  | 0
1.1.2.3.2 | Connectors A | 126000 | 70085 | 52195.85 |  | 3719.15
1.1.2.3.3 | Connectors B | 0 | 0 | 0 |  | 0
1.1.2.3.4 | Sheathing | 18000 | 0 | 18000 |  | 0
1.1.2.3.5 | Factory setup | 33650 | 2500 | 31150.08 |  | -0.08
1.1.2.3.6 | Test/QC system | 26429 | 0 | 26429 |  | 0
1.1.2.3.7 | Fabrication/testing | 142500 | 0 | 142500 |  | 0
1.1.2.4 | Visible Light Photon Counter Cassette | 4755314 | 32926.5 | 4673989.266 | 0 | 48398.234 | 25000 | 250000
1.1.2.4.1 | Production cassettes | 4627275 | 32926.5 | 4545950.256 | 0 | 48398.244 | 25000 | 250000
1.1.2.4.1.1 | VLPC Hybrids | 3158000 | 0 | 3158000 |  | 0
1.1.2.4.1.2 | Cassette Mechanical Parts | 565602 | 32926.5 | 509277.456 |  | 23398.044
1.1.2.4.1.3 | Cassette Electrical Connectors | 220132 | 0 | 220131.8 |  | 0.2
1.1.2.4.1.4 | Cassette Flex Circuits | 552241 | 0 | 527241 |  | 25000 |  | 250000
1.1.2.4.1.5 | Cassette Internal Fiber | 131300 | 0 | 131300 |  | 0
1.1.2.4.2 | VLPC Test Cassettes | 128039 | 0 | 128039.01 |  | -0.01
1.1.2.5 | Visible Light Photon Counter Cryogenics | 346007.6 | 131803.29 | 127732.7 | 0 | 86471.61 | 10000
1.1.2.5.1 | Test Cryostat | 19117.6 | 0 | 19117.8 |  | -0.2
1.1.2.5.2 | Final Cryostat System | 210290 | 131803.29 | 25970.92 | 0 | 52515.79
1.1.2.5.2.1 | Raw Materials | 46119 | 22706.85 | 25970.92 |  | -2558.77
1.1.2.5.2.2 | Machining and Construction | 104171 | 86274.38 | 0 |  | 17896.62
1.1.2.5.2.3 | Intercepts, Shields, Insulation, Vacuum | 25000 | 11819.08 | 0 |  | 13180.92
1.1.2.5.2.4 | Top Lid Heater and Controls | 20000 | 10356.64 | 0 |  | 9643.36
1.1.2.5.2.5 | Relief and Check Valves and Fasteners | 15000 | 646.34 | 0 |  | 14353.66
1.1.2.5.3 | Helium Distribution System | 70836 | 0 | 60836.1 | 0 | 9999.9
1.1.2.5.3.1 | Detector Valve Box, Bayonet Cans | 45021 | 0 | 45021.1 |  | -0.1
1.1.2.5.3.2 | Transfer Lines | 25815 | 0 | 15815 |  | 10000
1.1.2.5.4 | Cryostat Installation | 10000 | 0 | 0 | 0 | 10000
1.1.2.5.4.1 | Staging Stands, Roll in Plates | 5000 | 0 | 0 |  | 5000
1.1.2.5.4.2 | Movement Mechanisms | 5000 | 0 | 0 |  | 5000
1.1.2.5.5 | Temperature Controller | 35764 | 0 | 21807.88 | 0 | 13956.12
1.1.2.5.5.1 | Cryostat Sensors | 20764 | 0 | 15764.08 |  | 4999.92
1.1.2.5.5.2 | Cassette Controller Mods, Power Supp. | 15000 | 0 | 6043.8 |  | 8956.2
1.1.2.6 | Calibration System | 107000 | 67500 | 39000 | 0 | 500 | 10000
1.1.2.6.1 | Optical Panels and LEDs | 14000 | 7500 | 6000 |  | 500
1.1.2.6.2 | Support Structure for Optical Panels | 2000 | 0 | 2000 |  | 0
1.1.2.6.3 | Drive Electronics | 50000 | 38000 | 12000 | 0 | 0
1.1.2.6.3.1 | Driver chips | 4000 | 3000 | 1000 |  | 0
1.1.2.6.3.2 | Receiver chips | 4000 | 3000 | 1000 |  | 0
1.1.2.6.3.3 | DACs | 4000 | 3000 | 1000 |  | 0
1.1.2.6.3.4 | Passive components | 8000 | 6000 | 2000 |  | 0
1.1.2.6.3.5 | Circuit boards | 20000 | 15000 | 5000 |  | 0
1.1.2.6.3.6 | Board assembly | 10000 | 8000 | 2000 |  | 0
1.1.2.6.4 | Pulsing Electronics | 5000 | 5000 | 0 |  | 0
1.1.2.6.5 | Cabling, connectors | 5000 | 5000 | 0 |  | 0
1.1.2.6.6 | Power supplies | 2000 | 2000 | 0 |  | 0
1.1.2.6.7 | Computer control (VME interface) | 10000 | 10000 | 0 |  | 0
1.1.2.6.8 | Data storage (disks) | 0 | 0 | 0 |  | 0
1.1.2.6.9 | Design/fabrication/testing | 19000 | 0 | 19000 |  | 0
1.1.2.7 | Mechanical Support, Services | 395986 | 61610.56 | 301351.082 | 0 | 33024.358 | 10000
1.1.2.7.1 | Support cylinders | 296845 | 3423.68 | 284491.422 | 0 | 8929.898
1.1.2.7.1.1 | Cylinder Materials | 160681 | 814.98 | 159866.414 |  | -0.394
1.1.2.7.1.2 | Mandrels | 55421 | 2443.7 | 52977 |  | 0.3
1.1.2.7.1.3 | End Rings | 50000 | 0 | 41070 |  | 8930
1.1.2.7.1.4 | Construction Tooling | 30743 | 165 | 30578.008 |  | -0.008
1.1.2.7.2 | Cylinder Coupling Supports | 84141 | 58186.88 | 12859.66 | 0 | 13094.46
1.1.2.7.2.1 | OD Rings | 3000 | 0 | 1705.46 |  | 1294.54
1.1.2.7.2.2 | Disks | 17500 | 5700 | 0 |  | 11800
1.1.2.7.2.3 | Fixturing | 63641 | 52486.88 | 11154.2 |  | -0.08
1.1.2.7.3 | External Supports | 5000 | 0 | 0 |  | 5000
1.1.2.7.4 | Purge gas system | 10000 | 0 | 4000 |  | 6000
1.1.2.8 | Detector Assembly | 28500 | 993.1 | 0 | 0 | 27506.9 | 20000
1.1.2.8.1 | Waveguide install fixturing | 10000 | 993.1 | 0 |  | 9006.9
1.1.2.8.2 | Survey fixturing | 10000 | 0 | 0 |  | 10000
1.1.2.8.3 | Tracker installation fixtures | 8500 | 0 | 0 |  | 8500
1.1.3 | CENTRAL PRESHOWER DETECTOR | 238167.84 | 0 | 228176.21 | 0 | 9991.63
1.1.3.1 | Engineering & Design | 0 | 0 | 0 | 0 | 0
1.1.3.1.1 | Mechanical Support | 0 | 0 | 0 |  | 0
1.1.3.1.2 | Signal Electronics | 0 | 0 | 0 |  | 0
1.1.3.2 | Scintillator Extrusion | 35680.34 | 0 | 35680.34 | 0 | 0
1.1.3.2.1 | Polystyrene | 5701 | 0 | 5701 |  | 0
1.1.3.2.3 | Compounding | 3179.34 | 0 | 3179.34 |  | 0
1.1.3.2.4 | Die | 11200 | 0 | 11200 |  | 0
1.1.3.2.5 | Extrusion Service | 15600 | 0 | 15600 |  | 0
1.1.3.3 | Strip Preparation | 10000 | 0 | 10000 | 0 | 0
1.1.3.3.1 | Wrapping | 10000 | 0 | 10000 |  | 0
1.1.3.4 | Fiber & Connectors | 50117 | 0 | 50117.13 | 0 | -0.13
1.1.3.4.1 | WLS Fiber | 24660 | 0 | 24660 |  | 0
1.1.3.4.2 | Silvering | 5000 | 0 | 5000 |  | 0
1.1.3.4.3 | Connectors (WLS fiber side) | 7540 | 0 | 7540 |  | 0
1.1.3.4.4 | Fiber/connector assembly | 2467 | 0 | 2467.13 |  | -0.13
1.1.3.4.6 | Fiberguide material | 1000 | 0 | 1000 |  | 0
1.1.3.4.7 | Fiberguide machining | 6000 | 0 | 6000 |  | 0
1.1.3.4.8 | Shipping & handling | 1450 | 0 | 1450 |  | 0
1.1.3.4.9 | Supplies | 2000 | 0 | 2000 |  | 0
1.1.3.5 | Detector Modules | 99306.5 | 0 | 99306.74 | 0 | -0.24
1.1.3.5.1 | Strongback material/skin | 28064.5 | 0 | 28064.5 |  | 0
1.1.3.5.2 | Mounting fixtures | 4155 | 0 | 4155 |  | 0
1.1.3.5.3 | Slumping press and shape formation | 17180 | 0 | 17180 |  | 0
1.1.3.5.4 | Assembly tables and setups | 9221 | 0 | 9220.79 |  | 0.21
1.1.3.5.5 | Alignment jigs and tools | 4000 | 0 | 4000 |  | 0
1.1.3.5.6 | Vacuum bagging system | 4000 | 0 | 4000 |  | 0
1.1.3.5.7 | Glue and syringes | 3283 | 0 | 3283 |  | 0
1.1.3.5.8 | Detector assembly | 14021 | 0 | 14021 |  | 0
1.1.3.5.9 | Quality control/monitoring | 7112 | 0 | 7112 |  | 0
1.1.3.5.10 | Storage & shipping fixture | 3392 | 0 | 3392.45 |  | -0.45
1.1.3.5.11 | Assembly supplies | 3633 | 0 | 3633 |  | 0
1.1.3.5.12 | Shipping & handling | 1245 | 0 | 1245 |  | 0
1.1.3.6 | Clear Waveguides | 17242 | 0 | 17250 | 0 | -8
1.1.3.6.1 | Clear Waveguide | 1350 | 0 | 1350 |  | 0
1.1.3.6.2 | Connectors (detector side) | 7540 | 0 | 7540 |  | 0
1.1.3.6.3 | Connector Tooling and Supplies | 8352 | 0 | 8360 |  | -8
1.1.3.7 | VLPC Cassettes (in WBS1.1.2.4) | 0 | 0 | 0 |  | 0
1.1.3.8 | Calibration System | 20042 | 0 | 15822 | 0 | 4220
1.1.3.8.1 | Blue LEDs and Power Supply | 10000 | 0 | 10000 |  | 0
1.1.3.8.2 | Light bar (material/machining) | 42 | 0 | 42 |  | 0
1.1.3.8.3 | Temperature monitor system | 2000 | 0 | 2000 |  | 0
1.1.3.8.4 | Mounting/tooling fixture | 3000 | 0 | 3000 |  | 0
1.1.3.8.5 | Controller | 5000 | 0 | 780 |  | 4220
1.1.3.9 | Detector Assembly | 5780 | 0 | 0 | 0 | 5780
1.1.3.9.1 | Mounting/alignment tooling | 4075 | 0 | 0 |  | 4075
1.1.3.9.2 | Lead rework/install | 1705 | 0 | 0 |  | 1705
1.1.4 | FORWARD PRESHOWER DETECTOR | 524313 | 14057.5 | 500313.395 | 0 | 9942.105 | 5000
1.1.4.1 | Engineering & Design | 0 | 0 | 0 | 0 | 0
1.1.4.1.1 | Engineering design | 0 | 0 | 0 |  | 0
1.1.4.2 | Scintillator Extrusion | 42342 | 0 | 42342.59 | 0 | -0.59
1.1.4.2.1 | Polystyrene | 8377 | 0 | 8377 |  | 0
1.1.4.2.2 | Fluor | 9822 | 0 | 9822.1 |  | -0.1
1.1.4.2.3 | Compounding | 6689 | 0 | 6689.41 |  | -0.41
1.1.4.2.4 | Die | 4412 | 0 | 4412 |  | 0
1.1.4.2.5 | Extrusion | 13042 | 0 | 13042.08 |  | -0.08
1.1.4.3 | Strip Preparation | 990 | 0 | 989.995 | 0 | 0.005
1.1.4.3.2 | Mylar | 990 | 0 | 989.995 |  | 0.005
1.1.4.3.3 | Supplies | 0 | 0 | 0 |  | 0
1.1.4.4 | Fiber & Connectors | 36906 | 0 | 36906.2 | 0 | -0.2 | 5000
1.1.4.4.1 | WLS Fiber | 15631 | 0 | 15631.2 |  | -0.2
1.1.4.4.3 | WLS Fiber Silvering | 0 | 0 | 0 |  | 0
1.1.4.4.4 | Connectors (WLS Fiber Side) | 14715 | 0 | 14715 |  | 0
1.1.4.4.6 | Connector supplies/hardware | 6560 | 0 | 6560 |  | 0
1.1.4.4.7 | Fiber/Connector Polishing, Potting | 0 | 0 | 0 |  | 0
1.1.4.5 | Detector Module Assembly | 50200 | 0 | 50200 | 0 | 0
1.1.4.5.1 | Construction Domes | 10000 | 0 | 10000 |  | 0
1.1.4.5.3 | Epoxy | 3000 | 0 | 3000 |  | 0
1.1.4.5.4 | Vacuum bagging setup | 5000 | 0 | 5000 |  | 0
1.1.4.5.5 | Assembly supplies | 5000 | 0 | 5000 |  | 0
1.1.4.5.6 | Alignment Tooling | 20000 | 0 | 20000 |  | 0
1.1.4.5.7 | Water-Jet Cutting | 7200 | 0 | 7200 |  | 0
1.1.4.6 | Clear Waveguides | 263685 | 13000 | 250685 | 0 | 0
1.1.4.6.1 | Clear Waveguide | 237020 | 0 | 237020 |  | 0
1.1.4.6.2 | Connectors (Det. End of Clear Fiber) | 13665 | 0 | 13665 |  | 0
1.1.4.6.3 | Connectors (VLPC End of Clear Fiber) | 0 | 0 | 0 |  | 0
1.1.4.6.4 | Sheaths for Clear Fiber Bundles | 0 | 0 | 0 |  | 0
1.1.4.6.5 | Bundling Setup and Supplies | 3000 | 3000 | 0 |  | 0
1.1.4.6.6 | Fabrication of Clear Fiber Bundles | 10000 | 10000 | 0 |  | 0
1.1.4.7 | VLPC Cassettes (in WBS1.1.2.4) | 0 | 0 | 0 |  | 0
1.1.4.8 | Calibration System | 41145 | 0 | 31090 | 0 | 10055
1.1.4.8.1 | Blue LEDs | 10000 | 0 | 10000 |  | 0
1.1.4.8.3 | Controller | 10000 | 0 | 10000 |  | 0
1.1.4.8.4 | Mounting Hardware / Tooling | 3090 | 0 | 3090 |  | 0
1.1.4.8.5 | Temperature Monitoring System | 2000 | 0 | 2000 |  | 0
1.1.4.8.6 | Calibration System Assembly | 12000 | 0 | 6000 |  | 6000
1.1.4.8.7 | Calibration Cylinders | 4055 | 0 | 0 |  | 4055
1.1.4.9 | Detector Assembly | 89045 | 1057.5 | 88099.61 | 0 | -112.11
1.1.4.9.1 | Assembly and Installation Tooling | 15350 | 0 | 15349.61 |  | 0.39
1.1.4.9.2 | Lead Absorber | 14000 | 0 | 14000 |  | 0
1.1.4.9.3 | Storage and Shipping Fixture | 6000 | 0 | 6000 |  | 0
1.1.4.9.4 | Assembly Supplies | 6000 | 0 | 6000 |  | 0
1.1.4.9.5 | Shipping & Handling | 6000 | 0 | 6000 |  | 0
1.1.4.9.6 | Aluminum Support Skins | 3750 | 0 | 3750 |  | 0
1.1.4.9.7 | Fabrication of Support Ribs/Rings | 25945 | 1057.5 | 25000 |  | -112.5
1.1.4.9.8 | Module/Connector Mounting Hardware | 12000 | 0 | 12000 |  | 0
1.1.5 | TRACKING ELECTRONICS | 3703704.3 | 420728.89 | 2902061.92 | 0 | 380913.49 | 100000 | 0
1.1.5.1 | Engineering & Design | 180 | 180 | 0 |  | 0
1.1.5.2 | Si Readout System | 1311716.3 | 102180.62 | 1162917.955 | 0 | 46617.725
1.1.5.2.1 | Port Card System | 450167 | 52776.14 | 398138.255 | 0 | -747.395
1.1.5.2.1.1 | Port Cards | 400093 | 15301.5 | 384791.255 |  | 0.245
1.1.5.2.1.2 | Backplanes | 13624 | 568 | 13056 |  | 0
1.1.5.2.1.3 | Power Supplies | 21793 | 22540.61 | 0 |  | -747.61
1.1.5.2.1.4 | Controller Card | 14657 | 14366.03 | 291 |  | -0.03
1.1.5.2.1.5 | Rack Prep | 0 | 0 | 0 |  | 0
1.1.5.2.2 | Fiber optic system | 18206 | 0 | 18206 | 0 | 0
1.1.5.2.2.1 | Fiber cables | 18206 | 0 | 18206 |  | 0
1.1.5.2.3 | VRB System | 843343.3 | 49404.48 | 746573.7 | 0 | 47365.12
1.1.5.2.3.1 | VRB Cards | 676615 | 4654.74 | 671960.15 |  | 0.11
1.1.5.2.3.2 | J3 Backplanes | 20048 | 3488.24 | 14195.15 |  | 2364.61
1.1.5.2.3.3 | VRB Controller | 43059 | 41215.75 | 1842.85 |  | 0.4
1.1.5.2.3.4 | Rack Prep & Crates | 55773.5 | 45.75 | 55727.75 |  | 0
1.1.5.2.3.5 | Diagnostic Computer | 45000 | 0 | 0 |  | 45000
1.1.5.2.3.6 | VRB Test tooling | 2847.8 | 0 | 2847.8 |  | 0
1.1.5.3 | Fiber/Preshower Readout System | 2391808 | 318368.27 | 1739143.965 | 0 | 334295.765 | 100000 | 0
1.1.5.3.1 | Trigger Card | 635207 | 146028.46 | 475916.675 | 0 | 13261.865 | 25000 | 0
1.1.5.3.1.1 | SVX II Chip | 49302 | 0 | 49302 |  | 0
1.1.5.3.1.2 | Front End Chip | 37774 | 0 | 37774 | 0 | 0
1.1.5.3.1.2.1 | Front End Chip | 37774 | 0 | 37774 |  | 0
1.1.5.3.1.2.2 | Chip Testing and Dicing | 0 | 0 | 0 |  | 0
1.1.5.3.1.3 | Field programmable Gate Arrays | 104558 | 101400 | 3158 |  | 0 | 25000
1.1.5.3.1.4 | Multi chip module | 137854 | 8995.48 | 128859 |  | -0.48
1.1.5.3.1.6 | PC Board | 112412 | 5416.4 | 93734.15 |  | 13261.45
1.1.5.3.1.7 | Miscellaneous Chips | 62505 | 5475 | 57030 |  | 0
1.1.5.3.1.8 | Port Card | 33810 | 0 | 33809.525 |  | 0.475
1.1.5.3.1.9 | Assembly | 55960 | 0 | 55960 |  | 0
1.1.5.3.1.10 | Power supply | 23194 | 23193.78 | 0 |  | 0.22
1.1.5.3.1.11 | Backplanes | 17838 | 1547.8 | 16290 |  | 0.2
1.1.5.3.2 | Tooling | 323896 | 0 | 323896.05 | 0 | -0.05
1.1.5.3.2.1 | Front end chip development | 237896 | 0 | 237896.05 |  | -0.05
1.1.5.3.2.2 | Pulser system | 0 | 0 | 0 |  | 0
1.1.5.3.2.4 | SVX packaging | 86000 | 0 | 86000 |  | 0
1.1.5.3.3 | Stereo Card | 398829 | 7989.34 | 390838.525 | 0 | 1.135
1.1.5.3.3.1 | SVX II chip | 46221 | 0 | 46221 |  | 0
1.1.5.3.3.2 | Multi chip module | 120805 | 0 | 120805 |  | 0
1.1.5.3.3.4 | PC Board | 53505 | 3804.54 | 49700 |  | 0.46
1.1.5.3.3.5 | Miscellaneous Chips | 47797 | 0 | 47797 |  | 0
1.1.5.3.3.6 | Port Card | 30429 | 0 | 30428.525 |  | 0.475
1.1.5.3.3.7 | Assembly | 44200 | 0 | 44200 |  | 0
1.1.5.3.3.8 | Bias supply | 0 | 0 | 0 |  | 0
1.1.5.3.3.9 | Power supply | 0 | 0 | 0 |  | 0
1.1.5.3.3.10 | Backplanes | 20475 | 4184.8 | 16290 |  | 0.2
1.1.5.3.3.11 | Front End Chip | 35397 | 0 | 35397 |  | 0
1.1.5.3.4 | Fiber Optic system | 3996 | 0 | 3996 | 0 | 0
1.1.5.3.4.1 | Fiber optic cables | 3996 | 0 | 3996 |  | 0
1.1.5.3.5 | VRB System | 179389 | 1810.92 | 177577.94 | 0 | 0.14
1.1.5.3.5.1 | VRB Cards | 169608 | 0 | 169607.55 |  | 0.45
1.1.5.3.5.2 | J3 Backplanes | 1525 | 0 | 1525 |  | 0
1.1.5.3.5.3 | VRB Controller | 24 | 24 | 0.3 |  | -0.3
1.1.5.3.5.4 | Rack Prep | 2842 | 1786.92 | 1055.09 |  | -0.01
1.1.5.3.5.5 | Diagnostic Computer | 5390 | 0 | 5390 |  | 0
1.1.5.3.6 | FPS Readout/Trigger | 537634.5 | 127483.45 | 289902.275 | 0 | 120248.775 | 30000 | 0
1.1.5.3.6.1 | SVX II chip | 39416 | 0 | 39416 |  | 0
1.1.5.3.6.2 | Front End Chip | 30079 | 0 | 30079 |  | 0
1.1.5.3.6.3 | Field programmable Gate Arrays | 0 | 0 | 0 |  | 0
1.1.5.3.6.4 | Multi chip module | 103122 | 0 | 103122 |  | 0
1.1.5.3.6.6 | PC Board | 176009 | 90485.2 | 17722.25 |  | 67801.55 | 20000
1.1.5.3.6.7 | Miscellaneous Chips | 63760 | 20429 | 11760 |  | 31571
1.1.5.3.6.8 | Port Card | 33810 | 0 | 33809.525 |  | 0.475
1.1.5.3.6.9 | Assembly | 35210 | 0 | 14210 |  | 21000 | 10000
1.1.5.3.6.10 | Power supply | 8361 | 8391 | 0 |  | -30
1.1.5.3.6.11 | Backplanes | 47867.5 | 8178.25 | 39783.5 |  | -94.25
1.1.5.3.7 | CPS Stereo | 210112.5 | 2375.5 | 77016.5 | 0 | 130720.5 | 25000 | 0
1.1.5.3.7.1 | SVX II Chip | 12326 | 0 | 12326 |  | 0
1.1.5.3.7.2 | Front End Chip | 9255 | 0 | 9255 |  | 0
1.1.5.3.7.3 | Field programmable Gate Arrays | 0 | 0 | 0 |  | 0
1.1.5.3.7.4 | Multi chip module | 32215 | 0 | 32215 |  | 0
1.1.5.3.7.5 | PC Board | 130720 | 0 | 0 |  | 130720 | 25000
1.1.5.3.7.6 | Miscellaneous Chips | 0 | 0 | 0 |  | 0
1.1.5.3.7.7 | Port Card | 10143 | 0 | 10143 |  | 0
1.1.5.3.7.8 | Assembly | 0 | 0 | 0 |  | 0
1.1.5.3.7.9 | Power supply | 1012 | 1011.5 | 0 |  | 0.5
1.1.5.3.7.10 | Backplanes | 14441.5 | 1364 | 13077.5 |  | 0
1.1.5.3.8 | Mixing Box | 102744 | 32680.6 | 0 | 0 | 70063.4 | 20000
1.1.5.3.8.1 | Mixing Board | 72072 | 12000 | 0 | 0 | 60072
1.1.5.3.8.1.1 | Board Fab | 13000 | 0 | 0 |  | 13000
1.1.5.3.8.1.2 | Ivds Receivers/Drivers | 8778 | 0 | 0 |  | 8778
1.1.5.3.8.1.3 | CPLD Logic | 39119 | 12000 | 0 |  | 27119
1.1.5.3.8.1.4 | Connectors | 2175 | 0 | 0 |  | 2175
1.1.5.3.8.1.5 | Misc Logic | 2400 | 0 | 0 |  | 2400
1.1.5.3.8.1.6 | Assembly | 6600 | 0 | 0 |  | 6600
1.1.5.3.8.2 | Back Planes | 6000 | 0 | 0 |  | 6000
1.1.5.3.8.3 | Crate | 3000 | 0 | 0 |  | 3000
1.1.5.3.8.4 | Power Supply | 800 | 0 | 0 |  | 800
1.1.5.3.8.5 | Cable | 20872 | 20680.6 | 0 | 0 | 191.4
1.1.5.3.8.5.1 | Input Cables | 12236 | 13568.6 | 0 |  | -1332.6
1.1.5.3.8.5.2 | Output Cables | 8636 | 7112 | 0 |  | 1524
1.2 | CALORIMETER | 4656825.84 | 65399.71 | 4163383.28 | 210000 | 218042.85 | 25000 | 72000
1.2.1 | FRONT-END ELECTRONICS | 4347619.84 | 61115.71 | 3915513.94 | 210000 | 160990.19 | 15000 | 67000
1.2.1.1 | Preamp System | 1078371.3 | 21198.89 | 1057726.43 | 0 | -554.02 | 10000 | -10000
1.2.1.1.1 | Preamp Engineering & Design | 14137 | 0 | 14137.3 |  | -0.3
1.2.1.1.2 | Preamp Hybrids | 657479 | 0 | 657478.87 | 0 | 0.13
1.2.1.1.2.1 | Parts | 266479 | 0 | 266479 | 0 | 0
1.2.1.1.2.1.1 | Transistors / Diodes | 85690 | 0 | 85690 | 0 | 0
1.2.1.1.2.1.1.1 | MMBD7000LT1 (D1) | 3300 | 0 | 3300 |  | 0
1.2.1.1.2.1.1.2 | MMBT3904LT1 (Q9) | 2520 | 0 | 2520 |  | 0
1.2.1.1.2.1.1.3 | MMBT3906T (Q13) | 5040 | 0 | 5040 |  | 0
1.2.1.1.2.1.1.4 | MMBTH10LT1 (Q2,3,4,8,10,12) | 36420 | 0 | 36420 |  | 0
1.2.1.1.2.1.1.5 | MMBTH81LT1 (Q1,5,6,7,11) | 38410 | 0 | 38410 |  | 0
1.2.1.1.2.1.2 | Capacitors | 83967 | 0 | 83967 | 0 | 0
1.2.1.1.2.1.2.1 | 4.7uF,1206,35V,Y5V, -20+80% (C17,19,2123) | 35645 | 0 | 35645 |  | 0
1.2.1.1.2.1.2.2 | Bypass | 12491 | 0 | 12491 | 0 | 0
1.2.1.1.2.1.2.2.1 | 68nF, 0603, 25V, Y5V, -20+80% (C25,26,27) | 3008 | 0 | 3008 |  | 0
1.2.1.1.2.1.2.2.2 | .1uF, 0805,50V,Z5U,-20+80% (C2,4,10,12,16,18,20,22) | 9483 | 0 | 9483 |  | 0
1.2.1.1.2.1.2.3 | Precision | 35831 | 0 | 35831 | 0 | 0
1.2.1.1.2.1.2.3.1 | .47uF,0805,16V,X7R,+/-10% (C1) | 4410 | 0 | 4410 |  | 0
1.2.1.1.2.1.2.3.2 | .15uF,0805,15V,X7R,+/-10% (C6,11) | 6937 | 0 | 6937 |  | 0
1.2.1.1.2.1.2.3.3 | 3pF,0805,50V,NPO,+/-0.5pF (C9,14) | 1302 | 0 | 1302 |  | 0
1.2.1.1.2.1.2.3.4 | 22pF,0805,50V,NPO,+/-2% (C5) | 464 | 0 | 464 |  | 0
1.2.1.1.2.1.2.3.5 | 10pF,0805,50V,NPO,+/-0.25pF (C3) | 832 | 0 | 832 |  | 0
1.2.1.1.2.1.2.3.6 | 5pF,0805,50V,NPO,+/-0.25pF (C3) | 440 | 0 | 440 |  | 0
1.2.1.1.2.1.2.3.7 | 10nF,1210,50V,NPO,+/-1% (C15,24) | 19746 | 0 | 19746 |  | 0
1.2.1.1.2.1.2.3.8 | C8 | 850 | 0 | 850 |  | 0
1.2.1.1.2.1.2.3.9 | C13 | 850 | 0 | 850 |  | 0
1.2.1.1.2.1.3 | Connectors | 96822 | 0 | 96822 |  | 0
1.2.1.1.2.2 | Assembly (ceramic, resistors) | 366445 | 0 | 366444.9 | 0 | 0.1
1.2.1.1.2.2.1 | Engineering Samples | 3386 | 0 | 3385.5 |  | 0.5
1.2.1.1.2.2.2 | Substrate Mold | 3040 | 0 | 3040 |  | 0
1.2.1.1.2.2.3 | NRE | 21050 | 0 | 21050 |  | 0
1.2.1.1.2.2.4 | Hybrid production | 338969 | 0 | 338969.4 |  | -0.4
1.2.1.1.2.3 | Test Station | 24555 | 0 | 24554.97 | 0 | 0.03
1.2.1.1.2.3.1 | DAQ | 6200 | 0 | 6200 |  | 0
1.2.1.1.2.3.2 | Test Jig | 18355 | 0 | 18354.97 |  | 0.03
1.2.1.1.3 | Preamp Motherboards | 282364 | 9916.75 | 272447.25 | 0 | 0
1.2.1.1.3.1 | NRE setup | 790 | 0 | 790 |  | 0
1.2.1.1.3.2 | PC boards | 110792 | 1180.75 | 109611.25 |  | 0
1.2.1.1.3.3 | Assembly | 19548 | 0 | 19548 |  | 0
1.2.1.1.3.4 | Parts | 145665 | 8736 | 136929 | 0 | 0
1.2.1.1.3.4.1 | Connectors | 94016 | 8736 | 85280 |  | 0
1.2.1.1.3.4.2 | Precision resistors | 29314 | 0 | 29314 |  | 0
1.2.1.1.3.4.3 | Fuses, diode, resistor | 9340 | 0 | 9340 |  | 0
1.2.1.1.3.4.4 | DIN connector | 12995 | 0 | 12995 |  | 0
1.2.1.1.3.5 | Testing | 5569 | 0 | 5569 |  | 0
1.2.1.1.4 | Preamp Power Supplies | 124391.3 | 11282.14 | 113663.01 | 0 | -553.85
1.2.1.1.4.12 | Vicor Power Supply & Chassis | 81915 | 0 | 81915.45 |  | -0.45
1.2.1.1.4.13 | Chassis | 3619 | 445.84 | 3173 |  | 0.16
1.2.1.1.4.14 | Interface | 35132.3 | 8459.1 | 27184.31 | 0 | -511.11
1.2.1.1.4.14.1 | PC Board | 10056 | 51.9 | 10004.03 |  | 0.07
1.2.1.1.4.14.2 | Shunt Resistors | 2043 | 0 | 2043 |  | 0
1.2.1.1.4.14.3 | 3 Phase S.S. Relays | 1680 | 0 | 1680 |  | 0
1.2.1.1.4.14.4 | Fuse/fuse block | 3938 | 2510.44 | 1938.49 |  | -510.93
1.2.1.1.4.14.5 | Terminal Block | 17 | 0 | 17.25 |  | -0.25
1.2.1.1.4.14.6 | Water Cooler | 3523 | 26.85 | 3496.25 |  | -0.1
1.2.1.1.4.14.7 | IC's | 1510.3 | 0 | 1510.3 |  | 0
1.2.1.1.4.14.8 | Temp Sensors | 0 | 0 | 0 |  | 0
1.2.1.1.4.14.9 | Anode Connector | 712 | 0 | 712 |  | 0
1.2.1.1.4.14.10 | D Connectors | 1439 | 0 | 1439 |  | 0
1.2.1.1.4.14.11 | Discrete Components | 7939 | 5869.91 | 2068.99 |  | 0.1
1.2.1.1.4.14.12 | Control Power | 2275 | 0 | 2275 |  | 0
1.2.1.1.4.15 | Assembly & Testing | 3725 | 2377.2 | 1390.25 |  | -42.45
1.2.1.2 | BLS System | 2423097.54 | 39495.56 | 2279429.01 | 0 | 104172.97 | 5000 | 61000
1.2.1.2.1 | BLS Engineering & Design | 22919.04 | 0 | 22919.04 |  | 0
1.2.1.2.2 | BLS Switched Capacitor Arrays | 672522 | 10682.77 | 661838.87 | 0 | 0.36 |  | 10000
1.2.1.2.2.1 | SCA die | 611670 | 0 | 611670 | 0 | 0
1.2.1.2.2.1.1 | Prototype 10 wafers | 27000 | 0 | 27000 |  | 0
1.2.1.2.2.1.2 | Production wafers | 529270 | 0 | 529270 |  | 0
1.2.1.2.2.1.3 | Photoplate generation | 55400 | 0 | 55400 |  | 0
1.2.1.2.2.2 | Die packaging | 51779 | 10682.77 | 41095.8 |  | 0.43
1.2.1.2.2.3 | Test Jig | 9073 | 0 | 9073.07 |  | -0.07
1.2.1.2.3 | Shaper Hybrid | 801066 | 0 | 801066 | 0 | 0
1.2.1.2.3.1 | Filter | 148885 | 0 | 148885 | 0 | 0
1.2.1.2.3.1.1 | Transistors | 72085 | 0 | 72085 |  | 0
1.2.1.2.3.1.2 | Tantallum Caps (2.2uF) | 48000 | 0 | 48000 |  | 0
1.2.1.2.3.1.3 | Ceramic Caps (Z5U) | 9600 | 0 | 9600 |  | 0
1.2.1.2.3.1.4 | Precision Caps (NPO) | 19200 | 0 | 19200 |  | 0
1.2.1.2.3.2 | x1/x8 amp | 223200 | 0 | 223200 | 0 | 0
1.2.1.2.3.2.1 | HFA1135 | 194400 | 0 | 194400 |  | 0
1.2.1.2.3.2.2 | Tantallum Caps (2.2uF) | 24000 | 0 | 24000 |  | 0
1.2.1.2.3.2.3 | Ceramic Caps (Z5U) | 4800 | 0 | 4800 |  | 0
1.2.1.2.3.3 | Trigger pickoff | 21000 | 0 | 21000 | 0 | 0
1.2.1.2.3.3.1 | Transistors | 9000 | 0 | 9000 |  | 0
1.2.1.2.3.3.2 | Ceramic Caps (Z5U) | 2400 | 0 | 2400 |  | 0
1.2.1.2.3.3.3 | Precision Caps (NPO) | 9600 | 0 | 9600 |  | 0
1.2.1.2.3.4 | Ceramic Chip (with resistors) | 405000 | 0 | 405000 |  | 0
1.2.1.2.3.5 | Male Pins | 2981 | 0 | 2981 |  | 0
1.2.1.2.4 | Analog Buffer Daughter Board | 326009 | 14942.5 | 311066 | 0 | 0.5 |  | 16000
1.2.1.2.4.1 | Daughter Board (10 layer) | 61116 | 0 | 61116 |  | 0
1.2.1.2.4.2 | Connectors & Sockets | 74600 | 0 | 74600 | 0 | 0
1.2.1.2.4.2.1 | 25 pair | 19680 | 0 | 19680 |  | 0
1.2.1.2.4.2.2 | 20 pair | 15270 | 0 | 15270 |  | 0
1.2.1.2.4.2.3 | 17 pair | 7750 | 0 | 7750 |  | 0
1.2.1.2.4.2.4 | PLCC 68 pin sockets | 31900 | 0 | 31900 |  | 0
1.2.1.2.4.3 | Capacitors | 35580 | 13980 | 21600 | 0 | 0
1.2.1.2.4.3.1 | Tantallum Caps (10uF) | 4200 | 0 | 4200 |  | 0
1.2.1.2.4.3.2 | 0.1uF Ceramic Caps (Z5U) | 19000 | 12000 | 7000 |  | 0
1.2.1.2.4.3.3 | Precision Caps (NPO) | 10380 | 1980 | 8400 |  | 0
1.2.1.2.4.3.4 | 0.22uF Ceramic Caps (Z5U) | 2000 | 0 | 2000 |  | 0
1.2.1.2.4.4 | Resistors | 25963 | 962.5 | 25000 | 0 | 0.5
1.2.1.2.4.4.1 | Precision Resistor (0.1%) | 21600 | 0 | 21600 |  | 0
1.2.1.2.4.4.2 | Regular Resistors (1%) | 1240 | 720 | 520 |  | 0
1.2.1.2.4.4.3 | Low Precision Resistors (5%) | 3123 | 242.5 | 2880 |  | 0.5
1.2.1.2.4.5 | LM311M comparator | 7800 | 0 | 7800 |  | 0
1.2.1.2.4.6 | HFA1135 Op-Amp | 97200 | 0 | 97200 |  | 0
1.2.1.2.4.7 | Cmos 4053 switch | 10800 | 0 | 10800 |  | 0
1.2.1.2.4.8 | Cmos 4174 registor | 2900 | 0 | 2900 |  | 0
1.2.1.2.4.9 | Cmos 4519 MUX | 3150 | 0 | 3150 |  | 0
1.2.1.2.4.10 | TL074X2 Op-Amp | 6900 | 0 | 6900 |  | 0
1.2.1.2.5 | S/H & Output Buffer | 38556 | 0 | 38556.25 | 0 | -0.25
1.2.1.2.5.1 | TL074X2 Op-Amp | 3680 | 0 | 3680 |  | 0
1.2.1.2.5.2 | Capacitors | 6975 | 0 | 6975 | 0 | 0
1.2.1.2.5.2.1 | 0.1uF Ceramic Caps (Z5U) | 2775 | 0 | 2775 |  | 0
1.2.1.2.5.2.2 | Precision Caps (NPO) | 4200 | 0 | 4200 |  | 0
1.2.1.2.5.3 | Cmos 4066 switch | 4200 | 0 | 4200 |  | 0
1.2.1.2.5.4 | Ceramic Chip (with resistors) | 23201 | 0 | 23201.25 |  | -0.25
1.2.1.2.5.5 | Male Pins | 500 | 0 | 500 |  | 0
1.2.1.2.6 | BLS Boards | 403809.5 | 674.32 | 403135.65 | 0 | -0.47 | 5000 | 35000
1.2.1.2.6.1 | Connectors | 150530.5 | 0 | 150530.5 | 0 | 0 | 0 | 0
1.2.1.2.6.1.1 | 96 pin DIN | 3750 | 0 | 3750 |  | 0
1.2.1.2.6.1.2 | 64 pin DIN | 13248 | 0 | 13248 |  | 0
1.2.1.2.6.1.3 | Board mount Socket Pins | 49387.5 | 0 | 49387.5 |  | 0
1.2.1.2.6.1.4 | 25 pair Header | 43150 | 0 | 43150 |  | 0
1.2.1.2.6.1.5 | 20 pair Header | 27330 | 0 | 27330 |  | 0
1.2.1.2.6.1.6 | 17 pair Header | 13665 | 0 | 13665 |  | 0
1.2.1.2.6.2 | Control & Drivers | 16692 | 554.32 | 16138 |  | -0.32
1.2.1.2.6.3 | Trigger sum driver | 15000 | 0 | 15000 |  | 0
1.2.1.2.6.4 | Power Conditioning | 32645 | 120 | 32525.15 |  | -0.15 | 5000 | -5000
1.2.1.2.6.5 | Motherboards | 188942 | 0 | 188942 |  | 0
1.2.1.2.7 | Backplanes | 104753 | 0 | 20847.2 |  | 83905.8
1.2.1.2.8 | BLS Power Supplies | 33463 | 13195.97 | 0 | 0 | 20267.03
1.2.1.2.8.1 | Main Power transformers | 27463 | 12993 | 0 |  | 14470
1.2.1.2.8.3 | Control Panel | 4800 | 0 | 0 |  | 4800
1.2.1.2.8.5 | Parts/PC boards | 1200 | 202.97 | 0 |  | 997.03
1.2.1.2.9 | BLS Crate Controllers | 20000 | 0 | 20000 |  | 0
1.2.1.3 | ADC Controllers | 0 | 0 | 0 |  | 0
1.2.1.4 | Timing System | 77750 | 378.96 | 20000 | 0 | 57371.04 | 0 | 16000
1.2.1.4.1 | Central Crate Cards (MCH3) | 41250 | 0 | 10000 |  | 31250
1.2.1.4.2 | Signal Fanout Cards | 24000 | 0 | 5000 |  | 19000
1.2.1.4.3 | Signal Fanout Crates | 3000 | 0 | 3000 |  | 0
1.2.1.4.4 | Signal Fanout Power Supplies | 4500 | 0 | 2000 |  | 2500
1.2.1.4.5 | Coax Cabling (MCH3 to Quadrants) | 5000 | 378.96 | 0 |  | 4621.04
1.2.1.5 | Pulser Calibration | 211155 | 42.3 | 1112.5 | 210000 | 0.2 | 0 | 0
1.2.1.5.3 | Motherboard | 116155 | 42.3 | 1112.5 | 115000 | 0.2
1.2.1.5.3.1 | Board | 20000 | 0 | 0 | 20000 | 0
1.2.1.5.3.2 | Cabling | 30016 | 16.02 | 0 | 30000 | -0.02
1.2.1.5.3.3 | Mechanics | 10000 | 0 | 0 | 10000 | 0
1.2.1.5.3.4 | Power Supplies | 51139 | 26.28 | 1112.5 | 50000 | 0.22
1.2.1.5.3.5 | PC + Interface | 5000 | 0 | 0 | 5000 | 0
1.2.1.5.4 | Active Fanout | 95000 | 0 | 0 | 95000 | 0
1.2.1.5.4.1 | Board | 15000 | 0 | 0 | 15000 | 0
1.2.1.5.4.2 | Cables | 25000 | 0 | 0 | 25000 | 0
1.2.1.5.4.3 | Connectors | 15000 | 0 | 0 | 15000 | 0
1.2.1.5.4.4 | Components | 30000 | 0 | 0 | 30000 | 0
1.2.1.5.4.5 | Cabling | 10000 | 0 | 0 | 10000 | 0
1.2.1.6 | Cables Feedthrough-Preamp | 557246 | 0 | 557246 |  | 0
1.2.2 | INTERCRYOSTAT DETECTOR | 309206 | 4284 | 247869.34 | 0 | 57052.66 | 10000 | 5000
1.2.2.1 | Engineering and design | 5000 | 0 | 5000 | 0 | 0 | 0 | 0
1.2.2.1.1 | Second Protoype | 5000 | 0 | 5000 |  | 0
1.2.2.2 | Scintillator Modules | 64062 | 0 | 46422 | 0 | 17640
1.2.2.2.1 | Module design | 4641 | 0 | 0 |  | 4641
1.2.2.2.2 | Scintillator | 16000 | 0 | 16000 |  | 0
1.2.2.2.3 | WLS Fiber | 3234 | 0 | 2033 |  | 1201
1.2.2.2.4 | Fiber Splicer | 9001 | 0 | 8641 |  | 360
1.2.2.2.5 | Fiber Tester | 4438 | 0 | 0 |  | 4438
1.2.2.2.6 | Connectors | 760 | 0 | 760 |  | 0
1.2.2.2.7 | Other Supplies | 6500 | 0 | 1000 |  | 5500
1.2.2.2.8 | Module Assembly | 11400 | 0 | 11400 |  | 0
1.2.2.2.9 | Cosmic Ray Testing | 8088 | 0 | 6588 | 0 | 1500
1.2.2.2.9.1 | CR Teststands | 5000 | 0 | 3500 |  | 1500
1.2.2.2.9.2 | CR Testing | 3088 | 0 | 3088 |  | 0
1.2.2.3 | Fiber System | 44913 | 0 | 39115 | 0 | 5798 | 5000 | 0
1.2.2.3.1 | Fiber System Design | 8482 | 0 | 8482 |  | 0
1.2.2.3.2 | Fiber Ribbons | 28264 | 0 | 23264 | 0 | 5000 | 5000 | 0
1.2.2.3.2.1 | Ribbon Testing | 3496 | 0 | 3496 |  | 0
1.2.2.3.2.2 | Ribbon Construction | 16248 | 0 | 11248 |  | 5000 |  | 5000
1.2.2.3.2.3 | Connectors | 1520 | 0 | 1520 |  | 0
1.2.2.3.2.4 | Connector Polisher | 7000 | 0 | 7000 |  | 0 | 5000 | -5000
1.2.2.3.3 | Fiber Backplane | 8167 | 0 | 7369 | 0 | 798
1.2.2.3.3.1 | Fibers | 2360 | 0 | 1562 |  | 798
1.2.2.3.3.2 | Cookies | 2422 | 0 | 2422 |  | 0
1.2.2.3.3.3 | Connectors | 760 | 0 | 760 |  | 0
1.2.2.3.3.4 | Fiber Routing | 1625 | 0 | 1625 |  | 0
1.2.2.3.3.5 | Enclosures | 1000 | 0 | 1000 |  | 0
1.2.2.4 | Drawer System | 72684 | 0 | 72212 | 0 | 472 | 0 | 2000
1.2.2.4.1 | Drawer Design | 4331 | 0 | 3831 |  | 500
1.2.2.4.2 | Drawers | 31160 | 0 | 31160 |  | 0
1.2.2.4.3 | Connectors | 1140 | 0 | 1140 |  | 0
1.2.2.4.4 | Electronics Design | 7141 | 0 | 7141 |  | 0
1.2.2.4.5 | Motherboards | 9168 | 0 | 9196 |  | -28
1.2.2.4.6 | HV Bases | 4340 | 0 | 4340 |  | 0
1.2.2.4.7 | Electronics Testing | 4408 | 0 | 4408 |  | 0
1.2.2.4.8 | Drawer Assembly | 10420 | 0 | 10420 |  | 0 |  | 2000
1.2.2.4.9 | Temperature Sensors | 576 | 0 | 576 |  | 0
1.2.2.5 | Crate System | 38387 | 624 | 37763 | 0 | 0
1.2.2.5.1 | Crate Design | 4331 | 0 | 4331 |  | 0
1.2.2.5.2 | Crates | 6320 | 0 | 6320 |  | 0
1.2.2.5.3 | Steel Blocks | 11800 | 0 | 11800 |  | 0
1.2.2.5.4 | Pulser/LVPS Boards | 7056 | 0 | 7056 |  | 0
1.2.2.5.5 | Cooling System | 8880 | 624 | 8256 |  | 0
1.2.2.6 | PMT System | 36126 | 0 | 36125.56 | 0 | 0.44
1.2.2.6.1 | PMT Holders | 20140 | 0 | 20139.56 |  | 0.44
1.2.2.6.2 | PMT sockets | 2170 | 0 | 2170 |  | 0
1.2.2.6.3 | PMT testing | 13816 | 0 | 13816 | 0 | 0
1.2.2.6.3.1 | PMT Teststand | 5000 | 0 | 5000 |  | 0
1.2.2.6.3.2 | PMT Testing | 8816 | 0 | 8816 |  | 0
1.2.2.7 | Calibration System | 16094 | 0 | 11094 | 0 | 5000
1.2.2.7.1 | Laser Calibration Design | 6094 | 0 | 6094 |  | 0
1.2.2.7.2 | Hardware | 10000 | 0 | 5000 |  | 5000
1.2.2.8 | Cabling and Platform Electronics | 17395 | 3660 | 137.78 | 0 | 13597.22 |  | 3000
1.2.2.8.1 | Pulser Cables | 3040 | 0 | 0 |  | 3040
1.2.2.8.2 | LVPS Cables | 1900 | 0 | 0 |  | 1900
1.2.2.8.3 | HVPS Cables | 3255 | 0 | 0 |  | 3255
1.2.2.8.4 | Signal Cables | 3040 | 0 | 137.78 |  | 2902.22
1.2.2.8.5 | Preamp LV Supply | 3660 | 3660 | 0 |  | 0
1.2.2.8.6 | Preamp Pulser Supply | 2500 | 0 | 0 |  | 2500
1.2.2.9 | Shipping | 5000 | 0 | 0 |  | 5000
1.2.2.10 | Installation | 4670 | 0 | 0 | 0 | 4670 | 5000
1.2.2.10.1 | Support Design | 1547 | 0 | 0 |  | 1547
1.2.2.10.2 | Install Boxes & Drawers | 3123 | 0 | 0 |  | 3123
1.2.2.11 | Commissioning | 4875 | 0 | 0 |  | 4875
1.3 | MUON DETECTORS | 9498261.382 | 573504.59 | 7839899.8592 | 665274 | 419582.9328 | 33000 | 42050
1.3.1 | COSMIC RAY SCINTILLATOR | 1223200 | 0 | 963200 | 260000 | 0 | 0 | 0
1.3.1.1 | Scintillator | 614397 | 0 | 354397 | 260000 | 0
1.3.1.1.1 | Top counters (113) | 140955 | 0 | 140955 |  | 0
1.3.1.1.2 | Side counters (108) | 52429 | 0 | 52429 |  | 0
1.3.1.1.3 | Side counters (81) | 54018 | 0 | 54018 |  | 0
1.3.1.1.4 | Machining | 12758 | 0 | 12758 |  | 0
1.3.1.1.5 | Side scintillator | 7587 | 0 | 7587 |  | 0
1.3.1.1.6 | Bottom scintillator | 26678 | 0 | 26678 |  | 0
1.3.1.1.7 | TATA Side scintillator (108), '93 | 59972 | 0 | 59972 |  | 0
1.3.1.1.8 | TATA side scintillator (81), '94 | 260000 | 0 | 0 | 260000 | 0
1.3.1.2 | Waveshifter fiber | 110984 | 0 | 110984 | 0 | 0
1.3.1.2.1 | WLS fiber | 110984 | 0 | 110984 |  | 0
1.3.1.2.2 | TATA WLS fiber -1 | 0 | 0 | 0 |  | 0
1.3.1.2.3 | TATA WLS fiber -2 | 0 | 0 | 0 |  | 0
1.3.1.3 | Phototubes | 122100 | 0 | 122100 | 0 | 0
1.3.1.3.1 | Phototubes | 122100 | 0 | 122100 |  | 0
1.3.1.3.2 | Tests | 0 | 0 | 0 |  | 0
1.3.1.4 | Phototube bases | 71815 | 0 | 71815 | 0 | 0
1.3.1.4.1 | Bases | 59215 | 0 | 59215 |  | 0
1.3.1.4.2 | Magnetic shields | 12600 | 0 | 12600 |  | 0
1.3.1.5 | Electronics | 217 | 0 | 217 | 0 | 0
1.3.1.5.1 | Electronics (SciBo) | 217 | 0 | 217 |  | 0
1.3.1.6 | HV Cables | 12078 | 0 | 12078 | 0 | 0
1.3.1.6.1 | Cable | 817 | 0 | 817 |  | 0
1.3.1.6.2 | Connectors | 11261 | 0 | 11261 |  | 0
1.3.1.7 | Signal Cables | 1980 | 0 | 1980 | 0 | 0
1.3.1.7.1 | Cable | 862 | 0 | 862 |  | 0
1.3.1.7.2 | Connectors | 1118 | 0 | 1118 |  | 0
1.3.1.8 | High Voltage | 92456 | 0 | 92456 | 0 | 0
1.3.1.8.1 | Modules | 35560 | 0 | 35560 |  | 0
1.3.1.8.2 | Crates & LV power | 0 | 0 | 0 |  | 0
1.3.1.8.3 | Controllers | 0 | 0 | 0 |  | 0
1.3.1.8.4 | Fanouts | 56896 | 0 | 56896 |  | 0
1.3.1.9 | Mechanical Assembly | 197173 | 0 | 197173 | 0 | 0
1.3.1.9.1 | Counter construction | 74210 | 0 | 74210 |  | 0
1.3.1.9.2 | Assembly/testing | 122963 | 0 | 122963 |  | 0
1.3.1.9.3 | TATA other materials | 0 | 0 | 0 |  | 0
1.3.1.9.4 | TATA machining | 0 | 0 | 0 |  | 0
1.3.1.9.5 | TATA shipping | 0 | 0 | 0 |  | 0
1.3.1.9.6 | TATA test stand | 0 | 0 | 0 |  | 0
1.3.2 | CENTRAL TRIGGER DETECTORS | 951934.2013 | 61769.15 | 713603.28 | 145785 | 30776.7713 | 0 | 0
1.3.2.1 | Engineering design | 0 | 0 | 0 |  | 0
1.3.2.2 | A-phi Counters | 480012.4386 | 4169.92 | 464606.85 | 0 | 11235.6686
1.3.2.2.1 | Purchase scintillator (cut &polish, .5") | 114045 | 0 | 114045 |  | 0
1.3.2.2.2 | Machining Scintillator | 19495 | 0 | 19495.31 |  | -0.31
1.3.2.2.3 | Waveshifter Fiber G2 | 27720 | 0 | 27720 |  | 0
1.3.2.2.4 | Phototubes (1"115M) | 39000 | 0 | 39000 |  | 0
1.3.2.2.5 | Phototube bases (assembled) | 16995.5 | 0 | 16995.5 |  | 0
1.3.2.2.6 | Magnetic shields | 28099.74 | 0 | 28100 |  | -0.26
1.3.2.2.7 | Counter Case | 50592 | 0 | 50592.49 |  | -0.49
1.3.2.2.8 | HV Fanout box 1 | 24745 | 0 | 24744.8 |  | 0.2
1.3.2.2.9 | HV Fanout box 2 | 3340 | 0 | 3340 |  | 0
1.3.2.2.10 | Scintillator frame and support | 61745 | 3468 | 51242.04 |  | 7034.96
1.3.2.2.11 | Calibration system | 22072.1986 | 701.92 | 17168.82 |  | 4201.4586
1.3.2.2.12 | HV cable | 11653 | 0 | 11652.78 |  | 0.22
1.3.2.2.13 | Signal cable | 10549 | 0 | 10549.45 |  | -0.45
1.3.2.2.14 | Glues/bits/tapes | 4621 | 0 | 4620.66 |  | 0.34
1.3.2.2.17 | Assembly at ITEP | 10000 | 0 | 10000 |  | 0
1.3.2.2.18 | HV Power Supplies | 19968 | 0 | 19968 |  | 0
1.3.2.2.19 | Shipping to/from ITEP | 15372 | 0 | 15372 |  | 0
1.3.2.2.20 | NIU Technician Labor | 0 | 0 | 0 |  | 0
1.3.2.3 | Cosmic Cap and Bottom Counters | 298184.7627 | 7574.17 | 137402.31 | 145785 | 7423.2827
1.3.2.3.1 | Scintillator | 66885.23 | 0 | 0 | 66885 | 0.23
1.3.2.3.2 | Scintillator machining | 1605 | 0 | 1604.7 |  | 0.3
1.3.2.3.4 | Scintillating fiber (Bicron 91A) | 37500 | 0 | 0 | 37500 | 0
1.3.2.3.5 | Phototubes (1"115M) | 9775 | 0 | 9775 |  | 0
1.3.2.3.6 | Phototube bases (assembled) | 4074 | 0 | 4074 |  | 0
1.3.2.3.7 | Magnetic shields | 6688.01 | 0 | 6688.01 |  | 0
1.3.2.3.8 | Counter frame and case | 34554 | 0 | 34554.36 |  | -0.36
1.3.2.3.9 | HV Fanout box 1 | 21503 | 0 | 21503 |  | 0
1.3.2.3.11 | HV cable | 6852 | 0 | 6852.04 |  | -0.04
1.3.2.3.12 | Signal cable | 10449 | 0 | 10449 |  | 0
1.3.2.3.13 | Calibration System | 24653.5227 | 7574.17 | 9656.32 |  | 7423.0327
1.3.2.3.14 | Glues/bits/tapes | 5641 | 0 | 5640.77 |  | 0.23
1.3.2.3.15 | Counter Assembly at TIFR | 20000 | 0 | 0 | 20000 | 0
1.3.2.3.16 | Shipping Counters from TIFR | 15000 | 0 | 0 | 15000 | 0
1.3.2.3.17 | Shipping Counters to TIFR | 6400 | 0 | 0 | 6400 | 0
1.3.2.3.18 | Hole & Side b Counter Scintillator | 8784 | 0 | 8783.64 |  | 0.36
1.3.2.3.19 | Hole & Side b Counter Fiber | 4680 | 0 | 4680 |  | 0
1.3.2.3.20 | Hole & Side b Counter Cases & Assem. | 13141 | 0 | 13141.47 |  | -0.47
1.3.2.4 | Cable, Power Supplies | 173737 | 50025.06 | 111594.12 | 0 | 12117.82
1.3.2.4.2 | New Signal Cable | 37000 | 19681.35 | 19658.61 |  | -2339.96
1.3.2.4.3 | Modify Electronics Mounts | 32900 | 0 | 32225.2 |  | 674.8
1.3.2.4.4 | Data/1553 cables/connectors | 40000 | 0 | 37470.17 |  | 2529.83
1.3.2.4.5 | Refurbish LVPS | 15300 | 3058.84 | 12241.14 |  | 0.02
1.3.2.4.6 | New 3/5V LV PS | 9999 | 0 | 9999 |  | 0
1.3.2.4.7 | WAMUS Gas System | 38538 | 27284.87 | 0 |  | 11253.13
1.3.3 | FORWARD TRIGGER DETECTOR | 2133281.6807 | 26325.79 | 1673079.38 | 259489 | 174387.5107 | 33000 | 0
1.3.3.1 | Engineering design | 25000 | 0 | 25000 |  | 0
1.3.3.2 | Scintillator | 430236 | 0 | 430236 |  | 0
1.3.3.3 | Wave-shifter Bars | 76917.5 | 0 | 76917.5 |  | 0
1.3.3.4 | Phototube System | 603376.8 | 0 | 343887.45 | 259489 | 0.35
1.3.3.4.1 | Phototubes (1", Meltz) | 282000 | 0 | 282000 |  | 0
1.3.3.4.2 | Phototube Bases | 123856.8 | 0 | 41753.8 | 82103 | 0
1.3.3.4.2.1 | Socket | 28009 | 0 | 3500 | 24509 | 0
1.3.3.4.2.2 | High Voltage Connector | 13475.8 | 0 | 13475.8 |  | 0
1.3.3.4.2.3 | Signal BNC Connector | 16278 | 0 | 16278 |  | 0
1.3.3.4.2.4 | Resistors | 66094 | 0 | 8500 | 57594 | 0
1.3.3.4.3 | Magnetic Shields | 197520 | 0 | 20133.65 | 177386 | 0.35
1.3.3.4.3.1 | Soft Steel Shield | 123450 | 0 | 12500 | 110950 | 0
1.3.3.4.3.2 | Mu-metal Shield | 49380 | 0 | 5000 | 44380 | 0
1.3.3.4.3.3 | Assembly Parts | 24690 | 0 | 2633.65 | 22056 | 0.35
1.3.3.5 | Counter Packaging | 160545 | 0 | 160545.16 | 0 | -0.16
1.3.3.5.1 | Light Tight Counter Package | 132280 | 0 | 132280 |  | 0
1.3.3.5.2 | Wrapping Materials | 16569 | 0 | 16569.16 |  | -0.16
1.3.3.5.3 | Support Frames | 11696 | 0 | 11696 |  | 0
1.3.3.6 | Mechanical Supports | 430000 | 21325.79 | 271814.17 | 0 | 136860.04 | 33000
1.3.3.6.1 | Pixel Octant Frame | 297000 | 20930 | 205900 |  | 70170
1.3.3.6.2 | Pixel Octant Frame Supports and Mover | 70000 | 395.79 | 2914.17 |  | 66690.04
1.3.3.6.3 | Pixel Counter Holders | 63000 | 0 | 63000 |  | 0
1.3.3.7 | Signal Cables | 59872.45 | 0 | 59872.35 | 0 | 0.1
1.3.3.7.1 | Coax RG58 Cables | 20102.45 | 0 | 20102.35 |  | 0.1
1.3.3.7.2 | BNC Connectors | 10961 | 0 | 10961 |  | 0
1.3.3.7.3 | Lemo Connectors | 28809 | 0 | 28809 |  | 0
1.3.3.8 | High Voltage System | 219530.9 | 0 | 201158.01 | 0 | 18372.89
1.3.3.8.1 | Coax RG58 Cable | 20274.9 | 0 | 20274.58 |  | 0.32
1.3.3.8.2 | SHV Connectors | 36666 | 0 | 36666 |  | 0
1.3.3.8.3 | HV Fanout Box | 56851 | 0 | 56851 |  | 0
1.3.3.8.4 | Other Parts | 7000 | 0 | 4971.43 |  | 2028.57
1.3.3.8.5 | HV Power Supplies | 98739 | 0 | 82395 |  | 16344
1.3.3.9 | Monitoring System | 76803.0307 | 0 | 63193.12 | 0 | 13609.9107
1.3.3.9.1 | Light Pulsers | 22900 | 0 | 11947 |  | 10953
1.3.3.9.2 | Clear Fiber Light Guides | 36288 | 0 | 34630 |  | 1658
1.3.3.9.3 | Optical Connectors | 17615.0307 | 0 | 16616.12 |  | 998.9107
1.3.3.10 | Testing & Shipping | 51000 | 5000 | 40455.62 | 0 | 5544.38
1.3.3.10.1 | Test Fixtures | 10000 | 0 | 5455.62 |  | 4544.38
1.3.3.10.2 | Shipping | 36000 | 5000 | 30000 |  | 1000
1.3.3.10.3 | NIU Technician Labor | 5000 | 0 | 5000 |  | 0
1.3.4 | FORWARD TRACKING DETECTOR | 1410768.5 | 331311.73 | 953805.867 | 0 | 125650.903 | 0 | 4000
1.3.4.1 | Engineering design | 0 | 0 | 0 |  | 0
1.3.4.2 | Mini-Drift Tubes | 555516.5 | 7878.79 | 545264.942 | 0 | 2372.768
1.3.4.2.1 | 8-Cell Comb | 162435 | 0 | 162434.6 |  | 0.4
1.3.4.2.2 | Plastic Sleeve | 43359 | 0 | 43358.96 |  | 0.04
1.3.4.2.3 | Plastic Cover | 20918 | 0 | 20918.2 |  | -0.2
1.3.4.2.4 | End Cap | 60220 | 0 | 60220 |  | 0
1.3.4.2.5 | Wire Locks | 43739 | 0 | 43738.6 |  | 0.4
1.3.4.2.6 | Wire Supports | 54527 | 6 | 54521.4 |  | -0.4
1.3.4.2.7 | Gas Connectors | 40465 | 57.6 | 38034 |  | 2373.4
1.3.4.2.8 | Anode Wire | 28480.5 | 6831.11 | 21650 |  | -0.61
1.3.4.2.9 | High Voltage Connectors | 41203 | 0 | 41203 |  | 0
1.3.4.2.10 | Signal Connectors | 53881 | 0 | 53881 |  | 0
1.3.4.2.11 | Low Voltage Bus | 6289 | 984.08 | 5305.182 |  | -0.262
1.3.4.3 | Mechanical Supports | 516827 | 296954.86 | 142748.81 | 0 | 77123.33
1.3.4.3.1 | MDT Blades | 52800 | 17188.3 | 12662 |  | 22949.7
1.3.4.3.2 | MDT Octant Frames | 328270 | 198851.37 | 129418.23 |  | 0.4
1.3.4.3.3 | MDT Octant Frame Supports | 135757 | 80915.19 | 668.58 |  | 54173.23
1.3.4.4 | Gas System | 103071 | 431.48 | 62540 | 0 | 40099.52 |  | 4000
1.3.4.4.1 | Gas Lines | 10481 | 431.48 | 9120 |  | 929.52
1.3.4.4.2 | Gas Connection/Monitoring Boxes | 62590 | 0 | 23420 |  | 39170
1.3.4.4.3 | Gas Monitoring Devices | 30000 | 0 | 30000 |  | 0
1.3.4.5 | Signal Cables | 100619 | 0 | 100618.74 | 0 | 0.26
1.3.4.5.1 | Signal Flat Cables (ADB-MDC) | 18720 | 0 | 18720 |  | 0
1.3.4.5.2 | Connectors (ADB-MDC) | 13849 | 0 | 13848.9 |  | 0.1
1.3.4.5.3 | Signal Cables (MDT-ADB) | 16298 | 0 | 16298 |  | 0
1.3.4.5.4 | Connectors (MDT-ADB) | 51752 | 0 | 51751.84 |  | 0.16
1.3.4.6 | High Voltage System | 94546 | 16615.4 | 71875.685 | 0 | 6054.915
1.3.4.6.1 | HV Distribution Boards | 65000 | 180 | 63277.905 |  | 1542.095
1.3.4.6.2 | HV Cables | 10236 | 10098 | 137.78 |  | 0.22
1.3.4.6.3 | Connectors | 19310 | 6337.4 | 8460 |  | 4512.6
1.3.4.7 | Testing & Shipping | 40189 | 9431.2 | 30757.69 | 0 | 0.11
1.3.4.7.1 | Test Fixtures | 15189 | 9431.2 | 5757.69 |  | 0.11
1.3.4.7.2 | Shipping | 20000 | 0 | 20000 |  | 0
1.3.4.7.3 | NIU Technician Labor | 5000 | 0 | 5000 |  | 0
1.3.5 | FRONT-END ELECTRONICS | 3779077 | 154097.92 | 3536211.3322 | 0 | 88767.7478 | 0 | 38050
1.3.5.1 | WAMUS Front End Electronics | 1044559.5 | 91036.82 | 947417.564 | 0 | 6105.116 | 0 | 10500
1.3.5.1.1 | Engineering design | 0 | 0 | 0 |  | 0
1.3.5.1.2 | Wamus Front-End boards (FEB) | 705839 | 69317.86 | 631361.232 | 0 | 5159.908 | 0 | 7400
1.3.5.1.2.6 | Board Fabrication & Assembly | 201980 | 6834 | 189980.27 |  | 5165.73 |  | 2300
1.3.5.1.2.7 | Parts | 441909 | 533.86 | 441380.962 |  | -5.822 |  | 5100
1.3.5.1.2.8 | SLDB Transmitter Parts | 61950 | 61950 | 0 |  | 0
1.3.5.1.3 | HV Service Card | 106147 | 0 | 106146.6 | 0 | 0.4
1.3.5.1.3.5 | Parts | 39996 | 0 | 39996 |  | 0
1.3.5.1.3.6 | Board Fabrication & Assembly | 66151 | 0 | 66150.6 |  | 0.4
1.3.5.1.4 | Wire Signal Delay/Jumper Board | 58917 | 0 | 58917.22 | 0 | -0.22
1.3.5.1.4.4 | Board Fabrication & Assembly | 41145 | 0 | 41145.02 |  | -0.02
1.3.5.1.4.5 | Parts | 17772 | 0 | 17772.2 |  | -0.2
1.3.5.1.5 | Wamus control boards (WCB) | 160867.5 | 21651.36 | 138203.02 | 0 | 1013.12 | 0 | 3100
1.3.5.1.5.5 | Board Fabrication & Assembly | 50714.5 | 20234.69 | 30997.5 |  | -517.69 |  | 1000
1.3.5.1.5.6 | Parts | 110153 | 1416.67 | 107205.52 |  | 1530.81 |  | 2100
1.3.5.1.6 | Test fixtures | 12789 | 67.6 | 12789.492 |  | -68.092
1.3.5.2 | Mini-drift Chamber Electronics | 1401805 | 22070.15 | 1369883.6572 | 0 | 9851.1928 | 0 | 11500
1.3.5.2.1 | Engineering design | 0 | 0 | 0 |  | 0
1.3.5.2.2 | Amplifier/Discriminator Board | 847910 | 0 | 847909.6 | 0 | 0.4
1.3.5.2.2.4 | Board Fabrication & Assembly | 140006 | 0 | 140006.32 |  | -0.32
1.3.5.2.2.5 | Parts | 667802 | 0 | 667801.68 |  | 0.32
1.3.5.2.2.6 | Power Supplies | 40102 | 0 | 40101.6 |  | 0.4
1.3.5.2.3 | Front-end Card | 481784 | 15780.05 | 460253.7632 | 0 | 5750.1868 | 0 | 6500
1.3.5.2.3.5 | Board Fabrication & Assembly | 58088 | 10750.05 | 42888.2 |  | 4449.75 |  | 2300
1.3.5.2.3.6 | Parts | 423696 | 5030 | 417365.5632 |  | 1300.4368 |  | 4200
1.3.5.2.4 | Mini-drift Controller Card | 63132 | 5548.1 | 53482.894 | 0 | 4101.006 | 0 | 5000
1.3.5.2.4.5 | Board Fabrication & Assembly | 20738 | 5386.1 | 12088.4 |  | 3263.5 |  | 1000
1.3.5.2.4.6 | Parts | 42394 | 162 | 41394.494 |  | 837.506 |  | 4000
1.3.5.2.5 | MDT Test Fixtures | 8979 | 742 | 8237.4 |  | -0.4
1.3.5.3 | Scintillator Electronics | 725365.5 | 15528.93 | 696799.41 | 0 | 13037.16 | 0 | 9650
1.3.5.3.1 | Engineering design | 0 | 0 | 0 |  | 0
1.3.5.3.2 | Scintillator Front-End board (FEB) | 640575.5 | 4655 | 625420.8 | 0 | 10499.7 | 0 | 6300
1.3.5.3.2.4 | Board Fabrication & Assembly | 45963 | 4655 | 41308.3 |  | -0.3 |  | 500
1.3.5.3.2.5 | Parts | 594612.5 | 0 | 584112.5 |  | 10500 |  | 5800
1.3.5.3.3 | Scintillator control board (SCB) | 48645 | 2075.33 | 45994.99 | 0 | 574.68 | 0 | 1250
1.3.5.3.3.5 | Board Fabrication & Assembly | 41668 | 1525 | 39568.3 |  | 574.7 |  | 1250
1.3.5.3.3.6 | Parts | 6977 | 550.33 | 6426.69 |  | -0.02
1.3.5.3.4 | Test fixtures | 8319 | 7910.6 | 408 |  | 0.4
1.3.5.3.6 | Scint Led Pulser | 27826 | 888 | 24975.62 | 0 | 1962.38 | 0 | 2100
1.3.5.3.6.1 | Parts | 16691 | 888 | 14840.62 |  | 962.38 |  | 1100
1.3.5.3.6.2 | Board Fabrication | 11135 | 0 | 10135 |  | 1000 |  | 1000
1.3.5.4 | Crate Electronics | 607347 | 25462.02 | 522110.701 | 0 | 59774.279 | 0 | 6400
1.3.5.4.1 | Muon readout card (MRC) | 67305 | 5696.22 | 61608.71 | 0 | 0.07 | 0 | 0
1.3.5.4.1.1 | Parts | 36032 | 1631.22 | 34400.81 |  | -0.03
1.3.5.4.1.2 | Board Fabrication & Assembly | 31273 | 4065 | 27207.9 |  | 0.1
1.3.5.4.2 | Muon master fanout card | 99917 | 3668.5 | 41620.07 | 0 | 54628.43 | 0 | 5000
1.3.5.4.2.1 | Parts | 83545 | 2004.4 | 41620.07 |  | 39920.53 |  | 5000
1.3.5.4.2.2 | Board Fabrication & Assembly | 16372 | 1664.1 | 0 |  | 14707.9
1.3.5.4.3 | CPU Board (VSCB-20) | 129003 | 5163.9 | 124002.8 | 0 | -163.7
1.3.5.4.3.1 | Board | 129003 | 5163.9 | 124002.8 |  | -163.7
1.3.5.4.4 | VME Crates | 276846 | 108.7 | 276738.01 | 0 | -0.71
1.3.5.4.4.1 | Crates | 270345 | 108.7 | 270236.7 |  | -0.4
1.3.5.4.4.2 | J3 Backplanes | 6501 | 0 | 6501.31 |  | -0.31
1.3.5.4.5 | Trigger Fanout Card (TFC) | 18200 | 6339.9 | 6549.74 | 0 | 5310.36 | 0 | 1400
1.3.5.4.5.1 | Parts | 7392 | 371 | 6549.74 |  | 471.26 |  | 1400
1.3.5.4.5.2 | Board Fabrication & Assembly | 10808 | 5968.9 | 0 |  | 4839.1
1.3.5.4.6 | Test Stand Equipment (PCs…) | 15882 | 4484.8 | 11396.971 |  | 0.229
1.3.5.4.7 | MRC Tester | 194 | 0 | 194.4 | 0 | -0.4
1.3.5.4.7.1 | Parts | 194 | 0 | 194.4 |  | -0.4
1.3.5.4.7.2 | PCB Fabrication | 0 | 0 | 0 |  | 0
1.3.5.4.8 | MFC/TFC Tester | 0 | 0 | 0 | 0 | 0
1.3.5.4.8.1 | Parts | 0 | 0 | 0 |  | 0
1.3.5.4.8.2 | PCB Fabrication | 0 | 0 | 0 |  | 0
1.4 | TRIGGER | 6594476.2 | 163902.155 | 4919486.37 | 546672 | 964415.675 | 35000 | 62000
1.4.1 | FRAMEWORK | 1859350.2 | 0 | 1859350.2 | 0 | 0
1.4.1.1 | Engineering and Design | 660372 | 0 | 660372 |  | 0
1.4.1.2 | Framework L1 | 740992.6 | 0 | 740992.6 | 0 | 0
1.4.1.2.1 | Circuit boards | 601314 | 0 | 601314 |  | 0
1.4.1.2.2 | Crates | 98099 | 0 | 98099 |  | 0
1.4.1.2.3 | Cables | 18512.6 | 0 | 18512.6 |  | 0
1.4.1.2.4 | Installation | 23067 | 0 | 23067 |  | 0
1.4.1.3 | Framework L2 | 252112 | 0 | 252112 | 0 | 0
1.4.1.3.1 | Circuit boards | 145922 | 0 | 145922 |  | 0
1.4.1.3.2 | Crates | 65039 | 0 | 65039 |  | 0
1.4.1.3.3 | Cables | 18084 | 0 | 18084 |  | 0
1.4.1.3.4 | Installation | 23067 | 0 | 23067 |  | 0
1.4.1.4 | Foreign Scalers | 205873.6 | 0 | 205873.6 | 0 | 0
1.4.1.4.1 | Circuit boards | 145922 | 0 | 145922 |  | 0
1.4.1.4.2 | Crates | 18372 | 0 | 18372 |  | 0
1.4.1.4.3 | Cables | 18512.6 | 0 | 18512.6 |  | 0
1.4.1.4.4 | Installation | 23067 | 0 | 23067 |  | 0
1.4.2 | LUMINOSITY MONITOR | 136370 | 6057 | 124209.41 | 0 | 6103.59
1.4.2.1 | PMT and Asssociated Hardware | 1545 | 0 | 1545 |  | 0
1.4.2.2 | PMT and Asssociated Hardware | 53664 | 0 | 53664 |  | 0
1.4.2.3 | Mechanical Support & Enclosures | 10000 | 0 | 10000 |  | 0
1.4.2.4 | Electronics | 71161 | 6057 | 59000.41 | 0 | 6103.59
1.4.2.4.1 | Luminosity Monitor Electronics | 48000 | 6057 | 35839 |  | 6104
1.4.2.4.2 | Accelerator Diagnostic DAQ | 11661 | 0 | 11661.41 |  | -0.41
1.4.2.4.3 | Cables & Connectors | 11500 | 0 | 11500 |  | 0
1.4.2.4.4 | Timing Discriminators | 0 | 0 | 0 |  | 0
1.4.3 | LEVEL 1 | 1502610 | 49522.035 | 1119962.26 | 0 | 333125.705 | 20000 | 0
1.4.3.1 | Calorimeter L1 Trigger | 206444 | 0 | 48293.38 | 0 | 158150.62
1.4.3.1.1 | Engineering & Design | 0 | 0 | 0 |  | 0
1.4.3.1.2 | Installation | 0 | 0 | 0 |  | 0
1.4.3.1.3 | Readout to L2 and L3 | 46000 | 0 | 0 |  | 46000
1.4.3.1.4 | Quadrant Signal Generation | 24900 | 0 | 0 |  | 24900
1.4.3.1.5 | Trigger Pickoff Signals | 41900 | 0 | 0 |  | 41900
1.4.3.1.6 | Timing Signal Generation and Distrib | 6800 | 0 | 0 |  | 6800
1.4.3.1.7 | Cal L1 to TCC Interface | 1200 | 0 | 0 |  | 1200
1.4.3.1.8 | VRB Readout Cards | 72444 | 0 | 48293.38 |  | 24150.62
1.4.3.1.9 | VRB Controller Card | 1000 | 0 | 0 |  | 1000
1.4.3.1.10 | Crates & power | 12200 | 0 | 0 |  | 12200
1.4.3.2 | Muon L1 Trigger | 1035608 | 9215.635 | 1024610.6 | 0 | 1781.765
1.4.3.2.1 | MTCXX Card | 135700 | 0 | 135700 | 0 | 0
1.4.3.2.1.1 | Engineering | 12300 | 0 | 12300 |  | 0
1.4.3.2.1.2 | Parts | 59400 | 0 | 59400 |  | 0
1.4.3.2.1.3 | Layout | 10000 | 0 | 10000 |  | 0
1.4.3.2.1.4 | Fabrication | 27000 | 0 | 27000 |  | 0
1.4.3.2.1.5 | Assembly | 27000 | 0 | 27000 |  | 0
1.4.3.2.2 | MTFB Board (4 types) | 97748 | 0 | 97748 | 0 | 0
1.4.3.2.2.1 | Engineering | 0 | 0 | 0 |  | 0
1.4.3.2.2.2 | Parts | 68148 | 0 | 68148 |  | 0
1.4.3.2.2.3 | Layout | 8000 | 0 | 8000 |  | 0
1.4.3.2.2.4 | Fabrication | 16200 | 0 | 16200 |  | 0
1.4.3.2.2.5 | Assembly | 5400 | 0 | 5400 |  | 0
1.4.3.2.3 | MTCM Card | 42750 | 0 | 42750 | 0 | 0
1.4.3.2.3.1 | Engineering | 12300 | 0 | 12300 |  | 0
1.4.3.2.3.2 | Parts | 14700 | 0 | 14700 |  | 0
1.4.3.2.3.3 | Layout | 3500 | 0 | 3500 |  | 0
1.4.3.2.3.4 | Fabrication | 8750 | 0 | 8750 |  | 0
1.4.3.2.3.5 | Assembly | 3500 | 0 | 3500 |  | 0
1.4.3.2.4 | SLDB Transmitter Boards | 33280 | 0 | 33280 | 0 | 0
1.4.3.2.4.1 | Engineering | 0 | 0 | 0 |  | 0
1.4.3.2.4.2 | Parts | 22100 | 0 | 22100 |  | 0
1.4.3.2.4.3 | Layout | 0 | 0 | 0 |  | 0
1.4.3.2.4.4 | Fabrication | 4680 | 0 | 4680 |  | 0
1.4.3.2.4.5 | Assembly | 6500 | 0 | 6500 |  | 0
1.4.3.2.5 | SLDB Receiver Boards | 236800 | 0 | 236800 | 0 | 0
1.4.3.2.5.1 | Engineering | 0 | 0 | 0 |  | 0
1.4.3.2.5.2 | Parts | 157250 | 0 | 157250 |  | 0
1.4.3.2.5.3 | Layout | 0 | 0 | 0 |  | 0
1.4.3.2.5.4 | Fabrication | 33300 | 0 | 33300 |  | 0
1.4.3.2.5.5 | Assembly | 46250 | 0 | 46250 |  | 0
1.4.3.2.6 | MCEN Cards | 146730 | 0 | 146670 | 0 | 60
1.4.3.2.6.1 | Engineering | 10000 | 0 | 10000 |  | 0
1.4.3.2.6.2 | Parts | 92380 | 0 | 92320 |  | 60
1.4.3.2.6.3 | Layout | 5600 | 0 | 5600 |  | 0
1.4.3.2.6.4 | Fabrication | 27900 | 0 | 27900 |  | 0
1.4.3.2.6.5 | Assembly | 10850 | 0 | 10850 |  | 0
1.4.3.2.7 | Physics Board (2 types) | 56130 | 0 | 56130 | 0 | 0
1.4.3.2.7.1 | Engineering | 2800 | 0 | 2800 |  | 0
1.4.3.2.7.2 | Parts | 44640 | 0 | 44640 |  | 0
1.4.3.2.7.3 | Layout | 2800 | 0 | 2800 |  | 0
1.4.3.2.7.4 | Fabrication | 4340 | 0 | 4340 |  | 0
1.4.3.2.7.5 | Assembly | 1550 | 0 | 1550 |  | 0
1.4.3.2.8 | MCCM Card | 33600 | 0 | 33600 | 0 | 0
1.4.3.2.8.1 | Engineering | 5600 | 0 | 5600 |  | 0
1.4.3.2.8.2 | Parts | 11200 | 0 | 11200 |  | 0
1.4.3.2.8.3 | Layout | 5600 | 0 | 5600 |  | 0
1.4.3.2.8.4 | Fabrication | 8750 | 0 | 8750 |  | 0
1.4.3.2.8.5 | Assembly | 2450 | 0 | 2450 |  | 0
1.4.3.2.9 | Muon Trigger VME Crates | 135500 | 9005.635 | 125634 | 0 | 860.365
1.4.3.2.9.1 | L1 VME Crates and Backplane | 24500 | 0 | 24500 |  | 0
1.4.3.2.9.2 | MCEN VME Crates | 6000 | 0 | 6000 |  | 0
1.4.3.2.9.3 | MCEN Backplane | 15000 | 0 | 15000 |  | 0
1.4.3.2.9.4 | Microprocessor (mve162) | 30000 | 0 | 34366 |  | -4366
1.4.3.2.9.5 | Microprocessor Extender | 5000 | 0 | 5000 |  | 0
1.4.3.2.9.6 | Extender Cards | 15000 | 0 | 15000 |  | 0
1.4.3.2.9.7 | Power Supplies | 35000 | 8490.635 | 25768 |  | 741.365
1.4.3.2.9.8 | Cooling | 0 | 0 | 0 |  | 0
1.4.3.2.9.9 | Additional Crate Parts | 5000 | 515 | 0 |  | 4485
1.4.3.2.10 | Cabling | 81870 | 0 | 82298.6 | 0 | -428.6
1.4.3.2.10.1 | Detector SLDB Cable | 31200 | 0 | 31628.6 |  | -428.6
1.4.3.2.10.2 | Detector SLDB Cable Connectors | 21600 | 0 | 21600 |  | 0
1.4.3.2.10.3 | Board SLDB Cable | 570 | 0 | 570 |  | 0
1.4.3.2.10.4 | Board SLDB Cable Connectors | 13300 | 0 | 13300 |  | 0
1.4.3.2.10.5 | Timing, Trigger Cable | 1000 | 0 | 1000 |  | 0
1.4.3.2.10.6 | Timing, Trigger Cable Connectors | 200 | 0 | 200 |  | 0
1.4.3.2.10.7 | Cabling Supplies, Testers | 2000 | 0 | 2000 |  | 0
1.4.3.2.10.8 | Splitter Boards | 10500 | 0 | 10500 |  | 0
1.4.3.2.10.9 | Splitter Crates | 1500 | 0 | 1500 |  | 0
1.4.3.2.11 | Accessory Cards | 5000 | 0 | 5000 | 0 | 0
1.4.3.2.11.1 | Engineering | 0 | 0 | 0 |  | 0
1.4.3.2.11.2 | Parts | 0 | 0 | 0 |  | 0
1.4.3.2.11.3 | Layout | 0 | 0 | 0 |  | 0
1.4.3.2.11.4 | Fabrication | 0 | 0 | 0 |  | 0
1.4.3.2.11.5 | Assembly | 0 | 0 | 0 |  | 0
1.4.3.2.11.6 | Test Equipment (PCs, etc.) | 5000 | 0 | 5000 |  | 0
1.4.3.2.12 | Hardware and Software Support | 30500 | 210 | 29000 | 0 | 1290
1.4.3.2.12.1 | Additional Hardware | 4500 | 210 | 3000 |  | 1290
1.4.3.2.12.2 | Additional Software | 5000 | 0 | 5000 |  | 0
1.4.3.2.12.3 | Altera Key at Fermilab (2 years) | 6000 | 0 | 6000 |  | 0
1.4.3.2.12.4 | AZ Technician Labor | 7500 | 0 | 7500 |  | 0
1.4.3.2.12.5 | BU Technician Labor | 7500 | 0 | 7500 |  | 0
1.4.3.3 | Central Fiber Tracker L1 Trigger | 260558 | 40306.4 | 47058.28 | 0 | 173193.32 | 20000
1.4.3.3.1 | Front End | 117272 | 0 | 9840.33 |  | 107431.67
1.4.3.3.2 | Receivers | 80066 | 0 | 37217.95 |  | 42848.05
1.4.3.3.3 | Concentrator L1 | 5004 | 0 | 0 |  | 5004
1.4.3.3.4 | Concentrator L2 | 10536 | 0 | 0 |  | 10536
1.4.3.3.5 | Racks | 42862 | 40306.4 | 0 |  | 2555.6
1.4.3.3.6 | CFT Trigger Manager | 4818 | 0 | 0 |  | 4818
1.4.4 | LEVEL 2 | 2047110 | 98981.12 | 1002302 | 546672 | 399154.88 | 10000 | 62000
1.4.4.1 | L1.5 Calorimeter Electron Trigger | 265564 | 0 | 265564 | 0 | 0
1.4.4.1.1 | L1 Interface | 104564 | 0 | 104564 |  | 0
1.4.4.1.2 | DSP System | 100000 | 0 | 100000 |  | 0
1.4.4.1.3 | Software Development | 61000 | 0 | 61000 |  | 0
1.4.4.2 | L2 Trigger Components | 1445046 | 98981.12 | 574738 | 446672 | 324654.88 | 10000 | 62000
1.4.4.2.1 | Alpha in VME | 300758 | 66440.12 | 75005 | 142737 | 16575.88 | 0 | 40000
1.4.4.2.1.1 | Engineering & Design | 5000 | 0 | 0 |  | 5000
1.4.4.2.1.2 | Prototypes | 56491 | 61491 | 2000 |  | -7000 |  | 30000
1.4.4.2.1.3 | Final Card | 239267 | 4949.12 | 73005 | 142737 | 18575.88 |  | 10000
1.4.4.2.2 | MBT (Magic Bus Transceiver) | 390000 | 0 | 235000 | 0 | 155000 | 0 | 10000
1.4.4.2.2.1 | Engineering & Design | 204000 | 0 | 100000 |  | 104000 |  | 10000
1.4.4.2.2.2 | Prototypes | 33000 | 0 | 25000 |  | 8000
1.4.4.2.2.3 | Final Card | 153000 | 0 | 110000 |  | 43000
1.4.4.2.3 | SLIC (Serial Link Interface) | 291772 | 0 | 120000 | 171772 | 0
1.4.4.2.3.1 | Engineering & Design | 116718 | 0 | 100000 | 16718 | 0
1.4.4.2.3.2 | Prototypes | 32211 | 0 | 20000 | 12211 | 0
1.4.4.2.3.3 | Final Card | 142843 | 0 | 0 | 142843 | 0
1.4.4.2.4 | SCL Fanout | 61400 | 21692 | 39708 | 0 | 0 | 0 | 2000
1.4.4.2.4.1 | Engineering & Design | 14400 | 9400 | 5000 |  | 0
1.4.4.2.4.2 | Prototypes | 9891 | 6405 | 3486 |  | 0 |  | 2000
1.4.4.2.4.3 | Fanout SFO | 37109 | 5887 | 31222 |  | 0
1.4.4.2.5 | Fiber Input Converter | 96000 | 0 | 0 | 96000 | 0
1.4.4.2.5.1 | Engineering & Design | 24000 | 0 | 0 | 24000 | 0
1.4.4.2.5.2 | Prototypes | 12000 | 0 | 0 | 12000 | 0
1.4.4.2.5.3 | Final Card | 60000 | 0 | 0 | 60000 | 0
1.4.4.2.6 | Mbus Backplane | 62629 | 10849 | 4507 | 0 | 47273 | 0 | 10000
1.4.4.2.6.1 | Engineering & Design | 0 | 0 | 0 |  | 0
1.4.4.2.6.2 | Prototypes | 23322 | 1548.5 | 0 |  | 21773.5 |  | 5000
1.4.4.2.6.3 | Final Card | 39307 | 9300.5 | 4507 |  | 25499.5 |  | 5000
1.4.4.2.7 | Bit 3 MPM | 72387 | 0 | 53824 | 18363 | 200
1.4.4.2.8 | PC | 11500 | 0 | 11494 |  | 6
1.4.4.2.9 | Cables | 30000 | 0 | 0 |  | 30000
1.4.4.2.10 | Crates | 128600 | 0 | 35200 | 17800 | 75600 | 10000 | 0
1.4.4.2.10.1 | VME | 53000 | 0 | 35200 | 17800 | 0
1.4.4.2.10.2 | Power | 57600 | 0 | 0 | 0 | 57600 | 5000
1.4.4.2.10.3 | Monitoring and Cooling | 12000 | 0 | 0 |  | 12000 | 5000
1.4.4.2.10.4 | Rack | 6000 | 0 | 0 |  | 6000
1.4.4.3 | System ED&I | 54000 | 0 | 42000 |  | 12000
1.4.4.4 | Calorimeter Preprocessor | 172000 | 0 | 48000 | 100000 | 24000
1.4.4.4.1 | L2 Calorimeter ED&I | 72000 | 0 | 48000 |  | 24000
1.4.4.4.2 | Calorimeter Inputs | 100000 | 0 | 0 | 100000 | 0
1.4.4.5 | L2 Muon | 10000 | 0 | 0 | 0 | 10000
1.4.4.5.1 | L2 Muon ED&I | 10000 | 0 | 0 |  | 10000
1.4.4.5.2 | Development Hardware | 0 | 0 | 0 |  | 0
1.4.4.5.3 | Simulation Software | 0 | 0 | 0 |  | 0
1.4.4.6 | L2 CFT | 12000 | 0 | 6000 |  | 6000
1.4.4.7 | L2 Preshower | 6000 | 0 | 0 |  | 6000
1.4.4.8 | L2 Global ED&I | 60000 | 0 | 48000 |  | 12000
1.4.4.9 | Test Stand ED&I | 22500 | 0 | 18000 |  | 4500
1.4.5 | LEVEL 3 | 1049036 | 9342 | 813662.5 | 0 | 226031.5 | 5000 | 0
1.4.5.1 | Engineering & Design | 331167 | 0 | 331167 |  | 0
1.4.5.2 | Bandwidth Expansion | 27900 | 0 | 27900 | 0 | 0 | 5000 | 0
1.4.5.2.1 | VBD upgrade VME readout | 27900 | 0 | 27900 |  | 0 | 5000
1.4.5.3 | Level 3 Nodes | 317800 | 0 | 92800 | 0 | 225000
1.4.5.3.1 | Processor Upgrade | 225000 | 0 | 0 |  | 225000
1.4.5.3.2 | Processor Bus Adapter | 72000 | 0 | 72000 |  | 0
1.4.5.3.3 | L3 Rack Upgrades | 10800 | 0 | 10800 |  | 0
1.4.5.3.4 | L3 Supervisor and Inerfaces | 10000 | 0 | 10000 |  | 0
1.4.5.4 | Readout control | 244000 | 0 | 244000 | 0 | 0
1.4.5.4.1 | Collector Cards and Fiber | 60000 | 0 | 60000 |  | 0
1.4.5.4.2 | Distributor Controllers | 111000 | 0 | 111000 |  | 0
1.4.5.4.3 | Event Tag Generator, Interfaces | 10000 | 0 | 10000 |  | 0
1.4.5.4.4 | Multiport Memory Daughter Cards | 48000 | 0 | 48000 |  | 0
1.4.5.4.5 | Monitoring and Diagnostic Systems | 15000 | 0 | 15000 |  | 0
1.4.5.5 | SCL and HUB System | 128169 | 9342 | 117795.5 | 0 | 1031.5
1.4.5.5.1 | Trigger Hub | 13899 | 0 | 13899.2 |  | -0.2
1.4.5.5.2 | Serial Line Fanout | 33020 | 0 | 33020 |  | 0
1.4.5.5.3 | Status Concentrator | 9150 | 0 | 9149.98 |  | 0.02
1.4.5.5.4 | Serial Receiver | 67750 | 9342 | 57376.3 |  | 1031.7
1.4.5.5.5 | J3 Backplane | 4350 | 0 | 4350.02 |  | -0.02
1.4.5.5.6 | Cabling | 0 | 0 | 0 |  | 0
1.5 | ONLINE COMPUTING | 746000 | 137863.4 | 293369.69 | 0 | 314766.91 | 0 | 68000
1.5.1 | ONLINE EQUIPMENT | 746000 | 137863.4 | 293369.69 | 0 | 314766.91 | 0 | 68000
1.5.1.1 | Workstations | 391000 | 97395 | 109458 | 0 | 184147 | 0 | 0
1.5.1.1.1 | DAQ Wrkstns (CPU,mem,netwk,IO,soft) | 197000 | 7995 | 88179 |  | 100826
1.5.1.1.2 | Monitoring Workstations | 194000 | 89400 | 21279 |  | 83321
1.5.1.2 | Network (switch,bridge,router) | 110000 | 16010 | 79634.92 |  | 14355.08
1.5.1.3 | Disk/tape Peripherals | 155000 | 24458.4 | 57539.8 | 0 | 73001.8 | 0 | 65000
1.5.1.3.1 | Disk | 145000 | 24458.4 | 57539.8 |  | 63001.8 |  | 65000
1.5.1.3.2 | Tape | 10000 | 0 | 0 |  | 10000
1.5.1.4 | Printers/Monitors | 60000 | 0 | 20062.53 |  | 39937.47
1.5.1.5 | Software | 30000 | 0 | 26674.44 |  | 3325.56 |  | 3000
Note on C15: Philip Michael Tuts: 2/11/00 increased by 101,080 to account fr actuals + $40,970 of CSEM order that should be on 1.1.1.3.3
Note on C16: Philip Michael Tuts: 2/10/00 take back 5000 to close out because it was moved to operating
Note on C18: Philip Michael Tuts: 2/10/00 added 555 to close this out 2/25/00 add 107 to close out
Note on C19: Philip Michael Tuts: 2/10/00 take back 10k as per discussion with Ron & marel
Note on C20: Philip Michael Tuts: 2/10/00 add 1935 to close this out 2/25/00 add 215 to close out
Note on C23: Philip Michael Tuts: 2/10/00 add 14750 to close this out, note this includes $23390 of CSEM order that belongs on 1.1.1.3.3
Note on C24: Philip Michael Tuts: 2/10/00 remove 60k as per Ron & Marcel discussion
Note on D25: Philip Michael Tuts: 2/10/00 removed 11,300 to operating
Note on C25: Philip Michael Tuts: 2/10/00 inceased by 35 to close out
Note on C26: Philip Michael Tuts: 2/10/00 added 2k after speaking with Ron & Marcel
Note on C27: Philip Michael Tuts: 2/10/00 added 3286 to closeout overrun + 3k for future spending
Note on D29: Philip Michael Tuts: 2/10/00 removed 25708 to operating
Note on C31: Philip Michael Tuts: 2/10/00 removed 15k to close it out
Note on C33: Philip Michael Tuts: 2/10/00 added 9712 to balance overrun + 21k for future needs 3/1/00 add 72450 + 10750+8000 that was on operating "spares"
Note on C36: Philip Michael Tuts: 2/10/00 removed 20k to operating
Note on C42: Philip Michael Tuts: 2/10/00 added 655 to close out
Note on C41: Philip Michael Tuts: 2/10/00 note that $70.2k has been put on operating
Note on C48: Philip Michael Tuts: 2/10/00 there is some exposure here while they understand whether Al Clark will be billing us
Note on C51: Philip Michael Tuts: 2/10/00 add 10038 for additional HDI spares
Note on D52: Philip Michael Tuts: 2/10/00 15200 was moved to operating 3/1/00 put back 16620 from operating 3/25/00 add 7600 for Feb (believe will save when Speedy ordr closes)
Note on C52: Philip Michael Tuts: 2/10/00 add 14237 to close out 3/1/00 add back the "operating" reqs 16620
Note on G54: Philip Michael Tuts: 2/10/00 we might have an additional exposure of $60k here due to coax piece
Note on G58: Philip Michael Tuts: 2/10/00 Marcel & Ron will check this ETC
Note on C58: Philip Michael Tuts: note that $90k of KSU SWF was put on operating
Note on E60: Philip Michael Tuts: 2/10/00 leave but Cooper says this is really fiber tracker
Note on C60: Philip Michael Tuts: 2/10/00 add $10k because Marcel & Ron nervous about this low balance
Note on G64: Philip Michael Tuts: 2/10/00 Marcel & Ron checkimg -- this might be returned
Note on C66: Philip Michael Tuts: 2/10/00 add $5k because of general unease
Note on C67: Philip Michael Tuts: 2/10/00 add $5k because of general unease
Note on C68: Philip Michael Tuts: 2/10/00 add $5k because of general unease
Note on C75: Philip Michael Tuts: 2/10/00 add 57656 to account for additional shop charges 2/24/00 add 6985 for Jan charges 5/4/00 112-050300-01 Change request to increase by 16590 approved by K. Stanfield.
Note on C76: Philip Michael Tuts: 2/10/00 add 2036 to close out
Note on C77: Philip Michael Tuts: 2/10/00 add 43875.5 to account for additional shop charges
Note on C81: Philip Michael Tuts: 2/10/00 add 3352 to close it out
Note on C82: Philip Michael Tuts: 2/10/00 remove $3k based on new estimate
Note on C83: Philip Michael Tuts: 2/10/00 remove 24190 to close out 2/24/00 add 80 for Jan 5/4/00 112-050300-02 Change request to increase by 1592 approved by K. Stanfield.
Note on C85: Philip Michael Tuts: 2/10/00 add 16063 to close out (shipping charges) 3/1/00 add 75000 for charges that were to be on operating 3/22/00 reduce by 25000 and add to 1.1.2.4.1.2 as per Cooper Comm. Rec. 5/4/00 112-042000-01 Change request to increase by 45000 approved by K. Stanfield and P. Philp. 5/17/00 add 45000 from 1.4.5.3.1 (15K) and from transfer of Solenoid AIP funds (30K) per Mike e-mail 5/3/00.
Note on C86: Philip Michael Tuts: 2/10/00 remove $4k based on talk with Alan
Note on D90: Philip Michael Tuts: 2/10/00 canceled 3900
Note on C95: Philip Michael Tuts: 2/10/00 add 108325 to close out -- due to ~$73k shop charges + $25k sundries 3/22/00 add 25000 as per Cooper Comm recs from 1.1.2.3.1
Note on C97: Philip Michael Tuts: 2/10/00 add 81643 for shop charges -- these are NOT understood 3/1/00 add 25000 that projected to be on operating
Note on C98: Philip Michael Tuts: 2/10/00 there is a potential $10k risk here
Note on C101: Philip Michael Tuts: 2/10/00 add 1572 to close out
Note on C103: Philip Michael Tuts: 2/10/00 add 17290 to close out - wastage 2/24/00 add 2829 to cover Jan spending, remove from 1.1.2.5.2.2
Note on G104: Philip Michael Tuts: 2/10/00 this may not be all needed?
Note on C109: Philip Michael Tuts: 2/10/00 add $10k because of nervousness 3/22/00 reduce cost by 10000 as per Cooper Comm rec. and add to 1.1.2.5.3.2
Note on C115: Philip Michael Tuts: 2/10/00 add $5k for nervousness
Note on C135: Philip Michael Tuts: 2/10/00 add 18645 for close out -- shop charges??
Note on C138: Philip Michael Tuts: 2/10/00 add 165 to close out
Note on C140: Philip Michael Tuts: 2/10/00 remove 2000
Note on C141: Philip Michael Tuts: 2/10/00 careful -- these are shop charges!
Note on C142: Philip Michael Tuts: 2/10/00 add 50641 for shop charges
Note on C194: Philip Michael Tuts: 2/10/00 add 47 to close out
Note on C201: Philip Michael Tuts: 2/10/00 add 8 to close out
Note on C202: Philip Michael Tuts: 2/10/00 add 689 to close out
Note on C206: Philip Michael Tuts: 2/10/00 remove 10 to close out
Note on C224: Philip Michael Tuts: 2/10/00 remove 375 to close out
Note on C232: Philip Michael Tuts: 2/10/00 add 90 to close out
Note on C246: Philip Michael Tuts: 2/12/00 add 180 to close out
Note on C249: Philip Michael Tuts: 2/12/00 add 13432 to account for overrun, but make up from 1.1.5.2.1.3-1.1.5.2.1.5 as per Marvin disussion 2/24/00 add 1420 in Jan to cover overrun and close? 5/17/00 add 450 from 1.1.5.2.1.5, 1.1.5.2.2.1, & 1.1.5.2.3.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C251: Philip Michael Tuts: 2/12/00 remove 6432 (see 1.1.5.2.1.1) 5/17/00 add 5725 from 1.1.5.2.1.5, 1.1.5.2.2.1, & 1.1.5.2.3.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C252: Philip Michael Tuts: 2/12/00 remove 5000 (see 1.1.5.2.1.1) 2/24/00 add 2064 to cover overrun in Jan 5/17/00 add 1302 from 1.1.5.2.1.5, 1.1.5.2.2.1, & 1.1.5.2.3.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C253: Philip Michael Tuts: 2/12/00 remove 2000 (see 1.1.5.2.1.1) 5/17/00 remove 2000 to cover overrun in 1.1.5.2.1.1 - 1.1.5.2.1.4 & 1.1.5.2.3.3 per Marvin / Mike e-mail 4/28/00.
Note on C255: Philip Michael Tuts: 2/12/00 add 6k as per Marvin -these are spares 5/17/00 remove 6000 to cover overrun in 1.1.5.2.1.1 - 1.1.5.2.1.4 & 1.1.5.2.3.3 per Marvin / Mike e-mail 4/28/00.
Note on C257: Philip Michael Tuts: 2/14/00 add 640 to close out 2/24/00 add 4015 to cover overrun in Jan
Note on C258: Philip Michael Tuts: 2/14/00 add 6k as per Marvin 5/17/00 remove 147 to cover overrun in 1.1.5.2.1.1 - 1.1.5.2.1.4 & 1.1.5.2.3.3 per Marvin / Mike e-mail 4/28/00.
Note on C259: Philip Michael Tuts: 2/14/00 add 19127 to absorb overrun, then add 5600 as per Marvin - not sure why now? 5/17/00 add 102 from 1.1.5.2.1.5, 1.1.5.2.2.1, & 1.1.5.2.3.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C260: Philip Michael Tuts: 2/14/00 add 46 to close out
Note on G261: Philip Michael Tuts: 2/14/00 expect we might recoup $15k at some point
Note on C270: Philip Michael Tuts: 2/14/00 add 3k as per Marvin 2/24/00 add 5995 to cover overun, make up from 1.1.5.3.6.6
Note on C275: Philip Michael Tuts: 2/14/00 remove 3800 as per Marvin, to make up for 1.1.5.3.3.4 overrun 3/14/00 add 4040 from 1.1.5.3.1.9 prior yr correction 5/17/00 add 5354 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C284: Philip Michael Tuts: 2/14/00 add 3805 to cover overrun 3/14/00 add 5200 from 1.1.5.3.6.3
Note on C296: Philip Michael Tuts: 2/14/00 add 25 to close out
Note on C302: Philip Michael Tuts: 2/14/00 add 5 to close out
Note on C310: Philip Michael Tuts: 2/14/0 add 6720 to cover overrun 2/24/00 add 1364 to cover overun, make up from 1.1.5.3.6.6 3/14/00 add 5646 from 1.1.5.3.5.3, 1819 from 1.1.5.3.5.4, 3610 from 1.1.5.3.5.5, 9499 from 1.1.5.3.6.6, 1742 from 1.1.5.3.6.7
Note on C314: Philip Michael Tuts: 2/14/00 remove 1000 as per Marvin 3/14/00 remove 3400 to cover 1.1.5.3.6.9
Note on C377: Philip Michael Tuts: 2/14/00 add 8700 to cover overrun for parts losses in assembly 2/24/00 add 36 to close out
Note on C384: Philip Michael Tuts: 2/14/00 add 2351 to cover overruns
Note on C391: Philip Michael Tuts: 2/14/00 add 27 to close out
Note on C386: Philip Michael Tuts: 2/14/00 add 52 to close out
Note on C396: Philip Michael Tuts: 2/14/00 add 870 to cover overruns
Note on C398: Philip Michael Tuts: 2/14/00 add 2335 to cover overruns
Note on C406: Philip Michael Tuts: 2/14/00 add 6650 to cover additional packing needs to cover low yields 2/24/00 add 4033 for PO amount?
Note on C690: Philip Michael Tuts: 2/15/00 removed 4355 to close out
Note on C691: Philip Michael Tuts: 2/15/00 removed 1361 to close out
Note on C692: Philip Michael Tuts: 2/15/00 removed 662 to close out
Note on C693: Philip Michael Tuts: 2/15/00 removed 1920 to close out
Note on C694: Philip Michael Tuts: 2/15/00 removed 1371 to close out
Note on C695: Philip Michael Tuts: 2/15/00 removed 1633 to close out
Note on C696: Philip Michael Tuts: 2/15/00 removed 1168 to close out 2/24/00 add 2373 to cover overrun and cover from 1.3.4.4.2
Note on C697: Philip Michael Tuts: 2/15/00 add 6228 to close out 2/24/0 add 603 and cover from 1.3.4.4.2
Note on C698: Philip Michael Tuts: 2/15/00 removed 1307 to close out
Note on C699: Philip Michael Tuts: 2/15/00 removed 1694 to close out
Note on C700: Philip Michael Tuts: 2/15/00 removed 8711 to close out
Note on C703: Philip Michael Tuts: 2/15/00 add 91395 + 9605 to cover overrun 2/24/00 add 66856 to cover Jan and reduce 1.3.4.3.3 by same amount 5/17/00 add 21214 from 1.3.4.3.3 to cover overrun per Mike e-mail 5/3/00.
Note on C704: Philip Michael Tuts: 2/15/00 add $101k to cover overrun 2/24/00 remove 66856 to cover 1.3.4.3.2 and 5189 to cover 1.3.4.7.1 3/24/00 add 30000 to over the rework of the shielding 5/17/00 remove 21214 to cover overrun in 1.3.4.3.2 per Mike e-mail 5/3/00.
Note on C706: Philip Michael Tuts: 2/15/00 add 431 to close out 2/24/00 add 930 to cover Jan and remove from 1.3.4.4.2
Note on C707: Philip Michael Tuts: 2/15/00 add 45000 to cover overrun 2/24/00 remove 930 to cover 1.3.4.4.1 overrun 3/23/00 add 7000 as per Cooper Comm recs
Note on C710: Philip Michael Tuts: 2/15/00 remove 780 to close out
Note on C711: Philip Michael Tuts: 2/15/00 removed 2401 to close out
Note on C712: Philip Michael Tuts: 2/15/00 add 48 to close out
Note on C713: Philip Michael Tuts: 2/15/00 removed 1028 to close out
Note on C716: Philip Michael Tuts: 2/15/00 removed 23889 to close out
Note on C717: Philip Michael Tuts: 2/15/00 removed 44000 to close out
Note on C647: Philip Michael Tuts: 2/15/00 add 25000 to close out and account for this item
Note on C649: Philip Michael Tuts: 2/15/00 add 4340 to close out
Note on F653: Philip Michael Tuts: 2/15/00 increase by 100 to match cost estimate and close out -- done
Note on F656: Philip Michael Tuts: 2/15/00 decrease by 100 to match cost estimate and close out - done
Note on G653: Philip Michael Tuts: 2/15/00 subtract the completed foreign contribution
Note on G656: Philip Michael Tuts: 2/15/00 subtract the completed foreign contribution
Note on G658: Philip Michael Tuts: 2/15/00 subtract the completed foreign contribution
Note on G659: Philip Michael Tuts: 2/15/00 subtract the completed foreign contribution
Note on G660: Philip Michael Tuts: 2/15/00 subtract the completed foreign contribution
Note on F660: Philip Michael Tuts: 2/15/00 remove 134 to match cost estimate and close out - done
Note on C662: Philip Michael Tuts: 2/15/00 add 11320 to cover overrun and close out
Note on C663: Philip Michael Tuts: 2/15/00 add 1569 to cover overrun and close out
Note on C664: Philip Michael Tuts: 2/15/00 add 1696 to cover overrun and close out
Note on C666: Philip Michael Tuts: 2/15/00 add 4850 + 76150 to cover overrun
Note on C668: Philip Michael Tuts: 2/15/00 remove 2000 to close out
Note on C670: Philip Michael Tuts: 2/15/00 add 689 to close out
Note on C674: Philip Michael Tuts: 2/15/00 add 827 to close out, comes from 1.3.3.8.5
Note on C676: Philip Michael Tuts: 2/15/00 add 29899 for overrun, take from 1.3.3.8.5
Note on C678: Philip Michael Tuts: 2/15/00 reduce by 29899 and 827 to cover overruns in 1.3.3.8.1&3
Note on C680: Philip Michael Tuts: 2/15/00 reduce by 23940
Note on C981: Philip Michael Tuts: 2/15/00 remove 2000 to close out
Note on C982: Philip Michael Tuts: 2/15/00 remove 13850 to close out
Note on C984: Philip Michael Tuts: 2/15/00 remove 4680 to close out
Note on C985: Philip Michael Tuts: 2/15/00 remove 1110 to close out
Note on G481: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G482: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G483: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G484: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G485: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G487: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G488: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G489: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G490: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on G491: Philip Michael Tuts: 2/15/00 spent by French, so remove it from balance
Note on C482: Philip Michael Tuts: 2/15/00 add 15 to close out
Note on C484: Philip Michael Tuts: 2/15/00 add 1139 to close out
Note on C492: Philip Michael Tuts: 2/15/00 subtract 34 to close out
Note on G568: Philip Michael Tuts: 2/15/00 this is done, remove from the balance
Note on C602: Philip Michael Tuts: 2/16/00 add 45 to close out
Note on C603: Philip Michael Tuts: 2/16/00 remove 94 to close out
Note on C604: Philip Michael Tuts: 2/16/00 remove 520 to close out
Note on C606: Philip Michael Tuts: 2/16/00 add 1487 to close out
Note on C608: Philip Michael Tuts: 12/16/00 add 20 to close out
Note on C609: Philip Michael Tuts: 12/16/00 add 19827 to close out overrun
Note on C610: Philip Michael Tuts: 12/16/00 remove 270 to close out
Note on C611: Philip Michael Tuts: 12/16/00 add 3526 to close out -- but need to check with Sherie
Note on C613: Philip Michael Tuts: 12/16/00 add 837 to close out
Note on C614: Philip Michael Tuts: 12/16/00 remove 373 to close out
Note on C618: Philip Michael Tuts: 12/16/00 add 372 to close out - check w/ Sherie because Tom thinks there may be another $5k?
Note on C619: Philip Michael Tuts: 12/16/00 close out, support elsewhere?
Note on G621: Philip Michael Tuts: 12/16/00 remove this contribution from the balance
Note on G623: Philip Michael Tuts: 12/16/00 remove this contribution from the balance
Note on C627: Philip Michael Tuts: 12/16/00 remove 446 to lose out
Note on C628: Philip Michael Tuts: 2/16/00 add 20904 to close out and cover overrun
Note on G633: Philip Michael Tuts: 12/16/00 remove this contribution from the balance - done
Note on G634: Philip Michael Tuts: 12/16/00 remove this contribution from the balance - done
Note on G635: Philip Michael Tuts: 12/16/00 remove this contribution from the balance - done
Note on C643: Philip Michael Tuts: 12/16/00 remove 650 to close out
Note on G923: Philip Michael Tuts: 2/16/00 remove the non-DOE contribution from the balance
Note on G931: Philip Michael Tuts: 2/16/00 remove 174k of non-DOE funds from the balance
Note on G937: Philip Michael Tuts: 2/16/00 remove 24k non-DOE funds from balance
Note on G938: Philip Michael Tuts: 2/16/00 remove 12k non-DOE funds from balance
Note on G939: Philip Michael Tuts: 2/16/00 remove 60k non-DOE funds from balance
Note on G949: Philip Michael Tuts: 2/16/00 remove 18k of non-DOE contribution from balance
Note on G955: Philip Michael Tuts: 2/16/00 removing 167.5k in non-DOE funds, but note this makes little sense since total cost is 100k!
Note on C965: Philip Michael Tuts: 2/16/00 dd 167 to close out
Note on C320: Philip Michael Tuts: 2/16/00 add 1012 to close out?
Note on C551: Philip Michael Tuts: 2/22/00 add 1160 to close out
Note on C536: Philip Michael Tuts: 2/22/00 add 624 to close out
Note on C538: Philip Michael Tuts: 2/22/00 add 176 to close out
Note on C760: Philip Michael Tuts: 2/22/00 add 19 to close out
Note on C762: Philip Michael Tuts: 2/22/00 add 1350 to close out 3/23/00 add 500 as per Coopr Comm recs
Note on C768: Philip Michael Tuts: 2/22/00 significant $50k exposure if we have to trash and redo
Note on C779: Philip Michael Tuts: 2/22/00 add 1534 to close out 3/23/00 remove 652 to close out as per Cooper Comm rec
Note on C769: Philip Michael Tuts: 2/22/00 add 1628 to balance, and make up from 1.3.5.4.2.2 3/23/00 add 40000 as per Cooper Comm for new MFC
Note on C770: Philip Michael Tuts: 2/22/00 remove 1628 to accommodate overrun in 1.3.5.4.2.1
Note on C775: Philip Michael Tuts: 2/22/00 remove 584 to close out
Note on C425: Philip Michael Tuts: 2/23/00 add 1116 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C427: Philip Michael Tuts: 2/23/00 add 8900 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C428: Philip Michael Tuts: 2/23/00 add 5800 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C429: Philip Michael Tuts: 2/23/00 remove 300 to close out
Note on C433: Philip Michael Tuts: 2/23/00 add 12000 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C438: Philip Michael Tuts: 2/23/00 remve 155 to close out 2/24/00 add 720 to close out Jan
Note on C449: Philip Michael Tuts: 2/23/00 add 2475 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C451: Philip Michael Tuts: 2/23/00 add 1700 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C452: Philip Michael Tuts: 2/23/00 add 701 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C453: Philip Michael Tuts: 2/23/00 add 3 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C457: Philip Michael Tuts: 2/23/00 add 8248 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C458: Philip Michael Tuts: 2/23/00 add 11588 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C459: Philip Michael Tuts: 2/23/00 add 25300 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C460: Philip Michael Tuts: 2/23/00 add 11650 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C461: Philip Michael Tuts: 2/23/00 add 335 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C462: Philip Michael Tuts: 2/23/00 add 11138 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9) 2/24/00 add 554 to close out
Note on C464: Philip Michael Tuts: 2/23/00 add 20025 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9) 2/24/00 add 120 to close out
Note on C465: Philip Michael Tuts: 2/23/00 add 1442 to cover overrun (from 1.2.1.2.7 and 1.2.1.2.9)
Note on C466: Philip Michael Tuts: 2/23/00 remove 24778 to cover overruns in 1.2.1-.2.4.1,.2.4.2.1-3,.2.4.3.2,.2.4.4.2,.2.5.2.1,.2.5.3-5,.2.6.1.2-6,.2.6.2.2.6.4,.2.6.5
Note on C471: Philip Michael Tuts: 2/23/00 remove 97188 to cover overruns in 1.2.1-.2.4.1,.2.4.2.1-3,.2.4.3.2,.2.4.4.2,.2.5.2.1,.2.5.3-5,.2.6.1.2-6,.2.6.2.2.6.4,.2.6.5
Note on C132: Philip Michael Tuts: 2/24/00 reduced by 40k because it was moved to operating as part of the pre-Lehman deal to move $400k from M&S to OP
Note on A824: Philip Michael Tuts: 2/24/00 New WBS added based on Blazey change control
Note on C824: Philip Michael Tuts: 2/24/00 New item added
Note on C17: Philip Michael Tuts: 2/24/00 add 2 to close out
Note on D18: Philip Michael Tuts: 2/24/00 add 107 for Jan 3/25/00 add 966 for Feb
Note on D20: Philip Michael Tuts: 2/24/00 add 215 for Jan 3/25/00 add 306 for Feb
Note on D33: Philip Michael Tuts: 2/25/00 add 944 for Jan 3/1/00 add 72450+10750 +8000 that was moved from operating 3/25/00 add 13876 for Feb (travel)
Note on D35: Philip Michael Tuts: 2/25/00 add 90 for Jan
Note on D37: Philip Michael Tuts: 2/25/00 remove 760 for Jan 3/25/00 add 2400 for Feb
Note on D54: Philip Michael Tuts: 2/25/00 add 4215 for Jan 3/25/00 add 28054 for Feb
Note on D64: Philip Michael Tuts: 2/25/00 add 11608 for Jan 3/25/00 add 131 for Feb
Note on D75: Philip Michael Tuts: 2/24/00 add 6985 for Jan. This is an overrun 3/25/00 add 16590 for Feb
Note on D83: Philip Michael Tuts: 2/24/00add 80 for Jan 3/25/00 add 1592 for Feb
Note on D89: Philip Michael Tuts: 2/24/00 add 2500 for ND MOU
Note on D103: Philip Michael Tuts: 2/24/00 add 2829 for Jan, Kurt says it as not meant for here - subtract this from 1.1.2.5.2.2 3/25/00 add 2559 for Feb
Note on C104: Philip Michael Tuts: 2/24/00 remove 2829 to cver overspending in 1.1.2.5.2.1
Note on D104: Philip Michael Tuts: 2/24/00 remove 9910 to reflect actual PO amount in Jan 3/25/00 add 4400 for Feb
Note on D105: Philip Michael Tuts: 2/24/00 add 3409 for Jan 3/25/00 add 246 for Feb
Note on D118: Philip Michael Tuts: 2/24/00 add 7500 for Jan
Note on D121: Philip Michael Tuts: 2/24/00 3000 for Jan, ND MOU
Note on D122: Philip Michael Tuts: 2/24/00 3000 for Jan, ND MOU
Note on D123: Philip Michael Tuts: 2/24/00 3000 for Jan, ND MOU
Note on D124: Philip Michael Tuts: 2/24/00 6000 for Jan, ND MOU
Note on D126: Philip Michael Tuts: 2/24/00 8000 for Jan, ND MOU
Note on D127: Philip Michael Tuts: 2/24/00 5000 for Jan, ND MOU
Note on D128: Philip Michael Tuts: 2/24/00 5000 for Jan, ND MOU
Note on D129: Philip Michael Tuts: 2/24/00 2000 for Jan, ND MOU
Note on D130: Philip Michael Tuts: 2/24/00 10000 for Jan, ND MOU
Note on D141: Philip Michael Tuts: 2/24/00 3900 for Jan
Note on D226: Philip Michael Tuts: 2/24/00 add 3000 for Jan ND MOU
Note on D227: Philip Michael Tuts: 2/24/00 add 10000 for Jan ND MOU
Note on C226: Philip Michael Tuts: 2/24/00 increase by 3000 cost estimate for ND MOU
Note on C227: Philip Michael Tuts: 2/24/00 increase by 10000 cost estimate for ND MOU
Note on D249: Philip Michael Tuts: 2/24/00 add 1420 for Jan
Note on D251: Philip Michael Tuts: 2/24/00 add 4462 for Jan 3/25/00 add 4766 for Feb
Note on D252: Philip Michael Tuts: 2/24/00 add 5366 for Jan 3/25/00 add 1302 for Feb
Note on D257: Philip Michael Tuts: 2/24/00 add 4015 for Jan
Note on D258: Philip Michael Tuts: 2/24/00 add 3488 for Jan
Note on D259: Philip Michael Tuts: 2/24/00 add 5362 for Jan 3/25/00 add 340 for Feb
Note on D269: Philip Michael Tuts: 2/24/00 add 101400 for Jan
Note on D270: Philip Michael Tuts: 2/24/00 add 8995 for Jan
Note on D272: Philip Michael Tuts: 2/24/00 add 5475 for Jan
Note on D275: Philip Michael Tuts: 2/24/00 add 7026 for Jan 3/25/00 add 5095 for Feb
Note on D276: Philip Michael Tuts: 2/24/00 add 1548 for Jan 3/25/00 add 64 for Feb
Note on D290: Philip Michael Tuts: 2/24/00 add 2780 for Jan 3/25/00 add 495 for Feb
Note on D298: Philip Michael Tuts: 2/24/00 add 126 for Jan 3/25/00 add 860 for Feb
Note on D305: Philip Michael Tuts: 2/24/00 add 82287 for Jan
Note on D306: Philip Michael Tuts: 2/24/00 add 52000 for Jan 3/25/00 remove 31571 for Feb
Note on C306: Philip Michael Tuts: 2/24/00 add 3000 to cover overrun, take from 1.1.5.3.6.6 3/14/00 remove 1742 to cover overrun in 1.1.5.3.6.11, and 7498 to cover overrun in 1.1.5.3.6.9
Note on C305: Philip Michael Tuts: 2/24/00 remove 3000 to cover overrun in 1.1.5.3.6.7 2/24/00 remove 18454 to cover overruns in 1.1.5.3.1.4,1.1.5.3.1.6,1.1.5.3.1.11,1.1.5.3.3.10,1.1.5.3.7.10 3/14/00 remove 9499 to cover overrun in 1.1.5.3.6.11
Note on D310: Philip Michael Tuts: 2/24/00 add 1364 for Jan
Note on D321: Philip Michael Tuts: 2/24/00 add 1364 for Jan
Note on C272: Philip Michael Tuts: 2/24/00 add 5475 to cover overun, make up from 1.1.5.3.6.6 3/14/00 remove 2970 from prior yr correction and move to 1.1.5.3.1.6
Note on C276: Philip Michael Tuts: 2/24/00 add 1548 to cover overun, make up from 1.1.5.3.6.6
Note on C290: Philip Michael Tuts: 2/24/00 add 2780 to cover overun, make up from 1.1.5.3.6.6 5/17/00 add 1405 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C321: Philip Michael Tuts: 2/24/00 add 1364 to cover overun, make up from 1.1.5.3.6.6
Note on D377: Philip Michael Tuts: 2/24/00 add 36 for Jan
Note on D406: Philip Michael Tuts: 2/24/00 add 4033 for Jan
Note on D434: Philip Michael Tuts: 2/24/00 add 1980 for Jan
Note on C434: Philip Michael Tuts: 2/24/00 add 1980 for items purchsed at FNAL
Note on D438: Philip Michael Tuts: 2/24/00 add 720 for Jan
Note on D439: Philip Michael Tuts: 2/24/00 add 243 for Jan
Note on C439: Philip Michael Tuts: 2/24/00 add 243 to close out
Note on D462: Philip Michael Tuts: 2/24/00 add 554 for Jan
Note on D464: Philip Michael Tuts: 2/24/00 add 120 for Jan
Note on D612: Philip Michael Tuts: 2/24/00 add 211 for Jan
Note on D631: Philip Michael Tuts: 2/24/00 add 4259 for Jan 3/25/00 remove 1934 for Feb
Note on D640: Philip Michael Tuts: 2/24/00 add 6561 for Jan 3/25/00 add 8611 for Feb
Note on D645: Philip Michael Tuts: 2/24/00 add 1802 for Jan 3/25/00 add 2561 for Feb
Note on D667: Philip Michael Tuts: 2/24/00 add 396 for Jan
Note on D696: Philip Michael Tuts: 2/24/00 add 2373 for Jan 3/25/00 remove 2373 for Feb
Note on D697: Philip Michael Tuts: 2/24/00 add 603 for Jan
Note on D702: Philip Michael Tuts: 2/24/00 add 4934 for Jan May - Add 4548 for University of WA
Note on D703: Philip Michael Tuts: 2/24/00 add 76461 for Jan 3/25/00 add 9480 for Feb
Note on D704: Philip Michael Tuts: 2/24/00 add 66305 for Jan 3/25/00 add 6844 for Feb
Note on D706: Philip Michael Tuts: 2/24/00 add 930 for Jan 3/25/00 remove 930 for Feb
Note on D719: Philip Michael Tuts: 2/24/00 add 9431 for Jan
Note on C719: Philip Michael Tuts: 2/24/00 add 5189 to cover Jan and remove from 1.3.4.3.3
Note on D736: Philip Michael Tuts: 2/24/00 add 1000 for Jan
Note on D747: Philip Michael Tuts: 2/24/00 add 4394 for Jan
Note on D755: Philip Michael Tuts: 2/24/00 add 4655 for Jan
Note on D758: Philip Michael Tuts: 2/24/00 add 1400 for Jan
Note on D766: Philip Michael Tuts: 2/24/00 add 1471 for Jan 3/25/00 remove 194 for Feb
Note on D779: Philip Michael Tuts: 2/24/00 reduce by 652 for Jan, PO change?
Note on C755: Philip Michael Tuts: 2/24/00 add 4655 to cover Jan, and remove from 1.3.5.4.1.2
Note on C758: Philip Michael Tuts: 2/24/00 add 1400 to cover Jan, and remove from 1.3.5.4.1.2 3/23/00 add 1250 as per Cooper Comm rec 5/17/00 remove 550 to cover overrun in 1.3.5.3.3.6 per Mike e-mail 5/4/00.
Note on C767: Philip Michael Tuts: 2/24/00 decrease by 4655 for 1.3.5.3.2.4 and 1400 for 1.3.5.3.3.5 3/23/00 remove 6274 to close out as per Cooper Comm recs 5/4/00 135-050400-01 Change request to increase by 456 approved by K. Stanfield. 5/17/00 add 194 from 1.3.5.4.4.1 to reduce overrun - remainder of overrun (456) is a request for contingency per Mike e-mail 5/4/00.
Note on D881: Philip Michael Tuts: 2/24/00 add 546 for Jan 3/25/00 add 4815 for Feb
Note on D912: Philip Michael Tuts: 2/24/00 add 2560 for Jan 3/25/00 add 35625 for Feb
Note on C49: Philip Michael Tuts: 3/1/00 add 70200 which was put on operating 3/22/00 remove 34000 as per Cooper Comm. Rec. for smaller SVX order
Note on D49: Philip Michael Tuts: 3/1/00 add 70200 which was moved from operating to EQ 3/22/00 remove 34000 as per Cooper Comm. Rec. for smaller SVX order
Note on C32: Philip Michael Tuts: 3/1/00 add back 14000 which was on operating
Note on D32: Philip Michael Tuts: 3/1/00 add 14000 that was on operating for replacements
Note on C34: Philip Michael Tuts: 3/1/00 add 2000 which was on operating 3/22/00 add 20000 to cover Micron incentives for Jan-Mar
Note on D34: Philip Michael Tuts: 3/1/00 add 2000 that was on operating
Note on E271: Philip Michael Tuts: 3/9/00 remove 3600 to match Sherie Feb spending
Note on E272: Philip Michael Tuts: 3/10/00 remove 2970 to match Sherie Feb spending
Note on E274: Philip Michael Tuts: 3/10/00 remove 4040 to match Sherie Feb spending
Note on E284: Philip Michael Tuts: 3/10/00 add 5200 to match Sherie Feb spending
Note on E285: Philip Michael Tuts: 3/10/00 add 5200 to match Sherie Feb spending
Note on E287: Philip Michael Tuts: 3/10/00 add 5200 to match Sherie Feb spending
Note on E305: Philip Michael Tuts: 3/10/00 remove 9240 to match Sherie Feb spending
Note on E306: Philip Michael Tuts: 3/10/00 remove 9240 to match Sherie Feb spending
Note on E308: Philip Michael Tuts: 3/10/00 remove 6790 to match Sherie Feb spending
Note on E310: Philip Michael Tuts: 3/10/00 add 22316 to match Sherie Feb spending
Note on C922: Philip Michael Tuts: 3/10/00 remove 7672 to match Jim L. estimate
Note on C923: Philip Michael Tuts: 3/10/00 add 61785 to cover overrun as perJim L. discussion on 3/1/00
Note on C925: Philip Michael Tuts: 3/10/00 add 108000 to cover overrun as perJim L. discussion on 3/1/00 for UMd
Note on C926: Philip Michael Tuts: 3/10/00 add 8000 to cover overrun as perJim L. discussion on 3/1/00 for UMd
Note on C927: Philip Michael Tuts: 3/10/00 add 21000 to cover overrun as perJim L. discussion on 3/1/00 for UMd
Note on C929: Philip Michael Tuts: 3/10/00 remove 14802 to cover overrun as perJim L. discussion on 3/1/00
Note on C930: Philip Michael Tuts: 3/10/00 remove 2748 to cover overrun as perJim L. discussion on 3/1/00
Note on C931: Philip Michael Tuts: 3/10/00 remove 154935 to cover overrun as perJim L. discussion on 3/1/00
Note on C933: Philip Michael Tuts: 3/10/00 add 9400 to cover overrun as perJim L. discussion on 3/1/00
Note on C934: Philip Michael Tuts: 3/10/00 add 6405 to cover overrun as perJim L. discussion on 3/1/00 for Nebraska
Note on C935: Philip Michael Tuts: 3/10/00 add 5887 to cover overrun as perJim L. discussion on 3/1/00
Note on C943: Philip Michael Tuts: 3/10/00 remove 3627 to cover overrun as perJim L. discussion on 3/1/00
Note on C944: Philip Michael Tuts: 3/10/00 remove 23933 to cover overrun as perJim L. discussion on 3/1/00
Note on C946: Philip Michael Tuts: 3/10/00 remove 14000 to cover overrun as perJim L. discussion on 3/1/00
Note on C948: Philip Michael Tuts: 3/10/00 add 2000 to cover overrun as perJim L. discussion on 3/1/00 3/12/00 remove 1000 to match actuals (36000 was really 35200)
Note on C949: Philip Michael Tuts: 3/10/00 remove 6400 to cover overrun as perJim L. discussion on 3/1/00
Note on C950: Philip Michael Tuts: 3/10/00 remove 2000 to cover overrun as perJim L. discussion on 3/1/00
Note on C951: Philip Michael Tuts: 3/10/00 remove 1000 to cover overrun as perJim L. discussion on 3/1/00
Note on C958: Philip Michael Tuts: 3/10/00 remove 20000 to cover overrun as perJim L. discussion on 3/1/00
Note on C959: Philip Michael Tuts: 3/10/00 remove 3000 to cover overrun as perJim L. discussion on 3/1/00
Note on F923: Philip Michael Tuts: 3/12/00 add 85237 to bring up to Jim L memo of 3/10
Note on E923: Philip Michael Tuts: ** MOU to MSU 3/12/00 reduce by 58719 to get 61263 for MSU MOU (but remove 12258 for MOU $ not yet provided), then add 24000 for UIC MOU 3/24/00 we have now officially reprogrammed the $24k to UIC MOU
Note on F955: Philip Michael Tuts: ** MOU to MSU 3/12/00 remove 67500 to lower cost estimate
Note on F944: Philip Michael Tuts: 3/12/00 use 18363 from MOU (a change)
Note on E944: Philip Michael Tuts: 3/12/00 reduce by 42496 because some on MRI and some reduced cost
Note on F948: Philip Michael Tuts: 3/12/00 add 8900 to shift some cost to MRI as per Jim L memo 3/10/00 + add another 8900 from Blazey MRI portion
Note on E948: Philip Michael Tuts: 3/12/00 reduce by 66240 because no spending on MOU as per Jim L memo 3/10/00
Note on E945: Philip Michael Tuts: 3/12/00 7000 of this is MSU MOU
Note on E930: Philip Michael Tuts: 3/12/00 remove 14959 Neb MOU and let Blazey cover with MOU
Note on F930: Philip Michael Tuts: 3/12/00 add 12211 to cover Neb MOU with MRI
Note on E929: Philip Michael Tuts: 3/12/00 remove 20000 for Neb MOU and cover with MRI
Note on F929: Philip Michael Tuts: 3/12/00 add 16718 to cover Neb MOU with MRI
Note on E931: Philip Michael Tuts: 3/12/00 reduce by 21246 to remove from UNL MOU and shift to MRI money
Note on F931: Philip Michael Tuts: 3/12/00 reduce by 31157 to match actual costs including NIU MOU to UNL
Note on E925: Philip Michael Tuts: 3/12/00 add 20000 to cover the funds that were originally in Umd MOU but purchsed directly by FNAL
Note on E922: Philip Michael Tuts: 3/12/00 remove 62163 o match Jim L change, now as direct charge to fnal
Note on F949: Philip Michael Tuts: 3/14/00 remove 18000 to match JL 3/10 reallocation
Note on C468: Philip Michael Tuts: 3/14/00 remove 2000 to cover overrun in 1.2.1.1.4.14.4 5/17/00 remove 2537 to cover overrun in 1.2.1.1.3.2
Note on C389: Philip Michael Tuts: 3/14/00 add 2000 from 1.2.1.2.8.1 to cover overrun for safety rework
Note on E943: Philip Michael Tuts: 3/14/00 add 4507 for MSU MOU (not in original)
Note on C269: Philip Michael Tuts: 3/14/00 remove 1042 to close out and move to 1.1.5.3.1.6
Note on C271: Philip Michael Tuts: 3/14/00 add 1042 from 1.1.5.3.1.3 closeout, and add 2970 from 1.1.5.3.1.7 prior yr correction
Note on C274: Philip Michael Tuts: 3/14/00 rmove 4040 to close out from prior yr correction
Note on C303: Philip Michael Tuts: 3/14/00 remove 14400 because of design change and shift 5200 to 1.1.5.3.3.4, and 5200 to 1.1.5.3.3.5, and 4000 to 1.1.5.3.3.7
Note on C285: Philip Michael Tuts: 3/14/00 add 5200 from 1.1.5.3.6.3
Note on C287: Philip Michael Tuts: 3/14/00 add 4000 from 1.1.5.3.6.3 5/17/00 add 1200 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C297: Philip Michael Tuts: 3/14/00 remove 5646 to cover overrun in 1.1.5.3.6.11 5/17/00 add 24 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C298: Philip Michael Tuts: 3/14/00 remove 1819 to cover overrun in 1.1.5.3.6.11 5/17/00 add 1661 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C299: Philip Michael Tuts: 3/14/00 remove 3610 to cover overrun in 1.1.5.3.6.11
Note on C308: Philip Michael Tuts: 3/14/00 add 7498 from 1.1.5.3.6.7, 3400 from 1.1.5.3.7.3, 3312 from 1.1.5.3.8.1.3
Note on C326: Philip Michael Tuts: 3/14/00 remove 11211 cost reduction 5/17/00 remove 8881 to cover overrun in 1.1.5.3.1.10, 1.1.5.3.3.7, 1.1.5.3.3.10, 1.1.5.3.5.3, 1.1.5.3.5.4, & 1.1.5.3.6.10 per Marvin / Mike e-mail 4/28/00.
Note on C316: Philip Michael Tuts: 3/14/00 add 7899 from 1.1.5.3.8.1.3, add 110101 as cost overrun for 12MCM boards 3/24/00 add 12720 to cover layout req bounced from operating
Note on C908: Philip Michael Tuts: 3/14/00 add 90152 to cover overrun, where 15534 from 1.4.3.3.2, 3776 from 1.4.3.3.3, 11099 from 1.4.3.3.5, and 59743 is genuine cost overrun
Note on C909: Philip Michael Tuts: 3/14/00 reduce by 15534
Note on C910: Philip Michael Tuts: 3/1/4/00 remove 3776 to cover 1.4.3.3.1
Note on C912: Philip Michael Tuts: 3/14/00 reduce by 11099 to cover 1.4.3.3.1 3/22/00 increase by 2724 to cover expected order, get from 1.1.5.3.8.5.1 reduction
Note on I34: Philip Michael Tuts: 3/22/00 25000 for continuation of Micron incentives, 150000 for possible contract renegotiation
Note on I52: Philip Michael Tuts: 3/22/00 additional for uncertainty in HDI recovery
Note on I53: Philip Michael Tuts: 3/22/00 additional uncertainty
Note on C110: Philip Michael Tuts: 3/22/00 add 10000 as per Cooper Comm. Rec from 1.1.2.5.3.1
Note on C116: Philip Michael Tuts: 3/22/00 reduce by 25000 because double counted in analog front end bard in 1.1.5 according to Marvin, and suggested by Cooper Comm rec.
Note on I112: Philip Michael Tuts: 3/22/00 Committee suggested +5000, but Cooper says Garbincius already counted it
Note on I144: Philip Michael Tuts: 3/22/00 Committee suggested +5000, but Cooper says Garbincius already counted it
Note on E466: Philip Michael Tuts: 3/22/00 the smaller charges are work done at Nevis for the backplanes, materials costs and plating
Note on I454: Philip Michael Tuts: 3/23/00 add 40000 as per Cooper Comm rec
Note on C727: Philip Michael Tuts: 3/23/00 reduce by 35908 to close out s per Cooper Comm recs
Note on C726: Philip Michael Tuts: 3/23/00 reduce by 12220 to close out as per Cooper Comm recs
Note on C736: Philip Michael Tuts: 3/23/00 reduce by 19081 to close out as per Cooper Comm recs
Note on C737: Philip Michael Tuts: 3/23/00 reduce by 25329 to close out as per Cooper Comm recs
Note on C746: Philip Michael Tuts: 3/23/00 reduce by 22612 as per Cooper Comm recs
Note on C747: Philip Michael Tuts: 3/23/00 reduce by 13419 as per Cooper Comm recs
Note on C749: Philip Michael Tuts: 3/23/00 reduce by 3162 as per Cooper Comm recs 5/4/00 135-050300-01 Change request to increase by 7000 approved by K. Stanfield.
Note on C750: Philip Michael Tuts: 3/23/00 reduce by 22342 as per Cooper Comm recs
Note on C756: Philip Michael Tuts: 3/23/00 add 10500 as per Cooper Comm rec
Note on C763: Philip Michael Tuts: 3/23/00 add 1000 as per Cooper Comm recs
Note on C766: Philip Michael Tuts: 3/23/00 remove 6274 to close out as per Cooper Comm recs 5/17/00 remove 194 to finish and to reduce overrun in 1.3.5.4.1.2 per Mike e-mail 5/4/00.
Note on C772: Philip Michael Tuts: 3/23/00 remove 12397 to close out as per Cooper Comm rec 5/4/00 135-050300-04 Change request to increase by 5000 approved by K. Stanfield.
Note on C777: Philip Michael Tuts: 3/23/00 remove 5108 as per Cooper Comm rec
Note on C778: Philip Michael Tuts: 3/23/00 remove 3467 to close out as per Cooper Comm rec 5/4/00 135-050300-02 Change request to increase by 6775 approved by K. Stanfield.
Note on C781: Philip Michael Tuts: 3/23/00 remove 256 to close out as per Cooper Comm rec
Note on C782: Philip Michael Tuts: 3/23/00 remove 2550 to close out as per Cooper Comm rec
Note on C784: Philip Michael Tuts: 3/23/00 remove 3000 to close out as per Cooper Comm rec
Note on C785: Philip Michael Tuts: 3/23/00 remove 3000 to close out as per Cooper Comm rec
Note on H967: Philip Michael Tuts: 3/23/00 concerns about safety/fusing
Note on C990: Philip Michael Tuts: 3/23/00 add 24000 as per Cooper Comm rec for VxWorks licenses (60x$400) 5/17/00 Cost Estimate reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Decrease from 231000 to 194000.
Note on C512: Philip Michael Tuts: 3/23/00 add 5000 as per Cooper Comm rec
Note on I701: Philip Michael Tuts: 3/23/00 10000 from Cooper Comm moved to Installation
Note on C334: Philip Michael Tuts: 3/22/00 decrease by 2724 to cover expected overrun on 1.4.3.3.5
Note on E954: Philip Michael Tuts: 3/24/00 reduce this by 24000 because we are reprogramming these funds to UIC MOU 1.4.4.2.1.3, the $48k is in MOU to MSU
Note on D19: Philip Michael Tuts: 3/25/00 add 1170 for Feb
Note on D28: Philip Michael Tuts: 3/25/00 add 261 for Feb
Note on D53: Philip Michael Tuts: 3/25/00 dd 8915 or Feb
Note on D55: Philip Michael Tuts: 3/25/00 add 18719 for Feb
Note on D58: Philip Michael Tuts: 3/25/00 remove 7435 for Feb
Note on D62: Philip Michael Tuts: 3/25/00 add 902 for Feb
Note on D63: Philip Michael Tuts: 3/25/00 add 87 for Feb
Note on D136: Philip Michael Tuts: 3/25/00 add 2444 for Feb
Note on D146: Philip Michael Tuts: 3/25/00 add 114 for Feb
Note on D246: Philip Michael Tuts:
Note on D250: Philip Michael Tuts: 3/25/00 add 568 for Feb
Note on D334: Philip Michael Tuts: 3/25/00 add 12236 for Feb
Note on D335: Philip Michael Tuts: 3/25/00 add 8636 for Feb
Note on D468: Philip Michael Tuts: 3/25/00 add 11991 for Feb
Note on E611: Philip Michael Tuts: 3/25/00 remove 7035 for Feb
Note on E707: Philip Michael Tuts: 3/25/00 add 6900 for University of WA Add 5000 for University of WA
Note on D726: Philip Michael Tuts: 3/25/00 add 6834 for Feb
Note on D727: Philip Michael Tuts: 3/25/00 add 5 for Feb
Note on D738: Philip Michael Tuts: 3/25/00 add 68 for Feb
Note on D751: Philip Michael Tuts: 3/25/00 add 192 for Feb
Note on D762: Philip Michael Tuts: 3/25/00 remove 462 for Feb
Note on D767: Philip Michael Tuts: 3/25/00 add 650 for Feb
Note on D774: Philip Michael Tuts: 3/25/00add 109 for Feb
Note on D809: Philip Michael Tuts: 3/25/00 add 6057 for Feb
Note on D990: Philip Michael Tuts: 3/25/00 add 22350 for Feb
Note on E52: Landrud: Reduced prior by $14,250 for Speedy canel of 75 units (but corrected Speedy p.o. by adding $2,500 not included in original p.o.)
Note on E702: 3/25/00 Add 5452 for University of WA
Note on C374: 5/17/00 add 2537 from 1.2.1.2.8.1 to cover overrun
Note on C250: 5/17/00 add 568 from 1.1.5.2.1.5, 1.1.5.2.2.1, & 1.1.5.2.3.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C309: 5/17/00 add 1161 from 1.1.5.3.8.1.3 & 1.1.5.3.8.5.2 to cover overrun per Marvin / Mike e-mail 4/28/00.
Note on C335: 5/17/00 remove 1924 to cover overrun in 1.1.5.3.1.10, 1.1.5.3.3.7, 1.1.5.3.3.10, 1.1.5.3.5.3, 1.1.5.3.5.4, & 1.1.5.3.6.10 per Marvin / Mike e-mail 4/28/00.
Note on C969: 5/4/00 145-042000-01 Change request to decrease by 15000 approved by K. Stanfield. 5/4/00 145-050400-01 Change request to increase by 15000 REJECTED by K. Stanfield. 5/17/00 remove 15000 to cover overrun in 1.1.2.3.1 per Mike e-mail 5/3/00 (a change request was submitted to use contingency to cover 15K reduction - Stanfield rejected the request - to be revisited later).
Note on C243: 5/17/00 add 945 from 1.1.4.8.7 to cover overrun per Mike e-mail 5/4/00.
Note on C235: 5/17/00 remove 945 to cover overrun in 1.1.4.9.7 per Mike e-mail 5/4/00.
Note on C759: 5/17/00 add 550 from 1.3.5.3.3.5 to cover overrun per Mike e-mail 5/4/00.
Note on C136: 5/4/00 112-050300-03 Change request to increase by 2444 approved by K. Stanfield.
Note on C774: 5/4/00 135-050300-03 Change request to increase by 108 approved by K. Stanfield.
Note on C751: 5/4/00 135-050400-02 Change request to increase by 742 approved by K. Stanfield.
Note on D922: 5/17/00 April '00 Cost Transfer to CDF for Alpha Boards $61491 per Blazey e-mail 4/14/00.
Note on D923: 5/17/00 April '00 Cost Transfer to CDF for Alpha Boards $4949.12 per Blazey e-mail 4/14/00.
Note on D942: 5/17/00 April '00 Cost Transfer to CDF for Alpha Boards $1548.5 per Blazey e-mail 4/14/00.
Note on D943: 5/17/00 April '00 Cost Transfer to CDF for Alpha Boards $9300.5 per Blazey e-mail 4/14/00.
Note on C989: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Increase from 170000 to 197000.
Note on C991: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Increase from 80000 to 110000.
Note on C993: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Increase from 120000 to 145000.
Note on C994: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Decrease from 25000 to 10000.
Note on C995: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Decrease from 75000 to 60000.
Note on C996: 5/17/00 Cost Estimate Reallocation per Stu e-mail 3/22/00 - total reallocation is a wash. Decrease from 45000 to 30000.