## Title
Sample Work Breakdown Structure (WBS)
The spreadsheet also includes columns for assignments, scheduling, cost estimation

## WBS Columns
NOTE: In the WBS table, each row represents a task.
BASIC WBS COLUMNS | USE
WBS | WBS number, in outline style
Task | Task name
Task Description | Brief description of the task; especially useful for defining "phases" and "builds"
Organization | Organization responsible for the task
Assigned to | Person within organization responsible for task to whom the task is assigned
Schedule for Completion | When the task is to be completed. May be a range of project phases.
COST ESTIMATE COLUMNS
Internal Hours | Hours that state staff will expend on the task.
External Hours | Hours that subcontract staff will expend on the task.
External Costs | Costs that result from subcontract labor hours; computed as rate ($90 in this sample) multiplied by the hours value in column H
Purchases | Cost for purchased items, such as servers and database user licenses; at weigh stations may entail expensive sensors and roadwork.
Services | Cost for services such as networking services.
Travel | Cost for local and other travel, for example to status meetings and professional conferences.
Other | Other direct costs.
Basis | How the estimate was generated (e.g., vendor quotes, similar project's costs, roll-up of detailed estimate, experienced person's engineering judgment, etc.)
PROCUREMENT COLUMNS
Procurement? | Indicate "yes" or "no". Later, procurement items will be grouped into an overall procurement strategy. Any item with an external cost is presumably a procurement item.

## Illustrative WBS
|  |  | <-- Status | Basic WBS columns | [5 empty] | Cost Estimate Columns
Cost | Sched | Tech | WBS | Task | Task Description | Responsible Organization | Assigned to | Schedule for Completion | Notes | Internal Hours | External Hours | Computed External Costs | Purchases | Services | Travel | Other Costs | Basis of Estimate | Procurement?
State CVISN Program
Y | G | R | 1 | Program Management |  | Motor Veh Admin (MVA) | (Program Manager) DJ Samuels |  |  |  | 1 | 90
|  |  | 1.1 | Planning & Coordination |  | MVA | DJ Samuels |  |  |  |  | 0
|  |  | 1.1.1 | Program Plan |  |  |  | 2002-12-01 | Complete |  |  | 0
|  |  | 1.1.2 | Phase 1 Planning |  |  |  | 2003-03-01 | Complete; Phase complete |  |  | 0
|  |  | 1.1.2.1 | Safety | [7 empty] | 0
|  |  | 1.1.2.2 | Credentials | [7 empty] | 0
|  |  | 1.1.2.3 | Electronic Screening | [7 empty] | 0
|  |  | 1.1.3 | Phase 2 Planning |  |  |  | 2003-07-01 | Complete; Phase complete |  |  | 0
|  |  | 1.1.4 | Phase 3 Planning |  |  |  | 2003-11-01 | Complete; Phase complete |  |  | 0
|  |  | 1.1.5 | Phase 4 Planning |  |  |  | 2004-03-01 | Complete; Phase complete |  |  | 0
|  |  | 1.1.6 | Phase 5 Planning |  |  |  | 2004-08-01 | Complete; Phase complete |  |  | 0
|  |  | 1.1.7 | Phase 6 Planning |  |  |  | 2005-02-01 | Complete; Phase in work |  |  | 0
G | G | G | 1.1.8 | Phase 7 Planning |  |  |  | 2005-08-01 | Planning started |  |  | 0
|  |  | 1.1.9 | Phase 8 Planning |  |  |  | 2006-01-01 |  |  |  | 0
|  |  | 1.1.10 | Staff key positions | [7 empty] | 0
|  |  | 1.1.10.1 | CVISN Program Manager | [7 empty] | 0
|  |  | 1.1.10.2 | System Architect | [7 empty] | 0
|  |  | 1.1.10.3 | Administrator/facilitator | [7 empty] | 0
|  |  | 1.1.10.4 | Safety Project Leader | [7 empty] | 0
|  |  | 1.1.10.5 | Credentials Project Leader | [7 empty] | 0
|  |  | 1.1.10.6 | Electronic Screening Project Leader | [7 empty] | 0
|  |  | 1.1.10.7 | Information Technology Representative | [7 empty] | 0
|  |  | 1.2 | Carrier Coordination |  | MVA | RE Richards |  |  |  |  | 0
|  |  | 1.3 | Showcases & Outreach |  | MVA | DJ Samuels |  | 2 showcases conducted |  |  | 0
|  |  | 1.4 | Regional Coordination |  | MVA | DJ Samuels |  | ongoing |  |  | 0
|  |  | 1.5 | O&M Planning |  | MVA | DJ Samuels |  |  |  |  | 0
|  |  | 1.6 | Training |  | MVA | RE Richards |  |  |  |  | 0
|  |  | 1.7 | Policy |  | MVA | DJ Samuels |  |  |  |  | 0
|  |  | 1.8 | Subcontract & Procurement Mgt |  | MVA | DJ Samuels |  |  |  |  | 0
G | G | G | 2 | System Engineering & Integration |  | MVA Subcontract - VGU | (System Architect) GH Brown |  |  |  | 2 | 180
|  |  | 2.1 | System Requirements Definition |  | MVA Subcontract - VGU | GH Brown | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.1.1 | Goals |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.1.2 | COACH Part 1 |  |  |  | 2005-06-01 | Updated with new version |  |  | 0
G | G | G | 2.1.3 | COACH Part 4 |  |  |  | 2005-07-01 | Completed |  |  | 0
|  |  | 2.1.4 | Other state requirements |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.1.5 | Operational Scenarios |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.1.5.1 | Inspection |  |  |  | 2003-03-01 | Last update |  |  | 0
|  |  | 2.1.5.2 | IRP |  |  |  | 2004-06-01 | Last update |  |  | 0
G | Y | G | 2.1.5.3 | IFTA |  |  |  | 2005-08-01 | Started |  |  | 0
|  |  | 2.1.5.4 | Screening |  |  |  | 2005-05-01 | Last update |  |  | 0
|  |  | 2.2 | System Design |  | MVA Subcontract - VGU | GH Brown | 2002-12-01 | Complete; revisited for each phase |  |  | 0
G | G | G | 2.2.1 | Allocation of requirements to components |  |  |  | 2005-08-01 | Started |  |  | 0
G | G | G | 2.2.1.1 | COACH Part 3 |  |  |  | 2005-07-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.2.1.2 | Description of functions for each component |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.2.2 | Interface summaries |  |  |  | 2004-06-01 | Last update |  |  | 0
|  |  | 2.2.3 | Physical Design | [7 empty] | 0
|  |  | 2.2.3.1 | Allocation of systems to computers |  |  |  | 2005-04-01 | Last update |  |  | 0
Y | G | G | 2.2.3.2 | Network upgrades |  |  |  | 2005-09-01 | Update for IFTA |  |  | 0
|  |  | 2.3 | Architecture Conformance |  | MVA Subcontract - VGU | GH Brown | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.3.1 | Verify commitment to principles |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.3.2 | Verify plan is sound & top-level design conforms |  |  |  | 2002-12-01 | Complete; revisited for each phase |  |  | 0
|  |  | 2.3.3 | Verify detailed designs conform | [7 empty] | 0
|  |  | 2.3.3.1 | Safety Build 2 | [7 empty] | 0
|  |  | 2.3.3.2 | Credentials Build 2 | [7 empty] | 0
|  |  | 2.3.3.3 | E-Screening Build 2 | [7 empty] | 0
|  |  | 2.4 | System Integration & Test |  | MVA Subcontract - VGU | GH Brown |  |  |  |  | 0
|  |  | 2.5 | Interoperability Testing |  | TBD | TBD |  |  |  |  | 0
G | Y | G | 3 | Safety Project |  | Field Ops Bureau | (Project Leader) DT Greenwood |  |  |  | 3 | 270
|  |  | 3.1 | Project Management |  | Field Ops Bureau | DT Greenwood | ongoing |  |  |  | 0
|  |  | 3.2 | System Engineering & Integration |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
|  |  | 3.3 | Subcontract & Procurement Mgt |  | Field Ops Bureau | DT Greenwood | ongoing |  |  |  | 0
G | Y | G | 3.4 | CV Information Exchange Window (CVIEW) |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
G | G | G | 3.4.1 | Product Mgmt |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
G | G | G | 3.4.2 | Subcontract & Procurement |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
G | G | G | 3.4.2.1 | XYZ Subcontract Administration |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
|  |  | 3.4.3 | Operations & Maintenance |  | Field Ops Bureau | TBD | 2009 |  |  |  | 0
G | G | G | 3.4.4 | Communications |  | Field Ops Bureau | JD Morgan | 2007-01-01 | Initial testing successful |  |  | 0
G | Y | G | 3.4.5 | Version 1.0.x |  | Field Ops Bureau | AA Norman |  |  |  |  | 0
|  |  | 3.4.5.1 | Requirements |  | Field Ops Bureau | AA Norman | 2006-09-01 | Complete |  |  | 0
|  |  | 3.4.5.2 | Design |  | Field Ops Bureau | AA Norman | 2006-12-01 | Complete |  |  | 0
G | Y | G | 3.4.5.3 | Implementation |  | Subcontract - XYZ Software | JA Doe | 2007-04-01 | Down one staff member |  |  | 0
G | Y | G | 3.4.5.4 | Version testing |  | Subcontract - XYZ Software | JA Doe | Start May-07 | Testing delayed - staffing |  |  | 0
|  |  | 3.4.5.5 | Bug fixes |  | Subcontract - XYZ Software | JA Doe | Complete Jul-07 |  |  |  | 0
|  |  | 3.4.5.6 | Deployment |  | not applicable | not applicable |  |  |  |  | 0
|  |  | 3.4.5.7 | Training |  | Subcontract - XYZ Software | TBD | 2007-08-01 |  |  |  | 0
|  |  | 3.5 | ASPEN |  | Field Ops Bureau | JA Shaffer |  |  |  |  | 0
|  |  | 3.5.1 | Product Mgmt |  | Field Ops Bureau | JA Shaffer |  |  |  |  | 0
|  |  | 3.5.2 | Subcontract & Procurement |  | Field Ops Bureau | JA Shaffer |  |  |  |  | 0
|  |  | 3.5.3 | Operations & Maintenance |  | Field Ops Bureau | AL Snark |  |  |  |  | 0
|  |  | 3.5.4 | Communications |  | Field Ops Bureau | EC Smith |  |  |  |  | 0
|  |  | 3.5.5 | Deployment 1 | Upgrade some ASPEN units to Version 2 and still report inspection via SAFER | Field Ops Bureau | JA Shaffer | Safety Build 2 |  |  |  | 0 | [5 empty] | Yes
|  |  | 3.5.5.1 | Installation |  | Field Ops Bureau | JA Shaffer |  |  |  |  | 0
|  |  | 3.5.5.2 | Test |  | Field Ops Bureau | JA Shaffer |  |  |  |  | 0
|  |  | 3.5.5.3 | Training |  | Field Ops Bureau | RG Roger |  |  |  |  | 0
|  |  | 3.5.6 | Deployment 2 | Upgrade all ASPEN units to Version 2 and report some inspections via CVIEW | Field Ops Bureau | AL Snark | Safety Build 3 |  |  |  | 0 | [5 empty] | Yes
|  |  | 3.5.6.1 | Installation |  | Field Ops Bureau | AL Snark |  |  |  |  | 0
|  |  | 3.5.6.2 | Test |  | Field Ops Bureau | AL Snark |  |  |  |  | 0
|  |  | 3.5.6.3 | Training |  | Field Ops Bureau | RG Roger |  |  |  |  | 0
|  |  | 3.5.7 | Deployment 3 | All ASPEN units are at Version 2 and reporting inspections via CVIEW | Field Ops Bureau | AL Snark | Safety Build 4 |  |  |  | 0 | [5 empty] | Yes
|  |  | 3.5.7.1 | Installation |  | Field Ops Bureau | AL Snark |  |  |  |  | 0
|  |  | 3.5.7.2 | Test |  | Field Ops Bureau | AL Snark |  |  |  |  | 0
|  |  | 3.5.7.3 | Training |  | Field Ops Bureau | RG Roger |  |  |  |  | 0
|  |  | 3.6 | SAFETYNET |  | Field Ops Bureau | TBD |  |  |  |  | 0
|  |  | 3.6.1 | Product Mgmt | [7 empty] | 0
|  |  | 3.6.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 3.6.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 3.6.4 | Communications | [7 empty] | 0
|  |  | 3.6.5 | Deployment 1 | [7 empty] | 0
|  |  | 3.6.5.1 | Installation | [7 empty] | 0
|  |  | 3.6.5.2 | Test | [7 empty] | 0
|  |  | 3.6.5.3 | Training | [7 empty] | 0
|  |  | 3.7 | Safety Build 1 | [7 empty] | 0
|  |  | 3.8 | Safety Build 2 | [7 empty] | 0
|  |  | 3.9 | Safety Build n | [7 empty] | 0
|  |  | 4 | Credentials Project | [6 empty] | 4 | 360
|  |  | 4.1 | Project Management | [7 empty] | 0
|  |  | 4.2 | System Engineering & Integration | [7 empty] | 0
|  |  | 4.3 | Subcontract & Procurement Mgt | [7 empty] | 0
|  |  | 4.4 | International Registration Plan (IRP) |  | Motor Vehicle Administration (MVA) | DR Cashell |  |  |  |  | 0
|  |  | 4.4.1 | Product Mgmt |  | MVA | DR Cashell |  |  |  |  | 0
|  |  | 4.4.2 | Subcontract & Procurement |  | MVA | PL Harvey |  |  |  |  | 0
|  |  | 4.4.3 | Operations & Maintenance |  | MVA | DD Hunter |  |  |  |  | 0
|  |  | 4.4.4 | Communications |  | Information Technology | RE Lee |  |  |  |  | 0
|  |  | 4.4.5 | Version x.y.z | e.g. Connect to IRP Clearinghouse | MVA | DD Hunter | Cred Build 3 |  |  |  | 0
|  |  | 4.4.5.1 | Requirements | [7 empty] | 0
|  |  | 4.4.5.2 | Design | [7 empty] | 0
|  |  | 4.4.5.3 | Implementation | [7 empty] | 0
|  |  | 4.4.5.4 | Version testing | [7 empty] | 0
|  |  | 4.4.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.4.5.6 | Deployment | [7 empty] | 0
|  |  | 4.4.5.7 | Training | [7 empty] | 0
|  |  | 4.5 | International Fuel Tax Agreement (IFTA) | [7 empty] | 0
|  |  | 4.5.1 | Product Mgmt | [7 empty] | 0
|  |  | 4.5.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 4.5.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 4.5.4 | Communications | [7 empty] | 0
|  |  | 4.5.5 | Version x.y.z | [7 empty] | 0
|  |  | 4.5.5.1 | Requirements | [7 empty] | 0
|  |  | 4.5.5.2 | Design | [7 empty] | 0
|  |  | 4.5.5.3 | Implementation | [7 empty] | 0
|  |  | 4.5.5.4 | Version testing | [7 empty] | 0
|  |  | 4.5.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.5.5.6 | Deployment | [7 empty] | 0
|  |  | 4.5.5.7 | Training | [7 empty] | 0
|  |  | 4.6 | Credentialing Interface (CI) |  | DOT Info Tech | (Network & Facilities Sys Engr) JB Connect |  |  |  |  | 0
|  |  | 4.6.1 | Product Mgmt | [7 empty] | 0
|  |  | 4.6.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 4.6.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 4.6.4 | Communications | [7 empty] | 0
|  |  | 4.6.5 | Version x.y.z | [7 empty] | 0
|  |  | 4.6.5.1 | Requirements | [7 empty] | 0
|  |  | 4.6.5.2 | Design | [7 empty] | 0
|  |  | 4.6.5.3 | Implementation | [7 empty] | 0
|  |  | 4.6.5.4 | Version testing | [7 empty] | 0
|  |  | 4.6.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.6.5.6 | Deployment | [7 empty] | 0
|  |  | 4.6.5.7 | Training | [7 empty] | 0
|  |  | 4.7 | Motor Carrier Home Page & Web Credentialing | [7 empty] | 0
|  |  | 4.7.1 | Product Mgmt | [7 empty] | 0
|  |  | 4.7.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 4.7.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 4.7.4 | Communications | [7 empty] | 0
|  |  | 4.7.5 | Version x.y.z | [7 empty] | 0
|  |  | 4.7.5.1 | Requirements | [7 empty] | 0
|  |  | 4.7.5.2 | Design | [7 empty] | 0
|  |  | 4.7.5.3 | Implementation | [7 empty] | 0
|  |  | 4.7.5.4 | Version testing | [7 empty] | 0
|  |  | 4.7.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.7.5.6 | Deployment | [7 empty] | 0
|  |  | 4.7.5.7 | Training | [7 empty] | 0
|  |  | 4.8 | Carrier Credentialing Systems (CAT or module) | [7 empty] | 0
|  |  | 4.8.1 | Product Mgmt | [7 empty] | 0
|  |  | 4.8.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 4.8.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 4.8.4 | Communications | [7 empty] | 0
|  |  | 4.8.5 | Version x.y.z | [7 empty] | 0
|  |  | 4.8.5.1 | Requirements | [7 empty] | 0
|  |  | 4.8.5.2 | Design | [7 empty] | 0
|  |  | 4.8.5.3 | Implementation | [7 empty] | 0
|  |  | 4.8.5.4 | Version testing | [7 empty] | 0
|  |  | 4.8.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.8.5.6 | Deployment | [7 empty] | 0
|  |  | 4.8.5.7 | Training | [7 empty] | 0
|  |  | 4.9 | Intra-State Registration | [7 empty] | 0
|  |  | 4.9.1 | Product Mgmt |  | Field Ops Bureau | DT Greenwood |  |  |  |  | 0
|  |  | 4.9.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 4.9.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 4.9.4 | Communications | [7 empty] | 0
|  |  | 4.9.5 | Version x.y.z | [7 empty] | 0
|  |  | 4.9.5.1 | Requirements | [7 empty] | 0
|  |  | 4.9.5.2 | Design | [7 empty] | 0
|  |  | 4.9.5.3 | Implementation | [7 empty] | 0
|  |  | 4.9.5.4 | Version testing | [7 empty] | 0
|  |  | 4.9.5.5 | Bug fixes | [7 empty] | 0
|  |  | 4.9.5.6 | Deployment | [7 empty] | 0
|  |  | 4.9.5.7 | Training | [7 empty] | 0
|  |  | 4.1 | Credentials Build 1 | [7 empty] | 0
|  |  | 4.11 | Credentials Build 2 | [7 empty] | 0
|  |  | 4.12 | Credentials Build n | [7 empty] | 0
|  |  | 5 | Electronic Screening Project | [6 empty] | 5 | 450
|  |  | 5.1 | Project Management | [7 empty] | 0
|  |  | 5.2 | System Engineering & Integration | [7 empty] | 0
|  |  | 5.3 | Subcontract & Procurement Mgt | [7 empty] | 0
|  |  | 5.4 | Roadside Operations |  | Field Ops Bureau | PD Schindler |  |  |  |  | 0
|  |  | 5.4.1 | Product Mgmt |  | Field Ops Bureau | PD Schindler |  |  |  |  | 0
|  |  | 5.4.2 | Subcontract & Procurement |  | Field Ops Bureau | MO Jones |  |  |  |  | 0
|  |  | 5.4.3 | Operations & Maintenance |  | Field Ops Bureau | MO Jones |  |  |  |  | 0
|  |  | 5.4.4 | Communications |  | Field Ops Bureau | EC Smith |  |  |  |  | 0
|  |  | 5.4.5 | Version x.y.z | e.g. Screen on interstate carrier & vehicle snapshots | Field Ops Bureau | PD Schindler | EScr Build 4 |  |  |  | 0
|  |  | 5.4.5.1 | Requirements | [7 empty] | 0
|  |  | 5.4.5.2 | Design | [7 empty] | 0
|  |  | 5.4.5.3 | Implementation | [7 empty] | 0
|  |  | 5.4.5.4 | Version testing | [7 empty] | 0
|  |  | 5.4.5.5 | Bug fixes | [7 empty] | 0
|  |  | 5.4.5.6 | Deployment | [7 empty] | 0
|  |  | 5.4.5.7 | Training | [7 empty] | 0
|  |  | 5.5 | Screening | [7 empty] | 0
|  |  | 5.5.1 | Product Mgmt | [7 empty] | 0
|  |  | 5.5.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 5.5.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 5.5.4 | Communications | [7 empty] | 0
|  |  | 5.5.5 | Version x.y.z | [7 empty] | 0
|  |  | 5.5.5.1 | Requirements | [7 empty] | 0
|  |  | 5.5.5.2 | Design | [7 empty] | 0
|  |  | 5.5.5.3 | Implementation | [7 empty] | 0
|  |  | 5.5.5.4 | Version testing | [7 empty] | 0
|  |  | 5.5.5.5 | Bug fixes | [7 empty] | 0
|  |  | 5.5.5.6 | Deployment | [7 empty] | 0
|  |  | 5.5.5.7 | Training | [7 empty] | 0
|  |  | 5.6 | Site Mods | [7 empty] | 0
|  |  | 5.6.1 | Site Mods Mgmt | [7 empty] | 0
|  |  | 5.6.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 5.6.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 5.6.4 | Communications | [7 empty] | 0
|  |  | 5.6.5 | Site ABC | [7 empty] | 0
|  |  | 5.6.5.1 | Requirements | [7 empty] | 0
|  |  | 5.6.5.2 | Design | [7 empty] | 0
|  |  | 5.6.5.3 | Implementation | [7 empty] | 0
|  |  | 5.6.5.4 | Testing | [7 empty] | 0
|  |  | 5.6.5.5 | Bug fixes | [7 empty] | 0
|  |  | 5.6.6 | Pre-Selected Mobile Sites | [7 empty] | 0
|  |  | 5.7 | Carrier E-Screening Enrollment | [7 empty] | 0
|  |  | 5.7.1 | Product Mgmt | [7 empty] | 0
|  |  | 5.7.2 | Subcontract & Procurement | [7 empty] | 0
|  |  | 5.7.3 | Operations & Maintenance | [7 empty] | 0
|  |  | 5.7.4 | Communications | [7 empty] | 0
|  |  | 5.7.5 | Version x.y.z | [7 empty] | 0
|  |  | 5.7.5.1 | Requirements | [7 empty] | 0
|  |  | 5.7.5.2 | Design | [7 empty] | 0
|  |  | 5.7.5.3 | Implementation | [7 empty] | 0
|  |  | 5.7.5.4 | Version testing | [7 empty] | 0
|  |  | 5.7.5.5 | Bug fixes | [7 empty] | 0
|  |  | 5.7.5.6 | Deployment | [7 empty] | 0
|  |  | 5.7.5.7 | Training | [7 empty] | 0
|  |  | 5.8 | E-Screening Build 1 | [7 empty] | 0
|  |  | 5.9 | E-Screening Build 2 | [7 empty] | 0
|  |  | 5.1 | E-Screening Build n | [7 empty] | 0
|  |  | 6 | Evaluation | [6 empty] | 6 | 540
|  |  | 6.1 | Self-Evaluation | [7 empty] | 0
|  |  | 6.1.1 | Evaluation Team | Form the evaluation team. | [6 empty] | 0
|  |  | 6.1.2 | Evaluation Strategy | Write document; ensure adequate test points in system technical design. | [6 empty] | 0
|  |  | 6.1.3 | Evaluation Plan | Write document. | [6 empty] | 0
|  |  | 6.1.4 | Lessons Learned | Periodically capture and publish lessons learned, in 5 specified areas. | [6 empty] | 0
|  |  | 6.1.5 | Cost Data | Collect cost accounting data (on-going). | [6 empty] | 0
|  |  | 6.1.6 | Test Plans | Write test plan for each test. | [6 empty] | 0
|  |  | 6.1.7 | Analysis | Collect and analyze data. | [6 empty] | 0
|  |  | 6.1.8 | Final Report | Write document. | [6 empty] | 0
|  |  | 6.2 | National Evaluation (Funded Separately) | Participate if selected. | [6 empty] | 0

## Blank WBS
|  |  | <-- Status | Basic WBS columns | [5 empty] | Cost Estimate Columns
Cost | Sched | Tech | WBS | Task | Task Description | Responsible Organization | Assigned to | Schedule for Completion | Notes | Internal Hours | External Hours | Computed External Costs | Purchases | Services | Travel | Other Costs | Basis of Estimate | Procurement?
State CVISN Program

## Cost Estimate
WBS | Task | Internal Hours | External Hours | Computed External Costs | Purchases | Services | Travel | Other Costs
1 | Program Management | 0 | 1 | 90 | 0 | 0 | 0 | 0
2 | System Engineering & Integration | 0 | 2 | 180 | 0 | 0 | 0 | 0
3 | Safety Project | 0 | 3 | 270 | 0 | 0 | 0 | 0
4 | Credentials Project | 0 | 4 | 360 | 0 | 0 | 0 | 0
5 | Electronic Screening Project | 0 | 5 | 450 | 0 | 0 | 0 | 0
6 | Evaluation | 0 | 6 | 540 | 0 | 0 | 0 | 0
| TOTAL | 0 | 21 | 1890 | 0 | 0 | 0 | 0

## Notes for Cost Estimate
Notes on Generating Cost Estimate The Cost Estimate spreadsheet can be used as a starting point for estimating costs for your CVISN program. Note the outflow of dollars is not a complete measure of the "cost"-- you also need a significant comittment of in-house talent at least for CVISN Program Management, individual Project Leadership, Network & Communication, and Operations & Maintenance. Your state may require an official multi-year cost estimate in a state-specific standard form. This spreadsheet is a starting point for that, but cannot substitute for that. To use this workbook to make a cost estimate: 1. Adapt this workbook for your own use. Read the "WBS Columns" worksheet that expains each column of the WBS table. Modify the WBS to suit your state's CVISN program. 2. Enter your task cost estimates at the lowest level in the WBS that you feel is useful. At too high a level you won't think of everything needed; at too low a level it is subject to the vagaries of design decisions. Take care not to cover the same activities twice -- once at a lower level (for example 2.2.5.3) and again at a higher level (example 2.1). 3. Don't be dismayed that you "don't know enough". Make a reasonable guess at a high level, and then when you know more as time goes on, make more detailed, more substantive estimates. 4. To consider in-house staffing, it might be helpful to think of the duration and level-of-effort (LOE) each activity will require. For example, 1.1.10.1 CVISN Program Manager could be a LOE of 30% for 3 years, or 1800 hours. (That's assuming a round number of 2000 working hours per year.) 5. For external hours, begin by imagining the size of the team and number of months. One phase of one software product might take 5 people 9 months, or 900 hours assuming 20 8-hour days per month. You might then assume $90/hour as a fully-burdened commercial cost factor. This factor goes into each of the associated cost cells. 6. Full in the remaining columns, including the basis of estimate. 7. The worksheet "Cost Estimate" has totals for each level 2 WBS element. There are some test quantities entered into the "external hours" column so that you can see the propegation of computations.