Exhibit 3

IDIQ Development of PI Specific Experiments, Instruments and Diagnostics

Statement of Work

# Introduction

The National Aeronautics and Space Administration (NASA) Microgravity Science program advocates and coordinates an interdisciplinary research community to conduct specified research and to disseminate the results of that research.  Research selected for flight definition is assigned to a carrier or a research facility best suited for that experiment (Space Shuttle, Sounding Rocket, International Space Station, Glovebox, etc.).  NASA has a requirement for the development and operation of these individual flight experiments to perform microgravity investigations in combustion and fluid science research.

This statement of work (SOW) defines the contractor’s efforts required to provide performance-based activities in the design, development, fabrication, assembly, test, delivery, and operation of Microgravity Science payloads.  The contractor will perform the tasks for the Microgravity Science program managed by the NASA Lewis Research Center (LeRC).  Particular requirements and tailoring of this SOW shall be defined in the Delivery Order issued for each specific Principal Investigator’s mission.  The statement of work is structured by historical NASA development phases (NHB 7120.5), see Figure 1, with the anticipation that the Delivery Order requirements and end-item deliverables will be defined within that life-cycle phase.  The development approach shall be tailored as appropriate to most effectively meet the requirements of the experiment.

Figure 1 - Typical Project Management Process

(Note: Phase A activities are nominally performed by the Government)

# Scope

The contract encompasses the design, development, testing, engineering, production, delivery, and operations of Microgravity Science flight payloads.  The flight experiments are designed to accommodate basic research, commercial applications, and studies of phenomena in fluid physics, combustion science, acceleration measurements, and other microgravity investigations.  The contractor shall, except as otherwise specified herein, furnish all personnel, facilities, materials and services necessary to support the contract efforts.  The contractor shall work from Delivery Orders describing required deliverables and specifications required to satisfactorily complete each order.

# Applicable Documents

The nature of flight hardware development is such that conformance to various standards and codes shall be specified if required.  Those that are applicable will be specified in each Delivery Order. Typical standards and codes, which may be required of the contractor, are the following:

ASTM Standards

Mil-Specifications and Standards

ANSI codes as sponsored by ASME

Department of Transportation Regulations

NASA Standards and Handbooks

The contractor shall suggest alternatives to these standards if use of alternatives can lead to a better or less costly product that satisfies requirements and regulations.  The contractor shall also prepare and/or utilize other applicable documents, not explicitly called out herein, as needed to produce, test, and deploy hardware and software meeting the requirements.  The contractor shall be responsible for identifying, acquiring, and properly using such documents.  The contractor is encouraged to submit alternative standards to the use of any military specification or standard.  The contractor shall also utilize other applicable documents and efforts, including the performance of tests and analyses not otherwise explicitly stated herein or in other parts of the SOW, needed to produce the required flight hardware, software, or support documentation.  The contractor shall ascertain the totality of the applicable documents and shall use each in accordance with the document’s purpose.  In the event of conflicting requirements, the requirements stated in the Delivery Order shall take precedence over requirements stated in the applicable documents and/or the SOW.

## APPLICABLE REQUIREMENTS

The appropriate applicable requirements shall be identified in each Delivery Order based on the specific needs of the experiment.

## REFERENCE

The following provides a subset list of key documents for each potential carrier or product assurance that provide the basis for flight hardware and software development for that particular carrier.  The contractor shall obtain the latest version and all applicable carrier requirements from the appropriate carrier integrator.

### Management & Product Assurance

Standard Assurance Requirements and Guidelines for Experiments (SARGE): Defines safety, reliability, and quality assurance requirements and guidelines by carrier for developers of space experiments within the LeRC system.

LeRC Product Assurance Manual (PAM): Product assurance instructions (PAIs) employed at LeRC to address specific assurance topics.

NASA Procedures and Guidelines [NPG 7120.5A]: Establishes the management system for processes, requirements, and responsibilities for implementing program/project management within NASA.

Government Surveillance Plan: Defines NASA’s approach for contract surveillance in-sight activities for product assurance.

### Get Away Special (GAS)

Get Away Special (GAS) Small Self-Contained Payloads Experimenter Handbook: Handbook includes all interface requirements, all carrier capabilities, selected materials requirements and recommendations, selected safety requirements, and selected test and verification requirements.

### Hitchhiker (HH)

Customer Accommodations and Requirements Specification (CARS) [HHG-730-1503-07]: Includes all interface requirements, all carrier capabilities, selected materials requirements and recommendations, selected safety requirements, and selected test and verification requirements.

### Sounding Rocket

Sounding Rocket User’s Handbook: Describes sounding rocket capabilities, hardware design considerations, payload development process, integration, testing, safety, etc.

### Glovebox

Microgravity Glovebox Experiment User’s Manual: Describes the Glovebox carrier capabilities and the mechanical and electrical interfaces to which the experiments must be designed.

### Spacehab/STS

Spacehab User’s Handbook [MDC-SH-0002]: Includes all carrier capabilities, selected materials requirements and recommendations, selected safety requirements, and selected test and verification requirements.

Spacehab Experiment Requirement Questionnaire [MDC-94-W5718]: Establishes the format and content of information about experimenter requirements to be used during the manifesting process and subsequent formal definition process.

Spacehab Payload Processing Facility Experimenter’s Handbook [MDC-94-W5719A]: Defines the generic capabilities of the Spacehab Payload Processing Facility (SPPF) for the experiment user.

### International Space Station

Station Program Implementation Plan [SSP 50200]: Defines the implementation structure for the International Space Station Program functions and documents the flowdown of detailed implementation.

Pressurized Payload Interface Requirements Document [SSP 57000]: This document defines the minimum Space Station Requirements for Pressurized Payloads and provides requirements for incorporation in the NASA Space Station hardware procurements and technical programs.

Space Station Program Requirements for Payloads [SSP 50431]: This document provides a consolidation of all International Space Station Program (ISSP) programmatic requirements, documentation and processes to be used by all ISSP funded and barter agreement Payload Developers (PDs) and processors.

# Performance Work Statements

The following describes the functional performance work required of the contractor upon receipt of a Delivery Order necessary for the successful and on-time implementation to meet the mission-specific Delivery Order requirements.

## MANAGEMENT

The contractor shall provide a management function for the monitoring, control, and reporting of the specific Delivery Order effort.  The contractor’s management function shall provide to NASA reporting and real-time insight into status based on the contractor’s Performance Measurement Plan (DID# CD-01), as well as, technical and performance measurement of all contractor responsibilities and activities performed under the Delivery Order.  The contractor shall be responsible for the submission of all change order proposals (DID# PM-05) as required by this contract.  The contractor shall implement appropriate management systems that prevent the improper dissemination of Principal Investigator competition sensitive information.  All contractor and subcontractor internal data, reviews, audits, meetings, and other activities pertinent to the execution of a Delivery Order shall be open to NASA attendance to provide NASA insight.  To facilitate NASA attendance the contractor shall provide to NASA reasonable and timely notification of events.  The following paragraphs describe detailed requirements for performance measurement, configuration management, property management, and review requirements that apply to all elements of Exhibit 3.

### Performance Measurement

The contractor shall provide NASA with the necessary information to implement the Government Surveillance Plan to monitor product assurance, identify significant problems, and implement corrective action as applicable based on the contractor’s Performance Measurement Plan (DID# CD-01).  The contractor shall generate Performance Measurement Reports (DID# CD-02) for the basic contract and each exercised option in accordance with this plan.  Additional Delivery Order specific technical performance measurement requirements may also be identified in the Delivery Order.  The contractor shall participate for each cost plus type Delivery Order in a monthly progress review meeting with the identified NASA Project Manager (Delivery Order technical manager) to review cost, schedule technical status, issues, and technical interchange to assure understanding of all Delivery Order requirements.  The contractor shall participate for each fixed price type Delivery Order in a monthly informal Technical Information Meeting, unless otherwise modified by the individual Delivery Order, with the identified NASA Project Manager (Delivery Order technical manager) to review technical, schedule, and contractual issues, and provide a forum for technical interchange to assure understanding of all Delivery Order requirements.  The contractor is not required to develop information or deliver data beyond what is normally produced by the contractor in the day-to-day management of the Delivery Order.

### Configuration Management

The contractor shall establish a configuration management process to control critical hardware, software, and documentation.  The specific process to be used during development and operations of the specific experiment hardware shall be defined in a Configuration Management Plan (DID# PM-04), based on the level of hardware complexity and carrier requirements.   The contractor shall also implement an engineering control system that shall review and approve changes to drawings, parts lists, test procedures and quality procedures once a baseline has been established.  Any modifications to requirements or deviations shall be in accordance with DID# PM-05.

### Property Management

The contractor shall maintain an inventory of all Government Furnished property and of items purchased for Contract Delivery Orders for both on-site and at contractor facilities per the Property Clauses of the contract.  The contractor shall provide NASA with a current inventory list quarterly and be subject to annual audits.  During the audits, the contractor shall verify the accuracy of the inventory listing and verify the existence and locations of listed items.  All flight hardware shall be identified and controlled based upon the configuration management plan which shall include a bonded storage capability to control the tracking of and physical access to flight hardware inventory.

### Reviews

The contractor shall provide engineering, management, documentation and planning support for NASA design reviews required by NASA Headquarters, other NASA field centers and the program offices to certify hardware and software maturity readiness.  NASA design reviews typically include but are not limited to the Science Concept Review (SCR), Requirements Definition Review (RDR), Preliminary Design Review (PDR), Critical Design Review (CDR), Verification and Test Review (VTR), Pre-Ship Review (PSR), and Flight Readiness Review (FRR) as defined in section 5.0 Milestone Reviews.  The contractor shall also participate in other technical reviews based on the individual Delivery Order, such as Verification and Safety Reviews.

The SCR, RDR, and PSR shall be held at NASA’s Lewis Research Center and the Safety reviews shall be held at NASA Johnson Space Center, all other reviews shall be held at the contractor’s location or unless modified by the individual Delivery Order.  The contractor shall ensure that appropriate personnel attend each review.  The baseline dates for each review and any modifications to the review requirements shall be defined in the Delivery Order to meet unique mission requirements.

Review presentation packages shall be developed in accordance with DID# D-01, unless otherwise defined in the Delivery Order.  Action Items from the reviews shall be generated by NASA and shall require written responses for closure from the contractor.  The contractor shall evaluate the scope and content of each review and suggest modifications, per NASA approval, to the review requirements for more value-added reviews and/or cost reductions.

## PRODUCT ASSURANCE

The contractor will be required to plan, implement and maintain a product assurance system to support all tasks under the Contract.  The Product Assurance requirements are defined in the LeRC’s Standard Assurance Requirements and Guidelines for Experiments (SARGE) based on carrier selection.  The product assurance system of the contractor is subject to periodic review by NASA LeRC or its designated NASA representative(s) as defined in Government’s Surveillance Plan.

The contractor will be required to prepare, implement and maintain Product Assurance Plans (DID# PA-01) and other documentation or procedures which assure compliance with product assurance requirements.  The contractor will need to develop specific plans per the Delivery Order to show how applicable product assurance requirements for individual experiments will be addressed.  Product Assurance Plans shall include system safety, materials and processes, quality assurance, problem reporting and corrective action system (PRACA), reliability and maintainability and software product assurance.

### Quality Management

The contractor shall be certified to ISO 9001, in the process of becoming certified or as a minimum have an established proven effective quality program that is in accordance with FAR 42.202-3 Higher-level Contract Quality Requirements (e.g. MIL-Q-9858).  The contractor’s Quality Management system shall be capable of meeting the quality assurance requirements in SARGE and SSP 41173, "Space Station Quality Assurance Requirements”.  The Quality Management system is subject to review as defined in the MRDOC Surveillance Plan by NASA LeRC or its representative.

### System Safety

The contractor shall assure the overall system safety of the design that minimizes or reduces safety risk to an acceptable level.  The contractor shall develop a System Safety Plan (DID# PA-02) for each payload or experiment per the Delivery Order.  The contractor shall deliver all safety documentation required by and in accordance with NSTS/ISS 13830 for Shuttle or ISS experiments (DID# PA-05).  The contractor shall support all reviews of this safety documentation.  The contractor shall meet the requirements of NSTS 1700.7, NSTS 1700.7 Addendum, NSTS/ISS 18798, and KHB 1700.7 where applicable (e.g., operations at Kennedy Space Center).  In addition, for ISS experiments, the design and operational requirements of NSTS 1700.7 Addendum shall be met.  The contractor shall meet the requirements of GHB 1771.1, Range Safety, GMI 1771.1, Range Safety Policies & Criteria for GSFC/Wallops Flight Facility and White Sands Users Handbook for sounding rocket payloads.  Any activity conducted at NASA LeRC facilities shall be conducted in accordance with NASA Lewis Safety Manual and the  LeRC Environmental Programs Manual..  The contractor shall impose the above mentioned applicable safety requirements on all subcontractors and suppliers.

The contractor shall provide a Safety and Health Plan based on DID# PA-12.   This plan shall address all hazards related to the work to be performed at LeRC and the contractor’s facilities, exposures to workers and LeRC personnel and plans to mitigate these hazards.

### Materials and Processes

The contractor shall have a materials assurance process for documenting the Materials and Processes associated with the final design hardware using a Materials Identification and Usage List (MIUL), see DID# PA-06.  Materials Usage Agreements shall also be submitted for all materials on the MIUL that are not rated “A” or better per MSFC-Handbook-527.  Materials not located in MSFC-Handbook-527 shall be tested per NSTS 22648 for Flammability Configuration or NASA-STD-6001 for all testing.  The materials assurance process must provide for certification of all parts and materials for composition and properties as defined by the design criteria.  Materials used in applications, such as, limited life, safety, and fracture critical shall be traceable through all critical processing procedures up to end-item application.  The contractor shall assure NASA that the space flight materials used meets all relevant safety requirements and can be flight certified by NASA.

For hardware developed under the contract, the contractor shall consider materials used in the fabrication of space flight hardware to be selected by considering the design and operational requirements.  The properties of the candidate materials can be obtained per Mil-Handbook-5 “Metallic Materials and Elements for Aerospace Vehicle Structures” and Mil-Handbook-17, “Polymer Matrix Composites”.  Material properties that shall be considered include, but not limited to, mechanical properties, fracture toughness, flammability, off-gas characteristics, corrosion, stress corrosion, thermal and mechanical fatigue properties, thermal vacuum stability, and fluid compatibility.  Material codes used for evaluation shall be obtained from MSFC-Handbook-527 “Materials Selection List for Space Hardware Systems”.  For International Space Station payloads, refer to SSP 30233 “Space Station Material and Processes” for the material assurance requirements.

### Reliability and Maintainability

The contractor shall assure the reliability, availability and maintainability (RAM) of the hardware that meets the definitive requirements defined in SARGE.  The contractor shall be responsible for imposing the RAM requirements on all subcontractors and suppliers and integrate all subcontractor and supplier RAM products into a comprehensive compliance package as specified in SARGE.

For some Delivery Orders, the contractor shall be required to perform RAM assessments.  In addition, the contractor may be required to conduct tests to demonstrate the ability of flight experiments to survive mission simulation conditions, be reliable/maintainable in the space environment, and offer a 90% probability for the mission to succeed.

### Software Product Assurance

The contractor will be required to assure the management, safety, and control of all flight-related software/firmware (including that used for ground support or mission operations) and the software development process (reference NASA-STD-2201-93).  The contractor will be expected to assess the control level of the software and its safety related requirements and level (reference NASA-STD-8719.13A & NASA-GB-1740.13-96).  Based on software control level (reference LeR-P-2.10.2 and the LeRC Software Development Manual) the contractor will be expected to develop and utilize a Software Assurance Plan (DID# PA-11) to assure the management, safety, and control of the software products and the software development process (e.g., configuration management, risk management, performance, functionality, safety, reliability, verification & validation processes and non-conformance reporting).

### Risk Management

The contractor shall have a risk management process to control critical flight hardware, software, and documentation.  Specific attention shall be given to the control of physical and functional interfaces.  The specific process to be used by the contractor shall be defined in the Risk Management Plan (DID# PM-02), per 7120.5A Section 4.3, based on the level of hardware complexity and carrier requirements.  The contractor shall provide a status of the critical risks identified at the Technical Information Meetings or Progress Reviews as defined in the management section.

## EXPERIMENT DEFINITION

The Government shall nominally provide initial system level experiment concept(s) for the Science Concept Review (SCR) to meet science requirements as defined by the Principal Investigator (PI), identify any engineering feasibility issues and perform key tests that demonstrate the proposed science requirements can be satisfied.  The Government will support the PI’s identification and refinement of the science requirements by designing and developing bench-top hardware (breadboards) and rigs for laboratory and/or low-gravity ground-based testing.  The outcome of the Experiment Definition phase is to establish, through science peer-review, that the scope and feasibility of the experiment have been adequately addressed to propose a definitive flight experiment.  The completion of this phase occurs upon peer-review approval at the Science Concept Review.  Typical activities performed during the Experiment Definition phase are described in the following sections (provided for information purposes only):

### Requirements Definition

Top-level engineering requirements that address the Principal Investigator’s science requirements are defined.  The NASA hardware development team works with the experiment's Project Scientist through a structured process to interpret the PI’s experiment needs and determine the top-level technical requirements.

### Concept Feasibility

The system design and mission analysis are conducted to produce feasible concept(s) that address the science requirements and to evaluate potential mission carrier options.  The concepts identify possible subsystems that address the science objectives and the key high-risk development areas.  The mission analysis may include: technology alternatives, operations scenarios, risks identification, and infrastructure evaluations.

Engineering feasibility issues are identified based on the science requirements to determine a resolution approach and perform initial breadboard level testing as required.  Engineering feasibility issues include: fundamental capabilities required to meet science objectives, reduce life-cycle costs, assess technical viability based on current industry capabilities, and assess the diagnostic methods utilized in the PI’s research.

### Project Formulation

The Government will formulate a preliminary engineering plan for development of the experiment concept.  Schedule and budget information is developed to meet the requirements of the Science Concept Review with a rough order of magnitude estimate for the overall budget and schedule that includes key milestones and an overall implementation approach to flight.

## REQUIREMENTS DEFINITION

The contractor shall thoroughly define project requirements and provide sufficient detailed definition of the project technical, management, budget, and institutional support plans needed to enable a firm NASA commitment to accomplish the science objectives on schedule and within budget.  The outcome of the Experiment Definition phase is to establish, through science and engineering peer-review, that the engineering concept of the experiment will be sufficient to meet the detailed science requirements in the Principal Investigator’s Science Requirements Document (SRD), the engineering requirements derived from the science requirements have been determined, major feasibility issues have been resolved or feasibility resolution plans established, and the project plan and initial costs have been developed to enable NASA to assess the readiness of the project to enter the preliminary design phase.  The performance standard for successful completion of this work element occurs upon peer-review approval to NASA at a Requirements Definition Review (RDR).  In the performance of Experiment Definition efforts, the contractor shall accomplish the following:

### System Requirements Analysis

The contractor shall define the fundamental system requirements per DID# R-01 (Draft) based on science, potential carrier, operations, and safety and quality requirements.  A requirement compliance matrix based on these system requirements shall also be developed for the Requirements Definition Review that shows compatibility between engineering implementation and the science requirements.

### Concept Feasibility

The contractor shall determine the overall feasibility of the candidate experiment concept(s) that consider affordability, technology readiness, operations, infrastructure, content, risk, and potential procurement strategies.  The technology readiness assessment shall evaluate the fundamental technology requirements of the experiment concept to ensure that specified science objectives will be met, project cost or risk will be minimized and identifies where significant technology gaps exist, such that it would be difficult for a concept to be realized.

### Breadboards

The contractor shall minimize development risk based on identified engineering feasibility issues through the design and development of breadboards, as appropriate, to evaluate functional performance.   Breadboard testing should be focused on determining whether the engineering experiment concept will meet the science requirements defined in the PI’s SRD.  Any concept limitations should be identified and alternate concepts and technologies should be tested in areas where meeting a science requirement may be challenging.  This may require the use of ground-based low-g test facilities (drop towers, KC-135, etc.), the contractor shall identify and schedule with NASA the use of such facilities.  The results of the breadboard testing shall be made available for NASA review.  Any requirement for additional hardware breadboarding of high risk subsystem function(s) or special equipment that are necessary to be performed during the Preliminary Design phase shall be identified and documented in the RDR presentation package (DID# D-01).

### Integrated Concept

The contractor shall develop an initial integrated concept of the selected experiment that includes the design constraints and interfaces of the recommended carrier (ISS, sounding rocket, NSTS, etc.).  This initial concept shall provide sufficient detail to show the overall feasibility, compliance to the SRD requirements, carrier integration compatibility, and subsystem level packaging.  The integrated concept may require the use of the carriers ground integration unit or simulators to determine overall feasibility; this need shall be identified to NASA for proper availability for testing.  The selected experimental concept shall be documented in a draft Baseline Concept Description (DID# D-03) document and presented at the RDR.

### Project Planning

The contractor shall formulate an overall engineering plan which defines and details the approach, schedule, hardware classification, and resource requirements, so that programmatic commitments can be made based on a recommended flight carrier.  The contractor shall also provide a life cycle costing analysis necessary to produce the selected concept.  Schedule and budget information shall be developed and presented as part of the RDR review package that meets the requirements of the Requirements Definition Review with a rough order of magnitude estimate for the life cycle costs and overall schedule that includes key milestones and an implementation approach to flight.

## PRELIMINARY DESIGN

The contractor shall develop a preliminary design that can demonstrate at the system, subsystem and component level compliance to the system and science requirements with acceptable risk.  The outcome of the Preliminary Design phase is to establish, through independent engineering-review, that the proposed engineering design solution for the experiment is expected to meet the performance and functional requirements at the configuration item level, the design is verifiable and does not pose major problems which may cause schedule delays or cost overruns, all interfaces and verification methodologies have been identified, and all system requirements have been allocated to the subsystem and component level and the flow down is adequate to verify system performance.  The design activities may include the design of diagnostic packages (illumination, imaging, optical diagnostic techniques, microscopy, interferometry, etc.), avionics packages (command, control, data handling, image processors, communication, etc.), power distribution packages (monitoring, switching, power isolation, conditioning, V/A regulation, EMI suppression, electrical fault protection, etc.), instrumentation (temperature sensors, pressure sensors, flow rate sensors, thermal imaging, leak detection, etc.), structural hardware, associated interfaces, environmental control (collection, transportation, and rejection of thermal, precision temperature and flow control), gas distribution (storage, mixing, valving, composition , containment, etc.), capture and containment of contamination sources, design of experiment test cells, and the design of an integrated system.  The performance standard for successful completion of this work element occurs upon engineering-review approval by NASA at a Preliminary Design Review (PDR).  In the performance of Preliminary Design efforts, the contractor shall accomplish the following:

### Requirements

The contractor shall develop preliminary design-to specifications (DID# R-01) that incorporates the PI experiment requirements, carrier requirements and determine all interface requirements, including software interfaces, shall be documented.  Also, if required by the Delivery Order, a preliminary Interface Control Document (DID# R-02) shall be developed with the carrier based on the appropriate carrier integration template.  All experiment functional requirements shall be allocated to either hardware or software with a flow-down of requirements to the subsystems and components, if applicable.  The estimated resources required of the carrier shall also be determined that includes resource allocations and appropriate margins.  Compliance with experiment requirements shall be determined based on the preliminary design and documented in a Requirements Compliance Matrix (DID# D-07).

### Design

The contractor shall develop a preliminary hardware and software design that complies with the experiment’s system requirements based on the science, carrier, interface, and product assurance requirements.  These requirements are defined in the specific project Science Requirements Document and System Requirements Document or as identified in the Delivery Order.  The preliminary design shall establish the overall system architecture, identify all the external interfaces, develop an operations concept, develop experiment layouts, detailed drawings, mass properties, interface schematics, and preliminary materials & parts lists.  The contractor shall perform engineering analyses (thermal, dynamic, vibration, optics, etc.) as appropriate in the design of the mechanical, electrical, and system hardware.

The contractor shall submit and present design progress for review at various times and locations as specified in the Delivery Order.  The contractor shall develop a Preliminary Design Review package (DID# D-01) that shows a mature understanding of the mission objectives and requirements (Packaging, Structural, Thermal, Testing of components, electrical EMI) and preliminary drawings according to DID# D-04.  The preliminary design may also be documented in a Baseline Concept Descripiton document (DID# D-03).

The contractor shall develop a software design and initial programming in parallel with the hardware design.  The design shall clearly define the hardware/software interfaces and identify software requirements, documented in a preliminary Software Requirements Document (DID# V-04).

The contractor shall also identify, design and develop/procure any required ground support equipment necessary for the development and/or implementation of the experiment hardware.  This shall include identifying any transportation and handling considerations that will impose requirements on the flight hardware or support equipment.

### Prototype/Breadboard  Development

The contractor shall minimize system and/or subsystem development risk based on identified engineering feasibility issues through the design, development and fabrication of system and/or subsystem-level mockups, breadboards, brassboards and prototype hardware, as specified by the Delivery Order.  The hardware may be required to evaluate form, fit and/or functional performance, as well as manufacturing techniques, to determine overall performance and compliance to the system requirements.  Risk reduction hardware development and testing should be focused on the details of the engineering experiment design in meeting all of the requirements defined in the experiment’s system requirements.  Any hardware limitations should be identified and alternate design prototypes should be built and tested in areas where meeting a system and/or subsystem requirement may be challenging.  The results of the prototype testing shall be made available for NASA review and incorporated into the final design and if appropriate, the engineering model.

### Verification & Safety

The contractor shall provide assurance that the preliminary design will meet all carrier safety and verification requirements.  The contractor shall perform safety hazard analysis to identify hazards and mitigation methods to assure that the proposed preliminary design does not violate any safety requirements which will endanger human life or mission success.  These analyses shall be documented in Safety Hazard Reports (DID# PA-03) and a Phase 0/1 Safety Compliance Data Package (DID# PA-05), unless otherwise defined in the Delivery Order.  The contractor shall also participate in the Phase 0/1 Safety Review at the site designated per the Delivery Order.  The safety critical structures shall also be identified through analysis and documented in a Safety Critical Structures Data Package (Preliminary) and a Fracture Control Plan (DID# PA-04).

The contractor shall develop preliminary verification plans (DID# V-01 and DID# V-02) that identify clearly where, how, and when each function and performance requirement is verified in the verification program before launch and, if applicable, how these requirements are again going to be verified on-orbit.

The contractor shall assure that all the chosen materials for the experiment design are properly safety and meet material requirements for corrosion resistance, stress corrosion cracking susceptibility, outgassing, flammability, fluid compatibility, and offgassing in habitable areas (SOW 4.2.3).  The contractor shall identify material usage in a preliminary Materials Identification and Usage List (DID# PA-06) document or justify the use of non-A-rated materials (MUA) in space flight hardware if required.

### Integration and Operations Planning

The contractor shall develop preliminary versions of the Payload Integration Agreement (DID# R-03) main volume and the Interface Control Document (DID# R-02) or equivalents, based on the carrier’s integration template. These integration planning and requirements documents shall include evaluations based on the preliminary design that include: payload configuration, payload training requirements, payload command and data handling requirements, ground data services requirements, payload operations requirements, and payload ground integration/deintegration requirements.

The contractor shall identify and design any simulators required for training, integration, and operations to support the experiment mission.  The identified simulators and concepts for each shall be provided as part of the PDR presentation package.  For ISS FCF sub-payloads, the contractor shall work with the FCF engineering team to determine the training requirements to support the formulation of an integrated FCF training plan.

### Project Planning

The contractor shall develop a detailed engineering plan, or modification of the existing Contractor Project Plan (DID# PM-01) that defines the structure, approach, and processes required to complete the final design, development, fabrication, assembly, and test of the required hardware, software, and associated infrastructure. The contractor shall also develop a Software Management and Development Plan (Preliminary), per DID# PM-03, that provides the overall approach for development of the project software.   The life cycle costs of the project may also be requested in the Delivery Order that include: the direct, indirect, recurring, nonrecurring, and other related costs in the design, development, production, operation, maintenance, support, and retirement of the experiment.  The contractor shall also identify key risks based on the contractor’s Risk Management Plan (DID# PM-02) that requires on-going monitoring to assure compliance to requirements, schedule or costs.  The key risks shall be identified and provided to NASA along with evidence that the preliminary design will meet performance, cost, and schedule as planned as part of the PDR presentation package that includes any long lead items which may threaten schedule compliance are identified and/or procured.

### Product Assurance Plan

The contractor shall provide a Product Assurance Plan (DID# PA-01) that defines the tailored approach to assure the safety, quality and reliability of Delivery Order’s space experiment systems and components.  The contractor shall also develop a Software Assurance Plan in accordance with DID# PA-11 which describes the software management procedures, policies, and controls to be used in developing the flight software.

The contractor shall perform reliability and maintainability analysis where appropriate to assure that the experiment’s preliminary design will meet the mission requirements through reliable subsystems/components and/or through maintenance.  Reliability analysis is based on sound methodology and presents realistic predictions for logistics planning and life cycle cost analysis.  The results of this analysis shall be part of the PDR presentation package.

## DESIGN AND DEVELOPMENT

The contractor shall develop a final design that can demonstrate at the system, subsystem and component level compliance to the system, carrier, product assurance, and science requirements, as well as other applicable requirements identified in the Delivery Order.  The outcome of the Design and Development phase is to complete the design of the experiment hardware and software that meets all performance and functional requirements as demonstrated through test and analysis with all technical problems and design anomalies resolved without compromising system performance, reliability, and safety.  The performance standard for successful completion of this work element occurs upon NASA approval at a Critical Design Review (CDR) or a Verification and Test Review (VTR).  In the performance of Design and Development efforts, the contractor shall accomplish the following:

### Specifications and Analyses

The contractor shall generate complete system build-to specifications that includes hardware and software.  This activity shall include preparation of specifications for systems, subsystems, and, if appropriate, components which meet the requirements of DID# R-01.  Requirement traceability establishing the linkage of all derived requirements shall be performed to ensure verification and validation of the overall system.  All requirements allocated to software shall be documented in a Software Design Document (DID# D-06) as defined in the Delivery Order.

The contractor shall perform, where required, system level analyses and trade studies to optimize the operating design conditions; support the development of the final design; demonstrate overall compliance with requirements; support the verification activities; establish system performance; evaluate thermal, environmental and structural behavior (vibration, loads, etc.); determine reliability and maintainability; and support the integration of developed components.

### Flight Design

The contractor shall develop an overall detailed reference design such that all requirements are achieved, unless specifically waived by NASA.  The contractor shall develop a comprehensive description of the flight design describing the resultant final design and documented per the Delivery Order, such as a Baseline System Document (DID# D-03).  As part of this final design effort, the contractor shall develop overall system schematics, layouts, interface requirements and drawings, mass properties, volumetric characteristics, resupply requirements, and resource requirements.  The contractor shall develop a system layout showing the relationship of each component or subsystem, the system structure, harnessing, mounts and assembly requirements.  Fabrication and assembly drawings of the design shall be in accordance with drawing standards defined in DID# D-04.

The contractor shall develop a software design and code development based on the hardware design and requirements that may also include simulator software, training software and ground support software, based on carrier requirements, hardware requirements, and NASA software development requirements.  The contractor shall also develop the software design that includes software simulations and prototyping to eliminate any potential risks, which may hamper software coding, and integration.  The software design shall be documented in a Software Design Document (DID# D-06) that describes the interface design, data requirements and architectural design of the software.

Upon request of the Delivery Order, the flight hardware and software design may be subjected to external design audits by NASA involving specialty engineering groups, manufacturing, safety, quality, operations and utilization and test organizations to ensure the integrity and validity of the final design.

### Engineering Model Development

If defined in the Delivery Order, the contractor shall minimize development risk through the design, development and fabrication of an engineering model.  The contractor shall perform the testing and integration activities associated with the engineering model and/or component, subsystem, and system development required to validate the final design.  The results of the testing and integration activities shall be made available for NASA review and incorporated into the final design.

### Verification and Safety

The contractor shall develop a final, comprehensive Verification Plan (DID# V-01) and associated Individual Item Verification Plans (DID# V-02) to assure that the payload hardware and associated software will meet all defined requirements.  The Verification Plan(s) shall identify clearly where, how, and when each function and performance requirement is verified in the verification program before launch and, if applicable, how these requirements are again going to be verified on-orbit.

The contractor shall assure that all the chosen materials for the experiment design are properly safety and meet material requirements for corrosion resistance, stress corrosion cracking susceptibility, outgassing, flammability, fluid compatibility, and offgassing in habitable areas (SOW 4.2.3).  The contractor shall identify material usage in a final Materials Identification and Usage List (DID# PA-06) document or justify the use of non-A-rated materials (MUA) in space flight hardware if required.

The contractor shall provide assurance that the final design will meet all carrier safety and verification requirements.  The contractor shall perform an integrated safety analysis of the final design that shows that there are no outstanding hazards, which cannot be controlled or are within an acceptable risk level if waivers are required.  These analyses shall be documented in Safety Hazard Reports (DID# PA-03) and a Phase 2 Safety Compliance Data Package (DID# PA-05), unless otherwise defined in the Delivery Order.  The contractor shall also participate in the Phase 2 Safety Review at the site designated per the Delivery Order.  The safety critical structures shall also be identified through analysis and documented in a final Safety Critical Structures Data Package .

### Carrier Integration, Operations & Training Planning

The contractor shall perform the analysis and implementation planning necessary to define, prepare for and execute the operation of the experiment, including design or development of any equipment required for operations.  The contractor shall prepare the experiment’s operational requirements and plans, operations concepts, mission profiles, mission rules, crew procedures and timelines, and contingency plans. The operations requirements with the carrier shall be documented in a preliminary Payload Operations Requirements Data Set (DID# R-03) based on the carrier’s integration template unless otherwise directed by the Delivery Order.

The contractor shall document the experiment’s with the carrier in a preliminary Payload Configuration Data Set (DID# R-03) based on the carrier’s integration template unless otherwise directed by the Delivery Order.

The contractor shall prepare training requirements and plans, training aids, models, simulators, software, and other training necessary for ground and flight operations.  The Training Requirements with the carrier shall be documented in a Payload Training Requirements Data Set (DID# R-03) based on the carrier’s integration template unless otherwise directed by the Delivery Order.

The contractor shall prepare ground data services requirements and plans necessary for ground and flight operations on the specified carrier.  The ground data service requirements with the carrier shall be documented in a Ground Data Services Data Set (DID# R-03) based on the carrier’s integration template unless otherwise directed by the Delivery Order.

The contractor shall perform the integrated logistic analyses required to formulate optimum spares provisioning and maintenance strategies for the life of the experiment.  The transportation and handling of the experiment hardware and associated ground support equipment shall be identified.  If requested in the Delivery Order, the results of these analyses shall be incorporated and maintained in an Integrated Logistics Support Plan per DID# OP-01.  The contractor shall also determine the predicted reliability of the system hardware.

### Project Planning

The contractor shall develop a detailed Assembly, Integration, and Test Plan (DID# V-12) for the required activities that includes carrier integration activities as part of CDR or VTR.  The schedule shall indicate parts procurement, fabrication, and the acquisition of required special tooling or fixtures, if required.  The closeout of all PDR actions shall also be documented as part of the CDR or VTR review presentation.

## FABRICATION, ASSEMBLY AND TEST

The contractor shall fabricate, assemble, test, verify, and deliver the required hardware, software, and documentation specified in the Delivery Order.  The outcome of the Fabrication, Assembly and Test phase is to provide an operational system that satisfies the ultimate user.  This involves the development of a certified flight system, unless otherwise specified in the Delivery Order, all-necessary development and qualification hardware and software; ground/flight/logistics support equipment, spare parts required to sustain the system and required integration documentation.  The performance standard for successful completion of this work element occurs upon engineering-review approval by NASA at a Pre-Ship Review (PSR) and approval of a Certification for Flight Readiness.  In performance of fabrication, assembly and test effort, the contractor shall accomplish the following:

### Mission Integration

The contractor shall perform mission and technical integration efforts necessary to assure delivery of a fully functional system (flight and ground unit) which satisfies all applicable carrier requirements.  The contractor shall ensure compatibility of the major subsystems with each other and shall assure compatibility of the total system with all required test facilities, the selected carrier (ISS, FCF, EXPRESS, etc.), and the associated transportation system.  This effort shall also include development and/or support of the appropriate integration documentation and its annexes (DID # R-03) in accordance with development and delivery of required interface and operational data in the appropriate carrier integration format; support of all carrier integration working groups and panels; and development of required safety, operation, and training documentation.  Functional, thermal, fracture control, and fatigue analyses shall be performed as required in accordance with the selected carrier requirements documents to demonstrate that the hardware design satisfies system requirements.

### Flight Unit/Ground Unit

The contractor shall fabricate, assemble, and test a flight unit that meets the specifications, quality and product assurance requirements identified in the Delivery Order and SARGE for the experiment classification and flight carrier.  The Flight Unit shall be subjected to acceptance test levels and durations with its intended use to be operational in space as defined in the Verification Plan.

The contractor may be required to fabricate, assemble, and test a Qualification Unit to determine flight acceptance verification and compliance with specifications.   The Qualification Unit shall consist of the same systems and subsystems as the Flight Unit and shall be verified to be physically and functionally identical to the Flight Unit.  The primary function of the Qualification Unit is to demonstrate through testing to qualification levels that the Flight Unit design meets all requirements.  The Qualification Unit is not intended for flight unless otherwise specified in the Delivery Order.  The Qualification unit shall be refurbished by the contractor to flight level specifications if intended for flight.  The Qualification Unit shall be maintained under the same quality control and configuration management procedures as the Flight Unit.

A Ground Unit may also be required (per the Delivery Order) to be used for ground integration activities, trouble shooting of the on-orbit hardware, and/or the checkout of proposed upgrades to the on-orbit hardware.  This unit is typically identical to the Flight Unit, but will not receive full flight qualification testing.

The contractor shall design, fabricate/procure, assemble and verify the hardware necessary for handling, transporting, storing, and qualifying the flight unit, ground unit and trainer  (hardware and software) in accordance with the applicable carrier ground support design requirements identified in the Delivery Order.   The contractor shall supply and maintain the spare parts required supporting the flight and ground-based hardware and related equipment as specified in the Delivery Order and the experiment’s Integrated Logistics Support Plan.  All fabrication, inspection, checkout, acceptance test, and preparation for delivery requirements, applicable to deliverable hardware and software, shall also apply to the spare items furnished.

The contractor shall develop, verify, validate, and maintain all software necessary to control and utilize the hardware deliverables developed to Delivery Order specifications.  The contractor shall install and verify/validate all software necessary for the operation of all developed hardware per the Delivery Order such as the Ground Unit, Qualification Unit, Flight Unit, Trainers, interface verification, ground support equipment, and simulators.

### Installation, Assembly & Checkout (IACO)

The Contract shall conduct all necessary activities as defined in the Assembly, Integration, and Test Plan to ensure the successful integration of all hardware and software with the selected carrier.  These activities shall be in accordance with applicable carrier interface documentation to ensure that hardware and software comply with all carrier payload certification requirements, as well as to ensure that all operational, safety, and reliability requirements are met.  Results of this task shall be reported in accordance with the experiment’s Verification Plan (Certification Certificates).  The contractor shall provide calibration, proof testing, dynamic balancing and integrated operation of the experiment system and functional checkout of fabricated systems and components as specified in the Delivery Order.  Specific Delivery Orders may require assembly, installation and system checkout in NASA facilities.  The contractor shall inspect all work prior to delivery to insure compliance to requirements.  A written inspection report shall be delivered with the completed hardware (DID# V-11).

### Verification and Safety

The contractor shall conduct qualification, acceptance and verification activities (test, analysis, etc.) on components, subsystems and combined assemblies.  These activities shall be in accordance with the Verification Plan (DID# V-01) to assure that the payload hardware and associated software meets all defined requirements.  The contractor shall verify integrated performance, assembly interactions, and interfaces, as appropriate.   Unless furnished by NASA, the contractor shall provide all test support equipment, test fixtures, ground support equipment, and simulators, required in the performance of the verification tests.  The contractor shall generate and maintain a requirements management and traceability and close-out system to ensure and document that all design and performance requirements requiring verification are addressed by the verification program and all verification requirements are closed-out.  The closeout system shall maintain verification and assessment reports, certification statements, and comprehensive verification reports (DID # V-04 & DID# V-08).  The experiment system verification tests shall include science verification & validation tests that includes an assessment of the system performance by the Principal Investigator to ensure that the hardware can successful perform the functions required to meet the science requirements of the experiment.  The software shall also be verified and validated based on a Software Verification and Validation Plan (DID# V-09) with the results documented in a Software Verification and Validation Report (DID# V-10).

The contractor shall provide assurance that the experiment system meets all carrier safety and verification requirements.  The contractor shall perform an integrated safety analysis and test of the flight hardware that shows that there all hazards are controlled or approved waivers have been approved detailing acceptable risk level.  These analyses and verification tests shall be documented in Safety Hazard Reports (DID# PA-03) and a Phase 3 Safety Compliance Data Package (DID# PA-05), unless otherwise defined in the Delivery Order.  The contractor shall also participate in the Phase 3 Safety Review at the site designated per the Delivery Order.

The contractor shall facilitate the pre-mission operations with the PI to characterize the hardware and obtain ground-based data in preparation for flight.  This activity shall include providing availability of the hardware and software, set-up of operational parameters, and supporting the operation of the experiment.

### Operations Capability Development

The contractor shall develop procedures for crew tended, untended, and off-nominal operations with the input and approval of experiment, PI, and carrier representatives, including Flight Safety.  The contractor shall deliver any hardware or software required for operations capability as identified in the Delivery Order, such as simulators or data processing equipment to support the mission.

The contractor shall conduct logistics support analyses to determine the support required for pre-flight, flight, on-orbit, return, and post-flight operations of hardware and software integrated in an ISS experiment.  Based on the logistics support analyses and other inputs, the contractor shall provide adequate flight and non-flight spares.  The analyses shall include plans for the most efficient physical transfer of flight and non-flight items required supporting the experiment operations.  The contractor shall provide the physical packaging, handling, storage, and transportation of all flight and non-flight items.  A final Integrated Logistics Support Plan (DID# OP-01) shall be provided that documents the experiment’s ILS approach.

### Training

The contractor shall develop, in conjunction with specific users, all training materials for the experiment, including experiment specific training unit development as defined in the Delivery Order.  The contractor shall develop and support the installation of the experiment-training unit at the appropriate site for the carrier, if applicable.  The contractor shall work with the PI teams, the flight crew, and the carrier training organization to develop the requirements for crew training, if applicable.  These requirements will drive the design and development for the experiment training materials.  The contractor shall implement the training requirements for the training sessions, for any computer-based training, for part-task trainers, and for on-orbit training.  The contractor shall provide experiment hardware and software training for the PI (s) and associated team, the Project Scientist, and Payload Specialist(s) in the operational/functional limitations and capabilities of the instrumentation for proper decision making and development of experiment procedures.

### Carrier Integration

The contractor shall be responsible for all ground servicing at the launch site (e.g. KSC) to ensure the successful integration of all experiment hardware with the carrier or transportation system (i.e. MPLM for ISS). The contractor personnel shall actively participate in the launch processing team activities and shall add/modify requirements, concur on procedures, analyze data, make engineering recommendations and decisions required by conditions not within specifications.  The contractor’s launch site activities shall be in support of the payload ground operations effort provided by NASA’s launch site personnel.  Specifically the contractor shall: develop and implement Launch Site Operations and Test Procedures (DID# OP-04) for the experiment hardware, support the development of the requirements for testing, servicing, and facility services required to process the experiment hardware through pre-launch activities, monitor tests, evaluate test data, maintain records of the tests, and provide engineering expertise to resolve hardware/software problems, and ensure the experiment hardware has been properly tested, support Launch Readiness Reviews (LRRs) and Flight Readiness Reviews (FRRs) with engineering and management data to ensure the experiment hardware is ready for flight.  Following verification of flight readiness, the flight hardware and associated documentation shall be provided to the launch element manager for pre-flight processing and launch.

### Product Assurance

The contractor shall implement the experiment specific Product Assurance Plan (DID# PA-01) in the performance of the hardware and software development, test, and verification.  The contractor shall maintain and provide to NASA the failure history of the hardware and software along with remedial and preventive actions taken.  The contractor shall provide identification of any specification waivers and deviations required along with the basis for approval.  The contractor shall also maintain the status of limited life components of the experiment system.

## OPERATIONS

The contractor shall support on-orbit integration activities, flight and data reduction, experiment real-time operations, and data reduction for PI analysis.  The outcome of the Operations phase is to operate the experiment to acquire the required scientific data for the PI.  The operational activities commence with delivery of the experiment to the ultimate operator for use in its intended environment.  The performance standard for successful completion of this work element occurs upon achieving the full success criteria for the experiment as described in the Science Requirements Document.  In performance of operations effort, the contractor shall accomplish the following:

### On-orbit Operations

The contractor shall be responsible for the real-time operations and any supporting activities of the PI’s experiment in conjunction with the carrier operations per the Delivery Order.  The contractor shall provide trained staff for console operations.  Appropriate personnel shall be on console when the experiment is active or other planned operations are being performed.  The contractor shall be responsible for on-console support of on-orbit installation & set-up, check-out and verification of the experiment hardware and software, if applicable; the planning and scheduling of all experiment on-orbit operations; obtaining or requesting all necessary ground and on-orbit resources; and implementing and following the planned experiment operations.  The contractor shall be prepared to respond to crew and ground team communications, and off-nominal situations.  The contractor shall develop standard procedures to resolve on-orbit problems or anomalies.

The contractor shall provide PI mission operations support including coordination of real-time experiment requirements with the PI, the carrier, and other appropriate entities; acquire and process scientific real-time data according to pre-determined requirements; support the correlation of scientific data with mission events; provide appropriate personnel to support on-console mission operations and scientific data analysis at the carrier’s control center (LeRC TSC for FCF, White Sands for Sounding Rockets, etc.); preparation of data products for data dissemination including general and PI-specific mission summary reports; preparation of unique data analysis reports for the PI; maintain scientific information databases; and participate in working group interchanges as defined in the Delivery Order.

### Post Mission Operations

The contractor shall be responsible for the post mission operations of the PI’s experiment to obtain baseline scientific data per the Delivery Order.  The contractor shall be responsible for ground installation & set-up, check-out and verification of the experiment hardware and software, if applicable; the planning and scheduling of all experiment ground operations; and implementing and following the planned experiment operations that duplicates PI experiment data points per the Delivery Order.  The contractor shall acquire and process scientific real-time data according to past flight timelines; support the correlation of the scientific data; preparation of data products for data dissemination; preparation of unique data analysis reports for the PI; maintain scientific information databases; and participate in working group interchanges as defined in the Delivery Order.

### Sustaining Engineering & Maintenance

The contractor shall conduct appropriate analyses, data evaluations, and ground tests to maintain the on-orbit system.  This includes the tracking of limited life items for safety and/or mission assurance reasons; incorporating small upgrades as required; standard reporting of the on-orbit experiment performance; developing trend analyses using on-orbit systems reports and other available data; and implementing the experiment maintenance plan designed to maintain the full operational capability of the experiment.

# Milestone Reviews

Successful completion of each review includes the following:

- Delivery of a review presentation package no later than two (2) weeks prior to the review, (unless waived by the Delivery Order)

- Delivery of supporting documents no later than six (6) weeks prior to the review, unless otherwise indicated in the Delivery Order

- Formal review presentation (unless waived by the Delivery Order)

- Delivery of all items listed below for each review, plus any additional items identified in the Delivery Order

- Documented closure of any actions submitted at prior reviews

- Review board determination of adequacy of all deliverables (documented in the review board’s assessment report)

The review board’s assessment report shall be issued within 4 weeks of the review.  Individual documents shall be reviewed by NASA and approved, approved with modification, or disapproved.  Any documents disapproved by NASA will require re-submittal and re-review until approved by NASA.

The descriptions of the major milestone reviews anticipated for the Development of PI Specific Experiments, Instruments and Diagnostics activities are provided in the following sections.

## Science Concept Review (SCR)

The purpose of the SCR (to be conducted by the Government, the contractor may be asked to attend for information purposes) is to establish, through peer-review, that the scope and feasibility of the experiment have been adequately addressed to propose a definitive flight experiment.  The primary objectives of the SCR are to:

Affirm the merit of and need for the experiment (value to the scientific community), establish the detailed scientific objectives, confirm the rationale for a microgravity experiment, justify the use of space-based laboratories for the microgravity environment, and review the proposed scope and experimental approach.  In addition, assess maturity, priority, and completeness of the preliminary science requirements to meet the objectives, and confirm that scientific feasibility has been completely demonstrated.  The PI presents the information for the review panel to make these judgments.

Identify the PI’s plan of activity with specific milestones between SCR and the Requirements Definition Review (RDR) with the goals of finalizing science requirements, improving models or theories, conducting additional ground-based experiments and completing technology development.  (Often the plan proposed at SCR needs modification based on the panel’s input provided at this review).  The PI presents this information.

Evaluate proposed space-based experiment concept (block diagram level) with emphasis on compatibility with science requirements and identify engineering feasibility issues.

Define engineering plans (emphasizing the most critical, costly and difficult tasks) to develop the experiment concept into flight hardware (cartoon flight concept may be presented).  Prepare the schedule and budget to reach RDR in reasonable detail, and provide rough order of magnitude budget and schedule estimates to flight.

## Requirements Definition Review (RDR)

The purpose of the Requirements Definition Review (RDR) is to evaluate, through peer-review, the maturity of the engineering requirements of the project.  Successful completion of this review will be based upon the following success criteria (some items provided are overall review requirements and are not the responsibility of the contractor):

Science requirements document (SRD) is finalized (PI Responsibility).

Relevance of the science objectives and the requirement to conduct a flight experiment are confirmed (PI Responsibility).

Feasibility of the experiment has been demonstrated with the presentation of results of the ground-based science or laboratory testing.

Engineering design requirements are documented and reviewed by the panel and demonstrate compliance with the science requirements.

Experiment design is documented, as a minimum at the system level and reviewed by a NASA selected engineering and science panel.

The payload carrier accommodations and interfaces are defined and documented.

The development issues identified at the SCR have been resolved or plan in place to resolve by PDR.

Review the disposition of any SCR action items provided to the contractor.

Submit for review and NASA approval the Contractor’s Project Plan which includes the approach, work breakdown structure, configuration management approach, hardware/software development and test philosophy, schedules, and costs.

Methodology used to develop the cost estimate, and costs by work breakdown structure is reviewed.

Document and submit for review the technical, schedule, and cost risks of the proposed experiment in accordance with the Risk Management Plan.

RDR Minimum Deliverables:

Documented results of ground based science or laboratory testing

System Requirements (draft)

Requirements Compliance Matrix showing compliance with the science requirements

Baseline Concept Descripiton document that describes the concept and anticipated performance and operation

Disposition of SCR action items

Identification of flight hardware development risks that includes schedule and cost risks of the proposed experiment

Payload/Carrier interface requirements (can be part of the System Requirements)

Contractor’s Project Plan that includes a software development approach

RDR Presentation Package

### Preliminary Design Review

The Preliminary Design Review is a formal technical review of the system design and development approach.  The PDR is conducted after the completion of the preliminary design synthesis and before the detailed design process.  This review shall be conducted prior to the fabrication of an engineering model of the flight experiment or prior to completion of the breadboard testing if an engineering model is not being fabricated.  Successful completion of this review will be based upon the following success criteria (some items provided are overall review requirements and are not the responsibility of the contractor):

Principal Investigator’s operations plan and data analysis plan is reviewed (PI responsibility).

Compliance of the system design with the science and carrier requirements is documented or demonstrated.

Functional and performance requirements of the entire system are documented and shown to be appropriate.

Breadboard level testing directed at resolving feasibility issues is presented and reviewed.

Compliance with appropriate design guides and standards, including safety and quality are shown.

Existence and compatibility of the physical and functional interfaces, including software is established.

Special test equipment or tooling requirements is determined.

Long lead part procurements and associated risks are determined.

Review the disposition of any RDR action items provided to the contractor.

Submit for review and NASA approval the Contractor’s Project Plan (DID# PM-01) which includes the approach, work breakdown structure, configuration management approach, hardware/software development and test philosophy, schedules, and costs.

Methodology used to develop the cost estimate, and costs by work breakdown structure is reviewed.

Document and submit for review the technical, schedule, and cost risks of the proposed experiment in accordance with the Risk Management Plan.

A NASA appointed review board shall assess the status of the project in regard to the above items, recommend whether or not to proceed with the project into the software and engineering model development and test and the flight design phase, identify any concerns that exist, and recommend any actions to be taken to enhance the success of the next phase of the project.

PDR Minimum Deliverables required:

Design-to Specifications

PDR Presentation Package

Preliminary Structure Design & Analysis

Preliminary Thermal Analysis

Preliminary Reliability Analysis

Preliminary Environmental Testing Requirements

Draft Payload Integration Agreement (w/carrier organization)

Safety, Flight & Ground, Phase 0/ 1 Data Package and associated Safety Hazard Reports

Preliminary Baseline Concept Descripiton document, or equivalent

Preliminary Requirements (Engineering and Science) Compliance Matrices

Preliminary Verification Plan

Product Assurance Plan

Software Assurance Plan

Interface Control Document (Preliminary), if required, with the carrier

Software Management and Development Plan

Draft Software Requirements Document

Software Design Document (Preliminary)

Documented results of software prototypes

Packaging Layouts

Breadboard/Brassboard/Prototype Test Results

Ground Support Equipment and  Flight Support Equipment Requirements

Revised Contractor Project Plan

### Critical Design Review

The Critical Design Review is a formal technical review conducted after the design has reached the degree of completion needed to permit a comprehensive and detailed examination and data analysis.  Typically, this review shall be conducted after the review of engineering model system testing (if an engineering model is being built) and/or prior to release of drawings for fabrication of the end item hardware. The goal is to have 90 percent of the flight hardware drawings released at the time of the CDR.  Successful completion of the CDR and close out of all action items provides the technical definition for the end item baseline.  Successful completion of this review will be based upon the following success criteria:

The detailed design satisfies the design requirements established in the governing specification unless waivers or exceptions have been approved.

Results of the engineering model system tests and any impact on the flight hardware specifications or design have been incorporated into the design.

Interface relationships that must exist between the end item and the payload carrier (e.g. ISS, FCF, SpaceHab, Sounding Rocket etc.) have been documented.

Predicted performance of the hardware including reliability has been completed.

Compliance with all requirements including safety and quality requirements.

Controls of safety hazards have been identified and reviewed.

Adequacy of the packaging of all subsystems.

Effectiveness of the design for fabrication and test has been determined.

Fabrication plans and the progress in the identification and acquisition of required special tooling or fixtures is reviewed.

Test plans, including preparation of any special test equipment, and software test plans and procedures are documented.

Document and submit for review the technical, schedule, and cost risks of the proposed experiment in accordance with the Risk Management Plan.

A NASA appointed review board shall assess the status of the project with respect to the above items, recommend whether or not the project should proceed to the flight hardware fabrication, integration, and test phase, identify any concerns that should be addressed, and recommend any actions that should be taken to enhance the success of the next phase of the project.

CDR Minimum Deliverables required:

90% of Drawings

Software Design Document

Software Verification and Validation Plan

Thermal & Structural Analysis

Reliability Analysis

Phase 2 Safety Package with Preliminary Verification Analysis

Baseline System Descripiton document

Science and Engineering Compliance Matrices

Preliminary Data Delivery Plan

Verification Plan

Preliminary Integration Documentation required of the carrier

Engineering Model Test Results

PDR RFA Closeout

GSE Design

Assembly, Integration and Test Plan

### Verification and Test Review

A Verification and Test Review shall be conducted prior to the assembly of the experiment (subassemblies may be assembled).  The overall purpose of the review is to present the overall test plan for the hardware and software and obtain approval of project management to commence environmental and verification testing. The specific purposes of the review are to:

Assess the process in which the science, engineering and safety requirements shall be verified through the testing of the hardware and software. The process shall include the rationale for testing (i.e. testing high risk subsystems before system assembly etc.) and have direct traceability to the science, engineering and safety requirements.

Assess the verification & test plan which shall include test levels (i.e. thermal, vibratory, EMI, and radiation etc.) and test durations (i.e. number of thermal cycles, vibration duration, etc.) of the hardware and software subsystem/systems.  The environmental test plan shall include the expected carrier vibration, EMI/susceptibility, thermal and radiation levels.

Review assembly procedures to assess the link with the test plans.

Assess the risk mitigation plan for compliance with all science, engineering and safety verifications.

Review the definition of the work to be accomplished during verification and environmental testing.  The results of all testing shall be formally reported at the Pre-ship review.

NASA appointed review board shall assess the status of the flight experiment test plan and recommend whether to proceed with the presented test plan or to modify the presented test plan. NASA appointed review board shall also make an independent judgment of the risks involved in any areas, and identify any concerns which would affect the success of the flight experiment.

V&TR  Minimum Deliverables:

Science and Engineering Compliance Matrix

Verification Plan (Science & Engineering)

Software Verification and Validation Plan

Reliability Analysis

Complete Phase 2 Safety Package with Verification Test/Analysis/Inspection Plan

Environmental, Verification and Safety Test Risk Assessment Plan

Assembly, Integration and Test Plan

### Pre-Ship Review

A preship review is a formal review conducted prior to shipment of the flight experiment hardware to the launch site for integration.  The overall purpose of the review is to obtain approval of the Center management that the flight experiment meets all requirements and is ready to be shipped.  Successful completion of this review will be based upon the following success criteria:

The flight worthiness and readiness of the flight experiment hardware and software; ground support hardware and software; and science operations plans will be reviewed.

Results of the verification testing including any specifications that were waived because of non-compliance and any significant modifications made to the flight experiment will be reviewed for completeness and meeting specifications.

All significant non-conformances and functional failures are provided to assess for corrective action and closeout.

The plans are completed and appropriate following shipment of the hardware for integration.

Flight hardware, along with associated GSE and software, is ready to ship to the launch site

NASA appointed review board shall assess the status of the flight experiment and recommend whether or not to ship the flight experiment to the launch site, make an independent judgment of the risks involved in any areas, and identify any concerns which would affect the success of the flight experiment.

PSR Minimum Deliverables:

100% of As-Built Drawings

Thermal & Structural Analysis (final)

Launch Site Operations and Test Procedures (final)

Reliability Analysis (final)

Phase 3 Safety Package with Final Verification Analysis

Software Code

Software Verification and Validation Reports

Baseline System Descripiton document (final)

Science and Engineering Compliance Matrices (final)

Integration Documentation required of the Carrier

Integrated Logistics Support Plan (final), if required by Delivery Order

Integration Data Package that including non-conformances, failure reports, etc.

CDR RFA Closeout

PSR Presentation Package

GSE Drawings

### Flight Readiness Review

A Flight Readiness Review is a formal review conducted after carrier installation, integration and initial checkout.  The overall purpose of the review is to obtain NASA approval and final acceptance of the flight hardware and associated ground support infrastructure.  Successful completion of this review will be based upon the following success criteria:

The readiness of the flight experiment hardware will be reviewed based on the results of initial checkout of the hardware and/or software

Results of the verification (and calibration, if appropriate) testing including any specifications that were waived because of non-compliance and any significant modifications made to the flight configuration will be reviewed for completeness and meeting specifications.

All significant non-conformances and functional failures are provided to assess for corrective action and closeout.