# Attachment A

RFP # ED-07-R-0070

# STATEMENT OF WORK

Technical Assistance for Development of a Training Manual and Parent Activity and Resource Guide to help K-3 Parents with Low Literacy Skills Build Knowledge about Reading

I.  BACKGROUND

The National Institute for Literacy (Institute) was established to ensure that literacy would have a place on the federal policy agenda and to invigorate a national effort to improve adult literacy.  Its primary activities to strengthen literacy across the lifespan are authorized by the U.S. Congress under two laws, the Adult Education and Family Literacy Act (AEFLA) in the Workforce Investment Act and the No Child Left Behind Act (NCLB).  The AEFLA directs the Institute to provide national leadership regarding literacy, coordinate literacy services and policy, and serve as a national resource for adult education and literacy programs. The NCLB law directs the Institute to disseminate information on scientifically based reading research pertaining to children, youth, and adults as well as information about development and implementation of classroom reading programs based on the research.

A significant component of the Institute’s NCLB-authorized dissemination effort has focused on parents with well-developed literacy skills who are accustomed to consulting printed materials for information.  The Institute has printed and distributed millions of copies of Put Reading First:  Helping Your Child Learn to Read and A Child Becomes A Reader through national organizations, parent resource centers, schools, and other intermediary organizations.   While the Institute will continue to disseminate information based on the findings from scientific research to these parents, the Institute is beginning to turn its attention to a different group of parents.

In FY 06-07 {07-08}, the Institute is starting a pilot project that focuses on parents of K-3 children who would benefit from learning more about how to support their children’s acquisition of reading skills but who are not likely to use stand-alone print materials.  These are likely to be hard to reach parents with low literacy skills with low educational attainment. The purpose of this project will be to disseminate information that engages parent-participants in activities that develop their knowledge of how children learn to read and their ability to help their children become successful readers. Parent participants are expected to be active participants for a 3-4 month period, with an average participation rate of 2-6 hours per week.

To aid this project, the Institute seeks technical assistance in developing 2 sets of materials drafted from scientific reading research products produced by the National Institute for Literacy:

1. A Parent Activity and Resource Guide

The parent activity and resource guide will be used to administer the pilot project and will serve as both a guide for the administering staff and a practical resource for the parent participants. The resource and activity guide will be used during the participation sessions to introduce and break down beginning reading concepts and skills thru instruction and hands on activities and to provides activity ideas that the parent can use at home with their child.

2.  A Training Manuel

This training module shall be a companion to the parent activity and resource guide and will be used to train staff who will be working with the parent participants in the pilot program. The training manual serves the purpose of providing background knowledge on scientific reading research, training tips and activity suggestions and ideas to be used during the parent participations sessions. The training manual shall mirror the activity and resource guide in design and format.

The following National Institute for Literacy resources shall be used in the development and design of the training manual and parent activity and resource guide, and can be found the Institute’s website: http://www.nifl.gov/nifl/publications.html

To be used as background knowledge for the development of the training manual and parent activity and resource guide:

The Effect of Family Literacy Interventions On Children's Acquisition of Reading (October 2006) 
A Meta-Analytic Review conducted by Monique Sénéchal
PDF format (297KB), HTML (accessible format)

Report of the National Reading Panel: Teaching Children to Read
www.nationalreadingpanel.org

To be incorporated into the training manual and parent activity and resource guide:

Shining Stars - Kindergartners Learn to Read (October 2006) How Parents Can Help Their Kindergartner Learn to Read PDF format (369KB), HTML (accessible format)

Shining Stars - First Graders Learn to Read (October 2006) 
How Parents Can Help Their First Grader Learn to Read.
PDF format (314KB), HTML (accessible format)

Shining Stars - Second & Third Graders Learn to Read (October 2006) 
How Parents Can Help Their Second & Third Grader Learn to Read.
PDF format (400KB), HTML (accessible format)

Big Dreams - A Family Book About Reading (October 2006) 
PDF format (790KB), HTML (accessible format)

Dad's Playbook: Coaching Kids to Read (September 2006) 
PDF format (705KB), HTML (accessible format)

Put Reading First
Helping Your Child Learn to Read - A Parent Guide
PDF format (835KB), HTML (accessible format)

A Child Becomes a Reader
Proven Ideas for Parents from Research--Kindergarten through Grade Three
PDF format (770KB), HTML (accessible format)

La Lectura es lo Primero
Cómo ayudar a su hijo a aprender a leer
PDF format (230KB), HTML (accessible format)

###### II. Purpose of the Acquisition

To develop and design a training manual and a companion parent resource and activity guide that uses scientific reading research products produced by the National Institute for Literacy, to be used with K-3 parents with low literacy skills in a pilot program that engages parent-participants in activities that develop their knowledge of how children learn to read and their ability to help their children become successful readers.

IV. SCOPE OF WORK

The contractor shall perform the following tasks:

Task 1:  Attend post-award meeting with Institute staff and the product designer

The contractor shall attend a post-award meeting at the Institute’s offices, within 5-7 business days of the contract award to discuss contract tasks and timeline and answer questions. The contractor shall also attend a secondary meeting on the same day at the Institute’s offices with Institute staff and the product designer to discuss initial design and layout of the training manual and parent resource and activity guide.

The contractor shall provide a written summary of the post-award meeting to Institute staff no later than 5 business days after the conclusion of the post award meetings to be submitted via electronic mail.

Task 2:  Recommend K-3 Literacy Experts to provide technical assistance in the development of the training manual and the parent activity and resource guide

  - The Contractor shall recommend to the Institute via email on or before September 21, 2007 three-four experts in the field K-3 literacy and parent education, with knowledge of the literacy information needs of the target audiences.

  - The Contractor shall submit final list of experts to the Institute on or before October 1, 2007.

  - The Contractor shall secure the services of the 2 final approved experts, both of whom will be reviewing the draft text for both the training manual and the parent activity and resource guide.

Task 3: Develop 2 separate outlines for the training manual and parent activity and resource guide

3.1 The contractor shall develop an outline for the training manual.

3.2 The contractor shall develop and outline for the parent activity and resource guide.

3.2 The contractor shall submit the draft outlines via email to the Institute staff for review on or before October 9, 2007.

3.3 The Contractor shall submit revised outlines of the training manual and parent activity and resource guide via email to the Institute staff for approval on or before October 19, 2007.

Task 4:  Draft text for the training manual and parent resource and activity guide

4.1 The contractor shall submit via email the draft of the training manual and the parent activity and resource guide to the two approved experts (Task 2) for review on or before November 16, 2007.

4.2 The contractor shall submit to Institute staff via email a revised first draft of the training manual and parent activity and resource guide based on feedback from the experts to Institute staff on or before December 10, 2007.

4.3 The contractor shall submit via email a final draft of the training manual and parent activity and resource guide to Institute staff for approval on or before December 31, 2007.

V. Schedule of Deliverables

| TASK | DELIVERABLE | DUE DATE |
| --- | --- | --- |
| Task 1 | Post award meeting with Institute staff and product designer | 5-7 business days following contract award date |
| Task 1 | Written summary of meeting | 5 business days following meeting |
| Task 2 | Submit names of 3-4 experts to institute | September 21, 2007 |
| Task 2 | Submit final expert list to Institute staff | October 1, 2007 |
| Task 3 | Submit draft outline of training manual and parent resource and activity guide to Institute staff | October 9, 2007 |
| Task 3 | Submit final draft outline of training manual and parent resource and activity guide to Institute staff | October 19, 2007 |
| Task 4 | Submit draft text of training manual and parent resource and activity guide to Institute staff | December 10, 2007 |
| Task 4 | Submit final draft of text for training manual and parent resource and activity to guide to Institute staff | December 31, 2007 |

VI.	Performance Period

September 15, 2007 –January 18, 2008