NOAA Climate Test Bed                                                Interim Report to the CTB Science Advisory Board (FY07)

_____________________________________________________________________________

March 2007

Executive Summary

A NOAA Climate Test Bed (CTB) Interim Science Meeting was held February 23, 2007 at the NOAA Science Center in Camp Springs, MD.  The meeting was intended to bring together the CTB management and staff and the SAB Chair to review CTB progress on previous SAB recommendations and to begin planning for the 3rd CTB SAB Meeting late this summer.  A related purpose of the meeting was to begin discussion on science issues and alternative solutions for which the CTB will request independent expert advice from the SAB.

The purpose of this report is to provide the SAB with some details on the outcome of the CTB Interim Science Meeting, including the science issues and alternatives and tentative plans for the 3rd CTB SAB meeting.  The CTB will request a formal written response from the SAB on these issues following the 3rd CTB SAB meeting.  The CTB has benefited greatly from previous SAB advice and thanks you in advance for your future efforts.

For reference, the presentations made at the February 23rd Interim Science Meeting are found on the CTB Webpage:

http://www.cpc.ncep.noaa.gov/products/ctb/ctb-meetings.shtml

Relevant background materials, including the CTB Multi-Model Ensemble Strategy “White paper”, and the latest draft of the CTB Science Plan and Implementation Strategy are also found on the CTB Webpage.  Tentative plans for the 3rd CTB SAB meeting are found in Appendix A of this report.

- Introduction

NCEP’s Climate Forecast System (CFS) became operational in August 2004. This combined weather and climate modeling into a single "global modeling" effort  in which model improvements can be applied to both the GFS and CFS concurrently.  NCEP also supported the Climate Test Bed through the Climate Program Office and reallocated  human and computing resources onto the CTB. These efforts have really paid off for both operations and research.  For example, since the establishment of the CTB there has been a string of very good seasonal forecasts, which have raised skill levels well above the target level (Fig. 1).

US Seasonal Temperature Skill

Fig. 1.  US seasonal temperature forecast skill.  Actual skill (blue line) and skill goal (red squares).  Points used to compute the Heidke skill score come from regions that were not assigned the equal chances, “EC”, category.

These skillful forecasts can be attributed, at least in part, to early CTB efforts to  consolidate the CFS with existing statistical forecast tools used in CPC forecast operations. Ongoing efforts to accelerate improvements in the CFS and related tools may improve these forecasts further and maintain new skill levels above current GPRA goals.

Through the CTB transition efforts and related interactions with the larger research community, NCEP is poised to make significant advancements with the next upgrade of the CFS and work this advancement within a Multi Model Ensemble (MME) framework consistent with recent advice of the SAB and the broader climate research community.

In response to these recent successes, and consistent with previous SAB advice, the CTB has adopted the following strategic priorities:

- Accelerate improvements in the NCEP CFS;

- Partner with the community in the MME enterprise;

- Accelerate development and delivery of new and improved climate forecast products for a diverse user community

Details of the CTB strategy and the related science priorities are discussed in the CTB Science Plan & Implementation Strategy and in an MME “White Paper” on the CTB web page at:

http://www.cpc.ncep.noaa.gov/products/ctb/ctb-documentation.shtml

While the CTB has made considerable progress, the CTB can only make this strategy work with full NOAA Climate Program Office (CPO) support for MME, CFS, and related climate forecast product development.   In section 2 we discuss recent CTB progress on these priorities, identify specific gaps / limitations, provide alternative solutions, and pose some specific questions for SAB advice.  These topics will be the focus of the 3rd CTB SAB meeting.  Tentative plans for the 3rd CTB SAB Meeting are found in Appendix A.  The agenda from this Interim Science meeting is found in Appendix B.

- Science Priorities, Gaps, and Alternative Solutions

2.1.  Next implementation of CFS

The NCEP CFS became operational in August 2004.  Currently, there are two fully-coupled (ocean-atmosphere-land) 9-month forecasts made every day.  The present CFS operational system is frozen.

Development work is underway at EMC to improve the CFS and the proposed timeline for the next CFS implementation is as follows:

Oct 2006: 	Testing of the sigma-p version of the GSI scheme for GFS.

Jun 2007: 	Testing of the ESMF version of the CFS coupler and MOM4.

Aug 2007: 	Pilot studies for fully coupled CFS reanalysis with new GFS, GODAS & GLDAS.

Jan 2008:  	Production and Evaluation of CFS Reanalysis for 1979 to 2007 (29 years)

Jul 2008: 	Prepare CFS Retrospective Forecasts (2 initial months: October and April)

Jan 2009: 	Complete CFS Retrospective Forecasts (remaining 10 months)

Nov 2009: 	Compute calibration statistics for CFS daily, monthly and seasonal forecasts.

Prepare CFS Reanalysis & Retrospective Fcst data for public dissemination.

Jan 2010: 	Operational implementation of the next CFS monthly & seasonal forecast suite.

The three main components of the next CFS implementation are:

- Fully coupled Ocean-Atmosphere-Land-Cryosphere Model

- CFS Reanalysis (1979-2007)

- CFS Retrospective Forecasts (1981-2007)

The CFS upgrade will have improved physics, improved horizontal and vertical resolution, improved land modeling (through cross cutting efforts involving NCEP, OHD and the broader research community), improved MOM4 ocean model (in collaboration with GFDL), improved assimilation of ocean, land, ice and atmospheric data, and improved ice modeling in the polar regions.

Though we have made extensive progress towards the next operational implementation of CFS, current budget plans are insufficient to sustain the CFS upgrade schedule given above.  Some specific gaps are

- The coupled CFS reanalysis must be done with existing resources.  Human resources are needed to assimilate radiance data from old satellites (60 of them), and to develop the coupler and 3DVAR system for the new ocean model, etc;

- Computing resources for the CFS reanalysis have not been identified;

- Computing resources for the CFS re-forecasts depend on the availability of the next operational computer in 2008;

- Human resources to generate, diagnose and disseminate the reanalysis and re-forecast datasets are very limited.

A proposed solution to the gaps noted above is for the CTB CFS Testing and Assessment Team to join forces with the EMC CFS Development Team in 2008-2009 to accelerate the CFS reanalysis and re-forecasting efforts for the next implementation of CFS.  In order to carry out this proposal, roughly half of the CTB computing resources would be needed during the 2008-2009 period.  This poses a considerable risk as the CTB anticipates a considerable increase in the number of AO driven competitive projects (and associated requests for computer resources) during FY08 (see section 2.3).  It also comes at a time when MME activities are rapidly spinning up, with their own resource needs (both computing and human).  Because the CTB computer resources are limited, inevitable conflicts will arise, and the CTB must work with the community and the SAB to find an equitable solution.

Because weather and climate modeling are combined into a single "global modeling" effort at NCEP, EMC expects that many modifications to CFS will first be implemented in GFS.  Therefore, the CTB funded external researchers must collaborate with NCEP developers of both GFS and CFS to implement their improvements in future implementations of the CFS.  This might involve running the models both in coupled and uncoupled mode, for both short-term predictions and long-term simulations.

Some specific questions for the SAB are:

- Should the CTB use its computing resources to help NCEP meet its goal for the timing of the next implementation of CFS?

- Should the CTB staff on the CFS Testing and Assessment Team join forces with the EMC CFS Development Team to accelerate CFS reanalysis and re-forecasting efforts required for the next implementation of CFS?

- What is the appropriate balance between AO-driven external projects and internal activities (such as CFS reanalysis and re-forecasting)?  Should this balance be determined by whether a project contributes to the next implementation of CFS as opposed to the implementation that follows the next one?

- What procedures should the CTB use to ensure that its computing facility is equitably shared between external (competitive) and internal projects?

- With reanalysis and re-forecasts, we will be able to determine expected improvements to the skill of objective, model-based forecasts.  How do we measure the economic and social benefit of these improvements?

2.2. Multi-Model Ensemble Prediction System

NCEP, through the CTB, is working with the climate community to develop a strategy for a MME Prediction System at NCEP with CFS included.  Steps toward an operational MME Prediction System at NCEP include :

- Next implementation of CFS;

- Preliminary skill evaluation of International MME (IMME) and National MME (NMME) members;

- Assembly of full re-forecast data sets from IMME and NMME contributors;

- Consolidation of the IMME and NMME members with CFS included into a single operational MME Prediction System;

- Assessment and communication of uncertainty for MME prediction.

Considerable progress on the preliminary skill evaluation of the IMME was reported at the Interim Science meeting (see TPT-MME-Saha-23feb07.ppt) on the CTB Webpage:

http://www.cpc.ncep.noaa.gov/products/ctb/ctb-meetings.shtml

In particular, two studies were conducted using the CFS and European DEMETER data to evaluate the following questions:

- How extensive (long) should hindcasts be?

- Do the NCEP CFS forecasts add skill to the European DEMETER-3 forecasts to produce a viable International Multi Model Ensemble (IMME)?

For question 1 it was shown that CFS improves from extensive hindcasts (21 years was noticeably better than 8) and that it has the most skill of the 4 models considered for the IMME.   For question 2 it was shown that NCEP CFS contributes to the skill of an IMME (relative to DEM3) for equal weights. This was especially the case when the probabilistic Brier Score was used, and for precipitation.  In comparison to ECMWF, METFR and UKMO, the CFS as an individual model did well in deterministic scoring (Anomaly Correlation) for precipitation and very well in probability scoring (Briar Score) for both precipitation and surface temperature over both the US and Europe.

The results of this study were sent to the ECMWF.  The Director showed interest, but wanted his own scientists to carry out a similar evaluation.  Dr. Doblas-Reyes (ECMWF) has downloaded the CFS retrospective data from the CFS server and is in the process of evaluating the IMME, but using the latest EUROSIP data (instead of the DEMETER data).

Progress on the NMME was also reported, though it has been relatively slow.  Hindcast data have been obtained from GFDL for 4 initial months (Apr, May, Oct and Nov).  These data are being postprocessed and transferred to NCEP for evaluation and inclusion in an NMME with the CFS.  Though NCAR is not ready to start their hindcasts, COLA has done a few hindcasts with the NCAR model which show promise.  A full hindcast dataset is required for evaluation of an NMME with the CFS.  NASA is not ready to start their hindcasts.

The MME enterprise carries considerable risk for NCEP.  Some key gaps are:

- Lack of a National Strategy on MME, including insufficient (US) computer resources for generating hindcast data sets;

- Lack of a concept of operations, including MOUs with partners (International and US) for exchanges of operational models and real time forecast data;

- The Europeans may well decide to keep their MME European;

- NCAR and NASA have their own time lines for model development;

- CTB has resource limitations for skill assessments, post-processing, calibration, consolidation, and preparation for operations;

- Operational requirements dictate that there must be additional skill in monthly and seasonal 2-meter temperature and precipitation over the US as the basis of any MME. What happens if none of the NMME models add additional skill to the CFS in these measures? Concentrate on IMME?

Based on the results to date, the CTB MME Team proposes that CTB continue working on both the IMME and the NMME.  In addition to the IMME activities reported above, the CTB has partnered with other countries to develop the IMME, including BMRC, Australia and BCC, China.  However, many of the gaps and limitations noted above are the result of much bigger issues that cannot be resolved by the CTB.

Some specific questions for the SAB are:

- Has the CTB developed an effective MME implementation strategy?

- Should CTB proceed with both IMME and NMME, and in what balance?

- How can CTB influence development of a National Strategy for MME, and climate model development?

- Does the CTB have the appropriate balance between MME and CFS activities?

2.3 Climate Forecast Products and Services

The CTB plays a unique and critical role in NOAA Climate Services.  The CTB collaborates with the R&D community (e.g., ARCs, IRI) to accelerate the transition of new and improved science driven climate forecast and analysis products into operations with emphasis on the CPC specific product range (6-10 day, week 2, monthly, seasonal).  The CTB also collaborates with the applications research community (e.g., RISAs, SARP) for requirements on new and improved demand driven climate products and services.

Three important examples that illustrate how the CTB is fulfilling its role are given below.  First, the CTB has established a program to enhance interactions (partnerships, cooperative research, planning, exchange visits) between CPC and the climate applications science community.  To date the effort has been primarily focused on the cultivation of relationships with the RISAs in order to develop a deeper understanding of decision contexts and needs for climate forecast products, as well as effective means for supporting access to and use of climate forecast information (Table 1).  The basic premise of these interactions is that the development of user-centric climate forecast products would benefit from partnerships of the technology driven efforts of CPC and the stakeholder-driven efforts of interest to the RISAs.  However, these communities have different priorities: CPCs technology-driven projects are often limited in their ability to determine specific user needs; stakeholder-driven projects are often limited in their ability to fully implement sophisticated engineered software projects required for successful transition to sustainable operations.   The challenge for the CTB is to bridge this gap between communities in the development and delivery of user-centric climate forecast products.

Table 1. CTB/CPC - RISA Interactions

RISA		CTB/CPC Liaison	RISA Contact	RISA Visitor to CPC

SECC 		Muthuvel Chelliah 	James Jones		Guillermo Baigorria / 									Shrikant Jagtap (May 07)

PEAC/PaCIS	Luke He 		Eileen Shea

Alaska 	Jon Gottschalck	James Partain

CAP		Kingtse Mo		Dan Cayan

CLIMAS	Ed O’lenic		Holly Hartmann

WWA		Michelle L’Heureux	Andrea Ray

CIG		Douglas LeComte	Dennis Lettenmaier

The CTB program summarized by Table 1 includes exchange visits in which CPC/CTB staff make short visits to the RISAs to provide customized overviews of CPC products.  The RISAs in turn send longer term visitors (up to several months) to CPC to develop customized products off of the NCEP database and the CPC product suite.  These interactions have already led to a number of important new products that would not exist without the CTB, including a concerted effort to convert CPCs monitoring and forecast product suite to GIS format.

Second, the CTB has been working with the NOAA CPO to expand its Competitive Grants Program through Annual Announcements of Opportunity (AO) with priorities that accelerate improvements in NCEP climate forecast models, products and applications.  During FY06 the CTB funded 3 competitive projects aimed at accelerating improvements in the NCEP CFS (section 2.1).  During FY07 the CTB funded 2 competitive projects to enhance CPCs suite of climate forecast products.  These 5 projects are listed in Table 2.  During FY08 the CTB anticipates a somewhat larger AO, with science priorities that include CFS improvements, Multi-Model Ensembles, and drought / NIDIS.  The CTB FY08 Federal Funding Opportunity and Information Sheet is in preparation.

Table 2.  List of current CTB competitive transition projects.

FY06

Using initial tendency errors to reduce systematic errors

(PI: Tim Delsole, COLA; Co-PI: Hualu Pan, EMC)

Neural network emulations of model physics for CFS

(PI: Michael Fox-Rabinovitz, U. MD; Co-PI: Kransapolsky, Suru Saha, EMC)

Ocean component of the NCEP ENSO CFS

(PI: Michael McPhaden, PMEL; Co-PI: Yan Xue, EMC)

FY07

Probabilistic forecasts of extreme events and weather hazards in the US

(PI: Charles Jones (UCSB); NCEP Co-PI: Jon Gottschalck, CPC)

System-wide advancement of user-centric climate forecast products

(PI: Holly Hartmann (UAZ); NCEP Co-PI: Ed O’Lenic (CPC))

The CTB is also providing resources for and actively participating in a number of CPO Climate Prediction Program for the Americas (CPPA) funded projects to support NIDIS:

Finally, CPC is in the midst of a gradual transition to a more objective approach to the climate forecast problem that relies on objective statistical and dynamical forecast tools, consolidation techniques, and objective verification.  Though the forecaster still plays an important role in the forecast process, it is also true that this transition has allowed CPC to redirect more of its resources towards the development and delivery of regionally and sectorally specific climate forecast products and services.  During the past year the CTB has been working with RISA participants to help develop a list of user-centric products that CPC could provide, a so-called RISA “wish list”.   The original “wish list” was compiled by Kelly Redmond and sent from the NOAA RISA program participants to both the SAB and the CTB in June 2006.  Shortly after the 2nd CTB SAB meeting, CTB staff provided an initial response to the “wish list” outlining actions that were deemed relatively painless, moderately difficult, and requiring careful thought, and pledging to move forward on several items.  The CTB has moved forward on those items and will discuss progress with the applications research community during the 5th Climate Prediction Applications Science (CPAS) Workshop, March 20-23, 2007, in Seattle, WA.  The CTB is sending 7 CPC participants to this meeting (Table 1) together with CTB management.  In addition to the Workshop, additional “face-to-face” meetings involving the CPC personnel, CTB management, and RISA participants will be held to discuss progress on and additional refinements of the “wish list”.

Some specific questions for the SAB are:

- Are CTB efforts to link CPC with the research applications community developing appropriately?

- What criteria should the CTB use in developing the list of new user-centric products to be developed and transitioned to operations?

- How should the CTB work with CPC forecast operations to enhance the development and delivery of climate forecast products and services (e.g. balance between objective and forecaster-enhanced forecast products)?

- What should the CTB do to influence the research agenda of the applications research community in the longer term?

- How should CTB measure success (e.g. number of new and improved products, economic impact, social utility, etc.)?

- How do we decide on the proper balance of efforts between improvements to the skill of models and new climate products?

- Should CTB develop a suite of web-based interactive tools that allow users to develop their own decision-oriented products?

- Should CTB develop a real-time attribution system as part of an enhanced overall effort to explain forecasts to users?

- Should CTB work with THORPEX to develop a long-term strategy aimed at improving extended range (6-10 day, week-2) forecasts by enhancing the climate-weather connection?

Appendix A.  Tentative Plans for the 3rd CTB SAB Meeting

Proposed dates for the 3rd CTB Science Advisory Board (SAB) meeting are August 28-29, 2007 at a hotel in the Washington DC area.  These dates are subject to change based on the schedules of the SAB members.  The proposed meeting objectives, expected outcome, and a strawman agenda are given below.  The SAB is invited to revise the tentative meeting plans and to communicate revisions to the CTB Director.

The proposed meeting objectives for the 3rd CTB SAB Meeting are: (i) to review CTB  progress on science priorities and SAB recommendations; and (ii) to obtain independent expert advice on short-term (FY08-FY09) and long-term (next 5 years and beyond) science priorities and implementation strategy.  The Expected Outcome of the 3rd CTB SAB Meeting is a SAB written report with expert advice and recommendations that address the specific questions raised in this report as well as other pertinent issues raised at the 2rd CTB SAB meeting.  Invitations will be extended to the SAB (10), OB (7), CST (13), External PIs (5), and CTB Staff (40).  A venue that accommodates at least 50 people will be chosen.

The science presentations during the 3rd CTB SAB meeting will be focused on the priorities, gaps, alternative solutions and questions raised in section 2 of this report.  We propose that roughly 1 day be devoted to the science presentations, with roughly ½ day for a SAB Executive Session and another ½ day for SAB closed meetings with CTB Team Chairs, the CTB Oversight Board, and Exit Interviews.  A strawman agenda is given on the following page:

Proposed Agenda for 3nd CTB Science Advisory Board Meeting

Hilton Silver Spring

Silver Spring, MD

August 28-29, 2007

Tuesday, August 28, 2007

8:00 a.m. 	SAB Executive Session / Continental Breakfast

9:00 a.m.	Welcome – Louis Uccellini

9:15 a.m.	Introductions, Logistics – Melvyn Gelman

9:30 a.m.	Update on the CTB and Meeting Objectives – Wayne Higgins

9:45 a.m.	Break

10:00 a.m. 	MME Prediction System – Suranjana Saha and MME Team

(How extensive (long) should hindcasts be?; International Multi Model Ensemble

(IMME); National Multi Model Ensemble (NMME); Consolidation ; etc.)

11:30 a.m. 	MME Discussion

12:00 p.m.	Lunch

1:00 p.m.	CFS Testing and Assessment – Jae Schemm, Shrinivas Moorthi and CFS Team

(Next Implementation of CFS, CFS Reanalysis and Re-forecasting, Outcome of

FY07 Experiments, PI Presentations, etc)

2:30 p.m.	CFS Discussion

3:00 p.m.	Break

3:15 p.m.	Climate Forecast Products – Ed O’lenic and Climate Products Team

(CTB/CPC Interactions with RISAs, New developments in CPC Forecast

Operations; Drought Monitoring and Prediction / NIDIS)

4:30 p.m.	Climate Forecast Products Discussion

5:00 p.m.	General Discussion of Science Presentations

6:00 p.m.	Adjourn

Wednesday, August 29, 2007

8:00 a.m. 	SAB Executive Session / Continental Breakfast

9:00 a.m.	CTB Grants Program / Proposed O2R Concept – Ken Mooney

9:30 a.m	Shared Computing Facility – Hualu Pan

9:45 a.m.	Tracking CTB Tasks – Mel Gelman

10:00 a.m.	Break

10:15 a.m.	Future of CTB Teams  –Siegfried Schubert and Hualu Pan

10:30 a.m.	General Discussion of Administrative Presentations

11:00 a.m. 	Discussion with TPT Chairs (Saha, Moorthi, Schemm, O’lenic) and CST

Chair (Schubert) but without CTB Management (closed) – Tony Busalacchi

11:30 a.m.	Discussion with Oversight Board (Koblinsky, Uccellini, Kumar, et al.) – Tony

Busalacchi

12:00 p.m. 	SAB Executive Session (closed) – Working lunch (provided) to draft

responses to CTB questions

2:00 p.m. 	Exit Interview with CTB Management and Oversight Board

3:00 p.m.	End of Meeting

Appendix B.  Agenda for CTB Interim Science Meeting

Agenda for CTB Interim Science Meeting

NOAA Science Center, Room 802

Camp Springs, MD

February 23, 2007

1:00 p.m.	CTB Issues – Wayne Higgins

1:15 p.m.	CTB Progress and Tracking CTB Tasks – Mel Gelman

1:30 p.m	CFS Issues / Limitations / Risks – Hualu Pan

1:45 p.m.	Future Role of the CST and TPTs – Siegfried Schubert

2:00 p.m.	Transition Project Team Reports

Multi-Model Ensembles – Suranajana Saha

CFS Testing and Assessment – Shrinivas Moorthi and Jae Schemm

Climate Forecast Products – Ed O’lenic

3:00 p.m.	Discussion on planning for 3rd CTB SAB Meeting – Wayne Higgins

3:30 p.m.	Adjourn