DATE: 1/25

ATTENDEES: Roy Arnold, Fernando Ayala, Rich Beck, LeRon Bielak, Michael Brown, Betty Buxton, Bill Corrington, Brendon DesPres, Kathryn East-Faushaugh, Angela Herring, Anthony Irish, John Kinley, Joel Lynch, Bob Misch, Carol Moore, Robert Moore, Jessica Rancourt, Chris Richey, Kylie Santini, Raymond Smith, Dot Sugiyama, Ramsay Tanham, Kathy Tynan, Mona Williams, Marlene Walker, Dave Murphy, Kathy Marshall, Quinntella Moore, Debra Burrell, Ralph Sokolowsky, Charlene Raphael, Becky Bageant, Barbara Newman, Daryl Koncer, and Philip Yoo.

ACTION ITEMS

WHAT WHO WHEN Meeting with Leron Bielak, representative from the Ramsay TBD strategic planning office 202 208-5340 to: Compare the strategic planning schedule to GT project plan Review secretary offices, determine which ones should be part of this task (management excellence - CIO and CFO office etc). AOT meeting GT Team 2/9 Set-up meeting with John Kinley and Angela to ensure we Fernando Before 2/3 have the most current ABC information from MMS

DETAILED MINUTES

Topic 1: Introduction from Performance Perspective (Rich Beck)

Benefits/Goals of the Budget, Cost and Performance Integration Initiative: By linking ABC (Costing) and performance (Strategic Planning), we can understand how the work of the Department directly relates to execution of Strategic Plan goals/objectives. Major step toward achieving Budget and Performance Integration (BPI) Ability to identify changes in funding and how they affect performance Even with the PAR it is not apparent how funding affects performance – this task will help DOI do that Linking Budget, Cost and Performance is key to developing concise budget requests tied to performance. This task will also help to strengthen DOI and bureau data validation/verification procedures/processes. Must link work done with what results from work done (Mercator report).

Topic 2: Introduction from ABC Perspective (Dorothy Sugiyama)

Benefits/Goals of the Budget, Cost and Performance Integration Initiative: Additionally, ability to see what it costs to achieve a certain level of effort/targeted level of performance. “What it costs to get a product out the door” Meaningful whole rather than two unassociated methodologies (ABC and Performance Measurement / Budgeting)

Topic 3: Budget, Cost and Performance Integration Presentation (Kathryn East Faushaugh)

Project Goals: Alignment: Assess current bureau alignment to DOI strategic plan end outcomes, measures and cost. Gather pertinent documents that describe current performance management structure Analyze the methodology, form and extent of alignment Synthesize bureau-level results and recommend action If it is linked to the end outcome measures then we will review; this include PART measures Want to account for all resources Integration: develop methodology to integrate AMC and performance measurement and identify gaps/overlaps and/or dependencies Gather pertinent documents and data to support budget and performance integration Analyze the data, cost and bureau funds Synthesize results and develop integration methodology Show funding as it relates to performance Link ABC to performance 2/9/06 AOT meeting Verification: Assess bureau data validation and verification processes. Gather pertinent documents to support performance data verification and validation Analyze data verification and validation process Synthesize results and recommend process improvement This task is a result of KPMG audit findings; need to assess/identify weaknesses before DOI’s next audit. Implementation Strategy: Strategic alignment approach ABC integration approach V&V remediation approach Key steps and action plan Timeline Critical success factors Project deliverables: Bureau performance alignment draft due 2/24/06 Integration methodology draft due 3/24/06 Data validation and verification process draft due 3/31/06 Overall implementation process draft due 4/12/06 What you can expect: Request for bureau information Meetings and workshops as required Tools and templates applied to assess the performance management framework (methodology to assess data sets) Dedicated GT team member for your bureau Draft work products for review Discovery

Topic 4: Question and answer session

Question 1: Will the team be looking at PART measures? Ramsay Tanham: Yes, we will be looking at these. We will take any documents that the bureaus use to report measures and look at how/and if these link to the DOI Strategic Plan. Rich Beck: We also plan on doing a gap analysis at some point in this process to see how much of the agency’s budget is being accommodated in the Strategic Plan etc. Question 2: What documents should (versions) the bureaus provide Grant Thornton with? The ones being proposed or the old ones? Rich Beck: We do not want a moving baseline. Provide the Grant Thornton team with the most current approved documents. Kathy Tynan: requests that the GT team also be provided with documentation of proposed changes. Rich Beck: GT analysis will inform the FY07-FY12 strategic plan update process. Question 3: How/will we look at the work level activities at each bureau? Kathryn East-Fausnaugh: will look at where the bureaus link to the Department. Rich Beck: Bureaus need to show if/how/where these activities link to the DOI Strategic Plan Question 4: Will ABC overhead costs and bureau indirect costs be reviewed during this Task? Dot Sugiyama: No, Management Excellence measures and DOI and bureau Sustain the Organization activities will not be part of this task. Question 5: Will the GT team look at only the formal measures that bureaus collect for the department or also informal bureau level measures? Rich Beck: It depends on the level of these measures. This will be determined on bureau by bureau basis. Bureaus can link and build up their lower level activities but only need to show the linkage to DOI. Question 6: Which offices of the Secretary will be interviewed? Dot Sugiyama: Only offices with robust measures and ABC systems, like OHA and OST.