Ministry of Regional Development Authorities

COAST DEVELOPMENT AUTHORITY

P.O. BOX 1322

MOMBASA

Contact Person

The Managing Director

Tel. +254 41 224406, Fax +254 41 224411

Email address: cda@africaonline.co.ke (Main Office)

cmscsec@africaonline.co.ke (KCMP Office)

Kenya Coastal Management Program (KCMP)

31st December 2003 – 31st December 2006

MONITORING, EVALUATION

AND

REPORTING PLAN

FIRST DRAFT

The KCMP is a partnership between USAID/Kenya and CDA- Kenya under

Development Assistance Grant Agreement No. 615-005

July 2004

PREFACE

The Kenya Coastal Management Program (KCMP) is a partnership between the Coast Development Authority (CDA) and USAID/Kenya. The goal of KCMP is to improve natural coastal resources management in targeted bio-diverse areas by and for the stakeholders in line with the USAID’s Strategic Objective 5 (SO5) and the vision and mission of CDA. The main performance indicators are Land use change in target areas (ha) and the number of stakeholders benefiting from involvement in improved ICM.

The KCMP work plan for the period between July 1, 2004 and June 30, 2005 build on the Year 1 activities with the main focus being:

- To consolidate and strengthen local ICM programs outside of marine protected areas through site-specific initiatives for coastal management activities to demonstrate tangible community benefits of ICM.

- To expand stakeholder capacity and participation in ICM process through capacity building of coastal managers and institutional capacity support to ICAM institutional partners.

- To contribute experience, information and a strong constituency to support and catalyze development of a Coastal Management Policy in Kenya through initiating development of an ICM Policy, conducting of Conferences / Seminars on Coastal Policy issues, and enhancing the ICM advocacy capacity

- To develop Capacity (Organizational Development and Enterprise Development and Natural Resources Management planning) of CBO groups involved in ICM activities.

This Performance Monitoring Plan has been prepared so as to track the impacts of the various site-specific activities. It describes all the indicators to be monitored, the units of measurement, data sources, methodology of data collection, monitoring frequency, responsibility, baseline values and the targets set. A three-tier management structure has been set up to monitor and evaluate the Program. It consists of a Program Steering Committee to provide overall guidance and leadership, Program Management Team responsible for the key operations of the program, and a Program Implementation Team responsible for the direct implementation of the program.

| Name of the Program Leader: | Wainaina Mburu | Date Submitted: | 1st May 2005 |
| --- | --- | --- | --- |
| Role in Program: | Program Officer |  |  |
| Name of Grantee: | Coast Development Authority | KCMP Work-plan: | 2004/05 |

LIST OF ACCRONYMS

| CB | Community Based |
| --- | --- |
| CBNRM | Community Based Natural Resource Management |
| CBO | Community Based Organization |
| CDA | Coast Development Authority |
| CORE | Conservation of Resources through Enterprise |
| CRC | Coastal Resources Centre |
| DCMA | Diani-Chale Management Area |
| DCMC | Diani-Chale Management Committee |
| DCMC | Diani-Chale Management Committee |
| DDC | District Development Committee |
| EEZ | Exclusive Economic Zone |
| EIA | Environmental Impact Assessment |
| FAO FD | Food and Agriculture Organization Forest Department |
| FiD | Fisheries Department |
| FORREMS | Forest Rangeland Rehabilitation Environment & Management Strengthening |
| GIS | Geographical Information System |
| ICAM | Integrated Coastal Area Management |
| ICM | Integrated Coastal Management |
| INRM | Integrated Natural Resource Management |
| IR | Intermediate Result |
| IUCN | World Conservation Union |
| IWRM | Integrated Water Resources Management |
| JKPB | Jomo Kenyatta Public Beach |
| JKPBSHG | Jomo Kenyatta Public Beach Self Help Group |
| KAHC | Kenya Association of Hotel-keepers and Caterers |
| KCMI | Kenya Coastal Management Initiative |
| KCMP KEFRI | Kenya Coastal Management Program Kenya Forestry Research Institute |
| KMF | Kenya Marine Forum |
| KMFRI | Kenya Marine and Fisheries Research Institute |
| KWS | Kenya Wildlife Service |
| LMMA | Locally Managed Marine Areas |
| LUP | Land Use Planning |
| M & E | Monitoring and Evaluation |
| MCM | Municipal Council of Mombasa |
| MoU | Memorandum of Understanding |
| NEMA | National Environment Management Authority |
| NGO | Non-Governmental Organisation |
| NMK | National Museums of Kenya |
| NRM | Natural Resources Management |
| OCA | Organizational Capacity Assessment |
| PMP | Performance Monitoring Plan |
| PRA | Participatory Rural Appraisal |
| SO5 | Strategic Objective 5 |
| TD | Tourism Department |
| TOR | Terms of Reference |
| TTF | Tourism Trust Fund |
| UNDP | United Nations Development Program |
| UNEP | United Nations Environment Program |
| URI | University of Rhode Island |
| USAID | United States Agency for International Development |
| WRM | Water Resources Management |
| WSS WORTH | Water Supply and Sanitation |

TABLE OF CONTENTS

1.0	INTRODUCTION	1

1.1	Kenya Coastal Management Program	1

1.2	Vision and Mission	1

1.3	Coast Development Authority	1

1.4	Purpose of the Monitoring, Evaluation and Reporting Plan	2

1.5	Audience Analysis	3

1.6	Monitoring and Evaluation Questions	4

2.0	RESULTS FRAMEWORK	5

2.1	Results Framework Hypothesis	5

2.2	Framework and other Frameworks	7

3.0	IMPLEMENTATION PLAN	8

4.0	INDICATOR INFORMATION & REFERENCE SHEETS	8

5.0	DATA QUALITY PLAN	45

6.0	INDICATOR MEASUREMENT TOOLS	45

7.0	MONITORING TOOLS	45

8.0	EVALUATION PLAN	46

9.0	REPORTING PLAN	50

APPENDIX B: KCMP ORGANIZATIONAL CHART	ii

APPENDIX C: INTEGRATED COASTAL AREA MANAGEMENT (ICAM) INSTITUTIONAL MEMBERS	iii

Table 2: KCMP  Year 2 Links to USAID SO5 Results Framework, Performance Monitoring Plan (PMP) Indicators	7

INTRODUCTION

Kenya Coastal Management Program

Kenya Coastal Management Program (KCMP) is a partnership between Coast Development Authority (CDA) and United States Agency for International Development (USAID) in Kenya. The Partnership is founded on an assessment of CDA’s Integrated Coastal Management (ICAM) activities by USAID conducted in the Year 2003 that determined that these activities contribute to the objectives of USAID’s Improved Natural Resources Management Program.

Vision and Mission

The KCMP goal is to “improve natural coastal resources management in targeted bio-diverse areas by and for stakeholders.” This clearly supports CDA’s core functions and strategic development objectives and is in line with the USAID’s Strategic Objective 5 that seeks to improve natural resources management in targeted biodiverse areas by and for stakeholders. The Program seeks to:

- Consolidate and strengthen local ICM programs outside of marine protected areas so that tangible community benefits of ICM are demonstrated

- Expand stakeholder capacity and participation in ICM processes, and

- Contribute experience, information and a strong constituency to support and catalyze the on-going national environmental dialogue in Kenya

Major program activities are issue driven. Issues are identified through a consensus building process where the majority of the stakeholders participate. Short and long term actions and plans are similarly developed to address the issues.

In line with its mandate, CDA works with all institutional members or partners who have either a comparative advantage on particular issues or the legal mandate to perform the same. Institutional members of the ICAM secretariat listed in Appendix E are directly involved.

Coast Development Authority

Coast Development Authority (CDA) is one of the six Regional Development Authorities in the Republic of Kenya. It was established by an Act of Parliament No. 20 of 1990 (Cap 449) to provide integrated development planning, coordination and implementation of projects and programs within its area of jurisdiction namely: the Coast Province, Ijara district of North Eastern Province and the Kenyan Exclusive Economic Zone (EEZ).

The Act mandates the Authority to initiate, plan, coordinate and facilitate development programs and projects within its area of jurisdiction that contribute to poverty reduction and rapid sustainable regional economic growth. The Authority's vision is to attain the level of sustainable utilization of the unique coastal resources for increased food production, employment and wealth creation in the communities of the jurisdicted area.  This vision has to be achieved through CDA’s mission, which is exploitation and development of the unique coastal resources for the benefit of the communities in the area and Kenya in general.

To be more focused in its activities, the Authority has identified the following core functions to minimize overlap with functions of other line ministries:

- Regional data identification, collection, collation and correlation for integrated regional planning purposes.

- Integrated Regional Planning for sustainable utilization and management of coastal resources, based on environmental carrying capacity.

- Development of local capacities to sustain the continuation and maintenance of integrated communal projects through sensitization and training.

- Initiation, Harmonization, and Coordination of sectoral and community interests in the implementation of regional socio-economic development projects.

- Exploration, Promotion, and Conservation (including surveillance) of Marine resources within Exclusive Economic Zone and other coastal resources for sustainable development.

- Sourcing for Innovations and Research findings for implementation of pilot/ demonstration projects for the purpose of dissemination of the technology.

- Promotion of Private Sector involvement in commercial activities and community development within its area of jurisdiction.

- Monitoring and Evaluation of regional development projects and programs for effective achievement of the set objectives.

CDA has identified the following strategic development objectives to be pursued during the plan period 2003 to 2008:

- To contribute to food self-sufficiency in the region by reducing current food deficit by 20%.

- To reduce high incidence of absolute poverty in the region by 10%.

- To reduce high rate of unemployment in the region by about 9% (from 23% to national rate of 14.6%).

- To conserve and manage the environment for sustainable development.

- To improve socio-economic well-being (water, education, health etc) of the communities in CDA’s area of jurisdiction.

- To develop and sustain institutional capacity of CDA.

- To strengthen CDA’s financial base for self-sustainability.

Purpose of the Monitoring, Evaluation and Reporting Plan

The Monitoring, Evaluation and Reporting Plan (MER) has been designed with the following specific objectives in mind:

- Structure for Monitoring and Evaluation

- Clear performance indicators

- Focused reporting system for all the partners

- Reporting system understood by beneficiaries

- Reporting system for KCMP

- Effective monitoring system

- Simple indicators and targets for monitoring and evaluation

- A clear performance monitoring plan

Audience Analysis

| Internal Audience who need information about the progress and results / performance | Information they need | Why they need the information |
| --- | --- | --- |
| Board of Director | Activity Reports |  |
|  | Annual Reports |  |
|  | Financial Reports |  |
| Community Leaders | Activity Reports |  |
|  | Financial Reports |  |
|  | Annual Reports |  |
| Program Directors and Managers | Monthly Reports |  |
|  | Quarterly Reports |  |
|  | Monthly E-Mail updates |  |
|  | Final Performance Reports |  |
|  | Financial, Audit and Close out Reports |  |
| ICAM Partners | Annual Reports |  |
|  | End of Project Report |  |

| External Audience who need information about the progress and results / performance | Information they need | Why they need the information |
| --- | --- | --- |
| USAID | Financial Report Quarterly Report |  |
|  | Bi-annual Progress Report |  |
|  | Annual Report |  |
|  | Mid- Assessment |  |
| Parent Ministries | Budget Estimates |  |
|  | Annual Workplans |  |
|  | Annual Reports |  |
| Politicians | Casual Contacts |  |
|  | Newsletters (Quarterly) |  |
|  | Activity Briefings |  |
|  | Fact Sheets (Quarterly) |  |
|  | DDC Presentations |  |
| Communities | Meetings / Barazas |  |
|  | Activity Inception Meetings |  |
|  | Progress Meetings |  |
|  | Commissioning forums |  |
| Others NGOs | Meetings |  |
|  | Newsletters |  |
|  | Stakeholders |  |
|  | Meetings |  |
|  | Other forums |  |

Monitoring and Evaluation Questions

| What components of the program do we want to learn more about or evaluate | What exact questions do we want to answer or want evaluated / explored |
| --- | --- |
| ICM Initiatives | How many of the planned structures are complete & at what level? Reasons for completion / incompleteness? What is the level of stakeholder involvement? Is there sense of ownership? Which infrastructure development initiatives worked better and why? |
|  | What resources are targeted? Where are the resources located? Who & how many are participating/involved-technical, stakeholders-? How many planning sessions held? What is the KCMP contribution? What is the beneficiary’s contribution? Which are the success stories? Have the ICM plans been adopted, implemented and replicated? |
|  | Which interventions have been put in place to promote resource utilization? How successful are the interventions? How are the stakeholders utilizing the resources? Are there any success stories? Are there safeguards to ensure sustainable utilization of resources? |
|  | How many stakeholders are aware of ICM? Are the stakeholders using ICM in their activities? How much resources are spent on creating awareness on ICM? What media covered ICM activities? |
| ICM Policy | What were the policy issues identified? How were the issues identified? How far did we go in having the issues addressed? What role did communities play in advocating for policy change? How far did we go in the policy process and why? To what extent were grassroots/local institutions involved in the policy process? What role did the national office play in the process? What level of financial resources were allocated to policy development? |
| Capacity Building | How were the capacity building needs identified? What areas of capacity building needs were identified? To what extent were target institutions/CBOs involved in the process? What kind of capacity building processes and inputs (funds included) were provided? How effective were the capacity building processes, inputs and methods provided/used? Have the training needs of program officers been identified and met? |
| Program Management | Are we meeting the program targets in time? How are partners involved in planning and implementation? Are the resources allocated adequate and timely? How committed are the partners and are they motivated? Are there program time over runs? |

RESULTS FRAMEWORK

Results Framework Hypothesis

The KCMP Results Chain and Indicators could be depicted as follows:

| Inputs / Processes (Results relating to provision of resources and processes): |
| --- |
| RESULTS SOUGHT Funding for programs, facilities and materials provided. Training / mentoring for key stakeholders and service providers funded. Staff hired and organizational structures in place. Needs identified. Community mobilization conducted. Provision of participatory planning services/support. Stakeholder / constituency groups established. MOUs and partnerships established. Networks established. Key information / best practices / lessons identified and/or disseminated (including indigenous traditional knowledge). Investment funds/ capital leveraged. Advocacy or communication materials and messages developed. Facilities / Infra-structure installed. Water quality and shoreline monitoring conducted. Secure land title/leases. Safety & security (patrols, communication...) improved. Resources mapped. Conduct coastal related adaptive research (forestry/mangroves, fisheries, social…). Consolidation of information that is key for decsionmaking. Leading to…( | INDICATORS SELECTED: Number of trainings/workshops/key meetings held, by type. Number of new CBOs formed to participate in ICM. Number of partners actively involved in ICM process. Amount of funding leveraged ($). Number of infrastructures installed, by type Number of new data sets available. Number of titles/leases issued. Number of violations reported by type (secondary data). |
| Outputs (Results relating to short term change effects and results sought): |
| Increased knowledge and skills of stakeholders in integrated coastal resource management and and/or policy needs. Improved access to key information by local decision-makers / stakeholders. Increased stakeholder access to integrated coastal resource management tools and technologies. Improved organizational capacity developed (knowledge, skills and systems) within targeted CBOs (involved in planning, mgmt or advocacy of ICM processes). Increased capacity to develop policies / legislation. Strengthen the business capacity (including financial leveraging capabilities) of targeted CBOs involved in coastal friendly enterprises and increase access to markets. Increased stakeholder access to key resources. | Number of people trained by type of training. Number of stakeholders demanding ICM related services. Number of reports disseminated to local decision-makers Number of conservation tools and technologies in use by targeted stakeholders Organizational capacity of targeted constituency groups (Org development index) Level of capacity of selected CBOs in policy formulation and advocacy Business capacity (Enterprise Index) Number of management agreements being implemented. Incidence of stakeholder newly access resources (anecdotal) Infra-structure put in place (input) |

| Outcomes (Results relating to intermediate change and effects sought): |
| --- |
| Replication of improved models (site specific initiatives) of integrated coastal resource management (in partnership with public and private sector). Improved coastal management planning and decision-making (incorporating related inland and offshore effects). Increased benefits to communities from coast friendly natural resource related enterprises / activities. Increased action / advocacy by an enlarged constituency for improved coastal management. Coastal polices drafted and or policies changed (encompassing related inland and offshore effects). | Number of ICM initiatives successfully implemented in target areas. Number of ICM plans implemented. Incidence of use of ICM information provided among stakeholders for decision making (anecdotal information). Number of stakeholders benefiting (by type of benefit) from involvement in improved ICM. Financial benefits (wages and revenue) to communities from nature focused businesses Number of CBOs actively participating in coastal and marine policy dialogue by type of participation (i.e. advocacy campaigns, meeting participation...) (See also Level of policy / legislation advancement) Operational level of legislative and policy functions within selected institutions. |
| Impacts (Results relating to long term change and effects sought): |
| Improved conservation & management of coastal and marine natural resources in Kenya. Policy enacted and implemented in favor of integrated coastal management.. | Number of hectares (coastal and marine) under improved conservation or management. Level of policy / legislation advancement |

Framework and other Frameworks

Table 2: KCMP  Year 2 Links to USAID SO5 Results Framework, Performance Monitoring Plan (PMP) Indicators

| SO5 Statement: Improved natural resources management in targeted biodiverse areas by and for stakeholders | KCMP Goal: Improving natural coastal resources management in targeted biodiverse areas by and for stakeholders |
| --- | --- |
| SO5 Intermediate Results (IR) | KCMP Intermediate Results (IR) |
| Indicator#1: Land use change in target areas (ha) | Indicator #1: Land use change in target areas (ha) |
| Indicator #2: Number of stakeholders benefiting from involvement in improved NRM | Indicator #2 : Number of stakeholders benefiting from involvement in improved ICM |
| IR5.1 – Site Specific Initiatives For NRM Implemented Outside Protected Areas Indicator #3: Number of NRM initiatives successfully implemented in target areas | KCMP IR5.1 –Models for Integrated Coastal Resource Management in Partnership with Public & Private Stakeholders Implemented Indicator #3: Number of ICM initiatives successfully implemented in target areas |
| IR5.1.1 – Appropriate NRM Tools and Technologies Adopted Indicator #4: Number of conservation tools/technologies in use by targeted stakeholders | KCMP IR5.1.1 – Appropriate tools and technology for ICM adopted by Public & private stakeholders Indicator #4: Number of conservation tools/technologies in use by targeted stakeholders |
| IR5.1.2 – Integrated Community NRM Plans Established Indicator #5: Number of integrated NRM plans implemented | KCMP IR5.1.2 – Integrated development plans for 3 ICM sites implemented Indicator #5: Number of ICM plans implemented |
| IR5.1.3 – Improved Local Decision-Making Based on Monitoring and Analysis Indicator #6: Functionality of databases available to targeted local decision-makers | KCMP IR5.1.3 – Improved Coastal Management decision-making based on improved disseminated information Indicator #6: Number of local decisions made based on monitoring and analysis |
| IR5.1.4 – Nature-Focused Business Practices Improved Indicator #7: Financial benefits to communities from nature-focused businesses | KCMP IR5.1.4 – Small and micro nature-focused business practices improved Indicator #7: Financial benefits to communities from nature-focused businesses |
| IR5.1.5 – Awareness of Incentives For NRM Increased Indicator #8: Stakeholder awareness of incentives for NRM | KCMP IR5.1.5 – Awareness of incentives for ICM increased Indicator #8: Number of stakeholder aware of incentives for ICM |
| IR5.4 – Environmental policy and legislative reform advanced Indicator #12: Selected environmental policies and legislations advanced | KCMP IR5.4 – Advocacy for Integrated Coastal Management Policy Advanced Indicator #12: Integrated Coastal Management Policy advocacy advanced |
| IR5.4.2 – Constituencies to support improved NRM strengthened Indicator #13: Organizational development index of targeted CBOs | KCMP IR5.4.2 – Constituencies for ICM Advocacy established Indicator #13: Organizational Capacity of targeted constituency groups |

IMPLEMENTATION PLAN

See the KCMP Detailed Matrix for the KCMP Year 2 Work-Plan

INDICATOR INFORMATION & REFERENCE SHEETS

Indicator Reference Sheet: Indicator #1

| Performance Indicator Reference Sheet #1 |
| --- |
| Indicator: Number of hectares (coastal and marine) under improved conservation or management. |
| Description |
| Precise Definition: Hectares of Coastal and marine area put in positive use. There can be change towards positive or negative use. Target areas are currently defined as Nyali Bamburi Shanzu area, Diani Chale and Shimoni Vanga. Positive use of the area is defined as area which is purposefully dedicated to improved Coastal Resources Management (CRM) or open space placed under site-specific conservation programs or CRM plans (and is not a National Park or Reserve) through formal agreements and actions. Negative land use is defined as land dedicated for non-conservation purposes and thus unavailable for improved CRM (settlements, agricultural plantations, industries, mining, dynamite fishing, etc). Unit of Measure: Hectares Disaggregated by: Type of positive land classified by three program CRM regimes (Coastal and Marine management: Fisheries Management, Community management and Coastal forestry and mangroves management) |
| Plan for Data Acquisition by KCMP |
| Data Collection Method: Meeting with partners and site visits. Data Source(s): Focal area base maps provided by KCMP partners (CDA, KWS, Fisheries Department KEFRI, KMFRI, PACT Kenya, Forest Department, Tourism Department, NMK) and CBOs records. Timing / Frequency of Data Collection: Monthly/Annually. Est. Cost of Collection: Minimal as the information may be with the partners. But could rise if GIS maps were to be prepared. Responsible individual(s):KCMP partners |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare Coastal and Marine area uses targets for positive use to actual performance. Review trends over time. Reporting of Data: This indicator may be appropriate for inclusion in the PSC. Internal and External Audiences. |
| Data Quality Issues |
| Known Data Limitations and Significance (if any): 1) Current collection methods are based on KCMP partners team knowledge and have not been verified through remote sensing techniques and thus current measures are considered rough estimates. 2) Data is collected at the site specific areas and small changes in other Coastal and Marine areas use patterns may not be identified. 3) Responsibility for promoting positive Coastal and Marine area use change is broader than the KCMP program and must be shared by a combination of other relevant government agencies and NGOs. 4) This indicator only tracks change occurring in the designated target areas, and does not account for displacement of negative Coastal and Marine area uses from target areas to other areas. If this were to occur it would not be captured through this exercise. Actions Taken / Planned to Address Data Limitations: 1) GIS maps to be prepared. 2) Title Deeds/agreements/ leases to be acquired where appropriate. |
| Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | NA |  |
| 12 2005 | 10 |  |  |
| 12 2006 | 25 |  |  |
| THIS SHEET LAST UPDATED ON |

Data collection form

| Site | Type of Regime | Number of hectares | Source |
| --- | --- | --- | --- |

Indicator Reference Sheet: Indicator #2

| Performance Indicator Reference Sheet #2 |
| --- |
| Indicator: Number of Stakeholders Benefiting (by type of benefit) from involvement in improved ICM. |
| Description |
| Precise Definition: Number of stakeholders directly or indirectly benefiting from improved NRM through involvement in ICM initiative.. Stakeholders are defined as individuals involved in SO5 programs. Stakeholders are classified in two categories: (1) Stakeholders Directly Involved and Benefiting (individuals who receive funding, training, technical assistance, commodity/infrastructure support, resource access or financial returns from SO5 programs); and (2) Stakeholders Indirectly Involved and Benefiting (individuals who do not personally receive funding, training, technical or commodity/infrastructure assistance but still receive a benefit from SO5 programs. For example, a registered member of a CBO benefits if the capacity of the CBO leadership to effectively govern and manage funds is improved). Improved NRM is defined as reversing, halting or reducing the rate of unsustainable use of the natural resource base through an integrated management approach. Unit of Measure: Number of Individuals. Disaggregated by: Level of benefit (by type of benefit) (direct/indirect); Directly benefited stakeholders will be disaggregated by gender. |
| Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners. Data Source(s): KCMP implementing partners Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Negligible. Responsible individual(s): KCMP program coordinator |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting gets to actual performance. Review trends over time. Analyze type of benefit and ratio of stakeholders in direct versus indirect classifications (it would be a notable result if programs were able to move stakeholders from an indirect classification to a direct beneficiary’s classification. Discuss gender and disadvantaged groups involvement data in terms of culture, access to resources and decision-making relating to coastal & marine resource management. Report on stakeholder involvement per geographic region (ICM Areas) as relevant. |
| Data Quality Issues |
| Initial Data Quality Assessment: Known Data Limitations and Significance (if any): CBO registration of membership may not be current and usually only counts 1 person per household where benefits may touch all household members. Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: Rough Baseline data will be available in 2003 to set initial targets, but targets should be finalized once all SO5 programs are online. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Date collection form 2(a) Direct stakeholders by CBO

| Data Collector: | Date: |
| --- | --- |
| CBO Name: | Location |  |
| Individuals by name | Type of intervention/benefit | Male | Female | Comments: |

Data collection form 2(b) List of stakeholders by CBO

| Name of CBO | Number of Members | Number of Direct benefiaciries by gender | Number of Indirect beneficiaries by gender |
| --- | --- | --- | --- |

Indicator Reference Sheet: Indicator #3

| Performance Indicator Reference Sheet #3 |
| --- |
| Indicator: Number of ICM initiatives successfully implemented in target areas. |
| Purpose |
| In each of the target areas, specific CRM initiatives (mechanisms) will be implemented which support local stakeholders in their efforts to improve management of their community’s natural resources. These initiatives are expected to result in changing community and individual behaviors in favor of conservation and sustainable natural resource utilization practices. |
| Description |
| Precise Definition: Cumulative number of CRM initiatives successfully undertaken in targeted areas. A CRM Initiative is defined as a project undertaken by local communities to improve natural resource management and promote conservation and sustainable natural resource utilization practices [or more precisely a site-specific application of a conservation tool/technology (or a number of those tools or technologies)]. For example, creation of a conservation trust, incorporation of a nature focused business, Spin-off Enterprise Development, Coastal and Marine area set aside for ecotourism or wildlife, Nature focused enterprise development, Forum/network creation, Woodlots and Plantations, Product Development; Domestication of plant and animal species etc, are considered initiatives. A community is determined to have successfully implemented an initiative once they can produce a tangible sign of action and commitment, such as incorporation of a nature focused business, a signed MOU or letter of intent, a written action plan, established written operating procedures, etc. Target areas are currently defined as Nyali-Bamburi-Shanzu, Diani-Chale and Shimoni-Vanga areas. Unit of Measure: Cumulative Number of Initiatives Implemented Disaggregated by: By resources type |
| Plan for Data Collection |
| Data Collection Method: Meetings with partners and site visits. Data Source(s): KCMP partners (CDA, KWS, Fisheries Department KEFRI, KMFRI, PACT Kenya, Forest Department, Tourism Department, NMK) and CBOs records. Timing / Frequency of Data Collection: Monthly/annually. Est. Cost of Collection: Negligible as implementation officers will collect the data during their normal field trips. Responsible individual/s: KCMP partners |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Discuss disadvantaged group involvement data in terms of culture and decision-making relating to CRM. Report on stakeholder involvement per site specific area. Discuss results in conjunction with indicator #4 Conservation Tools/Technologies. |
| Data Quality Issues |
| Initial Data Quality Assessment: To be conducted ----. Known Data Limitations and Significance (if any): To be determined Actions Taken / Planned to Address Data Limitations: ------. |
| Performance Data Table |
| Notes on Baseline and Targets: ----- |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form

| Site | Type of ICM Initiative | Number of Initiatives | Source |
| --- | --- | --- | --- |

Indicator Reference sheet: Indicator #4

| Performance Indicator Reference Sheet #4 |
| --- |
| Indicator: Number of Conservation Tools/Technologies in Use by Targeted Stakeholders. |
| Description |
| Precise Definition: Cumulative number of conservation tools / technologies in use by targeted stakeholders. A conservation tool or technology is a device or application of science that facilitates conservation or sustainable utilization practices of natural resources. Conservation tools to be counted include: 1) Buffer zones; 2) Land Trusts; 3) Focused commodity support; 4) Farm forestry technologies; 5) Monitoring & evaluation systems and databases; 6) Conservation leases; 7) CRM Planning (Forest, Wildlife Parks, Marine Protected Areas, Locally managed marine areas etc; 8) Strategic planning; 9) Organizational capacity development tools and skills; and 10) Water harvesting and management, 11) Easements etc. Use means taken, implemented, or followed. Stakeholders are local community members/individuals and GoK in the target area. Target areas are currently defined as the KCMP site specific areas. Unit of Measure: Cumulative number of tools / technologies in use. Disaggregated by: -Resource type |
| Plan for Data Collection |
| Data Collection Method: Meeting with partners and site visits. Data Source(s): KCMP partners (CDA, KWS, Fisheries Department KEFRI, KMFRI, PACT Kenya, Forest Department, Tourism Department, NMK) and CBOs records. Timing / Frequency of Data Collection: Monthly/Annual. Est. Cost of Collection: Negligible as implementation officers will collect the data during their normal field trips. Responsible individual(s): KCMP partners. |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Discuss disadvantaged group involvement data in terms of culture and decision making relating to CRM. Report on stakeholder adoption as per site specific areas. Discuss role of innovation in promoting improved CRM. Discuss results in conjunction with indicator #3. |
| E. Data Quality Issues |
| Initial Data Quality Assessment: To be conducted -----. Known Data Limitations and Significance (if any): Care should be taken that implementing partners are reporting the number of tools in use and not the number of groups using a tool. The purpose of this indicator is to track the increase in the number of tools available to stakeholders in the “toolkits” they are using to improve CRM. Actions Taken / Planned to Address Data Limitations: There will be need to review data carefully from each source to ensure they have comparable data sets. |
| F. Performance Data Table |
| Notes on Baseline and Targets: ---- |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data Collection Form

| Site | Type of conservation Tool/technology in use | Number of tools/technologies | Source |
| --- | --- | --- | --- |

Indicator Reference Sheet: Indicator # 5

| Performance Indicator Reference Sheet #5 |
| --- |
| Indicator: Number of ICM plans implemented. |
| Description |
| Precise Definition: Cumulative number of ICM plans implemented in target areas (based on model plans). An ICM plan identifies the range of ways a community needs to use their natural resources and establishes sustainable methods for conserving and utilizing those resources over time. Implemented is defined on two levels: 1- Initiated: Partnerships and/or agreements to undertake ICM planning established. 2-Operational: Plan finalized and actions taken in the field. Target areas are currently defined as Mombasa North (Nyali-Bamburi-Shanzu) and South Coast (Diani –Chale and Shimoni Vanga). Unit of Measure: Cumulative number of ICM Plans Implemented Disaggregated by: Type of Plan |
| Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners and/or certificates of completion Data Source(s): ICM partners, ICM Secretariat Timing / Frequency of Data Collection: Annual. Es. Cost of Collection: Negligible Responsible individual(s): Wainaina Mburu |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Review progression of plan implementation from initiated to operational. |
| Data Quality Issues |
| Initial Data Quality Assessment: Conducted 03/04. Known Data Limitations and Significance (if any): --- Actions Taken / Planned to Address Data Limitations: --- |
| Performance Data Table |
| Notes on Baseline and Targets: Prior to 2001/2002 some facilities and infrastructure had been developed in both sites – North and South Coast but were dilapidated and not based on any ICM plans |
| Other |
| Comments: Initial KCMP activities focused on development of model plans for the two sites and their implementation |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |
| 2004/2005 | 3 | 1 | Activities on 1 sites on-going |

ICM Plans Data Sheet

| Enumerator’s Name: __________________________ | Date Filled ______________________________ |
| --- | --- |
| Site | Type of ICM Plan | Level of Implementation Initiated: Partnerships and/or agreements to undertake ICM planning established Operational: Plan finalized and actions taken in the field |
| JKPB |  |  |  |
| Diani-Chale |  |  |  |
| Shimoni-Vanga |  |  |  |

Indicator Reference Sheet: Indicator #6 and #7

| Performance Indicator Reference Sheet #6 |
| --- |
| Indicator: #6. Incidence of use of ICM information provided among stakeholders for decision making (anecdotal information). #7. Incidence of stakeholder newly accessing resources (anecdotal). |
| Description |
| Precise Definition: Indicator refers to frequency of use of ICM information generated by partners for decision making. ICM information include research findings and recommendations from KCMP program activities Stakeholders include local decision makers, ICM partners, Gok departments, legislators managers, researchers, CBOs e.t.c Stakeholders Newly accessing resources refers to the number of emerging users/uses of coastal & marine resources. Unit of Measure: Number(s) Disaggregated by: Type of use/gender |
| Plan for Data Collection |
| Data Collection Method: Recorded incidence data sheets Data Source(s): KCMP partners Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Negligible. Responsible individual(s): |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting:. Review of information from Incidence narrative reports.. |
| Data Quality Issues |
| Initial Data Quality Assessment: Known Data Limitations and Significance (if any): Nil Actions Taken / Planned to Address Data Limitations: |
| Performance Data Table |
| Notes on Baseline and Targets: |
| Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 6 – Incidences of stakeholders accessing ICM information

| Data collector: | Date: Location: |
| --- | --- |
| Incident: |  |
| Comments: |

Data collection form 7 – Incidences of stakeholders newly accessing resources.

| Data collector: | Date: Location: |
| --- | --- |
| Incident: |  |
| Comments: |

Indicator Reference Sheet: Indicator #9

| Performance Indicator Reference Sheet #7 |
| --- |
| Indicator: Financial Benefits to Communities from Nature-Focused Businesses |
| Description |
| Precise Definition: Financial benefits are monetary returns received by local communities from nature-focused businesses. Social benefits are also identified and explained in the narrative. Businesses are those nature-linked enterprises targeted under the SO5 program in the SO5 focal areas (Laikipia-Samburu, Greater Amboseli, South Coast up to Malindi, Taita-Taveta, Mt. Kenya and Greater Maasai Mara). Improved means the business had economic benefits greater than their baseline score. Unit of Measure: Cumulative value of community financial business from nature-focused businesses in Kenya Shillings Disaggregated by: NA, although discussion of financial distribution by gender to be included in the narrative |
| Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners Data Source(s): Pact Kenya Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Staff time, travel, per diems and oversight costs. Responsible individual(s): Irene Gathinji |
| Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Discuss target group involvement data in terms of socio-economics (employment, wages, incomes, group membership), culture and decision-making relating to NRM. Report on social benefits in narrative form, as they are as important as financial benefits. . |
| Data Quality Issues |
| Known Data Limitations and Significance (if any): Under reporting on incomes and revenues Actions Taken / Planned to Address Data Limitations: Use proxies for measurement such as estimated expenditure |
| Performance Data Table |
| Notes on Baseline and Targets: Baseline data will be available in 2005. |
| Other |
| Comments: Most of the nature based enterprises are individual based hence difficulties in estimating overall group incomes |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |
| 2002-2005 | 0.5 million US $ | -- | Actual benefits to be provided by June 2005 |

Enterprise M&E Data Sheet

Completed By: …………………………………………..                  Date: ……………….

Reporting Period:……………………………………….

| Enterprise and Year Established/Registered | Employment Generated |
| --- | --- |
|  | Employment/Job/Position /Title | Number of Days Worked | Annual Income Earned |
| Enterprise Name: |  |  |  |
| Year of Establishment: |  |  |  |

| Revenue/ Income Earned and its Uses (Kshs) During the Last Full Year - |
| --- |
| Annual Income/ Revenue | Operating Expenses | Surplus/ Losses | Amount Reinvested | Purpose for Reinvestment | Dividends Distributed | Number of Shareholders Paid Dividends | Community Project Financed | Amount Given to the Project |

| Performance Indicator Reference Sheet #10 |
| --- |
| Indicator: | Organizational Capacity of Targeted CBOs |
| B. Description |
| Precise Definition: The average aggregate organizational capacity assessment score of targeted CBOs. The Organizational Capacity Assessment is a tool where organizations score their strengths and weaknesses on 196 items in the areas of: (i) governance, (ii) natural resource management, (iii) management, (iv) financial management, (v) conflict management, (vi) sustainability, and (vii) advocacy. These items are scored on a scale of 1-6 where: 1=needs immediate attention; 2=needs major attention; 3=needs attention on a wide scale; 4=needs attention on a limited scale; 5=acceptable, needs minor attention; and 6=acceptable no need for immediate attention. A median score is obtained for each organization and these are then compiled across organizations 1 reporting score produced. There are four levels of organizational development: Nascent (overall scores 2.3 or below), Emerging (2.4-3.5), Expanding (3.6-4.8) and Mature (4.9-6.0). Each CBO is periodically re-assessed (after receiving support from KCMP in their areas of identified weaknesses) resulting in a new score showing progress (or lack there of) over time. Unit of Measure: Average aggregate OCA score of targeted CBOs Disaggregated by: a) CBOs brought in the current year; b) CBOs brought in previous years |
| C. Plan for Data Collection |
| Data Collection Method: OCAT Data Source(s): Organizational Capacity Data Forms, Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Negligible. Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & reporting: Compare targets to actual performance. Review trends over time. Report qualitative information describing and organizational capacity development efforts undertaken and record notable outcomes. Include efforts beyond the targeted 10 CBOs to include entire SO5 focal areas population efforts. Display targets and actual performance data in Summary Data Performance Table. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: For the purposes of this indicator, 10 CBOs are originally planned to participate in the assessment process. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 10 - Organizational capacity of targeted CBO

| Name of OCATTER: |  | Date: |
| --- | --- | --- |
| Name of CBO | OCA Score | Comments |

Indicator Reference Sheet: Indicator #11

| Performance Indicator Reference Sheet #11 |
| --- |
| Indicator: Level of policy/legislation advancement |
| B. Description |
| Precise Definition: The policy reform indicator will use a point index to provide a qualitative measure of overall progress in the establishment of a policy environment supportive of improved CRM. The index will track the achievement of milestones in policy development process through to implementation of legislation or policy. The final weighting of specific milestones areas in this indicator reflect the amount of effort being undertaken and the areas where KCMP can most make a difference. Unit of Measure: Milestone phases. Disaggregated by: Each individual policy or Act will be rated equally in terms of potential or realized impact in ICM |
| C. Plan for Data Collection |
| Data Collection Method: Through meetings, advocacy Data Source(s): KCMP performance reports. Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Negligible. Responsible organization / individual(s): KCMP partners. |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Results are annual. Review progress over time. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): KCMP may use qualitative indicators where most appropriate. The implied hypothesis is that policies and legislation lead to increased expected incentives for management. Data may not always capture the linkage to expected incentives as there can be a difference between enactment and implementation. Actions Taken / Planned to Address Data Limitations: When qualitative data is used the KCMP will clearly define each term used in the measure and document all definitions. |
| F. Performance Data Table |
| Notes on Baseline and Targets: The year 2004 annual report data will be used as a baseline. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #12- 13 |
| --- |
| Indicator: | #12 Number (by type) of trainings/workshops held #13 Number of people trained |
| B. Description |
| Precise Definition: Indicator refers to the number of training sessions by type, provided for the target beneficiaries. They include workshops, seminars, meetings and exchange visits Here Type means the subject of training/workshop. Number of people benefiting directly through successful completion of the training by gender. Unit of Measure: Number(s) Disaggregated by: Type and gender |
| C. Plan for Data Collection |
| Data Collection Method: Training reports Data Source(s): KCMP partners Timing / Frequency of Data Collection: annual Est. Cost of Collection: Negligible Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: KCMP performance targets versus actual. Review of trends over time. . |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Nil Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: Rough Baseline data will available in 2001 to set initial targets. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 12 and 13 – Number (by type) of trainings/workshops and number of people trained

| Data collector: |  | Date: |  |
| --- | --- | --- | --- |
| Training/workshop | Type | Number trained | Comment: |
|  |  | M | F |  |

| Performance Indicator Reference Sheet #14 |
| --- |
| Indicator: | Number of CBOs participating in ICM (Number of new CBOs formed to participate in ICM) |
| B. Description |
| Precise Definition: Number of CBOs directly or indirectly involved in improved CRM initiatives. CBOs are defined as existing groups who have embraced ICM or new groups formed to participate in CRM and related activities. These are classified in two categories as: (1) CBOs Directly Involved and Benefiting (groups who receive funding, training, technical assistance, commodity support, resource access or financial returns from KCMP); and (2) CBOs Indirectly Involved and Benefiting (groups who do not personally receive funding, training, technical or commodity assistance but still receive a benefit from ICM. For example, when a CBO adopts a technology being applied by another CBO that had received training on Coastal Resource Focused management or enterprise development. Improved CRM is defined as reversing, halting or reducing the rate of unsustainable use of the natural resource base through an integrated management approach. Unit of Measure: Number of CBOs Disaggregated by: By resource type |
| C. Plan for Data Collection |
| Data Collection Method: Field visits and secondary data Data Source(s): KCMP partners and stakeholders. Timing / Frequency of Data Collection: Periodic and annually. Est. Cost of Collection: Negligible Responsible organization / individual(s): KCMP partners |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Review trends over time. Analyze ratio of CBOs in direct versus indirect classifications. Efforts should be made to move CBOs from an indirect classification to a direct beneficiary’s classification. Discuss gender and other disadvantaged group involvement data in terms of culture and decision-making relating to CRM. Report on CBO involvement per resource. |
| E. Data Quality Issues |
| Initial Data Quality Assessment: To be conducted ---- Known Data Limitations and Significance (if any): CBO registration of membership may not be current. Some may be registered and not active while other may have multiple activities. Actions Taken / Planned to Address Data Limitations:-Get data from registration officers and undertake proper assessment of the CBO. |
| F. Performance Data Table |
| Notes on Baseline and Targets: Rough Baseline data will available in 2005 to set initial targets, but targets should be finalized when all KCMI anticipated activities have been defined. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #15 |
| --- |
| Indicator: | Number of partners actively involved in ICM process. |
| B. Description |
| Precise Definition: Number of institutions actively involved in ICM process. Partners are defined as institutions who are participating in ICM. These may include government institutions, NGOs and private sector. Active participation means being involved in supporting ICM activities. Active participation involves benefiting from training, receiving funding, technical or commodity assistance to participate in the ICM process. Other institutions can be encouraged to participate in ICM activities. Unit of Measure: Number of Institutions. Disaggregated by: By mandates in CRM |
| C. Plan for Data Collection |
| Data Collection Method: Meetings and activities. Data Source(s): KCMP partners and stakeholders. Timing / Frequency of Data Collection: Periodic and annual Est. Cost of Collection: Negligible Responsible organization / individual(s): KCMP partners |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Review trends over time. Analyze level of participation of partners institutions. Efforts should be made to involve the partners as actively as possible. |
| E. Data Quality Issues |
| Initial Data Quality Assessment: To be conducted ---- Known Data Limitations and Significance (if any): Priorities may differ between and among institutions. Actions Taken / Planned to Address Data Limitations:-Capacity building of partners institutions to enable active participation, MoUs to make the CEOs accountable. |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #16 |
| --- |
| Indicator: | Amount of funding leveraged ($). |
| B. Description |
| Precise Definition: Cumulative amount of funds leveraged from other donors for investment in nature based enterprises based on business plans developed under KCMP. The amount leveraged to be presented in absolute figures committed by the donor for a specific business enterprise during certain GOK financial year (July-June). Unit of Measure: US $ Disaggregated by: N/A |
| C. Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners, Donor Financing Agreements Data Source(s): Pact Kenya, CDA Timing / Frequency of Data Collection: Annual Est. Cost of Collection: Staff time, Administrative Costs, Meetings, Travel and Per Diems Responsible organization / individual(s): Pact Kenya, CDA |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual amount leveraged/committed. Discuss sources of funding, amounts, nature of investments funded and modalities for disbursements. Identify collaborating partners and CBO roles and responsibilities in the financing arrangement. Presentation of Data: Display cumulative leveraged funds in narrative form Review of Data: Bi-annual (June & December ) review with implementing partners) Reporting Data: Report leveraged funds as part of the accrued benefits to the Community |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): None Actions Taken / Planned to Address Data Limitations: NA |
| F. Performance Data Table |
| Notes on Baseline and Targets: No targets set in the USAID SO5 Results Framework, Performance Plan (PMP) Indicators and Targets. However, due to inadequate investment funds provided under KCMP, financial leveraging is critical to the success of nature based enterprises. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Enterprise M&E Data Sheet: Funds Leveraged

Completed By: …………………………………………..                  Date: ……………….

Reporting Period:……………………………………….

Reporting Year:

| KCMP Investments in Enterprise |
| --- |
| Total Amount of Grant (Kshs) | Amount Disbursed (Kshs.) | By Who? | For What? |

Reporting Year:

| Investment Made by Private Sector |
| --- |
| Amount (Kshs.) | By who? | For What |

Reporting Year:

| Investment Made by Other Donors |
| --- |
| Amount (Kshs.) | By who? | For What |

Reporting Year:

| Investment by Community Based Organization (CB0) | Other Benefits Accruing to the CBO/Enterprise (Donations, etc) |
| --- | --- |
| Amount (Kshs) | For What? | Amount (Kshs) | For What? |

| Performance Indicator Reference Sheet #17 |
| --- |
| Indicator: | Number of infrastructures installed, by type. |
| B. Description |
| Precise Definition: Indicator refers to the number of infrastructure installed in specific project sites, by type. They include; fish depots, bandas beach access roads, rain water harvesting tanks, portable water, electricity, cold storage facilities (include freezers & ice boxes). It also includes fishing gears, communication facilities and boats., Unit of Measure:. Number(s) Disaggregated by: By type |
| C. Plan for Data Collection |
| Data Collection Method: Performance reports. Field observations Data Source(s): KCMP partners Timing / Frequency of Data Collection: Annual Est. Cost of Collection: Negligible Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Comparing KCMP targets to actual performance. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Nil Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets:. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 17 – Number of infrastructure installed by type

| Data collector: | Date: | Location: |
| --- | --- | --- |
| Type: | Number: | Comments: |

| Performance Indicator Reference Sheet #18 |
| --- |
| Indicator: | Number of data sets available. |
| B. Description |
| Precise Definition: Number of data sets on Coastal and marine areas. Data set is defined as periodic data of a particular field in coastal and marine areas (by resource) that is routinely collected and entered into a computerized system on a scheduled basis. Unit of Measure: Data by type. Disaggregated by: By resource type and purpose |
| C. Plan for Data Collection |
| Data Collection Method: Field studies, reports from researchers and research institutions. Data Source(s): Partner institutions, researchers and other stakeholders. Timing / Frequency of Data Collection: Periodic Est. Cost of Collection: Substantial-it may be necessary to hold workshops and engage consultants to process the data and softwares. Responsible organization / individual(s): KCMP partners |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: collation. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): to be determined. Actions Taken / Planned to Address Data Limitations: To be determined. |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #19 |
| --- |
| Indicator: | Number of titles/leases/user rights issued |
| B. Description |
| Precise Definition: Cumulative number of titles/leases or letters of allotment/authority secured from relevant authorities for community use. Titles/leases or letters of allotment are documentary evidence that enable community groups to acquire user rights for a resource such as access roads, public beach, fish landing sites and indigenous forests. Provision of user rights allow communities to have increased access to natural resources for the purpose of socio-economic activities including establishment of nature based enterprises. Unit of Measure: Cumulative number of user rights’ documents secured Disaggregated by: NA |
| C. Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners Data Source(s): CDA, Fisheries Dept., Forest Dept., MCM and Kwale County Council (KCC) Timing / Frequency of Data Collection: Annual Est. Cost of Collection: Negligible Responsible organization / individual(s): ICM Secretariat/ Wainaina Mburu |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Identify the user rights provided, roles and responsibilities of key stakeholders in resource management. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): None Actions Taken / Planned to Address Data Limitations: N/A |
| F. Performance Data Table |
| Notes on Baseline and Targets:. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data Sheet: User Right Documents (Titles, Leases, Letters of Allotment/Authority)

| Completed by (Name) : __________________________ | Date Filled ______________________________ |
| --- | --- |
| Site | Type of Document | Resource Type 1= Access roads, 2= Indigenous forests 3= public beach 4=fish landing site 5=LMMA | User Right Period (Years) |
| JKPB |  |  |  |
| Diani-Chale |  |  |  |
| Shimoni Vanga |  |  |  |

(NOTE: Consider dropping this Indicator as it’s covered elsewhere especially by Indicators on # new CBOs and # partners actively involved in ICM process)

| Performance Indicator Reference Sheet #20 |
| --- |
| Indicator: | Number of stakeholders demanding ICM related services |
| B. Description |
| Precise Definition: Unit of Measure: Disaggregated by: |
| C. Plan for Data Collection |
| Data Collection Method: Data Source(s): Timing / Frequency of Data Collection: Est. Cost of Collection: Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #21 |
| --- |
| Indicator: | Number of reports disseminated to local decision-makers |
| B. Description |
| Precise Definition: Refers to number of reports compiled and disseminated to local decision makers. These include program activities report,s performance reports, research findings and recommendations, Unit of Measure:. Number(s) Disaggregated by: NA |
| C. Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners Data Source(s): KCMP partners Timing / Frequency of Data Collection: Annual Est. Cost of Collection: Negligible Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: compare targets to actual performance from the reports/results. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Nil Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets:. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 21 – Number of reports disseminated to local decision makers

| Data collector: | Date: | Location: |
| --- | --- | --- |
| Type: | Number: | Comments: |

| Performance Indicator Reference Sheet #22 |
| --- |
| Indicator: | Business capacity (Enterprise Index) |
| B. Description |
| Precise Definition: The enterprise index provides information on the capacity of an enterprise to function and deliver services to its clients. The index is a tool where CBO enterprises score their strength and weaknesses on 67 items in the areas of community enterprise viability analysis, business planning, management, service delivery monitoring, financial management, costing and pricing, marketing, technology equipment, joint venture arrangements, tendering and benefits sharing. These items are scored on a scale of 1-6 depending on extent and magnitude of technical support required. Unit of Measure:. Median ECA score of targeted CBO enterprise Disaggregated by: Existing, Spin- off and New Enterprises |
| C. Plan for Data Collection |
| Data Collection Method: Performance reports from implementing partners Data Source(s): Enterprise Capacity Assessment Data Forms, Pact Kenya Timing / Frequency of Data Collection: Baseline and Annual Est. Cost of Collection: Staff time, Travel and Per Diem and administrative Costs Responsible organization / individual(s): Pact Kenya/Irene Gathinji |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Report qualitative and quantitative information describing enterprise capacity development efforts undertaken and record notable outcomes. Describe nature and level of enterprise development. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: To be conducted in 2004/2005 |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |
| 2003-2005 | 3 | 1 | Based on the envisaged business plans for the 3 sites |

Kenya Coastal Management Program

CBO Enterprise Capacity Assessment Tool Name of CBO: …………………………………………………………………... Date of Assessment: ……………………………………………………………………… Facilitated by (Name): ………………………………………………………………..

RATING SCALE

| N/A | Not Applicable |
| --- | --- |
| X | Sufficient information unavailable to assess |
| 1 | Needs immediate attention |
| 2 | Needs major attention |
| 3 | Needs attention on a wide scale |
| 4 | Needs attention on a limited scale |
| 5 | Acceptable, needs minor attention |
| 6 | Acceptable, no need for immediate attention |

Instructions: Circle the appropriate index below

| ENTERPRISE DEVELOPMENT |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Community Enterprise |  |  |  |  |  |  |  |  |
| a) The CBO has a business enterprise based on the use of natural resources | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) CBO has used benefits from natural resources to develop community enterprises | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 2. Viability/Feasibility Studies |  |  |  |  |  |  |  |  |
| a) The CBO undertakes feasibility studies prior to starting business | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The feasibility studies include an environmental impact assessment of the business activities | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The CBO has a system in place to monitor the impact of business activities on the environment | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO undertakes regular business appraisals | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 3. Business Planning |  |  |  |  |  |  |  |  |
| a) The CBO has business plans for its enterprise(s) | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b)The CBO engages in regular planning processes to revise business plans | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The business planning processes is participatory | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO has access to expertise in business planning | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) Members of the CBO understand the business plan | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| f) The CBO implements the business plan | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 4. Business Management |  |  |  |  |  |  |  |  |
| a) The CBO has clear systems for business management (financial, personnel, production, equipment/resources, information and marketing) | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The CBO has staff with skills and experience in various business activities | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The CBO has well defined production/service delivery processes | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO utilizes the systems in management of the business | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 5. Business Monitoring |  |  |  |  |  |  |  |  |
| a) The CBO has clear monitoring and evaluation systems | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The CBO regularly measures business performance against projections | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) Business performance data is used to inform decision-making | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO has production/service delivery standards | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) The CBO ensures quality control of its products/service | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 6. Costing and Pricing |  |  |  |  |  |  |  |  |
| a) The CBO has developed a costing and pricing system for each enterprise/product/service | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The costing and pricing system aims for profitability | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The CBO utilizes the costing and pricing system | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 7. Marketing |  |  |  |  |  |  |  |  |
| a) The CBO has a marketing plan | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The CBO implements its marketing plan | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) Market research is carried out prior to undertaking a business activity | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO solicits regular feedback from the market/customers | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The CBO uses feedback from the market to inform future plans/to improve its performance/products | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) The CBO has developed promotional materials | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| f) The CBO markets its products/services | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| g) The CBO undertakes new product development | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 8. Technology/Equipment |  |  |  |  |  |  |  |  |
| a) Technologies used are appropriate to local conditions | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) Technologies in use are accessible, easy to use and modify work-load of all social groups | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) Technologies in use are compatible with lifestyles and culture of members | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) Technologies are being used by appropriate persons | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) Training and technical assistance available | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| f) Training and technical assistance are accessed as required | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| g) Technologies enhance community’s self-reliance | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 9. Joint Ventures |  |  |  |  |  |  |  |  |
| a) The CBO understands joint venture guidelines | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) The CBO understands conditions of joint venture agreement | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) An agreement is in place with joint venture partner | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) The CBO adheres to the joint venture agreement | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO monitors the implementation of joint venture agreement | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) Joint venture selection is participatory and transparent | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 10. Tendering and Selection |  |  |  |  |  |  |  |  |
| a) The CBO advertises tender in a timely manner | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) Members participate in identifying options to be included in the tendering bid document | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The tendering process is carried out in a transparent manner | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) CBO notifies the joint venture partner of its intention to re-tender in a timely manner | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) CBO follows government/sector tendering guidelines and regulations | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| f) CBO follows government/sector selection guidelines and regulations | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| g) The CBO encourages local sourcing in awarding of tenders | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 11. Financial Management |  |  |  |  |  |  |  |  |
| a) Annual budgets are prepared according to operational plans | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) Budgeting procedures are adhered to | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) Financial management systems are in place | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) The CBO is using well defined financial control systems | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) Financial reports are prepared as required | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| f) Skills exist within management to implement financial systems | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 12. Organizational and Administrative |  |  |  |  |  |  |  |  |
| a) Clear management structure exists | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) Management carries out its defined roles | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) Management has the necessary skills to undertake their responsibilities | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) Administrative policies and procedures are documented | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) Administrative policies and procedures are followed | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| 13. Benefits Sharing |  |  |  |  |  |  |  |  |
| a) The CBO has a re-investment policy | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| b) Benefits sharing policy is utilized | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| c) The benefits sharing policy is reviewed regularly | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| d) CBO uses benefits accrued from natural resources to develop communities’ amenities, e.g. education, health services, clean water, improved shelter | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |
| e) The CBO benefits are valued by members | N/A | X | 1 | 2 | 3 | 4 | 5 | 6 |

| Performance Indicator Reference Sheet #23 |
| --- |
| Indicator: | Capacity of Constituency Groups in Advocacy |
| B. Description |
| Precise Definition: Capacity of constituency groups in advocacy as measured by an annual indexed figure. The Advocacy Index as developed by KCMP participants will be used. This index includekey components indicative of skill levels related to an organization's capacity in advocacy. For example, (i) The CBO has clearly stated advocacy objectives; (ii) the CBO has skilled manpower available for advocacy; and (iii) the CBO identifies advocacy issues with membership, etc. These items are scored on a scale of 1-6 where: 1=needs immediate attention; 2=needs major attention; 3=needs attention on a wide scale; 4=needs attention on a limited scale; 5=acceptable, needs minor attention; and 6=acceptable no need for immediate attention. The annual advocacy index score is the aggregated overall rating participating CBOs obtain on the advocacy index. Each CBO targeted will be periodically reassessed based on the advocacy index score ( after receiving capacity building support from KCMP fin their areas of identified weaknesses). Unit of Measure: Annual Advocacy Index figure representing the degree to which a group has capacity in advocacy. Disaggregated by: NA |
| C. Plan for Data Collection |
| Data Collection Method: OCAT Data Source(s): KCMP partners (Advocacy Index score) Timing / Frequency of Data Collection: Annual. Est. Cost of Collection: Negligible. Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Compare targets to actual performance. Review trends over time. Report qualitative information describing and advocacy activities undertaken and record outcomes to influence policy change or redress in policy environment. Note the percentage of targeted CBOs who have advocacy skill levels at the expanding or mature level. The information will be gathered through the OCA process and provided by Pact and reported accordingly. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Nil. Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: For CORE: 5 CBOs are originally planned to participate in the assessment and receive support in building advocacy capacity within their organizations. |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 23 – Capacity of constituency groups in advocacy.

| Name of OCATTER: |  | Date: |
| --- | --- | --- |
| Name of CBO | Advocacy index Score | Comments |

(NOTE: Consider dropping this Indicator as it’s covered elsewhere especially by Indicators on # titles/leases and formal authorities issued)

| Performance Indicator Reference Sheet #24 |
| --- |
| Indicator: | Number of management agreements being implemented. |
| B. Description |
| Precise Definition: Unit of Measure:. Disaggregated by: |
| C. Plan for Data Collection |
| Data Collection Method: Data Source(s): Timing / Frequency of Data Collection: Est. Cost of Collection: Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

| Performance Indicator Reference Sheet #25 |
| --- |
| Indicator: | Number of CBOs actively participating in coastal and marine policy dialogue by type of participation (i.e. advocacy campaigns, meeting participation...) |
| B. Description |
| Precise Definition: Indicator refers to the number of CBOs empowered to actively advocate and influence change through participating in policy dialogue and formulation processes. Unit of Measure:. Number(s) Disaggregated by: Type pf participation |
| C. Plan for Data Collection |
| Data Collection Method: Performance report. Data Source(s): KCMP partners Timing / Frequency of Data Collection: Annual Est. Cost of Collection: Negligible Responsible organization / individual(s): |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: compare targets versus actual performance |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): Actions Taken / Planned to Address Data Limitations: |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data collection form 25 – Number of CBOs actively participating in coastal and marine policy dialogue by type of participation (i.e. advocacy campaigns, meeting participation….)

| Data collector: | Date: | Location: |
| --- | --- | --- |
| Type of participation: | Number of CBOs | Comments: |

| Performance Indicator Reference Sheet #26 |
| --- |
| Indicator: | Number of violations (breach of safety and security) reported by type |
| B. Description |
| Precise Definition: Number of violations reported. A violation is an act that breaches safety and security of the Coastal resources and resource users. Unit of Measure: Number of violations. Disaggregated by: Type, resource and resource user. |
| C. Plan for Data Collection |
| Data Collection Method: Reports. Data Source(s): Partners, beneficiaries, Navy and police Timing / Frequency of Data Collection: Periodic and annual. Est. Cost of Collection: minimum-it can be low or high depending on circumstances. Responsible organization / individual(s): KCMP partners. |
| D. Plan for Data Analysis, Reporting, and Review |
| Data Analysis & Reporting: Review of reports. |
| E. Data Quality Issues |
| Known Data Limitations and Significance (if any): in-accurate and or false reports. Actions Taken / Planned to Address Data Limitations: Verifying the reports |
| F. Performance Data Table |
| Notes on Baseline and Targets: |
| G. Other |
| Comments |
| Date | Targets | Actual | Comments |
|  | (Baseline) | -- |  |

Data Collection Form

| Site/area | Type of violation | Number of violations | Source |
| --- | --- | --- | --- |

DATA QUALITY PLAN

See the Data Quality issues in the indicator information sheets.

INDICATOR MEASUREMENT TOOLS

See Indicator Protocol reference sheet to be developed

MONITORING TOOLS

Monitoring tools to be developed

EVALUATION PLAN

ACTIVITY EVALUATION

| What components of the program do we want to learn more about or evaluate | Sub components | What exact questions do we want to answer or want evaluated / explored | What data do we have to help us analyze this question/topic? | What further data will we need to acquire? | Who should be involved in either giving input or analyzing information? | When will we obtain info (dates) or conduct analysis? | When and how will we disseminate the data and adapt our program? |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ICM Initiatives | Infrastructure | How many of the planned structures are complete & at what level? Reasons for completion/incompleteness? What is the level of stakeholder involvement? Is there sense of ownership? Which infrastructure development initiatives worked better and why? | Indicator data form (Indicator form no. 17) Financial records | Sense of ownership through a social survey | KCMP staff & partners Recipient communities GOK Departs. i.e. public works | Indicator data sheets updated bi annually Mid-term assessment | July & January Reports to partners Newsletters to stakeholders Review of results framework -March |
|  | Resource Based planning | What resources are targeted? Where are the resources located? Who & how many are participating/involved-technical, stakeholders-? How many planning sessions held? What is the KCMP contribution? What is the beneficiary’s contribution? Which are the success stories? Have the ICM plans been adopted, implemented and replicated? | Signing sheets for training Indicator data forms (No. 5, 12 13,14,15, ) | Level of completion | KCMP staff & partners Recipient communities GOK Departs. i.e. public works | After each training session Indicator data sheets updated biannually | July & January Reports to partners Review of results framework -March |

|  | Resource access and utilization | Which interventions have been put in place to promote resource utilization? How successful are the interventions? How are the stakeholders utilizing the resources? Are there any success stories? Are there safe guards to ensure sustainable utilization of resources? | Indicator data form (Indicator form no. 4,6, 7) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Awareness and Mobilization | How many stakeholders are aware of ICM? Are the stakeholders using ICM in their activities? How much resources are spent on creating awareness on ICM? What media covered ICM activities? |  |  |  |  |  |
| Program Management |  | Are we meeting the program targets in time? How are partners involved in planning and implementation? Are the resources allocated adequate and timely? How committed are the partners and are they motivated? Are there program time over runs? | Performance review reports M & E report Financial records | Partner motivation-Survey on Appraisal partner motivation Activity reports | Internal review by KCMP partners External Consultant |  |  |
| ICM POLICY |  | -What were the policy issues identified? - How were the issues identified? - How far did we go in having the issues addressed? - What role did communities play in advocating for policy change? - How far did we go in the policy process and why? - To what extent were grassroots/local institutions involved in the policy process? - What role did the national office play in the process? -What level of financial resources were allocated to policy development? | - Several report on issues identified - Consultants and workshop reports - Notes on lobbying meetings at Ministerial headquarters, - - Minutes of ICM partners meetings, - Workshop reports - Indicator data no #25 Number of CBOs actively participating in coastal and marine policy dialogue by type of participation (i.e. advocacy campaigns, meeting participation) - Indicator data no #11: level of policy /legislations advancement - Indicator data on # 15 the number of partners actively involved in ICM process. Indicator data no # 21 -Number of reports disseminated to local decision makers | Cases of what has happened in other countries, Participation at national level in the policy process Communities participation in the process | KCMP Secretariat KCMP Partners AG Chambers Parent Ministries Experts/Key Informants | Quarterly reports on Issues identified Bi-annual program reports Indicators annual data Mid-assessment /evaluation Final evaluation | Discussions during monthly ICM meetings Bi-annual Stakeholders forums Chief Executives annual meetings |
| CAPACITY BUILDING |  | - How were the capacity building needs identified? - What areas of capacity building needs were identified? - To what extent were target institutions/CBOs involved in the process? - What kind of capacity building processes and inputs (funds included) were provided? - How effective were the capacity building processes, inputs and methods provided/used? - Have the training needs of program officers been identified and met? | - Indicator data on #10 organizational capacity of targeted CBO - Indicator data on # 9 financial benefits to communities from nature focused businesses - Indicator data on # 12 and # 13 number (by type) of trainings/workshop ; number of people trained - Indicator data on #22 on business capacity - Training evaluation forms - Training reports - Sign in sheets from training | Communities perception of the capacity building Other stakeholders/NGO reports/perceptions on capacity building | Implementing partners KCMP Secretariat Consultants/ Experts | Indicator data updated annually Training reports/ evaluations form after each training Quarterly performance reports Bi-annual and Annual performance reports Mid-term evaluation reports | Discussions during ICM meetings Annual results framework review Chief Executive annual meetings |

REPORTING PLAN

| Internal Audience | Communication Tool Selected for Reporting Purposes | Schedule for Reporting |
| --- | --- | --- |
| Board of Director | Activity Reports | Bi Annual (1st July,1st January) |
|  | Annual Reports | 1st January |
|  | Financial Reports | 1st January |
| Community Leaders | Activity Reports | Bi Annual (1st July,1st January) |
|  | Financial Reports | 31st December |
|  | Annual Reports | 1st January |
| Program Directors and Managers | Monthly Reports | 1st Working day of every month |
|  | Quarterly Reports | 1st April, 1st July, 1st Oct, 1st Jan |
|  | Monthly E-Mail updates |  |
|  | Final Performance Reports | Project Inception, On demand |
|  | Financial, Audit and Close out Reports | May 15th |
| ICAM Partners | Annual Reports | 1st September |
|  | End of Project Report | 30 days after end of grant |

| External Audience | Communication Tool Selected for Reporting Purposes | Schedule for Reporting |
| --- | --- | --- |
| USAID | Financial Quarterly Report | October 15th , January. April 15th |
|  | B… Annual Progress | January 31st |
|  | Annual Reports | September 30th |
|  | Mid- Assessment |  |
| Parent Ministries | Budget Estimates | December 31st |
|  | Annual Workplans | May 30th |
|  | Annual Reports | December 31st |
| Politicians | Casual Contacts | On demand |
|  | Newsletters (Quarterly) | April 15th |
|  | Activity Briefings | - |
|  | Fact Sheets (Quarterly) | Project Inception, On demand |
|  | DDC Presentations | May 15th |
| Communities | Meetings/Barazas | Project Inception/ All above/ On demand |
|  | Activity Inception Meetings | Inception |
|  | Progress Meetings | Ad hoc |
|  | Commissioning forums |  |
| Others NGOs | Meetings | Appointments |
|  | Newsletters | Periodic |
|  | Stakeholders | Periodic |
|  | Meetings | Ad hoc |
|  | Other forums | As above |

APPENDIX A: AUDIENCE ANALYSIS

## APPENDIX B: KCMP ORGANIZATIONAL CHART

## APPENDIX C: INTEGRATED COASTAL AREA MANAGEMENT (ICAM) INSTITUTIONAL MEMBERS

| Kenya Forestry Research Institute P.O. Box 20412 00200 Nairobi Tel: 066-32891/2/3 Fax: 066-32844 Director of Water Development P.O. Box 30521 Nairobi. Tel: 020-2716103 Fax: 020-2727622 Kenya Marine Fisheries & Research Institute P.O. Box 81651 Mombasa Tel:041-475151/475152/4 Fax: 475157 Fisheries Department P.O. Box 58187-00200 Nairobi Tel: 020-3742320/749936 Fax: 020-3744530 Kenya Wildlife Service P.O. Box 40241 Nairobi Tel: 020600800/602345 Fax: 020-501752/500276 Municipal Council of Mombasa P.O. Box 90440 Mombasa. Kenya Association of Hotelkeepers & Caterers P.O. Box 83378 Mombasa Or Fax: 041-5485652/405 Tel:041-5485926/7/8/9 National Museums of Kenya Museum Hill Rd. Westlands P.O. Box 40658 Nairobi Tel: 020-220058/222425 Fax: 020-3741424 | Kenya Ports Authority P.O. Box 95009 Mombasa Tel: 040-312211/221211 Fax: 0410311867 National Environment Management Authority P.O. Box 47146 Nairobi Tel: 020-609013/27 Fax: 020-608997 Forestry Department Chief Conservator of Forests P.O. Box 30521 Nairobi Tel: 020-3754904/5/6 Fax: 020-3764249 Coast Development Authority P. O. Box 1322, Mombasa Tel. 041 224406/225774 Fax. 041 224411 Department of Tourism Ministry of Information & Tourism P. O. Box 30027 Nairobi Tel: 020-313010 Tel: 041-223465 PARTNERS PactKenya P.O. Box 76390 - 00508 Nairobi Tel: 020-578271/3/4 Fax: 020-570775 |
| --- | --- |

PERFORMANCE MONITORING PLAN (PMP)/M E & R TRAINING WORKSHOP

DATE: MONDAY, 21ST TO THURSDAY, 24TH 2005

VENUE: SUN N’ SAND BEACH RESORT, KIKAMBALA

WORKSHOP REPORT

1.0	INTRODUCTION

The Monitoring, Evaluation and Reporting (ME & R) training workshop was organized by the Kenya Coastal Management Program (KCMP) in order to develop a Performance Monitoring Plan (PMP) for the Program. The Plan is necessary for the systematic and timely collection of performance data, analysis and reporting. The training workshop was attended by representatives from KCMP partner institutions (annex 1).

1.1	Workshop Objective

The objective of the workshop was to develop the components of the Performance Monitoring Plan for the Kenya Coastal Management Program (KCMP).

  - Workshop Outputs

The expected outputs for the workshop were as follows:

- Identification of audience and their information needs.

- Identification of some or all indicators to monitor efficiency and evaluate the effectiveness of the Program.

- Identification of the evaluation system to be put in place by the Program.

- Identification of the reporting system to be put in place by the Program.

2.0	OPENING REMARKS

Eng. Wainaina Mburu, Executive Secretary of ICAM/KCMP welcomed the participations and appreciated their continued support to the Program. In his opening remarks, Dr. B. A. J. Mwandotto underscored the need to consider the social dynamics of the KCMP target groups and therefore set realistic monitoring indicators and targets for effective implementation of the Program.

- WORKSHOP PROCESS AND RESULTS

Lynn McCoy was the main resource person on day 1 while Paul Cowles was the resource person on day 2 and 3.  The workbook on Monitoring, Evaluation & Reporting Course # 1 prepared by Pact, Inc. (2005) was used as the main training resource material.

Day One

During the morning session, the participants were led in listing their expectations for the workshop (annex 2). This was later followed by a presentation on the principles and essential elements of ME and R System and identification of audiences and information needs.   This included:

- identifying the benefits and purposes of tracking performance, measuring results and reporting the progress of a program

- defining the terms monitoring, evaluation and reporting (MER) as well as other key terms often used in the discussions of MER systems

- essential elements in developing a successful MER program

- factors that contribute to monitoring program failure

- determining different audiences for the Program and their unique information needs.

The group tasks involved identifying benefits of monitoring and evaluation and identification of the Program specific audiences and information needs.

In the afternoon, the focus was on Principles of Results Based MER and Review of Results Framework. Emphasis was laid on the importance of results based management and monitoring, levels of results and refining strategic plan elements into results statements to clarify linkages and hierarchy. The participants went into two groups during which they reviewed the KCMP activity results and thereby developing a Results Framework for KCMP. The last presentation for the day was on Indicators and the participants had an opportunity of learning the importance, how to identify indicators, selecting indicators, criteria for assessing the quality of indicators and how/why it is necessary to develop indicator protocols.

Day Two

Day two presentations/discussions and group work were largely on reviewing the indicators for the KCMP, assessing the quality of the indicators selected and developing indicator protocols/methods to be used to collect data for KCMP. Data Collection Forms were developed for the 25 indicators selected.

Day Three

The focus was on Monitoring Tools, Evaluation and Reporting. In addition to indicator protocols that a Program may use to track progress of their programs, other monitoring tools presented included:

- A benchmark calendar

- An activity based budget of the benchmark calendar

- A comparison chart

- A deliverables schedule

On evaluation and reporting, emphasis was laid on the importance of evaluation and reporting, the different types of evaluations, reports and communication tools for use by a Program, who should be involved in evaluations, developing a learning agenda and formats for project quarterly and final reports. Through group work and discussions, the participants were able to:

- Develop an evaluation program and schedule and identify some of the learning agenda questions.

- Develop a reporting program and schedule.

4.0	WAY FORWARD

In order to finalize the PMP, the following was agreed:

- To write up a draft PMP.

- Circulate draft PMP to the participants (within 2 weeks).

- Review the draft PMP (mid April 2005).

- Send the draft PMP to USAID.

- Review and finalize the PMP (early May 2005).

- Put together baseline and current data values.

WR Annex 1: List of Participants

| No. | NAME | INSTITUTION | ADDRESS/E-MAIL | TELEPHONE |
| --- | --- | --- | --- | --- |
| 1. | Dr. B.A.J. Mwandotto | Coast Development Authority | P.O. Box 1322, Mombasa | 0722-755749 |
| 2. | Mr. S.M. Mwanguni | Coast Development Authority | P.O. Box 1322, Mombasa | 0733-600910 |
| 3. | Mrs. M.W. Mukira | Fisheries Department | P.O. Box 90423, Mombasa | 0733-736704 |
| 4. | Mr. J. Ngugi | Pact – Kenya | P.O. Box 10042, Mombasa | 0722-968913 |
| 5. | Mr. P.E. Kahaso | Pact – Kenya | P.O. Box 10042, Mombasa | 0733-776983 |
| 6. | Mrs. S. Khamis | Kenya Association of Hotel Keepers & Caterers | P.O. Box 83378, Mombasa | 041-228208 |
| 7. | Mr. E. Mathuva | Tourism Department | P.O. Box 80091, Mombasa | 0722-865111 |
| 8. | Mr. F. Mdoe | Coast Development Authority | P.O. Box 1322, Mombasa | 0720-898052 |
| 9. | Ms. A. Mkazalla | Coast Development Authority | P.O. Box 1322, Mombasa | 0722-980787 |
| 10. | Mr. J. Wainaina Mburu | Coast Development Authority | P.O. Box 1322, Mombasa | 0722-556084 |
| 11. | Mr. Kaleb A. Mwendwa | Kenya Marine Forum | P.O. Box 85620, Mombasa | 0734-333712 |
| 12. | Mr.S. Mwangi | Kenya Marine Fisheries & Research Institute |  |  |
| 13. | Mr T.E. Mbuvi. | Kenya Forest Research Institute | P.O. Box 1078, Malindi kefrigede@africaonline.co.ke |  |
| 14. | Mr. H.S. Massa | Water Department |  |  |
| 15. | Esther Luganje | Coast Development Authority | P.O. Box 1322, Mombasa | 041-224406 |
| 16. | Ms. Lynn McCoy | Pact, Inc |  |  |
| 17. | Mr. Paul Cowles | Pact, Inc |  |  |

WR Annex 2: Workshop Expectations

The following are some of what the participants expected by the end of the training workshop:

- Develop/understand structure for Monitoring and Evaluation

- Develop clear performance/Monitoring and Evaluation indicators

- Develop focused reporting system for all the partners

- Coordinated Monitoring and Evaluation

- Develop a reporting system understood by beneficiaries

- Develop/understand reporting system for KCMP

- Develop/understand/set simple indicators and targets

- Develop clear performance monitoring plan for KCMP

# Text boxes

KCMP

ICAM

Secretariat

Community Activities

Program Steering

Committee (PSC)

Program Implementation Team (PIT)

Program Management Team (PMT)

USAID/Kenya

Managing

Director (CDA)