Proposal for Alaska Aviation Weather Enhancement Assessment Utilizing Geographic Information Systems (GIS)

Dr. Cherie Northon and Dr. Thomas Eley

Department of Geomatics, University of Alaska Anchorage

July 29, 2003

Background:

Geographic Information Systems (GIS) are computer-based systems that allow integration, mapping, and analyses of spatial data of all kinds (Figure 1).  GIS has been called the “digital lens” for analyzing the dynamic relationships between people and their environment.  Nowhere are spatial data and human-environmental interactions more evident and important than in aviation.  Alaska is a flying state, with many towns and villages only accessible by air.  Most visitors to Alaska arrive by air, and Alaska has the highest per capita private airplane ownership and airplane pilots of any state.  It is time to incorporate GIS into aviation operations, planning, and safety.

Objectives:

The goal of this proposed project is to gather selected existing geospatial data sets of Alaska that are important to aviation in order to demonstrate how a Geographic Information System (GIS) could be used to enhance the State’s aviation operations, planning, and safety.  Initially, the target datasets would encompass:

- State and Municipal Public Use Airports

- Weather reporting facilities (aviation quality automated and augmented observations)

- Terrain

- Flight routes

  - Visual

  - Victor Airways

  - Other

- Weather related aviation accidents

- Weather forecast areas

These datasets will then be brought into the aviation GIS database, where mapping and analysis of the data can be accomplished.  The GIS would allow multivariate analyses of aviation issues, such as accidents in relation to flight routes, terrain, weather reporting facilities and forecast areas, and communications facilities.  This GIS can later be enlarged to include other databases and conduct other analyses to enhance aviation in Alaska.

Implementation Plan:

The data sets listed above will be acquired and incorporated into a state-wide aviation database.  With the consultation of the sponsors, a small user team with representation from the FAA, NWS and aviation community will be established to work with the project staff on this project.  Initial maps will be generated showing the data sets for validation by user team.  After validation, project staff will work with the user team to make a special product used to display the planned surface weather observing equipment and weather camera locations and evaluate these locations with respect to parameters supplied by the team, such as terrain, airport location, and positions of fatal weather-related accidents.  The special product will be presented to the team for review and refinement. During this phase of the project, entry level training will be provided for up to ten members of the NWS and other cooperating agencies.  This training will be an introduction to ArcView, and will feature the Aviation GIS product developed during the project.

Following development of the initial aviation GIS database and special product, project staff will present the results to the sponsors, and discuss possible follow-on activities including, but not limited to, including expansion or refinement of the databases, options for long-term maintenance, training in GIS technologies for staff, etc.

In the final phase of the project, the project staff will develop a conceptual framework for a long-term, operational GIS for Alaskan aviation infrastructure.  The recommendations will include consideration of elements beyond those used in the demonstration project, an architecture for the system, and other factors required to make a successful long-term planning tool.

Schedule:

Phase I:

Following project approval, establishment of the user team with representatives from the sponsors and aviation community.  Acquisition and construction of the initial data base and data layers.  NWS to provide a list of Alaska aviation fatalities as part of the data sets.  Generation of initial data products for validation. (16 weeks)

Phase II:

Validation of initial data layers by the user team. Identify parameters to be used for special product development. (4 weeks)

Phase III:

Development of a special product. Presentation to user team, and refinement based on feedback.  Presentation of final products to the user team and project sponsors. Consultation with sponsors and development of recommendations for follow on activities. Three-day training group session encompassing an introduction to ArcView and the Aviation GIS product—assuming novice GIS users.  Student capacity—10.

(8 weeks)

Phase IV:

For the final phase of the project, the project staff will develop a conceptual framework for a long-term, operational GIS for Alaskan aviation infrastructure.  The framework will include elements beyond those incorporated in the initial project and will consider options for the architecture of the system, recommendations for implementation, use of standards and rough order of magnitude costs. (6 weeks)

# Text boxes

## Elevation & Topography

Airports

Forecast Areas

Flight Routes

Accident Sites

Orthoimagery (DOQ)

Weather Reporting

Figure 1.  The concept of an aviation GIS. Note: This is not intended to be an exhaustive list of the possible aviation layers, but only serves as an example.