# Introduction.

In this parts of our proposal we discussed production of EMU CMS chambers at USA (figure 1). Large CSC chambers (ME234/2 - 148 chambers) - will be build at FNAL’s production site. And final assembling and testing (FAST) of will be done at two sites. One FAST site is located at UCLA campus and operated by Universities of California Consortium. Second FAST site is located at University of Florida. Production tasks flow, which show responsibilities of each site, presented at figure 2. Some part of EMU CMS chambers will be assembled and test at foreign sites (table 1). Russian collaborators will response for assembling and testing at PNPI (Sant Peterburg) ME2/1(38) & ME3/1(38) CSC chambers. ME1/2(74) and ME1/3(74) chambers will be assemble and test at China (IHEP, Bejin). USA EMU CMS team (FNAL site) will design and develop: all chambers, assembling technology, tooling and QC/QA procedure for all type of chambers.  Prototypes of all chambers will be build at FNAL. Physicists and engineers from China and Russia will participate in the assembling corresponding pre-production prototypes at FNAL. US CMS will build at FNAL and provide to foreign sites a critical tooling (anode wires winding machine, wire tension measuring setup, gluing equipment end etc.). US CMS will supply chamber’s parts to foreign sites (panels, gap and wire-fixation bars, anode wire, glue, etc.). Major site for US EMU CMS production is located at FNAL (figure 3). FNAL have to cut and mill panels for whole project and assemble large ME234/2 chambers.  Schedule of CSC chambers production presented on table 1. Later we will discuss how we are correcting our production schedule, based on recent experience.

At this chapter, briefly summarizing status of readiness FNAL production site to start production, we have paid more attention to those places in production flow, where Yuriy Pischalnikov, as a member of production team and as a UCLA liaison-physicist, are playing a major role. Those places are including CSC Panels production (QC/QA issues), CSC production information database management and operation of Cosmic Ray Test Station, CSC alignment issues.

# Fermilab as a major EMU CMS production facility.

Inside CMS EMU project FNAL is the host Laboratory for production of CSC chamber. Fermilab CSC production team (based on physicists and engineers from several Universities (including UCLA) and FNAL) has concentrated during several last years on chambers R&D efforts.  During 1998 and 1999 we started to change direction. We still are doing some R&D (like building chambers prototypes for Radiation damage study, building prototypes for CERN test beam, etc.). But now we are spending near 100% of our times building CSC production facilities at FNAL. During last two years fermilab’s production team concentrated on

1). Finalizing design of all prototypes (design of ME234/2; ME1/2 done and ME2/1; ME2/1; ME1/3 and ME3/1 in working progress (see Table 2).

# 2). Designing of tooling for production’s facilities and for FAST sites

3). Developing QA/QC procedure for panels production and for assembling chambers

4.) Developing procurement strategy (close work with vendors).

Main facilities, which will be use by EMU CMS collaboration at FNAL to deliver chambers, are:

- LAB8 Panels production facility (figure 4);

- MP9 CSC chambers assembling facility (figure 5);

- LAB7 – cosmic rays CSC-factory test facility (figure 6).

# LAB8 Facility.

Yuriy Pischalnikov is UCLA physicist, who, as a member of Fermilab production team, is leading efforts at LAB8. He is working in close contact with LAB8 management and FNAL production site manager (G. Apollinari). His goal, as physicist-in-charge, was to develop Quality Control/ Quality Assurance (QC/QA) program for production of CSC panel. Also, as a member of Fermilab production team, Yu. Pischalnikov will maintain his role a physicist-liaison between Panel production site and chamber’s assembling site. His responsibility will include (but not limited) control of delivering CSC panels in complain with established and proven QA/QC procedure and according approved by DOE and collaboration schedule.

Pictures of main facility for CSC panel production – LAB8 presented at figure 6. For next 4 year this facility will mainly work for CMS EMU project. Two major machine Axxiom and Gerber are operating into 2 shift now. Axxiom is been used to drill holes in panels and cut panels in trapezoidal shape. And Gerber is been used to mill with precision of 2-3 mills strips on the surface of copper.

We worked closely with technical personal of LAB8 on solving all technical issues during last year to bring this facility in to operation. CMS EMU project support: relocation of Axxiom machine into new (more strong foundation) place inside LAB8, installation of vacuum lifting equipment. We have developed in collaboration with floor manager panel production flow scheme (figure 6). We started panel’s production at LAB8 at June, 1999. First several month, as a typical, we slowly and, some times painfully, went through the learning curve. Now, after more than 32 weeks in production,  we can claim that production speed is satisfy our schedule. And we have confidence, that LAB8 team can deliver to CMS EMU project 2736 (see table 1) panel during next 4 years. Plots, presented at figure 7, are panel’s production status. We are keeping those, weekly update information (Excel file: Completed Axxiom-Gerber Panels.xls), on the web-site (http://tdpc01.fnal.gov/project/UsCmsEmu/Lab8production/).

But main our efforts, before starting panel’s production, were concentrated on developing QC/QA program. There were many driven factors to leading existing panel’s production QC/QA program.  One of the crucial issues in the production of panels is precision of milling strips on the Gerber machine. We discussed this in details in next chapter.

# Using Gerber Machine for to mill strip artwork on the SCS panels.

Gerber is a more than 20 years old machine. And unfortunately, there are some features of Gerber, which we can’t correct. Accuracy and repeatability, with which Gerber milled artwork, not as good as we required. Our requirements for strip’s artwork precision  are near 1- 2 mils.

If we can’t mill strip’s artwork with this precision, we must to measure strips artwork on each panel with 1-2 mils precision afterward. All strip’s position measurements will store at  FNAL and CERN CMS data base (“CRYSTAL”-type). Later, we will calculate position of each particular strip inside global CMS system of coordinate.  We will use this info to calculate momentum of muon during off-line analysis. For purposes of using CSC chambers into trigger we must to have accuracy of milling strips vs. axis of panel not worse than +/-20 mils. Our experience during R&D stage and results from our first 25 “production like” panels, shown that Gerber can simple keep accuracy inside +/-20 mils requirement.

How we decided to measure position of strip’s artwork?  We have evaluated different techniques for this type of measurements. Best one, from our point of view, based on using Coordinate Measuring Machine (CMM) figure 8. We used CMM successfully during our R&D stage (see next chapter). Measurement of one panel required at least 1 day of work at CMM plus time to analyze the data. Definitely, we can’t afford to measure several thousand CSC panels for whole EMU CMS project. But we decided to use CMM machine to measure only few panels for each new prototype. We are planing to build  during FY2000 four new prototypes (see table 2)) (ME1/2; ME2/1; ME1/3; ME3/1). For each new prototype we will measure one panel. Also we are planing to choose some panels for random (one from several hundred) control (measurement) at CMM. This procedure will be part of our QA/QC program.

After some design work we come with simple (more robust) solution. We build manual measuring device figure 9.  This tool based on 40 inches long optical scale (made by Mitutoyo ) and telescope with 60X amplification. Technicians from LAB8 (which operate Gerber) spend typically 20-30 minute to measure one panel (13 alignment marks). Difference between two sets of alignment marks measurements (for several panels) presented on figure 9. First set of measurements were done at CMM and second with manual device. This histogram illustrated that simple manual device provided accuracy better than +/-2 mils.

What is alignment marks and how they reflect position of strips artwork on panels? Alignment marks is a short grooves (1,5” long), located in the edges of panels.

Gerber has milled alignment mark’s grooves and the strip’s artwork during one panel’s installation on Gerber’s table.

We are trying to keep Gerber’s milling condition, which would provide strong relation between strips and alignment marks position. Differences between strips position and corresponding alignment marks presented in the figure 10. Our knowledge of Gerber’s machine operation still don’t allow us to explain difference, which we observed figure 10. We are working now to eliminate this negative effect in Gerber’s operation.

We have defined to make several alignment marks on narrow and wide side of panels (total 13 alignment marks). Two alignment marks (A & B) at the narrow side of panel reflect position of  a 1st  and  a 81st grooves at X=1”.  Alignment marks C & D at wide side reflect position of a 1st and  a 81st grooves at X=144” (for ME234/2). As you can see from illustration on figure 11, four alignment marks will provide us following information about strip’s artwork inside X-Y system of coordinate: 1) scale in the narrow and wide side, 2) off-set and 3) rotation. We have build X-Y system of coordinate using panel’s two alignment holes (center of alignment hole is 0;0 and axis X going through center of alignment slot). We are using the rest of marks for different purposes related with QA/QC questions (control for consistency (quality) of LAB8’s measurements (figure 12) and with CSC alignment tasks (location for Retro-reflective targets (see chapter about RRT).

As a part of our CSC panel’s production procedure, technician  at LAB8 measure (figure 9) and write down into Traveler position of each alignment marks.  Later, we are transferring alignment marks position information from Travelers into EMU CMS TD (FNAL’s Technical Division) database.  Other information, which we will gather during chamber production, will be also store at this TD database: e.g. tension of anode wire; capacitance of anode wire and cathode’s strips; Chamber’s HV training data; etc.

# Yuriy Pischalnikov, as a physicist-in-charge, is managing measurements and transferring data related with alignment marks into TD database. Example of alignment marks data (in Excel format) from TD database for ME234/2 anode panels presented on table 3.  Yuriy Pischalnikov is also doing preliminary analysis of alignment marks data figure 12. This analysis is a part of our CSC production QA/QC system. TD database will be accessible through WEB by to all US CMS members.   Later all information from TD database will transfer to CMS CERN database (CRYSTAL -type). CMS physicists will use this data for off-line physics analysis.

# Measurements of CSC panels at CMM.

Accuracy and repeatability, with which Gerber milled strip’s artwork on CSC panels, will directly reflect accuracy of EMU CMS chambers to measure momentum of muons. EMU CMS requirements for strip’s artwork precision, which coming from ultimate space resolution of EMU Chambers, are better 2 mils.  Task to measure position of grooves on a panels with size a 5’x 12’ is quite ambitious. Best results can obtain by using of large size Coordinate Measuring Machine (CMM). We were lucky, that Technical Division (TD FNAL) has large enough size CMM – CORDEX (figure 8). During R&D stage (last 2 years) we have measured 15 panels.

Probe with 0.3mm diameter ball was used for measurements of profiles of each groove (figure 8). CMM allow to deliver accuracy of measurements near several m. As you can see from plot at figure 8 accuracy of determination of the center of groove was near 0.1 mills. Data from CMM were transfer to PC and were analyzed in Excel format using code written in Visual Basic.

Results of measurements of strips for cathode panel presented at figure 13. According EMU CMS technical requirements strips must to be straight and deviate from theoretical (drawing) position less that +/-2 mills. As you see from figure 13, grooves (strips) deviate from straight line not more than  +/-2 mills on the length of 60”. This is inside our technical requirements. But location of grooves deviates from theoretical position more than 8 mills for groove #81. This deviation of groove position from nominal (theoretical) position is near the edge of our production’s limits but still is acceptable for CSC production. Deviation of all 81 grooves for 3 P3 prototype panels shown on the figure 13. Measurements of alignments mark position presented on figure 13 also. Information, which we obtained from analysis of CMM measurements of first pre-production prototypes, turned to be very valuable in our efforts to improve the Gerber’s performance. Results of CMM measurements of next prototypes, which were build after significant Gerber’s improvements presented on Figure 14.

We broadly used CMM measurements to develop QA/QC program for CSC panel production. As an example, position of holes into CSC panels measured with CMM, presented on Figure 15. This information, which illustrated accuracy and repeatability of Axxiom machine, is very important for assembling of CSC chamber.  Using of CMM for panel’s measurements was crucial during developing of Panels alignment procedure (see next chapter). As we mentioned early we are planing to use CMM machine during all 4-year period of EMU CMS production. During one more year we will bring panels for all new prototype to CMM facility. And later, during production we will use CMM to measure panels, randomly selected at production line, as a part of our QA/QC program.

Using Retro-reflective targets (RRT) to resolve CSC panels alignment.

Inside EMU CMS project there is team, which working under CSC alignment issues. Those people (from FNAL, Wisconsin University and Northeastern University) are developing alignment of chamber as a whole object inside global CMS system of coordinate.

But we also need to know position of strip’s artwork for each panel vs. others inside one chamber with accuracy close to couple mils (50 m). Panels’ strips position for one panel vs. each other for all 6 panels inside one chamber can be resolve from fitting high energy muon straight tracks passing chambers (cosmic rays or/and accelerator beam). But this information will be not enough for “to close the EMU CMS alignment loop”. We still need to know absolute position  (and scale) of strip’s artwork on at-least one (better two) panel vs. alignment targets located on the chamber’s frame (or chambers alignment pins).

Yuriy Pischalnikov, as a physicist-in-charge for panel’s QC/QA program, are leading R&D program for develop techniques for transfer panels strip position to “out-side chamber” system of coordinate.

Main complication of this task is coming from conditions that after chamber have been assembled, there are no feasibility to see strip’s art-work from out-site chamber. Only alignment marks located on the narrow and wide sides of panels accessible and can be used for transferring strip’s position. As we discussed previously, we have measured with CMM relation between strip’s grooves and corresponding alignment marks figure10.

We have proposed to use Photogrammetry technique. We are planing to use Retro-Reflective Targets (RRT) made by Hubbs (Hubbs Machine & Manufacturing, INC). RRTs, which we ordered from Hubbs,  has non-concentricity between reflective dot and shaft less than 0.5 mils (12,5m). RRT will be mounted on the edge of CSC panels into alignment marks groove by nesting target’s shaft into alignment grooves. Axis of RRTs shaft and groove must to be parallel (figure 16).

In the frame of R&D program, which must to prove that this techniques will work, we made test piece of panel with 6 alignment grooves (figure 17). Locations each of 6 alignment marks have been measured on CMM with accuracy better than 0,2 mils (5 m) (see previous chapters). After that, we have nested and glued 6 custom-made RRTs into alignment grooves. Using Photogrammetry technique we have measured position of RRTs. Photogrammetry technique have provided us with X; Y; Z and X; Y;Z  for each RRT.

Differences between X1 -coordinates of center of groove (obtained with CMM technique) and X2 - coordinates of center of RRT (Photogrammetry output) presented on figure 18.  Taking into account: 1) results from figure 18 (x~1 mil), 2) non-concentricity for RRT (x~0.5 mil), 3) absolute accuracy of CMM and Photogrammetry (x~1 mil), we made conclusion that proposed techniques will allow us to determinate strip’s position vs. alignment elements of CSC chamber (e.g. Retro-reflective balls located on the alignment pins ) with +/-1.5 mils accuracy.

Techniques for transferring strip’s position (described in this chapter and  developed by Yu.Pischalnikov) will be use as chamber production techniques for all EMU CMS chambers.

MP9 facility.

Fermilab based team of EMU CMS (with support of  FNAL management) made significant progress in creating at MP9 Building (figure 5)  major facility for assembling of CSC chambers. 145 ME234/2 (“large”) EMU CMS chambers will be assembled at MP9. All pre-production prototypes ( Russian’s - ME1/2; ME2/1 and Chinese  ME1/3 and ME3/1) will be build at MP9 too.

All major CSC assembling tooling (figures 5 and 19) designed, build and installed at MP9 at the middle of 1999. QA/QC program for EMU chambers have been developed. We already tested this QA/QC program during assembling ME1/2 pre-production prototype. Critical tooling for foreign sites, designed and build at FNAL, have been installed and tested at MP9.

Commissions, which included experts, do not related with CMS project, conducted set of reviews: CSC Design Report, Production Readiness and Safety reviews.

Fermilab production site is ready to start CSC production. There is some small slippage in production schedule. We still have some unresolved CSC integration issues, which are delaying our start to assemble ME234/2 at a full speed production. Fermilab production team is concentrating now on building at MP9 pre-production prototypes (ME1/2 - January 2000, ME2/1-April 2000, ME1/3-May2000, ME3/1-June2000). Goal of this work is to check foreign sites tooling, train Russian and Chinese colleagues, verify design of small chambers before going to production.  According update schedule full speed production of ME234/2 – large CSC chambers will be started at summer of 2000.

LAB7- Cosmic Ray Test Station.

FNAL Cosmic ray setup is located at LAB7. Historically LAB7 facility was first and only one test setup to test all our previous CSC prototypes during last several years. Fermilab team, together with FAST’s sites participation, started to work under design of  new Cosmic Ray  Test Station (CRTS) at Spring of 1998. We have the goal to design and build at FNAL CRTS, which can be duplicated at UCLA and UF. Yuriy Pischalnikov led these efforts. Conceptual design of  CRTS (figure 20) was finished at FNAL at fall of 1998. And at November of 1998 we assembled and tested major system of CRTS and started tests of prototypes of CSC (P2 and P3)(figure 6). In parallel with FNAL FAST-site’s team (UC and UF) started to assemble their CRTS, using experience gain by EMU team at FNAL.

One of the key detector, which we use at CRTS, is scintillating counters hodoscopes, made from 48 scintillating counters. Each counters is a scintillating plate with size of 235cm*30cm*12cm and 2 PMTs collecting light from both ends of scintillating plate. The counters serve as a trigger on cosmic muons. There are total 24 counters assembled in two rows, top and bottom. Each from these counters is readout by two photomultipliers (PMT, total 48). The current trigger requires the coincidence of signals from four photomultipliers of two counters - the bottom and the top which form the vertical hodoscope. The trigger is “OR” of these 12 hodoscopes. As a common stop for TDCs of scintillation counters and front-end anode electronics of the chamber the latest in time signal from the coincidence of four photomultipliers is used.

Preliminary all counters were tested on a bench, to determinate efficiency curve vs. HV and estimate of time resolution. After assembling counter as a trigger system for CRTS we repeated measurements with the goal to estimate the averaged time resolution of the signal from PMT and to estimate the contribution of the trigger time vs. coordinate dependence into the CSC anode "bunch crossing efficiency". The means and resolutions of each hodoscope are shown in figure 21. One can see that resolutions are within the interval of 0.8-1.0 nsec.

During next 4 years of EMU CMS chamber’s production, we are considering Femilab’s CRTS as a testing setup for production site.  Major volume of ME234/2 chambers will be tested at UCLA and UF FAST sites. Fermilab’s CRTS will be played a role of a “fast-response” setup to all concerns, which would arise during production.

One of the example of “quick-response” from Cosmic Ray Test Station to chamber’s assembling floor is our experience with assembling of P2* prototype. Results of measurements of P2* prototype at CRTS presented on figure 22. We were able to measure gas gain uniformity from P2* chamber just week after chamber has been assembled at MP9. One of the technical requirement for chamber quality is chamber’s gas gain variation. Gas gain inside whole chamber must to be less than +/-50%.  After gain measurement on CRTS we found that panel #3 has section of anode wire with gain 1,5-2.0 of average P2* chamber’s gain. Detail  analysis of panel#3 has reveal  that we have a problem with our “anode wire winding” machine. Anode wires at “high gain” region of  panel #3 have been placed out of center (see figure 22). Now we fixed this problem, but this is good example of  using of CRTS for “fast response” during chamber production.

Other example of that type of “fast-response” is utilization of FNAL’s CRTS  during last several month. EMU team are using FNAL’s CRTS as a central place to investigate complex of issues related with CSC integration (grounding and location of front-end electronics on the chamber, measurements of efficiency of cooling system, cables location, alignment’s questions, etc.).