Lesson Info

- Lesson Number: 	FPPD-LL-0005

- Lesson Date: 	26-jul-2000

- Submitting Organization: Swales Aerospace, Inc. (GSFC 491)

- Submitted by: 	Michael J. Cully

Subject/Title/Topic(s):

EO-1 Solar Array Cable Wrap Damage Problem Report 1045-40-1

Description of Driving Event:

Final inspections of EO-1 Spacecraft prior to T/V#2 revealed a hair line mark on the Solar Array Cable Wrap Bundle. Further inspection at 10-20X magnification indicated cut insulation of seven wires approximately 0.75 inches off the face of panel 5. Geometry of the cut (alignment, cleanliness, etc.) indicated damage due to a sharp object.

Corrective Action was as follows:

- Made use of current internal Bay 5 SADA cabling interface connection and spare wires.

- Fabricated “Connector Bracket Assembly” which essentially swapped wires (J2-7, J2-37, J2-19 & J2-27) with the spares. Parts were simple & made use of the existing bolt & hole pattern for brackets.

- Milliohm & insulation resistance (cross pin) testing conducted on entire cable to verify all wires prior to initiation of the change & rework of damaged cables.

- Although J 2-7, J2-37, J2-19, & J2-27 wires were being abandoned, the exposed copper & insulation wiring needed to be covered. Guard wires also needed to be reworked.

- All work was performed to Certification Logs, Work Order Authorizations (WOAs), & released drawings.

- Milliohm & HiPot tested entire cable following rework. (Connector Bracket Assembly testing which also included HiPot testing was performed prior to delivery to Spacecraft).

- Integrated Connector Bracket Assembly with Cable Wrap Assembly.

- Verified all SADA signals after the Connector Bracket Assembly was installed.

- Performed full SADA functional following rework.

- Performed S/C Aliveness Test following completion of S/C bay closure.

Other Global actions were as follows:

- Inspected all external cabling prior to blanket installation.

- Fabricated Red Tag Item to cover critical area of Solar Array cable.  To be removed prior to Solar Array installation.

- Verified Mechanical Margins of Safety for new bracket and inserts (no test factors).

- Determined that the Deployment Hinge has >4x torque margin for worst case environmental effects.

Lesson(s) Learned:

Further investigation of probable cause is as follows:

- It is believed that this damage occurred while in the 238 T/V chamber in the preparation of the Spacecraft for T/V (October ‘99) or while clearing out the GSE blankets in and around the SADA .  This cannot be verified and it is more than likely an accident which went unnoticed. The SADA and cable wrap were thoroughly inspected via bore scope shortly before T/V and was found to be nominal.

- Prior to T/V #1, a thorough inspection was performed in this area without issue.

- No work has been done in this area since leaving T/V, until recently.

- Cutting instruments are generally used in chamber operations (TC number cutting, GSE MLI clearing, etc.).

- One T/V GSE cable was found damaged in similar manner following T/V.

- Configuration in chamber was not conducive to “ideal working conditions for technicians” due to extremely tight configuration and poor lighting.

- QA oversight was from a distance during T/V buildup and T/V teardown due to continuous monitoring of oxygen level at chamber door due to concern over nitrogen purge in closed chamber.  Safety of personnel was first priority!  Also there was insufficient room to have two people in the same general physical area.

- Other post-T/V activity required use of razor blades (radiator tape cutting, excess adhesive removal/trimming, etc.) however this has been limited and is under constant monitoring by QA.

Recommendation(s):

Recommendations to prevent a similar event are as follows:

- Critical external harness (SA Cable Wrap, Deployment Harness, etc.) that are vulnerable during the I&T process if possible should be protected.

- Evaluate the incorporation of amble spare wiring for Solar Array Cable Wrap wiring. This will allow quick recovery if damage does occur, as in the case of EO-1.

- Minimize to the extent possible the use of sharp objects around the spacecraft. This is common practice for flight thermal blanket work however for ground support blanketing (removal operations) it is not standard practice.

- Limit the extent of test Thermal Couples and Heaters termination work "in the chamber" following the test. Typically terminating TCs in the chamber is quick versus breaking the connections at the chamber bulkhead and coiling up the wiring. However this can potentially expose flight hardware to damage if cutting tools are mishandled.

- GSE fixturing should be inspected for sharp edges that could potentially damage GSE cabling. Corrective action would be tapping edges as required.

- Evaluate lighting and general work conditions in the chamber prior to the start of flight hardware work. If required develop ways to increase light in the chamber.

- Amble time must be provided for chamber operations. Technicians involved in chamber operations are working in a very constrained environment (limited lighting, space constraints, clean suits, etc.) and therefore sufficient time must be alloted to perform their work safely.

- Route spare cable wrap wires to an access location conducive to rework.

Evidence of Recurrence Control Effectiveness:

A number of the above recommendations where implemented prior to the second Thermal Vacuum test on EO-1. The satellite was removed from the chamber and no issues have arisen to date in this regard.

Applicable NASA Enterprise(s):

Applicable Crosscutting Process(es):

Additional Key Phrase(s):

Facilities

Safety & Mission Assurance

Spacecraft

Test Article

Test Facility

Test & Verification

Can this lesson be included in the International Safety Lessons Learned (ISLL) Database? 	No

Submitted by:  		Michael J. Cully

Mail Stop/Code:     		Swales Aerospace, Inc.

Lesson Author (if different):    N/A

Phone Number:		301-902-4356

E-Mail Address:		mcully@swales.com

Lesson Date:			07 / 24 / 2000

Reference:

EO-1 Test Readiness Review to Code 300 June 23, 2000

Thermal Vacuum #2 – Solar Array Cable Wrap Damage