# CONCEPT PHASE

# 3.1  		Introduction

_____________________________________________________________

## 3.1.1	Purpose

The Concept Phase will determine whether an acceptable and cost-effective approach can be found to address the business need with high confidence that technology can support that approach.

The Concept Phase will determine whether an acceptable and cost-effective approach can be found to address the business need with high confidence that technology can support that approach.  The purposes of this phase are to:

- Establish system boundaries, identify goals, objectives, critical success factors, and performance measures,

- Evaluate costs and benefits of alternative approaches to satisfy the basic functional requirements,

- Assess project, technical, and business risks,

- Identify and initiate risk mitigation actions,

- Identify system interfaces,

- Identify basic high level requirements to satisfy the business need,

- Develop high level architecture, process models, data models, and a Concept of Operations, and

- Identify high level electronic records management requirements.

For all AIS projects designated as mission critical, the Program Sponsor must approve high level requirements defined in the Requirements Specification validating that the high level requirements provided therein are complete before a High Level Requirements Review can be conducted.  This phase is completed upon approval of the high level requirements by the Technical Review Board at the High Level Requirements Review, and when the Program Sponsor and the CIO agree to the system boundary.

## 3.1.2	Overview

Following approval of the Business Case, the Concept Phase begins when the Project Manager appoints the project team and the CIO appoints a System Development Manager.  The Program Sponsor, with the assistance of the Project Manager and the System Development Manager, evaluates realistic approaches that address the Business Case and determines which approach will be implemented.  This may involve making several trade-off decisions such as the decision to use COTS software products as opposed to developing custom software or reusing software components, or the decision to use an incremental delivery versus a complete, one-time deployment.

Project Managers and System Development Managers must work with the Office of System Product Assurance to tailor their life cycle processes to the specific needs of their AIS project.

Unnecessary and significant costs will be incurred if too much or too little effort is expended in planning, documenting, or reviewing an AIS project.  A key decision that must be made during the Concept Phase is determining the appropriate level of effort for these activities given the scope, complexity and importance of the AIS under consideration.  Project Managers and System Development Managers must develop the project tailoring and the System Development Manager coordinates with the Office of System Product Assurance during this phase to tailor their life cycle processes to the specific needs of their AIS project.  These tailoring decisions will be reflected in the Concept Brief, the Project Management Plan, and in the Quality Assurance Plan.  The AIS Life Cycle Process Tailoring TSG, IT-212.2-03, provides guidance for LCM tailoring. The Project Manager must ensure that the Project Management, Quality Assurance, Data Management, Operational Support, Test Plans, and the Detailed Design all reflect appropriate levels of security operations and administration.

Depending upon AIS size, scope, complexity, and risk, there may be as many as ten plans and documents initiated during the Concept Phase.  Of these, only eight, the System Boundary Agreement (containing the statement of requirements), the Project Management Plan, the Configuration Management Plan, Data Management Plan, the Quality Assurance Plan, the High Level Architecture, Requirements Specification, and the Concept of Operations are absolutely required for all AIS development projects. These are the only Concept Phase documents that must be completed or have a baseline established before the beginning of the Detailed Analysis and Design Phase. An Economic Analysis is required for all AIS projects that are designated as mission critical.  A Security Plan is required if the system processes sensitive data. The Program Sponsor, in signing the Requirements Specification, Part 1 validates that the high level business requirements are complete.  In approving the Requirements Specification, Part 1, the Technical Review Board, with the assistance of the Office of System Product Assurance, verifies that the high level business requirements provided in the Requirements Specification, Part 1 are clearly expressed.

The Project Manager, the System Development Manager, and the System Architect should work together during this phase to estimate the extent to which COTS products will be used in meeting functional requirements.  If significant use of COTS programming features is anticipated, then the System Development Manager must ensure that appropriate design, operation, testing, and maintenance documentation to adequately support the development of this code is provided for in the Project Management Plan.  The System Development Manager will ensure that requirements, design, development, operation, and testing reviews necessary to adequately support the development of this code are conducted.  The Office of System Product Assurance will ensure that these reviews and documents are specified in the Concept Brief and the Quality Assurance Plan.

During the Concept Phase, the Project Manager and the System Development Manager should also initiate discussions with the Office of Acquisition Management to plan for acquisition and contractor support to the AIS project.

## 3.1.3	Tasks

Many of these tasks can be performed more effectively with the aid of prototyping.  Construction of executable prototypes is encouraged to confirm requirements or to evaluate technology needed to support the business process.

The primary tasks performed during the Concept Phase are as follows:

- Update the business case,

- Establish the system boundary,

- Begin project planning and develop the Project Management Plan,

- Develop the Concept of Operations,

- Determine functional requirements and informational needs,

- Develop the Requirements Specification, Part 1,

- Develop the Quality Assurance Plan,

- Develop the Configuration Management Plan,

- Investigate alternative business processes and procedures,

- Consider data management,

- Identify electronic records management requirements,

- Perform an economic analysis of alternatives,

- Select the most cost-effective alternative,

- Identify, estimate and allocate resources to support project plans and major activities,

- Determine the level of contractor support needed for each major project activity,

- Analyze project risk and initiate risk mitigation activities,

- Define the High Level Architecture, and

- Plan acquisition needs.

Many of these tasks can be performed more effectively with the aid of prototyping.  Construction of executable prototypes is encouraged to confirm requirements, manage risks, or to evaluate technology needed to support the business process.  Prototypes must conform to the USPTO Technical Reference Model.

## 3.1.4	Activities and Documentation

Concept Phase activities and documentation requirements as summarized in the following table must conform to the indicated Technical Standard and Guidelines or other standards as noted.  The Technical Review Board establishes the System Boundary Baseline during this phase.  Section 3.3 of this document and the Configuration Management TSG, IT-212.2-06, provide additional information about the System Boundary.  Published standards and guidelines may be augmented with Tailoring Agreements.

| Work Product | TSG / Standard | Who’s Responsible | Must Create | May Create | Should Update | Must Update | Must Complete |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Business Case |  | Program Sponsor, Project Manager |  |  |  | X |  |
| Project Management Plan | IT-212.2-01 | Project Manager, SDM | X |  |  |  |  |
| AIS Project Quality Assurance Plan | IT-212.2-04 | Office of System Product Assurance | X |  |  |  | X |
| Data Management Plan | IT-212.2-05 | Office of Data Management |  | X |  |  |  |
| AIS Configuration Management Plan | IT-212.2-06 | Office of System Product Assurance | X |  |  |  |  |
| System Boundary Agreement | IT-212.2-10 | Project Manager, System Development Manager | X |  |  |  |  |
| Requirements Specification, Part 1 |  | System Development Manager | X |  |  |  |  |
| Concept of Operations | IT-212.2-11 | Program Sponsor, Project Manager | X |  |  |  |  |
| High Level Architecture | IT-212.2-12 | Office of System Architecture & Engineering | X |  |  |  | X |
| Economic Analysis1 | IT-212.2-13 | Project Manager, System Development Manager | X1 |  |  |  | X1 |
| AIS Security Plan (If sensitive data) | IT-212.2-08 | Project Manager, System Development Manager | X |  |  |  |  |
| NOTE 1: Required for AIS Projects designated as mission critical or whose life cycle costs are greater than $25 million. |

Table 3.1.4 Concept Phase Activities and Documentation Requirements

# 3.2  		Technical Management

_____________________________________________________________

Appointed by the CIO, the System Development Manager is responsible for designing, developing, and deploying an AIS.  The System Development Manager ensures that the AIS is consistent with the agency's strategic information technology plans and is managed according to sound life cycle management principles and practices.  The Project Management Technical Standard and Guideline, IT-212.02-01, describes the responsibilities of the System Development Manager in more detail. In addition, the System Development Manager must:

- Support the Project Manager,

- Coordinate with the Office of System Product Assurance to develop a Quality Assurance Plan,

- Ensure that technical resources are allocated within the constraints of the approved AIS development budget,

- Develop detailed technical plans and schedules, and

- Ensure technical performance and adherence to schedule.

Additional information regarding the roles and responsibilities of the System Development Manager is provided in the paragraph 1.9.5 of this Manual and in the Project Management Technical Standard and Guideline, IT-212.2-01.

# 3.3  		System Boundary

_____________________________________________________________

The system boundary established the context through which the AIS project addresses the requirements expressed in Business Case or equivalent document.  In this sense the development of the system boundary should be considered as a thought process involving several key project management activities and decisions that are usually interdependent and therefore are typically performed concurrently.  These activities include:

- Performing strategic planning,

- Documenting high level requirements,

- Determining feasibility,

- Allocating project resources, establishing a high level project schedule, and

- Stating assumptions about, and constraints imposed on the project by factors outside the Program Sponsor's or Chief Information Officer’s control.

Depending upon project needs and tailoring agreements, system boundary decisions may be recorded in one or several documents.  When all of these activities are treated in a single document, that document is referred to as the “System Boundary Agreement.”  When these topics are treated individually, the system boundary may be expressed in the Project Management Plan, the Requirements Specification, Part 1, and the Concept of Operations document.  Regardless of the approach taken, the System Boundary is developed by the Project Manager, with the assistance of the System Development Manager, and is a signed agreement between the Program Sponsor and the CIO affirming a mutual and sufficiently detailed understanding of project requirements, cost, and schedule.  Additional instructions for developing a System Boundary Agreement are provided in the System Boundary Technical Standard and Guideline, IT-212.2-10.

# 3.4  		Project Planning

_____________________________________________________________

## 3.4.1	Developing the Project Management Plan

The Project Management Plan serves as a management tool to direct and monitor the progress of system definition, design, development and deployment.  The Project Manager, with the assistance of the System Development Manager and the Director, Office of Technical Plans and Policy prepares the Project Management Plan at the beginning of the Concept Phase and revises this plan as necessary, throughout this phase and throughout the life of the project.  The Project Management Plan is approved by, and periodically reviewed by both the Program Sponsor and the CIO.  The Project Management Plan is also inspected by the Technical Review Board as part of a technical review to ensure that it accurately reflects technical, cost and schedule performance.  A sample Project Management Plan is provided in the Project Management Technical Standard and Guideline, IT-212.2-01.  Contractors may prepare components of the Project Management Plan, but are prohibited from determining requirements, and from assigning roles, responsibilities, or authority.

## 3.4.2	Developing the Concept of Operations

The Concept of Operations provides organization and business process information.  The Concept of Operations provides a high level description of how an organization currently performs its work, how it will perform its work in the future, what people and organizational changes will be required, and what risks are associated with the new or modified AIS. This document also provides a text-based description of business processes within the system boundary and establishes a transition process through which common definitions regarding the current and future business process are documented and managed.

The Project Manager is responsible for developing the Concept of Operations and may be supported by a team of business area experts, as well as experts from other areas such as Human Resources or Facilities.  This team defines, develops and documents the current and future business process using textual descriptions, and activity models, process maps, or other tools as appropriate.  The Program Sponsor approves the Concept of Operations and ensures that the necessary business policies, procedures, and resources are provided to the process improvement effort in an adequate and timely manner.  Refer to the Concept of Operations Technical Standard and Guidelines, IT-212.2-11, for additional details on preparing a concept of operations.

## 3.4.3	Developing High Level Requirements

High level requirements are contained in the System Boundary Agreement and the Requirements Specification, Part 1.  These requirements are based upon opportunities identified in the Business Case or equivalent document and represent a preliminary translation of business requirements into logical data and logical process models.  These logical models represent only the essential concepts needed to address a business need and, by intention, do not address technical performance or physical design considerations.  The purpose of this translation is to ensure that the project team has a clear understanding of the over-all business requirement that will be implemented before embarking upon detailed analysis and technical design.

High level requirements are expressed as high level entity relationship data models, high level business function decomposition diagrams, high level business process models, business rules and procedures, and other enterprise information.  These requirements are deduced from documents such as the System Boundary or the Concept of Operations, and through focus sessions with business area experts.

In many situations it will be advantageous to use automated tools to develop, record, and manage high level requirements. There are a variety of tools available to assist in performing this function, ranging from simple word processors, spreadsheets, and desktop database tools to sophisticated integrated information engineering, and requirements management packages, such as the Requirements Traceability Tool.  In selecting the most appropriate tools to perform this task, the System Development Manager should consider the scale, target environment, available resources, available skills, schedule constraints, system integration requirements, AIS implementation tools and consistency with the Technical Reference Model.

The standard OCIO requirements management tool must be used whenever practical.  The Office of System Product Assurance will provide technical support to the project in the use of this tool.  When it is not practical for the AIS project to use the OCIO standard tool, the Office of System Product Assurance will copy project requirements into the standard requirements management tool.

The following items must be reflected both in the system boundary, the requirements specification, and in the subsequent designs that are derived from these requirements:

- The purpose of the system including goals, objectives, and critical success factors,

- Performance measures that are meaningful to the Program Sponsor and end user,

- Functional needs, as perceived by the user from the business area(s) supported, captured as requirements by business area experts (these requirements are used as the basis for determining feasible alternatives),

- Assumptions and constraints concerning the business environment within which the system will operate, including legal, security, facility, and labor or work-flow considerations,

- Assumptions and constraints concerning the technology that may be used, such as conclusions from technology impact analysis, user interfaces, use of the information technology infrastructure, and waivers, and

- Assumptions and constraints concerning execution of the project, including the budget, schedule, project facilities, acquisition considerations, completion criteria, and the system development process.

High level requirements initially appear in the System Boundary Agreement and are more fully represented in the Requirements Specification, Part 1.  Guidance for documenting high level requirements is provided in several Technical Standards and Guidelines including the:

- System Boundary , IT-212.2-10,

- Requirements Management, IT-212.3-11, and

- AIS Life Cycle Process Tailoring, IT-212.2-03.

## 3.4.4	Developing the Quality Assurance Plan

The purpose of quality assurance planning is to ensure that project activities are visible and appropriately supported, and that project plans and work products, including information engineering models and diagrams, contribute to the delivery of an AIS product that is fit for use and meets customer expectations.  The Quality Assurance Plan is initially developed, approved and implemented during the Concept Phase to support this objective.  This plan identifies the standards and polices that will apply, identifies the specific work products to be delivered, and establishes the type and schedule of reviews to be conducted in developing or enhancing an AIS.

The Quality Assurance Plan is developed based on the Concept Brief, System Boundary, and the Project Management Plan.  These documents determine project size and scope and allocate project resources including support for quality assurance activities.  These documents also serve as the basis for tailoring decisions and agreements that are recorded in the Concept Brief and Quality Assurance Plan.  These decisions and agreements are intended to establish and document, at an appropriate level of detail, project management, design, development, testing, and support activities.  Analysts within the Office of System Product Assurance will assist the System Development Manager by preparing the Quality Assurance Plan.  The Project Manager addresses specific quality assurance issues relating to the customer workforce.  These issues are outside the scope of the Quality Assurance Plan.  The Quality Assurance Plan is prepared by the Office of System Product Assurance, reviewed by the System Development Manager, and is approved by the Technical Review Board as part of the High Level Requirements Review.  This plan is updated and reviewed at each phase of the life cycle.  Additional guidance on tailoring is provided in the AIS Life Cycle Process Tailoring Technical Standard and Guidelines, IT-212.2-03.  Additional guidance on quality assurance planning is provided in the Quality Assurance Technical Standard and Guideline, IT-212.2-04.

3.4.5 	Developing Electronic Records Management Requirements

It is appropriate at this stage for the system development manager and appropriate business users to begin assessing high level requirements in 13 electronic records management areas.  Not all areas of consideration apply to all AISs.  When this is the case, the particular Electronic Records Management (ERM) requirement area should be noted as not applicable to those AISs.

- Records Acquisition, which includes capture of complete electronic records, links to notes and annotations, hyperlinks, and working files, conversion of paper records to electronic form, quality control, quality assurance, and audits of the document capture process.

- Record Metadata, which addresses metadata management and record profile metadata.

- File Management, which covers physical and referential integrity protection.

- Preserve Integrity, which addresses protection against alteration and validating integrity.

- Protect Confidentiality, to ensure that information is not disclosed or revealed to unauthorized persons.

- Access Controls and Authentication, which covers identification and validation of identity.

- Search, Retrieval and Reproduction, which covers such issues as search and retrieval, storing search results, displaying and printing records with indices and annotations, and access privileges.

- Audit Trail, to address use history profiles, their creation and update, and links to other information system tracking or event logging systems.

- Vital Records Backup and Recovery, to cover policies and procedures for disaster recovery.

- Records Retention, which covers retention content, periods, schedules, and disposal procedure.

- Migration, to address the accessibility and transferability of electronic records despite changes in information technology and including copy, reformat, and transfer procedures as well as media management.

- Transfer to Permanent Archival Storage, which describe policy and procedure for long-term retention.

- Records Hold, which covers steps for holding records when litigation, audit or investigation is foreseen.

More detail describing these electronic records management requirement areas can be found in the technical note, “Electronic Records Management:  Checklist for Automated Information Systems.”

# 3.5  	Defining the High Level Architecture _____________________________________________________________

## 3.5.1	The System Architect’s Role

The Office of System Architecture and Engineering (OSAE) defines and evolves the USPTO-wide information technology infrastructure architecture, ensuring the proper development of that infrastructure while continuing to implement necessary upgrades and integrate applicable new technology.  OSAE evaluates and incorporates emerging technologies, standards, and products into the infrastructure Technical Reference Model and develops and/or reviews and approves technical architectural designs for automated information systems.   Principal focus areas include controlling the migration to an open systems environment, implementing adequate security measures, upgrading the performance and reliability of infrastructure components, establishing information technology standards, leveraging internet technologies to support USPTO business functions, and establishing remote access capabilities.  Additional information regarding the role of the system architect, AIS high level architecture, and detailed design can be found in the High Level Architecture TSG (IT-212.2-12).

## 3.5.2	Evaluating Commercial Off-the-Shelf Software

“COTS” or “off-the-shelf” software, if used effectively, can significantly reduce AIS delivery time and development costs.  System Development Managers should use COTS software whenever feasible.  In determining feasibility, AIS managers must make several difficult trade-off decisions in selecting and using a COTS approach.  These decisions will have significant, long-term impact on the cost for developing and operating the AIS.  The Project Manager, the System Development Manager, and the Systems Architect must carefully consider the benefits and disadvantages of using COTS software products when preparing an economic analysis or designing a high level architecture.

The benefits and costs associated with using COTS software must be identified in terms of several key characteristics including uses, packaging, and acquisition agreements.  This will allow managers to better understand the costs associated with acquiring a COTS solution, and will also assist in determining the costs of activities associated with the integration, maintenance, and operational support of COTS products.

There are at least five major ways COTS can be characterized according to use:

- Office automation systems (e.g., word processing, spread sheets, presentation tools, electronic mail).

- Application systems (e.g., human resources, financial management, payroll, project management).

- AIS production support packages (e.g., data base management systems, document management systems, report generators, search tools, work flow).

- System and network management (e.g., operating systems, help desk tools, software distribution tools, system performance monitors, security tools, network monitors).

- System analysis, design, and development and maintenance tools (e.g., I-CASE tools, compilers, test tools, configuration management, requirements management, and data modeling).

There are at least three ways COTS can be classified in terms of packaging:

- Highly specialized software modules (e.g., image viewers, bar code printing drivers),

- Groups of interrelated software functions that the manufacturer integrates into software environments (e.g., windows, desk-tops), and

- Turnkey products (e.g., high speed image capture scanners and software, point of sales registers and software).

It is also important to consider the terms and costs for COTS acquisition such as:

- Types of support service vendor provides (e.g., training, special modifications, consulting, remote diagnostics),

- Pricing structure (e.g., site licensing, upgrade pricing, support costs, volume discounts),

- Composition (e.g., incremental acquisition of functional components, bundling/unbundling of options), and

- Product format (e.g., source code, executable code, or network service provider).

## 3.5.3	Benefits of Using COTS Software

A major advantage of COTS software products is that these products come already developed and tested.  Frequently, a large number of commercial customers are able to use and evaluate specific COTS products in an operational environment, and based upon their experiences, provide constructive comments to the manufacturer.  As a result, COTS products come with many practical, user-driven, enhancements included.  This translates into an immediate gain in functionality, usability, and reliability.  Also, because a large number of commercial users share in the total costs to develop, market, distribute, and support COTS products, vendors are able to keep unit costs to a level that is affordable to the individual customer.

## 3.5.4	Disadvantages of Using COTS Software

No COTS solution provides all, or the exact business functionality that the user needs.  A comprehensive solution to a business area requirement may require that integrated COTS approaches be supplemented with in-house software.  Generally, COTS products are difficult to modify internally.  When the only alternative is to modify a COTS product, it is usually at significant risk to the vendor and, as a result, great cost to the customer.  The System Development Manager must be aware of the costs, time, and level of effort necessary to select and integrate COTS software into the overall AIS.  Due to issues relating to the cost of flexibility, compatibility, functionality, or control over source code, the System Development Manager may determine that the most economically feasible way to address a requirement is through in-house development.

## 3.5.5	Selecting an Approach

The System Development Manager must be aware of several key factors when deciding whether to develop software in-house or whether to purchase and integrate a COTS product.

- Business Focus and Potential for Reuse  --  if there is a reasonable chance that the needed AIS functionality is reusable on several other applications then it may become very practical to develop this functionality in-house.  Reuse provides almost all the benefits expected of COTS products such as labor and development cost savings, and rapid implementation, plus many of the benefits expected from software developed in-house including flexibility and controllability.  The System Development Manager must ensure that all reusable components, including requirements, specifications, and designs are placed in a CM repository for reuse.

- Compatibility with the Technical Reference Model  --  if the only COTS products needed and currently available are incompatible with the Technical Reference Model, then the System Development Manager should consider developing an in-house approach that is compatible with the Technical Reference Model.

- Cost of Integration and Maintenance  --  Integration costs may be higher for COTS products, while maintenance cost will be higher for in-house development.  However, both in-house developed functionality and COTS provided functionality will have full life cycle costs.  Poor performance by the manufacturer in designing, developing, testing, and supporting COTS products will result in higher costs to the AIS development organization.

- Reputation, Market Share, and Quality of Manufacturer Services  --  System Development Managers must consider the long term viability of COTS software. Software firms that stand behind their products, look to establishing a long term presence in their markets, and look to increasing market share will provide COTS products to their customers that are less costly to operate, enhance, and maintain.  This does not mean that there will not be problems from time to time.  It just means that software firms that do not live up to customer expectations will eventually suffer loss of credibility in the market.  This in turn provides some indication of the long-term costs the AIS project will incur for COTS maintenance, enhancement, integration, and support.

3.6  	Assessing the Information Technology Investment

_____________________________________________________________

Each AIS project must be evaluated in the context of the portfolio of all AIS projects to ensure that there is a strong business case for developing and deploying the new capability.

When the USPTO spends money on information technology, it is an investment in improving the quality and value of the agency’s business performance.  Senior management must assess the business worth of an AIS project in terms of the changing needs of the business, and in terms of advances or changes in technology or services.  Moreover, each AIS project must be evaluated in the context of the portfolio of all AIS projects during the strategic information technology planning process to ensure that there is a strong business case for developing and deploying the new capability.

When making an information technology investment, the Program Sponsor and CIO must be in agreement that project expectations are realistic and achievable.  This agreement, documented as part of the system boundary, must be revisited and reaffirmed several times throughout the life of an AIS project.  If there are any significant changes in business requirements, project resources, or project schedule, the system boundary and supporting economic analysis must be revised.

To help determine whether the AIS project is a worthy investment and to identify the preferred approach, the Project Manager, with the assistance of the System Development Manager, identifies and evaluates various alternative approaches.  This systematic process, called an economic analysis, compares the costs and benefits of alternatives that are potentially feasible.  An economic analysis must be prepared for each AIS project designated as mission critical.  There must be at least two feasible alternatives considered in the economic analysis - the current system and the proposed system(s). The Economic Analysis Technical Standard and Guideline, IT-212.2-13, provides guidance for preparing an economic analysis.

# 3.7  		Project Risk Management

_____________________________________________________________

The Project Manager must continually identify AIS project risks and identify ways to reduce these risks to acceptable levels.  During the Concept Phase these risks are primarily concerned with establishing a realistic commitment to addressing AIS project requirements and obtaining the resources necessary to achieve project goals.  The Project Manager will advise the Program Sponsor, the CIO, and the Systems Development Manager on matters of significant risk and will coordinate risk management activities with key managers and analysts based upon their ability to control risk.

## 3.7.1	Project Risk Assessment

The intent of this guideline is to establish a level of project risk assessment, planning, and management that is appropriate to the nature of the work that is expected to be performed using the AIS.

Continual analysis of the existing project situation will be conducted to identify significant AIS project risks.  Primary consideration will be given to identifying business and project risks, including major uncertainties in specifying or satisfying system boundaries (i.e., requirements, costs, and schedule).  Some of the most common business and project risks encountered in the Concept Phase are associated with:

- Replacement of key managers or loss of sponsorship,

- Loss of funding,

- Change in mission,

- Reorganization, and

- Unclear leadership structure and back-up process for key personnel.

The Project Manager and the System Development Manager will identify all significant business and project risks to the best of their ability.  These managers will estimate and evaluate significant business and project risks, and will provide some brief discussion of pragmatic approaches they might take should any of these risks materialize into a situation that could adversely impact the project. There are three major sources of project risk that the Project Manager must consider:

- Availability of detailed and complete project information,

- Sufficient project time and project resources, and

- Sufficient project control.

The intent of this guideline is to establish a level of project risk assessment, planning, and management that is appropriate to the nature of the work that is expected to be performed using the AIS.  Excessive, duplicative, or unnecessary risk management should be avoided.  Project Managers and System Development Managers are encouraged to reuse or adopt already existing risk management practices, policies, procedures, and mechanisms whenever practical.  It is vitally important that the Project Manager is fully aware of business and project risks in terms of actual damage, cost of prevention, and cost of corrective measures.  Information used to identify, estimate, and evaluate significant risks will be documented.

## 3.7.2	Project Risk Review and Mitigation

The Project Manager presents project risk assessment findings to the Program Sponsor, Technical Review Board, or the CIO, as needed during the course of the AIS project.

Risk considerations will be part of normal business and will reaffirm the significance of risks.  To illustrate, risks associated with the High Level Architecture should be identified and presented during the High Level Requirements Review.  The Project Manager should solicit management support for addressing significant risks.  Based upon the recommendations of the Project Manager, the Program Sponsor or the CIO may assign additional staff or allocate additional resources to reduce or avoid significant risks.  Additional guidance for managing project risk can be found in the risk management section within the Project Management TSG (IT-212.2-01).

# 3.8  		AIS Security

_____________________________________________________________

While USPTO, OCIO, and issue-specific security policies address security from a broad perspective, the formulation and full implementation of these policies is independent of the life cycle and generally beyond the control of any individual project manager.  As a rule, these organizational security policies do establish general security goals and objectives, but they do not provide sufficient information or direction necessary to implement specific AIS security measures.  For this reason, the Project Manager must consider project level security planning for each AIS project and/or PTOnet infrastructure project.  The Project Manager must work closely with the security analysts in the Office of Information Systems Security (OISS) to accomplish project level security planning.

The processes of security planning and risk management share many common activities and purposes.  For example, a collateral benefit derived from analyzing and managing risks, is that project managers are aware of AIS assets (e.g., data, hardware, software, facilities, etc.) and are able to anticipate specific events that could compromise the integrity of those assets, render those assets unavailable to the end-user, or render those assets unfit for service.  Risk assessment and management also provides project managers with an understanding of functional and technical management’s willingness to accept a broad range of risks, including security risk.  Based upon this knowledge, project managers are able to develop cost-effective project-level security plans, policies, and procedures that meet business needs.

Some of the most commonly thought-of AIS security issues include:

- AIS back-up, contingency, and disaster recovery,

- Data center security planning,

- Security test and evaluation, and

- Security certification and accreditation or interim authority to operate.

## 3.8.1	Concept Phase Security Activities

Like most other aspects of AIS life cycle management, security is most effective and efficient if planned and managed throughout the AIS life cycle.  During the Concept Phase, the System Development Manager develops early conceptual designs of anticipated AIS security features.  Typically, due to the fact that the AIS is early in its life cycle, these designs are not supported by detailed requirements but are based upon a common sense understanding or “sensitivity assessment” of the business and the underlying security needs.

## 3.8.2	Sensitivity Assessment

A sensitivity assessment looks at the value of AIS data/information and the AIS itself to USPTO.  This assessment should consider financial impact, legal implications, USPTO policy (including federal and Department of Commerce policy), and the functional needs of the business.  Sensitivity is normally expressed in terms of integrity, availability, and confidentiality.  Project management must consider such factors as the importance of the AIS to USPTO’s mission and the consequences of unauthorized modification, unauthorized disclosure, or unavailability of AIS information when assessing sensitivity.  To address these types of issues, it is essential that those USPTO business partners who will use the AIS participate in this assessment.

In performing a sensitivity assessment, project management must address the following questions:

- What information is handled by the system?

- What kind of potential damage could occur through error, unauthorized disclosure or modification, or unavailability of information or use of the AIS?

- What laws or regulation affect security (e.g., The Privacy Act or the Fair Trade Practices Act)?

- To what threats is the AIS or AIS information particularly vulnerable?

- Are there significant environment considerations (e.g., hazards associated with AIS location - for example, next to an airport or railroad office)?

- What are the security-relevant characteristics of the AIS end-user community (e.g., level of computer or AIS sophistication and training, security clearances, etc.)?

- What internal security standards, regulations, or guidelines apply to this AIS?

The sensitivity assessment starts an analysis of security that continues throughout the life cycle.  The assessment helps determine if the AIS project needs special security considerations, if further analysis is needed before committing to begin the next phase of the LCM (to ensure feasibility and reasonable cost), or in rare instances, whether the security requirements are so strenuous and costly that system development or acquisition will not be pursued.  The sensitivity assessment can be another planning document or may be combined with the System Boundary Agreement, Requirements Specification, or Project Management Plan according to tailoring agreements reached between AIS project management and the Office of System Product Assurance.

# 3.9  		Acquisition of Information Technology Resources

_____________________________________________________________

Acquiring information technology resources is often a difficult task that requires knowledge, experience, the ability to work effectively with people, good judgment, and common sense.  The process is mandated by regulations designed to ensure that USPTO acquires only what is needed, and that USPTO considers and makes use of existing resources, including Department of Commerce and other agency programs and contracts.  When a procurement action is determined to be appropriate, the acquisition process attempts to ensure full competition among vendors and to prevent abuses.  USPTO strategies for acquiring information technology products and services are contained in the most recent version of the Strategic Information Technology Plan.  All AIS managers should have a fundamental grasp of federal, departmental, and USPTO Information Resource policies and procedures.

AIS project managers must coordinate with the Office of Acquisition Management throughout the AIS life cycle to acquire information technology products and services.  The goals of acquisition management are to ensure that:

- The information technology is appropriate to the needs of the organization,

- Procurements are consistent with the Technical Reference Model and the overall architectural concept,

- Information technology components are interchangeable and interoperable,

- Information technology procurements are performed according to Federal acquisition laws and regulations,

- Information technology procurement plans are well documented,

- Information technology procurement plans encourage small business participation,

- Procurements rely on GSA schedules and government-wide contracts, and

- Procurements enable contractor end-to-end responsibility.

The Office of Acquisition Management directs the acquisition of information technology hardware, software, and support services.  This office ensures that information technology acquisitions are conducted in a manner that is consistent with USPTO's strategic information technology plans. The Office of Acquisition Management provides acquisition management support services, including Contracting Officers' Technical Representatives functions for USPTO-wide information technology support service contracts. The Office of Acquisition Management also advises and assists in the administration of other information technology contracts.

# 3.10  	Project Management Plan Update

_____________________________________________________________

The Project Manager must update the Project Management Plan in preparation for the High Level Requirements Review.  This update will include a refinement of the project schedule with special emphasis on the Detailed Analysis and Design Phase.  This update must also include completion of initial plans for AIS development, configuration management, quality assurance, security, risk management, and data management prepared in accordance with the applicable Technical Standards and Guidelines.  The Technical Review Board must review and approve the updated Project Management Plan before the System Development Manager can officially begin the Detailed Analysis and Design Phase.

# 3.11		Concept Approval

_____________________________________________________________

## Project Manager and System Development Manager

#### Evaluate Documentation

The Project Manager and the System Development Manager evaluate the System Boundary Agreement, Project Management Plan, Quality Assurance Plan, Concept of Operations, Security Plan, Data Management Plan, Configuration Management Plan, Requirements Specification, Part 1, High Level Architecture, and all supporting initiatives and plans and assess the following:

- Conformance to requirements and business needs,

- Conformance to standards and guidelines, and

- Technical and economic feasibility.

Based upon the findings of this evaluation, the Project Manager and the System Development Manager will submit these plans to the Technical Review Board for approval at the High Level Requirements Review.

## 3.11.2	High Level Requirements Review

Before beginning analysis to elaborate detailed requirements, the Project Manager will ensure that the project team and the users who generated those requirements reach consensus on their interpretation.

Before beginning analysis to elaborate detailed requirements, the Project Manager will ensure that the project team and the users who generated those requirements reach consensus on their interpretation.  A technical review will be conducted in accordance with procedures in IT-212.2-04, Quality Assurance, to provide a basis for support planning in the Detailed Analysis and Design Phase and to establish the foundation for technical reviews throughout the remainder of the AIS life cycle. The Concept Phase is completed upon approval by the Technical Review Board at the High Level Requirements Review and the Program Sponsor and CIO agree to the system boundary.

# Footnotes

The Concept of  Operations is prepared by the Project Manager and summarizes business structure, policies, procedures, and anticipated changes to the business organization.  This document describes how the business area organization is currently structured, how it currently performs work, and how this organization may be structured in the future.  The Concept of Operations also describes what new processes will be used to perform work in the future, and compares business process alternatives in terms of impact and risk to the organization.

The Requirements Specification is organized into high level and detailed level requirements.  Part 1 of the Requirements Specification (Sections 1, 2, 3.2, 3.2.1, 3.2.2, 3.3, and 3.3.1) documents the high level requirements and Part 2 (the remaining sections of the specification), documents the detailed level requirements.

The project team is responsible for assisting the Project Manager in identifying detailed business requirements, and addressing end-user issues regarding planning, requirements validation, training, logistics, facilities, and end-user acceptance testing.

A High Level Architecture (HLA) defines the integration of business processes, data models,  application software, and common information technology infrastructure components.  The AIS High Level Architecture is a refinement of the Concept of Operations that symbolically describes the business functions, activities, and information flows that the AIS will provide or support.  The HLA also describes the implementation of the AIS within the operational environment by providing textual and graphical descriptions of AIS hardware, software, and network components, and by illustrating the interconnections between these components.  The HLA is refined during the Detailed Analysis and Design Phase and is the basis for preparing the Detailed Design.  Additional information regarding technical architecture can be found in the Technical Architecture TSG (IT-212.2-12).

The Office of Technical Plans and Policy coordinates project planning, project reviews, and associated program oversight and project monitoring activities; administers baseline project plans; and manages the automated Project Control and Analysis Tool for project tracking; coordinates the development and implementation of agency-wide information technology policy; annual strategic and operational technology plans; and supporting budget submissions.

The Project Manager should exercise care to differentiate between project risk analysis and security risk assessment.  Many AIS projects analyze the risk of failing to successfully complete the project -- a different activity from security risk assessment.  Though both activities share many common traits and underlying principles, security risk assessment focuses more upon ensuring the integrity, availability and confidentiality AIS components including business information and business processes.

Based upon the recommendation of the Project Manager and the System Development Manager, the CIO may grant a security certification and accreditation or an interim authority to operate at the end of the Development Phase.

These early conceptual designs are informal and are simply used to facilitate the development process in much the same manner that prototypes are used.  These designs will be further modified, refined, and formalized as firm requirements are identified and developed.

The definition of sensitive is often misconstrued.  Sensitive is synonymous with important or valuable.  Some information is sensitive because it must be kept confidential.  Much more information, however, is sensitive because its integrity or availability must be assured.  The Computer Security Act and OMB Circular A-130 state that information is sensitive if its unauthorized disclosure, modification (i.e., loss of integrity), or unavailability would harm the agency.  In general, the more important a system is to the mission of the agency, the more sensitive it is.