|  |  | Federal Aviation Administration |
| --- | --- | --- |
|  |  | Fully Releasable POC: Kip Spurio Version 2.0 September 08, 2006 |
| Concept and Requirements Definition Guidelines Air Traffic Organization Operations Planning Service Systems Engineering NAS Architecture Group |  |

Table of Contents

1	Introduction	3

2	Overview of Concept and Requirements Definition	3

3	Plan for CRD	5

3.1	Develop the CRD Plan	5

3.2	Form CRD Team	5

4	Initiate CRD	6

5	Conduct Detailed Shortfall Analysis	7

6	Analyze Operational Functions	7

7	Develop Range of Alternatives	8

8	Develop Safety Risk Management Decision Memo	9

9	Develop Concept(s) of Use	9

10	Develop Preliminary Requirements	10

11	Estimate Rough Order Lifecycle Cost	11

12	Develop Enterprise Architecture Products and Amendments	12

13	Conduct Technical Review	12

14	Conduct Financial Review	13

15	Plan for Investment Analysis	13

16	Prepare for Investment Analysis Readiness Decision	13

Appendix A: Template for the Concept and Requirements Definition Plan	15

Appendix B: Template for the Shortfall Analysis Report	22

Appendix C: Template for the Functional Architecture	27

Appendix D: Template for the Alternative Descriptions	31

Appendix E: Template for the Investment Analysis Readiness Decision Briefing	36

Appendix F: Definitions and Acronyms	38

# Introduction

This document describes the activities of the concept and requirements definition (CRD) phase of Federal Aviation Administration (FAA) mission analysis.  It will be maintained and hosted on the FAA Acquisition System Toolset (FAST) website (http://fast.faa.gov ).  Revisions and additions will be made periodically to incorporate lessons learned and process improvements.  This document currently represents only one segment of an overall mission analysis process document that is planned to be released at a later date.

The guidelines and specific procedures described in this document generally apply to all FAA organizations seeking an investment decision.  However, the guidelines do not apply to the Airport Improvement Program.  Additionally, initiatives dealing with technologies which are not commercial off the shelf (COTS) solutions ready for implementation must follow the appropriate research guidelines before entering into CRD.

CRD is meant to be flexible; and it is recognized that some steps may be conducted concurrently or iteratively.  Under exceptional circumstances, the FAA Acquisition Executive (FAE) may waive some of the activities.  All lines of business (LOB) must coordinate their CRD activities with the appropriate systems engineering organization to ensure consistency with the FAA Enterprise Architecture (EA).  The FAA EA defines the operational and technical framework for all capital assets of the FAA.  It describes the agency’s current and target architectures, as well as the transition strategy for moving from the current to the target architecture.  The EA is approved annually by the Joint Resources Council (JRC) in support of budget and strategic management processes.  The Office of Operations Planning (ATO-P) Systems Engineering provides advice on National Airspace System (NAS) Operations EA initiatives and the Office of Information Services (AIO) provides advice on Mission Support and Administrative EA initiatives.

# Overview of Concept and Requirements Definition

The CRD phase of mission analysis follows service analysis. Service analysis is an annual, cyclic process at the service organization level that first conducts and then keeps current a service-level mission need assessment (SLMNA). The SLMNA is developed within the context of, and is incorporated into, the EA.  When the EA specifies the need to start a specific investment opportunity to meet a priority service need, CRD begins with development and approval of the plan for CRD. CRD is the start of the lifecycle management process for a specific investment initiative. The purpose of CRD is to ensure readiness for investment analysis. Readiness is based on development of sound and measurable preliminary requirements; a concept of use acceptable to the user; a viable set of alternatives that would satisfy the need; and the availability of resources to conduct investment analysis.  Figure 2-1 shows the normal set of CRD activities that will be followed for all proposed investment analyses (except when any type of waiver has been approved).

The following products are required for initiation of CRD:

- Approved SLMNA/EA Roadmap

- FAA EA changes

- Functional Architecture

- CRD Plan.

These products are completed during service analysis.  See Section 3 for a description of the CRD Plan.

Due to the breadth and scope of CRD activities, multiple service organizations may participate in CRD activities and contribute resources (people and funds) to ensure quality products are produced.  The Office of Operations Planning (ATO-P) Systems Engineering is responsible for providing oversight and guidance throughout CRD, leading up to an investment analysis readiness decision (IARD).

The ATO Chief Operating Officer or Associate Administrator (non-ATO) of the LOB makes the IARD and authorizes entry into investment analysis or makes other disposition such as returning the need to CRD or directing research activity to reduce risk. The investment analysis begins immediately after a successful IARD.

Figure 2-1. Concept and Requirements Definition

# Plan for CRD

This section begins to describe CRD activities that lead up to the investment analysis readiness decision. Two pre-CRD activities must take place prior to the official start of CRD: (1) a CRD Plan must be developed and approved; and (2) the CRD Team must be formed. Subsequent sections of this document describe the activities that occur during CRD.

## Develop the CRD Plan

The ATO-P Systems Engineering organization will work collectively with the service organization and other organizational elements to develop a plan for completing CRD activities to achieve proposed or required deadlines for the investment analysis readiness decision.  The CRD Plan specifies the deliverables, tasks, schedules, organizational roles and responsibilities, and resources needed to successfully complete CRD.  Specific roles and responsibilities of CRD team members are specified in the CRD Plan as agreed to by the service organization, ATO-P Systems Engineering, and affected organizational elements. The Plan will also include as attachments:  definition of any required analyses and a legacy system description (if applicable). The expected time frame for completing CRD is two to five months. The ATO Vice President or Director (non-ATO) of the service organization with the mission need and operating service organization(s) approve the CRD Plan after coordination with affected organizations. The CRD Plan is to be developed in accordance with Section 4.2 of the System Engineering Manual. Appendix A of this document provides a template for the Plan.

## Form CRD Team

The ATO-P Systems Engineering organization appoints a CRD Team Lead who is responsible for advising the service organization in developing the CRD Plan. The CRD Team Lead will identify and obtain commitment of the requisite team members to facilitate the development of each of the necessary deliverables to be produced during CRD, monitor and participate in their development, and ensure that major milestones are specified in the approved CRD Plan.  Table 3-2 identifies generic roles and responsibilities for each of the deliverables to be produced during CRD.

Table 3-2. Generic Roles and Responsibilities for CRD Activities

| Task | Responsible Lead | Participants |
| --- | --- | --- |
| Plan for CRD | Joint effort between Service Organization & CRD Team Lead | Office of Information Services (AIO) SE as appropriate |
| Initiate CRD | CRD Team Lead | CRD Team |
| Conduct Detailed Shortfall Analysis | Service Organization | ATO-P Strategy and Business Planning Organization: Operations Research |
| Analyze Operational Functions | Service Organization | ATO-P SE: NAS Operations Concepts and Service Engineering / AIO SE |
| Develop Range of Alternatives | Service Organization | ATO-P NAS Architecture / AIO SE |
| Develop Concept(s)of Use | Service Organization | ATO-P SE: NAS Operations Concepts and Service Engineering / AIO SE (non-ATO)/ ATO-P Human Factors (HF) |
| Develop Preliminary Requirements | Service Organization | Participating Service Organizations / ATO-P SE NAS Requirements and Interface Management (ATO projects)/ AIO SE (non-ATO projects)/Safety Services/ATO-P Security Advisors/ATO-P HF |
| Estimate Rough Order Lifecycle Costs | Service Organization | ATO Finance (ATO-F) Investment Planning and Analysis |
| Develop Enterprise Architecture Products and Amendments | Service Organization | ATO-P NAS Architecture / AIO SE |
| Conduct Technical Review | System Engineering Council | CRD Team |
| Conduct Financial Review | ATO-F | CRD Team |
| Plan for Investment Analysis | Service Organization | ATO-F Investment Planning and Analysis |
| Prepare for IARD | CRD Team | CRD Team |

# Initiate CRD

The CRD Team Lead plans and holds a kick-off meeting. The kick-off meeting is the official start of the CRD.  CRD meeting minutes are provided to all affected personnel.

Responsible Agent:  CRD Team Lead.

Product:  Kick-off meeting; CRD meeting minutes.

Approving Agent:  NA.

Supporting Tools and guidance: CRD Plan; System Engineering Manual (SEM) (http://www.faa.gov/asd/SystemEngineering).

# Conduct Detailed Shortfall Analysis

The service organization will quantify the priority infrastructure or service shortfall in the EA and its impact on service capability in sufficient detail to serve as the basis for determining realistic and economic alternative solutions to the service need, developing a concept of use, and defining preliminary program requirements.  This detailed shortfall analysis is also the basis for quantifying likely program costs and benefits during investment analysis.  The service organization will work with the ATO-P Operations Research (OR) to quantify the shortfalls.  The service organization will work with the ATO Finance (ATO-F) Investment Planning and Analysis (IP&A) organization to quantify the shortfall whenever the shortfall analysis involves cost avoidance and also to refine the legacy case.  The information regarding data, assumptions, and methodology used to generate shortfall estimates, as well as the legacy case, may be captured in a Shortfall Analysis Report (SAR).  Appendix B provides a template for the SAR.

Responsible Agent:  Service organization with advice from ATO-P OR and ATO-F IP&A.

Product:  SAR; Legacy Case.

Approving Agent:  Service organization.

Supporting Tools and Guidance:  SAR Template (See Appendix B).

# Analyze Operational Functions

The ATO-P SE National Airspace System (NAS) Operations Concepts and Service Engineering organization completes an analysis of operational functions during service analysis. During CRD the service organization will provide a further refinement of the functional analysis that began in service analysis. The analysis translates user needs and human performance (capabilities and limitations) into a sequenced and traceable Functional Architecture. The Functional Architecture captures the functions and sub-functions necessary to provide the needed service or operational capability.  The approach is to analyze what must be done without defining specifically how to do it.  The Functional Architecture is the foundation for the Preliminary Program Requirements.  The functional analysis is performed in accordance with Section 4.4 of the System Engineering Manual (SEM).

The Functional Architecture will be documented for use in investment analysis.

Responsible Agent:  Service organization with advice from ATO-P SE NAS Operations Concepts and Service Engineering.

Product:  Functional Architecture.

Approving Agent:  Manager, service organization with concurrence from Manager, ATO-P SE NAS Operations Concept and Service Engineering or the FAA EA Chief Architect (for non-NAS initiatives).

Supporting Tools and Guidance: Functional Architecture template (Appendix C); SEM (http://www.faa.gov/asd/SystemEngineering).

# Develop Range of Alternatives

The service organization working with the systems engineering and Research, Engineering, and Development (RE&D) organizations -- develops a set of feasible alternatives to resolve the mission shortfall(s).  Alternatives must:

Satisfy the capability shortfall (Alternatives may not meet 100 percent of preliminary requirements.)

Have a positive impact on FAA performance metrics.

At least one alternative comes from the Enterprise Architecture (EA). The market place is surveyed to identify additional feasible and economic alternatives to service need. Both material and non-material opportunities are evaluated. Key factors to consider are operational cost efficiencies (particularly those related to telecommunications and information systems security), technological maturity, and impact on the EA.  Alternatives should be qualitatively different from each other; for example, airborne-based vs. ground-based, satellite-based vs. ground-based, traditional system acquisition vs. service acquisition, etc.; so that maximum creativity, flexibility, and innovation can be encouraged in developing and evaluating investment proposals. Operationally suitable commercial or non-developmental solutions are preferred.

At least three diverse alternative descriptions must be developed to satisfy the OMB Capital Planning and Investment Control (CPIC) requirements described in OMB Circular A-11, Part 7.  During CRD, these alternatives will be developed as high-level concepts and will be called Preliminary Alternative Descriptions.  During investment analysis, these concepts will later be documented as detailed descriptions that provide the Joint Resources Council (JRC) and cost and benefits estimators with a complete understanding of what is being proposed.

If necessary, trade studies should be conducted to support the development of preliminary alternatives. Trade Studies are conducted in accordance with the System Engineering Manual (SEM) (http://www.faa.gov/asd/SystemEngineering ). Results of the trade studies are recorded in Trade Study Reports as described in the SEM, Section 4.6.

A nonmaterial solution that emerges at this point may be implemented without proceeding further in the lifecycle management process, provided it satisfies the need, can be achieved within approved budgets, and is acceptable to the users and customers. This determination is presented to the appropriate JRC Subordinate Board.

The Preliminary Alternative Descriptions are documented for use in the initial investment analysis process.

Responsible Agent:  Service organization.

Product:  Preliminary Alternative Descriptions; Trade Study Report(s).

Approving Agent:  Director of the operating service organization after concurrence by the appropriate systems engineering organization.

Supporting Tools and Guidance: Alternative Descriptions template (Appendix D); Trade Study Report template in the SEM (http://www.faa.gov/asd/SystemEngineering ); RE&D, FAA Enterprise Architecture, and systems engineering representative(s).

# Develop Safety Risk Management Decision Memo

ATO Safety Services will guide the operational service unit / LOB to determine what safety work is required for this initiative.  The resulting plan will be submitted to the chair of the System Safety Working Group (SSWG) for concurrence.  If it is determined that there is no safety impact to the NAS, the service team will produce a signed Safety Risk Management (SRM) Decision Memo containing rationale why the proposed initiative does not impact the safety of the NAS.  The SRM Decision Memo will be presented to the appropriate JRC Subordinate Investment Review Board as input to the investment analysis readiness decision.

Responsible Agent:  Service organization.

Product:  SRM Decision Memo.

Approving Agent:  ATO Safety Services Representative, after concurrence from the SSWG Chair.

Supporting Tools and Guidance:  ATO Safety Services Representative.

# Develop Concept(s) of Use

The service organization develops the Concept of Use.  The Concept of Use defines how capabilities will function within the operational environment or service delivery concept and how the capabilities will satisfy the service need.  It also defines the roles and responsibilities of key participants (e.g., controllers, operators, and pilots) and key elements of the required capability. It explains operational issues that systems engineers must understand to develop requirements, identifies procedural issues that may lead to operational change, and establishes a basis for evaluating benefits. The Concept of Use must not be based on a particular solution to the capability shortfall or mission need.

The Concept of Use focuses on the operation of specific components of the NAS or LOB system under consideration, and must be consistent with the NAS or LOB Concept of Operations.  The Concept of Use must show how each new part or component complements, fits into, and harmonizes with the NAS or LOB Concept of Operations.

The Concept of Use clearly defines needed functions and provides the initial set of performance indicators of the required performance with human-in-the-loop.  Therefore, the Concept of Use must be developed before operational requirements are defined.

The Concept of Use specifies how the capability is to be used, and what in the FAA will be done differently as a result of implementing the new concept.  Specifically, the concept will illustrate how, when, and where the new approach will improve FAA performance and satisfy ATO or other LOB metrics.

The Concept of Use identifies benefit mechanisms that will be incorporated into the system design.  For example:

“Through improved surveillance detection and greater position accuracy, allow a 5% increase in the number of aircraft handled safely in each sector by en route controllers through greater situational awareness of the entire sector and its boundary conditions.”

The Concept of Use is developed in accordance with Section 4.4 of the System Engineering Manual (SEM). The Concept of Use will be incorporated in the Preliminary Program Requirements.

Responsible Agent:  Service organization with advice from the appropriate systems engineering organization.

Product:  Concept(s) of Use.

Approving Agent:  ATO Director or the Division Manager (non-ATO) of the service organization with the mission need and the ATO Director or the Division Manager (non-ATO) of the operating service organization with concurrence from the manager of ATO-P Systems Engineering NAS Operations Concepts and Service Engineering.

Supporting Tools and Guidance:  Section 2 of the Preliminary Program Requirements template ( http://fast.faa.gov ); SEM section 4.4, System Level Concept of Operations template ( http://www.faa.gov/asd/SystemEngineering ).

# Develop Preliminary Requirements

Requirements definition translates operational needs described in the service level mission need assessment into Preliminary Program Requirements. This defines the capability or service required by the agency.  It is imperative that key functional disciplines such as safety, security, and human factors participate in the activities of CRD in order to determine mandatory requirements and evaluate their impact on potential alternative solutions.

Preliminary requirements should specify:

What functions the new capability must perform

How well the new capability must perform these intended functions

What interfaces it must have with related systems, facilities, and users.

Research and analysis, simulation, modeling, prototyping, or full-scale development may be necessary to fully identify the acceptable and achievable range of requirements.  At this early stage, an in-depth requirements document is neither necessary nor desirable.  Instead, provide a relatively high-level summary statement to describe the major functions and performance the new capability must deliver. Also, address any major constraints (e.g., latest acceptable operational readiness date) that must be satisfied.

Preliminary requirements must not be written so that they constrain the answer to a single solution.  Instead, they should specify functional, performance, and interface requirements in a way that permits several alternative solutions to be evaluated.  Preliminary requirements are to be developed in accordance with Section 4.3 of the System Engineering Manual (SEM).

Preliminary requirements specify performance parameters of the new capability.  Care must be taken to specify only function and performance and not define a specific solution.  Express preliminary requirements such that performance values can be defined for measuring and evaluating the degree to which a particular solution satisfies the functional requirements.

Key performance parameters (KPP) are those relatively few (perhaps five to six) most important performance characteristics of the Preliminary Program Requirements set that are crucial to its operational or economic value.  The KPP requirements should be expressed (“scaleable”) such that the degree to which different solutions satisfy them can be measured.

Responsible Agent: Service organizations, corporate mission and requirements analysis organizations, and ATO-P NAS Requirements and Interface Management.

Product:  Preliminary Program Requirements.

Approving Agent:  ATO Vice President or the Director (non-ATO) of the service organization with the mission need and the ATO Vice President or the Director (non-ATO) of the operating service organization. Concurrence by Director ATO-P Systems Engineering.

Supporting Tools and Guidance:  Preliminary Program Requirements template (http://fast.faa.gov ); SEM ( http://www.faa.gov/asd/SystemEngineering ).

# Estimate Rough Order Lifecycle Cost

A rough order of magnitude (ROM) lifecycle cost estimate for each alternative is developed.  The service organization develops the ROM cost estimate using standard ATO-F cost estimating techniques. The service organization will use the Preliminary Alternative Descriptions as the main basis for computing estimated costs. The Technical Alternative Descriptions will be produced during investment analysis and will provide the information needed for developing a detailed cost estimate.

Responsible Agent: Service organization with advice from ATO-F Investment planning and Analysis (IP&A).

Product:  ROM Lifecycle Cost Estimate for each alternative solution.

Approving Agent: Director, service organization with the mission need.

Supporting Tools and Guidance:  FAA Investment Analysis Standards and Guidelines (cost estimation).

# Develop Enterprise Architecture Products and Amendments

Service organizations work with the appropriate systems engineering organization to define Enterprise Architecture (EA) products and amendments.  For NAS Operations initiatives, the EA products and amendments include the Operational (business rule) and Systems (engineering) View families.  These families facilitate development, support, and execution of both service and infrastructure investment programs.  The Administrative and Mission Support initiatives use the Federal Enterprise Architecture Framework (FEAF).  For non-NAS initiatives, the operational view is split between the business process, application, and data views.  The systems view in the FEAF is specified in the technical view.  The service organization will submit NAS EA products and amendments to the NAS EA Board (EAB) through the NAS Chief Architect.  The EAB will review the products for consistency with the EA. After review, the EAB will work with the service organization to update the NAS EA Products or forward the EA products to the Vice President, Operations Planning for approval.  The service organization will present Mission Support and Administrative products and amendments to the Architecture Review Board (ARB) through the FAA EA Chief Architect.

Responsible Agent: Service organization with advice from the appropriate systems engineering organization.

Product:  Enterprise Architecture products and amendments.

Approving Agent: ATO-P Vice President approves NAS EA products and amendments after concurrence by the Director of the Service Organization and the EAB.  The CIO approves Mission Support and Administrative Architecture products and amendments after concurrence by the ARB and FAA EA Chief Architect.

Supporting Tools and Guidance:  Consultation with CRD Team Lead and FAA EA Chief Architect for guidance; FAA Enterprise Architecture.

# Conduct Technical Review

For key initiatives, the System Engineering Council (SEC) will review specific CRD products for maturity and readiness for investment analysis.  These may include, but are not limited to, the Preliminary Alternative Descriptions, Concept (s) of Use, Preliminary Program Requirements and Enterprise Architecture products and amendments.  Based on the results of the reviews, the SEC may update the products or recommend updates to the products as necessary for entry into investment analysis.  The SEC will provide a statement as to whether the products are mature enough for investment analysis or what needs to be done to make the products mature enough. The information will be used as input to JRC Subordinate Investment Review Board decision-making.  The SEC will include appropriate stakeholders in its reviews.

Responsible Agent:  Director, ATO-P Systems Engineering.

Product:  Statement of readiness for technical products; CRD technical product updates; recommendations for CRD technical product updates.

Approving Agent:  ATO-P Vice President.

Supporting Tools and Guidance:  SEC; System Engineering Manual

(http://www.faa.gov/asd/SystemEngineering ).

# Conduct Financial Review

ATO-F will conduct quality reviews of the rough order of magnitude (ROM) cost estimates of the proposed investment.  The ROM cost estimates may be updated to accommodate any recommendations from the quality reviews.

Responsible Agent:  ATO-F.

Product:  Approval of ROM cost estimate methodology.

Approving Agent:  ATO-F Investment Planning and Analysis (IP&A).

Supporting tools and guidance:  ATO-F IP&A.

# Plan for Investment Analysis

The service organization develops the Initial Investment Analysis Plan (IAP), with assistance from ATO Finance (ATO-F), as the final step prior to the IARD.  The plan for investment analysis:  (1) defines scope and assumptions; (2) defines alternatives and rough-order lifecycle cost estimates; (3) defines organizational roles and responsibilities, (4) specifies a target schedule, and (5) estimates resources needed for the work.  By signing the plan for investment analysis, the organizations that will conduct the analysis agree to provide the resources necessary to complete the work.

Responsible Agent: Service organization with advice from ATO-F.

Product:  Initial IAP.

Approving Agent:  ATO Vice President or Director (non-ATO) of the service organization.

Supporting Tools And Guidance:  Initial IAP template (http://fast.faa.gov/investment/iarapp-a.htm).

# Prepare for Investment Analysis Readiness Decision

The investment analysis readiness decision (IARD) Brief is presented to the JRC Subordinate Investment Review Board.  The CRD Team will assemble all of the material needed to assess the readiness for proceeding into investment analysis.  When consensus is reached to proceed, a briefing is prepared and presented by the service organization to the appropriate JRC Subordinate Investment Review Board.

The IARD entrance criteria are:

Preliminary Program Requirements

Enterprise Architecture products and amendments

Signed Initial Investment Analysis Plan

Safety Risk Management Decision Memo (if applicable).

Responsible Agent:  Service organization.

Product:  Briefing package to the JRC Subordinate Board.

Approving Agent:  CRD Team / Service organization.

Supporting Tools And Guidance:  IARD Briefing template (http://employees.faa.gov/worktools/branding_guidelines/powerpoint/ and Appendix E).

Appendix A: Template for the Concept and Requirements Definition Plan

|  |  | Federal Aviation Administration |
| --- | --- | --- |
|  |  | Fully Releasable Version x.x Date |
| Concept and Requirements Definition Plan for the (name of proposed investment initiative) Line of Business (Name of) Service Organization (Name of) Service Office Approved By: ________________________________________________Date _______ ATO Vice President or Director (non-ATO) of the Service Organization with the mission need and the Operating Service Organizations |  |

Concept and Requirements Definition Plan

for

(Proposed service/infrastructure initiative(s))

This Plan specifies the scope, assumptions, constraints, methods, data sources, resources, control strategy, team composition, roles and responsibilities, schedule, and deliverables for a proposed concept and requirements definition (CRD) activity that addresses a priority service need within the Service-Level Mission Need Assessment/Enterprise Architecture and develops the information necessary for an investment analysis readiness decision (IARD).

Scope:  Identify the specific capabilities or components of the Service-Level Mission Need Assessment that will be examined. Define how these capabilities or components fit into the overall service delivery strategy of your service organization.

Assumptions, Constraints, and Guidance:  State the key assumptions, constraints, and guidance that will govern the CRD Team as they conduct CRD activities. These may include:

The quantified capability shortfall that will be addressed

The remaining service life of the existing capability

The required operational date of any needed new or replacement capability

Any component of the proposed new capability that has a higher priority for early delivery than the entire capability

The required mission life or economic service life of the proposed new capability

The proposed date for the IARD—date by which all CRD activity must be complete with findings and recommendations presented to the appropriate decision board (Executive Council (EC) for Air Traffic Organization (ATO); Information Technology Executive Board (ITEB), which reviews and recommends investments related to FAA administrative and some mission support services; and the lines of business (LOB) review boards that review and recommend investments within a LOB

Any design cost, unit acquisition cost, Operations cost, or any other economic goal that must be satisfied by the new or replacement capability (e.g., “Unit initial acquisition cost must be less than $2 Million.”)

Any LOB performance goal that must be satisfied by the new or replacement capability (e.g., “Reduce cost per flight by 1%.”)

Any milestone constraint (i.e., external influences) that must be satisfied by the new or replacement capability

Any human resource constraints on staffing levels, training time, personnel abilities or attributes ,or human-system performance data.

Any constraints on the choice of an alternative (e.g., “No alternative may be developed that will require the mandatory carriage of new avionics by the airlines and other National Airspace System (NAS) users.”)

Any policy guidance that influences, constrains, or dictates the choice of a new or replacement capability or operational requirement

Any interdependencies with other new, existing, or proposed Federal Aviation Administration assets that must be satisfied (e.g., “Delivery of new digital Airport Surveillance Radar-11 radars must be completed prior to installation of new digital Standard Terminal Automation Replacement Systems.”)

Any NAS safety issues that influence, constrain, or dictate the choice of a new or replacement capability

Any required safety risk acceptance and safety risk management documentation.

Methods:  Define methods and techniques to be used in each CRD activity and task.

Data Sources:  Define the data sources that will be used for each CRD activity.

Resources Required:  Identify the resources and respective costs needed to complete CRD activities. For example:  team members, required skill levels, level of effort, level of contract support needed, consultants needed, and travel, training, or technology (software or hardware) required.

CRD Team Composition:  Define the CRD Team composition alphabetically by name and affiliated FAA organization. Acquisition Management System policy designates ATO Operations Planning (ATO-P) Systems Engineering as lead.

Roles and Responsibilities:  Define the roles and responsibilities of each team member for each CRD activity and deliverable.  Attachment 1 provides boilerplate material for this section.

Control Strategy:  Describe the control strategy that will be used by the CRD Team Lead to ensure timely delivery of quality CRD products to the JRC Subordinate Investment Review Board. Discuss how commitment to these activities will be obtained (e.g., through a request for participation, memorandum for action or of understanding, letter of agreement, bargaining negotiations, or management coordination).

Deliverables:  List and describe all deliverables; and provide the required completion date for each. At a minimum, CRD deliverables shall include a Preliminary Program Requirements document; a Concept of Use; Functional Architecture; a description of the preliminary alternatives; a rough estimate of lifecycle cost for each alternative; Safety Risk Management Decision Memo (if applicable); and Investment Analysis Plan.

Attachment 1

CRD Roles and Responsibilities

There are many program and service organization members, as well as support contractors, that make up an effective CRD team. The roles and responsibilities of team members generally fall into four categories, which are addressed here.  They include the CRD Team Lead, CRD Sub-Team Lead, Subject Matter Expert (SME), and service organization project manager or point of contact. A team member may assume one or more of these roles.

CRD Team Lead

ATO-P Systems Engineering is responsible for providing oversight and guidance throughout the CRD phase.  The CRD Team Lead, appointed by ATO-P, performs quality assurance functions to ensure the CRD plan is implemented and the expectations of all deliverables are met.  In addition, the Lead manages the team process.  This leadership and management is accomplished by (1) acting as an information hub, (2) bringing the different units and elements together within ATO-P and other organizations for synergistic purposes of completion, and (3) driving the process for establishing schedules in conjunction with other SMEs and program stakeholders.

As the information hub, the CRD Team Lead maintains insight into the status of all deliverables.  The Lead is proactive in evaluating collaborative feedback from team members; scheduling and attending meetings; and maintaining records on activities, issues, and deliverable status.  By openly soliciting information, the Lead identifies area/team issues or concerns as they emerge.  The Lead seeks resolution to keep the process moving forward and on track in accordance with the CRD Plan.  In addition, the Lead keeps the Management informed through regularly scheduled progress reports.

The CRD Team Lead creates a synergistic team environment by promoting and reinforcing cohesion and commitment to complete the products and tasks.  This individual drives the process by establishing and fostering teamwork and facilitating consensus through agreed to performance metrics.

Sub-Team Lead

Sub-teams may be established for each deliverable produced in CRD.  Sub-Team Leads will be appointed and may be responsible for leading one or more sub-teams.  These individuals are expected to perform quality assurance functions to ensure the intents of their respective deliverables are achieved. In addition, they are responsible for keeping the Team Lead informed of progress and issues.

Subject Matter Experts (SMEs)

The SMEs from ATO-P, ATO Finance (ATO-F), Office of Information Services, or other organizations may act as consultants and advisors to the LOBs or service organizations or may develop information and data to satisfy the investment analysis readiness decision criteria.  They are responsible for ensuring the completion of respective products of the CRD phase by not only serving as experts and remaining engaged, but also providing direction and vision to completing the task at hand.  SMEs are a resource for helping the team complete the designated product.

Line of Business/Service Organization Point of Contact (POC)

The POC may hold the title of project manager or program lead for the investment opportunity.  This individual is responsible for the coordination of resources within the LOB/service organization.  This individual also serves as part of the communication hub interacting with the ATO-P CRD Team Lead, Sub-Team Leads, and SMEs in establishing and meeting timelines, producing deliverables, and coordinating CRD activities within the LOB/service organization.

Line of Business/Service Organization Technical Representative

This Technical Representative is responsible for supporting the development and coordination of technical products whether developed by the service organization or other organizations. This individual must have knowledge about the current system/capability, if applicable, and requirements for any future capabilities needed to address the mission need or performance shortfall.

# Appendix B: Template for the Shortfall Analysis Report

|  |  | Federal Aviation Administration |
| --- | --- | --- |
|  |  | Fully Releasable Version x.x Date |
| Shortfall Analysis Report Line of Business Service Organization Service Office or Division Service Group or Branch Approved By: _________________________________________________ Date _____________ Service Organization with the mission need |  |

Shortfall Analysis Report for (name of initiative)

Purpose:  The service organization is required to identify shortfalls and quantify their impacts to support the mission need decision. This work requires research and analysis.  This document provides the requirements and guidelines to capture the details of this research and analysis.

Description:  This document is completed for all initiatives.  It captures all of the detailed information regarding the data, assumptions, and methodology used to generate the shortfall estimates.  This shortfall document can also point out anticipated analytical challenges that would be helpful to the business case analysis after the mission need decision.

Comprehensive documentation is essential for future validation, verification, and accuracy of the estimate.  Detailed documentation also provides important methodological guidance for future benefit estimates.  The shortfall analysis report should explain how and what was done to generate the shortfall estimate.  The major elements of a sound capability shortfall document should include the following sections:

- Introduction

Historical background of the initiative: Explain the initiative, including a brief technical description.

Describe the scope of the analysis:  List and explain shortfall categories.  First, list all possible service gaps and explain how and why this situation could theoretically lead to a service shortfall. Select a subset of these categories for quantification. That is, in the service analysis stage, quantify categories that will be enough to justify the program and support the mission need decision.  Select categories that have accessible data and are anticipated to be the main drivers of the shortfall. Analyze these selected categories, some of which may yield low estimates

List the participants involved.

- Ground Rules and Assumptions

List and explain all general assumptions that apply to all shortfall categories.

Define all specific assumptions that apply to certain shortfall categories.  This may include very detailed explanations and/or justifications for specific assumptions.  Supply data used for the assumptions and explain the methodology implemented to develop these assumptions. This explanation should include any reference or source material.

- Data Inputs

In the narrative data inputs section, the quality of the data used should be discussed and evaluated.  Any corrective procedures or adjustments to the data, including the rationale for the adjustment should also be provided.

If the shortfall analysis involves costs, include quantities, unit costs, schedules, inflation and discount rates used, and other cost parameters.

This section would also include the use of previous analyses and/or studies on benefits estimation.  Protocol for data inputs citations and referencing also applies to the use of previous analyses and/or studies.

Input data should also identify those shortfalls of previous analysis which have already been addressed as well as those which have to be addressed in the horizon year of the shortfall.

- Measures Chosen

All benefits should be listed and then organized into general benefits/measures groupings.  Assistance may be found by reviewing the connection between the benefits and the Benefits Breakdown Structure.  Explanations and justifications for the measures chosen and how they will be measured should be included.

- Description of Methodology

Overview of methodology should clearly explain what was done and how it was done in a step-wise chronological progression.

All diagrams and tables depicting the methodology should have citations and headings describing their contents.

Models used in the estimation process should be identified and described in detail, including how they operate, input assumptions, known weaknesses, and outputs. References should also be provided.  Describe any risk analyses and adjustments that were done.

If the shortfall analysis involves cost, provide basis of estimate document by FAA WBS element in the format contained in “Documentation Guidance for FAA Cost Estimates.”

- Results

Report the shortfall estimate and display it in appropriate tables and graphs.  Include any explanation that might be helpful to the service team.

- Qualitative Shortfalls  (non-quantified, enabling, and quantified, non-monetized)

Due to expediency, these shortfall categories are treated in a qualitative fashion.

Discuss why these were not quantified—lack of available data, would require too much work, anticipated small shortfall, etc.

- Future Work/Next Steps

Helpful hints or challenges to overcome in concept and requirements definition.

Comments on how a more accurate analysis can be conducted during concept and requirements definition, as required, than was done in service analysis.

Summary of shortfall categories that were not pursued in the service analysis phase, but probably should be considered in concept and requirements definition.

# Appendix C: Template for the Functional Architecture

|  |  | Federal Aviation Administration |
| --- | --- | --- |
|  |  | Fully Releasable Version x.x Date |
| Functional Architecture for the (name of proposed investment initiative) Air Traffic Organization Operations Planning Service Systems Engineering NAS Operations Concepts and Service Engineering Approved By: _________________________________________ Date__________ Director of Organization with Mission Need Concurred By: _________________________________________ Date _________ Manager, NAS Operations Concepts and Service Engineering, Systems Engineering, Operations Planning Service, Air Traffic Organization |  |

Functional Architecture for the (proposed initiative)

Purpose:  Functional analysis translates user needs and human performance (capabilities and limitations) into a sequenced and traceable functional architecture that captures the functions and sub-functions necessary to provide the needed service or operational capability.  The approach is to analyze what must be done without defining how to do it.  The output is a Functional Architecture, which is the primary foundation for defining requirements and physical architectures, in accordance with the FAA Enterprise Architecture.

The functional architecture presents a function list to the requirements management systems engineering process for analysis and development of requirements.

Content: The general content of a Functional Architecture description includes:

Functional Analysis:  Describe how top-level functions were decomposed to lower-level functions. Define and depict functional interface.

Functional Architecture:  Assemble and integrate all of the foregoing into a complete Functional Architecture.  The Systems Engineering Manual (SEM), http://www.faa.gov/asd/SystemEngineering ), Section 4.4, should be consulted for the format and process for developing a Functional Architecture.

Inputs:  Inputs to a functional analysis vary depending upon the scope of a given functional analysis effort and iteration of the process.  Section 4.4 of the SEM provides information regarding generic inputs to functional analysis.

# Appendix D: Template for the Alternative Descriptions

|  |  | Federal Aviation Administration |
| --- | --- | --- |
|  |  | Fully Releasable Version x.x Date |
| Alternative Descriptions for the (proposed investment initiative) Line of Business Service Organization Service Office Approved By: ______________________________________________ Date ______________ ATO Director or Division Manager (non-ATO) (Service Organization with the mission need) Concurred By: __________________________________________ ___ Date ______________ Manager, (Appropriate Systems Engineering Organization) |  |

Alternative Descriptions for the (proposed investment initiative)

Purpose:  This document provides Federal Aviation Administration (FAA) Executives engaged in making investment decisions with a basic understanding of each alternative solution being proposed to meet a mission or service need.  It provides the technical basis for estimating lifecycle costs and facilitating the estimation of benefits.  During concept and requirements definition, it supports estimating costs to a rough order of magnitude (ROM). During initial investment analysis phases, this document describes each alternative in sufficient technical and programmatic detail so that it can support accurate cost and benefits estimates.  This is a “living document,” which is updated for major reviews and decision points.

Constraints: At least three alternatives are necessary to satisfy the Office of Management and Budget (OMB) Capital Planning and Investment Control (CPIC) requirements described in OMB Circular A-11.  In concept and requirements definition, these alternatives will be developed as high-level concepts and will be called Preliminary Alternative Descriptions.  During initial investment analysis, these concepts will later be documented as detailed descriptions that provide the Joint Resources Council (JRC) and cost and benefits estimators with a complete understanding of what is being proposed.

Alternatives should be qualitatively different from each other (e.g., airborne-based vs. ground-based, satellite-based vs. ground-based, traditional system acquisition vs. service acquisition, etc.) so that maximum creativity, flexibility, and innovation can be encouraged in developing and evaluating investment proposals.  Each proposed alternative must be capable of meeting any design-to-cost goals or unit cost goals.

The alternatives must:

Satisfy the capability shortfall (alternatives may not meet 100% of requirements)

Have a positive impact on FAA performance measures

Contain a quantitative and narrative description, including the technical, physical, and performance features pertinent to costing the alternative and quantifying the benefits

Describe all efforts and impacts associated with an alternative regardless of the funding source or performing organization (e.g., staffing, training, infrastructure).

Responsibilities: The service organization; working with the sponsor, appropriate systems engineering organization, and Research, Engineering, and Development (R,E&D) organization; develops the set of alternative concepts to resolve the service shortfall.

Alternatives:  Describe each alternative.  Include descriptions of the Reference Case.  The Reference Case (current capability or legacy case) may assume a modest level of sustainment (e.g., buy-out of spare parts and line replacement units) to extend service life as much as feasible, but it should not assume significant levels of investment, such as a service life extension program would require.

Content: Costs are estimated according to how closely the proposed new capability matches an existing capability whose actual costs are known.  This is called analogous estimation.  To facilitate analogous cost estimation, write the Alternative Descriptions in a way that facilitates cost estimation. Include reasonable assumptions and analogies of any new capability’s similarities to and differences from existing systems, in cases in which specific information on a proposed capability is not available.  Describe an existing or under-development capability that is reasonably similar in function, size, or complexity to the proposed capability.  Describe any current operational product(s) that is similar in nature and performance (e.g., same functions, same size) to this proposed alternative.  Summarize the similarities and differences between the analogous products and this alternative.

Highlight technical, operational, and programmatic similarities and differences that drive cost differences among alternatives and are relevant to their costing (e.g., different acquisition strategy, such as competitive down-select or sole source from the outset).    Include the following information for each alternative:

Product Overview:  Describe the product and its key performance parameters, as well as a diagram or concept drawing with major segments, parts, and sub-elements.

Characteristics:  Briefly describe prime mission equipment facilities, hardware and software; the discussion should follow the elements in the FAA standard Work Breakdown Structure.  Describe the principal physical and functional features of the proposed new capability, as compared to the analogous capability.  These include:

New hardware:  Describe required equipment types and quantities.  If not known specifically, then identify generically and explain how the planned capability differs from the analogous capability.

New software:  State the number of Source Lines of Code or Function Points; if not known, estimate the size relative to the analogous system (e.g., “50% larger”).  Identify the expected software language to be used.

Facilities Requirements:  Describe any new facilities or major modifications to existing facilities needed to support the development, production, or deployment of the alternative. If a new facility will be needed, state its relative size in square feet and where it will be located.  For each facility type (Air Route Traffic Control Center, Terminal Radar Approach Control facility, Air Traffic Control Tower, Air Traffic Control System Command Center, etc.), describe the expected impact (i.e., low, medium, high) of the alternative on existing facilities (e.g., space, power, lighting).

Performance Quality Factors:  Describe requirements for operational availability, reliability, and maintenance.

Maintenance Concept:  State whether the alternative needs specific organic (in-house) or contractor maintenance and, in general, how maintenance will differ from that of the analogous capability.

Interface Requirements:  Describe needed interfaces between the alternative and new or existing NAS or other FAA systems or facilities with which it must interact, either physically or functionally.

Telecommunications Requirements:  Describe any major telecommunications requirement that will be needed beyond what the current/future FAA Telecommunications Infrastructure program or its follow-on will provide.

Quantities:  State the number of sites and number of assets per site for each alternative.

Schedule:  Identify contract award, initial operating capability, and final operating capability target dates.

Complexity:  Give the reasons why acquisition and deployment of this capability will be more or less difficult, unique, or complex than the analogous system or other prior FAA experience.

Risks:  Describe where the alternative likely is “pushing the envelope,” either in its production (i.e., process risks that threaten cost and schedule growth in production) or its in-service use (i.e., product risks) that may prevent the product from being successful in its intended use).  This may include major risk or uncertainty areas such as software development, software certification, pilot acceptance, controller acceptance, human-system interface optimization, concept of use, technology maturity, schedule, acquisition strategy, competition, staffing and training, or other major risk areas.

Interdependencies:  Describe other initiatives or programs that may have a potential impact on this alternative, or those on which this initiative may have an impact.

Testing Strategy:  Describe the testing and evaluation strategy that will be used.

Staffing and Training Impact:  Describe the estimated changes in manpower levels, personnel selection criteria, and training requirements for all users (e.g., operators, maintainers, supervisors, and support personnel) needed to support the system in its In-Service phase.

Activity Rates:  Summarize the expected operational tempo in terms of operating hours per year, number of operations per month, volume of transactions, etc.

# Appendix E: Template for the Investment Analysis Readiness Decision Briefing

Investment Analysis Readiness Decision Briefing

for the (proposed investment initiative)

Purpose:  The briefing for the investment analysis readiness decision (IARD) provides an objective and fair assessment of the merits of proceeding to investment analysis.

Format: The briefing format is located at the following web link:

http://employees.faa.gov/worktools/branding_guidelines/powerpoint/ .

Content:  The investment analysis readiness review is conducted after quantifying a shortfall and developing supporting documentation. It assesses the readiness of proceeding into initial investment analysis.

The IARD briefing includes:

Description and scope of initiative

Integration with the strategic management process

Integration with the FAA Enterprise Architecture

Identification of the shortfall

Quantification of the shortfall

Criticality of the shortfall

Economic and verifiable operational impact of the shortfall, especially on Federal Aviation Administration and lines of business metrics

How much of the shortfall will be eliminated

Preliminary Program Requirements, including key performance parameters

The set of alternatives, with limited technical descriptions of each including the state of technology development, and degree of external customer support

The rough cost estimates for each alternative, including an assessment of the reliability of costs

Summary of the Initial Investment Analysis Plan (include high level schedule)

High level risks (if known at this time)

Critical interdependencies

Recommendation for Investment Analysis Team Lead

Decision requested.

# Appendix F: Definitions and Acronyms

Definitions and Acronyms

Definitions

Only terms not defined in Acquisition Management System/FAA Acquisition System Toolset are defined here.

Concept of Use:  A document that specifies how an operational capability will be used in the operational environment.  Provides functions to be performed and indicates benefit mechanisms to be employed.

Investment Analysis Readiness Review: A subordinate investment board review of the readiness of a proposed new investment to enter investment analysis.  The review is intended to ensure the investment description is sufficiently mature and complete, and needed information is in hand, before proceeding into the considerable resource expenditure for a full investment analysis.

Acronyms

| AIO | Office of Information Services |
| --- | --- |
| AMS | Acquisition Management System |
| ARB | Architecture Review Board |
| ATO | Air Traffic Organization |
| ATO-F | Air Traffic Organization, Finance |
| ATO-P | Air Traffic Organization, Operations Planning |
| B/C | Benefit to cost ratio |
| BOE | Basis of Estimate |
| CIO | Chief Information Officer |
| CIP | Capital Investment Plan |
| CIT | Capital Investment Team |
| COTS | commercial-off-the-shelf |
| CPIC | Capital Planning and Investment Control |
| CRD | Concept and Requirements Definition |
| CSEC | Chief System Engineering Council |
| EA | Enterprise Architecture |
| EAB | Enterprise Architecture Board |
| EC | Executive Council |
| ESL | Economic Service Life |
| F&E | Facilities and Equipment |
| FAA | Federal Aviation Administration |
| FAE | FAA Acquisition Executive |
| FAST | FAA Acquisition System Toolset |
| FEAF | Federal Enterprise Architecture Framework |
| FOC | Full Operational Capability |
| IA | Investment Analysis |
| IAP | Investment Analysis Plan |
| IARD | Investment Analysis Readiness Decision |
| IID | Initial Investment Decision |
| IP&A | Investment Planning & Analysis |
| ITEB | Information Technology Executive Board |
| JRC | Joint Resources Council |
| KPP | Key Performance Parameters |
| L | Lead |
| LCC | Lifecycle Cost |
| LOB | Line of Business |
| MS | Microsoft |
| NA | Not Applicable |
| NAS | National Airspace System |
| NAS-SR | NAS System Requirements |
| OBS | Organizational Breakdown Structure |
| Org. | Organization |
| O&M | Operations and Maintenance |
| OMB | Office of Management and Budget |
| PM | Program Manager |
| POC | Point of Contact |
| PRC | Progress Review Checkpoint |
| RE&D | Research, Engineering, and Development |
| ROM | Rough Order of Magnitude |
| S | Support |
| SAR | Shortfall Analysis Report |
| SE | Systems Engineering |
| SEC | System Engineering Council |
| SEM | System Engineering Manual |
| SLMNA | Service Level Mission Need Assessment |
| SME | Subject Matter Expert |
| SRM | Safety risk management |
| SSWG | System Safety Working Group |

# Footnotes

Note that the roles and responsibilities are a part of the CRD Plan.

The American Association of Cost Engineers defines the ROM estimating accuracy boundary as –30% and +50%.