Request for Proposal

Construction Management Services

for

DC COURTS PROJECTS

Washington, DC

Project No.  NDCXXXXX

SOLICITATION NO. GS11P02MKC0042

PART I – THE SCHEDULE

SECTION C

DESCRIPTION/SPECIFICATION/WORKSTATEMENT

SECTION C - DESCRIPTION/SPECIFICATIONS/WORK STATEMENT

C.1  General

(a)		The Construction Manager (CM) shall provide CM services related to various projects at DC Courts, including, but not limited to:  (1) new underground parking garage at D Street and 5th Street NW, Washington, DC and (2) renovation and adaptive re-use and addition to Old DC City Hall at D Street, between 4th and 5th Streets, NW, Washington, DC.

(b)	   	Construction Management (CM) Services as specified, will be required for the various and non-concurrent stages of the projects including (1) Planning Phases, (2) Procurement Phases, (3) Design Phases, (4) Design-Build Phases including claims, (5) Construction Phases including Claims and (6) Testing, and Miscellaneous Services as appropriate, adequate, and necessary for the projects. It is anticipated that for the garage project, procurement of the design-build contractor will be starting at the time the CM contract is awarded. It is anticipated that for the Old DC Hall renovation, adaptive re-use and addition, the Brooks Act procurement (utilizing GSA’s design excellence program) will be in progress at the time the CM contract is awarded.

C.2  Construction Projects Description

(a) 		Project:	DC Courts Projects

WASHINGTON, DC

PCN:  XXXXXXXXX

(b).. 	The underground parking garage will be a new garage for approximately 230 cars on	three levels. The garage users will be able to enter the Old DC City Hall and the US Court of Appeals for the Armed Forces (USCAAF) without exiting the structure. Following completion, the garage will be jointly used by DC Courts and USCAAF. Existing street level plaza located in the way of garage construction will be demolished. Existing sculpture will be stored and protected for the duration of the construction. Included in the project shall be filling the area of the plaza above the garage with dirt, grass seeding of the area, re-installation of the sculpture and installation of a security fence. The above ground penetrations for exhaust shafts, emergency egress and vehicular driveway shall be completed functionally. It is the intent to include the design of the plaza with the design excellence program for the renovation and adaptive re-use and addition to Old DC City Hall and to include the new plaza construction with that project. Design build procurement is planned for the garage. Procurement documents for the garage will include GSA initiated studies, soil samples from borings, surveys, environmental assessment and concept design. Approvals from Fine Arts Commission (FAC) and National Capital Planning Commission (NCPC) will be obtained for the concept design prior to garage procurement. It is intended to include within the garage project preventive maintenance and operation of all systems (except of operation of security and actual operation of the garage) for a period of 12 months following substantial completion of the garage. The garage will be subject to DC reviews, permitting and certificate of occupancy.

(c)   	The Old City Hall City Hall is a 170-year-old structure in poor condition. The project includes extensive renovation, adaptive re-use for court of appeals use and a new addition of approximately 40,000 SF.  The renovation work will include the restoration of a portion of the exterior walls and entrances, replacement of the roof and windows, restoration of architectural interior finishes, new elevators, replacement of mechanical, electrical, plumbing, and communication systems and removal of materials containing asbestos and lead based paint. Areas surrounding the building will require extensive landscaping and site work.

(d) 		The estimated total cost for the projects (garage and renovation, adaptive re-use and an addition to Old DC Hall (renovation) is between $70 million and $80 million.

(e)		Client Agencies: DC Courts and USCAAF.

- Nature of Facilities:  following is a representative list of the types of spaces which will be     	included in the project:

- Courtrooms

- Judges Chambers

- Judges Studies

- Conference and Training Rooms

- Public and Private Toilet Rooms

- Secure, Restricted and Public Corridors

- Secretarial and Law Clerks Offices

- File and Storage Rooms

- Library

- Food Service Facility and Break rooms

- Jury Deliberation Suites

- Prisoner Holding Cells

- Office Automation Facilities

- Interview Rooms

- Public Document Intake Counters

- Computer Rooms

- Executive Suites

- Office Space

- Public Space

- Parking Garages and Areas

- Building Support and Operating Systems Rooms

- Loading Dock

- Atrium

- New Underground Parking Garage

C.3  Standard Services

- The CM Contractor shall perform all Standard Services (Core Team) for the actual duration of the various phases of the project within the firm fixed prices.  The Level of effort, as defined in C.6 (f) shall be the basis for compensation to the CM.

- The CM Contractor shall perform supplemental services in accordance with paragraph C.25 as requested by GSA.

- The estimated time frame for the design-build of the garage is 19 months, design of the renovation, adaptive re-use and addition to the Old DC Hall – 15 months and construction/ renovation of the Old DC City Hall - 27 months.  Project close out period for the garage will coincide with the renovation project while the closeout period for the renovation project will be 3 – 6 months. Design-build of the garage will be performed concurrently with the design and construction procurement of the renovation project. Construction Management for other projects at the DC Courts Campus may be incorporated into this contract under additional supplemental services.  Additional projects are anticipated to have a total value of less than $30 million.

- The current schedule for the projects is as follows:

Garage, start procurement of Design Build 9/27/02, end 3/27/03

Garage, start design/build 3/28/03, end 11/4/04

Garage closeout, start 11/5/04, end 2/5/05 – 5/5/05

Renovation, A/E design excellence procurement end 1/30/03

Renovation, design start 1/31/03, end 4/22/04

Renovation, construction procurement start 4/23/04, end 10/21/04

Renovation, construction start 10/22/04, end 3/8/07

Renovation, closeout start 3/9/07, end 6/9/07 – 9/9/07

C.4  Period of Performance.

The CM contract is effective from the date of award until one (1) month after final settlement of the last construction contract.

C.5  Extent of Services.

All CM services set forth in this contract apply to performance of work at the following locations:

GSA-NCR, 7th and D Streets, SW,

Project site

Financial Management, such as obtaining information such as NEAR Reports, reconciliation of financial data with GSA finance staff, obtaining financial certifications/validations, obtaining signatures of COR and CO as required for change order processing, presenting contractor pay requests to CO and any other financial and administrative effort required to successfully perform CM functions shall be performed at GSA-NCR, 7th and D Streets, SW,

C.6	Definitions.

#### Government Representatives. This is not a personal services contract and representatives of the Government are not authorized to supervise Contractor personnel.  However, non-supervisory directions and guidance from GSA officials are authorized.

## Contracting Officer (CO).  See FAR 52.202-1

## Contracting Officer's Authorized Representative (COR).  See FAR 52.202-1

## Project Managers for Construction – also known as (AKA) Construction Engineers or CEs.  The CEs are GSA employees assigned to the project(s) during the Construction Phases.  The CEs may be assigned full time to the construction sites, or will periodically visit the sites.  The functions and authorities of the CEs may be defined in writing, but generally include providing advice and assistance to the primary GSA Project Manager or key personnel of the Government and the construction contractors, reviewing the status, technical adequacy, and quality of construction; and ensuring compliance with applicable contract documents

## Project Manager (PM).  These are GSA employees assigned to the projects as representatives of the GSA.  The functions and authorities of PM generally include providing advice and assistance to CM personnel, and serving as focal points of project management operations for the Government.

- Project Executive (PE).  GSA employee assigned to the projects, as representatives of the GSA.  PE is in charge of the project and represents GSA, subject to CO and legislative limitations.

## Architect-Engineer (A/E).  The professional services contractors responsible for   designing the projects.  The A/Es may perform other services during the construction phases that are not included in the contracts for the CMs, the construction contractors, or other firms associated with the project. Under the design-build contracts, A/E is a part of the contractor’s team.

## Construction Manager (CM).  The CM firm is the Contractor selected GSA to provide Program and Project Management Services for the purpose of providing standardized technical and management expertise for each project.

## CM Provided Services.  Provided services integrate different phases of the project including planning, design procurement, design, construction procurement, construction and post-construction project close-out including claims resolution and initial operation and maintenance of the facilities performed by contractors. For design-build projects, design procurement and construction procurement phases are combined.  In providing the project services described in the contract, the CM maintains a working relationship with architect-engineers, construction contractors, and other contractors supporting the Government.  Nothing in this contract shall be construed to mean that the CM assumes any of the contractual responsibilities or duties architects-engineers or construction contractors.  The construction contractors are solely responsible for construction means, methods, sequences and procedures used in the construction of the projects, and for related performance in accordance with their contracts with the Government.  The architects-engineers are solely responsible for the project designs and shall perform all design related services in accordance with their contracts with the Government.

Miscellaneous Services Performed by CM. This term refers to performance of services associated with Miscellaneous Items, Additional Services, Other Services, and Testing Services in support of those required under the individual contract phases.  Advance approval by GSA is required.  These services may be required by the COR and ordered by contract modifications under the "Changes" Clause.  The CM will be reimbursed for their costs and expenses without mark-up for overhead and profit.

## Miscellaneous Items and Support Items.  This term refers to the provision of facilities or obtaining and performance of work by the CM which may include, but not be limited to,  signs; safety barricades; cleaning; preparation for ceremonies, including minor construction activities in connection therewith; temporary toilets and sanitation; fencing;  security; obtaining special/multi-use equipment; temporary water, heat and electricity; temporary utility connections to buildings; temporary protective enclosures; additional field office facilities and related costs thereof such as equipment, furnishings and supplies; installation of Government furnished items; general maintenance; disposal of refuse and debris; blueprinting; pest control; providing for first aid; miscellaneous carpentry.  Such work may be ordered under the "Changes" Clause. NOTE:  In accordance with statutory and regulatory requirements, no ADP hardware may be procured under this clause or this contract and the Contractor shall not accept any such orders.

## CM Home Office Area.  This term means the cities/states/ counties in which the CM's active office(s) is/are located.  If the CM's active office(s) is/are located in metropolitan areas consisting of more than one county, the metropolitan area shall be considered the Home  Office Area.

## CM Local Office.  The active production office to be utilized by the CM that is located within the GSA National Capital Region (See definition in Section B).  All management, communications, and control associated with the projects must be through this office.

## CM Level of Effort.  The CM is responsible for its performance and deliverables.  CM work shall be accomplished with Core Team members and through supplemental services as requested by the Government.  For Core Team services, the CM will be compensated only for the hours actually worked at the project site and at GSA, 7th and D Streets, SW, as reflected in the certified attendance log.  Annually, the CM contract will be adjusted to reflect the fees for the actual billable hours for the Core Team personnel. This adjustment will either decrease contract amount should the hours be fewer than anticipated, or increase contract amount for more hours worked. Increase in contract hours shall be implemented prior to the increase. In addition to personnel described in the Core Team, personnel required for proper execution of the required work, shall be obtained under supplemental services.  Annual requirements for the supplemental services will be implemented through a contract modification. Other requirements for personnel shall be implemented when needed. Adjustments shall be made annually to reflect actual hours worked at the project as reflected on the attendance logs. For CM billing purposes, for both core team and supplemental services, only hours that are actually worked and are indicated in the log may be billed for.

## CM Standard Services.  This term refers to the performance of core team services proposed by the CM for the project.  The billings for these services shall be based on hours actually worked at the project site and as documented on certified daily logs. Unit prices will be established in the contract.

## CM Supplementing Services.  This term refers to performance of Contract services by the CM that may be required in addition to the Standard Services, for which the Government will order under the “Changes” clause and will be priced based on the unit prices established in this contract and as negotiated.

## C.7 CM Personnel

## Construction Executive (CEX).

## Quality Control Superintendents (QCS).

## Senior Architects/ Senior Engineer (SAR/SEN).

## Engineers/Technicians (TEN/TTE).

## Inspectors (INS).

## Finance Manager (FIM).

## Office Support (OFS).

## Senior Estimator (SES).

## Estimator (EST).

## Scheduler (SCH).

## (a).    	Availability of CM Personnel.  Within ten (10) working days following CM contract award all required personnel must be available full time or part time (as required by the Government) for work associated with performance of this contract.

## (b)		Duties and responsibilities of CM Personnel

## 1. Construction Executive (CEX).  The principal CM employee who is responsible for overall administration of the CM contract, coordination of the CM efforts, general direction, and accomplishment of CM contractual functions on the projects.  The CEx shall work closely and cooperatively with the A/Es, the construction contractors, and the COR during all phases of the projects.

## 2.Quality Control Superintendents (QCS).  The CM employee designated as the key senior level on-site representative responsible for ensuring delivery of the day-to-day construction management services for the duration of construction.  The QCS shall be energetic, detail oriented and pro-actively manage and administer all work for which the CM is responsible through all phases of the project.

## QCS duties include:

## (a) 		M Staff: (1) managing, supervising, leading and motivating of all CM  professional, administrative and clerical staff on the project, (2) forecasting and fulfilling staffing needs,  (3) certifying time and attendance for CM employees.

## (b) 		Preparation and keeping current Project Procedures Manual,

## (c) 		Implementation of Project Information System and hands –on involvement of some portions of information system including review, preparation and issuance of all correspondence, and oversight of all filing system including issues files.

(d) 		Overseeing (survey, coordinate, watch, inspect, examine, manage and monitor) A/E and contractor’s performance, including quality control, request for information oversight, change order oversight, schedule oversight and pro-active claims avoidance management.

## (e) 		Continually monitoring project(s) costs and being responsible for issuing a very detailed monthly reports consisting of executive summary, project directory, project descriptions, progress report, costs and schedule. Costs section of the report needs to include (as a minimum): (1) funds authorized, (2) pending authorizations, (3) funds expended (by contract, change orders, purchase orders, charge card purchases), (4) pending expenditures (where applicable, separated by paperwork pending, proposals received and awaiting proposals), (5) reservations for all known and forecastable exposures, (6) contract records, (7) RWA’s logs, (8) no cost directive logs, and (8) contingency analysis and projections.

(f) 		Reviewing and making recommendations for all pay requests.

## 3. Finance Manager (FIM).  The CM employee designated as the senior level representative responsible for ensuring oversight and implementation of all financial and budget aspects of the projects The FIM shall be energetic, detail oriented and pro-actively manage and administer all work for which the FIM is responsible through all phases of the project. FIM duties include:

- Processing all pay requests (including consultations with appropriate CM technical employees) from contractors, A/E and CM,

- Processing change orders (including overseeing issuing requests for proposals, overseeing preparation of independent government estimates,

- Receiving proposals,

- Monitoring and coordinating pre-negotiation preparation,

- Monitoring and coordinating negotiations,

- Monitoring and coordinating preparation of negotiation memoranda,

- Preparing SF30’s in GSA’s Comprizon

- Obtaining contractor’s signatures,

- Obtaining funds approval,

- Assisting CO in  issuing the change orders,

- Monitoring project budget,

- Issuing comprehensive monthly Status Report (including Executive Summary, Project Description, Project Directory, Organization Chart, Project Status, and financial summary consisting of funds allocated, Funds Obligated, Pending Obligations, Reservations, Purchase Orders, RWA Summary, Contract Record, Project Schedule, Log of No Cost Letter Directives, Change Order Analysis),

- Keeping and managing of time and CM attendance log,

- Coordinating all financial and cost issues with GSA funds validation clerks, GSA finance, D.C. Courts Finance

- Performing and any additional finance / budget related services

- Maintaining contracts modifications in GSA Comprizon Database

- Reconciliation project budget with GSA FMIS and Near Databases.

- Setting up and maintaining very complex data basis, spreadsheets, and utilizing latest versions of commercial software applicable to budgets, accounting, cost monitoring, and project management.

4.  Office Support (OFS). OFS will be responsible for all administrative and secretarial duties including answering the phones, copying, faxing, filing, establishing and maintaining complex computerized data bases, establishing and maintaining complex computerized spreadsheets, digital photography (including image manipulation and prevention and digital photo archiving) ,  electronic storage of information, maintaining all office equipment including computers, setting up, monitoring and training for office network, making deliveries, overseeing certified payroll and any additional services required

## 5. Senior Architects/ Senior Engineer (SAR/SEN).  The CM employee designated    as the senior level representative responsible oversight and implementation of all       architectural, engineering and technical aspects of CM effort. This position includes    Senior Architect, Senior Electrical Engineer, and Senior Mechanical Engineer. The     SAR/SEN shall be energetic, detail oriented and pro-actively manage and                   administer all work for which the SAR/SEN is responsible through all phases of the     project. SAR/SEN duties include:

## During pre-design phase services, the SAR/SEN shall be responsible for:

## Preparation of applicable portions of Project Management Plan and Project Procedures Manual and shall assist with preparation of management information system

## Arrange for and conducting pre-design meetings

## Coordinate applicable portions of pre-design work such as master plan,   design intent drawings, concept design (for “design build” project), studies, analysis

## Coordinate all effort with NCPC, Commission of Fine Arts, D.C Historical Preservation Officer

## Preparation of design and “design-build” scope of work.

## Preparation of preliminary IGE for design services and design component of “design-build” services.

## During design procurement phase services, the SAR/SEN shall be responsible for:

- Assistance with preparation of A/E scope of work,

- Preparation of Independent Government Estimate (IGE) for A/E and design Services

- Evaluation of A/E proposals and preparation of pre-negotiation memorandum

- Assistance with A/E negotiation

- Preparation of negotiations memorandum

- Assistance with issuance of the A/E contract

## During design phase services, the SAR/SEN shall be responsible for:

## Monitoring design services performed by other parties,

## Scheduling, coordinating and overseeing design reviews,

- Conducting constructibility reviews

## Coordinating Value Engineering effort

## Assisting with A/E contract administration including preparing requests for proposals with detailed scopes for additional services, preparing IGE, reviewing proposals and preparing pre-negotiation memorandum, assisting with negotiations, preparing record of negotiations, and coordinating issuance of contract modifications (all project phases).

## Receiving, reviewing and assisting with processing pay requests for design services.

## During construction (or “design-build’) procurement phase services, the SAR/SEN shall be responsible for:

- Assisting in preparation of IGE based on documents used in obtaining proposals.

- Assisting in preparing adjustments to IGE to reflecting addenda.

- Compiling documents and distributing them to interested parties as authorized by C.O.

- Conducting (with A/E assistance) pre-proposal conference and site visit with preplanned and scripted descriptions and pre-determined stops along the site visit.

- Receiving questions and inquiries from interested offerrors and researching and obtaining answers to the questions and issuing written responses to the questions. This function shall be performed through CO.

- Keeping detailed log of all questions and status of replies

- Compiling replies to questions and assisting with issuance of addenda.

- Assisting CO with receipt of proposals

- Assisting CO with evaluation of proposals

- Assisting CO with negotiations with short listed contractors

- Assisting CO with issuance of the contract

## During construction phase services, the SAR/SEN shall be responsible for:

## Monitoring contractor’s performance

## Keeping an updated set of drawings and specifications

## Performing inspections

## Resolving issues and problems,

## Coordinating resolution of difficult issues with A/E

## Overseeing inspectors

## Receiving RFI’s and either responding to them or coordinate responses with an A/E

## In response to contractor’s requests for equitable adjustment, performing determination of a need for equitable adjustment and preparing recommendation for CO consideration.

## Preparing scope of work and requests for proposals for change order work

## Assisting in preparation of IGE

## Assisting with review of change order proposals

## Assisting with comparison of IGE with proposals and preparation of pre-negotiation objective memorandum

## Assisting with change order negotiations

## Assisting with preparation of negotiations memorandum

## Receiving shop drawings and submittals and coordinating reviews with A/E.

## Monitoring design for design deficiencies and assisting with recovery, where applicable.

## Preparing all correspondence within the applicable area of expertise

- Assessing and evaluating all issued change orders on the project to determine if they were caused design deficiencies by the A/E of record, assigning dollar value to the design deficiencies.

- Coordinating start-up and commissioning

## During post construction phase services, the SAR/SEN shall be responsible for:

## Organization of O & M Manuals, delivery of manuals to operations entities and documenting the deliveries.

- Reviewing all applicable Design Deficiencies and assisting Project Executive in recovering funds from the A/E.

## Assembling record drawings, delivery of record drawings to operations and DC Courts Engineering entities, and documenting the deliveries.

## Monitoring and contractor follow-up with punch list, remaining items, new issues and general resolution of all remaining construction, design and operational issues.

- Preparing, issuing and documenting a list of all mechanical and electrical equipment, including a date of substantial completion, and warrantee information.

## Assisting with tenant move-in

## Coordinating start-up and commissioning

## Assisting with project closeouts.

## 6. Engineers/Technicians (TEN/TTE).  The TEN/TTE are responsible for the performance of testing work.  TE/Ts can be employees of the CM or of a testing laboratory, but in either case must be approved by the COR.

## 7. Inspectors (INS).  The CM employees responsible for scheduling, coordinating, and performing the actual specialized field inspection work commensurate with their designated adjectival discipline.  Relative to their respective disciplines, Inspectors are required to physically inspect work at the site(s) for code compliance and adherence to construction contract requirements; recommend approvals or rejections of materials and workmanship as appropriate; monitor labor and safety requirements; complete written inspection reports for every test and inspection; process field reports through the QCS for the Government; maintain inspection logs and records of defects and/or omissions; and similar activities. INS shall take pro-active and aggressive role in resolving (or attempting to resolve) all field problems (quality, testing, contract compliance, etc.) as they occur. For problems that they can not resolve on their own, they shall be responsible for assisting QCS and/or SAR/SEN  in resolving them and shall be responsible for monitoring the resolution.

8. Senior Estimator (SES). SES will be responsible for reviewing all requests for proposal (CE), preparing independent government estimates before arrival of proposals, evaluating proposals and preparing pre-negotiation memorandum,  obtaining Government approvals prior to negotiations, negotiating change orders, preparing negotiation memoranda, assisting FM in preparation of change orders. SEST will be responsible for all trades and disciplines including demolition, site, architectural, mechanical, plumbing, and electrical and equipment.

9. Estimator (EST). Responsibilities similar to SEST except for expertise in selected (not all) trades.

10. Scheduler (SCH). Schedule shall be responsible for evaluating and recommending approval of contractor submitted baseline schedule, preparation of as planned schedule, review of contractor schedule submittals, assessing with aggressive claims prevention program and assisting with time extension requests and claims defense.

# C.8  References

###### (a)  		Reference materials or appropriate portions thereof will be made available after award, as applicable to the project, upon written request by the CM.  GSA will also provide all references contained in the AE scope of work, and other Government guidelines and handbooks as the needs arise.

(b)  		The CM must become familiar with and use the versions/ revisions in effect as of the effective date of each major Project Phase under this contract, and the CM is required to comply with the policies and procedures set forth in all such references.

- PBS-P100 Facilities Standards for the Public Buildings Service. www.oca.gsa.gov

- PBS-PQ 250 – Value Engineering Program Guide for Design and Construction, Volume 1, December 1992.  - www.oca.gsa.gov

- PBS-P 3440.5 – Project Estimating Requirements, August 24, 1981.

- PBS-P 3440.7 – Estimating Construction Modifications, July 1983.

- Life-Cycle Costing Manual for the Federal Energy Management Program, (NIST Handbook 135).

- Instructions for Developing Construction Cost Estimates, October 1994.

- “General Guide for Editing Specifications”, April 1988.

- Leadership in Energy and Environmental Design (LEED) of the U.S. Green Building Council.

- Environmental Management Technical Guides, GSA Safety and Environmental Branch.

- HUD document; “Lead Based Paint Interim Guidelines for Hazard Identification and Abatement” dated June 1995.

- Federal Property Management Regulations (FPMR), Temporary Regulation D-76.

- “Streetscape Manual,”Architectural/ Engineering Subgroup, August 1992. www.nps.gov/streetscape/

- Energy Policy Act of 1992 (PL 102-486).

- International Building Code (IBC), maintained by the International Code Council.

- For all projects, the egress requirements of the National Fire Protection Association (NFPA), Life Safety Code shall apply in lieu of other code references.

- For all projects, the electrical requirements of the National Fire Protection Association (NFPA), National Electric Code, have been adopted by GSA in lieu to the electrical requirements of the national model building codes.

- International Mechanical Code (IMC).

- International Plumbing Code (IPC).

- Elevator Code – ASME A17.1, and with the UFAS/ADA Accessibility Guidelines.

- Occupational Safety and Health Regulations for Construction; 29 CFR, Parts 1926 and 1910.

- Environmental Protection Agency Regulations.

- Uniform Federal Accessibility Standards (UFAS) is mandatory on all GSA projects.  Current GSA policy also encourages compliance with the requirements of the American with Disabilities Act Accessibility Guidelines (ADAAG) where those requirements are stricter that UFAS. The A/E is responsible for checking whether there are local accessibility requirements.  If they exist, the most stringent will prevail between local and UFAS/ADA.

- Applicable local DC codes and regulations.

- National Fire Protection Association (NFPA) Standards.

- Washington Suburban Sanitary Commission (WSSC) Plumbing Codes.

- Occupational Safety and Health Standards.

- American National Standards Institute (ANSI) Publications.

- The Institute of Electrical and Electronics Engineers (IEEE), Inc., Publications.

- National Electrical Manufacturers Association (NEMA) Publications.

- American Waterworks Association (AWWA).

- Federal Information Processing Standard 175: Federal Building Standard for Telecommunication Pathways and Spaces (see also Electronic Industries Association (EIA/TIA Standard 568-A and related bulletins).

- Federal Information Processing Standard 174-1:Federal Building Telecommunications Wiring Standard (see also Electronic Industries Association EIA/TIA Standard 569 and related bulletins).

- National Roof Contractors Association (NRCA), “Roofing and Waterproofing Manual.”

- American Association of Nurserymen: ANSI Z60.1.

- All Codes and Standards listed in the P100 (excluding metric requirements).

C.9  GENERAL REQUIREMENTS

###### (a)  		Contract award will include various phase services.  The numbers, types, and functional involvement of the CM's personnel and/or teams may vary during performance of this contract, however, CM staff commitment is required throughout the project as accepted in its proposal.  No key personnel may be substituted at any time during the life of the project(s) without the express advance consent of the CO.  The CM is required to take the initiative and actively pursue the earliest possible completion of all services.  There may be periods of inactivity during the project.  The CM must manage its staff commitments during such fluctuations.  Accordingly, the CM shall perform various phase services plus Supplementing, Miscellaneous, Claims, Additional, and Testing Services when requested by the Government, as appropriate, adequate and necessary to ensure that:

(1)  Construction work is performed within budget and in conformity with all applicable requirements.

(2)  All construction is completed as early as possible, but not later than the scheduled construction contract completion dates.

- The project is considered to be highly complex. Services which the CM is required to provide include, but are not limited to, those described or specified herein (Section C) and all other sections in the RFP.  The services so described or specified shall not be deemed to constitute a comprehensive specification having the effect of excluding services not specifically mentioned; the CM is required to furnish all other services necessary to fulfill the undertakings set out in this contract within the lump sum price.  No services are reimbursable unless specifically indicated.

(c)   	The CM will not be held responsible for:

    - Design deficiencies.

    - Defective completion of construction, provided that the CM exercised all due diligence, utilizing competent personnel within authorized limitations, to make reasonably certain that construction was performed in conformity with applicable construction contract plans and specifications.

(3)  Time overruns, provided the CM has taken all reasonable measures to anticipate problems and delays, and to eliminate or minimize their adverse impacts on completion of construction by scheduled construction milestone dates.

(d)  	With the exception of miscellaneous items as stated in this contract, the CM shall not be responsible for and shall not have control or charge of construction means, methods, techniques, sequences or procedures; safety contractors, agents or employees, or any other persons performing any of the work.

(e)  	The CM agrees to furnish skills and judgements, and to perform all required services in the most effective, efficient and economical manner consistent with the interests of the Government.

C.10 PROJECT MANAGEMENT PLANS

(a)  	General. For each project, and within 30 calendar days after execution of the Notice to Proceed, the CM shall develop and submit to the COR a detailed Draft  Project Management Plan (PMP).  Three copies of each plan must be submitted to the COR in three ring, slant ring binders, and all subsequent updates must be submitted on pre-punched documents for ready insertions.  In developing this plan and its updates, the CM must work closely with GSA (including Federal Protective Service), DC Courts, US Courts, US Marshal, Courts, Consultants, the AE, the construction contractor(s), and other appropriate firms and individuals involved with the project.  Following a Government review of the Draft MPMP, the CM shall incorporate Government comments, and issue a final MPMP within 10 days of receipt of Government comments. The preparation of the PMP and subsequent updates are included in the Standard Services – Core Team. Throughout the life of the project (or CM period of performance) the PMP shall be updated and kept current. PMP and its content shall be confidential between the Government and the CM.

(b)  	Contents.  The PMP must be detailed and fully describe the program and requirements for executing the work planned for entire project, and the participating organizations. To achieve desirable uniformity in preparation and use, the plan must include all of the following sections:

        - Project Description.  Known characteristics of the project described in general terms that reflect the requirements of the Government, including security clearance requirements.  Also, include a detailed site use plan.

        - Master and Milestone Schedules

        - Budget / Work Breakdown Structure

        - Quality Management Approach

        - Site Mobilization Plan

        - Roles and Responsibilities

        - Organization Chart / Staffing Plan

        - Environmental Concerns

        - Communications Protocol

        - Procurement Strategies

C.11 PROJECT PROCEDURES MANUAL

(a)	General. Within 30 calendar days after execution of the Notice to Proceed, the CM shall     develop and submit to the COR a detailed Draft Project Procedures Manual (PPM).  Three copies of the manual must be submitted to the COR in three ring, slant ring binders, and      all subsequent updates must be submitted on pre-punched documents for ready insertions.  In developing this manual and its updates, the CM must work closely with GSA, the AE, the construction contractor(s), and other appropriate firms and individuals involved with the project.  Following a Government review of the Draft PPM, the CM shall incorporate Government comments, and issue a final PPM within 10 days of receipt of Government comments. The preparation of the PPM and subsequent updates are included in the Standard Services – Core Team. Throughout the life of the project (or CM period of performance) the PPM shall be updated and kept current. PPM and its content shall be confidential between the Government and the CM.

(b)	Contents.  The PPM must be detailed and fully describe the program and requirements for executing the work planned for entire project, and the participating organizations. To achieve desirable uniformity in preparation and use, the plan must include all of the following sections:

- Budget and systems to monitor and control costs

- Quality Assurance Program

- Schedule preparation, updates, monitoring and plans for pro-active management and minimization of anticipated delays

- Detailed and specific systems, methods and procedures

- Functional responsibilities and authority levels and limits

- Procedures for contractor coordination

- Safety programs

- Various check (or verification) lists

- Scheduled meetings, types and frequencies

- Sample forms

- Procedures for procurement

- Procedures for monitoring construction

- Correspondence, RFI’s, submittals, change-orders distribution matrix.

- Procedures in case of an emergency (caused by the project and/or caused by circumstances outside the project.

C.12 INFORMATION MANAGEMENT SYSTEM (MIS)

(a)  		The CM must manipulate data and data bases as specified herein.  In turn, information may be delivered to the CM in electronic format.  MIS needs to address status and forecast in the context of the PMP, be used as a basis of problem and variance management including identification, evaluation and management, address information needs, data sources and control elements for quality, cost and schedule control, be able to accept continuous data input and be an efficient communication tool for all stakeholders. As a minimum, the MIS shall include the following:

- General correspondence

- RFI’s

- Periodic reports of performance for various activities

- Schedule of drawings, specifications and other construction documents

- Submittals

- Transmittals

- Change orders (including requests, evaluations, estimates, records of negotiation)

- Weather information

- Contract actions and issues

- Material control

- Meeting minutes and sign up sheets

- Records of telephone conversations

- Record of oral instructions (if any), field instructions and formal directives

- Record of controlled inspections

- Record of nonconforming work

- Scheduling records

- Progress and other project photos and videos

- Issues listing with all supporting facts and evidence

- Progress reports and rercords

(b)   	For each employee located full time at the site, the CM shall provide its own ADP               hardware/computer equipment and software to fully satisfy all operational requirements of the   contract.  All associated costs must be included in the established pricing for this contract as no reimbursement is authorized for such items.  The CM’s computer software must be compatible with software used by the Government including latest version of Windows, MS Office Professional, MS Project, Primavera, and Photoshop.

C.13  PROGRESS REPORTS AND RECORDS

(a)  	Keep accurate and detailed computerized/written records of progress on the project during all stages.  Maintain frequent contacts by telephone, site visits, meetings, etc., with all parties involved in the project and file weekly hard copy/written progress reports. Reports shall include information concerning the work of the AE and other contractors, initiatives taken by the CM to preclude delays, percentages of completion, number and amounts of modifications and claims, analyses of the schedule, and other analyses necessary to compare actual performance with planned performance. The CM must use any applicable GSA forms and standard GSA procedures.

(b)  	Provide computer generated progress schedules, with monthly updates reflecting actual progress of the project against previously projected progress, for all Project Phases.

(c)  		Monitor and enter all construction Change Orders as issued by the CO and COR on the CPM data files.  Analyze the effects of all Change Orders entailing time delays and their impacts on the construction schedules.  Make periodic reports when and as required by the COR.  These reports must include the compatible CPM schedule, all Change Orders issued to that point in time, and narratives addressing cause and effect relationships.

C.14  CONSTRUCTION SITE OFFICE FACILITIES

(a)  	Field Office Facilities for CM own use. The CM will provide and maintain adequate site office space with basic utilities (heat, air conditioning, water, electricity, rest-room facilities) for the CM and GSA project team.  The office will house the CM on-site staff during the CM’s contract performance.  The field office shall include furniture, file cabinets, tables, chairs, equipment,  facsimile machine, digital cameras, video cameras, TV, VCR, supplies, and physical security for its facilities. All equipment furnished by the CM (including equipment furnished for the use by the Government) must include maintenance service contracts and all supplies. The CM shall be responsible for regular cleaning of the office. The office can be in construction trailers or in a leased facility within half a mile of the furthest construction area. In addition to adequate space for CM personnel and filing, there shall be a furnished conference area for 20 people. The Government will not be responsible for any losses of items from such facilities.  Upon completion of work the CM shall be responsible for the immediate removal of any temporary facilities, equipment, and any related furnishings, and for cleaning and restoration of the site/location.

NOTE:  ADP hardware and software required of the CM must be provided in accordance with Section B.

(b)  	Field Office Facilities for Government use. The CM shall provide, within its site office, a private and   secure (with lockable door) space (minimum 260 square feet) for use by two government officials.  The space shall have windows, window coverings such as mini-blinds, shall be carpeted with good quality commercial product and shall have good quality lighting with a minimum of 50 foot candle level at 30 inch above floor height. Climatic controls shall include heating, and air-conditioning with controls independent from other areas. CM shall  provide for Government use, the following furnishings and equipment:

(1)  Furniture

|  | 2 desks (42” x 60”), with return, laminate or wood top, single pedestal at the desk and pedestal at the return, with lockable drawers including center drawer. |
| --- | --- |
|  | 2 desk chairs with arms, height adjustment swivel tilt control, 5 span base with easy rolling casters. |
|  | 2 side chairs with arms |
|  | 1 Drafting stool with built in foot rest, pneumatic height adjustment |
|  | 3 Letter size, 4 drawer lateral file cabinets, full suspension lockable drawers, laminate top, include 600 hanging folders. |
|  | 1 Plan table, 37” x 72” with adjustable top and task lighting (can be shared if GSA and CM offices are in the same space). |
|  | 1 Mobile (on rollers) stand (vertical filing system for drawings) adjustable height for sheets up to 54”, 27” wide, 42” clamp length, free standing (can be shared if GSA and CM offices are in the same space). |
|  | 2 Bookshelfs, 36” wide, 3 shelves high, with laminate top. |
|  | 1 Printer/fax table |
|  | 1 Coat rack. |
|  | 1 Storage cabinet, lockable, for office supplies. |

(2) Telephones and equipment:

|  | 2 digital cordless (2.4 Gh) telephones, including dedicated private local service number for the duration of the project. The telephones shall have speaker, hold and 25 number speed dialing. The phones shall be connected to a digital voice mail and will be part of a system capable of being answered by the CM secretary. (Any long distance charges, for calls made by the Government employees, will be paid for by the Government to the CM, providing CM can furnish proper documentation as determined by CO. |
| --- | --- |
|  | 1 Fax machine with dedicated private local service. (Long distance charges, if any, will be paid for by the Government to the CM.) The Fax machine will use plain paper; have a speed dial and a 50 page memory. |

(3)  Other equipment:

|  | 1 Color Laser Printer |
| --- | --- |
|  | 1 Color photocopy machine with enlargement, reduction, sorting and collating capability and capable of copying on paper up to 11” x 17”. If the office space for the Government use is in the same location as the CM office, the photocopy machine can be shared. If the GSA office is located away from the CM office, the copier shall be provided for GSA’s exclusive use in the GSA location. |

# C.15  RECORDS OF SERVICES PROVIDED

(a).  	Registration Logs:  The CM shall maintain registration logs at the job site.

(1)  	All CM employees, and the CM's consultants and subcontractors, shall sign the logs when reporting to and leaving the site.

(2)  	All logs shall be clearly legible and show services provided (e.g. review concepts, inspect foundation steel,  meet with AE to discuss availability of stonework, etc.), location(s) where the services were provided,  the names and positions of CM personnel providing the services, and the number of hours each person spent on performing the services.  The originals of these logs will be retained by the CM.  Copies of monthly logs must be sent along with progress payment requests to the COR in support of the invoice in accordance with FAR 52.232-25.  Payment requests will not be considered unless accompanied by the logs.

(3)  	Logs will be available for inspections by the Government at all times.

(b)  	Status Information:  The CM will keep Government and AE representatives fully apprised of project activities, schedules, and any issues relative to work in progress.

C.16  CONTRACTOR PERSONNEL STAFFING AND ASSIGNMENTS

(a)  	Assignments.  The CM agrees to provide office support (secretarial and/or clerical, administrative) , technical, and professional personnel as required herein and as negotiated and agreed upon for performing work specified during the duration of the CM contract.  The CM must provide a dedicated, stable, and technically qualified staff to maintain continuity in the level of services.  The people named in the proposal shall actually perform the contract; requests for substitutions in the original staffing proposed, evaluated, and accepted are undesirable and will be stringently reviewed.  Substitutions are not permitted unless authorized in advance and in writing by the Contracting Officer (CO).

(b)  	Staffing.  Before performance of any contract work, the CM must provide the most appropriately qualified members of its staff.  The CM is required to submit for administrative approval by the COR listings of the project team members by names, organizations, and roles along with their resumes, if not provided in the CM’s proposal.

(c)  	Subcontractors and Consultants.  Substitutions of subcontracted or consultant firms included in the proposal are subject to the written approval of the CO.  This contract must be modified, via a formal contract modification, before a follow-on firm commences work.  Changes in individuals employed by these firms will be approved administratively by letter between the COR and CM.

C.17  ACCEPTANCE AND QUALIFICATIONS

(a)  	Acceptance:  In the event that any of the personnel/consultants named are unable to perform because of death, illness, resignation from the CM's employ, dissolution of agreement, or other reasons, the CM shall promptly submit to the COR detailed written explanations of the circumstances necessitating the proposed substitutions, complete resumes for the proposed substitutes, and any other information deemed pertinent to approvals of substitutions.  No substitutions shall be made without the prior written approval of the Government.  No increases in contract pricing will be allowed when substitutions are authorized by the Government.

(b)  	Removal:  The COR shall have the right to effect removals of any CM employees at any time during the life of this contract, if those employees are deemed by the COR not to possess the proper level of competence, abilities, energy or pro-active performance, or who are otherwise found to be unsuitable for work required under this contract.  In such cases, the CM must promptly submit the names, complete resumes for the proposed substitutes, and any other information pertinent to approvals of substitutions.

(c)  	Further Documentation:  The COR is authorized to require that the CM provide further evidence and/or demonstration of abilities and/or suitability for their intended positions.  This may include additional work examples and/or other evidence, oral interviews and/or testing, and/or other appropriate means.

C.18  SPECIAL PERSONNEL QUALIFICATIONS:  Personnel possessing unique technical specialties may be required for supplementary services related to the scope of regular services.  Such personnel shall have qualifications as required and approved by the COR which are appropriate to the nature of the services that will be provided.

C.19  FAILURE TO PROVIDE QUALIFIED PERSONNEL:  Repeated failure or excessive delays by the CM to provide qualified personnel, who meet the stated requirements, may be deemed sufficient reason by the COR to recommend termination for default to the Contracting Officer for work under this contract.

C.20  ORIENTATION OF PERSONNEL:  The CM may be required to send its key personnel to the GSA Regional Office for up to 2 working days of orientation in Government policies and procedures, as required, by the COR.  Subsequent to GSA orientation, the CM is responsible for providing instructions to other team members working under this contract, and to ensure that all project personnel are aware of applicable Government regulations, policies, procedures, and uses of forms affecting the conduct of their work.  Orientation must be initiated and arranged for by the CM immediately after contract award.

C.21  SECURITY CLEARANCES:  Not required for the performance of this contract.

C.22  PRE-DESIGN PHASE SERVICES (including portions of pre-design for the “design-build” project.):  Core team members shall perform Pre-Design Phase Services.  The services shall consist of:

- Project organization

- Preparation of Project Management Plan

- Preparation of Project Procedures Manual

- Conducting pre-design meetings

- Coordinating ongoing pre-design work such as master plans, design intent drawings, concept design (for “design build” project) studies, analysis, etc. This work is being performed by contractors procured by GSA ahead of design phase services.

- Assistance with preparation of A/E scope of work,

- Establishing management information system

C.23  DESIGN PROCUREMENT SERVICES (including portions of design-build procurement dealing with design):  Core team members shall perform Design Procurement Phase Services.  The services shall consist of:

- Assistance with preparation of A/E scope of work,

- Preparation of Independent Government Estimate (IGE) for A/E Services

- Review of A/E cost proposals and preparation of pre-negotiation objective memorandum

- Assistance with A/E negotiation

- Preparation of price negotiations memorandum

- Obtaining funds validations for A/E contract

- Assistance with issuance of the A/E contract

C.24  DESIGN PHASE SERVICES (including portions of “design-build” project dealing with design):  Core team members shall perform Design Phase Services.  The services shall consist of:

- Conducting pre-design conference

- Coordinating and arranging for Value Engineering Analysis at preliminary design stage.

- Participating in Value Engineering workshops

- Participating in Partnering sessions.

- Design document review at various stages of completion

- Coordination of reviews with GSA (Senior experts and others including elevators, fire protection and environmental, concessions, historical preservation, etc.) and courts personnel.

- Document distribution

- Assistance with preparation of A/E contract modifications including requesting proposals, preparing IGE, analyzing proposals and preparing pre-negotiation memorandum, assisting with negotiations, obtaining funds validation and preparing modifications for CO signature

- Preparing general conditions for inclusion into A/E specifications.

- Monitoring project funding and cost control and evaluating estimated construction costs throughout the design process

- Scheduling and conducting meetings

- Time control

- Coordinating and consulting with various entities such as NCPC, Fine Arts, D.C. Historical preservation Officer, D.C. Courts, U.S Marshall Service, Federal Protective Service, D.C. permits and inspections, other adjacent projects, etc.

C.25 CONSTRUCTION PROCUREMENT PHASE SERVICES: (including portions of design-build procurement dealing with construction):  Core team members shall perform Construction Procurement Phase Services.  The services shall consist of:

- Preparing IGE based on documents used for obtaining proposals.

- Preparing adjustments to IGE to reflect addenda.

- Compiling documents and distributing them to interested parties as authorized by C.O.

- Conducting (with A/E assistance) pre-proposal conference and site visit with pre planned and scripted descriptions and pre-determined stops along the site visit.

- Receiving questions and inquiries from interested offerrors and researching and obtaining answers to the questions.

- Keeping detailed log of all questions and status of replies

- Compiling replies to questions and assisting with issuance of addenda

- Assisting CO with receipt of proposals

- Assisting CO with evaluation of proposals

- Assisting CO with negotiations with short listed contractors

- Assisting CO with issuance of the contract

NOTE:  When procurement services are required, employees of the CM who are involved may be deemed Procurement Officials.  As such, they will be subject to the execution of the certifications required by the provisions of Section 27 of the Federal Procurement Policy Act (41 USC 423).  The CO must be consulted in advance with respect to these statutory requirements.

C.26  CONSTRUCTION PHASE SERVICES.  Construction Phase Services shall be performed by Core Team members shall perform Post Construction Phase Services.  The CM is required to operate in both anticipatory and pro-active modes; the CM must take the initiative, act in advance to generate activity, and follow-up so that construction is started and completed as early as possible. The CM must use any applicable GSA forms and procedures as instructed by the COR. The services shall consist of:

- Set up logically organized and indexed job files and working folders for a complete record keeping system to be used for the project.  Record all incoming and outgoing communications.  Maintain a detailed daily diary and a running log of all events affecting project activities and progress; provide copies as instructed by the COR.  File content and documentation must be satisfactory to the COR.

- The CM must use log books to record all daily activities and events.  The CM is required to enforce the daily use and maintenance of all record logs.

- Monitor all construction activities scheduled, with emphasis on milestones, phasing/sequencing, submittals, efficient and balanced work flow, major tests, and any unique requirements needing special scheduling or tracking.  Inform the COR on the progress of construction work and any activities that affect ABMC.

- Maintain logs for registering receipt of required submittals, posting dates received and actions taken.  Monitor the submittal process to ensure timely submissions, approvals of shop drawings, approvals of samples of materials, and other submittals, and maintain logs of both authorized and disapproved Change Orders as instructed by the COR.  Notify, in writing, the parties delaying any submittals.

- Maintain current at the site or as instructed by the COR records on all contracts, including but not limited to, correspondence issued and received; documents related to project plans, samples, requisitions, materials, equipment; change orders; inspections; claims; and any others deemed pertinent.

- Participate in all “Partnering” workshops, sessions, etc. conducted in relation to the project.

- Coordinate with any GSA Testing Service Contractor(s).

- Prepare correspondence as necessary to respond to contractor(s), clients; answer questions which arise requiring clarification (including construction contractor initiated RFI’s); confirm project matters, etc.  Documentation of all actions taken and decisions made during the course of a project is essential to build an accurate project history for future reference.

- Recommend reviews of particular drawings and/or sketches as needed for clarifications or changes.

- Assist in handling disputed project issues.  Provide input for preparation of Government position, prepare related correspondence, and, when required, draft final decision letters denying contractor’s position which initiates the formal claim/dispute process.

- As-Built Drawings.  Maintain at the job site a current marked set of working drawing prints and specifications (obtained from the Government), indicating thereon all changes and deviations from original construction contract documents.  Check these marked prints against those maintained by the construction contractor as changes occur: reconcile any differences.  Upon completion of construction, deliver the marked set of documents and drawings to the AE.  When CADD generated, these must be in a format that is compatible with the system used by the Government.

- Maintain listings of observed defects and omissions. Provide copies of the initial  listing to the construction contractor(s) and the COR.  Whenever changes are made to the listing, provide copies of those changes to the construction contractor(s) and the COR.  Make recommendations to the COR relative to phased occupancy and/or final inspection and acceptance of the facility.

- Monitor and inspect the construction contractor's compliance with current safety     regulations, standards, the project safety plan, and report any noncompliance to the COR.  Immediately notify the Government when any life threatening conditions are observed, and provide assistance as necessary to remedy such situations.  Prepare and process any accident and fire reports as instructed by the COR.

- Maintain site records on the construction contractor's compliance with labor standards.

- Labor Standards Monitoring.  The CM must monitor compliance with the labor standards requirements of the construction contract(s).  The CM will interview a minimum of two employees per month per contract, either general contractor or subcontractor(s) employees, to verify proper classifications and wage rates, and check the posting of the current effective wage rate decision at the site, as required in regulations issued by the Department of Labor implementing construction labor standards (29 CFR Part 5).  The CM will observe and report to the COR any disproportionate ratio/number of laborers, helpers, trainees and apprentices to journeymen.  The CM must verify that apprentices are enrolled in a bona fide apprentice program.  The CM will review all construction contractor payrolls after receipt from the construction contractor(s).  The CM will be responsible for preparing cover letters and GSA Forms 2017 and 1995 informing contractors of violations and corrective actions to be taken; these will be signed by the COR.  The CM must maintain a suspense system on all violations reported, and follow-up as necessary and/or as required by the Government until every violation is resolved.

(p)	Review and verify all requests for payments submitted by the construction contractor(s).  In all cases, submit recommendations concerning approvals to the COR within 3 calendar days of dates payment requests are received.

(1) 	The CM's reviews of all payment requests will be based on the construction contractor's itemized schedule of values for the project.

(2) 	As part of the payment review process, conduct monthly meetings with the construction contractor(s) to reach agreement on requisition amounts, before receiving requests for payments.  The agreed upon dollar amounts will be based on correct materials delivered and/or in secured storage on or off site, proper materials installed, and percentage of work satisfactorily completed and in place.  The CM must physically verify all of these prerequisites before recommending approvals of payment requests.

(3) 	Recommendations must be based on subparagraphs (a) and (b) above.  The CM will prepare typed vouchers reflecting resolved recommendations on Standard Forms (SF)-1034, GSA Forms 184, 184A, and 184B, other forms as instructed by the COR, any related/supporting documentation, and submit them to the COR. CM shall hand deliver all pay requests for all required signatures and shall hand deliver signed pay request to the CO for processing.

(q)	Review and verify all certified payrolls/payment vouchers submitted by the					construction contractor(s) in accordance with Davis-Bacon Act requirements.  In    			all cases, review, verify, and report the results to the COR within 3 calendar  	days.

(r)	Schedule and conduct progress meetings, weekly or as instructed by the COR, with all concerned parties to review the project, discuss problems, and resolve issues as necessary.

(s)		Arrange for and participate in all construction related conferences.  The CM will take minutes of all meetings; the format and content must be acceptable to the COR.  Minutes must include the meeting date and time; agenda; meeting location; list of participants with their affiliations, addresses, and telephone numbers; be fully descriptive of issues, problems, and decisions made; and action items with names of responsible parties and handout materials, unless the materials are part of a formal submission.  The CM will provide complete copies of all minutes to the Project Executive (hand deliver), COR and all attendees within 1 working day.  All challenges to the minutes will be reflected in revised versions, with distribution to everyone who received the previous account.

(t)	The CM will submit daily, weekly, and monthly reports addressing all project operations, and prepare any special reports and/or exhibits as required by the COR.

(u)		Monitor the design and construction clarification process, and when appropriate remind the AE and other parties involved of the need for timely actions.  Maintain logs of all clarifications requested.  Provide written responses to contractor questions and/or firms requesting design clarifications.  The CM must make all parties aware of responses given to information requests, and confirm the agreement of all parties on the contract interpretation. Any written communications that should or must be signed by the Government will normally be prepared for the signature of the COR.

(v)		Inspect the installation of materials and/or workmanship in accordance with GSA policies and procedures, and assure compliance with all construction contract specifications and all other project requirements.  All CM manpower assignments for construction inspection must be coordinated with the COR prior to performance.  Where defects may be addressed by ensuing work, the CM will immediately arrange for additional reviews by the Government before the construction work proceeds.

(w)		Inspect work performed by the contractor(s) for conformity with the requirements of the construction contract.  Prepare progress and completion inspection reports.  Maintain daily logs on corrections required and their status.  Inspect and report all qualitative and quantitative differences between construction contract deliverables ordered and received. At the minimum, the CM must compare construction deliverables received to approved plans and specifications together with the construction contractor(s) schedules of values and requisitions. In addition, the Government may provide site inspection personnel who will furnish inspection reports, and advise on content and procedures.  The CM must follow-up on all corrections of deficiencies noted by CM and GSA personnel.  Immediately notify the COR in writing if the construction contractor(s) fail to promptly correct deficient work and/or deliverables.

(x)		Recommend rejections of materials and/or workmanship not conforming to contract/project requirements.  Provide written reports supporting any such rejections as instructed by the COR. When differences of interpretation are encountered, document the facts as obtained from all parties involved, and report them to the COR.

(y)		The CM will prepare completely all Change Order packages for the signature of the CO or COR, and handle all related processing.  (Includes estimating, participation in negotiations, etc.)

(z)		The CM shall monitor the project proactively to identify or warn the COR of contractor or government caused delays or any claim situation.  Recommend solutions for recovery from such actions.  Assist the government in claim avoidance.

(aa)		Preparing for Government issuance all substantial completion letters

(ab)		The CM shall, in anticipatory mode dealing with future claims, requests for equitable adjustments and requests for CO final decision, establish and maintain complete records of all contentious issues on the project. The records shall duplicate information stored in other places and shall be full and complete.

C.27 POST CONSTRUCTION PHASE SERVICES: Post Construction Phase Services shall be performed  by Core team members  shall perform Post Construction Phase Services.  The services shall consist of:

- Prepare all documents that will be required for project close-out at conclusion of each construction contract.

- Prepare and transmit documents connected with final payment

- Organize O&M manuals and transmit to DC Courts

- Assemble record drawings and transmit to DC Courts

- Assist with initial phases of operations and maintenance of the facility

- Monitor, resolve and complete all outstanding design, construction and tenant issues

- Implement project close-out

C28  Additional Supplementing Services.  Modifications under the “Change” Clause will be issued for these requirements as needed:

(a)		Perform surveys of the project site when required:

(1)  	Using subcontract or other resources, obtain and submit to the Government accurate/dimensioned records, in duplicate, of infrastructure data; building and approach lines; foundation data; elevations at bottoms of footings; superstructure data; floor levels; and approaches made as work progresses.  Records must be certified by a registered architect or engineer as appropriate.

(2)  	Upon completion of construction, obtain accurately dimensioned drawings showing locations and elevations of utility lines installed outside building lines.  Include locations of valves, connections, changes in direction and other details.  Points where utility lines emerge from the buildings must be located from building corners; points where utility lines leave the property must be located from lot monuments.

(3) 	Drawings will be of the specified types, sizes, finishes, accurately scaled, and/or otherwise prepared as required by the COR/PO;  the use of CADD may be required.  Smear proof and waterproof must be used, unless otherwise directed by the COR/PO.  Properly prepared drawings (scaled at 100%), and the CADD diskettes, if CADD is used, will be delivered to and become the property of the Government.

(b)		Provide reimbursable drafting/ CADD services when required for miscellaneous project drawings, with CADD support in a format compatible with the system used by the Government.

(c) 		Perform reviews of shop drawings as instructed by the COR based on submissions provided by the AE/COR/Government.

(d)		Progress and Final Photography (per Construction Phase).  All photographs and/or video tapes must be taken by a competent professional photographer experienced in architectural photography; all will become the property of the Government upon delivery to and acceptance by the COR.  Label each photograph/ video tape with a description including at least the following information: Identity of photographed contractor; Type of photograph (progress, special (indicate purpose), final); The date taken; Name and location of building; What was photographed and from where taken; Identities of the CM and the photographer. For each building or structure under contract, the CM must provide:

(1) 	Monthly.  A total of ten separate shots showing interior and exterior views in color each month of progress photographs in sharp focus, approximately 8x10 inches, mounted on 8-1/2xll -inch hardboard.  Photographs will be taken on the first working day of each month, weather permitting, whether or not any work was done during the preceding month.  Take the photographs from points selected by the COR, deliver two sets and the negatives to the COR, and retain one set at the site office for a total of three sets per month.

(2) 	Final.  Final color photographs, reproduced in duplicate, when the project is complete, taken on a bright, sunny day.  They must be produced with such artistic skill as to be suitable, as determined by the COR, for exhibition and reproduction. Deliver two sets and the negatives of all photographs to the COR, and retain one set at the site office for a total of three sets.

(i)  	Take exterior photographs from two points of view, one showing the entire front elevation and one side; the other showing the entire rear elevation and remaining side.  The front elevation must appear approximately three times the width of the side. For buildings with courtyards or atriums, take additional photographs from two points of view within the courtyards or atriums, each showing two sides.  A total of eight final exterior photographs, reproduced in triplicate, is required from points of view selected by the COR.

(ii)  	Take a total of ten interior photographs, reproduced in triplicate, from points of view selected by the COR.

(iii)  	Mechanical and Electrical Equipment. Take ten final color photographs of mechanical and electrical equipment, reproduced in triplicate, and taken from points selected by the COR.

    - Video Photography.  Provide color video cassette tapes, with sound, of construction work in progress, narrated to describe what is being seen.  When and as required by the COR, a minimum of one 10 minute taped presentation per week will be forwarded to the Government.  Individual taped presentations will be consolidated into master tapes which must be maintained at the site or as instructed by the COR.  The sequencing of all video tapes must be chronological and parallel the progress of physical work on the project; taping segments must reflect continuity in viewpoints of the various job areas so that progressive comparisons can be made by the Government.

(e)		Perform professional, technical and/or administrative services that may be requested by the Government .

C.29  CLAIMS SERVICES.  The CM must perform Claims Services when and as required by the Government.  Claims services will be obtained with a modification prepared using the extended contract Man Hour Rates.  Services for which pricing has not been established will be procured under the “Changes” clause. Throughout performance under this contract, the CM must take the initiative and act to mitigate circumstances that could lead to claims, resolve conflicts promptly, and keep the Government advised of any potential disputes.  A claim does not arise solely upon the occurrence of a dispute or controversy.   For definition purposes, Claims Services apply to handling disputed matters once a contractor has made written demand for payment or other relief under the contract and submitted it to the Contracting Officer for decision in accordance with the Disputes Act of 1978.  In relation to Claims Services, the CM will review disputes and claims from the A-E and/or construction contractor(s) and render all assistance that the Government may require, including, but not limited to the following:

- Furnishing reports with supporting information necessary to resolve disputes or defend against the claims.

- Preparation and assembly of appeal files.

- Participation in meetings or negotiations with claimants.

- Appearance in legal proceedings.

- Preparation of cost estimates for use in claims negotiations.

- Preparation of risk assessments/analyses relative to claim exposures.

- Preparation of findings of fact and any other documentation required by the Government.

C.30  SUBCONTRACTING.  All such work must be authorized in advance by the Government under the "Changes" clause.  When a subcontract is requested by the Government, the CM normally will obtain competitive bids/offers (minimum of 3).  The CM must prepare all solicitation documents, the Statements of Work with performance requirements, the cost estimates, price negotiation memorandums, and other documents as required by the COR.  Based on the quotes received, fair and reasonable fixed prices will be negotiated with the CM for having the requirements subcontracted.  In addition, the negotiated fixed prices will include an itemized administrative fee for procuring, awarding, and administering each subcontract. This administrative fee is negotiable and may vary according to the nature, extent, and complexity of the work involved, but in no case may it exceed 3 percent of the subcontract award amount. Additional mark-up for overhead and profit will not be authorized for these transactions.

C.31  ADDITIONAL SERVICES.  When required to support work being performed under any of the major Project Phases, the Government may authorize Additional Services such as those listed below.  All such work must be authorized in advance by the Government.  Mark-up for overhead and profit will not be authorized for these transactions, except for services procured under the "Changes" clause for which pricing has not been established.  When appropriate, such work will be required under the "Changes" Clause of this contract (new disciplines and work which are not itemized and priced in Part I, Section-B).

- Special consultant or special inspection services, such as assessments of hazardous materials, an Industrial Hygienist to monitor removal of hazardous material, a historic preservation consultant to review historically significant matters related to the project, etc.

- Unique services provided within six months after final settlement of the construction contract with the exception of Claims Services.

- Special studies and/or updates to prior studies.

- Other specialized services as may be requested by the COR, such as updates to master or environmental plans, interior space planning, existing site surveys, site models, etc.

- Tenant relocation and moving services at facilities other than those addressed by the project scope.

- Photographic records beyond the normal scope of presentation and inspection services required.

- Coordination of tenant moves.

- Expertise as required in unusual situations from specialty disciplines, such as expert testimony for hearings, etc.

- Certification services of trade societies, institutes, organizations, etc.

- Provision of special plant facilities and equipment such as: trailers, unusual testing apparatuses, etc.

- Construction phasing plans and schedules encompassing relocation of building occupants at facilities other than those addressed by this contract, i.e., moves into/out of temporary space, and into/out of new/renovated space.  Development of these plans will require close coordination with the AE and involved GSA offices.

- Occupancy planning and coordination, the CM must accomplish and/or provide for identifying, quantifying, and coordinating the activities necessary for relocating agency functions/departments among existing facilities including, but not limited to, the following:

(1) Schedule and coordinate the integration of occupancy activities.

(2) Identify construction and occupancy interfaces.

(3) Estimate costs.

(4) Provide timely alerts to agency representatives.

(5) Take all appropriate actions to mitigate delays and costs.

(6) Prepare and maintain master schedule(s) and updates.

(7) Develop relocation procedures.

(8) Develop inventory lists and provide for taking inventories.

(9) Develop pre-move activities.

(10) Assist in developing/processing/administering contracts for moving services for the project(s).

(11) Coordinate and monitor moving activities.

(12) Prepare and implement memoranda of understanding and interdepartmental/inter-agency agreements on occupancy activities.

(13) Develop and prepare for Government reproduction such facility/building orientation manuals as instructed by COR. Issue these manuals when required.

C.32  TESTING SERVICES.  When required to support work being performed under any of the major Project Phases, the Government may authorize Testing Services such as those listed below.  All such work must be authorized in advance by the Government.  Mark-up for overhead and profit will not be authorized for these transactions, except for services procured under the "Changes" clause for which pricing has not been established.  When appropriate, such work will be required under the "Changes" Clause of this contract (new disciplines and work which are not itemized and priced in Part I, Section-B).

- When and as applicable (consult the COR/CO), obtain and evaluate up to three bids/offers from qualified laboratories or firms, and make recommendations for awards to the COR.

- When obtained, all offers for testing services must be structured on a fixed unit price basis.

- Testing services will be coordinated with on-going work at the site for efficient performance and so as not to delay work in progress.

- Requirements may include appropriate disciplines/labor categories and laboratory support as determined by the Government.

- Monitor all testing services, and immediately notify the COR in writing of any inadequate processes and/or materials not meeting construction requirements.

C.33  MISCELLANEOUS SERVICES AND SUPPORT ITEMS.  The Government may require the CM to either perform or subcontract for Miscellaneous Items (as defined in Article-I) in support of services being performed within the major Project Phases.  Such work will be required under the "Changes" Clause of this contract.

Miscellaneous services/items will be obtained by means of Blanket Change Orders.  All Blanket Change Orders must include a schedule of anticipated line items, negotiated unit prices for each, a negotiated total not-to-exceed price, and be approved only by the CO.  The COR may place written Work Orders against the Blanket Change Orders as requirements arise. ADP hardware shall not be procured under this contract for the Government’s title.

C.34  PERFORMANCE AND PAYMENT BONDS.  When authorized to perform certain Miscellaneous Services and Support Items (MSSI) priced at $25,000 or more in the aggregate per order, the CM may be required (under the Miller Act) to provide a Performance Bond (Standard Form 25) and a Payment Bond (Standard Form 25A) covering the MSSI with good and sufficient surety or sureties acceptable to the Government, on a reimbursable basis, as determined solely by the CO.  The penal sums of the Performance and Payment Bonds shall be determined by the CO.  When required, the Performance and Payment Bonds shall be furnished by the CM before performing MSSI.  If any sureties on any bonds furnished in connection with this contract become unacceptable to the Government, the CM shall promptly furnish such additional security as required.  This is to protect the interests of the Government.

C.35  BUY AMERICAN ACT.  The Buy American Act Construction Materials clause (FAR 52.225-5), included in Part II, Section-I, is applicable to Miscellaneous Services and Support Items ordered under this contract.

C.36  LABOR STANDARDS PROVISIONS (DAVIS BACON ACT).  The Labor Standards provisions as set forth in Part II, Section-I, of this contract are applicable to Miscellaneous Services and Support Items ordered under this contract.

C.37  DAVIS BACON WAGE RATE DECISION.  When the COR authorizes the CM to provide any Miscellaneous Services and Support Items, he will provide the CM with the current applicable wage rate decisions of the Secretary of Labor, containing wage rates and fringe benefits for categories of labor to be utilized in performing the specified work.  The CM agrees to be bound by such wage decisions, and if all or part of the Miscellaneous Services and Support Items will be performed via subcontracts, to include the wage rate decisions in each subcontract.

C.38  CM PERSONNEL.  The CM must take the initiative establishing and maintaining proper business like relations with representatives of the construction contractor(s), with the GSA Buildings Manager(s) and through the COR, with client agencies at the work site.

(a)  	The official dealings of the CM will be with prime contractors, but not with subcontractors.

(b)  	CM personnel will not settle disputes or differences of opinion between prime contractors and their subcontractors, or between subcontractors.

(c)  	Where differences of opinion exist between CM personnel and Government personnel, the differences will not be discussed in the presence of prime contractors or their subcontractors.

(d)  	The CM shall not disseminate any information concerning the project or any information that might be confidential, inflammatory, or derogatory.  All requests for information must immediately be forwarded to the COR before being acted upon.

(e)  	The CM will not issue oral instructions to, or make any agreements with, prime contractors or their representatives which affect the work in material ways, or which may result in disputes and claims.

(f)  	The CM will not assume the responsibilities of the construction contractor(s), particularly in areas of coordination of work to be performed by subcontractors.

C.39  GOVERNMENT RECORDS.  The CM and its subcontractors or consultants shall not disclose any information or data that is proprietary to the Government.  All such information or data is reserved exclusively for use between the Government and the CM Contractor, including employees of the CM's firm. When deemed appropriate, the Government may authorize the release of certain information or data necessary for use by the CM in performance of contract work, and in such cases specific written authorization must be given in advance.  Such data so released shall not be further disseminated and shall not be considered released into the public domain.  The CM must ensure that this clause is included in all tiers of subcontracts.

C.40  PROPRIETARY INFORMATION.  In the event that performance of any work under this contract causes the CM to gain access to proprietary and/or confidential information of other firms/ contractors, the CM is required to immediately execute Technology Exchange Agreements with those firms/contractors, in order to protect the information from unauthorized use.  The CM is required to refrain from using any such information for any purposes other than for which it was furnished.  The CM must immediately provide the Contracting Officer with a copy of any such agreements with original signatures affixed.

C.41  PROTECTION AND CONTROL OF GOVERNMENT RECORDS AND PROPRIETARY INFORMATION.

The CM is required to develop and utilize procedures for custody, use/handling, reproduction, preservation, storage, safeguarding, and disposition of all documents and information of this nature. These procedures must be designed and carried out so that there is no unauthorized disclosure of such documents and information throughout the course of contract performance.