| Financial Management Line of Business |  |
| --- | --- |

Migration Planning Guidance (Version 1)

Section 4.1 Project Schedule Overview

This section provides an overview for the migration Microsoft Project Schedule template in Section 4.2.  It includes an explanation of the purpose and tasks within each phase and their dependencies. The tasks and timelines will vary for various phases depending on the complexity of business process changes and the extent of system customizations.

Table of Contents

Introduction to Project Scheduling	1

Earned Value Management	1

Additional Resources	2

Overview of the Project Schedule Template	2

Scope of the Project Schedule Template	2

Assumptions of the Project Schedule Template	2

Additional Notes	4

Notes regarding specific phases in the template	4

Notes regarding the overall template	4

Organization of the Microsoft Project Schedule	5

Description of the Phases	6

Project Initiation Phase	8

Purpose	8

Assumptions	8

Tasks	9

Concept of Operations Phase	9

Define Current Environment Sub-Phase	10

Purpose	10

Tasks and Dependencies	10

Requirements Analysis Sub-Phase	11

Purpose	11

Assumptions	11

Tasks and Dependencies	11

Design Phase	12

Design/Change Specification Development Sub-Phase	13

Purpose	13

Tasks and Dependencies	13

Test Plan Development Sub-Phase	13

Purpose	13

Tasks and Dependencies	13

Configuration Approach Development Sub-Phase	14

Purpose	14

Tasks and Dependencies	14

Development Phase	14

Technical Setup Sub-Phase	15

Coding Sub-Phase	15

Unit Testing Sub-Phase	15

Purpose	15

Tasks and Dependencies	15

Testing Phase	16

Testing Environment Setup Sub-Phase	17

Purpose	17

Tasks and Dependencies	17

System Testing/Business Process Testing Sub-Phase	18

Purpose	18

Tasks and Dependencies	18

Integration/End-to-End Testing Sub-Phase	18

Purpose	18

Tasks and Dependencies	18

System Performance Testing (Load Testing) Sub-Phase	18

Purpose	18

Tasks and Dependencies	19

Regression Testing Sub-Phase	19

Purpose	19

Tasks and Dependencies	19

Conversion Testing Sub-Phase	20

Purpose	20

Assumptions	20

Tasks and Dependencies	20

User Acceptance Testing (UAT) Sub-Phase	21

Purpose	21

Tasks and Dependencies	21

Develop User and Training Documents Phase	21

Purpose	21

Tasks and Dependencies	21

End User Training Phase	22

Training Plan Development Sub-Phase	22

Purpose	22

Tasks and Dependencies	22

Training Logistics Sub-Phase	22

Purpose	22

Tasks and Dependencies	22

Conduct Training Sub-Phase	23

Implementation Phase	23

Migration Planning Sub-Phase	23

Purpose	23

Tasks and Dependencies	23

Migration Dry-Run Testing Sub-Phase	23

Purpose	23

Tasks and Dependencies	24

Production Software Cutover Sub-Phase	24

Purpose	24

Tasks and Dependencies	24

Production Data Conversion Sub-Phase	24

Purpose	24

Tasks and Dependencies	24

Bring up New Financial System Sub-Phase	25

Migration/Implementation Complete Sub-Phase	25

Independent Verification and Validation (IV&V) Phase	25

Migration Checklists	27

1.  Milestone Checklist	27

2.  Technical Migration Checklist	27

3. Detailed Implementation Checklists	27

4.  Conversion Checklist	27

5. Verification Checklist	28

| Section | Project Schedule Overview |
| --- | --- |
| 4.1 |  |

This section provides an overview for the migration Microsoft Project Schedule template in Section 4.2.  It includes an explanation of the purpose and tasks within each phase and their dependencies. The tasks and timelines will vary for various phases depending on the complexity of business process changes and the extent of system customizations.

# Introduction to Project Scheduling

Comprehensive project scheduling is critical to the success of a migration effort, regardless of the scale or complexity of the migration effort, agency, or the agency’s business processes.  A comprehensive project schedule provides the overall project timeline, tasks and deliverables, dependencies, resources, and milestones.  Migrating agencies and shared service providers (SSPs) can use the project schedule to communicate with stakeholders, guide their work efforts, and to manage and control the project execution. The migrating agency and the SSP should have a disciplined process for managing the systems migration effort to focus their efforts and reduce risk. It is expected that project schedules be reasonable and integrated and that both the migrating agency and the SSP sign-off on the project schedules.

## Earned Value Management

Earned value management (EVM) should be used for implementation and migration projects to help evaluate and control project risk.    EVM is a management methodology used to objectively measure a project’s performance against schedule and budget (also referred to as cost) by evaluating variances in dollar value.  Resources for EVM include, but are not limited to, the Project Management Institute, the Office of the Under Secretary of Defense for Acquisition, Technology & Logistics, and the Defense Acquisition University, and the Office of Management and Budget.  Please also refer to FAR Case 2004-019, Earned Value Management Systems - Final Rule.

In addition, an extension to EVM has been emerging, called earned schedule (ES).  ES can be used in conjunction with EVM and measures a project’s performance against schedule and budget by evaluating variances in time.

## Additional Resources

The content of this sample project schedule template is based upon best practice methodologies and lessons learned. Additional resources for project scheduling include the Financial Systems Integration Office (FSIO), the U.S. General Accounting Office (GAO), the Institute of Electrical and Electronics Engineers (IEEE), the Project Management Institute (PMI), and the Software Engineering Institute (SEI).

# Overview of the Project Schedule Template

## Scope of the Project Schedule Template

The scope of this project schedule template includes the activities after the migrating agency has completed its source selection process and signed a contract with their service provider to migrate their system to a SSP.

## Assumptions of the Project Schedule Template

The tasks and timelines provided in this migration project schedule template are based on the following assumptions:

The requirements and business processes of the migrating agencies are relatively complex.

A single migration will occur. The migration will not be phased or require parallel operations. There are numerous migration strategies that migrating agencies should consider when migrating to an SSP.  These strategies include:

A single implementation strategy in which the entire organization is migrated at once;

The phased implementation strategy in which a subset of functions for an entire organization are migrated and evaluated before migrating the next subset;

The staggered implementation strategy in which a portion of the organization is migrated to the new system in full and acts as a pilot before migrating the entire organization.

Each agency should assess the pros and cons associated with each implementation strategy, keeping in mind the specific requirements and needs of their agency, and adapt the project schedule template to meet the alternative that best meets their needs with the least amount of risk.

The gap analysis identifies:

A need to modify business processes to the best practices identified by the SSP; or

A need to perform changes to software and/or develop new software. However, OMB does not encourage customization of the financial management software.

The migration has a “go-live” date of October 1, with user training continuing to occur after the go-live date.

Each written deliverable includes the delivery of a single draft document that is discussed in sufficient detail during a joint review by the service provider and the migrating agency such as not to require subsequent drafts, but will result in a final document.

The SSP will obtain sign-off from the migrating agency for all final deliverables.

## Additional Notes

The following notes should be taken into consideration as each agency customizes its project schedule to meet the specific needs of its migration:

### Notes regarding specific phases in the template

The project schedule template places heavy emphasis on Requirements Analysis and Gap Analysis phases.   Clear requirements are a necessary component to any successful system migration effort and are the foundation for business process (re-)engineering, system design, development, and implementation.

The template assumes that a Development Phase is necessary.  It is assumed that the SSP may perform new development, customizations, or extensions to the existing system to accommodate a mission critical requirement of the migrating agency that cannot be met by the SSP’s system or a reengineering of the migrating agency’s business processes, such as integration with agency-specific feeder systems. This phase will need to be removed or modified based on the specific requirements of the agency.

The proposed timelines for the software development life cycle (SDLC) will vary depending on the degree of system customizations and/or changes necessary, the size of the agency, and the complexity of the agencies current systems and processes. Furthermore, if the migrating agencies identify new or missing requirements during subsequent phases of the SDLC, the migrating agency and SSP must meet to determine cost and schedule impacts.

The project schedule template places a heavy emphasis on testing throughout the SDLC. There is significant risk that defects or missing requirements will not be detected until after the migration if comprehensive testing is not conducted.

### Notes regarding the overall template

The template does not indicate the resources that must be assigned in order to perform the work. Resource planning must accompany the development of the project schedule and should be based upon the complexity and scope of the migration.

The template mentions a risk plan as a project management component, but does not detail specific project risk management activities.  Project risk management includes risk planning, identification, analysis, response planning and monitoring and control.  To be successful, each project must address the management of risk proactively and consistently throughout the project lifecycle.

The template may require additional levels of detail beyond what is provided.  For example, each sub-phase under the Concept of Operations might be further delineated by business function (i.e. Accounts Payable, Accounts Receivable, Funds Management, etc.); or phases within the systems development life cycle (SDLC) may be further delineated by software.

## Organization of the Microsoft Project Schedule

The columns shown in the Microsoft Project Schedule are as follows:

ID – an automatically-assigned, unique number that indicates the order of a task relative to other tasks in the project schedule.

( – small icons that represent information for a task or resource. The most common icon is the note icon (() which indicates that the task, resource, or assignment has a note attached to it.

WBS – the work breakdown structure (WBS) is a hierarchical outline of a project schedule. A unique code exists for each task, and represents the task’s position within the hierarchical outline. This particular plan includes six WBS levels.

Level 1 represents the overall FMLoB Migration

Level 2 represents a phase

Level 3  represents a sub-phase within a phase

Level 4 through 6 represent either task groupings or specific tasks

Task Name – the name of the task

Duration – the number of work days a task is anticipated to require for completion. Calculated as the number of work days between the start date and the finish date.

Start  – the date work is scheduled to begin

Finish – the date work is scheduled to be completed

Predecessors – the task ID number(s) upon which a task depends before it can be started or finished.

# Description of the Phases

The following table identifies each of the phases, sub-phases and core deliverables included in the project schedule.  A description is provided for each phase and sub-phase. The phases for the project schedule include:

| Phase | Sub-Phase | Core Deliverables / Activities |
| --- | --- | --- |
| Project Initiation Phase |  | Project Management Plan |
| Concept of Operations Phase | Define Current Environment Sub-Phase | “As-Is” Analysis and Documentation |
|  | Requirements Analysis Sub-Phase (Includes requirements gathering and gap analysis activities) | “To-Be” Analysis and Documentation Requirements Definition Enterprise Architecture Gap Analysis Documented gaps between SSP systems and processes and current agency’s existing operations Documented proposed configuration, software, and business processes changes to mitigate gaps Documented impact of changes to migrating agency |
| Design Phase | Design/Change Specification Development Sub-Phase | Functional Architecture System Architecture Data Structures Data conversion process documentation Data Conversion Jobs Data Cleansing Plan Application Software System Interfaces Job Streams Reports |
|  | Test Plan Development Sub-Phase | High level test plans including: Unit System/business process Integration / end-to-end System performance (load) Regression Conversion User acceptance |
|  | Configuration Approach Development Sub-Phase | Configuration Management Plan System/Data Configuration Document System Security Plan |
| Development Phase | Technical Setup Sub-Phase | Hardware/software procured, loaded, configured, tuned, and tested |
|  | Coding Sub-Phase | Development of any custom interfaces, reports, etc |
|  | Unit Testing Sub-Phase | Final Test Scripts and Results |
| Testing Phase | Testing Environment Setup Sub-Phase | Agency Test Data Testing Instance prepared |
|  | System Testing/Business Process Testing Sub-Phase | Final System Performance Test Scripts and Results |
|  | Integration End-to-End Testing Sub-Phase | Final Integration/End-to End Test Scripts and Results |
|  | System Performance Testing (Load Testing)Sub-Phase | Final System Performance Test Scripts and Results |
|  | Regression Testing Sub-Phase | Final Regression Test Scripts and Results |
|  | Conversion Testing Sub-Phase | Mock Conversion Test Scripts, Checklist and Results Data Cleansing |
|  | User Acceptance Testing (UAT) Sub-Phase | Final UAT Test scripts, results and resolved issues |
| Develop User and Training Documents Phase | Draft and Final Documentation Sub-Phase | User Documentation Training Materials Standard Operating Procedures |
| End User Training Phase | Training Plan Development Sub-Phase | Training Plan |
|  | Training Logistics Sub-Phase | Training Schedule |
|  | Conduct Training Sub-Phase | Training Curriculum |
| Implementation Phase | Migration Planning Sub-Phase | Migration Plan Migration Checklist |
|  | Migration Dry-Run Testing Sub-Phase | Migration Dry-Run results |
|  | Production Software Cutover Sub-Phase | Software Cutover Checklist |
|  | Production Data Conversation Sub-Phase | Conversion Reconciliation Results |
| Independent Verification and Validation Phase | IV&V Audit Sub-Phase | IV&V Results |

## Project Initiation Phase

### Purpose

The purpose of this phase is to ensure that both parties, the migrating agency and the service provider, have clarity and alignment on the scope, approach, governance, project schedule, and risks of the project; and have agreed on a process for addressing risks, and any changes to scope and timeframe. The Project Initiation Phase is important in setting expectations for the entire migration.

### Assumptions

The template assumes that both the migrating agency and the service provider have prepared for the Project Initiation Phase by documenting their understanding and ensuring internal alignment within their own organizations on project scope, approach, governance, project schedules, and risks.

### Tasks

The output of the Project Initiation Phase should be a documented project management plan.  It is recommended that this plan include the following information:

Project Scope and Approach – an understanding of the overall scope, level of effort/time estimate for the project, and methodologies to be used.

Project Governance – a description of the structure of the teams that will manage the project both on the migrating agency side and the service provider side; definition of how decisions will be made and issues escalated, how changes to project cost and timeline will be controlled, how configuration management will be performed, and how performance will be measured.

Project Schedule – a more detailed definition of the work to be performed, deliverables, timeframe, constraints and assumptions, and timelines are defined.

Resource Plan – identification of the individual resources necessary to perform the work and timeframes outlined in the project schedule.

Risk Management Plan – a categorization and description of each of the risks applicable to the project, including their probability, impact, triggers, and response or fall-back strategies (if the risk comes to fruition).  For negative risks, the plan should also outline strategies for avoidance, transference, and mitigation. For positive risks, the plan should outline strategies for taking advantage of the risks.

Change Management Plan – an approach for addressing how to help stakeholders understand and prepare for the changes associated with the migration. A change management plan will likely include a human capital plan and a communications plan.

IV&V Audit Plan – an approach for conducting the IV&V audit including identification of the following: work products to be reviewed/assessed, processes requiring IV&V oversight, quality assurance standards, and audit/testing schedule.

Sign-off on the initiation documents ensures that both the SSP and migrating agency agree on the scope, direction, and outcomes of the project.

## Concept of Operations Phase

The purpose of the Concept of Operations Phase is to align on the specific system and business process requirements, and identify the specific approaches that must be developed to meet those requirements.  During this phase both parties must work closely together, typically through employing working sessions.  If following an iterative approach, during this phase requirements are gathered, sorted and separated into releases or change efforts based on sorting or priority.

This migration project schedule assumes that a Concept of Operations has not been completed by the migrating agency prior to the start of its migration project.  As such, it assumes that the Concept of Operations Phase will begin only after sign-off has been obtained on the initiation documentation.  It is recommended however, that the migrating agency performs an “As Is” analysis and/or requirements analysis in house or issues a Request for Proposal or task order to have an SSP or other implementation services vendor assist in these tasks.  If the “As Is” analysis and/or requirements are already documented, the SSP will need to validate the completeness of the documentation for the migration. This approach may help to compress the overall migration schedule.

As a best practice, it is recommended that the migrating agency, at least, begin to perform data collection in preparation for the Concept of Operations Phase, and if possible, begin performing the “As Is” and “To Be” analysis.

### Define Current Environment Sub-Phase

#### Purpose

The purpose of the Define Current Environment Sub-Phase is to establish the starting point from which change must begin.  The current environment is documented in an “As Is” document. The “As Is” document should not only include the “as-is” business processing workflow but also information about feeder systems, users/user roles, system enhancements, reports, technical configuration, etc.   It is essential for agencies to understand their current business and technical architecture/environment in order to assess the impact of business process changes or system customizations on the migrating agency’s operations.  The “As Is” analysis can assist with human capital planning, training plan development, change management, and communications planning.

#### Tasks and Dependencies

An agency can begin analyzing its own current environment and creating an “As Is” document as soon as it makes the decision to migrate.  If the SSP defines the migrating agency environment and drafts the “As Is” documentation, the SSP can begin this analysis and documentation after receiving sign-off on the Initiation Phase.  After a joint review of the draft “As Is” documentation, the SSP can create and deliver the final documentation and obtain sign-off.

### Requirements Analysis Sub-Phase

#### Purpose

The purpose of the Requirements Analysis Sub-Phase is to gather the migrating agency’s various migration requirements, define and document the requirements, identify gaps between the migrating agency’s requirements and the SSP’s capabilities, and propose methods for mitigating the impact of the gaps.  The Requirements Analysis Sub-Phase consists of Requirements Gathering and Gap Analysis.

- Requirements Gathering:  During Requirements Gathering, migrating agency requirements for business process, application, feeder system/interface, reporting, data, technical (including disaster recovery, capacity planning, and performance requirements), security, training, and user documentation are gathered.  These requirements will be documented in a “To Be” document consisting of the requirements definition and Enterprise Architecture Blueprint.  Having a complete set of requirements is necessary in order to perform any type of gap analysis with the SSP.  These requirements should be developed based on the agency’s future business processes, not on the agency’s current system functions.  A complete set of requirements that maintain traceability throughout the Design, Development and Testing phases will contribute to the system’s success.

- Gap Analysis: During Gap Analysis, gaps between the migrating agency’s current operating environment, its requirements, and the capabilities of the SSP’s financial system or SSP’s current business processes are identified.  The end result will be an identification of business processes and/or software that need to be re-engineered to align the migrating agency with the SSP, and to the FMLoB Standard Business Processes and Common Government-wide Accounting Code.  During this phase, high level configuration, code, or business process changes may be proposed to mitigate the impact of the identified gaps.

#### Assumptions

It is assumed that the Enterprise Architecture Blueprint will follow the guidelines of the agency’s overall enterprise architecture plan.

#### Tasks and Dependencies

If the migrating agency has drafted, or is in the process of drafting the “As Is” documentation, the SSP can begin developing the “To Be” documentation once the Project Initiation Phase is complete.  The “To Be” documentation includes gathering requirements and drafting the “To Be” documentation, which includes the requirements analysis and enterprise architecture documents. Following a joint review of the draft, the SSP can develop and deliver the final “To Be” documentation and obtain sign-off.  Before finalizing the “To Be” documentation, the SSP should review the final “As Is” documentation provided by the migrating agency.

If the SSP is drafting the “As Is” documentation, the SSP can begin gathering requirements and creating draft documents after the joint draft “As Is” documentation review.  The final requirements analysis and enterprise architecture documents cannot begin until the SSP obtains sign-off on the final “As Is” document and the SSP and migrating agency have conducted a joint review of the draft requirements analysis and enterprise architecture documents.

Once the “As Is” and “To Be” environments are known, the gaps between the two must be identified. During the Gap Analysis, the migrating agency and SSP will engage in several joint discussions to determine changes that will be needed to mitigate the documented gaps. Methods of mitigating gaps could include the following: new development, customizations, and/or extensions to the software; reports and/or interfaces to feeder systems; and business process workarounds or business process changes.  The SSP will provide an estimate for any new development, customizations, or extensions proposed for the system, reports, or feeder system interfaces. For any workarounds or business process changes proposed, the SSP will document the impacts to the migrating agency’s existing operations.

## Design Phase

The purpose of the Design Phase is to establish how the migrating agency will operate in its new environment by detailing any changes that must be made to the system and/or business processes to achieve the migrating agency’s requirements and ensuring that changes are implemented correctly and are understandable to the users. Whenever possible, it is recommended that agencies realign their business processes to their SSP’s system instead of customizing the SSP’s system.  This will reduce costs and inconsistencies for the migrating agency.

During the Design Phase, the SSP establishes its functional architecture and creates or updates draft and final software design/change specification documents, test plans, and configuration approach documentation for each change effort.

The types of test plans will vary depending on whether new development, customizations or extensions are needed to the system, reports, or feeder system interfaces. However, the configuration approach documentation should be a standard.

The proposed timelines in this section will vary depending on the degree of customizations and/or changes required, the size of the agency, and the complexity of the agencies current systems and processes. If the migrating agencies identify new or missing requirements during its review of design documents, the migrating agency and SSP must meet to determine cost and schedule impacts.  If the SSP and migrating agency agree to implement the new requirement, all affected system definition/analysis and design documentation must be updated and changes tracked according to the Configuration Management Plan (reference Configuration Approach Development Sub-Phase for description).

### Design/Change Specification Development Sub-Phase

#### Purpose

The purpose of the Design/Change Specification Development Sub-Phase is to detail the software changes and/or new software needed to satisfy a requirement and to outline the new enterprise architecture, both functional and technical.

#### Tasks and Dependencies

During the Design/Change Specification Development Sub-Phase, the following documents will be created or modified depending on whether the SSP allows and the migrating agency requires system customization or extensions.  The following system design documents will need to be drafted or modified: functional architecture, system architecture, data structures, data conversion process documentation, data conversion jobs, data cleansing plan, application software, system interfaces, job streams, and reports.  Beginning this Sub-Phase depends on completing the Concept of Operations Phase.  Drafting one design/change specification is not dependent on drafting another.  Several designers can draft the documents simultaneously, although communication is required to ensure that all requirements are met.

### Test Plan Development Sub-Phase

#### Purpose

The purpose of the Test Plan Development Sub-Phase is to detail the testing objectives, tools, resources, methods, and evaluation criteria for the various testing Sub-Phases.

#### Tasks and Dependencies

After the design/change specifications are complete, high level test plans can be drafted or updated.  High level unit, system/business process, integration/end-to-end, system performance (load), regression, conversion, and user acceptance test plans will be drafted or modified and delivered to the migrating agency for approval.  The SSP can begin drafting high level test plans as soon as the SSP and migrating agency have completed joint review of the draft design/change specifications.  The SSP cannot begin drafting the final high level test plans until a joint review of the draft test plans has been conducted and the SSP has obtained sign-off on the final design/change specification documents.

### Configuration Approach Development Sub-Phase

#### Purpose

The purpose of the Configuration Approach Development Sub-Phase is to establish or update the following documents:

Configuration Management Plan – outlines the procedures that will be used to make changes to the system throughout the course of the migration and post-implementation. Changes include not only software changes but also configuration changes.

System Security Plan – details how security should be set up in the system for different users and user groups.

System/Data Configuration Document – details how certain tables should be configured in the system.

#### Tasks and Dependencies

The SSP can begin drafting/updating the Configuration Management Plan and the System Security Plan as soon as the SSP and migrating agency have completed joint review of the draft design/change specifications. The system/data configuration document, however, is dependent on items from the Configuration Management Plan and the System Security Plan, and therefore cannot be drafted/updated until these two documents are complete.  These three configuration approach documents are then delivered to the migrating agency, and the migration agency and SSP should conduct a joint review of the documentation.

The SSP cannot begin drafting the final configuration approach documents until a joint review of the draft configuration approach documents has occurred, and the SSP has obtained sign-off on the final design/change specification documents.

## Development Phase

The purpose of the Development Phase is to develop or modify the necessary software to match the design specifications based on the complete, signed off requirements.

After the migrating agency has provided final sign-off on design documentation for the change effort, the Development Phase for the change effort can officially begin, although the Technical Setup Sub-Phase should begin earlier.  The Development Phase consists of technical setup, coding, and unit testing.  The tasks and durations in this section may vary depending on whether the SSP allows and the migrating agency requires customizations and/or extensions and the extent of these customizations/extensions.  If the migrating agency identifies new or missing requirements during its review of unit test results, the migrating agency and SSP will meet to determine cost and schedule impacts.  If the SSP and migrating agency agree to implement the new requirement, all affected concept of operations, design, and/or development documentation must be updated and changes tracked according to the Configuration Management Plan.

The Development Phase is only necessary if new development, customizations, or extensions are needed to the system, reports, or feeder system interfaces.

### Technical Setup Sub-Phase

The purpose of the Technical Setup Sub-Phase is to procure the hardware and software, load and configure the hardware and software, tune the database, and test the baseline software. The SSP can procure the hardware and software required for system implementation (if necessary), configure servers, and load the baseline software on test and development servers, after a joint review of the draft design/change specifications has occurred (most importantly, the system architecture document).  The SSP, however, cannot begin configuring the hardware and software, tuning the database, and testing the baseline software until receiving sign-off on the final System/Data Configuration document.

### Coding Sub-Phase

The purpose of the Coding Sub-Phase is to develop any custom interfaces, reports, tables, code, or extensions and to modify baseline software, if necessary.  The Coding Sub-Phase also includes development or customization of conversion and conversion reconciliation scripts.  This sub-phase can begin after technical setup is complete, and the SSP has obtained sign-off on the Design/Change Specifications and Configuration Approach documents.

### Unit Testing Sub-Phase

#### Purpose

The purpose of the Unit Testing Sub-Phase is to verify that the code functions as developed.

#### Tasks and Dependencies

Draft unit test preparation materials (drafting or updating unit test scripts, creating test data, and documenting expected results) can begin after sign-off has been obtained on the Design Phase.  However, the execution of the unit test script cannot begin until after coding is complete and the SSP has conducted a joint review with the migrating agency on the draft unit test preparation materials.  The developer will log any errors found during unit testing into a database, resolve the errors, and retest.  The designers will update the designs/change specifications if necessary according to the configuration management plan.  The Unit Testing Sub-Phase is complete when the SSP delivers the final test scripts and test results to the migrating agency, conducts a joint review, and receives sign-off.

## Testing Phase

The purpose of the Testing Phase is to verify that the application software functions, as designed and developed, and that the software aligns with agency future business processes as identified in the Requirements Analysis and Gap Analysis.

After the Development Phase is complete for a software change effort, the Testing Phase for that change effort can officially begin, although some activities may begin earlier.  The durations in the project schedule for drafting test scripts may vary depending on the extent of system customization and/or the complexity of the migrating agency’s business processes.

If new development, customizations or extensions are needed to the system, reports, or feeder system interfaces, the Testing Phase will consist of the following seven testing cycles:

System Testing/Business Process Testing – for implementations involving new development, customizations, or extensions, system testing/business process testing will include testing the system’s compliance with the business process requirements and design/change specifications documentation.  For implementations involving changes to the migrating agency’s existing business process, system testing/business process testing will include testing the system’s compliance with the new business processes.

Integration/End-to-end Testing – end-to-end testing of the system and related interfaces and feeder systems, including security testing.

System Performance Testing (Load Testing) – volume and stress testing the system.

Regression Testing – for implementations involving new development, customizations, or extensions, regression testing includes high level re-testing of the system after all system fixes and modifications are complete.  This high level retesting confirms that code or configuration changes made to the system to fix requirements, design, software, or configuration problems are accurate and that the fix has not introduced or reintroduced new or previously discovered problems.

Regression testing is not necessary for implementations that do not include new development, customizations, or extensions.

Conversion Testing – testing conversion of existing financial system data to the new financial system.

User Acceptance Testing (UAT) – user directed testing of financial system compliance with requirements or new business processes.

In addition, the Implementation Phase includes one cycle of testing: the Migration Dry-Run Testing, which is described in that section of this document.

The testers will log any issues found during testing.  For implementations involving new development, customizations, or extensions, the developers and/or designers will resolve the errors.  For implementations that do not include new development, customizations, or extensions, developers will analyze the issue and resolve any system defects. After issues are resolved, the software will then be retested and the design documents will be updated if necessary according to the configuration management plan.  If the migrating agency identifies new or missing requirements during its review of test results, the migrating agency and SSP will meet to determine cost and/or schedule impacts.  If the SSP and migrating agency agree to implement the new requirement through new development, customizations, or extensions, all affected system definition/analysis, design, development, and/or test documentation must be updated and changes tracked according to the Configuration Management Plan.  If the SSP and migrating agency decide to change the migrating agency’s business process to resolve the new requirement, all affected system definition/analysis and test documentation must be updated and changes tracked according to the Configuration Management Plan.

### Testing Environment Setup Sub-Phase

#### Purpose

The purpose of the Testing Environment Setup Sub-Phase is to set the testing environment up with the data from the migrating agency and the baseline development software in preparation for System/Business Process, Integration/End-to-End, System Performance (Load), Regression, Conversion, and User Acceptance Testing.

#### Tasks and Dependencies

After the Design Phase is complete, the SSP can request test data from the migrating agency in accordance with the test plan.  After the SSP obtains the test data and the Development Phase is complete (i.e. the SSP obtains sign-off on the unit test results), the developers can migrate the code from the development environment to the testing environment (following the Configuration Management procedures), load the migrating agency’s test data, and configure the testing environment as specified in the System/Data Configuration Plan document.

### System Testing/Business Process Testing Sub-Phase

#### Purpose

The purpose of the System Testing/Business Process Testing Sub-Phase is to test the system’s compliance with design/change specifications and with the agency’s business process requirements or new business processes.   This Sub-Phase also consists of testing the functional operation of the application (e.g. ensuring that the application updates tables correctly).

#### Tasks and Dependencies

Draft system test/business process test preparation (drafting or updating system test/business process test scripts, selecting test data, and documenting expected results) can begin after sign-off has been obtained on draft unit test preparation (drafting or updating unit test scripts, creating test data, and documenting expected results). The system test/business process test execution can begin only after the test environment is set up and sign-off has been obtained on the draft system test/business process test preparation materials. After system test/business process test is complete, the SSP delivers the results to the migrating agency, conducts a joint review, and obtains sign-off.

### Integration/End-to-End Testing Sub-Phase

#### Purpose

The purpose of the Integration/End-to-end Testing Sub-Phase is to perform end-to-end testing of the entire system and all of its external feeder systems and interfaces.  This Sub-Phase includes testing technical, configuration, and reporting requirements.

#### Tasks and Dependencies

Draft integration/end-to-end test preparation (drafting or updating integration/end-to-end test scripts, selecting test data, and documenting expected results) can begin after sign-off has been obtained on the draft system test/business process test preparation materials (drafting or updating unit test scripts, selecting test data, and documenting expected results).  The integration/end-to-end test execution can begin only after sign-off has been obtained on draft integration/end-to-end test preparation and final system test/business process test results. After Integration/End-to-End Testing is complete, the SSP delivers the results to the migrating agency, conducts a joint review, and obtains sign-off.

### System Performance Testing (Load Testing) Sub-Phase

#### Purpose

The purpose of the System Performance Testing (Load Testing) Sub-Phase is to volume test and stress test the system to verify that the system meets agency defined performance requirements.

#### Tasks and Dependencies

During the System Performance Testing (Load Testing) Sub-Phase, volume and stress tests are executed. Volume testing verifies that the system can handle a set volume of data within a specified timeframe, as detailed in the requirements documentation and still meet agency performance requirements.  Stress testing verifies that a set number of users and processes, as detailed in the requirements documentation, can access the system at any given time and still meet agency user response time requirements.

Draft system performance test (load test) preparation (drafting or updating system performance test (load test) scripts, selecting test data, and documenting expected results) can begin after sign-off has been obtained on the draft integration/end-to-end test preparation (drafting or updating unit test scripts, selecting data, and documenting expected results).  System performance test (load test) and integration/end-to-end test execution can occur simultaneously. The system performance test (load test) execution can begin only after sign-off has been obtained on the draft system performance test (load test) preparation materials and the final system test/business process test results. After System Performance Testing (load testing) is complete, the SSP delivers the results to the migrating agency, conducts a joint review, and obtains sign-off.

### Regression Testing Sub-Phase

#### Purpose

The purpose of the Regression Testing Sub-Phase is to conduct high level retesting of the entire system and interfaces to test the impact of any code or configuration changes made to the system during the previous testing sub-phases and to verify that new or previously corrected problems are not introduced or reintroduced.  This phase is necessary only for implementations that involve new development, customizations, or extensions.  If system defects are identified during Conversion or UAT testing, or through the Independent Validation and Verification (IV&V) audit, then some portion of the regression tests may need to be re-executed.

#### Tasks and Dependencies

During the course of System, Integration/End-to-End, or System Performance (Load) Testing, code or configuration changes may be made to the system to correct identified problems or meet new requirements.  To ensure that no code changes negatively impact any previously tested modules, a high level regression test should be conducted on the system and its related interfaces and feeder systems. Draft regression test preparation (drafting or updating regression test scripts, selecting test data, and documenting expected results) can begin after sign-off has been obtained on draft  system performance (load) test preparation materials (drafting  or updating  system performance (load) test scripts, selecting data, and documenting expected results).  The regression test execution can begin only after sign-off has been obtained on draft regression test preparation materials and final system performance (load) test and integration/end-to-end test results.  After Regression Testing is complete, the SSP delivers the results to the migrating agency, conducts a joint review, and obtains sign-off.

### Conversion Testing Sub-Phase

#### Purpose

The purpose of the Conversion Testing Sub-Phase is to test the conversion of data from the agency’s prior financial system to the SSP financial system.  This phase consists of verifying that the converted data is accessible, accurate, and can be modified, added, or deleted as specified in the conversion design.  During this time, data issues should be identified and a data cleansing process should be created and tested for the production conversion.

#### Assumptions

This project schedule template assumes that any issues associated with conversion will be addressed after conducting two mock conversions. However, there is a risk that several additional mock conversions may be necessary. Each agency must assess the level of difficulty of its conversion when determining how many mock conversions to schedule.  Each agency must also plan for the risk that additional mock conversions beyond those that have been scheduled may be necessary.  Subsequent phases should not continue until a clean mock conversion is achieved.

#### Tasks and Dependencies

Draft conversion test preparation (drafting or updating conversion test scripts, drafting a conversion checklist, selecting test data, and documenting expected results) can begin after sign-off has been obtained on the regression test preparation materials (drafting or updating integration/end-to-end test scripts, selecting test data, and documenting expected results).  The conversion test execution can begin only after regression test sign-off and sign-off on the draft conversion test preparation materials.  In the Conversion Testing Phase, testers perform two or more mock runs of the conversion.  The testers reconcile the converted data with the original data and verify that the data is converted and accessible according to the conversion design document.  For any data that the migrating agency agrees cannot or should not be converted to the new financial system, the conversion test should verify that the data is accessible in the manner detailed in the conversion design document (e.g. datamart). During the course of Conversion Testing, any data issues will be identified and the data will be cleansed in preparation for production conversion.  After Conversion Testing is completed successfully, the SSP delivers the conversion test results to the migrating agency for sign-off.  It is during the Conversion Testing that the conversion checklist is developed for use in the Migration Planning Phase.

### User Acceptance Testing (UAT) Sub-Phase

#### Purpose

The purpose of the UAT Sub-Phase is for users to execute self-defined tests to verify system functionality.

#### Tasks and Dependencies

UAT can begin after the migrating agency has provided sign-off on the following test cycles: System/Business Process testing, Integration/End-to-End testing, System Performance testing (Load testing), Regression testing, and Conversion testing.  In this Sub-Phase, users from the migrating agencies will create their own test scripts to test the functionality of the system and verify that the system meets their business and system requirements and/or new business processes.  A recommended best practice is to create test scripts using a combination of converted and newly entered data. At the end of UAT, users provide sign-off on the system functionality.

## Develop User and Training Documents Phase

#### Purpose

Training is an essential element to any successful migration.  The purpose of the Develop User and Training Documents Phase is to develop documentation user manuals, user documentation, and training methods and materials to support migration.

#### Tasks and Dependencies

The development or update of draft user documentation cannot begin until after integration/end-to-end testing is complete because changes may be made to the system or existing agency business processes during system testing/business process and/or integration/end-to-end testing to correct defects or meet new agency requirements. The types of user documents that will be drafted or updated and delivered to the migrating agency will be based on the requirements agreed upon in the Requirements Phase, and may include: user documentation (including process documentation and FAQs), user training materials, and standard operating procedures.  The final draft of the user documents usually cannot begin until the SSP has conducted a joint review with the migrating agency on the draft user documents and the Test Phase is complete (i.e. SSP has obtained sign-off on System/Business Process, Integration/End-to-End, Performance Stress (Load), Regression, Conversion, and UAT).  However, during the interim, updates can continue to be made to the user documentation as system code, configuration, and/or business process changes are made.

## End User Training Phase

The purpose of the End User Training Phase is to plan for and conduct the training necessary to prepare users on the use of the system and any new business processes.

### Training Plan Development Sub-Phase

#### Purpose

The purpose of the Training Plan Development Sub-Phase is to outline a plan for meeting the training requirements.  The Training Plan may include items such as training techniques; training tools such as simulations and learning management systems; training methods such as train-the-trainer, classroom training or computer-based training; course curriculum; required materials, groups of personnel requiring training; length of training sessions; and a preliminary training schedule.

#### Tasks and Dependencies

For implementations involving new development, customizations, or extensions, creating or updating the first draft of the Training Plan should begin after the SSP has conducted a joint review of all drafts with the migrating agency, but can begin concurrent with the draft designs so long as the training impacts of the designs are well-known.  The training program will continue to evolve following the completion of design/change specification documents, configuration approach documents, draft user and training documentation, and all Testing phase activities.  For implementations that do not involve new development, customizations, or extensions, the existing system training plan can be updated or modified as necessary.

### Training Logistics Sub-Phase

#### Purpose

The purpose of the Training Logistics Sub-Phase is to solidify the Training Plan with the logistical details necessary to execute training including a final list of trainees and trainers, the securing of training venues, length of training sessions, and a specific schedule for courses and attendees.

#### Tasks and Dependencies

Identifying and scheduling trainees and establishing the training courses can begin after the Develop User and Training Documents Phase and the Training Plan Phase are complete.  Training sessions may need to be rescheduled if it is determined that the migration may not meet the scheduled deadline. The SSP can begin configuring the training database instance after the Testing Phase and Develop User and Training Documents Phase are complete.

### Conduct Training Sub-Phase

After the Training Logistics Sub-Phase and the Develop User Training Documents Phase are complete, the SSP can begin conducting training sessions according to the final Training Plan.  Migrating agencies should consider training users on basic changes within two weeks of the migration.  The project schedule assumes that training such as advanced user training and refresher training can continue past the ‘go-live’ date for as long as necessary.   It is recommended that agencies plan for ongoing training for new users and refresher courses for existing users.

## Implementation Phase

The purpose of the Implementation Phase is to migrate/implement the system into production. After obtaining sign-off on all of the testing results, the Implementation Phase can officially begin (although some activities may begin earlier).  The Implementation Phase consists of system migration and data migration/conversion.

### Migration Planning Sub-Phase

#### Purpose

The purpose of the Migration Planning Sub-Phase is to begin to create or update plans and checklists for a smooth migration of operations and to establish a fallback strategy, should an issue arise with the migration. The number and type of checklists necessary may be dependent on the complexity of the migration.  For information on the types of checklists that an agency may use in migration, see the Migration Checklist section at the end of this chapter.

#### Tasks and Dependencies

The Migration Plan and schedule should typically outline the dates/times of the migration, estimated timeframes for each step within the migration, roles and responsibilities during the migration, and the checklists that will be required. The number and type of checklists necessary may be dependent on the complexity of the migration.  The development or updating of draft Migration Plans should begin during the Conversion Testing Sub-Phase to ensure that the migration planning is complete in time to begin the migration dry-run immediately following UAT sign-off.  The final Migration Plan can begin after the joint draft Migration Plan review and the completion of the Testing Phase.

### Migration Dry-Run Testing Sub-Phase

#### Purpose

The purpose of the Migration Dry-Run Testing Sub-Phase is to test the processes and procedures (i.e. migration checklists) associated with the production migration.

#### Tasks and Dependencies

Migration Dry-Run Testing cannot begin until after the Migration Planning Sub-Phase and the Testing Phase have been completed.  The migration dry-run consists of verifying that all system related interfaces, objects, procedures, and packages are migrated successfully to the production environment.  Depending on the integrity of the data in the existing financial system, data cleansing may need to occur throughout the entire length of this sub-phase in order to prepare the data for production migration.

### Production Software Cutover Sub-Phase

#### Purpose

The Production Software Cutover Sub-Phase involves moving all of the necessary technical components into the correct environment to bring the financial system into production operations.

#### Tasks and Dependencies

The Production Software Cutover Sub-Phase cannot begin until the Migration Dry-Run Testing Sub-Phase is complete and the migrating agency has provided signoff on the IV&V audit results.  During this sub-phase, the software is migrated from the test environment to production.  The technical team will then establish user access and verify the migration.  The migration verification should be performed using the migration checklist to ensure that all objects, procedures, code, interfaces, and extensions are migrated to production.  Furthermore, verification activities should include user verification that the software is working as expected. The SSP will deliver the migration checklist and verification to the migrating agency for sign-off.

### Production Data Conversion Sub-Phase

#### Purpose

The Production Conversion Sub-Phase involves accurately moving all necessary data into the new environment.

#### Tasks and Dependencies

After the Production Software Cutover Sub-Phase is complete and the migrating agency has provided signoff on the IV&V audit results, data migration/conversion can begin. In this phase, the current system is brought down and data conversion and conversion reconciliation are executed. During this sub-phase, a verification team, which usually consists of members from the migrating agency, typically establishes the “before conversion” verification of key financial data.  This process is also known as the pre-conversion reconciliation.

Once the pre-conversion reconciliation is complete, the production database is then exported into the appropriate conversion environment, and the conversion scripts are then executed against the production database using a detailed conversion checklist for quality assurance. The conversion results are analyzed by the verification team using a verification checklist. Furthermore, verification activities should include user verification that the software functions properly with the converted data.

The migrating agency should sign-off on both the conversion checklist and the verification checklist before the system can be brought up for processing.

### Bring up New Financial System Sub-Phase

The purpose of the Bring up New Financial System Sub-Phase is to make the new financial system available for users.  A final Go/No Go checklist that incorporates elements from the checklists used in the previous Production Software Cutover Sub-Phase and the Production Data Conversion Sub-Phase can be used as a final sign off before the new system is brought up.

### Migration/Implementation Complete Sub-Phase

The migration/implementation is complete after the new system is brought up for users.  To minimize risks associated with Annual Close, the new system should be brought up at the beginning of the new fiscal year on October 1 or shortly thereafter.

## Independent Verification and Validation (IV&V) Phase

Purpose

The purpose of the IV&V Phase is to provide third-party monitoring and oversight to the project management processes, quality assurance of deliverables and work products at various stages of the project.  During the Independent Verification and Validation Audit Phase, verification and validation is performed by an individual or organization that is technically, managerially, and financially independent of the development organization.

The IV&V schedule can vary depending on the agreement between the IV&V provider and the client agency.  IV&V auditing may consist of any or all of the following:

- Validating that work products meet quality and performance guidelines and that the end result satisfies business goals, project objectives and requirements.

- Support quality assurance activities including but not limited to requirements traceability, process/product/progress assessment, suitability assessment, performance metrics, alignment with vision and mission, requirements management, program management support and change management oversight.

- Regression testing the entire financial system (after the SSP has obtained sign-off on the entire Testing Sub-Phase).

- Testing the system to verify compliance with any system changes or business process changes made during the course of the Testing Sub-Phase.

- Executing, on a smaller scale, all testing cycles executed by the SSP (usually these tests are executed after the SSP has obtained sign-off on a cycle).

Tasks and Dependencies

IV&V auditing typically occurs throughout the project lifecycle, typically beginning during the Concept of Operations Phase.  During the IV&V phase, the IV&V vendor reviews work products, conducts IV&V audit testing, reviews test results with the client, and works with the SSP to resolve any identified defects.  The IV&V vendor must provide signoff on all work products from design through migration dry-run before production software cutover can begin.  Following the migration dry-run, IV&V activities can continue through and post cutover as necessary and required by the migrating agency.

# Migration Checklists

Checklists are useful for the purposes of quickly identifying whether specific and detailed steps within a task or sub-phase have been completed.  SSPs and agencies may have standard checklist templates for system implementation and migration projects. However, it is likely that each checklist will need to be customized to meet the specific needs of an individual migrating agency. Several examples of checklists are provided below.

## 1.  Milestone Checklist

The Milestone Checklist contains important milestones and deliverables throughout the system implementation lifecycle such as design documentation delivery, testing result sign-off, system configuration completion, and system migration verification.  This type of checklist will enable the SSP and the migrating agencies to track important phases of the migration, determine the impact of missed deadlines, prioritize tasks, and measure progress.

## 2.  Technical Migration Checklist

The Technical Migration checklist lists all of the system tables, procedures, objects, and code that should be migrated to the production server.  The technical team responsible for the cutover can follow this checklist when performing the migration.  By requiring sign-off on this checklist, it can also be used to verify that all items were successfully migrated to production.

## 3. Detailed Implementation Checklists

Detailed Implementation Checklists specify tasks in the Migration Project Schedule to a lower level of detail.  These types of checklists are useful in tracking small components of the migration without having all of this information in the Migration Project Schedule.  For example, an alternative to adding detail by function to the Requirements Analysis Sub-Phase of the project schedule, is to use a Requirements Analysis Sub-Phase Checklist that lists the specific types of requirements analyses to be performed (i.e. system performance requirements, interface requirements, data accessibility requirements, data storage requirements, capacity requirements, etc.).

## 4.  Conversion Checklist

A Conversion Checklist typically outlines, in the appropriate sequential order, the specific programs and jobs that need to be executed, manual data changes that must be made, and other steps that must be performed, for a data conversion. By requiring sign-off on this checklist, it can also be used to verify that all steps were successfully executed for the data conversion.

## 5. Verification Checklist

The migrating agency may wish to maintain a checklist of items it desires to validate as part of the production software cutover and data conversion. By requiring sign-off on this checklist, it can also be used to verify that the software and data were successfully migrated to production.

# Footnotes

A Guide to the Project Management Body of Knowledge (PMBOK® Guide) Third Edition © 2004 Project Management Institute (PMI).   Additional information on Earned Value Management (EVM) is available from the Project Management Institute (PMI).

(http://www.pmi.org/info/default.asp)

(http://www.acq.osd.mil/pm/)

(https://acc.dau.mil/simplify/ev_en.php)

( http://www.whitehouse.gov/omb/)

https://acc.dau.mil/CommunityBrowser.aspx?id=104842

http://www.earnedschedule.com/Home.shtml

Financial Systems Integration Office, formerly Joint Financial Information Management Program, is an office under the U.S. General Services Administration (GSA) promoting the improvement of financial management practices in the federal government. http://www.fsio.gov/fsio/

Institute of Electrical and Electronics Engineers, Inc. is a non-profit professional association promoting the advancement of technology. http://www.ieee.org/portal/site/iportals

Project Management Institute is a non-profit professional association promoting the advancement of the project management profession.

The Carnegie Mellon Software Engineering Institute (SEI) is a federally funded research and development center sponsored by the U.S. Department of Defense and operated by Carnegie Mellon University with the mandate to advance the state of the practice of software engineering and to serve as a national resource in software engineering and technology. http://www.sei.cmu.edu/sei-home.html

Parallel operations is the process whereby the agency continues to operate their old financial system concurrently with the new financial management system for a specified period of time or until the agency has a level of confidence in the  new financial system operations.  Parallel operations require planning and coordination to minimize potential risks.    Processing transactions in both systems is required and can be a burden on an organization’s workforce, however it does provide a organization with a level of confidence that a restore to the old financial system can be made if necessary.