United States Department of Agriculture (USDA) eGovernment Program

Management and Planning Profile – Project Plan

eDeployment Business Case

DRAFT

May 2004

Table of Contents

Revision History	iii

Previous Change History	iii

Document Sign-off	iii

1	Introduction	1

2	Staffing Plan	2

2.1	Purpose	2

2.2	Government and Contracted Resources	2

2.3	The Project Team	3

2.3.1	eGovernment Advisory Teams	4

2.3.2	eGovernment Program Management Office	5

2.3.3	eDeployment Project Team	5

3	Quality Assurance Plan	13

3.1	Purpose	13

3.2	Application Standards and Policies	13

3.3	Configuration Management	14

3.4	Testing	14

3.4.1	Component (Unit) Testing	15

3.4.2	Assembly Testing	16

3.4.3	Product (System) Testing	16

3.4.4	Test Plan Quality Assurance	17

3.5	Reviews, Walkthroughs, and Audits	17

3.5.1	Reviews	17

3.5.2	Walkthroughs	17

3.5.3	Audits	18

3.6	Verification and Validation	18

3.7	Issue Tracking Process	18

4	Project Schedule	20

4.1	Purpose	20

4.2	eDeployment Tasks and Milestones	20

4.3	Plan for Progress Updates	26

4.4	Assessing and Managing Schedule Changes	26

5	Costs	27

5.1	Purpose	27

6	Project Deliverables	29

6.1	Purpose	29

6.2	eDeployment Project Deliverables	29

7	Assumptions	31

8	Appendix A – eGovernment Advisory Teams	32

9	Appendix B – Description of Deliverables	34

# Revision History

## Previous Change History

Table a – Previous Change History

| Version | Date | Author | Comment |
| --- | --- | --- | --- |
| 1.0 | 04/30/04 | Elfije Salihu | Initial Draft Review |

## Document Sign-off

Table b – Document Sign-off

| Date | Name | Title |
| --- | --- | --- |

# Introduction

The Project Plan is the comprehensive plan for delivering the eDeployment solution. It delineates the who, what, why, when, where, and how aspects of the project. It is the road map for achieving the program objectives and realizing the project benefits.  The Project Plan is a critical communication tool and is at the heart of the planning and management processes.

Ongoing project planning is crucial to a successful investment.  The Project Plan provides the starting position for project mobilization.  It provides a baseline workplan and identifies the key components of the project such as the project team, the tasks that will be completed, and the timeframe for completing the tasks.  The Project Plan will guide eDeployment team members, management, and stakeholders throughout the phases of the project.  During the course of the project, it may be necessary to update the plan to accommodate approved change requests.

The Project Plan for eDeployment includes the following sections:

- Staffing Plan:  Describes the project team’s organizational structure and their respective roles, responsibilities, and desired skills.

- Quality Assurance Plan:  Addresses the quality management activities for the duration of the project.

- Project Schedule:  Identifies the timeline the project will follow to achieve its stated objectives.

- Costs:  Describes the estimated cost to complete project tasks.

- Deliverables:  Defines all deliverables that will be created during the project.

- Assumptions:  Identifies assumptions made while writing the project plan, which may affect the estimates in each section of the Project Plan.

# Staffing Plan

## Purpose

Managing staff resources properly is crucial to the success of the eDeployment initiative.  The staffing plan will provide an overview of the teams, roles and responsibilities that will be required during various phases of the project to implement eDeployment.

The staffing plan for eDeployment is written to allow for changes in the number and type of staff and/or contracted resources, depending on the project phase and the types of tasks being conducted.  For example, early phases of the project will require a large number of implementation resources such as designers, developers, and testers.  During later phases of the project, the team composition will shift to favor operational roles such as maintenance, administration, and support.

The staffing plan will address the following components:

- Government and Contracted Resources; and

- eDeployment Project Team.

## Government and Contracted Resources

The recommended project team will be a mixture of USDA employees and contracted resources.  Personnel resources will be scaled according to project demands at a given phase.  Initial phases of the project will require a high number of contractors while USDA employees undergo the pre-requisite training and exposure to new technologies.  As the organization’s familiarity and knowledge of the technologies becomes integral to daily business operations, the ratio of contractors to USDA employees will decrease.

It is anticipated that USDA employees will focus in the following areas:

- Coordinating with USDA eGovernment initiatives on an ongoing basis;

- Documenting roles and responsibilities;

- Developing and maintaining a USDA taxonomy;

- Identifying metadata standards;

- Conducting business process re-engineering efforts;

- Defining workflows and associated business rules, roles, and responsibilities;

- Identifying USDA customers and analyzing their needs;

- Developing templates for improved workflow within the solution;

- Managing USDA web presence and content templates;

- Creating educational and marketing materials; and

- Promoting enterprise-wide and Agency communications.

Contracted resources will likely focus in the following areas:

- Designing, developing, installing, and integrating systems;

- Designing and developing shared data sets such as data warehouses;

- Providing program and project management;

- Developing User Interface (UI) standards and associated templates;

- Providing communications support;

- Performing data conversion; and

- Facilitating vendor relationships and procurement activities.

## The Project Team

The project team is comprised of personnel resources with a variety of skill sets.  Throughout the lifecycle of the project, the quantity and type of personnel resources on the project team will fluctuate depending on the phase of the project and the task at hand.

The project team is founded based on the following tenets:

- Focus on cross-Agency participation to continuously and correctly represent requirements from Agencies;

- Focus on a structure that provides governance due to executive sponsorship;

- Apply dedicated USDA full-time resources to build and run the initiative;

- Embody a mixed structure of both contractors and USDA employees; and

- Address the need for business expertise to ensure technology correctly supports the initiative.

The project team hierarchy is organized into three levels to support all USDA enabling initiatives.  The first level consists of executive leadership from the Deputy Secretary, Chief Information Officer (CIO), Associate Chief Information Officer (ACIO) for eGovernment, and eGovernment Advisory Teams.  The second level is the eGovernment Program Management Office, which provides program and project management to the project teams.  The third level consists of the enabling and strategic initiatives’ project teams.  Each project team (e.g., eAuthentication, eDeployment, eLearning, Strategic project teams, etc.) will have a project manager or multiple project managers depending on the scope of work.

Figure 2.3 – Project Organizational Hierarchy

### eGovernment Advisory Teams

The eGovernment Advisory Teams, led by USDA’s eGovernment Executive and supported by the Program Management Office, articulate the big ideas and instill the vision to turn the ideas into reality.  The Advisory Teams also provide leadership and issue resolution for the Enabling Project Teams, including eDeployment.  The Advisory Teams are:

- eGovernment Executive Council;

- eGovernment Working Group;

- eGovernment Steering Committee; and

- Agency eGovernment Team.

The eGovernment Advisory Teams will be responsible for periodically monitoring Agency initiatives for adherence to USDA’s eGovernment Strategic Plan, existing laws and regulations, OMB requirements, National Archives and Records Administration retention schedules, and business requirements.  They will also be responsible for mediating any conflicts that arise among the Agencies and resolving them in the best interest of USDA in upholding or modifying existing standards.  Detailed descriptions of each of the Advisory Teams are located in Appendix A of this document.

### eGovernment Program Management Office

An eGovernment Program Management Office (PMO) will organize and guide the delivery of the enabling initiatives (eDeployment, eAuthentication, and eLearning) while maintaining alignment with USDA’s overall strategic vision for eGovernment.  In addition to spearheading the enabling initiatives, the PMO will also support and partner with USDA’s strategic initiatives.  This will ensure that all eGovernment initiatives are planned and implemented in a consistent, integrated manner under the auspices of the eGovernment executive leadership and advisory teams.  The Program Management Office will require the following processes to support the program:

- Contract management;

- Communications management;

- Configuration management;

- Financial management;

- Issue management;

- Performance reporting;

- Quality management;

- Release management;

- Resource management; and

- Vendor management.

Members of the Program Management Office require the skills to work effectively with others and provide both leadership and support to the team in their respective areas.  The Program Management Office will also be responsible for coordinating overall PMO tasks with the Project Manager for eDeployment.

### eDeployment Project Team

The eDeployment project team is responsible for conducting all eDeployment implementation tasks and ensuring that the eDeployment solution meets the needs of all of its users.  The project team is organized into the following groups:

- Implementation Team; and

- Support Team.

USDA Agencies will work closely with the Implementation Team, the Support Team, and various subject matter experts when they are ready to implement eDeployment capabilities.  The Program Management Office will define a formalized process that outlines the guidelines and expectations for early adopter Agencies working with the eDeployment project team.

Figure 2.3.3 – eDeployment Project Team

#### Implementation Team

The eDeployment solution consists of distinct technical capabilities.  Therefore, it is recommended that separate implementation teams be created under the auspices of the eGovernment Program Management Office.  The implementation teams will include, but are not limited to, the following:

- Web Content Management;

- Document Management; and

- Portal Services / www.usda.gov.

Each Implementation Team is responsible for designing, developing, testing, and deploying the technology capability.  Each implementation team will be structured as follows:

- Project Management;

- Application Design/Development;

- Business Process/Quality Assurance; and

- Change Management/Training.

Personnel resources on the Implementation Team will fluctuate depending on the task at hand or the phase of the project.  For example, the project may have a high composition of designers/developers during early phases, but then may transition to a majority of testers and trainers in later phases of the project.

The Implementation Team will require the following roles and responsibilities:

- Project Manager:  Project managers ensure that all areas of the project match the scope and schedule identified at the beginning of the project.  If issues arise that affect these areas, they work with staff and management to resolve the issues efficiently and effectively.  Ideally, these risks are either avoided with a well-developed project plan and timely and effective communication with staff about deliverables and schedules, or seen very early and mitigated with the lowest impact on the project.  Project Managers also serve as liaisons with management on all areas of the project, such as in the Program Management Office (PMO).

- Application Designer/Developer:  The Application Designer/Developer is responsible for designing, building, testing, deploying, and maintaining the application components.   The Application Designer/Developer will also ensure that developed or modified application components align with the application architecture and meet application performance goals.

- Business Process/Quality Assurance:  The Business Process designer is responsible for identifying current eDeployment processes, documenting changes to these processes, and defining the processes that are required to manage new eDeployment activities.  The Business Process designer ensures that any changes to existing policies and standards are identified and documented.  Additional responsibilities include refining existing eDeployment requirements and documenting new requirements (such as functionality enhancements).

During later phases of the project, it is logical for the process designer to transition into a quality assurance/testing role.  This role consists of test planning and test execution to verify that project quality requirements are met.  Related tasks include writing test scripts, documenting expected results, and validating test results to ensure that they meet entry and exit criteria.

- Change Management/Training Specialist:  The Change Management/Training Specialist is responsible for planning and implementing the workforce transition to the new eDeployment capability.  Responsibilities include identifying critical roles for evolving and sustaining the eDeployment capability and developing the detailed design of the new organization (roles, responsibilities, reporting relationships, rewards, and career management).  It is critical that roles and responsibilities be defined for both the Department and Agency organizations in USDA.

During later phases of the project, the Change Management/Training Specialist will be responsible for preparing training materials and logistics, conducting training, and customizing training/education design to meet ongoing needs.

#### Support Team

In addition to tasks performed by the Implementation Team, there are also many tasks that will be required universally across all implementation teams.  A support team will be created to conduct these “core” implementation tasks and to ensure that all activities are consistent, integrated and performed in a collaborative manner.  This team is the “glue” that holds USDA’s enterprise capabilities together and ensures that all tasks are completed in an integrated fashion with an enterprise-wide perspective.  The support team will be comprised of the following groups:

- Project Management;

- Technical Architecture;

- Data/Migration;

- UI/Web Presence; and

- Production Support.

##### Project Management

- Project Manager:  The Support Team will require its own project management.  During initial project mobilization only one project manager will be required, but as the Support Team grows larger and the scope of work increases, additional project management support will be needed.

##### Technical Architecture

- Network Engineer:  The Network engineer is responsible for configuring the network development, production, and test environments for implementation efforts (e.g., Content Management, Document Management, Portal Services.)

- System Administrator:  The system administrator installs, configures, and maintains the software and hardware development, production, and test environments for implementation projects.  This includes installing and configuring Enterprise Application Integration (EAI) and Content Aggregation (CA) components.

- System Developer:  The System Developer is responsible for the design, development and testing of custom Enterprise Application Integration (EAI) components and custom Content Aggregation (CA) components.

- Technical Architect:  The Technical Architect is responsible for designing the enterprise-wide eDeployment physical architecture.  This resource will work with other architects to ensure that the developed and deployed capabilities align with specific application components and enterprise-wide architecture objectives.  In addition, the Architect will identify and resolve cross-capability issues that affect the business architecture integrity.

##### Data/Migration

- Content/Document Migrater:  The Content/Document Migrater is responsible for leading the content/document migration effort.  This includes managing the preparation of content/documents as well as the transition of content/documents into new tool.  Other responsibilities include identifying and resolving content/document ownership and deployment issues.  The Migrater will work closely with the implementation teams to ensure that all components interact to meet performance goals.  Following implementation, the Migrater will coordinate change requests to taxonomy, workflow, etc.

- Database Administrator:  The Database Administrator (DBA) supports the application Designer/Developer and Production Support by applying and implementing data models, administering user management of databases, and performing data backup and recovery.

- Data Architect:  Data Architects are responsible for designing and developing eDeployment databases and data stores such as data warehouses.  In addition to working with eDeployment, Data Architects will also work with other USDA implementation teams (e.g., eLoans, eGrants) to provide subject matter expertise in data design and development.  Data Architects will also coordinate with Taxonomy Specialists to ensure that the data model for the content management system is designed to support the taxonomy.  Data Architects will ensure that consistent communication and coordination exists with the Enterprise Architecture group in OCIO.

- Database Developer:  Database Developers are primarily responsible for writing database scripts for eDeployment applications.  Another key responsibility is to provide data development support for the Production Support team and other application development teams.

##### UI/Web Presence

- Graphic Designer:  Graphic Designers develop the visual presentation of Agency publications, Web pages, Agency branding elements, and user interfaces.  Graphic Designers are primarily responsible for developing graphical content, including prototypes and storyboards.

- Multimedia Specialist: Multimedia Specialists create original multimedia (such as streaming audio/video and digital imagery) and ensure that the files meet industry, USDA, and Government standards (such as captioning for video) for use and availability.

- UI Designer / Developer:  The UI Designer/Developer is responsible for ensuring that application user interfaces are designed effectively to meet the needs of all users.  The UI Designer/Developer will conduct focus groups and/or audience analysis tasks to aid in the design of presentation elements, content templates, and content standards and guidelines.  This resource will collect and analyze user needs to determine the content that users find to be most valuable and what might need to be revised or discarded.  The UI Designer/Developer will work closely with graphic artists to ensure that all elements of the interface work together and have a consistent look-and-feel.

- Usability Tester:  The Usability Tester ensures that web applications, forms, and content comply with usability best practices and standards, especially those mandated by Section 508.  The usability tester will prepare and conduct usability tests to document how usable and navigable a page is, as well as resolve any issues associated with the integration of text, media, graphic design, and branding with the UI.

##### Production Support

- Application Support and Maintenance:  The Application Support and Maintenance role is required once eDeployment applications are deployed to users.  This task consists primarily of responding to customer queries and working with customers to troubleshoot and solve issues related to eDeployment applications.  This will entail updating the application(s) to incorporate enhancements and to fix defects

- Environment Installation and Maintenance:  The Environment Installation and Maintenance team will exist within the selected hosting facility.  This team is responsible for designing, installing, configuring, and updating the technology infrastructure/physical environment.  Other tasks would include management of local area networks, data connectivity, site-wide software and other technology-based services in the operating environment.

- Training and Documentation Specialist:  Training and Documentation Specialists will be required following deployment of the eDeployment solution.  These specialists ensure that all system users are properly and adequately trained and provide follow-on training as the system is upgraded.  In addition, they will develop ongoing training (such as hands-on training and online training) for system users and technical staff.

#### USDA Subject Matter Expertise

Teams of subject matter experts in USDA will be formed on an as-needed basis to perform more specialized roles.  These types of roles may include Business Analysts, Content Managers, Production Managers, Digital Assets/Rights Managers, Records Managers, and Taxonomy Architects/Analysts.  It is expected that USDA employees will perform these roles on a part-time, as-needed basis.  Specialized eDeployment roles may include:

- Business Analysts: Business Analysts develop and follow all levels of the business strategy, including strategic plans, existing Federal laws and regulations, OMB requirements, and other Agency-specific business requirements. They see the big picture of how these systems fit into the overall strategy of the organization, identify and manage project sponsors, preside over the project mandate process, devise an overall workload and budget strategy, and work with the project teams to ensure that the project mandate is fully integrated into the organization. They understand the business, know how to negotiate, understand the concepts and complexities of the initiatives, and can motivate staff and management.

- Content Managers:  Content Managers are experienced in content/information development and management and fully understand the business requirements of both USDA and its Agencies. They lead the planning and execution of USDA/Agencies’ content/information initiatives through teaching, negotiating, and coordinating with all areas within and outside of the organization. Content Managers should be knowledgeable of web technologies, editorial and cataloging processes, information technology infrastructure, and abstract thought.

- Production Managers:  Production Managers ensure that content/information flow through the system(s) at an established rate and acceptable degree of quality. They manage production staff, design production workflow, create and enforce production schedules, and create and enforce quality.

- Digital Assets/Rights Managers:  Digital Assets/Rights Managers understand the complexities of trademark and copyright law for digital assets and ensure that USDA/Agencies do not violate existing U.S. and international laws. They oversee the workflow in any Digital Rights/Digital Asset management system.

- Records Managers:  Records Managers already exist within USDA/Agencies. They must ensure that all Federal laws and regulations about content/document/records management are followed within the system(s).

- Taxonomy Architects/Analysts:  Taxonomy Architects/Analysts develop and maintain taxonomies that relate to the business processes and functions of the organization.  They also assure that metadata usage follows established standards and/or guidelines.  It is ideal for editorial/indexing staff, preferably with library science experience, to be included in this role.  The Taxonomy Architect/Analyst should coordinate with content designers/developers and workflow process teams to provide input into processes such as approval, deletion, archival, updates, etc.

# Quality Assurance Plan

## Purpose

The Quality Assurance Plan for eDeployment outlines the methods and procedures that will ensure that stakeholder expectations and performance objectives are met, that project staff and business partners perform in accordance with metrics set forth in the requirements documents, and that measurable indicators are systematically tracked to assess progress and promote accountability.  It helps to ensure that the project is focused on improving delivery capability in terms of people, processes, and technology.

Although the approach for the Quality Assurance Plan is created in the early stages of the project, it will be updated and managed throughout the project lifecycle.  The Quality Assurance Plan describes:

- Application standards and policies;

- Configuration management;

- Testing;

- Reviews, walkthroughs, and audits;

- Verification and validation; and

- Issue tracking process.

## Application Standards and Policies

Application standards and policies consist of the standards, rules, and guidelines to be followed during the application development process for programming and documenting programs. Application standards and policies are not meant to be used for training purpose, but rather, as a reference manual for the standards set by the development architecture.

Application standards and policies will provide a consistent way of designing, documenting, and programming over the different areas of work, such as user interface design, database design, and application development.  Quality reviews may be derived from these standards and policies.

The application standards and polices will consist of the following:

- Programming standards;

- Performance design guidelines;

- File/Directory naming standards;

- Application program interface (API) description and use;

- Procedures for using the development architecture and its operations support components (e.g., checking in and out code, when backups occur and how to retrieve archived files, compiling programs);

- Data standards; and

- UI standards.

## Configuration Management

Configuration management is the process for controlling changes that occur during the project.  This includes managing changes to several types of project deliverables, including the work agreement/ arrangement letter, project plan, design documents, application modules, and other components of the business capability.

Configuration management relies on a systematic approach for controlling the changes that occur during the project.   The process defines the configuration management activities to be completed, how they are to be accomplished, who is responsible for performing specific activities, when the activities are to happen, and what resources are required.

The configuration management process is determined during project planning.  The process enforces the integrity of the project’s work products throughout all stages of development and maintenance.  The cornerstone of configuration management is the change control process to manage and track changes to all work products.  The change control process will be coordinated with issue tracking processes.

## Testing

Testing is the primary step for evaluating compliance with requirements and ensuring overall quality.  Testing for the eDeployment initiative will be conducted at several levels.  There are three generic test phases, which will be conducted for both application development and technology infrastructure delivery.  These phases include:

- Component or Unit Testing;

- Assembly Testing;

- Product or System Testing.

The same basic steps are followed for each phase of testing. The driver of every test phase is a specification, and the output of every test phase is an executed test model that includes test conditions and expected results, a cycle control sheet, test scripts, and actual results. This allows the testing activities to be described generically throughout this section of the Quality Assurance Plan, with unique considerations or techniques listed in the tasks related to each test phase.

Specifically, the activities common to all phases of testing in the application and architecture segments are as follows:

- Develop test approach – provides the objectives, schedule, environment requirements, and entry and exit criteria for the test stage.

- Plan test – identifies test conditions and test cycles for the test stage.

- Prepare test - defines input data and expected results, scripts the test cycles, defines stubs and job streams, and prepares the cycle control calendar.

- Establish test environment - ensures that the environment is established and tested before test execution.

- Execute test - performs the scripts contained in the test model, compares the actual results to the expected results, and identifies and resolves discrepancies.

### Component (Unit) Testing

A component test is the test of an individual component of the solution. The objective of a component test is to ensure that the component correctly implements the design specifications.

All components of a business capability including technology infrastructure, application programs, conversion programs, input/output (I/O) modules, and job control language are subject to component test. Some human performance and business process components may need to be tested with other components of the business capability.  All of the capabilities of the component should be exercised during component test to ensure that the component meets the functional and quality requirements of the specification.

It is important that the driver of a component test be the detailed design specification documents and not the component itself. If, for instance, one sets out to exercise all of the paths through a particular component as written, the component may pass the tests successfully and yet not implement the specifications from which it was supposed to be created.

### Assembly Testing

The assembly test verifies the interaction of related components to ensure that the components function properly when integrated. As in the case of component testing, this can occur at different levels depending upon ones perspective. Considering the business capability as a whole, assembly testing occurs when all of the business capability elements are brought together for the first time in the business capability release test. Within each business capability element (business process, technology and application), the assembly tests are a function of integrating individually developed components and making sure they work together properly.

In testing either the technology infrastructure or applications, assembly test ensures data is passed correctly between screens in a conversation or batch process and messages are passed correctly between a client and a server(s). The application flow diagram within the application architecture will depict the assemblies—either online conversations or batch assemblies—that will be assembly tested.

By the completion of assembly testing, the object of the test should be technically sound and the information flow throughout should be correct. Component and assembly testing ensures that all transactions, database updates, and conversation flows function accurately.

### Product (System) Testing

The product or system test ensures that all requirements have been met. Like the aforementioned tests, product testing may also occur at multiple levels. However, within these multiple levels, the purpose of testing is the same: to ascertain that the requirements have been met.

The product test verifies the actual functionality of the solution as it supports the various cycles of transactions, the workflow within organizational units and among these units. The specification against which the product test is run is the specification of all applicable requirements.

User Acceptance Testing, or focused user verification of capabilities, is accomplished through a final iteration of product (system) test execution.  In this test, users execute a sub-set of the system test scenarios that represent more end-to-end capabilities. A simulated production environment with production data is used for this iteration of testing.

### Test Plan Quality Assurance

Designated reviewers will participate in all formal testing and qualification activities.  These activities include the following verifications:

- Ensure that test plans adequately verify the software requirements;

- Confirm test environment has a controlled configuration;

- Validate that test data supports all test cases;

- Maintain the integrity of and adherence to test plans during testing; and

- Ensure accurate documentation of test results.

## Reviews, Walkthroughs, and Audits

The goal of the Quality Assurance Program is to deliver an error-free system that meets all requirements and satisfies the needs of the stakeholders and users.  As part of that goal, the quality of the project will be subjected to review, audits, and walkthroughs.  Both processes and technical solutions will be reviewed for quality assurance.  Within the Quality Assurance Plan, objective measures of quality will be used to:

- Monitor compliance;

- Identify deficiencies;

- Correct problems; and

- Avoid repetition of errors by identifying and eliminating their causes.

All reviews, walkthroughs, and audits will be documented.   If an issue is identified, it will be entered into the issue management process and formal project documentation will be updated.

### Reviews

Full reviews will be conducted to verify eDeployment system functionality.  To comply with the issue management process, any issues that are identified will initiate the creation of a system change order.  Functionality reviews will begin at the end of the development phase and any issues or concerns will be identified and corrected during the product test phase.

### Walkthroughs

The eDeployment technical implementation team will be responsible for conducting walkthroughs to support the development and change process.  Walkthroughs consist of a structured series of peer reviews to enforce standards, detect errors, and improve system quality.  The final responsibility of the walkthroughs lies with the eDeployment project management.

### Audits

A technical advisor or other designated technical auditor may be requested to conduct internal audits of the processes for development, issue management, and integration activities to verify compliance with USDA standards.  The project management will create an audit schedule and coordinate the schedule with the auditor.  Detailed results will be reported to management and appropriate team members in a written report.

## Verification and Validation

Verification and validation are performed to ensure that the total collection of deliverables is consistent with the specifications.  The deliverables are verified against the requirements, facilitating stakeholder sign-off. This process helps ensure that the current and future design work products are produced as planned.  In some cases, a separate contract for independent verification and validation may be considered.

The outcomes of this process are:

- Reconciled gaps between design and intent;

- Documented stakeholder buy-in; and

- Verified and validated application design.

## Issue Tracking Process

The issue tracking process documents any issues, open points, or decisions that will have a significant effect on the project. It also records design rationale for later stages of development, particularly maintenance.

An issue tracking process along with issue management is used to ensure that all issues are tracked and resolved.  This deliverable provides a framework to structure discussion of project issues from assessment to resolution. It also helps provide an audit trail of discussion and decisions on all project issues.

A separate issue entry will be created for each issue. These entries will be used as a reference for use by those working and reviewing issues. When creating an issue entry, the following information should be incorporated:

- A general description of the problem to be resolved. A brief and a full description, the issue class (e.g., management), and the items and areas of the project affected by the issue are all included here. Also noted are those groups and individuals that have a stake in the solution of this problem: management, development teams, and business representatives. Other information defined includes the issue's priority, status, date created, author, date due for resolution, and the responsible party for resolving the issue.

- A list of possible, proposed, and final solutions to the problem. In the sample, the process by which the staffing shortfall issue was resolved has been documented. Listed here are several possible alternative solutions to the problem and a brief description of the final resolution of the problem. A brief timeline of the resolution process is also provided.

# Project Schedule

## Purpose

The Project Schedule details all of the tasks required for accomplishing project objectives and satisfying requirements.  It shows the target start and stop dates for activities associated with the accomplishment of significant project milestones.  The Project Schedule is a task-oriented decomposition of the total work scope of the project from planning through implementation.

The Project Schedule contains a listing of tasks related to planning, design, development, testing, management, and quality control tasks.  The Project Schedule for eDeployment will discuss the following:

- eDeployment Project Tasks and Milestones;

- Plan for Progress Updates; and

- Assessing and Managing Schedule Changes.

The Project Schedule is a key component of the Project Plan as it serves as a basis for performance measurement, analysis, and reporting.  It will be updated continually throughout the project to reflect any changes.

## eDeployment Tasks and Milestones

The eDeployment project has been scheduled within a phased approach.  Those Agencies who want to immediately utilize some or all aspects of the eDeployment solution are called “Early Adopters”.  A phased approach will provide flexible options for implementation to accommodate the early adopters as well as other Agencies that are not prepared for implementation.

A phased approach to implementing this initiative is beneficial because it will provide scalability and extendibility.  Scalability means that hardware and software can be purchased to accommodate the needs of the early adopters.  As Agencies throughout the Department are ready to implement eDeployment, hardware, software, and support services can be scaled to accommodate them.  Extendibility means that early adopter Agencies have the ability to implement basic services covering a large subset of eDeployment functionality in a relatively quick timeframe.  Agencies then have the option to extend the functionality provided to meet their specific needs in subsequent phases.

Figure 4.2: eDeployment Project Milestones

eDeployment Project phases, as depicted in Figure 4.2, include:

- Ongoing eDeployment Project Tasks (Q2 FY03-Q4 FY07) – Ongoing eDeployment Project Tasks consist primarily of program management and project management tasks that will be applied consistently to all eDeployment initiatives throughout the lifecycle of the project.  Project management will originate and be coordinated from the eGovernment Program Management Office (PMO).  eDeployment will require ongoing operations, support, and maintenance tasks following the Early Adopters Capability Release.

- Phase 1: eDeployment Pre-Implementation Tasks (Q2 FY03-Q4 FY03)– Phase 1 consists of the tasks that must be performed prior to implementation.  These initial tasks include the vendor analysis and selection process as well as creating and configuring the technology infrastructure and the physical network required for implementation.

- Phase 2: eDeployment Early Adopter Implementation (Q2 FY03–Q2 FY04)– Phase 2 consists of early adopter Agencies’ full implementation of the eDeployment solution.  This includes project planning, design, build, test, conversion, pilot, and workforce transition activities.  It is estimated that early adopter Agencies will have completed the first eDeployment capability release by the fourth quarter (Q4) of fiscal year 2003 (FY2003).  Early adopters’ continued deployment activities, which may include enhancements to the solution or extensions of functionality, would be conducted over the remainder of FY04.

- Phase 3: eDeployment Enterprise-wide Implementation (Q2 FY04-Q4 FY07)– Agencies that did not participate in early adopter implementation activities are expected to deploy the enterprise-wide capability during the time period ranging from Q2 of FY2005 through Q4 of FY2007.  USDA-wide utilization of the eDeployment solution will be realized in Q4 of FY2007.  This, of course, hinges on Agencies’ ability and willingness to participate in implementation activities.

The following timeline shows the project tasks outlined in phases against a quarterly schedule:

Table 4.2a – Ongoing eDeployment Project Tasks

Table 4.2b – Phase 1: eDeployment Pre-Implementation Tasks

Table 4.2c – Phase 2: eDeployment Early Adopter Implementation

Table 4.2d – Phase 3: eDeployment Enterprise-wide Implementation

## Plan for Progress Updates

All members of the eDeployment Implementation Team will be responsible for providing weekly status reports to document their progress against the schedule.  Progress on all tasks will be monitored, documented on the overall project schedule, distributed to the team members and communicated to executive stakeholders.

## Assessing and Managing Schedule Changes

Deviations from the schedule will be assessed on a weekly basis by the eDeployment Project Management to determine impact on the project.  If there is a delay, management will assess its potential impact and decide on a process to address and correct the issue.

Once agreed upon, the project schedule at the beginning of the project will represent the baseline against which progress will be measured.  Weekly updates to the baseline will be made based on the process discussed in the previous section.

# Costs

## Purpose

The eDeployment initiative requires adequate funding to be successful. Funding support will ensure that adequate resources and the necessary subject matter experts are in place to complete this effort.  Funds may come from one of three sources or a combination thereof:

- USDA will fund the eDeployment initiative;

- eGovernment initiatives using eDeployment services will reimburse the project on a fee-for-service basis; or

- Managing Agencies will help subsidize the eDeployment initiative.

A summary of costs incurred in implementing this project is included in the table on the following page; a full description of the assumptions used to calculate these costs is located in the eDeployment cost benefit analysis.

Table 5.2 – Cost Assessment

| Task Description | Schedule | Cost |
| --- | --- | --- |
|  | Start date | End Date |  |
| Project Initiation/Planning | 1/01/03 | 9/30/03 | $305,720 |
| Project Management | 1/01/03 | 9/30/03 | $2,066,707 |
| Data Requirements Definition | 3/31/03 | 9/30/03 | $1,308,259 |
| Data Design | 3/31/03 | 9/30/03 | $2,265,099 |
| Software Acquisition | 3/31/03 | 9/30/03 | $13,846,665 |
| Hardware/Infrastructure Acquisition | 3/31/03 | 9/30/03 | $9,904,062 |
| System Build, Integrate & Test | 3/31/03 | 9/30/03 | $5,443,629 |
| Rollout | 3/31/03 | 9/30/03 | $75,000 |
| System Operations | 3/31/03 | 9/30/03 | $260,550 |
| Adaptive and Corrective Maintenance | 3/31/03 | 9/30/03 | $35,000 |
| Project Initiation/Planning | 10/01/03 | 9/30/04 | $252,000 |
| Project Management | 10/01/03 | 9/30/04 | $1,894,756 |
| Data Requirements Definition | 10/01/03 | 9/30/04 | $3,230,327 |
| Data Design | 10/01/03 | 9/30/04 | $1,696,609 |
| Software Acquisition | 10/01/03 | 9/30/04 | $16,044,374 |
| Hardware/Infrastructure Acquisition | 10/01/03 | 9/30/04 | $10,000 |
| System Build, Integrate & Test | 10/01/03 | 9/30/04 | $2,807,974 |
| Rollout | 10/01/03 | 9/30/04 | $400,194 |
| System Operations | 10/01/03 | 9/30/04 | $260,550 |
| Adaptive and Corrective Maintenance | 10/01/03 | 9/30/04 | $1,091,026 |
| Project Initiation/Planning | 10/01/04 | 9/30/05 | $343,300 |
| Project Management | 10/01/04 | 9/30/05 | $1,787,936 |
| Data Requirements Definition | 10/01/04 | 9/30/05 | $136,000 |
| Data Design | 10/01/04 | 9/30/05 | $285,492 |
| Software Acquisition | 10/01/04 | 9/30/05 | $20,335,740 |

| Task Description | Schedule | Cost |
| --- | --- | --- |
|  | Start date | End Date |  |
| Hardware/Infrastructure Acquisition | 10/01/04 | 9/30/05 | $3,731,892 |
| System Build, Integrate & Test | 10/01/04 | 9/30/05 | $2,162,552 |
| Rollout | 10/01/04 | 9/30/05 | $2,596,581 |
| System Operations | 10/01/04 | 9/30/05 | $288,150 |
| Adaptive and Corrective Maintenance | 10/01/04 | 9/30/05 | $1,091,026 |
| Project Initiation/Planning | 10/01/05 | 9/30/06 | $355,100 |
| Project Management | 10/01/05 | 9/30/06 | $1,605,656 |
| Data Requirements Definition | 10/01/05 | 9/30/06 | $142,000 |
| Data Design | 10/01/05 | 9/30/06 | $215,492 |
| Software Acquisition | 10/01/05 | 9/30/06 | $24,703,257 |
| Hardware/Infrastructure Acquisition | 10/01/05 | 9/30/06 | $6,435,272 |
| System Build, Integrate & Test | 10/01/05 | 9/30/06 | $1,296,892 |
| Rollout | 10/01/05 | 9/30/06 | $3,371,970 |
| System Operations | 10/01/05 | 9/30/06 | $339,900 |
| Adaptive and Corrective Maintenance | 10/01/05 | 9/30/06 | $1,151,026 |
| Project Initiation/Planning | 10/01/06 | 9/30/07 | $367,300 |
| Project Management | 10/01/06 | 9/30/07 | $1,622,756 |
| Data Requirements Definition | 10/01/06 | 9/30/07 | $147,240 |
| Data Design | 10/01/06 | 9/30/07 | $215,492 |
| Software Acquisition | 10/01/06 | 9/30/07 | $25,632,344 |
| Hardware/Infrastructure Acquisition | 10/01/06 | 9/30/07 | $40,000 |
| System Build, Integrate & Test | 10/01/06 | 9/30/07 | $1,296,892 |
| Rollout | 10/01/06 | 9/30/07 | $3,371,970 |
| System Operations | 10/01/06 | 9/30/07 | $339,900 |
| Adaptive and Corrective Maintenance | 10/01/06 | 9/30/07 | $1,091,026 |

# Project Deliverables

## Purpose

A deliverable reflects the documented information and knowledge produced as a result of executing the project.  The major project deliverables, along with the phase where the deliverable will be completed and the team who is responsible for producing the deliverable, is listed in the table below.

Some of the deliverables will be continuously updated throughout the project lifecycle and many will be delivered for each implementation of the solution.

## eDeployment Project Deliverables

Table 6.2 – eDeployment Project Deliverables

| Deliverable Name | Phase | Responsibility |
| --- | --- | --- |
| Request for Proposal | Phase 1 | Program Management Office |
| Project Plan | Phase 1 | Project Manager |
| Vendor Evaluation | Phase 1 | Project Manager, Application Design/Development Team |
| Vendor Comparison Matrix | Phase 1 | Project Manager, Application Design/Development Team |
| Application Interaction Model | Phase 1 | Application Design/Development Team |
| Application Process Model | Phase 1 | Business Process/Quality Assurance Team |
| Application Architecture | Phase 1 | Application Design/Development Team |
| Technology Infrastructure Design | Phase 1 | Technical Architecture Team |
| Project Plan | Phase 2 | Project Manager |
| Refined Functional Requirements | Phase 2 | Business Process/Quality Assurance Team |
| Business Process Design | Phase 2 | Business Process/Quality Assurance Team |
| Business Performance Model | Phase 2 | Change Management/Training Team |
| User Interaction Model | Phase 2 | UI/Web Presence Team |
| Application Architecture | Phase 2 | Application Design/Development Team |

| Deliverable Name | Phase | Responsibility |
| --- | --- | --- |
| User Interface Design | Phase 2 | UI/Web Presence Team |
| User Interface Standards and Guidelines | Phase 2 | UI/Web Presence Team |
| Data Model | Phase 2 | Data/Migration Team |
| Data Flow Diagram | Phase 2 | Data/Migration Team |
| Product/Assembly/Component/Acceptance Test Plan | Phase 2 | Business Process/Quality Assurance Team |
| Database Design | Phase 2 | Data/Migration Team |
| Usability Test Model | Phase 2 | UI/Web Presence Team |
| Media Content Design | Phase 2 | UI/Web Presence Team |
| Application Training Materials | Phase 2 | Change Management/Training Team |
| Product/Assembly/Component/Acceptance Test Deliverables | Phase 2 | Business Process/Quality Assurance Team |
| Project Plan | Phase 3 | Project Manager |
| Functional Requirements | Phase 3 | Business Process/Quality Assurance Team |
| Business Performance Model | Phase 3 | Change Management/Training Team |
| Business Process Design | Phase 3 | Business Process/Quality Assurance Team |
| User Interaction Model | Phase 3 | UI/Web Presence Team |
| Application Architecture | Phase 3 | Application Design/Development Team |
| User Interface Design | Phase 3 | UI/Web Presence Team |
| User Interface Standards and Guidelines | Phase 3 | UI/Web Presence Team |
| Product/Assembly/Component/Acceptance Test Plan | Phase 3 | Business Process/Quality Assurance Team |
| Database Design | Phase 3 | Data/Migration Team |
| Usability Test Model | Phase 3 | UI/Web Presence Team |
| Media Content Design | Phase 3 | UI/Web Presence Team |
| Application Training Materials | Phase 3 | Change Management/Training Team |
| Product/Assembly/Component/Acceptance Test Deliverables | Phase 3 | Business Process/Quality Assurance Team |
| Data Flow Diagram | Phase 3 | Data/Migration Team |
| Data Conversion Design | Phase 3 | Data/Migration Team |

# Assumptions

Assumptions made within the Project Plan regard the scope and approach to be taken for a project. The assumptions should be used to review the estimate with management and as a basis for understanding when to re-estimate.

Assumptions should continue to be documented throughout the development of the Project Plan; management will review the assumptions during the Project Plan approval process. The assumptions apply to all projects, including those that address the management functions, such as quality management or configuration management.

Table 7  – Project Plan Assumptions

| Number | Assumption |
| --- | --- |
| 1 | Costs are based on the assumptions in the CBA. |
| 2 | Skilled resources are available as planned. |
| 3 | USDA resources are available to assist with specific project tasks as defined by the project manager. |

# Appendix A – eGovernment Advisory Teams

This section describes the eGovernment Advisory Teams.

- eGovernment Executive Council:  The eGovernment Executive Council is an interagency management structure established to lead USDA’s transformation to a citizen-centric electronic service delivery provider in accordance with customer and industry expectations.  It is also intended to provide guidance delineated in mandates such as the Federal Records Act, the Paperwork Reduction Act, the Government Performance and Results Act, the Clinger-Cohen Act, Government Paperwork Elimination Act, Freedom to E-File Act of 2000, OMB Circular A-130, and President Bush’s Management Agenda.  The Council strives to champion the use of eGovernment technologies as an enabler for delivering enhanced USDA products and services more effectively and efficiently.

The eGovernment Executive Council is comprised of Senior Executive Program Leaders representing each USDA Mission Area.  The Council is chaired by USDA’s eGovernment Executive.

- eGovernment Working Group:  The eGovernment Working Group represents individuals who will coordinate activities related to eGovernment on behalf of their respective Agencies.  The members of the eGovernment Working Group are Executive Sponsors, designated by an Agency Head, from either the business or information technology area of each Agency.  The Working Group is chaired by USDA’s eGovernment Executive.

Members from the eGovernment Working Group will serve as liaisons to other working groups in USDA such as the Cyber-Security and Telecommunications Advisory Councils and the USDA Webmasters group as well as external committees such as those connected to the Federal CIO Council eGovernment Committee.

- eGovernment Steering Committee:  The USDA eGovernment Steering Committee will undertake the task of providing organization-wide guidance and coordination of Agency activities necessary to implement an enterprise-wide eDeployment solution. The eGovernment Steering Committee, comprised of subject area leads that represent each of the eGovernment strategic and enabling initiatives, will make every effort to support interoperability among the USDA Agencies as well as among other Federal government Agencies taking part in the overall eGovernment initiative.

- Agency eGovernment Teams:  Each Agency will form an internal Agency eGovernment Team, chaired by the Agency’s eGovernment Working Group member, to work in conjunction with and support of the broader enterprise Working Group and to develop Agency-specific initiatives.  The Agency eGovernment Teams will be comprised of program or business leaders as well as specialists who represent the Web team, capital planning and investment control, public affairs, information technology, security, privacy, forms management, and records management.  The Agency Head and associated eGovernment Executive Council member will also serve as ex-officio members on the Agency eGovernment Teams.

Agency liaisons to the eGovernment team and Agency business managers will be responsible for the following tasks:

- Ensuring that USDA receives regular reports on the implementation of the initiative;

- Ensuring that Agencies adhere to existing laws, regulations, and standards;

- Ensuring that any requests for additional resources are made according to existing rules;

- Ensuring that requests for cross-Agency services (such as portal services or B-to-B extranets with Agency or USDA partners) are managed; and

- Overseeing that all efforts are coordinated internally with Agency management, including CIO’s and Agency administrators.

# Appendix B – Description of Deliverables

This section includes explanations of the eDeployment Project Plan deliverables that are delineated in Table 6.2.

- Application Architecture:  The Application Architecture represents a set of overall decisions that are documented by mapping the functional requirements of the application to its internal architecture (i.e., decomposing the application into sub-components and specifying the interactions between them) and to a set of design standards.

- Application Interaction Model:  The Application Interaction Model represents the business processes from a user/application point of view.  It describes a level of workflow analysis that focuses on the user's business goal.  Typically, a series of application interactions will define an entire workflow.  In other words, all user and application tasks in a workflow will be part of an overall Application Interaction Model.

- Application Process Model:  The Application Process Model, created as part of a requirement analysis, describes the conceptual data process flows of the future application.  It documents the application as a hierarchical organization of processes.  It is used to document the new application's data flows on different levels of detail and/or different levels of process decomposition, supported by elementary process definitions where required. The process hierarchy can be optionally supplemented with data flow descriptions that document the information that flows between the processes.

- Business Performance Model:  The Business Performance Model contains the performance targets and indicators for the business architecture and for each business capability. The model includes the definitions of metrics as well as the methods of measurement, presentation, and communication that monitor the performance of each business capability during implementation.  The Business Performance Model is an iterative document that can be updated and refined as the delivery effort progresses through planning and analysis, to designing, building, deployment, and eventually operation.

- Business Process Design:  This deliverable contains all supporting information for Business Process Designs including workflow diagrams and other related information.

- Cost and Benefit Analysis of Vendor Finalists:  This deliverable contains a comparison of the costs and benefits associated with all of the vendor finalists.  It is created after collecting vendor information regarding capabilities and contract terms.  The document is used as input for selecting one vendor finalist.  It ensures that important costs and benefits, both economical and intangible, are considered in the finalist decision.

- Current Business Capability Assessment:  This document is a detailed analysis of the existing capability in terms of human performance, business processes, physical environment, application, and technology infrastructure.  The objective of the analysis is to establish a detailed understanding of not only the boundaries, operational implications, and rationale behind the current capability, but also the stimuli for change.  This type of analysis is applicable when specific requirements and the impact of the proposed changes need to be defined before detailed design begins.

- Data Conversion Design:  This deliverable defines the issues and resolutions involved in converting the data from the current application (if applicable) to the new application. It is useful for documenting the requirements, manual and automatic procedures, and programs needed to extract data from the current application(s), cleanse it, and load it into the new application.

- Data Flow Diagram:  The Data Flow Diagram is a common, convenient way to represent an information processing application as a series of data flows between application processes and entities. It graphically represents processes as transformations of inputs into outputs by showing a series of application processes connected by the required data flows.

- Data Model:  The Data Model is a description of the data requirements for the future application that is utilized during the requirements analysis process.  This document is critical for query and reporting applications, as well as tracking modifications to the data requirements over the course of the application's life cycle.

- Database Design:  This deliverable addresses the logical view (programmers and users) and the physical view (database administrators) of the database.  It models the logical and physical aspects of the future database prior to its construction.

- Functional Requirements:  Functional Requirements detail what the application must do to satisfy the business needs of the customers and stakeholders, including details such as categorization, importance, and clear descriptions.  Functional requirements do not include specific technical details related to implementation that are determined through the design process.

- Media Content Design:  This deliverable contains a detailed description of the media content.  The Media Content Conversion Procedures, as well as the Media Content Standards and Guidelines, are also documented within the Media Content Design deliverable.  Ultimately, the Media Content Design will serve as the basis for the work to be done by the media content developers.

- Vendor Evaluation:  A Vendor Evaluation documents the software selection process and its resulting decisions, including any recommendations for installation and contract negotiations.  This deliverable addresses vendor performance, software references, costs, benefits, risks, and the strategy for vendor contract negotiations.

Project Plan:  The Project Plan is a detailed schedule that documents the baselines mutually agreed to by the program and project managers.  It is an inherently flexible document that can accommodate any modifications to the schedule as the project progresses.  It consists of all project-planning documents needed to effectively perform and control project activity, such as the Project Schedule and Milestones, the Project Work Plan, the Project Resource Plan, etc.

- Request for Proposal:  This deliverable prepares a request to submit a quote or proposal for providing goods or services to a candidate supplier.  The request describes the item(s) being procured and all associated requirements (e.g., quantities, delivery dates, packaging and shipping instructions, warranties, etc.). Quotes are typically requested for procurement of goods, while proposals are requested for procurement of services, or a combination of goods and services.

- Product/Assembly/Component/Acceptance Test Plan:  The Product/Assembly/Component/Acceptance Test Plan is developed concurrently with the specification it is testing. It accurately and completely documents the test's conditions and expected results. The test plan also contains the list of test cycles: logical groups of test conditions that facilitate the preparation and execution of the test model.

- Product/Assembly/Component/Acceptance Test Deliverables:  The Product/Assembly/Component/Acceptance Test deliverables define the steps, input data, and expected output for a number of test conditions.  These deliverables provide detailed instructions to the test executor in a clear, unambiguous, and repeatable manner.

- Technology Infrastructure Design:  This deliverable consolidates the designs for the development, execution, and operations architectures as well as physical network and computing.

- Training Materials:  This deliverable outlines the plan for the eDeployment training program.  Guidelines for using the eDeployment solution will be documented for the workforce transition to the new capability.  Training materials could include instructor-led training, self-study training, and/or computer-based training.  If possible, eDeployment will leverage the eLearning solution.

- Usability Test Model:  This deliverable is a composite deliverable that contains the test plan, test scripts, and evaluator profiles for a particular usability test.

- User Interaction Model:  This deliverable describes how the users will interact with the future application and how the application will be integrated into their work.  This deliverable is used to support decisions on how the users will interact with the application by designing the high-level user interface and primary methods for interaction.

- User Interface Design:  This deliverable outlines the procedures and guidelines for the application user interface.  User interface design also includes planning the usability evaluations and determining the number of design iterations needed.  This deliverable is developed before finalizing the work plan for human-computer interaction-oriented tasks.  This aids the project planner in allocating resources in a way that can maximize the usability of the system.

- User Interface Standards and Guidelines:  This deliverable is used to document the user interface standards that must be followed, and the less strict user interface guidelines. The guidelines are general design principles that should be followed by user interaction designers, based on the user population and their tasks. Their main purpose is to provide an appropriate level of user interface consistency throughout the application. Develop initial user interface standards and guidelines early in the project, but be careful to provide a process for updating them as the project learns more about the business representatives and the tasks they perform.

- Vendor Comparison Matrix:  This deliverable compares how each vendor scores on each of the requirements groupings.  This deliverable can be used to summarize and compare the vendors' responses to screening criteria and to select two to three finalists.  Refer to it again when selecting one vendor finalist and while negotiating contract terms.

# Footnotes

eGovernment Advisory Teams are as follows:  eGovernment Executive Council, eGovernment Working Group, eGovernment Steering Team, and Agency eGovernment Teams.  A detailed explanation of these teams and their functions can be found in Appendix A of this document.

USDA’s strategic Smart Choice initiatives are: eLoans, eGrants, Online Trade Assistance, Food Safety and Security, and Supply Chain Management.