# Office of the Chief Financial Officer

# e-Payroll

# Project Plan

Version 2.0

February 2, 2004

DOCUMENT HISTORY LOG

| Status (Baseline/ Revision/ Canceled) | Document Revision | Effective Date | Description of Change |
| --- | --- | --- | --- |
| Baseline |  | 1/21/04 | Initial Release |
| V2.0 | V2.0 | 6/30/04 | Updated Configuration Management Section to reflect how changes to NASA related documentation and processes will be handled. Added comment to reference Operations Plan in Appendix |

TABLE OF CONTENTS

1	Scope	6

2	Applicable documents	7

3	Introduction	7

3.1	Project Identification	7

3.2	General History and Summary	7

3.3	e-Payroll Project Overview	10

3.4	Approach	11

4	Objectives	12

4.1	Agency Business Drivers	12

4.2	Functional Drivers	13

4.3	Performance Indicators	14

4.4	e-Payroll Success Criteria	15

4.5	e-Payroll Project Management Success Criteria	20

5	Customer Definition and Advocacy	21

5.1	Communication	22

6	Project Authority	26

7	Management	27

7.1	IFM Program Management Organization	27

7.2	e-Payroll Project Organization	31

7.3	Project Management Support, Monitoring and Status Processes	40

7.4	Management Support Systems/Tools	40

8	Project Requirements	42

8.1	Requirement Levels	42

8.2	Level I – Agency Business Drivers	42

8.3	Level II – Project Functional Drivers	43

8.4	Level III – High Level Requirements	43

8.5	Level IV – Acquisition Requirements	44

8.6	Level V – Implementation Requirements	44

9	Technical Summary	45

9.1	e-Payroll Functional Overview	45

9.2	Facilities	45

9.3	Mission Results Analysis and Reporting	45

10	Logistics	46

11	Schedule	46

11.1	Project Schedules Overview	46

12	Resources	49

12.1	Funding and Institutional Requirements	49

13	Controls	50

14	Implementation Approach	51

14.1	Implementation Overview	51

14.2	e-Payroll Project WBS	53

14.3	Contractor Support	53

14.4	Descope Approach	55

15	Program/Project Dependencies	56

16	Agreements	56

17	Safety and Mission Success	57

18	Risk and Issue Management	57

18.1	Risk	57

18.2	Issues	58

19	Environmental Impact	58

20	Test and Verification	58

20.1	Testing Phases	58

20.2	Testing Environments	59

21	Technology Assessment	59

22	Commercialization	60

23	Reviews	60

23.1	Management Reviews	60

23.2	Independent Assessments	61

23.3	Technical Reviews	61

24	Tailoring	61

25	Change Log	62

APPENDIX A:  Acronyms	63

APPENDIX B:  DOI Service Level Agreement	67

APPENDIX C:  LEVEL III Requirements	76

APPENDIX D:  Concept of Operations	82

# Scope

This is the Project Plan for implementation of e-Payroll, an element of the Office of Personnel Management (OPM) e-Government initiative mandated by the President’s Management Agenda (PMA).  The scope of this document includes all required sections as directed by NASA Procedures and Guidelines (NPG)-7120.5B.  The purpose of the Project Plan is to establish an overarching structure for managing the e-Payroll Project, including general requirements, performance goals, organization and management structure, participants and their roles and responsibilities, resources, schedules and controls, risk management, quality management, implementation approach, and customer definition and advocacy.

The e-Payroll Project will transition NASA’s payroll service delivery to the Department of Interior (DOI) utilizing the Federal Personnel and Payroll System (FPPS), a system operated and maintained by the National Business Center (NBC), a component of DOI.  Implementation will focus on those functions that allow the replacement of the NASA Personnel and Payroll System (NPPS) and provide additional functionality of automated workflow for SF 50/52 processing.

The scope of the e-Payroll Project will be limited to:

- Migration of NASA’s Payroll service delivery to DOI

- Migration of personnel transactional processing functions from NPPS to FPPS

- Incorporating additional functionality of SF 50/52 automated workflow

- Status Quo T&A and Labor Distribution processing

- Establishing report capabilities and interfaces to remaining legacy systems

- Conversion of NPPS personnel and payroll historical data to FPPS Datamart

- Additional transactional process automation achieved via the standardization of an Agency Award system

During the project formulation phase, standardization of a single Labor Distribution System or interface was determined to be out of scope for e-Payroll implementation.  Interfaces with existing unique Center Labor Distribution systems will be developed, rather than standardizing a single system or interface.  This is largely due to schedule constraints imposed by the OPM timeline for implementation.

In accordance with the Service Level Agreement (SLA) between NASA and DOI (Appendix B), the e-Payroll Project will use the FPPS in its native form and not seek to have the system modified.  The e-Payroll Migration Team will work with DOI to configure and test the software to include any required interfaces and reports.  NASA payroll staff, personnel staff, and end users will be trained in both the software operational processes and new processes related to NASA unique operations.

# Applicable documents

The following reference is the source documentation used in establishing the e-Payroll Project Plan:

NASA Program and Project Management Processes and Requirements, NPG 7120.5B, November 21, 2002

# Introduction

## Project Identification

Payroll was identified as a future Integrated Financial Management Program (IFMP) component to be implemented as part of the Integrated Human Capital Management (IHCM) module.  Under the PMA, the e-Payroll initiative accelerated the timeline for replacement of NASA’s payroll functions under IFMP.  The initiative addresses payroll functionality similar to that planned for IFMP with the goal of migrating all Federal agencies’ existing payroll service to one of four consolidated Federal payroll service providers no later than September 2004.  NASA has confirmed its commitment to proceed with the migration of its payroll operations to a service provider under the e-Payroll initiative rather than establish a new payroll capability as an extension of the IFMP Human Resources (HR) function.

The Agency Chief Information Officer is the focal point between NASA and Office of Management and Budget (OMB) for all e-Government initiatives.  Because of the tight linkage between e-Payroll and other IFM projects, the IFMP program team will be responsible for program management and ensuring integration with other Agency business processes and their enabling systems.  The e-Payroll Steering Committee will provide oversight and direction to the project.

The Marshall Space Flight Center (MSFC) is the lead Center for project planning and implementation, under the direction of the IFMP Administrative Systems Implementation Project Manager.  Planning will be conducted with broad participation across NASA and will include the e-Payroll Steering Committee, HR Steering Committee, NASA’s Consolidated Payroll Office, the IFM Integration Project Office, and the Sustaining Engineering Support for Agencywide Administrative Systems (SESAAS).

## General History and Summary

The President’s Management Agenda, as it relates to electronic government, designated a number of opportunities for improvement in the Federal Information Technology (IT) sector.  Among the initiatives identified for improvement, consolidation and standardization of Federal payroll were recognized due to the disparity of processes and systems performing essentially the same function, paying employees.  The e-Payroll initiative is a part of the larger e-Government initiative to streamline and modernize human capital systems in an effort to effectively support Agency missions.  As the overseer of payroll and managing partner for the e-Payroll initiative, OPM established and led a working group to analyze Federal civilian payroll service from a Governmentwide perspective in order to identify options for future investments in the modernization and improvement of payroll systems and processes.  The working group (OPM, OMB, and payroll providers) determined that the consolidation of payroll service delivery can be achieved by reducing the number of Federal agencies providing payroll services and systems operations.  Consolidation of payroll processes was the first step in achieving the end state, integrated HR/payroll services.  In September 2002, OPM announced that it intended to consolidate payroll activities at 22 Federal agencies into the 4 ‘best qualified’ organizations; Department of Defense (DOD), Department of Agriculture (DOA), Department of the Interior, and General Services Administration (GSA).  NASA was paired with the Department of the Interior.

NASA’s payroll legacy system and related systems provide the minimum functionality necessary to perform the Agency personnel and payroll functions, but they do not provide NASA employees and managers with the tools necessary to more effectively and efficiently achieve the Agency vision, mission and long-term human capital objectives.  The current payroll and HR systems are incapable of supporting NASA’s future vision as outlined by the IFM Program due to the lack of process standardization, systems compatibility, and integration.  The e-Payroll initiative will not, in and of itself, address all these shortcomings.  However, replacing NASA’s current systems with an e-Payroll solution would provide a framework for future initiatives to improve the accuracy and timeliness of available information, which would enable the Agency to make better decisions, facilitate the implementation of full cost management, and maintain data centrally while creating a foundation for implementation of the overall IFMP vision.

Current system drawbacks include:

- As a 1980’s mainframe system, NPPS has few users, a difficult interface, inaccessible data and narrow functionality;

- Lack of automation requires time-consuming manual intervention for many processes;

- NPPS does not provide the capability for performing out-of-cycle payment transactions;

- NPPS does not enable consolidation of HR operations such as transaction processing and record keeping;

- Inability to electronically process permanent change of station (PCS) data from Travel for purposes of updating taxes, employee profiles, W-2s, and Leave and Earnings Statement;

- Legacy systems track limited payroll and personnel data;

- NPPS gives managers no way to request services or get data on subordinates.

Many of the above items can be addressed by successful implementation of the e-Payroll initiative.

NASA has conceptualized a future state for IHCM that represents opportunities to reorganize and reenergize key IHCM activities to provide effective, efficient, and economical benefits.  For the purposes of e-Payroll, neither process reengineering nor legacy system rework will be in the scope of this activity.  However, the e-Payroll initiative has the potential to improve service, reduce costs, and establish a new framework for IHCM operations.  In order to reap the comprehensive benefits of the e-Payroll activity, it is essential that NASA take advantage of opportunities that move the Agency closer to an integrated system that can support its near-term goals and Governmentwide initiatives.

In response to the OPM e-Payroll initiative, NASA engaged a working group of payroll and HR experts across the Agency to study feasible alternatives for migrating its payroll service delivery to DOI.  The recommendation emerging from the e-Payroll Study proposed that NASA move forward with migration of its payroll services to DOI along with the use of the DOI system capabilities for SF50/52 automated workflow, HR transactional processing, and the use of current NASA time and attendance systems.  NASA’s formal e-Payroll implementation activities began in October 2003.

Since HR functions, as well as a few Payroll functions, are not standardized across the Agency, it was determined that the time leading up to formal implementation (March – September 2003) would be used to review HR and payroll processes and identify areas where standardization can be achieved.  This timeframe was identified as the e-Payroll Formulation Phase.  The following tasks will be covered during this phase:

- Define “to be” business processes

- Define Level IV functional requirements

- Identify interfaces and perform high-level requirements analysis

- Identify reports and perform requirements analysis

- Establish data conversion requirements

- Define project technical architecture

- Define technical requirements

- Finalize requirement analysis and document gaps

- Establish Project Plan for the Implementation Phase

- Establish cost, schedule, and technical success criteria

Department of Interior’s National Business Center is the implementer of e-Payroll.  NASA and DOI will work jointly with implementation activities, which include the following tasks:

- System analysis

- System modification and testing (including interface development)

- Conversion design, programming, and testing

- Change communication

- Training

- Client orientation

- Parallel processing

- Implementation

- Accomplishing operational readiness

- Transfer of records

## e-Payroll Project Overview

NASA’s scheduled implementation for e-Payroll is August 2004.  MSFC was selected to formulate the project and to implement an Agency solution that meets NASA’s payroll and human resource processes and requirements.

Currently, NASA’s payroll activities are consolidated at MSFC.  The NASA Personnel and Payroll System (NPPS) supports payroll and certain personnel transactional processes.  The project will transition sufficient payroll and personnel activities to allow NASA to close NPPS.  The Department of Interior also provides additional personnel functionality.  The scope of implementation for personnel functionality will be limited to HR transactional functions and automated SF50/52 processing, as determined during the project formulation phase.

The Project will coordinate Migration and Process Team activities, including developing standard Agency-level business process requirements analysis based on the selected provider capabilities, and gap assessments. Specific areas of Project responsibility include:

- Obtaining Center commitment to support the project

- Ensuring that interface and report requirements are coordinated with the Integration Project Office

- Supporting the e-Payroll Migration Team and the Center Transition Team activities during implementation

- Managing the successful implementation of the e-Payroll module across NASA

  - Communicating project status and issues to all Centers

  - Supporting the development of implementation plans and schedules with all Centers

  - Providing expertise to support Center implementation activities

  - Developing training materials and managing training at the IFM Competency Center

  - Supporting the facilitation of Change Management for all Centers

- Working with operations elements and supporting transition to operations

- Managing Project level risks

- Reporting of status to IFM Program Director

## Approach

To ensure a successful implementation of the e-Payroll migration, the Project has been divided into four phases.  Details concerning the phases are discussed in the Implementation Approach section of this document.  Table 3.4 displays a high level depiction of the e-Payroll project implementation phases, the tasks within each phase, and the responsible parties.

Figure 3.4 – e-Payroll Project Implementation

# Objectives

## Agency Business Drivers

Within the 2003 NASA Strategic Plan, IFMP is directly aligned with the Plan’s first Implementing Strategy, which is “IS-1. Achieve management and institutional excellence comparable to NASA’s technical excellence.”  Specifically, IFMP is an enabler of the following elements within this Implementing Strategy:  Human Capital, Financial Management, Budget and Performance Integration, Electronic Government and Institutions and Asset Management.  IFMP also works closely with the Agency Chief Information Officer (CIO) in supporting the Plan’s second Implementing Strategy, which is “IS-2. Demonstrate NASA leadership in the use of information technologies.”

Agency and Enterprise Strategic Plans act as a catalyst for assessment of business processes.  To accomplish its mission and support the crosscutting activity, IFMP has identified five business objectives that are characterized as Agency Business Drivers (IFMP Level I Requirements).  The Project’s success will be judged by how well the e-Payroll module supports these defined Agency Business Drivers.  The Agency Business Drivers are:

- Provide timely, consistent and reliable information for management decisions.  Implement standard systems and processes, data integration and a single point of data entry, which will eliminate reconciliation and provide every management level with consistent data for financial and program decision-making.  The IFM Program will also provide analysis and reporting tools to get the right information to the right people at the right level so that they can make timely, informed decisions.

- Improve NASA’s accountability and enable full cost management.  Implement full cost accounting resulting in increased accountability by providing the means to understand cost drivers, determine total program costs, and relate costs to value.  This will allow the Agency to manage programs using full cost management techniques and enhance the ability to manage institutional capabilities.

- Achieve efficiencies and operate effectively.  NASA must evaluate and improve the efficiency and effectiveness of business processes to appropriately support mission program requirements.  Budgets and staffing levels have already been reduced in many administrative areas.  New tools are required to ensure that processes operate effectively (The results are what the processes intended, and they facilitate accomplishing NASA values such as enhancing safety.), are conducted efficiently (reduce resources to implement the processes), and result in overall savings to the Agency (The products managed or acquired by the process are better or cost less.).

- Exchange information with customers and stakeholders.  Implement the infrastructure and tools that will support the free flow of information internally and externally to increase Agency level accountability, achieve integrity of data and information, and communicate cost effectiveness of NASA’s actions.

- Attract and retain a world-class workforce.  IFMP will provide tools and operational environments that contribute to NASA’s ability to attract and retain highly qualified individuals to support the goals and objectives of the strategic enterprises and the infrastructure of the Agency.  To accomplish this, IFMP will provide tools to enable NASA to compete with commercial markets for a highly motivated workforce representing a broad range of skill levels; provide tools to our employees that minimize frustration and maximize their ability to perform value-added functions; and enhance the ability of employees to work in teams across organizations and functions.

## Functional Drivers

The identification of functional drivers and specific measures of success to support the broader Agency Business Drivers provides a framework for Project commitments.  Functional Drivers are Level II requirements that materially contribute to achievement of the Agency Business Drivers.  The e-Payroll Project has developed a set of Functional Drivers that will allow evaluation of benefits resulting from implementation of the IFMP e-Payroll system and processes.  These Functional Drivers will lead to performance measures and success criteria that are the basis for measuring progress and benefit realization through implementation of the FPPS system.  The e-Payroll Project Functional Drivers and their relationship to the Agency Business Drivers are provided in the table below.

Table 4.2 – Mapping of Functional Drivers to Agency Business Drivers

| Business Driver | What it Means | e-Payroll Functional Drivers |
| --- | --- | --- |
| 1 | Provide timely, consistent and reliable information for management decisions | Implement standard systems and processes to promote data consistency, and provide analysis and reporting tools to get the right information to the right people at the right level so that they can make timely, informed decisions. | Provide reports containing timely and accurate personnel/payroll related information, which facilitates management analysis, decision-making, and reporting. |
| 2 | Improve NASA’s accountability and enable Full Cost Management | Implementing full cost accounting, budgeting, and management will result in increased accountability by providing the means to determine total program and project costs and relate costs to value. | Improve the ability to determine the personnel and related costs of providing specific Agency programs, projects, activities, and services. |
| 3 | Achieve efficiencies and operate effectively | NASA must evaluate and improve the efficiency and effectiveness of business processes to appropriately support mission program requirements. | Improve efficiency of payroll operations through consolidation and cross-servicing of processes and procedures, self service input and verification of data, automated work flow, faster processing of transactions, and consistent data quality |
| 4 | Exchange information with customers and stakeholders | Provide the infrastructure and tools that will make data accessible to a wider range of internal and external customers. | Enhance self-servicing of employee and management related actions throughout NASA Provide accurate and timely data to NASA's stakeholders and customers |
| 5 | Attract and retain a world class workforce | NASA needs to continue to attract and retain highly qualified individuals to support the goals and objectives of the Agency Strategic Enterprises and the infrastructure of the Agency. | Provide tools, reports, and self-servicing capabilities that advance NASA’s use of computing technologies. Provide a capability that facilitates integrated and timely personnel actions. |

## Performance Indicators

The General Performance and Results Act (GPRA) of 1993, 31 U.S.C. 1115 (a) – (e) and Office of Management and Budget (OMB) Circular A-11 require Agencies to submit annual performance plans that include performance measures.  A complete performance measure will include “a target level of performance expressed as a tangible, measurable objective, against which actual achievement can be compared, including a goal expressed as a quantitative standards, value, or rate.”  Such a “target” is normally identified as some level of change to baseline data, or through a commitment to a new capability or process.

The e-Payroll Process Teams have identified consensus areas for standardization to be reviewed and incorporated throughout the implementation of the e-Payroll Project.  The functional process owners at the Agency and Center levels approved these improvement areas.

Various performance measures will be employed to gauge the e-Payroll Project’s success, both during implementation and during operations (post-implementation).  During the implementation phase, performance measures are segregated into (a) project measures focusing on cost, schedule, and risk, and into (b) design measures, which target how well the acquired solution meets the basic functional needs.  After implementation, (c) operational measures will gauge the improvements resulting from the new solution.

Design measures are simulated during software testing and are used to measure the effectiveness of functional driver satisfaction during the design and implementation phases.  With operational measures, data concerning e-Payroll functionality will be gathered from current systems to compare existing process performance to the new software performance during implementation.  It is the responsibility of the e-Payroll Project Office to determine what data is compiled and when this activity will take place.

## e-Payroll Success Criteria

Specific success criteria have been developed for each defined functional driver performance metric.  Module success criteria will be measured at three levels:  today’s baseline, ideal or goal, and target or minimum acceptable levels.  The performance measures identified in the table 4.4 will be used to assess the success of the e-Payroll investment and impact on NASA.  The current baseline for each metric will be defined by the e-Payroll Migration Team, Consolidated Payroll Office (CPO), and each Center’s Human Resource Office.

Table 4.4a – Design Performance Measures

| Business Driver | e-Payroll Functional Drivers | e-Payroll Design Measures |
| --- | --- | --- |
| Provide timely, consistent, and reliable information for management decisions | Provide reports containing timely and accurate personnel/payroll related information, which facilitates management analysis, decision-making, and reporting. | Demonstrate reports containing information which supports management analysis, decision making, and reporting |
| Improve NASA's accountability and enable full cost management | Improve the ability to determine the personnel and related costs of providing specific Agency programs, projects, activities, and services. | Demonstrate the ability to calculate and feed labor cost by financial classification structure to Center legacy labor systems and ultimately to the IFMP Core Financial system. |
| Achieve efficiencies and operate effectively | Improve efficiency of payroll operations through consolidation and cross-servicing of processes and procedures, self service input and verification of data, automated work flow, faster processing of transactions, and consistent data quality | Demonstrate a single Agency system for the timely capture and processing of employee pay and benefit data. Demonstrate the ability of the system to deliver data to Center legacy labor systems for additional processing and delivery to the Core Financial module. |
| Exchange information with customers and stakeholders | Improve efficiency of payroll operations through consolidation and cross-servicing of processes and procedures, self service input and verification of data, automated work flow, faster processing of transactions, and consistent data quality | Demonstrate a single Agency system for the timely capture and processing of employee pay and benefit data. Demonstrate the ability of the system to deliver data to Center legacy labor systems for additional processing and delivery to the Core Financial module. |
| Attract and retain a world-class workforce | Provide tools, reports, and self-servicing capabilities that advance NASA’s use of computing technologies. Provide a capability that facilitates integrated and timely personnel actions. | Demonstrate the use of automated tools for data capture and employee self-service transactions. Demonstrate the ability to generate, process, and route personnel actions in an integrated manner with the subsequent payroll process. |

Table 4.4b – Operational Performance Measures

| Business Driver | e-Payroll Functional Drivers | e-Payroll Operational Measures |
| --- | --- | --- |
| Provide timely, consistent, and reliable information for management decisions | Provide reports containing timely and accurate personnel/payroll related information, which facilitates management analysis, decision-making, and reporting. | Demonstrate reports containing information which supports management analysis, decision making, and reporting |
| Improve NASA's accountability and enable full cost management | Improve the ability to determine the personnel and related costs of providing specific Agency Programs, Projects, activities, and services. | Demonstrate the ability to calculate and feed labor cost by financial classification structure to Center legacy labor systems and ultimately to the IFMP Core Financial system. |
| Achieve efficiencies and operate effectively | Improve efficiency of payroll operations through consolidation and cross-servicing of processes and procedures, self-service input and verification of data, automated work flow, faster processing of transactions, and consistent data quality | Demonstrate a single Agency system for the timely capture and processing of employee pay and benefit data. Demonstrate the ability of the system to deliver data to Center legacy labor systems for additional processing and delivery to the Core Financial module. |
| Exchange information with customers and stakeholders | Improve efficiency of payroll operations through consolidation and cross-servicing of processes and procedures, self service input and verification of data, automated work flow, faster processing of transactions, and consistent data quality | Demonstrate a single Agency system for the timely capture and processing of employee pay and benefit data. Demonstrate the ability of the system to deliver data to Center legacy labor systems for additional processing and delivery to the Core Financial module. |
| Attract and retain a world-class workforce | Provide tools, reports, and self-servicing capabilities that advance NASA’s use of computing technologies. Provide a capability that facilitates integrated and timely personnel actions. | Demonstrate the use of automated tools for data capture and employee self-service transactions. Demonstrate the ability to generate, process, and route personnel actions in an integrated manner with the subsequent payroll process. |

## e-Payroll Project Management Success Criteria

Measurement of the successful management of the e-Payroll Project will focus on cost, schedule, and technical/managerial risk.  Table 4.5 below defines specific metrics to be applied to the management of cost, schedule, technical, and management.

Additional measures will include support to the Centers during Agency Roll Out and change management (metrics to be defined in the e-Payroll Project Change Management Plan).

Table 4.5 – Project Management Success Metrics

| Project Criteria |
| --- |
|  | Cost | Schedule | Technical | Management |
| G | Cost at completion will have consumed <75% of reserves | Current phase or project completion will be completed no later than 5% beyond plan date | All Level 3 requirements will be met and performance metrics accomplished | All required management processes (issue, risk, reporting) are in place and working effectively, and Project is staffed with at least 80% of planned staff with no vacancies in key project positions, and Project Steering Committee is actively engaged and at least 80% of members are actively participating in meetings |
| Y | Cost at completion will have consumed >75% of reserves | Current phase or project completion will be completed by less than 15% beyond plan date | One or more Level 3 requirements will only be partially met or significant performance metrics not achieved | All required management processes are not in place or processes in place are ineffective; however, project has developed plans to implement or improve processes within the next reporting period, or Project is staffed with more than 60%, but less than 80% of planned staff with no vacancies in key project positions for a 30- day period, or Project Steering Committee meets infrequently, or members are not engaged with more than 60% but less than 80% of members actively participating in meetings |
| R | Completion of Project will require more funding than authorized in PCC | Pilot phase completion will be more than 15% beyond plan date | Material failure to meet one or more requirements. A business driver will not be satisfied | Required management processes are missing or are ineffective and there are no plans to make improvements, or Project is staffed with less than 60% of planned staff or one or more key project positions is vacant for a 30-day period or longer, or Project Steering Committee has not met in the last quarter or members are not engaged, with fewer than 60% of members actively participating in meetings |

# Customer Definition and Advocacy

For the e-Payroll Project, the direct NASA customers are the HR/Payroll functional process owners, the NASA CFO, and the Consolidated Payroll Office (CPO).  These individuals are responsible for any Payroll and HR processes that will be reengineered or automated under this Project.  As such, these customers will play a strong role in defining Project requirements and priorities, as well as evaluating the success of the Project.  Their organizations and staff will be impacted by the new processes and procedures and/or derive direct work related benefits from the new system.  At the Center level, the primary customers are employees.  NASA IFMP stakeholders in the e-Payroll Project include Program and Project Managers, Senior Executives, OPM, OMB, and Congress.  They are the ultimate beneficiaries of improvements in the systems and process efficiency and effectiveness.

IFMP is an agent of change for the Agency’s business systems but is not the determiner of those changes.  That responsibility resides with the functional process owners and acceptance of the changes resides with the stakeholders.  The IFMP:

- Does not own the functional business processes being changed

- Does not have direct control over institutional funds or staff needed to affect the changes

- Does not have the authority to dictate migration to Agency level processes and systems

- Does not dictate NASA information technology policy and standards

- Does not control policy or funding

Therefore, to be successful, the e-Payroll Project governance must build a coalition of advocacy among and across many levels of NASA.  The customers and stakeholders must have a desire for change and the willingness to fund and support it.

The e-Payroll Project is subject to multi-tiered governance structure through which it achieves advocacy and support:

- e-Payroll Project Steering Committee.  The e-Payroll Steering Committee is the primary governing body of the e-Payroll Project.  The governing role of the Steering Committee is to ensure that the functional area objectives (functional drivers) are met and that cross-Center commitments to Project implementation are achieved.  The e-Payroll Project Steering Committee is chaired by the Deputy Chief Financial Officer and includes the Program Executive Officer for Integrated Financial Management (PEOIFM), Associate Deputy Administrator for Institutions and Asset Management, Chief Information Officer, Assistant Administrator for Human Resources, and Director of the IFM Program as members.

- IFMP Steering Council.  The IFMP Steering Council is chaired by the Program Executive Office for Integrated Financial Management and includes the CFO, CIO, Assistant Administrator for Human Resources and Education, Assistant Administrator for Management Systems and Facilities, Assistant Administrator for Procurement, Institutional Program Officers, and Deputy Center Directors from Centers that have Lead Center responsibilities for the Project.  The governing role of the IFMP Steering Council under e-Payroll implementation is to advise, endorse, and act as advocates for the changes that will be required by e-Payroll implementation.

## Communication

Project communication management includes all the processes required to ensure timely and appropriate generation, collection, dissemination, storage, and ultimate disposition of project information.  It provides the critical link among all customers, stakeholders, ideas, and information necessary for the Project’s success.  The purpose of this section is to:

- Describe the communication approach for the e-Payroll Project.

- Describe the objectives, target audience, messages, and other communication activities in order to mitigate unnecessary resistance and obtain support and commitment from management, staff, and other internal and external customers and stakeholders.

### Communication Approach

Diagram 5.1.1 depicts the high-level activities in the communication approach for e-Payroll implementation.  Details on the e-Payroll communication strategy can be found in the Communication Plan.

Diagram 5.1.1 Change Management Approach

### Communication Objective

The communication objectives of the e-Payroll Project are to build partnerships and sponsorship with internal and external customers and stakeholders by:

- Ensuring that customers and stakeholders are aware of decisions made during Project implementation

- Addressing and resolving issues and concerns related to the design and implementation activities of the Project

- Helping workforce understand “what’s in it for them”

- Providing timely Project information to promote a better informed, more involved, and more committed workforce

- Apprising customers and stakeholders involved in the Project initiative of the expectations for their level of support, roles, and responsibilities

- Provide timely status and issue information to the IFMP office

- Provide effective internal communication among all Project team members

### Target Audiences

The following audiences have been identified as critical to the successful implementation of the e-Payroll Project:

- E-Payroll Steering Committee

- IFMP Office

- Integrated Project Office (IPO)

- IFMP Steering Council

- Consolidated Payroll Office

- Center Leadership

  - Center Director and staff

  - Center CFOs, Center Deputy Chief Financial Officers (DCFO), HR Directors, Center Functional Managers

- Employees

### Communication Messages

Messages developed by the e-Payroll Project will include the following concepts:

- Project status information

- Tactical information concerning implementation of the new system and processes

- Achievement of performance measures

- Benefits to employees and management

### Communication Methodology

The e-Payroll Project will utilize a wide range of communication media.  Mechanisms to support the communication requirements are provided in table 5.1.5.

Table 5.1.5 – Communication Hierarchy

| Target Audience | Objectives/Messages | Vehicle | Timing |
| --- | --- | --- | --- |
| e-Payroll Project Steering Committee | Project status, information exchange, decision making | Telecons, Face to Face Meetings | Monthly at a minimum |
| IFMP Office | Project status, information exchange | Weekly Program Status Telecons, Monthly Project Reviews | Weekly/Monthly |
| IPO | Project dependencies | Weekly Project Status Meetings | Weekly |
| IFMP Steering Council | Project status, information exchange | Briefings | As Required |
| Consolidated Payroll Office | Project status, information exchange | Face to Face Meetings | As Required |
| Center Directors (Financial and HR) | Project objectives, key milestones, high level status, information exchange | Face to Face Meetings | As Required |
| Center Functional Managers | Project-related news, need-to-know information, functional drivers, performance metrics, etc. | Face to Face Meetings, Monthly Program ViTS, e-Payroll Project Web site | Ongoing |
| Enterprise and Program/Project Resource Managers | Project impacts to resource management (process changes, training information, implementation timelines, etc.) | Electronic, Face to Face, Brochures, etc. | Ongoing |
| Employees | Project impacts to personnel (process changes, training information, implementation timelines, etc.) | Electronic, Face to Face, Brochures, etc. | Ongoing |

# Project Authority

The CFO Act of 1990 directs each Agency CFO to develop and maintain an integrated Agency accounting and financial management system.  NASA’s CFO has primary responsibility and authority for the execution of the IFMP.  The CFO is responsible for ensuring that the Program meets externally mandated requirements while satisfying internal customer needs in a cost effective manner.  The NASA Administrator is the approval authority for the IFMP.  The IFMP Director, reporting to the Agency CFO, heads the IFMP office at NASA Headquarters and is responsible for the IFMP management.  The Director is accountable to both the Agency CFO and the IFMP Steering Council.

OMB is the authoritative arm for all e-Government initiatives under the President’s Management Agenda for strategic management of Human Capital.   NASA’s Agency CIO is the focal point between OMB for e-Payroll.   Because of the tight linkage between e-Payroll and other IFM projects, the IFMP Program team will be responsible for Program management and ensuring integration with other Agency business processes and their enabling systems.  The e-Payroll Steering Committee will direct the Project.

The e-Payroll Steering Committee is the principal forum for ensuring that the Project meets OMB’s mandate for migration to the e-Payroll solution under the President’s Management Agenda for the Strategic Management of Human Capital Initiative.  The governing role of the e-Payroll Steering Committee is to ensure that the functional area objectives (functional drivers) are met and that cross-Center commitments to Project implementation are achieved.

The Agency Program Management Council (PMC) will serve as the Governing PMC (GPMC) for the IFM Program.  The PMC assesses Program planning and implementation at the Agency level, provides oversight, and ensures accountability.  The MSFC PMC will serve as the GPMC for the e-Payroll Project.  The MSFC PMC will assess e-Payroll Project planning and implementation.

# Management

The e-payroll project implementation will be accomplished under the IFMP project structure and management.   The IFM program office will provide program oversight for implementation with configuration management and project scope being monitored and approved by the e-Payroll Steering Committee.

## IFM Program Management Organization

Diagram 7.1 illustrates the IFMP Management Organization structure.

Figure 7.1 – IFMP Management Organization

### IFMP Steering Council

The IFMP Steering Council is established as the principal forum for ensuring that the Program meets NASA’s business objectives (Agency Business Drivers).  The Council, comprised of the CFO, CIO, Functional AAs, IPO Deputy Center Directors, and chaired by the Associate Deputy Administrator, will act as a forum for reviewing Program structure and integration issues and for key decision-making.  The Council will recommend actions to the IFMP Director.  Specific areas of responsibility include:

- Approving Program strategy

- Approving module sequencing and priority proposed by the Program Director

- Resolving cross project functional conflicts

- Approving Program scope change

- Ensuring functional integration issues

- Providing budget agreements

- Resolving Process Team issues

- Resolving Project execution issues

- Resolving programmatic and resource issues

- Resolving Change Management issues

- Establishing and assessing business drivers

### IFM Program Executive Officer (PEO)

The IFM PEO, located at NASA Headquarters and reporting to the NASA Administrator, has responsibility for “everything IFM,” including Center implementation and Information Technology (IT) infrastructure.  The most important role of the PEO is ensuring that the IFMP is fully integrated and aligned with major NASA initiatives and priorities.  The PEO also works on behalf of the IFMP to remove obstacles to the successful implementation of new IFMP processes and systems at NASA Headquarters and the Centers.  The PEO also has the responsibility of emphasizing the Program’s importance to NASA senior management.

### IFM Program Director

The IFMP Director, located at NASA Headquarters and reporting to the IFM PEO, has lead responsibility for IFMP management.  The IFMP office has the responsibility to implement the IFMP according to its approved Program Plan, the approved IFMP Project Commitment Agreement, and the individually approved IFMP Project Plans.  Specific responsibilities related to the e-Payroll Project include:

- Setting objectives and requirements

- Setting scope, priorities and control module sequencing and timing

- Establishing framework for conducting Program business within the Program Management Plan

- Managing Program budget

- Managing Program Level risks

- Reporting (PMC, Process Owners, OMB, Congress, Government Agency (GA), Inspector General (IG)

- Establishing the Change Management framework

  - Communications

  - Transition Activities

  - Training

- Assessing Program performance

- Remaining accountable to customers for Program performance

### IFMP Administrative Systems Implementation Manager

Relative to the e-Payroll Project, the IFMP Administrative Systems Implementation Manager is responsible for:

- Project oversight

- Establishing project priorities

- Approving and allocating project funding

- Reporting

- Assessing project performance

### IPO Manager

The IPO Manager at MSFC is responsible for establishing a viable technical infrastructure and ensuring the coordination of various functional module implementations.  Specific responsibilities include:

- Support to Agency Functional Owners

  - Facilitating issue resolution across functional lines

  - Establishing lifecycle requirements management and associated systems and procedures

  - Establishing Competency Center for supporting and sustaining the implemented systems

- Support to Program Office

  - Establishing and maintaining the overall IFMP architecture comprised of business, applications, and technical components

  - Defining technical and integration requirements

  - Providing configuration management infrastructure and support

  - Acquiring and managing the integration contractor

  - Providing support and input to Program Level Analyses

  - Managing Project level risks

  - Reporting status to IFMP Director

- Support to e-Payroll Project

  - Defining the technical requirements and the NASA technical architecture necessary to implement and operate the DOI system

  - Coordinating the development of interface requirements for implementing the DOI system

  - Implementing the integration architecture necessary to consistently integrate the DOI system with other IFM applications, external systems, other Agency systems, and Center level systems

  - Leading the development and implementation of each interface with the DOI system

  - Developing security requirements and working with DOI in the development of the Security Plan for e-Payroll

  - Working with the e-Payroll Project and DOI to establish reporting strategy for Payroll

  - Working with DOI to establish a Service Level Agreement (SLA) and operational procedures necessary to sustain the FPPS

  - Transitioning any NASA maintained components to the IFM Competency Center for long-term sustaining support

  - Work with NASA Center IFM IT Points of Contact (ITPOC) to insure Center level technical infrastructure is in place to support e-Payroll deployment

  - Coordinating IV &V and independent assessments

## e-Payroll Project Organization

Although the e-Payroll initiative addresses the migration of NASA’s payroll service delivery to a service provider, there is tight integration with Human Resource (HR) functions needed to produce payroll products.  Hence, HR transactional processing will be an integral part of e-Payroll implementation.  Because of the degree of integration of payroll and HR data with financial information currently contained within the IFMP module, the e-Payroll Project is organized around the concept of Integrated Product Teams (IPT’s).  An IPT is responsible for delivering a specific product or major work breakdown structure (WBS) element.  Each IPT is comprised of both NASA members and personnel from supporting contractors.  Day-to-day leadership of the IPTs is a shared responsibility between NASA and the implementer, Department of Interior.

Within the IPT concept, the e-Payroll Project Office will provide day-to-day project level management and communicate project implementation status and issues to the e-Payroll Steering Committee.  In addition, the e-Payroll Project Office will be responsible for project coordination among the e-Payroll Migration Team, Data Conversion Team, NASA Payroll and HR Process Teams, Change Management Team, Business Management Support, Integrated Project Office (IPO), Consolidated Payroll Office (CPO), Sustaining Engineering Support for Agencywide Administrative Systems (SESAAS), and Department of Interior.

The e-Payroll Project endorses a true partnering arrangement between NASA and the service provider; however, ultimate accountability rests with the NASA managers/leads.  The e-Payroll Project will rely heavily on the service provider for strategy, methodology, solution recommendations, best practices, benchmarking, and lessons learned data as well as tangible products.  However, the Project must own decisions and recommendations regarding NASA’s business processes and software solutions.

The overall project organization structure is show in Figure 7.2.

Figure 7.2 – e-Payroll Organization

### e-Payroll Project Steering Committee

The e-Payroll Project Steering Committee was established to support the e-Payroll project by serving as a decision making body.  The governing role of the e-Payroll Steering Committee is to ensure that the functional area objectives (functional drivers) are met and that cross-Center commitments to Project implementation are achieved.  The Steering Committee has the responsibility to plan for and ensure success of the e-Payroll Agencywide implementation.   Specific areas of responsibility include:

- Examine and approve the e-Payroll project strategy, e-Payroll service provider selection, migration schedule, scope, scope change, (increases or deletions) and project team issues. The Committee ensures functional integration with other IFMP components and the Agency Enterprise Architecture. The Committee will recommend actions to the e-Payroll Project Manager.

- Ensure adequate business infrastructure support and resource availability as an inherent requirement for achieving mission success. The Committee ensures that the project is making progress in accomplishing the business drivers established under the IFM Program.

- Resolve issues that deal with change management, project execution, business objectives, and programmatic and resource issues.

- Endorse and act as an advocate for the changes that will be required by the implementation of new business processes and systems.

- Ensure the viability of the project, approve the lead Center for the project, and be responsible for deployment Agencywide.

### Business Management Support

The e-Payroll Project Business Manager Support is responsible for:

- Project budget process management

- Provide advice, counsel, guidance, and decisions, as needed, to the Project Manager concerning budgetary matters

- Provide business management support to Center representatives

### e-Payroll Project Manager

The Project Manager is responsible for planning, managing, and implementing the e-Payroll Project with oversight guidance provided by the IFMP Administrative Systems Implementation Manager.  The Project Manager will be semiautonomous, having the authority to tactically manage the implementation of e-Payroll within the policies and guidelines established by the IFMP office and Agency policies and procedures.  The Project Manager will coordinate Migration Team activities, including developing standard Agency-level business processes, updating requirements based on the software capabilities, and gap analysis.  Specific Project Manager responsibilities include:

- Obtaining Center commitment to support project activities

- Working with IPO to establish reporting requirements

- Coordinating the activities of the Migration Team

- Implementing approved, NASA-specific ancillary solutions for functionality gaps in the proposed Government off-the-Shelf (GOTS) Package

- Supporting Center-level transition to the e-Payroll solution

- Leading the Agency transition

  - Coordinating plans with the Centers’ implementation team

  - Coordinating the development of Agency-level training materials and training activities

  - Supporting the facilitation of Change Management at all Centers

- Working with operations elements and supporting transition to operations

- Managing project level risks

- Reporting status to IFMP Director and Administrative Systems Implementation Manager

- Project management processes and documentation (schedule management, issue tracking, and configuration management)

- Quality Assurance

- Risk Management

### Migration Team

The Migration Team will lead Agency-level implementation activities for NASA under the guidance of the Project Manager.  The team will work directly with DOI throughout the formulation and implementation process.  The team is responsible for the overall functional solution and implementation support for the e-Payroll Project.  Team members are primarily Agency-level business process experts, change management experts, and administrative support.

Given the process-driven nature of this implementation effort, the work products of the Migration Team are the critical inputs to the work of the Integrated Project Office.  The Integrated Project Office provides direct support to the Migration Team.  At specified times in the implementation lifecycle, members of these teams will merge to accomplish certain implementation tasks (e.g., functional interface design, training material development, and testing).  Overall responsibilities of the Migration Team include the following:

- Ensuring all e-Payroll formulation prerequisites are fulfilled prior to formal implementation

- Risk management

- Implementation planning and support

- Data conversion, reporting, and interface functional specifications

- Change management (training, communications)

- Application configuration

- Procedure manuals

- Training materials

- Support to Centers during Rollout

#### Migration Team Membership

The Migration Team is composed of the following membership:

- Consolidated Payroll Office/SESAAS representation

- Payroll and HR Process Team Leads

- Agency Change Management Lead

- Project Administrative Support

- Test Team Lead

- Data Conversion Team Lead

- Center Transition Team Lead

#### Migration Team Member Responsibilities

Specific duties of the Migration Team members are shown below.

#### Consolidated Payroll Office/SESAAS

The Consolidated Payroll Office (CPO) and its technical support staff will:

- Provide functional and technical support for Payroll and HR process reviews

- Coordinate data calls for Payroll and HR interface and report activities

- Provide data files for analysis of NPPS/FPPS database crosswalk activities

- Provide consultation for clarification of files and data elements

- Support the IPO and DOI’s Automated Data Processing (ADP) staff with the NASA network and connectivity process

- Provide support for defining existing NPPS reporting capabilities and data structures

- Assist the IPO in interface definition and design activities

#### Payroll and HR Process Team Leads

Payroll and HR Process team leads provide process team lead support for requirement and gap analyses during the formulation phase and support for implementation activities during the implementation phase.

Process Team Leads will be responsible for:

- Directing the coordination of e-Payroll formulation workshops

- Supporting the e-Payroll implementation planning

- Support the e-Payroll Project Manager in resolving issues and actions

#### Agency Change Management Team Lead

The Change Management Team is responsible for coordinating e-Payroll change management, training, and communication activities. The Center-level Change Management Lead falls under the oversight of the Center Transition Team.  The Agency Change Management Lead works closely with Center Change Management Leads in the following areas of responsibility:

- Piloting Program-level change management framework, approaches, tools and techniques for the e-Payroll Project

- Sharing Project information across Centers and to IFMP

- Involving the other Centers’ representatives in Project activities

- Ensuring that management and workforce are prepared to use the e-Payroll solution effectively

- Promoting sponsorship for the e-Payroll Project throughout the Centers

- Ongoing commitment building with key Center stakeholders

- Executing actions to minimize organizational barriers to change

- Providing feedback and metrics to project representatives

- Engaging and seeking knowledge transfer between the e-Payroll Project Office and the NASA Centers

#### Project Administrative Support

The Project Management administrative support will be responsible for:

- Task monitoring

- Project documentation

- Schedule management

- Issue tracking

- Change request control

#### Test Team Lead

The Test Team develops the overall testing strategy for the e-Payroll Project.  The Test Lead works closely with the Process Teams in completion of the following responsibilities:

- Risk management

- Verification that all requirements are met

- Planning, execution, and tracking of pre-parallel testing activities

- Coordinating parallel testing

- Point-of-contact for testing issues

#### Data Conversion Team Lead

The Data Conversion Team Lead will lead the effort to convert data from NPPS to DOI’s FPPS.  The responsibilities will include:

- Oversight of the conversion of NASA’s Payroll and Personnel data to the FPPS data mart

- Support to the definition of data conversion requirements

- Risk Management

- Serving as point-of-contact for issues resolution involving NPPS data

#### Center Transition Team Lead

The Center Transition Team Lead will be responsible for:

- Coordinating Agency-level activities assigned to Centers

- Conducting Center-level status meetings

- Communicating Center-level status and issues to the Migration Team

### Data Conversion Team

The Data Conversion Team will be composed of Agency-level experts knowledgeable of NPPS data elements.  The team will be responsible for supporting DOI with the NPPS to FPPS data mapping, NPPS historical data conversion to the FPPS data mart, and reports and table validation.  Additionally, this team will work closely with the IPO in mapping NPPS to FPPS data elements that will be used by Centers for developing their unique interfaces.

Team member responsibilities include:

- Providing data files for analysis of NPPS/FPPS database crosswalk and conversion activities

- Providing consultation for clarification of files and data elements

- Providing support for defining existing NPPS reporting capabilities and data structures

- Assisting the IPO in interface definition, design, and report activities

### Payroll and Human Resource Process Teams

The Payroll and Human Resource Process Teams are the key players for the Payroll and HR Process Reviews during the formulation phase of e-Payroll and will serve as Center-level points-of-contact for the life of the project.  The process teams will consist of a functional and technical resource from each Center.  The teams will be tasked with evaluating and documenting current Payroll and HR processes under the direction of Process Team Leads and will support the Migration Team throughout implementation.   Results of the  process reviews will validate the existing processes and provide functional requirements for the NPPS to FPPS payroll implementation.

Payroll and HR Process Teams will be responsible for:

- Supporting Agency workshops for process reviews, interface inventory, and report requirements

- Providing Center policy and regulatory documentation as needed

- Supporting the e-Payroll implementation planning

### Test Team

The Test Team will be composed of Agency-level and Center-level experts knowledgeable of NPPS and FPPS data elements.  The team will be trained by DOI on the functionality of FPPS.  The team will be responsible for working with the Test Team Lead during parallel testing.  The team works closely with the Test Team Lead in the following areas:

- Planning and execution of parallel testing activities

  - NASA Test Plan development

  - Development of Test Plan scripts

  - Validation of Test Plan Results

- Coordinating any "work around" solutions for testers

- Point-of-contact for testing issues at respective center

- Inform the Test Team Lead of potential testing problems that arise

### Center Transition Team

The Center Transition Team will consist of Center-level project managers or coordinators.  NASA will deploy the FPPS using the “big bang” approach.  Under the oversight of the e-Payroll Project Manager, specific responsibilities include:

- Supporting Center-level implementation planning

- Site readiness assessments

- Union negotiations

- Post implementation support during stabilization periods

### Department of Interior

The implementation of e-Payroll will be a joint effort on the part of DOI’s National Business Center (NBC) and NASA.  In general, NBC will:

- Conduct requirements and gap analyses to ensure NASA requirements are met by FPPS

- Coordinate with NASA, NBC, and OPM on issue resolution not resolved via the submission of a change request

- Design, program, and test data conversion

- Facilitate/coordinate parallel testing

- Submit e-Payroll client monthly progress reports to OPM

- Conduct joint reviews of DOI’s implementation plan for NASA’s payroll migration

- Provide client orientation database

- Perform NPPS data file analysis during formulation phase (for data elements crosswalk and building historical file)

### Office of Personnel Management

The Office of Personnel Management will be responsible for monitoring the progress of NASA’s       payroll migration.  As the managing partner for e-Payroll, OPM will:

- Track the progress of NASA’s payroll migration by collecting information from DOI on a monthly basis

- Facilitate resolution of questions or issues between NASA and DOI

- Serve as the final decision-maker on e-Payroll related issues between DOI and NASA

## Project Management Support, Monitoring and Status Processes

The e-Payroll Project employs a rigorous weekly monitoring and status process beginning with the individual IPT members and concluding with a project-level status review.  The outcome of each monitoring activity feeds into management of risks, issues, cost and schedule.  Figure 7.3 is a graphical depiction of this weekly review cycle.

Figure: 7.3 – Project Management Monitoring and Status

## Management Support Systems/Tools

The e-Payroll Project uses a number of management support systems.  These support systems are identified below:

- Schedule.  Various schedules (developed with Microsoft Project) are used to evaluate progress towards meeting Project objectives.  Both Program Evaluation Review Technique (PERT) and milestones schedules are developed.

- Project Budget and Cost Tracking

The project budget and cost will be tracked using cumulative cost  and will be compared to the allocated budget on a monthly basis.  e-Payroll budget and cost information will be used for management of project funding and OPM reporting.

- Risk/Issues Management.  A standard Risk Management strategy will be used to support the consistent identification, classification, tracking, and management of Project-level risks.  Action items and issues tracking is based on prioritized lists stored in Excel. These tracking tools will continue to be utilized to initiate, track, and status Project-level issues and action items.  Issue resolution will be addressed through telecons with DOI or the formal process described in the e-Payroll CCB charter as appropriate.

- Requirements, Test Plan and Defect Tracking: Test Director will be utilized to document and track all functional and technical requirements.  Through this tool, test plans will be generated and scheduled to verify the validity of the requirement as it relates to the e-Payroll FPPS implementation.   Defects will be logged based on these test plans and as needed during the system integration and parallel testing.  Defects related to the operation of the FPPS online will be logged and distributed to DOI/NBC in their required problem report format.

- Configuration Management. The implementer, DOI, will be responsible for the configuration management of FPPS.  Configuration management of e-Payroll will apply to documentation as well as changes to FPPS software.  The process for determining when change requests should be passed to DOI is described in the e-Payroll Configuration Control Board (CCB) Charter.   All NASA e-Payroll Project team documentation will continue to reside within the IFMP key project document repository server and will require CCB approval before updating baseline information.

- Change Request Management. The implementer, DOI, and NASA will be jointly responsible for change control with the overall goal of ensuring that changes are identified, defined, evaluated, tracked through completion, and communicated to all affected parties.  During the implementation of FPPS,

NASA will:

- Utilize DOI’s electronic form (Impact Assessment) to define gaps and request changes to FPPS as follows:

  - Type of Gap (Regulatory/ Business Practice)

  - Provide a Description of Difference (between NPPS and FPPS)

  - What functionalities are needed

  - What information/data is used

  - Why the change is needed

  - When the change is needed

  - Provide details associated with this information (e.g., tables, edits, etc.)

  - What is impacted if the gap is not resolved?

- Document the disposition of change requests.

- Escalate change resolution to the OPM Project Manager, as appropriate, if resolution is not satisfactory

DOI will:

- Analyze the extent of changes required

- Classify the change request impact as follows:

  - Green: Minimal overall impact on project cost or quality but does not affect project schedule

  - Yellow: Some impact on project cost or quality, and/or negatively affects the project’s critical path by 5 days or less

  - Red: Substantial impact on DOI project cost or quality, and/or negatively affects the project’s critical path by more than 5 days.

- Determine if the change can be accommodated

- Determine the impact of not implementing the change

- Determine if the change can be deferred to a future release

- Determine any operational constraints that would prevent implementation of the change

- Recommend whether the request should be accepted, rejected, or deferred.

- Inform NASA of disposition of change request

After implementation the change request process will follow the guidelines identified in the e-Payroll CCB.

- Documentation and Control: During e-Payroll implementation, a document repository will be used to maintain and control key e-Payroll Project documentation.  Backups are maintained to ensure recovery from any major data server failure.

- Knowledge Sharing System(KSS): Knowledge Sharing System will be used to document lessons learned during e-Payroll implementation.

# Project Requirements

## Requirement Levels

There are five levels of requirements within the IFMP hierarchy.  Each lower level is derived from and consistent with the higher-level requirements in the hierarchy:

Level I – Agency Business Drivers

Level II – Project Functional Drivers

Level III – High Level Requirements

Level IV – Acquisition Requirements

Level V – Implementation Requirements

## Level I – Agency Business Drivers

An examination of the commonality of the business process and infrastructure needs identified in the Agency and Enterprise Strategic Plans resulted in five Agency Business Drivers approved by the IFMP Steering Council.  Success of e-Payroll will be judged by how well the project contributes to the defined Agency Business Drivers.  The Agency Business Drivers are:

- Provide timely, consistent and reliable information for management decisions

- Improve NASA’s accountability and enable full cost management

- Achieve efficiencies and operate effectively

- Exchange information with customers and stakeholders

- Attract and retain a world-class workforce

## Level II – Project Functional Drivers

Project Functional Drivers are functional area achievements that would demonstrate a measurable improvement in the Agency Business Drivers.  During Project formulation, the e-Payroll Migration Team identified and mapped Functional Drivers to Agency Business Drivers and, further, identified the success measures by which to judge the achievement of each Functional Driver.  The e-Payroll Project Steering Committee approved the Functional Drivers and Metrics.  Section 4.2 defines the Functional Drivers and associated success measures.

Minimum success criteria and performance metrics will be baselined at the outset of the Project and measured during implementation and after deployment to determine the relative level of Project success in meeting the Functional Drivers.

## Level III – High Level Requirements

The e-Payroll Process Team developed a set of Level III requirements, which are documented in the e-Payroll Scope Document.  The Scope Document is used by the IFMP to communicate high-level requirements and responsibility of the Lead Center for the formulation of the e-Payroll Project.  These requirements are used by the:

- Project Manager and Migration Team to brief and receive approval of the proposed process and system changes by the Functional Owners

- Project Manager and Migration Team to evaluate FPPS and develop a functional gap analysis

- IPO Manager to identify integration issues

The requirements at this level are not fixed until after the “period of understanding,” when the initial software gap analysis is completed.  Software gaps may be addressed by:

- Alternative Configuration Approaches – Implementing configuration alternatives within the DOI software that provide flexibility to establish configuration parameters to meet the NASA requirement.

- Policy or Process Change – A NASA policy or process change that is made in order to adapt to the business process supported by the DOI software.

- Bolt-on – A third party software product that can be “plugged in” to fill the gap.

- Extension – An extension to the baseline software that is typically developed using tools provided by the software provider.  Extensions do not involve modification to the baseline software code.

- Modification – A modification to the baseline software (NOTE:  One of the Program's First Principles is to use COTS software in its native form and not seek to have the COTS modified.  Such actions require approval by the IFMP Steering Council.  For the purposes of the e-Payroll Project, the DOI software will be treated as COTS software).

## Level IV – Acquisition Requirements

The e-Payroll Migration Team, Payroll and HR Process Teams, and the IPO developed the functional, technical and integration requirements for the e-Payroll Project.  The functional requirements include a textual list of the requirements and a business process model view of the e-Payroll requirements.  The Level IV e-Payroll Project Requirements were approved by the e-Payroll Project Steering Committee and are under configuration control in accordance with the IFMP Configuration Management Plan.  The e-Payroll Project Steering Committee serves as the Configuration Control Board (CCB) for these requirements.  A complete set of these requirements can be found in the e-Payroll Scope Project Scope document at web site http://epayroll.nasa.gov.

## Level V – Implementation Requirements

After the Project Formulation Phase, the Migration Team, DOI, and the IPO will work to configure and test the software to insure it is acceptable for implementation.  During the process, it is likely that additional functionality gaps will be discovered and resolved.  As a result, the baseline Level IV requirements will be updated.

In addition, in order to test the software, a more detailed statement of a requirement or process may be required in order to insure the successful completion of a test.  These changes will result in a more refined, testable set of requirements.  These Level V requirements are known as Implementation Requirements, and will serve as the basis for the testing that will occur during the e-Payroll implementation. The e-Payroll Project Manager will approve the Implementation Requirements and any changes to the baseline.

# Technical Summary

## e-Payroll Functional Overview

The e-Payroll functional architecture consists of two main subprocesses that contribute to the ability of FPPS to record, classify, and report all types of employee payroll/personnel actions.

These subprocesses are:

- Payroll:  Entity that records employee gross to net pay including benefits, deductions, and leave.

- HR/Personnel:  Captures transactions required by payroll for processing employee benefits, deductions, and leave.

## Facilities

The e-Payroll Project will be located in the IFMP Competency Center, an offsite facility.

## Mission Results Analysis and Reporting

As each major Project lifecycle phase is concluded, the e-Payroll Project will reassess its performance against the Project requirements, performance metrics, functional driver, Agency business drivers, and the business case to confirm viability of the Project.  Interim reports and analyses will be provided to the IFMP Director on a monthly basis.

# Logistics

The e-Payroll Project will utilize current logistics processes and systems in place at MSFC to support Project Management activities and requirements.  The e-Payroll Project will receive support from the IFMP IPO for technical environment operations and maintenance during the Project’s implementation activities.  Subsequent to Agencywide deployment, the IPO will continue to provide operations and sustaining support for the e-Payroll solution.

# Schedule

## Project Schedules Overview

The IFMP Schedule Management Framework provides details on the overall schedule management process for the e-Payroll Project.  Target dates for activities and milestones relative to the e-Payroll Project’s critical activities are established, tracked and controlled.  Significant to this process is the establishment of control points (key milestones) at the Program, Project, and Center levels.  Each level will maintain a separate schedule to support the control points that enable measurement of DOI and NASA e-Payroll Project accomplishment.  The schedule management process includes the following elements:

- Development

- Base lining

- Analysis and Maintenance

- Reporting

- Management Commitment and Effectiveness Measures

The amount of detail in the e-Payroll Project schedule management is a function of the phases of the Project’s lifecycle.  The e-Payroll Project will be managed through four distinct phases after Project Management/Project Set Up; Formulation Phase, Design Phase, Implementation Phase, and Go Live/Support Phase.  The phases are defined in the e-Payroll schedule, which is maintained in Microsoft Project, and follows the clearly defined WBS provided by IFMP.

As each major lifecycle phase is nearing completion, the schedules and baselines for the subsequent phases will be definitive and/or reassessed using the information and knowledge gained during the previous phase.  The schedule below provides a high level look of the e-Payroll Project.  This schedule will be updated at the conclusion of the Formulation Phase.

Figure 11.1 - High Level e-Payroll Implementation

Figure 11.2 - Key e-Payroll Project Dates

| Milestone | Date |
| --- | --- |
| Steering Committee Established | December 20, 2002 |
| Signed DOI/NASA Letter of Intent | March 7, 2003 |
| Payroll and HR “As Is” Processes Defined | May 13 – 16, 2003 |
| Interface and Report Discovery | May 30 – September 12, 2003 |
| Payroll and HR “To Be” Processes Defined | June 30, 2003 |
| Payroll and HR Preliminary Gap Assessment | August 14, 2003 |
| Technical Requirements Established | September 12, 2003 |
| Core FPPS Data Crosswalk Completed | September 18, 2003 |
| Payroll and HR Final Gap Analysis | September 25, 2003 |
| Payroll and HR Gaps Identified | October 9, 2003 |
| DOI Provides CR Impact Assessment | November 30, 2003 |
| NASA/DOI Web FPPS SSL Load Testing | December 15, 2003 – January 31, 2004 |
| Project Formulation Phase Ends | February 2004 |
| Implementation Begins | March 2004 |
| Tester Training | January 2004 – March 2004 |
| DOI Test Environment Available for Preliminary End-to-End Testing | March 19, 2004 |
| Center Training | March 2004 – May 2004 |
| NASA Client Orientation Database Available With NASA Data and CRs | May 28, 2004 |
| Parallel Testing | May 30, 2004 – July 11, 2004 |
| Go Live | August 8, 2004 |

# Resources

## Funding and Institutional Requirements

MSFC provides travel funds, facilities, and personnel for ongoing operations of the e-Payroll Project.  An overview of the e-Payroll Project activity costs and resource estimates are provided below.

The costs in Table 12.1 show the implementation as well as the Operation and Sustaining Support (O &SS) costs for e-Payroll.  In FY03, the project costs include project formulation (includes activities of Process Review teams) and the initial implementation design (primary activities include Requirements Analysis and Gap Analysis).  In FY04, the project costs include various implementation activities, including:  interface development, data mart planning and setup, data conversion, training, and cutover planning.  FY05 and beyond are for Operations and Sustaining Support.

Table 12.1—Budget Summary (in thousands)

|  | FY03 | FY04 | FY05 | FY06 | FY07 |
| --- | --- | --- | --- | --- | --- |
| Program | $802,707 | $7,872K |  |  |  |
| Enterprise | $735,471 | $15,778K |  |  |  |
| O&SS |  | $569K | $4,269K | $4,452K | $4,377K |
| Total | $1,538,178 | $24,219K | $4,269K | $4,452K | $4,377K |

Table 12.1a: Migration Team - Civil Servant Resource Commitments

| Migration Team Civil Servant Skill Mix | # of Team Members | Commitment | Duration | Hours per Team Member | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | 100% | LoP | 2080 | 2080 |
| PR Process Team Lead | 1 | 50% | LoP | 1040 | 1040 |
| HR Process Team Lead | 1 | 50% | LoP | 1040 | 1040 |
| PR Specialists | 1 | 50% | LoP | 1040 | 1040 |
| PR Specialists | 2 | 100% | 9 Months | 1560 | 3120 |
| HR Specialists | 1 | 50% | LoP | 1040 | 1040 |
| HR Specialists | 2 | 100% | 9 Months | 1560 | 3120 |
| Accountant/Finance Specialist | 1 | 100% | 4 Months | 693 | 693 |
| Applications and Data Expert | 1 | 100% | 6 Months | 1040 | 1040 |
| Business Process Specialists | 2 | 50% | 6 Months | 520 | 1040 |
| IT/Telecommunications | 1 | 50% | 6 Months | 520 | 520 |
| Test Team Lead | 1 | 50% | 6 Months | 1040 | 1040 |
| Change Management/Training Lead | 1 | 50% | LoP | 1040 | 1040 |
| Center Transition Lead | 1 | 50% | LoP | 1040 | 1040 |

The Life of Project (LoP) is March 2003 – August 2004.

Table 12.1b: Migration Team Contractor Resource Commitments

| Migration Team Contractor Skill Mix | # of Team Members | Commitment | Duration | Hours per Team Member | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Training Coordinator | 1 | 100% | 4 Months | 693 | 693 |
| Change Management Support | 1 | 100% | 6 Months | 1040 | 1040 |
| Process Review Support | 2 | 50% | 6 Months | 520 | 1040 |
| Applications and Data Expert | 1 | 100% | 6 Months | 1040 | 1040 |
| Administrative Support | 1 | 100% | LoP | 1040 | 1040 |
| IPO Technical Support | 2 | 100% | LoP | 2080 | 4160 |
| IPO Technical Support | 1 | 50% | Lop | 1040 | 1040 |

The Life of Project (LoP) is March2003 – August 2004.

Table 12.1c: Payroll Process Team Resource Commitment

| Payroll Process Team | # Per Center | Commitment | Duration | Hours Per Team Member | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Functional | 2 | 25% | LoP | 1040 | 1040 |
| Technical | 2 | 25% | LoP | 1040 | 1040 |

The Life of Project (LoP) is March2003 – August 2004

Table 12.1d: HR Process Team Commitment

| HR Process Team | # Per Center | Commitment | Duration | Hours Per Team Member | Total Hours |
| --- | --- | --- | --- | --- | --- |
| Functional | 2 | 25% | Lop | 1040 | 1040 |
| Technical | 2 | 25% | Lop | 1040 | 1040 |

The Life of Project (LoP) is March2003 – August 2004

# Controls

IFMP has established multiple levels of Program control over schedule, project deliverables, and budget.  Prior to approval by the IFMP Director and e-Payroll Steering Committee, the e-Payroll Project commits to a Project schedule containing milestones and control points.  The e-Payroll Project status is reported to the IFMP Director monthly.  The e-Payroll Steering Committee must approve any reported changes to the base lined schedule or e-Payroll Project Scope.  The e-Payroll Project will also have a project-planning schedule for implementation management addressing those activities leading up to the milestones and control points, agreed to by the IFMP Director.  This schedule is not controlled at the Program level and may change at the discretion of the

e-Payroll Project Manager and the IFMP Administrative Systems Implementation Manager as long as the agreed to milestones and control points remain unaffected.

The e-Payroll Project budget reserves are managed by the e-Payroll Project Manager with review, but not approval, by the IFMP Administrative Systems Implementation Manager.  The

e-Payroll Project Manager will establish and allocate reserves consistent with risk and schedule requirements.

IFMP has developed a complete set of management frameworks that establish standard policy, guidance, and processes for managing IFMP consistent with the principles of NPG 7120.5B.  These frameworks assure sufficient and comprehensive communication, coordination, oversight and control of all Project phases, as well as multiple phased initiatives.  Roles and responsibilities for each level of Project management, as well as standard processes and techniques, are identified.  These frameworks will serve as the basis for developing detailed management plans in support of the e-Payroll Project.

# Implementation Approach

## Implementation Overview

The implementation approach for the e-Payroll Project is defined by four major lifecycle phases, which include the Project Management/Project Setup Phase, Formulation Phase, Realization Phase, and Final Preparation /Go Live Phase.  Each of these phases is detailed below.

### Project Management/Project Set Up Phase

During the Project Management/Project Setup Phase of the e-Payroll Project, an e-Payroll Steering Committee and the Migration Team were established.  The Migration Team, with support from the IPO, established functional and technical requirements for the e-Payroll Project that were approved by the e-Payroll Project Steering Committee.  Functional drivers and associated performance measures were also defined, which contribute to the achievement of the Agency business drivers.  A Business Case Analysis (BCA) was also developed for the e-Payroll Project.

The major deliverables during this phase are performance commitments, cost, scope, and schedule baselines.

### Formulation Phase

The goal of this phase is to develop a standard, Agencywide integrated solution based on re-engineered business processes that operate within the capabilities of the provider’s software.

The key tasks in this phase include:

- Define “As Is” payroll and HR process

- Define “To Be” payroll and HR processes

- Conduct gap analysis

- Identify interfaces and reporting capabilities

- Develop change management, training, and migration strategy

- Role definitions and implementation plan

- Prepare to transition to the Realization Phase

The output of the Formulation Phase will be a gap definition between the FPPS and NPPS software. Gap definition will also include interfaces to Agency legacy systems, standard Agency reporting solutions, Agency training and change management strategy, Agency high-level data conversion strategy, and technical architecture.  The results of the Formulation Phase will then be used to revalidate the project scope and to initiate the Realization Phase.

### Realization Phase

The Realization Phase activity serves as the arena for all implementation efforts including data conversion plan, integration testing, and training.  The Agency-configured solution and re-engineered processes developed by the Migration Team during the Formulation Phase are the foundation for the activities performed during this phase.  It will include development of interfaces with supporting Agency/Center-level legacy systems, data conversion plans, and training development and implementation.  This phase will include integration and verification of all elements necessary to make the software work in a real world environment.  During this phase, all elements of Change Management will be developed and implemented in order to provide a baseline.

### Final Preparation/Go Live Phase

The Final Preparation/Go Live Phase will include the conversion of legacy data to the provider system, parallel testing, user training, and final cutover procedures.  During this phase, the Operation Readiness Review (ORR) will be conducted introducing the final clearance to migrate to the DOI FPPS for all Centers.

## e-Payroll Project WBS

The e-Payroll Project developed a WBS consistent with the IFMP Schedule Management Framework document.  This WBS depicts the e-Payroll Project specific activities associated with the formulation, planning, management, design, and implementation of the e-Payroll solution across NASA.  A breakdown of the e-Payroll Project WBS is provided below:

Figure 14.2 – Project WBS Breakdown

## Contractor Support

### e-Payroll Implementer

The DOI/NBC will support the broad range of activities required to successfully implement the FPPS at NASA.  These activities will include solution analysis, design and development (including configuration), interface design and development, report design and development, data conversion, testing support, training, and production cutover support.  Each of these activities will be completed at the 10 NASA Centers simultaneously in order to accommodate a “big bang” implementation strategy.  DOI/NBC will work closely with the Project Manager and  Change Management Lead as they execute change management tasks for the e-Payroll Project.

### Sustaining Engineering Support for Agencywide Administrative Systems (SESAAS)

Applications sustaining engineering is provided in support of the following NASA GOTS Agencywide Human Resources, Property, and Procurement Administrative Systems:

- NASA Personnel/Payroll System

- Acquisition Management System

- NASA Equipment Management System

- NEMS Central Database

- NASA Property Disposal Management System

- NASA Supply Management System

DOI/NBC will work with the SESAAS group to understand e-Payroll requirements with the appropriate set of applications listed above.

### Administrative Business Systems Support

Sustaining engineering support for MSFC-specific legacy administrative business systems is also provided via the MSFC Unified NASA Information Technology Services (UNITES) contract, for which SAIC is the prime contractor.  These applications support the business operations of three primary organizations at MSFC:  Customer and Employee Relations Directorate, Office of the Chief Financial Officer (CFO), and the Procurement Office.  The UNITES project organization will play a key support role for transitioning from NASA Payroll/Personnel System to the DOI Federal Personnel /Payroll System GOTS software.  Specific support to be provided to the Project will include mapping and extraction of data to be converted to the new system, development of interfaces to remaining legacy systems as required, support during acceptance testing, and development of report requirements.

### e-Payroll Project Management Support (Booz-Allen & Hamilton)

In support of the e-Payroll Project, this contract supplies project management assistance in the following areas:

- Planning

- Administrative

- Project Schedule

- Risk Management

- Special Studies and Analyses

- Quality Assurance

- Budget

### IFM Independent Validation and Verification (IV&V) Support (NASA)

The purpose of this effort is to provide the IFMP with an independent assessment of the module projects (in this case e-Payroll) requirements.  These tasks will be performed by the NASA IV&V in conjunction with its contractor, currently, Averstar, Inc.  The IFM Program will manage this activity on behalf of the IFMP.  The IV&V will analyze software requirements for accuracy, clarity, completeness, consistency, flexibility, and testability.  They will review requirements for completeness and applicability and will produce a Requirements Traceability Report.

### IFM Program-level Change Management Support (IBM)

The IFMP-level Change Management effort exists to:

- Ensure successful implementation of IFMP modules by providing common change tools, techniques, and corporate consulting to all IFMP projects, including the e-Payroll Project and the Centers.

- Build understanding of and commitment to changes associated with the implementations through continuous communication.

- Coordinate with and monitor progress of Centers, and analyze effectiveness of change management concepts and tools.

## Descope Approach

An initial baseline for requirements and gaps is established as the result of the software during the Project Setup and Formulation phases.  During the Formulation Phase, DOI/NBC works under the management of the e-Payroll Project Manager and the direction of the Migration Team to establish the application functionality and configure the system to best meet the Project’s requirements.

DOI/NBC, the e-Payroll Migration Team, and the IPO work together to address and eliminate system gaps through agreed upon configuration decisions, i.e., alternative configuration approaches, process redesigns, reengineering of business rules and processes, and/or software modifications.  Changes to the requirement baseline documentation are managed through the Project’s defined configuration management process.  The e-Payroll Project Steering Committee approves all configuration outcomes that impact the requirements baseline.  The e-Payroll Project Steering Committee will approve changes to the e-Payroll Project Scope.  Proposed changes to the e-Payroll Project Scope will be assessed in terms of impact to satisfaction of the e-Payroll functional drivers and performance measures, as well as in terms of impact to cost and schedule.

Any decisions to modify the FPPS software must be accompanied by a strong business case and approved by the e-Payroll Steering Committee.  The business case presents the business justification for the change, the cost to implement, the cost not to implement, an FPPS modification maintenance strategy, and the overall impact to the e-Payroll Project schedule.

In the event, the e-Payroll Project should require descoping, the strategy to be employed would vary depending upon which phase of the e-Payroll Project lifecycle was in process at the time.    Requirements would be assessed based upon their relative degree of contribution to the achievement of the e-Payroll functional drivers or to the fulfillment of regulatory or legal requirements.  During the Realization Phase and the Final Preparation Phase, priorities for interface development and data conversion volumes would be assessed for descope opportunities.

# Program/Project Dependencies

The IFMP and the e-Payroll Project are dependent upon a number of Agency-level organizations for the provision of Agencywide services and standards.  The IPO will establish Memorandums of Understanding (MOU’s) with these organizations as appropriate.

Following is a list of the organizations and a brief description of the relation between them and IFMP/e-Payroll Project:

    - NACC.  The NACC provides consolidation services and operations for various NASA Centers’ ADP workloads.  The NACC will provide data center operations services for the e-Payroll Project.  These operation services will be consistent with the overall set of operation services defined within the IFMP Operations Framework.

    - NASA Integrated Services Network (NISN).  NISN will provide the internal Centerwide area network systems support and services for the e-Payroll Project.

    - SESAAS.  SESAAS is responsible for the sustaining engineering support of the legacy Agencywide business applications.  The e-Payroll Project will require integration with the SESAAS maintained applications.

    - Outsourcing Desktop Initiative for NASA (ODIN).  ODIN is responsible for desktop services across the Agency.  The ODIN contractor at each Center will be involved in the traditional desktop, local area network, and user interface operational support of the e-Payroll Project.

# Agreements

The IFMP IPO will establish a Program-level MOU for managing program and e-Payroll Project interaction with other NASA entities in accordance with the IFMP Operations Framework.  The MOU will detail the roles and responsibilities of each entity in the IFMP.

The e-Payroll Project is dependent upon the IFMP IPO for coordination of required system interfaces, delivery and operation of the development environments needed, performance testing of the e-Payroll solution, the transition of the e-Payroll application into operation, and providing sustaining engineering support.  A Memorandum of Agreement (MOA) has been established with the IPO, detailing the specific roles and responsibilities to be performed in support of the e-Payroll Project.

Each NASA Center is responsible for supporting the implementation of the e-Payroll solution at their respective Center.  The e-Payroll Project is dependent upon each NASA Center to effectively plan, manage, and execute this implementation.  A critical, high-risk area of the responsibility for the Centers is the successful management of the transition to the new business processes deployed as part of the e-Payroll solution.  Project Plans will be developed by each NASA Center prior to beginning each Center’s deployment activity.

# Safety and Mission Success

Safety for the e-Payroll Project personnel, visitors, and facilities is a primary concern at NASA.  The e-Payroll Project does not precipitate any safety issues or concerns over and above normal facility attributes.  e-Payroll Project personnel are briefed and trained on the regulations and requirements at their respective facilities.  Employees are provided training and drill, and are assigned specific responsibilities in case of fire or for any other disaster that might occur.

# Risk and Issue Management

## Risk

The e-Payroll Project will actively manage technical and programmatic risk to maximize the probability of delivering the planned technology within cost and on schedule.  The project will follow the IFMP Risk Management Framework, which establishes the policy and guidance for controlling risks on the Program.  This framework was developed based on NPG 7120.5A and served as the basis for developing a detailed Risk Management Plan for the e-Payroll Project.

The purpose of the e-Payroll Risk Management Plan is to establish the strategy for managing risk for the Project.  At the core of this approach is the assignment of risk management responsibilities to the appropriate management level, where there is direct professional involvement and concern over the impact of risks and where identification, mitigation, and reporting activities become an integral component of the e-Payroll Project management planning, budgeting, and execution.  The Risk Management Plan includes the roles and responsibilities for each level of Project management as well as standard processes and techniques.

Figure 18.0 – Continuous Risk Management Model*

## Issues

Issues Management is the process of identifying, prioritizing, tracking, and resolving issues in a timely manner to prevent a critical impediment to the effective progress of a Project.  The IFMP ePayroll Project will adhere to the IFM Program Issue Management Framework.  e-Payroll will maintain in a database the issue name, priority, action, issue owner, due date and update status information of the Project’s issues.

An issue is a problem, question, or challenge that arises and needs to be addressed in some manner to avoid negative impact to the Project.  An issue differs from an action in that an issue describes a condition while an action is a directive or statement of intent.  An issue differs from a risk in that an issue describes a condition that exits or unquestionably will exit while a risk is characterized by a level of uncertainty.  Action items are assigned to issues in order to come to a resolution.  Additionally, actions can exist independently from issues.

The Project Manager is responsible for developing and managing an issue resolution process for the Project so any issues can be resolved quickly.  The Project Manager also escalates to the Program Office any issues, which meets the Program Office’s criteria for critical issues as defined in the IFM Program Issue Management Framework.  The Project Manager assigns both issues and actions to a responsible party to ensure they are appropriately addressed and closed.  The Project Manager will facilitate a weekly/biweekly review of currently open issues and issues that were closed since the last review.

# Environmental Impact

The e-Payroll Project utilizes existing NASA facilities and therefore does not require an Environmental Assessment and Environmental Impact Statement.

# Test and Verification

Testing is a particularly critical activity during the implementation of an Agencywide GOTS software solution.  The e-Payroll Project will utilize as a guideline the basic testing methodology defined by the IFMP in the Program Testing Framework document.  The framework will be adapted to the test strategy developed by the e-Payroll Project team in conjunction with the Service provider’s methodology.

## Testing Phases

The primary test components consist of the following testing phases:

    - Solution Testing.  This component of testing, traditionally known as System Test, will validate the configuration of the e-Payroll solution to meet the business processes developed by the Migration Team.  Business scenarios will be developed and used as the basis for conducting Solution Testing.  Results will be documented and adjustments made to the configuration as necessary.

    - Application Component Test.  Traditionally referred to as Unit or Assembly Test, this testing will validate any code that must be developed during the implementation process, including coding developed for interfaces, data conversion, extensions, and reports.

    - Application Product Test.  Traditionally referred to as Integration Test, this test will be conducted against converted data.  The objective of Application Product Testing is to make the system appear as close as possible to day one of production operations and to simulate actual business processing.

    - Business Capability Release/Parallel Test.  This component of testing is traditionally known as User Acceptance Test.  As part of e-Payroll, a series of parallel tests will be conducted, running both NPPS and FPPS simultaneously, through normal pay period processing.  During this testing activity, system users or their designated representatives will confirm that the release components have been build or configured to support business operations.    At the conclusion of this test phase, the system is ready to be released to the production environment.

    - Technical Testing.  The IPO will conduct all technical testing in support of the e-Payroll implementation.  This testing will include system performance and scalability testing as well as architecture component testing.

## Testing Environments

The specific test environments required for e-Payroll will be specified by the service provider.

# Technology Assessment

Over the past several years, information technology for IFMP applications has matured considerably.

- Proven COTS software applications are available for most IFMP requirements

- Client server is now the norm

- E-commerce is the current technology thrust

- Data warehousing and integrating alternatives exist for integration

- Enterprise Application Integration (EAI) tools are the future capabilities enabling integration

- Joint Financial Management Improvement Program (JFMIP) certified software products now include major software vendors such as Oracle and SAP.

The DOI FPPS software package is a proven product in production with over 200,000 employees being processed every pay period.  There will be adaptations required to the Agency-level information technology architecture that will be managed by the IPO.  There are a number of technologies that will be used to improve the user interface with the system or facilitate streamlined electronic processes and integration with legacy and other IFMP systems.  However, in the event that these technologies do not come to perform as required, existing technologies will be used.

During the implementation of e-Payroll, several key technology thrusts will be evaluated for implementation.  These include:

- World Wide Web technology to reduce software distribution costs and simplified user interface

- Latest digital signature technologies

- EAI tools

# Commercialization

As the e-Payroll Project is not producing new science or technology, there are no obvious opportunities for commercialization.  However, any success NASA has in selecting and implementing GOTS Payroll and HR system modules could become benchmark standards for success.  In addition, other Government agencies may capitalize on NASA’s lessons learned.

# Reviews

Various reviews will be conducted over the life of the e-Payroll Project.  The details of these reviews will be addressed in the Independent Assessment Process and Points of Application Framework and the IFMP External Reporting Requirements.

## Management Reviews

Management reviews will be scheduled periodically to assess the adequacy of planning and the effectiveness of implementation.  Progress will be measured against project scope, schedule, resources, risk, and requirement achievement.  The type and frequency of the reviews will be established according to the Program and the Project needs and requirements.  Reviews will be scheduled to keep Agency, Center, Program, and Project Management informed of the current status of existing or potential problem areas and to obtain expert advice before problems are encountered.  Special reviews by any level of management will be scheduled when the need arises.  Management reviews will include:

- Monthly Status Reviews (MSR)

- First Independent Annual Review (IAR) prior to Agency Design

- IARs

- Independent Assessment at major Project milestones

- Internal Controls Review

- Operational Readiness Review

### First Independent Annual Review

The IFMP underwent a successful Non-Advocate Review (NAR) during formulation.  The

e-Payroll Project will undergo a modified IAR during the period of understanding, which marries pertinent parts of the NAR to the IAR to address the e-Payroll Project pending approval.  The first IAR will make a recommendation regarding readiness of the Project to proceed with the Implementation Phase/Formulation Phase.  The First IAR will be conducted under the auspices of the Agency Chief Engineer’s Independent Program Assessment Office (IPAO) or by the Lead Center’s System Management Office (SMO) at the discretion of the IPAO.  IARs will be conducted over the life of the e-Payroll Project.

## Independent Assessments

The IFMP will employ professional independent assessment services at various milestones throughout the life of the e-Payroll Project.  The objectives of this approach include the ability to identify issues early in the process and the ability to reduce risks, costs, and schedule slippage.

Independent Assessment responsibilities are divided between the NASA Fairmont IV&V facility and an independent assessment contractor.  These assessments will be coordinated by the IFMP IPO.

## Technical Reviews

Various technical reviews will be conducted for the e-Payroll Project as required.  The purpose of these reviews is to ensure that the e-Payroll Project is achieving desired technical performance on schedule and within budget.  The timing of these reviews will be based on the e-Payroll Project lifecycle.  In projects of this nature, detailed lifecycle phases are driven based upon the specific implementation methodology defined by the software package(s) and implementation partner(s) being utilized.  As the methodology becomes known, specific technical reviews will be defined and scheduled for the e-Payroll Project.  At a minimum, the following reviews will be conducted:  Requirements Review, Test Readiness Reviews and Operational Readiness Reviews.

# Tailoring

The requirements of the NASA Policy Directive (NPD) 7120.4B and the NPG 7120.5B apply to the IFMP and the e-Payroll Project, as tailored by this document and the IFMP Program Management Plan, February 7, 2002.

Under the IFMP Program Commitment Agreement (PCA), the e-Payroll Project has the authority to initiate major acquisitions during the Formulation Phase/Project Set-Up Phase.  The e-Payroll Project will develop an addendum to attach to the PCA, which outlines its specific technical performance, schedule, and resource commitments.

IFMP is managed under the direction and leadership of the IFMP Director under the governance of the IFM Steering Council.  The e-Payroll Project is managed by the e-Payroll Project Manager under the governance of the IFMP Director, the IFMP Administrative Systems Implementation Manager, and the e-Payroll Project Steering Committee.

# Change Log

Changes to the e-Payroll Project Plan will be documented in the Document History Log on Page 3 of this document.  A History Log is used to provide an audit trail of all approved changes made to this document after baseline approval.  Changes will be reviewed, approved, and incorporated into the document using established configuration management procedures.

APPENDIX A:  Acronyms

| AA | Assistant Administrators |
| --- | --- |
| ADP | Automated Data Processing |
| ALC | Agency Location Code |
| BCA | Business Case Analysis |
| CCB | Configuration Control Board |
| CFO | Chief Finance Office |
| CIO | Chief Information Officer |
| COTS | Commercial Off-The-Shelf |
| CPO | Consolidated Payroll Office |
| CPDF | Central Personnel Data File |
| CSC | Computer Science Corporation |
| DOI | Department of the Interior |
| EAI | Enterprise Application Integration |
| FPPS | Federal Personnel and Payroll System |
| FTE | Full Time Equivalent |
| GA | Government Agency |
| GOTS | Government Off-The-Shelf |
| GPMC | Governing Program Management Council |
| GPRA | Government Performance and Results Act |
| GSA | General Services Administration |
| HR | Human Resources |
| IAR | Independent Annual Review |
| IFMP | Integrated Financial Management Program |
| IA | Interagency Agreement |
| IG | Inspector General |
| IHCM | Integrated Human Capital Management |
| IPAO | Independent Program Assessment Office |
| IPO | Integration Project Office |
| IPT | Integrated Product Team |
| IT | Information Technology |
| ITPOC | Information Technology Points of Contact |
| IV&V | Independent Verification and Validation |
| JFMIP | Joint Financial Management Improvement Program |
| MOA | Memorandum of Agreement |
| MOU | Memorandum of Understanding |
| MSFC | Marshall Space Flight Center |
| MSR | Monthly Status Report |
| NACC | NASA ADP Consolidation Center |
| NAR | Non-Advocate Review |
| NASA | National Aeronautics & Space Administration |
| NBC | National Business Center |
| NEBA | NASA Employee’s Benefit Administration |
| NISN | NASA Integrated Services Network |
| NPD | NASA Policy Directive |
| NPG | NASA Policy Guidelines |
| NPPS | NASA Personnel and Payroll System |
| ODIN | Outsourcing Desktop Initiative for NASA |
| OMB | Office of Management and Budget |
| OPM | Office of Personnel Management |
| O&SS | Operations and Sustaining Support |
| PCA | Program Commitment Agreement |
| PCS | Permanent Change of Station |
| PEO | Program Executive Officer |
| PEOIFM | Program Executive Officer for Integrated Financial Management |
| PERT | Program Evaluation Review Technique |
| PMA | President’s Management Agenda |
| PMC | Program Management Council |
| SESAAS | Sustaining Engineering Support for Agencywide Administrative Systems |
| SLA | Service Level Agreement |
| SMO | System Management Office |
| SPOC | Security Points of Contact |
| WBS | Work Breakdown Structure |

# APPENDIX B:  DOI Service Level Agreement

Service Level Agreement

BETWEEN

NATIONAL BUSINESS CENTER, PRODUCTS AND SERVICES

DEPARTMENT OF THE INTERIOR

AND

NATIONAL AERONAUTICS AND SPACE ADMINISTRATION

I.	STATEMENT OF LEGAL AUTHORITY

The statement of legal authority describes the existing legal codes and laws that allow agencies to provide the services.

The Department of the Interior’s National Business Center, Products and Services (NBC) agrees to provide service and/or product support as outlined below to the National Aeronautics and Space Administration (NASA), pursuant to the Economy Act as amended (31 U.S.C. 1535) and authority 43 U.S.C. § 1467 and 1468, which established the Department of the Interior Working Capital Fund.

II.	PURPOSE

This section describes reason(s) for executing this Service Level Agreement.

The purpose of this Service Level Agreement (SLA) is to identify the base level and optional services provided by the NBC with regard to the processing of payroll and personnel actions and their companion activities for the NASA.  This SLA establishes mutually agreed upon service levels, monitoring methods, and organizational responsibilities, where appropriate.

III.	PERIOD OF PERFORMANCE

This section outlines the time period and the terms under which this Agreement will be active.

The agreement is effective upon signature.  The agreement will remain in effect until amended, replaced, or terminated by signed, mutual agreement of both organizations.

IV.	LIST OF SERVICES

This section provides a broad outline of the services addressed by this agreement.

The NBC offers an array of reliable, multi-functional payroll and personnel processing applications and services in compliance with the Joint Financial Management Improvement Program (JFMIP) SR-99-5, OPM’s Guide to the Central Personnel Data File (CPDF), and Human Resources & Payroll Systems Requirements for payroll management activities. These include:

- Personnel Processing

- Time and Attendance

- Leave Processing

- Pay Processing

- DataMart

- Labor Cost and Distribution

- Reporting, Reconciliation, and Records Retention

- Customer Support

The services are a mix of standard base level services and optional services.

Base level services are provided to all clients and are priced based upon the number of employees paid.  The optional services have separate costs.  Agency-unique workload volumes or special requirements drive the majority of the separate costs.  This document cites the major examples within the categories of service.  The NBC intends the document to be used in conjunction with the annual Interagency Agreement (IA) to explain services being provided to the NASA.  These specific services include personnel processing; time and attendance editing and processing; pay processing: DataMart; labor cost reporting; reporting, reconciliation and records retention; and customer support.

A.  Base level Services

For the purposes of this document, base level services provided by the NBC will be categorized below as two separate functions.  The functions will identify base level services provided by the Federal Personnel/Payroll System (FPPS) and base level services provided by the Payroll Operations Division.

1.  FPPS system base level services include:

- Supporting the System such that it accommodates regulatory requirements, meets Federal reporting requirements, and provides for payroll and personnel processing in accordance with procedures described in the system documentation.

- Functional and technical support regarding proper use of the System to designated NASA staff and/or contractors.

- Payroll and personnel reports as described in the system documentation.  Reports will generally be provided for on-line viewing and client printing.  NASA can request that data files be made available for their access and subsequent downloading.

- The NASA will provide for the input and/or collection of all input data and will provide for receipt of the data in machine-readable form at the NBC computer facility according to the daily processing schedule, which is separately documented.

- Payroll processing will be on Tuesday evening following the end of the pay period.  In the event that processing is delayed, it will be rescheduled as soon as possible in order to meet NASA’s official payday of the second Tuesday following the end of the pay period.  Electronic fund payments will be scheduled for the first Friday following the end of the pay period, but in the event of contingencies or end-of-year taxable income situations are not required to be deposited until the NASA’s official payday.

2.  Payroll Operations base level services include:

- Assistance in submission of T&A’s

- T&A processing and adjustments

- Pay certification and disbursement

- Payroll reconciliation

- Reissued and supplemental checks

- Maintenance and certification of leave, health, Thrift Savings Plan, and retirement records

- Payment and reconciliation of Federal, state, and local taxes; issuance of W-2's

- Completion of reports for bonds and OWCP

- Unemployment reporting using contract services

- Garnishments processing

- Payroll debt collection

- Pay and leave adjustments and payments

- Separations Processing

- Customer Support

B.  Optional Services

Optional services provided by the NBC in support of personnel and payroll processing and reporting are:

- OPM's Employee Express

- Client specific ad-hoc reporting or other unique requests

- Training, after initial implementation

- Client-specific interface development/implementation

- Client-specific telecommunications

- Client-specific software modifications

- Quicktime employee-based T&A system

- Conversion and maintenance of historical data

- Licensing of DataMart retrieval software

V.   RESPONSIBILITIES:

This section contains detailed responsibilities for the provision of services under this SLA.

NASA Responsibilities:

- Conversion/Implementation:  NASA responsibilities during conversion/implementation are documented in detail in the NASA FPPS Implementation Plan.

- Interface Development:  NASA is responsible for establishing interfaces or data transfer mechanisms necessary to support its business processes.

- Operations:

- Provide remote (peripheral) hardware and communications

- Designate a representative(s) to participate in user groups meetings

- Designate principal contacts in the finance, human resources, and information technology areas.

- Designate a single security coordinator whose roles and responsibilities are documented in NBC Form NBCPS-01.

- Designate application security points of contact (SPOC) whose roles and responsibilities are documented in NBC Form NBCPS-02.

- Provide for the transmission of input data to the NBC computer facility according to the Personnel/Payroll System Biweekly Processing Schedule.  Both parties must agree to any changes to this schedule.

NBC Responsibilities:

- Conversion/Implantation:  NBC responsibilities during conversion/implementation are documented in detail in the NASA FPPS Implementation Plan

- The NBC will protect the NASA’s data in accordance with the NBC’s and the NASA’s security requirements, as well as other laws, regulations and guidelines.  The NBC will only disclose the NASA’s data to authorized personnel.

- Payroll and personnel processing will be accomplished following the end of the pay period in sufficient time to meet the NASA’s established payday.  In the event processing is delayed, it will be rescheduled as soon as possible in order to meet NASA’s official payday and the appropriate NASA personnel will be notified.

- Provide a back-up facility for NBC systems and data for use in the event of a catastrophe rendering NBC’s computers inoperable for an unacceptable period.

- Maintain a Disaster Recovery and Continuity of Operation Plan

- Provide a Letter of Assurance for Disaster Recovery and Continuity of Operation

VI.	PERFORMANCE MEASUREMENT

This section outlines the basic level of performance for which the provider will assume responsibility. It outlines the measures that will be used and describes the metrics that will be used to track performance.

Measurement of the NBC activities is critical to improving services and is the basis for cost recovery for services provided.  The NBC and the NASA have identified activities critical to meeting NASA’s business requirements and have agreed upon how these activities will be measured.

###### A.  MEasures and MEtrics

The NASA and the NBC have agreed to specific measures and metrics for personnel processing, payroll operations and technology management.  These measures and metrics will be applied during the normal course of business.

| Measurement | Metrics |
| --- | --- |
| Disbursements Disbursements are made on or before the scheduled process date | 99.9% timely payroll disbursements 99.9% accuracy based on information provided |
| Reports External reports/interfaces completed by scheduled due dates | 99% timely reports/interfaces 99% accuracy based on information provided |
| Hours of Operation Payroll staff available to NASA Monday through Friday, 6:00am – 4:00pm Mountain Time (MT); excluding Federal holidays. Employee and end-user help desks available to the NASA Monday through Friday, 6:00am – 5:30pm MT; excluding Federal holidays. Interactive Voice Response for common employee issues available 24x7. | 99% available 99% available |
| Help Desks: Employee calls returned within 2 hours. Employee issues resolved within 24 hours End-user calls returned within 4 hours. End-user issues resolved within 48 hours. | 95% returned within 2 hours or less 95% issues resolved within 24 hours or less 90% returned within 4 hours or less 90% issues resolved within 48 hours or less |
| System Availability Production system available to the NASA Monday through Friday, 5:00am – 6:00pm MT, Saturday 5:00am – 4:00pm MT; excluding Federal holidays, and during payroll processing or other regularly scheduled outages. Additional hours available upon request for special circumstances. | 95% available |
| System Performance Internal system response time within established parameters. | 95% available |
| System Operations End-user access granted within 72 hours of request. | 98% access granted within 72 hours or less |

    - SECURITY

This section outlines security responsibilities of the respective organizations.

Security roles, responsibilities, and procedures, and system interconnectivity requirements related to services included within this SLA will be documented in a separate agreement between NASA and NBC.

    - CONVERSION/IMPLEMENTATION

This section outlines the agreement concerning conversion and implementation of customer data.

Conversion and implementation of the NASA to the NBC’s system and transfer of its personnel processing and payroll operations to the NBC will be effective August 8, 2004 unless an alternate date is subsequently mutually agreed upon.  This effort includes the technical and administrative services necessary to support the conversion and implementation effort and incorporation of any mutually agreed upon NASA unique requirements.  It also includes integration of NASA information into the NBC’s personnel processing and payroll operations procedures.  A detailed conversion/implementation plan will be jointly developed indicating the responsibilities of each party.

IX.	STAFFING

This section outlines the staffing considerations between the parties.

No transfer of FTE (full time equivalent) ceiling is required as a result of this SLA.

X.	FUNDING

This section outlines the funding process.

Costs of the above described services are to be recovered by the NBC from all users on an equitable basis. Customer budgets are established by distributing total NBC costs to all clients on the basis of number of W-2s or on the basis of actual cost.  Funding will be approved yearly by both parties on an Interagency Agreement (IA). The NBC will notify the customer of their annual budget within the customer’s budget cycle. Billing will be done quarterly in advance using the client’s Agency Location Code (ALC) via the Department of Treasury’s Inter-Governmental Payment and Collection system (IPAC). Any optional services provided to the customer will be billed on an actual cost basis.

XI.	TERMINATION CLAUSE

This section outlines the circumstances under which this agreement may be terminated.

Both NASA and the NBC reserve the right to terminate this agreement at any time, upon written notice to the other party and OPM, at least twelve (12) months in advance of the termination date.  In the event of termination by either party, the NBC agrees to support and cooperate as necessary to ensure smooth transition to the successor system.

XII.	DISPUTE RESOLUTION

This section outlines the manner in which disputes will be identified and resolved.

Issues unable to be resolved informally between the NBC and NASA will be handled as follows: Either party may submit a formal request to the other party and that party will formally respond.  In both cases the formal request/response will be elevated internally to the appropriate management level.  In the event those officials cannot resolve the dispute, they will designate a mutually acceptable, independent third party to review the facts and recommend a fair resolution.

XIII.	APPROVALS:

This section identifies the individual authorized to enter into this Agreement for their respective organizations.

This SLA accompanies the initial Interagency Agreement and is considered binding for both NBC and NASA upon signing.  Future Interagency Agreements for these services will reference this SLA such that the terms, conditions, and responsibilities remain binding on all parties for the duration of service.

APPENDIX C:  LEVEL III Requirements

This section identifies the preliminary e-Payroll high-level requirements (IFMP Level III requirements), separating the in-scope items from the out-of-scope items.  Requirements are categorized into five areas:  User, Functional, Integration, Technical, and Reporting. The only defined in scope requirements are those currently embedded in the NPPS functionality, integration, and technical and reporting capabilities.  All other potential expansions of capability beyond NPPS are undecided and will be resolved during the formulation phase.

Table 2.—Requirement Line Items

| Category | In Scope | Out of Scope |
| --- | --- | --- |
| User | The system must allow employee access to certain self-service options or interface with OPM's Employee Express System. |  |
| Functional | The system must support paperless transactional processing (i.e., pay and leave changes, retroactive adjustments). |  |
| Functional | The system must perform automated retroactive pay and leave adjustments. |  |
| Functional | The system must perform e-mail messaging for routing functions |  |
| Functional | The system must process and perform final editing of Time & Attendance (T&A) data uploaded from T&A systems |  |
| Functional | The system must derive cost associated with project codes during the payroll calculation process |  |
| Functional | The system must have the capability to process special, supplemental, and emergency payments out side of the normal payroll cycle. |  |
| Functional | The system must perform debt management functions (salary overpayments, collection actions garnishments, and legal actions) |  |
| Functional | The system must have the ability to record cash payments for group health, life insurance, military deposits, or other indebtedness. |  |
| Functional | The system must be able to maintain individual retirement data, including service history for each employee. Maintain separate records for military (post-1956) and civilian (re-employed annuitant) deposits. |  |
| Functional | The system must allow processing, balancing, and reporting of payroll by NASA Center. |  |
| Functional | The system must have the capability to process timeoff awards. |  |
| Functional | The system must be able to calculate deductions for NASA Employee's Benefit Administration (NEBA). |  |
| Functional | The system must support the automation of Unemployment Compensation for Federal Employees processing and responding to ES 931 Requests for Wage and Separation Information – UCFE request. |  |
| Functional | The system must provide the capability to accommodate electronic funds transfer payments, (e.g., TSP, savings bonds, life insurance) as well as other methods of payments, including off-cycle and third party payments. |  |
| Functional | The system must compute various types of awards and incentives allowed by law including cash awards not documented with a personnel action such as military awards for non-NASA personnel. |  |
| Functional | The system must be able to receive, record, and report taxable extended TDY for tax purposes. |  |
| Functional | The system must have the capability to support mass rate changes. |  |
| Functional | The system must have the capability of making child support payments via EFT |  |
| Functional | The system must preclude duplicate data entry by automatically accessing position and employee information already residing within the system. |  |
| Functional | The system must process (with both current and future effective dates) the full range of individual and mass personnel actions such as appointments, reinstatements, transfers, promotions, separations, retirements, terminations, furloughs, change to lower grades, reassignments, pay changes (including locality and national adjustments, allowances, differentials, premium pay, movement between pay plans or schedules, and pay and grade retention), and details. |  |
| Functional | The system must fully document the associated personnel action with all regulatory required information such as legal authority and nature of action citations. |  |
| Functional | Incumbent-related information such as date of hire, service computation date, retirement service date, severance pay date, Civil Service Retirement System, Federal Employees Retirement System, Federal Employees Group Life Insurance and Thrift Savings Plan eligibility dates, Federal Employee Health Benefits enrollment date, step increase and prior military service information must also be recorded. There is also a need for the capability to correct or cancel these actions, and provide the necessary audit trail. |  |
| Functional | The system must provide for the performance of all activities associated with determination of proper leave balances for all types of leave, leave advances, accruals, usages, forfeitures, limitations, and transfers. |  |
| Functional | The system must apply current period leave accruals and leave charges to each employee’s available leave balances, leave transfers, donations to leave banks or individuals, and adjustments to leave balances for restored leave, EEO settlements, and similar after-the-fact situations. |  |
| Functional | The system must process leave forfeitures and carryovers for each employee. |  |
| Functional | The system must accumulate cost information for use in budgeting and controlling costs; performance measurement; determining fees and prices for services; assessing programs; and management decision-making. Labor costs are an integral part of determining the cost of doing business. |  |
| Functional | The system must accumulate work units by cost object (e.g., organization and activity), and responsibility center and be provided to other systems performing cost accounting functions. |  |
| Functional | Information Management Services: The system must provide access to data for reporting, reconciling, and retaining records to accommodate a number of requirements. |  |
| Functional | The report processing aspect accesses and formats data as required to satisfy regulatory, managerial, and accounting information requirements. |  |
| Functional | The system must provide the capability to manually override calculated deductions, employer contributions, and earnings when processing an employee's pay. |  |
| Functional | The system must have the capability to make salary payments, cost of living allowances, and compute deductions for employees who are stationed outside of the continental US, but not in foreign country, e.g., Hawaii. |  |
| Functional | The system must perform automated notification of health insurance enrollment data to carriers. |  |
| Functional | The system must have the ability to make payments and update payroll records (includes taxes) for the Home Marketing Incentive. |  |
| Functional | The system must update leave history each pay period to include current-period and prior-period adjusted leave information for each employee. |  |
| Functional | The system must provide the capability to process and update employee pay records based on permanent change of station (PCS) data. |  |
| Functional | The system must perform Automated workflow (i.e., SF 50/52 processing) |  |
| Functional | The system must process Human Resource transactions needed to calculate employees’ pay, deductions, and employer fringe benefits. |  |
| Functional | The system must provide for the SF50/52 processing including RTD, Retirement, Resignation, Death, Termination Appointment In, Accessions, Replacement in Non-pay Status, Changes in Pay, Term Expiration of Appointment, Promotions Not-to-Exceed, Reassignments, Change to Lower Grade, Change in D, Name Change, Data Elements, Name Change, Tickler Dates, Awards (Performance, SSA, Time Off, FAST), Service Computation Dates (Leave, Reduction In Force (RIF), New Hires, Review of OPFs) |  |
| Functional | The system must provide the capability for modification to data elements for Change in Tenure, Realignment, Reorganizations, Accessions of Non-Paid, Change in FEGLI, NASA Special Program Indicator (data element to be populated upon accession action, or changed upon conversion). |  |
| Functional | The system must provide the capability for processing corrections to Personnel Actions, Inter-Center Transfers, ICB Awards, Auto generated updates FEHB, TSP, Home Marketing Incentive, Performance data, cancellations, Physician Comparability Allowance (PCA), Coop Tracking, Bonuses/Allowances. |  |
| Integration | The system must have the capability to export actual costs of Labor including benefits and earnings at the conclusion of a pay cycle in a format that can be imported into external Labor Distribution systems. |  |
| Integration | The system must track the sources of changes (audit trail of transactions) to employee profiles from either self-service, payroll input, or interfaces. |  |
| Integration | The system must have the capability to export leave balances and employee attributes, periodically during the pay period, in a format that can be imported to external T & A systems. |  |
| Integration | The system must have the capability to export Labor cost by Center at the conclusion of a pay cycle, in a format that can be imported into NASA’s Labor Systems. |  |
| Integration | The system must provide the capability to receive uploads from external systems for processing and Performance Awards and Performance Ratings. |  |
| Technical | The system must provide a Web-based user interface. |  |
| Technical | The system must generate data in required electronic format for transfer to Federal Reserve for issuance of Savings Bonds. |  |
| Technical | The system must generate data in required electronic format supporting the TSP record-keeping system rules and for transmitting Thrift Savings Plan (TSP) contributions, TSP loan repayments, and employee status codes to the Federal Retirement Thrift Investment Boards. |  |
| Technical | The system must generate new hire data in required electronic format for transmitting to Office of Child Support Enforcement (OCSE) via SSA on a pay period basis. |  |
| Technical | The system must generate data in required electronic media format for transfer of dues withheld for life insurance [NASA Employee's Benefits Association (NEBA) payments]. |  |
| Reporting | The system must generate reports needed to monitor leave data. |  |
| Reporting | The system must provide reports for tax reporting and reconciling to federal, state, and local/city taxing authorities on a bi-weekly, monthly, quarterly, and/or yearly basis. The reports should designate what portion of taxes are PCS taxes. |  |
| Reporting | The system must make information available to other functions to generate internal and external payroll reports not created directly in the Pay Processing function. |  |
| Reporting | The system must generate Employees Leave and Earnings (L&E) Statements detailing the composition of gross deductions, net pay and adjustments for the pay period, year-to-date and cumulative amounts (for the purposes of tracking total NASA retirement contributions). The L&E statements must also include a detail of all leave balances used, donated, or forfeited for the pay period and year-to-date. |  |
| Reporting | The system must have ability to produce Individual Pay Record (IPR) with a pay history. Reports for all employees must show gross compensation (including allowances by type and amount), deductions (including allotments) by type and amount, and net pay for each pay period. |  |
| Reporting | The system must have the capability to produce reports documenting rates and units of pay, time in pay status, and entitlements for operational and audit needs. |  |
| Reporting | The system must have the capability to run reports for prior pay periods. |  |
| Reporting | The system must be able to provide a report of employee debt, caused by prior-period adjustments or current-period computation, to be used in administrative collection. |  |
| Reporting | The system must generate SF 2806 and 3100, Individual Retirement Records; SF 2807 and 3103, Register of Separations and Transfers for OPM. |  |
| Reporting | The system must generate SF 1150, Record of Leave Data, to provide to the gaining Agency. |  |
| Reporting | The system must provide the capability to generate reports needed to support human resource transactional processing. |  |
| Reporting | The system must generate current and historical reports on the status and composition of the civil service workforce |  |
| Reporting | The system must provide the capability to do ad hoc reporting on current and historical employee data |  |
| Reporting | The system must provide the capability to report SF-52 status and SPO workload-in-progress distribution. |  |
| Reporting | The system must provide the capability to enable ad hoc extraction of transaction data and status snapshot data |  |

Undecided Requirements

This section lists high-level requirements that are undecided.  For each undecided item, there is a plan for resolving the question of whether or not it belongs within the scope of the project.    This Scope Document represents the initial baseline scope of the project.  This document will be updated throughout the Project Formulation Phase, as issues are resolved.  At the end of Project Formulation, the Project Plan will subsume this document and at that time, it should contain no outstanding or undecided issues or the issues may be transferred to the Project Plan.

Table 3.—Undecided Requirements Line Items

| Category | Undecided | Plan for Resolution | Final Resolution |
| --- | --- | --- | --- |
| Technical | On-line correction of HR historical data | Pursue alternatives with Department of Interior’s National Business Center during e-Payroll Formulation Phase. | A process was established with DOI/NBC for NASA to offer written instructions and/or update scripts to the NBC Datamart group to allow for the modification of records within the Historical datamart area. NASA will be responsible for mapping NPPS to FPPS historical data elements and developing NPPS program routines for data conversion. DOI will be responsible for loading NPPS historical data in FPPS. |
| Technical | Use of DOI Data Mart solution | Evaluate requirements, cost, benefits, and risks of utilizing the DOI data mart solution compared to NASA solutions during the e-Payroll Formulation Phase (e.g., for queries, analyses, charts, existing canned reports, etc.). At the end of formulation, a recommendation will be made concerning use of the DOI data mart. | DOI/NBC Datamart will be used as the primary source of interface data and reporting data. |
| Technical | Use of Interface and Integration Architecture | Evaluate specific requirements, costs, benefits, and risks of alternative interface and integration architectures during the e-Payroll Formulation Phase. Explore and compare existing IFM, DOI recommended, existing NPPS, and other best practices from both a short term and long term perspective as interim solutions. Consider the goals of the eventual IHCM project in this evaluation process. The extent to which the DOI data mart can be used to replace separate NASA HR reporting systems will also impact the integration approach. At the end of formulation, a recommendation will be made on both a short-term and long-term architecture for e-Payroll. | NASA will use the current EAI architecture to support all e-Payroll interfaces. This architecture will interface directly with DOI for both inbound and outbound data then distribute this information to the Agency and Center level recipients. |
| Technical | Labor Distribution | Assessment of the feasibility of leveraging the DOI system capabilities to produce standardized Labor Distribution processing will be accomplished during the formulation phase. Impact to existing processes and interfaces with the IFMP Core Financial system will also be considered. At the end of formulation, a recommendation will be made as to the advisability of incorporating functionality associated with standardized Labor Distribution processing within the e-Payroll implementation effort. | Development of an Agency standardized Labor Distribution System was determined to be out of scope for e-Payroll implementation. The current process for labor cost reconciliation will remain unchanged. NASA Centers will continue to receive a labor cost file for downloading into their unique labor systems for reconciliation purposes and subsequent interfacing to the SAP module. |

# APPENDIX D:  Concept of Operations

See e-Payroll Operations Plan Document

# Footnotes

Office of Management and Budget, Circular No. A-11(1998), §200.2 Definitions

# Text boxes

- Project Manager

- Deputy Project Manager

- Integrated Product Team Leads

- Integrated Product Team Leads

- Integration Product Team Members

- Integration Product Team Members

Weekly Project

Status Meeting

Integrated Product Team Status

Integrated Product Team Member Status

- Update Project Plan

- Cost/Schedule Status

- Identification and Resolution

- Issues

- Risk Assessment and Mitigation

- Consolidated Team Status

- Integrated Product Team Issues and Resolution

- Deliverable Status

- Updated Team Schedule

- Time Reporting

- Estimates to Complete (ETCs)

- Issues and Resolutions

- Proposed Schedule Updates

Involvement

Activity

Outcome