COMPANION USER’S GUIDE:

A Modular Approach to Analyzing Environmental Management System

Projects and Programs

INTRODUCTION

Projects involving Environmental Management Systems (EMSs) may be process or substance-oriented, project or program-based, on a facility or geographic scale, community-based or nation-wide, or produce systemic organizational change.  In all cases, it is important to determine whether the project is achieving its intended outcomes, whether it provides greater process efficiencies or superior environmental performance compared to standard practice, and to identify ways in which to improve the project.  Program managers must be able to measure and describe to others the impacts of their programs.

The process of analyzing EMS projects will help practitioners answer these questions by agreeing on clear goals, developing performance indicators to track progress, establishing baseline data, setting targets for future performance and measuring progress toward such targets.  A well-planned and thoughtfully conducted analysis can help determine if program activities are providing the outcomes needed to achieve the stated goals.  With sound analysis, managers can understand barriers to an EMS project and modify the program as needed to accomplish objectives, or modify program goals to set more appropriate or realistic expectations.  Knowledge and insights obtained from analysis can serve as performance feedback and can play a pivotal role in mainstreaming EMS projects and policies into everyday work.

The National Center for Environmental Innovation (NCEI) has developed a series of analysis “modules” to assist staff and program managers to answer these questions and others throughout the life cycle of an EMS project – from pilot testing to broad-scale application of a successful project.  The purpose of this document is to assist users with the application of the modules.  Each chapter corresponds to the actual module, each of which may be used independently or in combination with other modules, and is intended to serve three purposes:

- To inform the evaluative process.

- To help a manager plan for evaluation at the beginning or intermediate stages of an EMS project.

- To help serve as a project management/development tool.

The modules can be tailored to meet each of the purposes mentioned above and the needs of the user.  Each module presents an assessment framework, which can be answered with varying degrees of rigor in order to answer the questions for his/her purposes.  The main goal of these tools is to allow the user to collect data in an organized manner, conduct an ongoing assessment of the EMS project, and provide the information necessary to conduct a full evaluation.

ENVIRONMENTAL MANAGEMENT SYSTEMS

EMSs are being adopted by a rapidly growing number of organizations in the United States.  An EMS is a practical tool that provides a systematic approach to environmental management, based on a Plan-Do-Check-Act cycle.  An EMS is a set of management processes and procedures that allows an organization to integrate environmental considerations into daily decisions and practices.  EMSs include processes for developing and continuously improving an organization’s environmental policy and goals under all media, and reducing negative regulated and unregulated environmental impacts,.

Many of the module questions are designed to help evaluate the outcomes that result when EMSs are used innovatively in a regulatory program.  In April 2004, the Environmental Protection Agency (EPA) issued a Strategy for Determining the Role of EMSs in Regulatory Programs, which can be found at:  (http://www.epa.gov/ems/policy/EMS_and_the_Reg_Structure_41204F.pdf).  This strategy provides guiding principles and a framework to assess what role, if any, EMSs should play in regulatory programs.  Evaluation of the EMS projects is critical to the strategy and helps EPA weigh future policy decisions on the use of EMSs in regulatory programs.  EPA and states are interested in whether there are potential benefits to be gained from incorporating EMS options into the permitting and regulatory structure.  States are already linking rule development and permitting to EMS.  EPA has been increasingly confronting questions about whether EMSs can be used to improve the efficiency and effectiveness of regulatory tools and what roles, if any, regulatory tools should play in promoting EMSs.  Continuing research and experimentation by EPA and its regulatory partners will assist in determining the effectiveness of EMSs in the regulatory structure and will ensure that EMSs remain a voluntary choice made by organizations that can lead to improved environmental performance.  This companion user’s guide provides additional assistance with evaluating EMS projects.

WHAT ARE THE EMS ANALYSIS MODULES?

The EMS analysis modules are a suite or series of evaluative questions that provide a framework to evaluate, understand, and share information on EMS projects.  The module questions are a compilation of research questions, some of which are presented in the aforementioned EPA strategy and other published work in the field.

Because of the diversity of EMS projects, NCEI designed the evaluation modules to provide guidance, direction, and flexibility.  The questions are designed to encourage critical thinking and assessment of environmental data, successes, obstacles, and lessons learned in order to help the user improve the EMS project.  The user is encouraged to consider the core questions contained in each module, determine their applicability to the project, make appropriate modifications to the questions, and gather the data—quantitative, qualitative, or anecdotal—available to assess progress.  The quantity and quality of data that the user has and the rigor with which the modules are applied will determine the quality of the analysis.  Although all of the modules do not have to be completed, the information collected from all the modules could offer a more complete picture of whether an EMS project is working well and highlight areas that need improvement.  Each module is described briefly below.  Detailed information on each module follows in the subsequent sections.

- Mapping the EMS Project – This module provides a systematic way to map the logic behind the EMS project by asking the user to list the goals, resources, activities, partners/customers, outputs, and intended outcomes of the EMS project.  This module also gathers background information to describe the project, its scope, goals, purpose, regulatory and programmatic issues, participants, and stakeholders.

- Assessing the Environmental Results of the EMS Project – This module is intended to assist the practitioner in measuring the environmental results of the EMS project.  Questions regarding the establishment of baseline data, environmental indicators, and performance measures are included.

- Assessing the Costs and Cost Savings of an EMS Project – Questions regarding the economic impact of the project are asked in this module.  The practitioner begins to gather information necessary to conduct a cost-effectiveness assessment.

- Enforcement and Compliance Assurance – This module is designed to assess the practical enforceability of the project.  This module may require the active participation of federal and state enforcement and compliance staff.

- Public Involvement – The questions contained in this module gather information regarding stakeholder/public participation in the process.

- Assessing the Potential Transferability of the EMS Project – This module sets forth questions that rank the project on a five-part transferability scale, with the objective of determining whether the EMS project is ready for broad-scale application.

WHO SHOULD USE THE ANALYSIS MODULES?

Program managers, designers, and staff participating in the EMS project should use the analysis modules to focus their thinking about the process, assess how well the EMS project is working, and assist in project management and development.  Different members of the project team may be responsible for different modules or different components of the modules.  For example, one member of the team may be in charge of data collection and management, whereas another member may be the coordinator of public participation.  The modules have been designed so that EPA or other federal government agencies, state agencies, local and tribal governments, regulated entities, and the public at large, can use them for evaluation purposes.  The questions in each module may be more or less relevant depending on who the user is and how the modules are applied.  Another example of a potential user may be a project manager who is designing an EMS project and decides to use the modules to help build evaluation into the design of the project.

WHO IS THE AUDIENCE FOR THE RESULTS OF THE ANALYSIS MODULES?

Information gathered by using the analysis modules will be a valuable resource for team members, decision makers within an environmental agency, participants in the project, the public, and others interested in the progress of the project.  The quality and results of the information obtained will likely influence decisions on the need for modifications to the project, or whether the project is ready for broad-scale application.

HOW CAN THE MODULES HELP?

The modules are flexible tools intended to guide and shape decisions and discussions around important EMS analytical questions.  The analysis modules provide a systematic way to conduct a full evaluation of the EMS project, collect and analyze data, make adjustments to improve performance, and organize, track, and monitor the progress of the EMS project.  The analysis modules can help determine whether a project is working as intended and whether it has the potential for broad-scale application.  As a project management tool, they can be used to raise important questions and make methodological decisions explicit.  Finally, they can, and should, be modified to adapt to the project and the needs of the project team.

AT WHAT PHASE OF THE EMS PROJECT SHOULD THE ANALYSIS MODULES BE USED?

The analysis modules are intended for use throughout the project – to help design a project for analysis at the planning phase, during implementation, when the pilot experimentation is complete, and to inform a formal evaluation.  For example, at the planning phase of an EMS project, a team member may describe the monitoring information that will be used to assess performance, the parties responsible for collecting and verifying the data, and the frequency and mode of collection.  At a more advanced phase in the project, there will be monitoring data to analyze and normalize.  Table 1: Uses of the Analyses Modules provides examples of how each of the modules can be used during the three primary phases of a project – design and planning, implementation, and maturity of the project (or completion of a phase of the project).

Designing and Planning an EMS Project – In order to design an EMS project, it is necessary to clearly define the problem that the project is addressing and then outline how the project will address the stated goals.  The modules provide a series of questions that identify the following: 1) project goals and desired environmental and behavioral outcomes; 2) baseline data; 3) performance measures; 4) enforcement and compliance aspects; 5) public involvement requirements; and 6) how to plan for the transferability of the project.  It is often difficult to assess how well the project is working or to conduct an evaluation without planning for data collection early on in the project design.

Implementation of an EMS Project – An EMS project can be assessed at different levels.  At the very basic level, every project should have a tracking and monitoring component during project implementation.  The modules provide questions to obtain this data and to help set up an adequate data collection system.  Project tracking and monitoring does mean that data and information on how the project is working is being collected according to schedule or protocol, and that the project is being tracked for progress.  The goal of using the modules at this phase is to be able to pinpoint and address successful elements of the project and barriers to success.  If the project is not meeting expectations in any one area of importance, the modules can be used to conduct a deeper level of analysis.

Assessing the EMS Project at the Termination Point – If the practitioner is looking back at the project to see how it performed, the modules can be used to conduct a more in-depth analysis.  Robust qualitative and quantitative information gained from each module can provide a complete picture of how well the EMS project performed in meeting its stated goals.  Each module asks the practitioner to assess how well the innovation performed relative to the traditional approach.  Determining the relative advantage of the innovation over the traditional approach is vital to innovation transferability and overall success.

Designing a Formal Evaluation – The modules can be used to help the practitioner design a formal evaluation study of the EMS project.  Evaluation looks at how well an innovation is working to achieve its stated outcomes and why it is working the way it is.  The modules ask the practitioner to construct a logic model (Module 1), which is an integral first step to doing an evaluation and to formulating the right evaluation questions.  In order to construct the rest of the evaluation study, the practitioner uses the completed modules to help address the following questions: 1) to what extent have the stated outcomes been achieved and why; 2) what aspects of the innovation lead to those outcomes; and 3) what is the context in which the outcomes were achieved.

WHAT KIND OF DATA IS NEEDED TO COMPLETE THE ANALYSIS MODULES?

Depending on user needs, the module questions may be answered with anecdotal, qualitative, and/or quantitative data.  Generally, more robust data results in greater certainty in the analysis, or the ability to characterize the uncertainties or successes of an EMS project in greater detail.  For example, in some cases, an anecdotal reporting of the costs required to pursue an EMS project may be sufficient, whereas a financial accounting of capital costs may be necessary for another type of project.  The modules encourage the user to collect anecdotal, qualitative, and/or quantitative data as important sources of analytic information.  Data collection, however, will depend largely on the needs of the project and available resources.  The modules together can be powerful evaluative tools if the user ensures that it is supported by thorough analyses and quality data.

# HOW TO USE THE SIX EVALUATION MODULES

In the sections that follow, each module is described in greater detail, with guidance provided on its application, the organizational structure of the questions, useful sources of information, and a methodology for addressing the content of each module.  Each module is attached in Appendix A.  It is recommended that the user answer the questions in each of the corresponding modules rather than within the companion user’s guide.  In addition, the practitioner should collect information from a variety of sources and in an iterative fashion throughout the life of the EMS project.  By returning to the key questions contained in the modules at different phases of the innovative process to assess progress, the practitioner will be better informed and can make adjustments to the EMS project, if necessary.  Since the modules were designed with a variety of EMS projects in mind, the key to using the modules is to answer the questions that are most relevant to the project.

# HOW TO USE THE SIX EVALUATION MODULES FOR EMSs

Evaluation of EMSs and EMS-type projects do follow the basic fundamentals of evaluation.  It is important to know if the project works, how well it works, what are its shortcomings, and if the EMS project provides lessons for other projects.  This user’s guide and set of modules provides an additional level of questions to factor in the characteristics of EMSs and the types of EMS projects that are being implemented.

The typical characteristics of EMSs provide a basis for identifying potential objectives (desired outcomes) for EMS-based innovative projects and potential indicators to measure and assess performance in those objectives with respect to pre-project baseline conditions.  Each EMS based project reflects one or more of the following areas of inquiry, which are covered by the six evaluation modules:

- Environmental performance: (for regulated entities and/or third parties such as suppliers, customers, and environmental quality trading partners) Assess whether an EMS-based project reduces significant environmental impacts (as identified in EMS aspect and impact analyses) relative to baseline conditions for regulated entities and/or third parties.

- Cross-media environmental performance: Determine whether a project leads to significant improvements in overall environmental quality due to decisions to redirect resources from non- or less-significant impact areas to high impact areas, based on EMS cross-media analysis.

- Regulatory compliance: Evaluate whether an EMS-based project lowers the frequency and/or severity of compliance problems and/or improves the ease of determine compliance, relative to existing regulatory programs.

- Efficiency: (for regulatory agencies and/or regulated entities) Assess whether an EMS-based project decreases the time and costs of permit development and implementation for regulators and regulated entities.

- Effectiveness: (specifically, the ability of regulatory agencies to shift regulatory oversight from lower to higher priority areas) Evaluate whether an EMS-based project allowed a regulatory agency to redirect time and resources for regulatory oversight from lower to higher priority activities.

- Public involvement: Assess whether an EMS-based project improved the quality of information available to the public, the transparency of decision-making, and the leverage stakeholders have over decisions through changes in the type of public involvement mechanism, and the scope, content, timing, and amount of information accessible to the public.

| Table 1: USES OF THE ANALYSIS MODULES |
| --- |
| Phases of the EMS Project | Module 1: Mapping the EMS Project | Module 2: Assessing the Environmental Results of the EMS Project | Module 3: Assessing the Costs and Cost Savings of the EMS Project | Module 4: Enforcement and Compliance Assurance | Module 5: Public Involvement and Stakeholder Feedback | Module 6: Assessing the Potential Transferability of the EMS Project |
| Design and Planning | Identify goals Identify partners and customers Identify tools to assist project Identify preliminary drivers and barriers Create a logic model for the project | Identify environmental goals Identify feasible measurement approach Characterize baseline Identify anticipated medium and long-term behavioral and environmental outcomes Identify data sources and collection/ monitoring protocols to obtain outcome data Set-up schedule to update information | Identify types of savings and costs associated with project Identify who is incurring the savings and costs (i.e., facility, government) Characterize baseline Identify data sources for savings and cost information | Identify the monitoring, reporting, and recordkeeping requirements Identify the method of determining compliance (i.e., record review, inspection) Identify responsible parties for verifying data and information | Identify key participants Identify approach for engaging stakeholders Determine resources available for addressing stakeholder issues Identify potential stakeholder issues (e.g., Environmental Justice) up-front | Identify data necessary to determine relative advantage Identify a path to disseminate information Define and focus targets of diffusion efforts |
| Implementation | Modify to accommodate changes in project conception, tools, etc. Review goals, partners, customers, drivers, barriers etc. identified in the planning stage Review logic model for completeness and accuracy | Review data collection and monitoring results to verify adherence to protocols Normalize and compare mid-course data to baseline to determine need for mid-course corrections Review data collection to ensure data will provide information on environmental and behavioral outcomes Review monitoring and measuring approach, baseline data, and anticipated outcomes identified in the planning stage | Review cost information for completeness and accuracy Normalize and compare mid-course data to baseline to determine need for mid-course corrections Review projections identified in the planning stage for comparison between perceived and actual results | Review and track information to monitor compliance and identify problems or trends that require mid-course corrections Review requirements established during implementation | Check in with stakeholders to assess whether there are stakeholder concerns and the level of participation Assess availability of information to the public Assess stakeholder participation and participation plans | Provide opportunities for potential early adopters of the project to participate in implementation Communicate early results of the project Analyze project for its relative advantage |
| End of the EMS Project | Verify accuracy of original information Adjust for unanticipated outcomes or changes in approach Compare goals and items identified in the planning stage with what happened during implementation Verify accuracy of logic model | Normalize data to account for changes in production Compare pre-project baseline to post-project results to determine net change Identify areas of success and shortcomings Determine if more in-depth evaluation is necessary Assess environmental/public health relative advantage of the project | Normalize cost/savings data to account for changes in production Compare pre-project baseline to post-project costs/savings to determine net change Identify areas of success and shortcomings Is there a cost/cost savings relative advantage? Determine if more in-depth evaluation is necessary | Verify and evaluate final record reviews, inspections, or other means of compliance assurance Determine if project is practically enforceable Identify areas of success and shortcoming Is there a relative advantage to the project? Determine if more in-depth evaluation is necessary | Request that stakeholders provide feedback regarding the quality of their experience in the project Identify areas of success and shortcomings Determine if more in-depth evaluation is necessary | Develop and facilitate workshops and networking opportunities to promote learning Develop users’ guides and Web-based tools to facilitate scale-up Identify areas of success and shortcomings Determine if more in-depth evaluation is necessary |
| Formal Evaluation | Compare goals and items identified in the planning stage with what happened during implementation Verify accuracy of logic model Use logic model to look for gaps and unanswered questions Use logic model to help identify key evaluation questions | Determine why there is a difference between pre-project baseline and post-project results Determine why there is or is not an environmental/ public health relative advantage of the project Describe environmental/ public health results in terms of customer, partner and stakeholder satisfaction and discuss why the results have meaning | Determine why there is a difference between pre-project baseline to post-project costs/savings Why or why not is there a cost/cost savings relative advantage? Determine if more cost-benefit analysis is necessary—why or why not? Describe costs/cost savings in terms of customer, partner and stakeholder satisfaction and discuss why the results have meaning | Determine if project is practicably enforceable and what it means Determine why there is a relative advantage in compliance and enforcement to the project? Describe enforcement and compliance assurance in terms of customer, partner and stakeholder satisfaction and discuss why the results have meaning | Determine why there are areas of success and shortcomings Why is or isn’t there a relative advantage to the project in terms of public involvement—i.e., did the public have greater access to information or greater means to participate—why or why not? Analyze public involvement in terms of satisfaction and ask the question of why are they satisfied or dissatisfied? | Determine how the project would fare if applied more broadly Determine what aspects of the project are working well and those key aspects that need to be modified in order for the project to be more broadly applied |

MODULE 1:  MAPPING THE EMS PROJECT

The following questions are designed to help evaluate the outcomes of projects that integrate EMSs with a regulatory program.  EPA’s Strategy for Determining the Role of EMSs in Regulatory Programs provides guiding principles and a framework to assess what role, if any, EMSs should play in regulatory programs.  Evaluation of the EMS project is critical to the strategy and helps EPA weigh future policy decisions on the use of EMSs in regulatory programs.

I.	Summary and Purpose of the EMS Project

This section provides basic background information on the EMS project, including a brief description of how the EMS project differs from the traditional way of doing business.  The user should also include the impetus for the project and its purpose, so that anyone reading about the project will quickly understand how and why EMSs are being used.  The following questions will help to frame this background information:

- Why was the EMS project developed or proposed?

- What problem or opportunity does the project address?

- To what extent and does the project focus on the following:

  - Individual facilities

  - Economic sectors or groups of sectors

  - Other regulated entities

  - Communities

  - Tribes

  - Other

- To what extent is the project intended to:

  - Improve technology

  - Streamline state/federal regulations

  - Improve organizational management/operations

  - Make more efficient use of state/local/federal resources

  - Improve stakeholder involvement

  - Foster organizational change, especially with respect to organizational culture

  - Improve environmental management practices (e.g., pollution prevention, environmental stewardship, environmental data, etc.)

  - Consider cross-media impacts or multi-media strategies

  - Other

- In what way(s) does the project involve new ideas and approaches when compared to the current/existing approach?

- What programs or policies are impacted by the project, and how?

- What are the key resources that the EMS project uses?

- What are the key activities that you undertake in your EMS project?

- What are the key outputs of your EMS project?

Questions 7 through 9 deal with the key resources, activities and outputs of the EMS project.

###### Key Resources

These are programmatic investments available to support the EMS project.  Examples could include FTE, support staff, extramural funding, grants, outside consultants and equipment.  Typically, you include those resources currently in hand versus projected or anticipated resources.

###### Activities

These are things that are done—activities that you plan—to conduct the EMS project.  Examples include designing marketing tools, holding training sessions, and conducting surveillance audits.

###### Outputs

These are products or service delivery/implementation targets the project aims to produce.  Examples include EMS templates, brochures produced, and audit reports.  There is some gray area between an activity and an output.  The important distinction is that there should be a logical link between the resources, activities and outputs that resembles the diagram below.

II.	Identifying Customers, Partners, Stakeholders of the EMS Project

Answering this set of questions will identify the major participants in the development and implementation of the project, and their respective roles and responsibilities.  Key individuals who are working together on the project should be identified as partners.  Partners will be those individuals who are necessary participants in order for the project to be implemented.  For example, in an EMS type project, the state and the regional EPA office will likely be identified as key partners.  In the case of a community-based project, the community leaders and organizers who are actively participating in the project should be identified and considered partners.  The roles and responsibilities of federal and state regulators should be described, key contact personnel identified, and the process for coordination and collaboration documented.  The user should also identify key customers of the project.  An example of a key customer may be an industrial sector that may benefit from knowing the results of a facility-specific EMS project.  Specificity in identifying customers of the project will allow the user to target resources, collect data and communicate results, and craft public involvement strategies.

The user should also make an attempt to describe the key regulated entities of the project.  For example, if the project is intended to benefit the government and regulated entities, the user should further specify which parties in the government that may benefit (e.g., inspectors, permit writers), the level of government at which the project is aimed (e.g., the project is intended to benefit state permit writers and inspectors), and the types of facilities that may benefit (e.g., is the project intended to help a sector or an individual facility?). Key stakeholders in the project are the individuals who may care about the project and its results, but may not be active in the everyday implementation and activities of the project.  For example, for an EPA project, key stakeholders may be a community, EPA senior managers and Congress.  For a facility project, senior corporate managers and shareholders may be key stakeholders to engage.  These stakeholders are important to keep in mind when communicating the results of the project or in designing the project.  The key message in this section is identifying those you are trying to reach and/or influence and those who you work with to influence your key customers.

  - Who are the key regulated entities in the project?

  - Who are the key partners of the project?

  - Who are the key customers of the project?

  - Who are the key stakeholders in the project?

  - Who has primary responsibility for designing, overseeing, and implementing the EMS project or using the innovative approach or tool?

  - Does the project involve delegation of regulatory responsibilities from EPA to a tribe or state or from the state to local government? (Y/N). If yes, how?

- Identifying Outcomes

Outcomes are the changes or benefits resulting from activities and outputs.  Outcomes should be described using the following structure to help set goals and clarify the scope of the project.

Outcome Structure:

Short-term outcomes—Changes in learning, knowledge, attitude, and skills.  Example:  Facilities learn about the benefits of Environmental Management Systems (EMSs) as a direct result of training (an activity).

Intermediate outcomes—Changes in behavior, practice or decisions.  Example: Facility identifies and implements three process improvements in their EMS.

Long-term outcomes—Changes in condition.  Example: Facility decreases wastewater discharge by 20 percent and increases hazardous waste generation by 10 percent.

This structure is known as the ABCs of outcomes.  You are looking for how your project leads to changes in Attitude or the acquisition of knowledge, which leads to a change in Behavior, which leads to a change in Condition.

- Please list and describe all intended or anticipated short-term outcomes.

- Please list and describe all intended or anticipated intermediate outcomes.

- Please list and describe all intended or anticipated long-term outcomes.

The key to describing the anticipated or actual outcomes of your innovation is to identify those outcomes that are the direct result of your EMS project (outcomes that you directly control) versus those outcomes that are greatly influenced by factors outside of the scope of your EMS project (outcomes that are indirectly controlled).  This is better illustrated in the following example:

Example A:  Your EMS project is designed to substantially reduce NOx emissions from a particular industrial sector that is heavily concentrated in one airshed with a high percentage of smog days.  You invest $100,000 and 2 FTE into the project for activities that include conducting on-site technical visits and consultation and producing helpful materials for the sector.  Your project is able to hold 10 on-site technical visits and produce 2 workbooks, one in English and one in Spanish.  You work with the Trade Association for this sector to disseminate the information.  You want this sector to adopt the changes proposed in the workbooks and through on-site assistance.  The facilities get the workbooks and meet with the technical assistance providers (short-term outcome) and adopt the changes (intermediate outcome).  These changes lead to a 15 percent reduction in NOx from the sector.  This is a long-term outcome that is the DIRECT result of your EMS project.  If you say that your project will reduce smog in the airshed, this is an INDIRECT long-term outcome.  It is true that your proejct did lead to NOx reductions in one particular sector and can reduce smog in a particular airshed if all other factors that control smog did not change.  There are many other factors in the environment that contribute to smog outside of your project.  Therefore, it is more important for your project to be measuring long-term outcomes that are directly related to your innovation rather than measuring all smog in the airshed since you would have little confidence in the way in which your project impacts the airshed when combined with the cumulative environmental impacts.

| Resources $100,000 2 FTE | Activities/ Programs -Develop workbooks -Develop on-site technical assistance materials | Outputs -Produce workbooks in Spanish and English -Conduct on-site visits | Customers -Sector Trade Association -Individual Facilities | Short-term outcomes -Facilities learn about workbooks and meet with technical assistance providers | Inter-mediate outcomes -Facilities adopt changes suggested by workbooks -Facilities adopt technical assistance suggestions | Long-term environmental outcomes - NOx emissions for this sector reduced DIRECT CONTROL | Long-term environmental outcomes -Smog in the airshed reduced INDIRECT CONTROL |
| --- | --- | --- | --- | --- | --- | --- | --- |

Example A:  Logic Model for EMS Project to Reduce Air Emissions

IV.	EMS Project – Tools, Drivers, and Barriers

Tools for the EMS Project

The tools that assist an EMS project may have significant influence on the progress and advancement of the project.  This section identifies and describes tools that have been or will be used during development and implementation of the project.  Tools that may be used to add to the EMS include but are not limited to: economic incentives, regulatory reform, smart permitting, pollution prevention, information management and access, and risk-based standards.  Since this user’s guide and accompanying modules refer specifically to EMSs, the question below asks the user to identify additional tools that are being developed to support the EMS.

- What additional tools are employed to supplement the EMS (e.g., economic incentives, regulatory reform, smart permitting, pollution prevention, information management and access)?  Please describe.

# Drivers for the EMS project

This question asks what the primary motivating factors that drive the project forward are.  Some drivers may include: the need for regulatory flexibility to reduce uncertainty within the permitting process, rapid economic growth, technological/scientific development, increased environmental awareness, population growth, urbanization, and international commerce.  Drivers that promote the EMS should be identified, and if possible, ranked according to their significance.  For example, the potential opportunity costs of project delays from air permitting can be high, creating a demand among companies for permit flexibility to stay competitive within a global market by engaging in an EMS permitting project.  By identifying the primary drivers for the project, the user may be better equipped to identify potential adopters of the project in the event of broad-scale application.

- Describe the motivating factors for undertaking the project and explain how such factors promote the EMS project (e.g., market forces, law or policy that promotes the project).

# Barriers to the EMS Project

Barriers to an EMS project may include the following: technical challenges consisting of inadequate tools or limited economic alternatives; lack of facilities or regulated entities willing to participate; scientific challenges consisting of the absence of key data or inadequate scientific understanding; institutional challenges such as a resistance to change, a jurisdictional challenge, or lack of an authorizing environment; or legal challenges arising from laws, regulations, or policies that impede the project.  Different barriers require different strategies to create a pathway for the project.  Barriers, and the strategies for overcoming these challenges, should be identified within this module.  The user should identify and address barriers, or perceived barriers, early in the project to enhance the chance of success.

- Describe all challenges to the project and explain how such challenges may present barriers.

## V.	Describing the Logic of the EMS Project

Many programs and projects often run into trouble because they lack a well-articulated road map describing the logic of the program or project.  Having gathered information on the purpose of the project, the problem or opportunity the project addresses, as well as the customers, drivers for and barriers to the project, as a next step in the process, the user may want to develop a logic model that synthesizes the key activities intended to achieve the goals of the project into a picture linking inputs to activities and to expected outputs and outcomes.  A logic model is a diagram and text that describes the logical (causal) relationships among program elements and the problem to be solved, thus defining measurements of success.

Using a logic model helps determine the degree to which project’s activities affect the expected outcomes and can help plan appropriate measures to achieve the outcomes.  Logic models can be created in many different ways.  For an ongoing project, the starting point can be the elements of the project, which are then organized into their logical flow.  For a new project that is in the planning phase, the starting point can be the mission and long-term goals of the effort.  The intermediate objectives that lead to those long-term goals are then added to the model, followed by the short-term outcomes that will result from those intermediate objectives.  The key to the logic model is that it tells the story of why the project is important, how it will make a difference, and the expected outcomes as a result of the project.  An example of a logic model is provided in Exhibit 1a on Page 16.

# Contextual Factors

Contextual factors are those program externalities that are outside of your control and are often surprise changes that can greatly impact your innovation.  Contextual factors can both be positive or negative.  For example, your EMS project has caught the eye of a prominent politician who requests more money for your program.  Conversely, your project may have lost political favor the next year.  These are factors outside of your control that can change the day-to-day operation of your program.  Question 22 asks you to hypothesize about these potential changes.  Some changes you may be aware of but have not accounted for as yet in the implementation.  For example, you know in one year that your program manager will be going to school part-time.  How does losing a full FTE impact your program one-year from now?

- Describe all contextual factors that are outside of your control that can effect the implementation of your innovation.

Question 23 asks about underlying assumptions of the program.  Underlying assumptions may include contextual factors, but should discuss aspects of your program that you assume exist and affects the way you implement your program.  Using Example A (on the previous page), you know that regional smog is based on weather patterns, emissions from stationary sources and emissions from mobile sources.  Your EMS project may be based on a sophisticated model that allows you to calculate smog formation based on NOx emissions from a particular sector and accurately predict how much smog was reduced for a given timeframe.  The use of a sophisticated model allows you to assume certain outcomes and helps describe how your program chooses to measure its long-term outcomes.  The underlying assumption in this example is that the model is accurately predicting smog formation.

23.	Describe the underlying assumptions of your program.

# VII.	Benefits of Developing a Logic Model

###### Design and Planning Phase

The logic model can help communicate the performance story of the EMS project and can help build a common understanding of the purpose, goals, and anticipated outcomes among staff and stakeholders.  By answering questions relating to what the project is trying to achieve, with what resources, through what customers, the program niche, and the expected results within a given context, the logic model can help identify potential pitfalls in the design of the project.  The logic model identifies potential outcomes that may be difficult to achieve based on the design of the EMS project.  For example, if the EMS project is supposed to result in a behavior change at the management level of the facility and if there is no built-in measurement system to assess whether or not facility managers have changed their behavior as a result of the project, then it will be difficult to measure the overall success of the project.

###### Implementation Phase

The logic model can be used to further design and develop the project by helping to identify gaps in the suite of activities and prioritize programs and resources towards achieving desired end outcomes and goals.  By being explicit about the program theory and assumptions behind a project, various stakeholders and policy-makers can better understand the project.

Once completed, the logic model can help the practitioner “manage for results”.  By arraying information in a logical sequence the user can identify and choose appropriate performance measures.  Specifically, the identification of anticipated outcomes will be useful in identifying and developing performance measures and indicators that can be used to determine if the project is achieving the stated goals, objectives, and results.  The development of performance measures and the collection of data can facilitate program improvement and allow the user to communicate the value of the project and influence new program development.  As a planning and evaluation tool, the logic model can help identify which areas of a program to focus an evaluation.

###### End of the EMS Project Phase

If a logic model of the program was not completed during the design or implementation phases, producing one at the conclusion of an innovation and at the outset of an evaluation can be an extremely valuable process.  A logic model at this stage will help describe the operation of the program to stakeholders and evaluators, identify potential questions to be asked through an evaluation, and highlight the key areas of program design and theory for further analysis.  If a logic model was created during an earlier phase, returning to it at this point and comparing how the innovation actually functioned to the earlier logic model can provide a starting point for areas to focus on during an evaluation.

Formal Evaluation

If a logic model was not completed during the design or implementation phases, producing one at the conclusion of a project and at the outset of an evaluation can be an extremely valuable process.  A logic model at this stage will help describe the operation of the program to stakeholders and evaluators, identify potential questions to be asked through an evaluation and highlight the key areas of program design and theory for further analysis.  If a logic model was created during an earlier phase, returning to it at this point and comparing how the project actually functioned to the earlier logic model can provide a starting point for areas to focus on during an evaluation.

The logic model can help identify the right evaluation questions to ask based on the major components of the innovation.  The evaluation focuses on the connection points between the elements of the program.  This means that the practitioner should focus on the “how and why” between the phases of the program.  For example, if the project is supposed to change the behavior of a target group of individuals in order to get improved compliance—some evaluation questions to ask are 1) to what extent has compliance improved; 2) what is the innovation doing to change people’s behaviors; and 3) what else could be causing the change in behavior?  The logic model provides a basis for identifying the major facets or components of the project being evaluated.  This is less difficult if the practitioner determines the major functions of the project and then aggregates similar functions into program components.  After each major function area or component is identified, it should be described in terms of the resources (inputs) needed to conduct the activities, (e.g., staff, time, finances, information, equipment, facilities, etc.) and activities (processes) that will be accomplished to achieve the objectives, outputs, and outcomes.  The following five steps can help in the development of a logic model of the project.

#### VIII.	Steps in the Logic Model Process

Please note that not all of the steps mentioned below have to be formalized.  Time and resources may limit extent to which implementation of the logic model process occurs, but at a minimum people involved with the project should work on a logic model.

STEP 1:	Establish a Stakeholder Work Group and Collect Documents

An important first step in developing the logic model is to establish a workgroup comprised of individuals/stakeholders that are knowledgeable about the project.  A stakeholder workgroup can provide a wide breadth of information and different perspectives and knowledge about the project that might otherwise be missed if developed by a single individual.  Once convened, the workgroup should review any available documentation about the project that will provide information on goals and objectives, costs, anticipated outcomes etc.  Sources of program documentation include, strategic and operational plans, budget requests, current metrics, past evaluations, evaluations of similar projects or programs, extant theories (e.g., economic, behavioral sciences), and interviews.  This stage does not have to be overly formal or does not have to be a large workgroup.  The main goal is to make sure that all logical pieces of the project are accounted for and that the logic model will provide a close to accurate road map of the project and its intended outcomes.

STEP 2:	Define the Problem and Context for the Project

Clearly defining the problem the project is designed to address and understanding the context in which the project is designed to operate will help the user understand the conditions that may influence the success or lack of success of the project.  Using the answers to the questions in Module 1, begin to develop a problem or issue statement that describes the problem(s) the project is attempting to solve or the issue(s) the project will address.  As part of this step, specify the needs and/or assets that led to the design of the project which addresses the problem.  In addition, state and/or identify desired results, or vision of the future (including those results out of the control or not in the direct influence of the project), by describing the expected near and long-term outcomes.  Next, list the possible factors that will influence change in the affected community and list general successful strategies or “best practices” that have helped achieve the kinds of results intended by the EMS project.  Last, state the assumptions behind how and why the change strategies will work.

STEP 3:	Define Elements of the Logic in a Table

Using the answers developed to the questions in Module 1, use the blank table included in Module 1 to: 1) describe the resources or influential factors available to support the innovation activities (question 7); 2) describe each of the activities conducted to support the innovation (question 8); 3) identify (for each activity) what outputs (service delivery/implementation targets) aimed to produce/provide (question 9); 4) describe the customer(s) the innovation is intended to reach through the activities and the partner(s) needed to implement the innovation (questions 11 and 12); and 5) identify the short-term, intermediate and long-term outcomes the innovation is expected to achieve for each (questions 16, 17 and 18).  Exhibit 1a below provides an example of a completed logic model table.  Just as a reminder, Remember your ABCs:  Short-term outcomes are described as changes to Attitudes, knowledge and/or skills of the target customers.  Intermediate outcomes are described as changes in Behaviors that result from the acquisition of knowledge or shift in attitude that flows from the short-term outcomes.  Long-term outcomes are outcomes that result in a change in Condition—e.g., the air is cleaner.

| Resources (what you invest) | Activities/ Programs (what you do in the program) | Outputs (what you produce) | Customers (who you reach and who you work with—individuals who use the outputs developed) | Short-term outcomes (what are the short term results you are looking for?—changes in Attitude, knowledge, skills) | Intermediate outcomes (what are the intermediate results you are looking for?—changes in Behavior) | Long-term environmental outcomes (what is the ultimate impact of the innovation on behavior, human health, environment—changes in Condition?) |
| --- | --- | --- | --- | --- | --- | --- |
| Examples: -EPA -State -Local -Private | Examples: -Materials Development -Recruiting -Training -Technical Assistance -Website | Examples: -Training video -Meetings -Brochures | Examples: -Developers -Builders | Example: -Increased awareness of harmful effects -Increased awareness of new technologies and incentives | Example: -Developers and builders acquire new technologies and change practice | Example: *Reduction in non-point source pollutants in waterway *Healthier wetlands *More fish clean beaches *Clean safe/ swimmable/ fishable water |

Table 1a—Logic Model of a Surface Water Program

STEP 4:	Develop a Diagram of Logical Relationships and a Narrative

As a logic model is developed, remember that project components are often related.  The logic model should help graphically depict and explain the logical relationships that exist between inputs, outputs, and outcomes.  It graphically illustrates what must occur in order for the project to accomplish its goals. While the boxes represent an activity, the arrows indicate the connection between the activities.  As the model is developed, limit the words in the diagram, but attach more detail in separate charts or a narrative that describes the research underlying the assumptions.  Keep in mind there are many different forms of logic model diagrams.  The practitioner may want to have more than one model that depicts different levels of detail, different groups of activities, different levels at which performance is measured, different stakeholder views, or different theories.

# Exhibit 1b—Level II Logic Model Surface Water Program

STEP 5:	Verify the Logic with Stakeholders

As a final step, be sure to verify the logic model to ensure that all aspects of the project have been captured and depicted.  The original stakeholder group can review the logic model or an even broader group of stakeholders can be employed for this.  As the model is reviewed, consider asking “How-Why” questions.  For example, start with a specific outcome and ask, “How is the outcome expected to be achieved?” Start at Activities and ask, “Why is this activity important?”  Also consider asking “If-Then” Questions.  For example, start at Activities and move along to Outcomes and ask, “If this activity happens, then what outcome is expected?”

MODULE 2:  ASSESSING THE ENVIRONMENTAL RESULTS

OF THE EMS PROJECT

Module 1: Mapping the EMS Project asks the user to describe the logic of the project, and the logic model process describes the relationship between the goals, activities, outputs, and outcomes of the project.  Module 2 is intended to help the practitioner identify the environmental goals of an EMS project, link environmental outcomes to those goals, identify appropriate performance measures, determine methods for measuring results, and measure the results of the project.  The term environmental results is intended to include output measures (e.g., number of facilities committing to a reduction in greenhouse gases in a voluntary program or number of permits issued), outcome measures (e.g., percent reduction of greenhouse gases over the baseline), and environmental indicator measures (e.g., air monitoring data that indicates improvements in air quality).

Environmental program and project evaluation often falls short on identifying environmental performance measures, tracking environmental indicators, and measuring environmental outcomes.  Performance measures should be designed at the start of the project and track with the goals of the project.  For example, if the project is testing a new environmental technology, an example of a performance measure is 50 percent increase in adoption of the technology within two years when compared to the current level of usage.  Environmental indicators help measure the state of air, water, and land resources, the pressures on them, and the resulting effects on ecological and human health.  An example of an indicator measure is the number of people living in areas with ozone (8-hour) and particulate matter levels above the National Ambient Air Quality Standards.  Outcome measures look at the extent to which the project is achieving its intended results.  There are three levels of outcome measures—short-term outcomes that look for impacts and changes in attitude (i.e., increase in environmental knowledge), intermediate outcomes look at change in behaviors (i.e., skills adopted from knowledge), and long-term outcomes that measure the change in conditions (i.e., the overall impact).  For example, EPA’s programs should have long-term outcomes that should include measures of improvement in public health and the environment to show that EPA is reaching its goals.

Environmental results may also include the benefits of having a cleaner environment – typically classified into four types of benefits: human health, ecological, amenities (i.e., taste, odor, visibility), and reduced environmental damages (e.g., reduced runoff).  Such environmental results should be identified and to the extent feasible, described quantitatively.  In situations where quantification is not possible, the user should qualitatively describe the benefits.  Results also may include or be dependent on behavioral changes that the project may be trying to address.  Behavioral changes can also be described in this section, however they may be described at different qualitative levels (e.g., anecdotal evidence versus a survey) depending on the evaluative rigor necessary for the project.  Table 2 below highlights performance measures across the logic model (discussed in Module 1).  This module will help you identify and define measures for your project; evaluate the measure in terms of data collection, analysis and reporting; and choose the most important measures according to the requirements of the project, importance of the measure and how relevant the measure is to defining how well the EMS project is working.

Table 2:  Types of Performance Measures Across the Spectrum

| Category | Definition | Examples |
| --- | --- | --- |
| Resources/ Inputs | Resources consumed by the organization. | Amount of funds, # of FTE, materials, equipment, supplies (etc.). |
| Activities | The work performed that directly produces the core products and services. | # of training classes offered as designed; Hours of technical assistance training for staff. |
| Outputs | Products and services provided as a direct result of program activities. | #of technical assistance requests responded to; # of compliance workbooks developed/delivered. |
| Customer Reached | Measure of target population receiving outputs. | % of target population trained; # of target population receiving technical assistance. |
| Customer Satisfaction | Measure of satisfaction with outputs. | % of customers dissatisfied with training; % of customers “very satisfied” with assistance received. |
| Outcomes | Accomplishment of program objectives; attributable to program outputs. | Pounds of pollutants reduced; Miles of beaches cleaned; % increase in industry’s understanding of regulatory recycling exclusion; # of sectors that adopt regulatory recycling exclusion. |
| The measures below are derived using the six measures identified above. |
| Efficiency | The ratio of the amount of input to the amount of output. Focus is on operating efficiency. Relating output to some specific resource in terms of cost or time. | Cost per workbook produced; Cost per inspection conducted. |
| Productivity | Measure of the rate of production per some specific unit of resource (e.g. staff or employee). The focus is on labor productivity. | Number of enforcement cases investigated per inspector. |
| Cost-Effectiveness | Measure that relates outcomes to costs. | Cost per pounds of pollutants produced; Cost per mile of beach cleaned. |
| Service Quality | Measure of the quality of products and services produced. | Percent of technical assistance requests responded to within one week. |

Environmental results may also include the benefits of having a cleaner environment, which can be classified into three types of benefits: 1) human health, 2) ecological, amenities (i.e., taste, odor, visibility), and 3) reduced environmental damages (e.g., reduced runoff).  Such environmental results should be identified and, to the extent feasible, described quantitatively.  In situations where quantification is not possible, the innovation practitioner should qualitatively describe the benefits.  Results also may include or be dependent on behavioral changes that the innovation may be trying to address.  Behavioral changes can also be described in this section, however they may be described at different qualitative levels (e.g., anecdotal evidence versus a survey) depending on the analytical rigor necessary for the innovation.

# Design and Planning Phase

For projects in the planning phase, the user should be able to identify goals, develop appropriate measures to assess whether the project is meeting its goals, and anticipate environmental outcomes.  Often, the hardest part of designing a project is in choosing appropriate measures to describe the intended outcomes of the project.  Many projects stop at the measurement of outputs (e.g., number of permits issued or number of inspections completed), especially in the design phase.  The user should have an eye to linking the output measure to the outcome measures for intended or expected outcomes (e.g., 10 percent improvement in compliance rates over the previous year of inspected permitted sources).

# Implementation Phase

For EMS projects in implementation (depending on how long the project has been implemented), the user should be able to measure and report results as to whether environmental outcomes are meeting or exceeding expectations when compared to the baseline measures.  Baseline measures will be discussed in greater detail in this module.  In addition, evaluators should look at collecting and reporting qualitative and quantitative information needed to explain if and how well the project is working.  During implementation, this module may be used to re-check the data measurement and collection approach depending on the results.  A mid-course analysis may reveal a data gap or incomplete data collection.  The user and the project team may have to decide what the impact of a data gap is on the long-term course of the project and whether the data should be collected mid-stream.

End of the EMS Project Phase

For mature projects, the practitioner should demonstrate if and how the project poses a relative advantage over the traditional approach in terms of environmental results.  This module explores possible differences between anticipated results and actual results in order to ascertain if and why, the project may or may not be working as intended.  For a project to succeed and possibly be replicated, qualitative information as well as quantitative data on environmental outcomes is needed.

Formal Evaluation

The practitioner should focus on how the results were achieved and if a causal link can be made between the project and the results.  The evaluation should address how the project caused the intended outcomes to be realized.  If the outcomes were not realized, the evaluation should focus on why they were not realized and how the project should be modified or improved to realize outcomes in the future.

This module concentrates on environmental results in contrast to process efficiencies such as permit streamlining that make more efficient use of federal, state, or local resources.  Such efficiencies could be addressed in Module 3: Assessing the Costs and Cost Savings of the EMS Project.  Process efficiencies may result in greater environmental protection because scarce resources are redirected to other environmental problems, but it may be difficult to track these connections and to determine a cause and effect relationship.

#### I.	Identifying Environmental Goals of the EMS Project

In Module 1, the practitioner identified the problem(s) that the project was designed to target and asks the user to identify outcomes for the EMS project in a logic model.  Module 2 asks the practitioner to identify the environment goal or goals that the project intends to achieve relative to the problem that the project is trying to solve.  The practitioner should ensure that the stated goals appropriately match in size and scope the nature of the environmental problem that the project is trying to solve.  In addition, the practitioner should ensure that the environmental goals listed below track with the expected outcomes identified in Module 1.

1.	What are the specific environmental goals that the EMS project intends to achieve?  Please describe.

- Do the goals of the project include improving the environmental performance of third parties (e.g., customers, suppliers, etc.)?

- Do the goals of the project match the expected/intended outcomes of the project?

- Do the goals of the project include cross-media transfers?  If yes, how many and what types of cross media transfers are being considered?

  - Measuring the Environmental Results

In order to make sound judgments about the potential benefits of the project, the user needs to measure the results of the project when compared to the current practice.  That is, the user needs to compare the current state (or world without the project) to the one in which the project is in effect to determine whether the project is achieving its intended outcomes.  If the user is in the federal government, measurement is also central to reporting obligations under the Government Performance and Results Act (GPRA).  The user can adapt the questions in the module to address the GPRA reporting requirements as well as any other reporting requirements specific to the project.  Below is a set of overview questions, followed by a discussion of the issues to consider in answering each question, how to design performance measures, and examples of how data might be organized to measure environmental impacts.

Measurement Approach.  A measurement approach is the method(s) that will be used to collect data and information on the project.  For example, the user may decide to use focus group interviews to collect qualitative data on the efficiency of the project and can use air-sampling data to collect data on the efficacy of the project.  The user must determine what measurement approaches are feasible based on the available data—anecdotal, quantitative, or qualitative—and the needs and resources of the project team.  The user is more likely to have greater flexibility at the design phase to choose the appropriate measurement approaches than if the project is already being implemented.

The availability of quantifiable environmental results depends on the type of intervention of the project.  For example, where a project results in a change in the level of emissions or discharges that are already being monitored and tracked for regulatory purposes, it will be easier to access data (e.g., permitted source will already be monitoring and tracking emissions through stack tests etc.).  If an EMS project is aimed at an environmental problem for which there exists little or no data (e.g., non-point source pollution for certain pollutants), it will be more difficult to quantify the level of improvement with the project.

Qualitative and anecdotal data can support a project and may be necessary to make the case for transferability of the project.  For example, in the case of a health benefit, it may be possible to qualitatively assert that the project is expected to be a contributing factor to a reduced incidence of asthma in children without establishing a direct correlation between the project and the reduced incidence.  Anecdotal data also provides information on how people perceive the project is working.  An example of anecdotal information might be where a regulatory agency is testing the merits of an Internet-based public participation process and stakeholders are asked informally to provide feedback because it is not feasible to conduct a statistically valid survey.

Baseline Data.  Establishing a credible baseline is critical for measuring the impacts of an EMS project.  Baseline data are usually built into the EMS, and the same baseline information should be used to measure progress in this module.  Developing a baseline involves more than taking stock of current conditions; it lays the foundation against which all future environmental progress will be measured.  Baseline data provide a frame of reference for the change that the project proposes.  Characterizing an appropriate baseline involves describing the conditions that prevail in the absence of the project by looking at measures, normalizing measures, timeframes, assumptions, and comparability.  It is important to collect baseline data before the project is implemented.

Measures:  The project’s goals should be translated into measurable parameters, and appropriate metrics should express both baseline conditions and expectations of future changes.  Appropriate measures to consider are environmental measures (e.g., particulate matter emitted), economic measures (e.g., tons of cement produced), and the inter-relation of environmental and economic measures (e.g., particulate matter emitted per ton of cement produced) when developing a baseline and planning for future reporting.

Baseline assessments are most helpful if project goals are addressed and well defined at the beginning of the project.  For example, if a facility’s goal is to reduce Hazardous Air Pollutants (HAPs), it should clarify whether it is committing to reduce all HAPs, or it is focusing its efforts on reducing a subset of HAPs.  Units of measurement and numeric expressions should be standardized early on.  For example, mass units (tons, pounds) and actual numbers are appropriate measures to use.  Similarly, measures for assessing economic activity should be standardized early on.  The established environmental and economic baseline measures should be transparent and as simple as possible.

Normalizing Measures:  Normalizing environmental and economic data helps to organize the data so that it is still relevant and meaningful in describing the project despite changes to processes or practices associated with the project.  A common way to normalize data is on a per unit basis, or using a normalizing factor to adjust performance to the baseline year.

To normalize data on a per unit basis, simply divide the environmental quantity by the production measure for the same time period, which is typically one year (e.g., tons of emissions per tons of product annually).  For example, if a facility produces 2000 tons of cement a year and 30 tons of air pollution, its per unit pollution is 30/2000 = 0.02 tons of air pollution per ton of cement.

When using a normalizing factor, the factor assigned to the baseline year is always one (e.g., Year 1).  For example, in the first year of reporting and then in subsequent years, a facility divides its current year production by its baseline year production to derive the normalizing factor for that year.  The facility then divides its actual environmental performance by the normalized factor to derive the normalized quantity.  In Year 1, the facility produces 2000 tons of cement and 30 tons of air pollution.  In Year 2, the facility produces 2300 tons of cement and 28 tons of air pollution.  Its normalizing factor for the baseline Year 1 is 1.15 (2300/2000).  To calculate Year 2 tons of air pollution normalized to the baseline Year 1, divide the tons of air pollution produced in Year 2 by the normalizing factor to get 24.35 (28/1.15) normalized tons of air pollution.  The normalized quantity is less than the actual quantity in Year 1, reflecting that the facility performed proportionally better than its actual environmental statement given the increase in production in Year 2.

Timeframes:  Another key decision to make when establishing a baseline is the appropriate period of time that characterized “current” or “normal” environmental and economic conditions.  Using one year of recent data or an average of two years data is appropriate when:

- Economic activity is relatively steady over time.

- Recent and significant environmental technology upgrades mean that older environmental data are no longer applicable to future activity.

- Reporting on past performance related to the same project and is providing applicable economic data, essentially providing a longer time horizon for baselining.

- Other facilities are involved in the project and may have one of the above circumstances.

It is important that environmental and economic data are reporting in the same timeframe when establishing a baseline, as well as throughout the life of the project.  Matching multi-year environmental data with single year economic data has the potential to skew the measurement of project results.

Assumptions:  The user should consider key assumptions behind the data collection.  For example, if the project will be affected by impending regulations, the baseline should account or include the effects of the new requirements in the baseline or explicitly identify the projected impacts of the regulations.  Criteria for making this determination could include the timeframe of the pending regulatory change compared with the timeframe for the project, the level of certainty regarding the change in regulations, and the level of certainty regarding the effect of the change on the threshold for compliance.

Comparability:  If the user is interested in comparing a series of like-projects for transferability potential, then it is important to standardize the baseline as much as possible to allow for comparison of data.  Specifically, individual projects that are part of a larger EMS initiative should ideally use the same measures, timeframes, and regulatory assumptions.  Failing to standardize baseline conventions often sets individual projects down different paths in terms of data reporting and can lead to great difficulty in comparing the results of multiple projects, and in analyzing factors that affect project success or lack of success.  The user should consider the following baseline comparability factors whenever possible:

- Identify a reasonable compromise format that suits all EMS projects within a program.

- Data is provided in multiple formats – to better reflect individual project needs and one that is suitable for comparison and aggregation with other projects.

- Try to identify the components that may not be comparable to others due to existing baseline conditions at the start of the project.

A determination of what entities will be subject to the project or program allows the user to define the extent to which segments of the community will be affected and to identify reliable databases from which to draw information regarding the number and size of such entities.  Alternatively, the user may need to confer with councils, trade associations, or community groups to determine methods for gathering data regarding existing conditions.  Despite efforts to use the best available data sources to establish a baseline analysis, the user should nonetheless identify areas of concern such as the consistency of variables over space and time, adherence to sampling protocols, sensitive populations, whether non-compliant or exempt entities are included, or any other limiting factors.  In addition, there may be cases where the project is providing data in an area where there is little existing data.  In such cases, if appropriate, surrogate data from research or data from similar experiments may be used.  Depending on the project, the baseline may in fact be the absence of information, activities, or data.

EMS Measures and Indicators.  This module should be used to list the significant environmental impacts, as determined through the EMS, provide objectives, indicators, and outcomes data.  An EMS should include regulatory and non-regulatory significant environmental impacts (total or per unit of production).  The EMS should also include baseline measures for the impacts or baseline measurement plans for environmental impacts.  These potential impacts should be described (as applicable) for:

- Products

- Processes

- Facilities

- Supply chain

- Facility support functions

- Customers

Environmental performance for an EMS project may cover regulated entities and third parties.  Possible indicators for EMS identified significant environmental impacts include:

- Releases (wastewater, air pollutants, greenhouse gases, solid waste, hazardous waste):

- Change in total amounts

- Change in facility risk or indexed release

- Resources consumption: non-renewable energy use, water use, raw materials used, reuse and recycling of materials, etc.

- Habitat conditions: Area of land converted/developed, percent of land covered by impervious surfaces, etc.

Environmental Indicators

- For each environmental goal, what qualitative and quantitative environmental indicators (i.e., EMS objectives and targets) are being used by individual facility EMSs to measure progress/impacts? (Examples include releases—wastewater, air, pollutants, greenhouse gases; resource consumption—nonrenewable energy use, water use; habitat conditions—area of land converted/developed; significant impact areas versus disinvested areas.)  Note:  The indicators should cover both compliance measures and those indicators of environmental performance integrated in the EMS.

- What project-wide indicators are being used to measure EMS effectiveness?  (Examples include: increased management review and attention to environmental outcomes, increased P2 as a result of EMS)

- Does the adoption of an EMS change the organization’s use of environmental indicators (e.g., organization pays more attention to additional unregulated indicators)?

- What is the measurement approach that will be used to measure progress for each environmental goal (e.g., modeling data, in-situ experiment, data extrapolation, real-time, one-time observations)?

- For each environmental indicator, what is the pre-project “baseline” against which progress is measured (e.g., baseline is 5 percent loss of product in facility waste streams—the EMS project is to only have 1 percent material loss in three years) in the EMS?

  - Baseline compliance indicators (e.g., frequency of noncompliance)?

  - Baseline process indicators (e.g., adoption of pollution prevention techniques, increase in senior management review of facility environmental footprint, consideration of local environmental issues)?

- For each of the environmental indicators listed above, what is the schedule for data collection (daily, weekly, quarterly, annually, etc.) and how is it reflected in each entity’s EMS or in the EMS project?

- Based on the indicators provided through EMS objectives and targets, what have been the environmental impacts of the project  (e.g., 100 tons of volatile organic compounds emissions have been eliminated to date)?  Note:  Provide both qualitative and quantitative outcomes.  The project may be of too recent origin for environmental impacts to be observable.  Provide qualitative outcomes if possible—e.g., increase in senior management review, etc.

Environmental Results of the EMS Project.  By comparing the pre-project baseline environmental results to the results during implementation or post-implementation, the practitioner can determine the net change.  This will allow for mid-course corrections, if necessary, or a determination as to whether the project had the desired outcomes.

An organizing table is provided in Exhibit 2.  This model table is neither intended to be comprehensive, nor to anticipate every kind of project for which practitioners will want to assess environmental results.  It should be modified to suit the user’s project as the elements provided in Exhibit 2 below are for illustrative purposes only.

Data Sources, Collection, and Verifiability.  It is recommended that the project team identify early in the process the data sources, collection and monitoring protocols, frequency of collection, persons responsible for data collection, and methods for data verification and quality control.  By establishing procedures up front, it will be easier during implementation and at the evaluation phase of a project to assemble the proper data to determine credible environmental results.

Environmental Results

- To what extent are the environmental impacts of the project consistent with what was expected at the time of design and implementation?

- Are sufficient data available to determine if the project has met its environmental goals (e.g., are the data qualitative or quantitative or both)?

- To what extent has the EMS project been an improvement over the prior/traditional approach with regard to:

    - Human health

    - Organizational management

    - Community based protection

    - Quality of life

    - Ecosystem health

    - Tribal management

    - Environmental Justice communities

    - Others

- How are environmental results verified and who is responsible for verifying results?  How is this reflected in the EMS project or in a facility’s EMS?

- How often are environmental results verified?  How is this reflected in the EMS project or in a facility’s EMS?

Cross-Media Performance.  EMS-related projects may determine whether a project leads to significant improvements in overall environmental quality due to decisions to redirect resources from non or less-significant impact areas to address high environmental impact areas, based on an EMS cross-media analysis.  Please answer these questions if applicable.

Cross-Media Analysis

    - What is the analytical basis used for cross-media shifts for facilities with EMSs (e.g. comparative risk based on acute and/or chronic toxicity)?

    - Has a cross-media analysis been performed?  Does the analysis help provide a baseline to measure cross-media performance?

    - What are the anticipated effects of the cross-media transfers?

    - How does the intended goal and indicators compare to the results of the cross-media transfers?

    - Have any new multimedia strategies been identified based on the cross-media analysis?

Exhibit 2 – Environmental Results Table

Project: Pallet Waste-to-Flooring Demonstration Project

Problem the project is trying to solve:  Demonstrate the technical and financial feasibility of recycling waste pallet wood into a value added flooring product

| Project Objectives with Goals | Indicators (EMS objectives and targets) | Pre-project Base Statistics | Output Metrics | Sources of info and Calculations | Impact/ Outcome |
| --- | --- | --- | --- | --- | --- |
| Produce recycle pallet flooring Goals sq. ft | Regulator Indicators—federal/state/Local | Pallet Hardwoods used in U.S: 4.5 billion board feet/yr (1998) | # square feet of flooring produced (from recycled pallets) | Production records | Natural resource conservation - Estimated percentage (increase compared to baseline) of hardwood tree conserve (trees/yr)* |
|  | Non-regulatory indicators |  |  |  |  |
|  |  |  | # trees not cut for flooring* | Calculation based on production records* | Percentage of trees saved from harvesting when compared to baseline |
| Divert Pallet wood waste from landfilling/waste management methods |  | Over 305,000 tons per year of wood pallets are disposed in landfills in NC (1998) | # square feet of pallet boards diverted | Production records | Conservation of landfill/waste management capacity (tons/yr) compared to the baseline |
|  |  |  | Tons of Pallet wood diverted from landfilling | Calculations based on production records |  |
| Reduce greenhouse gases through carbon sequestration and landfill methane reduction. |  | No statistics | MTCE | Model tools** | % GHG methane reduction MTCE |

*100 board ft/ 1 tree – USFS estimates based on trees 12” in diameter (DBH) with 2.5 16 foot long logs.  Conversion factors: 0.625 board ft/ft^2 of finished flooring (for a 3/8” thick flooring product)

**Metric tons of Carbon Equivalent (MTCE).  Emission factors for wood: (Methane generation in landfill: 0.170 MTCE/wet ton) + (Carbon storage of wood: 0.21 MTCE wet ton) = 0.39 MTCE per wet ton. Source: SOLID WASTE MANAGEMENT AND GREENHOUSE GASES, A Life-Cycle Assessment of Emissions and Sinks, 2nd EDITION, EPA530-R-02-006, May 2002

MODULE 3:  Assessing the Costs and Cost Savings of The EMS Project

This module assists users in determining the costs and cost savings associated with an EMS project.  Many projects are aimed at improving resource efficiency for the regulator or regulated community so that scarce resources may be re-allocated to other environmental priorities.  For example, if a permit streamlining project results in less permit review time by personnel within the regulatory agency, these full-time employees (FTEs) may now address other important problems.  In addition to calculating resource efficiencies, it may be possible with some EMS projects to conduct a cost-effectiveness analysis with the goal of minimizing the costs of achieving particular policy goals.  For example, if an EMS project results in reducing the compliance costs per ton of pollutant, the project is more cost effective than the traditional way of doing business.  In most cases, the project team will not have the resources to conduct formal cost-benefit or economic analyses, nor are such analyses appropriate in all cases.  Module 3 helps assess if the project is more cost-effective than standard practice and assists the user in identifying ways in which the project can be more efficient.  This module does not address a costs and benefits assessment of ecological or environmental attributes (e.g., economic value of a wetlands or health benefits).

An EMS project may address a number of objectives that can be examined for costs and cost-effectiveness.  Examples include: 1) Decreasing permit development and implementation times; 2) Decreasing costs (capital, labor) for permit development and implementation; 3) Decreasing permit complexity and permit development process; and 4) Redirecting regulatory oversight from lower to higher priority areas to increase the proportion of time spent addressing “high risk” activities relative to time spent addressing “low risk” activities.  It is important that the appropriate indicators (as discussed in Module 2) are developed and that costs and cost-savings are addressed in the design phase, implementation, and at the end of the project.

Design and Planning Phase

The user should design the project to ensure that information is collected on the expected cost-savings and costs of the project.  It is important at this phase to collect and assess the baseline costs before the project is implemented.  For example, the user should attempt to quantify FTEs, budget, time etc. of the traditional way of doing business of a traditional permitting system.  If the project is a streamlined facility-wide permit, the design of the project should include an estimation of the expected cost-savings (e.g., time, money, FTE etc.) and methods to collect this data so that the cost-savings can be compared to the traditional costs to demonstrate a relative cost advantage of the project.

Implementation Phase

The user should be tracking information on the cost-savings and costs of the project.  Often, higher transaction costs are associated with the initial implementation of project.  The user should anticipate these costs, but also track costs to see if those costs decrease with time over the life of the project, and that expected cost-savings projected in the design phase are being realized.  It is at this phase where the practitioner could be looking for anecdotal data and impressions regarding costs and cost-effectiveness.  Most importantly, cost and cost savings information is needed in order to help determine if there needs to be a mid-course correction of the project and if the project can eventually be transferable.

End of the EMS Project Phase

Consider if a full cost-benefit analysis is needed or warranted.  For more information on economic analyses, please see EPA’s Guidelines for Preparing Economic Analyses at:

(http://yosemite.epa.gov/ee/epa/eed.nsf/Webpages/Guidelines.html).  For the purposes of this module, looking at the transferability and evaluation of the project, the user should focus on whether or not the EMS project poses a relative cost-savings advantage over the traditional way of environmental protection.  Costs and cost savings do not have to be limited to transaction costs and cost savings, but can also include the amount of job creation, cost savings incurred by faster time to market, or property redevelopment benefits, etc.

Formal Evaluation

A cost and cost-savings evaluation addresses how much the EMS project or project components cost, preferably in relation to alternative uses of the same resources and to the benefits being produced by the EMS project.  The cost evaluation will include a description of the costs and savings associated with the project as well as an analysis of the efficiency, productivity and cost-effectiveness of the evaluation.  The evaluation will focus on the “how and why” resources invested achieved the intended outcomes. The practitioner may decide that a formal cost-benefit analysis is needed outside of a cost-evaluation.

I.	Measuring the Costs and Cost Savings of the EMS Project

Quantifying the costs and cost savings associated with the project may require use of data sources from different organizations (i.e., regulated entity, governmental body, or other stakeholder group).  Cost estimates will likely involve assumptions or uncertainties that users will want to identify and acknowledge, particularly if the EMS project is transferable.

Measurement Approach.  In most instances, the user will use a simple direct compliance cost method to analyze costs and cost savings.  This approach involves quantifying the compliance costs and cost savings realized or incurred organization(s) implementing the project.  The costs may include the capital costs associated with new technologies; the costs of operating and maintaining that new equipment; the costs of modifying operations to comply with the project; and the costs of complying with the project’s monitoring, record keeping, and reporting requirements.  In addition, the analysis can quantify the costs that state regulatory authorities and EPA will incur in administering the project.  Analysis of these costs is often likely to provide a reasonable approximation of the total social costs of the project.  A similar analysis can be performed for the cost savings of the project.  For EMS projects, the practitioner can look at the following potential indicators for the cost and cost-effectiveness analysis:

- Permitting cycle time

- FTEs and dollars spent on permit development and implementation

- Amount of permit backlog

- Number of permitting process steps (for the regulated and regulator)

- Number of (low-priority) inspections avoided

- Number of (low-priority) permit modifications avoided

- Rate errors and rework on permits

- Amount of information (pages) required

- FTEs and dollars saved from avoiding inspections, permit modifications, and/or other low-priority activities

Baseline Analysis.  Similar to the analysis undertaken to determine environmental results in Module 2, the user must also characterize baseline cost conditions to determine the net change in costs.  Without a baseline, there is no frame of reference for the change that the project proposes and it is difficult to say if the project poses a relative advantage to the traditional system.

Data Sources.  Sources of cost and cost savings information should be identified if possible at the outset of the project.  By recording the staff time incurred by the organization, governmental entities, and stakeholders during project development and implementation, the user will have a better estimate of the real costs of the project.

Costs or Cost Savings of the EMS Project.  By comparing the pre-project baseline costs to the costs during implementation or post-implementation, the practitioner can determine the net change as a result of the EMS project.  This will allow for mid-course corrections, if necessary, or a determination as to whether the project had the desired outcomes.

- What is the measurement approach that will be used to estimate the costs and cost savings of the project?  What indicators will be used (e.g., compliance measures, materials use, numbers of spills, etc.)?

- Does the adoption of an EMS change the organization’s use of economic performance indicators (e.g., identification of environment-related costs and benefits more explicitly for management attention)?

- What are the pre-project baselines against which costs and cost savings are measured?

  - Costs of compliance

  - Costs of EMS (i.e., design, training, implementation, and certification)

  - Cost savings of streamlined permitting system

  - Cost savings of reallocation of personnel

  - Other (e.g., new investments, time to market, competitiveness)

- What data sources will be used to measure costs and cost savings?

- To what extent has the project resulted in costs or cost savings?

- Cost Savings of the EMS Project

The user will need to estimate cost savings resulting from the project in comparison to the cost-savings that would be incurred or generated in the absence of the project.  For the purposes cost savings analyses, cost savings are represented as savings in time, personnel, capital, operation and maintenance, transactional costs, and economic activity.

6. What significant time savings/savings has the organization derived as a result of the EMS project? (Please describe the key types of time savings incurred including staff time and contractor savings involved in activities including project development, implementation, monitoring, reporting and record keeping, rule revisions, permit administration, and inspections.)

- Savings to the regulator

- Savings to the regulated?

- Local community or other stakeholder group savings?

7.	What significant cost savings in capital, operation, and maintenance of new equipment, operation and maintenance of existing equipment, materials, or energy has the organization derived as a result of the EMS project?

8.	What other savings (e.g., insurance, worker compensation, creation of jobs etc.) has the organization derived as a result of the EMS project?

9.	What economic activity, if any, has been generated by implementation of the EMS project (e.g., jobs may be created if a brownfields site is redeveloped)?

# Costs of the EMS Project

Costs that are frequently feasible to quantify include compliance costs, government regulatory costs, and transaction costs.  The practitioner may want to consider the costs and cost differences associated with implementing an EMS project when compared to the costs of the traditional approach.  The five basic categories of cost include:

- Real-resource compliance costs: the costs associated with changing production processes or with purchasing, installing, operating and maintaining new equipment to comply with the project or traditional regulations.  The costs can be fixed that require an investment over a period of time or they can be variable as a per unit cost.

- Government or stakeholder costs: any public sector administrative, training, permitting, monitoring, reporting, or enforcement costs associated with the EMS project or traditional approach.

- Social costs: costs associated with a rise in price of goods or the decrease in the production of goods and services as a result of the project or traditional approach.

- Transitional cost:  the costs associated with changes in processes or production due to the project or traditional approach—these costs could be a disruption in production or the costs of retiring old equipment and changing to new technology.

- Indirect costs: the unintended costs the project or traditional approach may have on product quality and productivity, or on markets for other goods and services.

The user should consider each of these potential costs, however, it is not always necessary or feasible to quantify costs in each category.  For example, if real-resource compliance costs are likely to be small, social costs and transitional costs may be insignificant.  Similarly, if the resources available for an analysis are limited, it may not be feasible to model indirect costs.  The user will want to indicate which costs can be quantified, and which will be addressed qualitatively.  An example of a qualitative cost may be changes in organizational management to account for an EMS.

Please describe the costs in terms of the real-resource compliance costs, social welfare costs, transitional costs, and/or indirect costs.

10. What significant time costs/investments has the organization incurred as a result of the EMS project? (Please describe the key types of costs incurred including staff time and contractor costs involved in activities including project development, implementation, monitoring, reporting and record keeping, rule revisions, permit administration, and inspections.)

- Costs to the regulator

- Costs to the regulated

- Costs to the local community or other stakeholders

- What significant costs/investments in capital, operation, and maintenance of new equipment, operation and maintenance of existing equipment, materials, or energy has the organization incurred as a result of the EMS project?

- What other significant costs (e.g., insurance, worker compensation, creation of jobs etc.) has the organization incurred as a result of the EMS project?

IV. 	Relative Cost Advantage

The user should look at costs and cost savings of the project relative to the system prior to implementing the project.

13. If the EMS project were used more widely in the future, how would the marginal (i.e., per EMS project) savings and costs of the project change for the organization?

  - For the regulator

  - For the regulated

  - For the local community and other stakeholders

14. What is the difference between the actual project costs and baseline costs (i.e., costs associated with current regulatory framework)?

Exhibit 3 below is an organizing table that is intended as a model only.  It is neither intended to be comprehensive, nor to anticipate every kind of cost associated with a project.

Exhibit 3

| Costs/Cost Savings Model Table |
| --- |
| Category of Costs | Baseline Costs | Costs of the Project | Net Change: Costs or Cost Savings |
| Real-Resource Compliance Costs |
| Project Development Costs |  |  |  |
| Capital Costs |  |  |  |
| Operation and Maintenance Costs |  |  |  |
| Government Regulatory Costs |
| Permit Review Costs |  |  |  |
| Inspection Costs |  |  |  |
| Social Costs |
| Cost of goods with recycled materials |  |  |  |
| Transitional Costs |
| Indirect Costs |

MODULE 4:  Enforcement and Compliance Assurance

This module evaluates the project’s reporting requirements, accountability, enforceability and effectiveness compared to the traditional reporting requirements.  Completion of this module may require input from EPA, state, and local enforcement and compliance assurance personnel at the design, implementation, and evaluation phases of the project.

EMS projects can be fairly complex for enforcement and compliance, especially if the project involves developing permits based on the EMS.  This module asks the user to look at requirements for monitoring, reporting, and record-keeping to demonstrate compliance and how these requirements would relate to an EMS project.  Potential objectives of an EMS project include: 1) Redirecting regulatory oversight from lower to higher priority areas; and 2) Increasing the proportion of time spent addressing “high risk” activities relative to time spent addressing “low risk” activities.  These objectives are addressed with targeted questions found at the end of this module.

Design and Planning Phase

To ensure that all substantive and procedural requirements of the project are met, the appropriate scope, timing, and availability of all monitoring, reporting, and record-keeping (MRR) requirements should be included in the EMS project at the design phase.  For an EMS-based project, the user should attempt to clearly delineate responsibilities for the facility, regulator, and expectations for third-party verification, if any.  For example, what will inspectors look for in an EMS based permit?  What compliance information would be covered in the EMS and what compliance information would belong in the permit?

Implementation Phase

During the implementation phase, regulatory authorities should review and track information submitted by the facility to monitor compliance and identify problems or trends that may require mid-course adjustments.

End of the EMS Project Phase

To verify and evaluate the results of the project, compliance assurance and enforcement staff may need to complete final record reviews and conduct a facility inspection or use alternative methods to verify results.  Federal, state, and local regulatory authorities should decide in advance how to allocate these responsibilities to conserve scarce resources.

Formal Evaluation

To evaluate the enforcement and compliance assurance, it is essential that the practitioner keep contextual factors in mind when asking how and why certain results were achieved.  For example, the EMS project’s results clearly show a rapid rise in the rate of compliance from a target sector.  The evaluation needs to ask why compliance changed—was it a direct result of new compliance assistance, was it the result of the EMS, or was it the result of economic factors or forces outside of the scope of the EMS project?  Enforcement and compliance can have important short-term outcomes that should be captured and fully explained in order to make the causal link between the EMS project and the outcome.

Monitoring, Record-Keeping, and Reporting (MRR) to State Agencies, EPA, and Stakeholders

The user may choose to standardize the collection and tracking of monitoring, record-keeping, and reporting information at the outset of an EMS project to assess compliance with MRR requirements at the design of the project, throughout implementation, and during evaluation of the project.  Exhibit 4 below is intended to assist EPA, state, and local regulatory authorities to develop a conceptual framework for verifying compliance with MRR requirements and to note any deviations.  The table can be modified to meet the needs of the project.  For each applicable requirement, team members will want to identify the monitoring approach and/or materials use and operating parameter requirements for the environmental media, specify the frequency of data collection, and identify the reporting and record-keeping requirements.  Depending on the method of determining compliance (i.e., record review, facility inspection, etc.), enforcement personnel will determine whether the project is in compliance with applicable requirements.  The user will want to tailor the table to meet the specific needs of each project, and may choose to create separate tables for monitoring, reporting, and record-keeping purposes.

I.	Reporting to State Agencies, EPA, or Stakeholders

###### Design Questions

- What is the legal implementing mechanism for the project?

- What standard permit conditions or regulatory requirements, if any, will require/have been modified?

- What are the specific requirements for environmental monitoring of this EMS project?  Clarify those requirements by law and regulation between requirements of the project (i.e., requirements over and above those required by law).

- What are the specific requirements for keeping records of this EMS project?  Clarify those requirements by law and regulation between requirements of the project (i.e., requirements over and above those required by law).

- What are the specific requirements for reporting to regulatory organizations regarding this EMS project?  Clarify those requirements by law and regulation between requirements of the project (i.e., requirements over and above those required by law).

- What are the specific requirements for reporting to stakeholders regarding this EMS project?  Clarify those requirements by law and regulation between requirements of the project (i.e., requirements over and above those required by law).

- Do the reports have a required audience(s)? (Y/N) If yes, please identify the audience(s).  Clarify those requirements by law and regulation between requirements of the innovation (i.e., requirements over and above those required by law).

###### Implementation Questions

- To what extent have the specific requirements for environmental monitoring of this project been met?

- To what extent have the specific requirements for keeping records been met?

- To what extent have the specific requirements for reporting to regulatory organizations been met?

- To what extent have the specific requirements for reporting to stakeholders been met?

- Have reports been delivered to the required audiences identified in Question 7?  (Yes/No)  If yes, please list dates and method of communication (e.g., Web site, email public notice).  If no, please provide explanation.

Compliance Assurance with a “Project Agreement”

For the purposes of this module, the term “project agreement” is being used to cover EMS type projects.  EMS project team members will want to structure the EMS project agreement carefully to ensure that all applicable requirements are met and function within the current regulatory framework, unless rule revisions are contemplated by the project.  Designers of the project agreement will want to address all substantive requirements (e.g., technology, emissions or effluent performance, work practice requirements, etc.) and procedural requirements (e.g., public notification, review, comment processes; potential termination of the project; and reporting and information availability requirements).

# Verification

    - How do users ensure that the parties to the EMS project comply with the provisions of the EMS project?

- How will the organization’s performance under the project be compared to the performance that could have been obtained under the normally applicable regulatory structure?

- Who is responsible for verifying compliance and environmental performance results and how will it be done?

# III.	Practical Enforceability

The user will want to ensure the practical enforceability of the project.  This is accomplished by developing monitoring, record-keeping, and reporting requirements that enable regulatory authorities to detect source compliance with all applicable requirements.  Compliance personnel will find the project to be practically enforceable if sufficient data regarding the project is available and well organized to perform compliance verification calculations according to established procedures.  Further evidence of the practical enforceability of a project can occur in the context of inspections and review of third-party audits of an EMS.  If inspectors find that inspecting the EMS projects is straightforward and comparable to conducting inspections for sources with conventional approaches, the project will prove to be practically enforceable.

14.	What is the pre-project “baseline” for enforcement and compliance assurance against which progress will be (is) measured?

15.	Can an inspector visiting the project site determine historic and current compliance from the records maintained on site?

16.	Does the EMS permit, if applicable, contain a legal obligation for the source to adhere to the terms and conditions of the limitation?

17.	Does the permit rely on the efficiency of a control technology for compliance with a permit limit?  If so, how is that efficiency determined and shown to be accurate?

18. 	Does the EMS project agreement require the correct type and amount of information (in logs, notices, monitoring data, etc.) to determine the number and duration of any deviations?

19. 	How will regulators determine—prior to and throughout the project—that the facility is continuing to maintain its EMS?

20. 	Who will audit EMS conformance?

21. 	Does the project include required self or third-party compliance auditing?  If yes, explain.

22. 	Do the terms of the project obligate a regulator to exercise its enforcement discretion in specific ways (if so, explain)?

23.	Does the regulatory preserve the requisite statutory inspection and enforcement authority to satisfy EPA-state delegations of authority?

24. 	How, and for what reasons, will the organization return to standard permit terms should it become necessary to terminate the organization’s participation in the EMS project?

  - Redirecting Regulatory Oversight

      - What screening criteria (e.g., compliance history or participation in leadership programs) are used to ensure that good facility partners participate in the EMS project?

      - If applicable, what combination of EMS conditions and facility characteristics is being used to establish the confidence or the analytical basis for redirecting resources (e.g., compliance history, transparency of decision-making, quality and degree of public involvement, third-party auditing, reporting, etc.)?

      - What is the analytical basis being used for determining the relative priority or risk of agency activities (for the purpose of targeting staff time and resources)?

      - What are the net resource implications to compliance and enforcement personnel/programs of substituting EMS terms for permit conditions or linking them to the permit conditions?

V.	Results and Relative Advantage

29. Has the project improved compliance rates and/or reduced the length or severity of noncompliance?

30. To what extent can the source in the project be more/less easily inspected to determine compliance than a similar source operating under conventional approaches?  How does this compare to what is expected?

31. Does the project improve on enforcement or enforcement practices over the current system (e.g., redirection of oversight resources)?

32. Does the adoption of an EMS allow organizations to remove regulatory burdens by moving down in “regulatory status” (e.g., moving from large quantity generator to small quantity generator status)?   If yes, describe.

Exhibit 4

| Model Table for Monitoring, Reporting, and Record-Keeping (MRR) |
| --- |
| Environmental Media and Pollutants of Concern | Monitoring Approach (continuous, parametric, analytical testing, composite sample, grab sample) | Materials Use and Operating Parameter Requirements (e.g., application rate, percentage by weight) | Data Collection Frequency | Reporting Requirements for Regulatory Authorities and Stakeholders | Record-Keeping Requirements | Compliance Notes (specify date of report and note any deviations) |
| Air Emissions by Pollutant (tons per year) |  |  |  |  |  |  |
| Average Effluent Concentrations by Constituent (mg/L) |  |  |  |  |  |  |
| Hazardous Waste Generated (pounds) |  |  |  |  |  |  |

MODULE 5:  Public Involvement and Stakeholder Feedback

An EMS project should maintain or enhance existing standards of public involvement and should not shift the burden of risk to disadvantaged populations or diminish the traditional levels of safety provided for workers responsible for creating, maintaining, or implementing the project.  In addition, in order to be accountable to the public, the project should be enforceable and produce measurable and verifiable environmental results.  The environmental and enforceability evaluation modules (Modules 2 and 4) seek to understand these latter issues of concern.  The public involvement and accountability module seeks to understand the former.

EPA defines public involvement as the full range of activities that are used to engage the American people in decision-making processes.  Public involvement is a progression that starts with outreach to build awareness and interest.  It evolves to information exchange, through collaboration and recommendation to agreement and decision-making.  The public may include private individuals, environmental or other advocacy groups, environmental justice groups, indigenous peoples, minority and ethnic groups, business and industrial interests (including small businesses), elected and appointed public officials, trade associations, or research and governmental associations.

Public involvement in the development and implementation of innovative projects is fundamental to ensure a transparent process that fosters trust and works to enhance the relationships between the public, the regulated community, and regulators.  Public participation can benefit the project, the regulated entity, the regulator, and the public by increasing awareness about innovative projects and their environmental benefits and impacts, developing measurable and verifiable environmental results, preventing shifts in risk burdens to disadvantaged populations, ensuring worker safety and protections are maintained, and enhancing the level of information available to the public.  By involving the public early in the project, practitioners will have the benefit of the public’s guidance, experience, and input.  Not everyone may choose to be an active participant; however, the goal should be to provide opportunities for people to engage at every point along the progression.  Individuals and groups should decide for themselves whether, when, and how to participate.  EPA issued a new Public Involvement Policy in May 2003, which contains useful tips on implementing effective public involvement strategies and helps define different stakeholder groups.  The policy also provides useful tools to assist practitioners in the public involvement process at the public involvement Web site: http://www.epa.gov/publicinvolvement/intro.htm.

Stakeholder Participation

The first step in stakeholder involvement is to identify key participants who may be interested in, or affected by, the project.  Depending on the nature of the project and who is implementing the project, stakeholders may include members of the regulated community, community groups, environmental or other advocacy groups, governmental entities, trade associations, and others.  The user may also want to consult with EPA, state, tribal, and local government partners.  To alert the public in low-income and minority communities regarding the opportunity to become involved in a project, practitioners should consider using various media such as advertising in local newspapers, making announcements on radio stations, and communicating through local institutions such as religious establishments.  Please see EPA’s Public Involvement Policy for more information on involving different stakeholder groups and stakeholder needs.  The key questions to ask are:

- Who are the key stakeholders?

- Have state, tribal, and local government partners been consulted?

- Have stakeholders and partners been consulted in the development and/or implementation of the EMS project?  If yes, describe the extent of the participation.

- How did stakeholder involvement change as a result of the adoption of the EMS or the implementation of the EMS program?

- What benefits does this involvement provide (e.g., ideas not otherwise considered, more positive community relations)?

- What effects does this involvement have on the decisions made by organizations or by the program?

- If applicable, what specific strategies are being considered to ensure the participation of low-income and minority communities?

- What is the pre-project “baseline” for public involvement and accountability against which progress will be measured?

- How does the project address regulatory requirements (federal/state/local/tribal) for public involvement?

- What changes to the transparency in decision-making (for the regulator and/or the regulated) and the degree of stakeholder/public leverage result from the EMS project?

II	Constructive Dialogue Approaches

The best means of involving stakeholders in the development and implementation of the EMS project depends on the number and diversity of the parties to be consulted, the geographic impacts of the project, the resources available to engage in consultative processes, and the type of communication networks generally used by particular stakeholders.  Constructive dialogue approaches may include outreach activities, information exchange, the solicitation of stakeholder advice or recommendations, technical workgroups, Web-based dialogues, Citizen Advisory Committees, and stakeholder negotiations.  Collaborative processes encourage an interactive and dynamic discussion that may lead to greater clarification of the issues and consensus among the parties.

- What are the best means of involving stakeholders in the development of the EMS project?

- What types of collaborative processes or other participatory practices will be used to solicit input?

III.	Availability of Information

For information to be readily available to stakeholders, it must be both understandable and accessible.  The user must prepare “plain English” (or other appropriate language) summaries and fact sheets to facilitate comprehension of otherwise complex environmental concepts.  Communication materials must engage participants at all levels—from members of the general public to experts in the field—and make available project materials such as innovative permits, progress reports, annual reports, emissions, and/or effluent data, etc.  Materials must be translated when appropriate so that diverse populations have access to the information.  In addition, the user must seek ways to ensure the broadest participation feasible and should work with all identified partners to enhance information distribution to all potentially interested parties.  Public information meetings can provide a valuable and interactive means for communication with interested stakeholders.

- Is information regarding the EMS project readily available to stakeholders?  If yes, how will it be shared?

- What changes to the type, scope, amount, quality (accuracy, relevance), and timing of information available to the public result from the project?

# IV.	Stakeholder Feedback

Stakeholder involvement needs to be carefully planned to allow sufficient time for discussion of the relevant issues with the stakeholders and to incorporate their feedback in the project.  If possible, how stakeholder feedback will be used in the project should be communicated and explained to participants from the start of the project.  The user should anticipate both positive and negative feedback from stakeholders.  The feedback may be content-based or about the process; and the feedback from one stakeholder group may be at odds with another group.  The practitioner should try to understand the feedback, work to resolve conflicts, and strive for consensus.

- At what stage in the project process will stakeholders be involved to ensure participation and an opportunity to incorporate feedback?

- To what extent has the practitioner been successful in obtaining feedback from the public about the project’s design and/or implementation?

# V.	Responsiveness to Stakeholder Priorities and Concerns

An EMS project may demand a high level of responsiveness to the priorities and concerns of stakeholders.  The user should develop a process to address the major concerns of stakeholders.  If resources are available, academic experts may provide objective technical assistance to stakeholder groups or a facilitator can be used to make sure that all concerns are heard and addressed.  It is important at the outset of a project to determine what resources will be available to address stakeholder issues.

17. How will the major concerns of stakeholders be addressed?

18. Is technical or financial assistance available to facilitate the participation of particular groups of stakeholders?

19. Are stakeholders likely to consider their involvement in the project a positive experience?  Why or Why not?

MODULE 6: ASSESSING THE POTENTIAL TRANSFERABILITY

OF THE EMS PROJECT

The purpose of this module is to help reduce the uncertainty about an EMS project’s expected consequences and determine its rate of adoption.  In 1962, Everett Rogers wrote the pioneering work, Diffusion of Innovations1, which presented a workable framework for diffusing innovations or innovative thoughts over time.  Rogers’ work provides a systematic approach to understanding the nature of innovations and the existing conditions and culture necessary for accepting, adopting and implementing innovations and can be easily applied to EMS projects.

In assessing the potential transferability, practitioners should consider a set of overview questions, followed by a ranking methodology based on Rogers’ innovation-diffusion model and a sample application of the transferability module.  It is recommended that the user first read through the questions and ranking methodology to understand the approach and how these two steps work together.  Some of the overview questions will also be addressed in the ranking process and the ranking will inform responses to the overview questions.  This transferability module is based on Rogers’ innovation-diffusion model, which has five components: 1) relative advantage, 2) compatibility, 3) complexity, 4) trialability, and 5) observability.  This module provides a definition of each component as it relates to environmental projects and key questions related to each component.  The practitioner will find that the five other modules also ask questions of relative advantage and those responses can be applied in this module.

I.	Relative Advantage is the degree to which the EMS project is perceived as being better than the idea it supersedes.  The degree of relative advantage is often expressed as enhanced environmental protection, reduced risk to public health, costs savings in meeting regulatory requirements, recognition for being an environmental leader, administrative streamlining, increased public involvement, or other benefits over the traditional approach.

Within this component, it is also important to identify who benefits from the EMS project or program.  If all parties to the project including the regulated community, the public, and federal and state environmental regulators benefit from the project, the relative advantage can be easier to ascertain.  If, however, regulated entities perceive a relative advantage while the public perceives a disadvantage, the project may need to be better communicated to the public and stakeholders or it may need modification prior to scale-up.

A final question regarding the relative advantage component is whether additional data is needed to inform this determination.  If additional information is required prior to making this assessment, it may be necessary to go back and re-check Module 2: Assessing the Environmental Results of the EMS Project to see where there are data gaps in data collection or methodology.  It is often the case that more complete information is necessary to make a determination of the potential for broad-scale application of the project.

- Compared to the traditional way of doing business, what has been the measurable impact (positive and/or negative) of the EMS project with regard to:

  - Environmental protection

  - Organizational management

  - Economic impacts

  - Expedited action

  - Public involvement

  - Accountability

  - Environmental Justice

  - Administrative burden

  - Other areas

- Who benefits from the EMS project?

  - What do they gain?

- Who incurs costs as a result of the EMS project?

  - What costs do they incur?

- What additional data are necessary to inform determination of the relative advantage of the project?

- To what extent does the adoption of an EMS change an organization’s use of advanced environmental and materials accounting techniques?

II.	Compatibility is the degree to which the project is perceived as consistent with the existing values, past experiences, and needs of potential adopters.  The user should assess how well the project is consistent with organizational needs and goals.  This module asks the user to look at the feasibility to adopt a project given the “culture” of those who are affected by the project, the users of the project, or the perceivers of the project.

As in the relative advantage component, it is important to assess the project’s compatibility with the multiple organizations that participate, or may be interested in participating, in the project.  For example, compatibility with the culture of the regulated entity is as important as compatibility with the culture of the environmental regulators.  If the project is embraced by the regulated community, and rejected by the regulators, the project is unlikely to be adopted.  It is also possible that a project may be embraced at the state level and not at the local level for a variety of reasons that may, or may not have to do with the project itself, but with the availability of resources.

- To what extent is the EMS project consistent with existing organizational beliefs, values, and/or management approaches?

- What is the level of support for the EMS project from:

  - Within EPA

  - The affected entity or entities

  - Other regulated entities

  - State agencies

  - Federal agencies

  - Local community

  - Environmental non-governmental organizations (NGOs)

  - Environmental Justice groups

    - Local government

- To what extent has a similar EMS project been tested before?

  - Different sector or industry

  - Different media

  - Different state, EPA region, local government, tribe

  - Different community

- Among existing users, to what extent does the EMS project support organizational goals, (i.e., department, office or divisional goals, community goals)?

- Among existing users, to what extent are organizational changes necessary to enable widespread use of the EMS project (what specific changes are necessary)?

- Among potential users, to what extent does a broader user market or audience exist for the EMS project?

- Among potential users, to what extent does the project need modifications to be used more broadly (what specific changes are necessary)?

- Who else might use or be interested in the EMS project (e.g., regulated entities not originally contemplated as users of the project, or regulators who might be able to transform the project in a creative way for other purposes)?

  - Other regulated entities

  - Other regulators (tribes, local state, EPA region, EPA Headquarters)

  - Communities

III.	Ease of Adoption is the degree to which a project is perceived as relatively easy to understand and use.  If the project is complex, the development of assistance materials to assist adoption may be considered.  Or, if the project has been tested before in a different sector, media, governmental entity, or community, are there existing users that would be willing to provide testimonials, or existing materials that might prove helpful?

- How readily understood is the EMS project?

- To what extent is assistance necessary, and available, to understand and use the EMS project?

- If the project needs to be brokered, what assistance products are available?

  - Are they in development?

  - Do they need to be created?

IV.	Trialability is the degree to which a project may be experimented on a limited basis.  New ideas that can be tried in a phased approach are generally adopted more rapidly than projects that are not easily implemented in stages.  The user should identify, to the extent feasible, how the project might be divisible, and in what sequence, to solicit feedback for this component.

- To what extent can the project be tried on a temporary basis (i.e., one month, one year, etc.)?

- To what extent can the project be tried on a limited scale (i.e., fewer facilities initially or with fewer regulatory authorities)?

V.	Observability is the degree to which the results of a project are visible to potential users of the project.  If the project is targeted at a small group of technical experts, dissemination of the idea in a trade journal may be adequate, whereas a project that affects a large municipality will need a different strategy to assure optimal visibility and broad-scale adoption.

- To what extent are the EMS project results apparent to others?

# VI.	Personal Experience and Observations

This set of overview questions asks fundamental questions that must be addressed in any assessment of transferability potential, including whether the project represents an improvement, whether it is ready for diffusion, what the primary drivers and barriers are to scale-up, how to best implement the project, and at what organizational level?

- To what extent can the EMS project be considered to be an improvement over the traditional way of doing business?  In what way(s) was the project an improvement?

- Is the EMS project mature enough to have a full understanding of its advantages and disadvantages?

  - If not, when will it be possible to gain a full understanding of the advantages and disadvantages of the EMS project?

- What are the primary lessons learned from testing and analyzing the EMS project that pertain to its broad-scale application?

- What is the potential for broader application of the EMS project?

  - Could the EMS project be used to address another problem?

- What are the primary barriers to broader application of the EMS project?

- What are the critical implementation elements needed to overcome the barriers to broader application of the EMS project?

- How would the EMS project best be applied?

  - What steps could be taken to facilitate more widespread application of the EMS project?

b.	What steps could reduce the transaction costs of the diffusion?

  - What elements should be scaled-up?

  - What elements should be changed?

  - How might other users be identified?

  - Are there unique circumstances that could impact broader application of the EMS project (e.g., window of opportunity)?

    - Are there resource limitations, if any, which would constrain broad-scale application?

    - At what level—national, state, or local—should the project be applied?

  - What are the appropriate mechanisms for such application?

- How do users feel about the voluntary incorporation of EMSs with the regulatory system?

## Innovation-Diffusion Model:  Using a Transferability Scale

By assessing the potential transferability of an EMS project by the five diffusion components, the user will be able to better identify candidates for broad-scale application.  Those projects with high scores on all or more diffusion components are likely to be better candidates for broad-scale application than those projects with low scores.  This ranking methodology should provide the user some insight into the potential transferability of a project, but it will not substitute for the judgment of experienced practitioners and it does not guarantee the predicted results.  Projects can take on a life of their own despite the best predictions.  For example, an EMS project that ranks as a “low” on the transferability scale may be able to be scaled-up due to unanticipated events.  The converse is true for those projects that may seem to be highly transferable, and may end up sidelined in the end.  The ranking table should be used to emphasize the strengths of the project and to continue to improve on the weaknesses.  The table can also be used to help identify priority projects for scale-up.  If the user has multiple projects, but limited resources, the ranking table can help assist decisions to scale-up those projects which are highly transferable first.

Relative Advantage: If an EMS project were perceived as resulting in significant environmental benefits and cost savings when compared to the traditional way of doing business, it would be ranked as high on the transferability scale for this component.  Conversely, if the project yields environmental results that are no better than the traditional approach and the costs are increased, it would be ranked as low for the relative advantage component.

A more difficult case is when environmental results are superior, but costs are significantly increased.  In this case, the user may want to identify the benefits that are being ranked (i.e., rank the relative advantage for environmental results as high and the relative advantage for costs as low).  Or, the practitioner may choose the “moderate” rank to reflect the competing considerations.  In either case, the practitioner is advised to explain the rankings so that the rationale is transparent.

Compatibility: An initial ranking regarding compatibility should begin with the existing users of the project, and then address compatibility of the project with potential adopters.  For example, in an EMS project a state project manager may want to do the initial ranking with other staff and then do a comparability ranking with the participating regulated entities.  Existing users and, to the extent feasible, potential adopters should be consulted to ascertain whether the project is, or is likely, to be consistent with organizational beliefs and management approaches.  If not, are there specific changes that would make the project more compatible?  Again, if there are differences in the compatibility rankings among the participants, or between existing users and potential users, note these differences and provide explanations, if possible.  The practitioner should use these differences to honestly assess how feasible adoption of the project will be, and how to communicate differently with parties to address differences.

Ease of Adoption: A project will be ranked high on the ease of adoption component if potential adopters readily understand it and little assistance is needed to implement the project.  If the EMS project is complex, difficult to understand, and requires considerable assistance to inform adoption of the project, the project will be ranked low on the ease of adoption component.

Trialability: For this diffusion component, a high ranking means that the project may be tested on a temporary basis, or on a limited scale, before being fully adopted.  A low ranking would indicate that the project must be tried with a large number of facilities or over a significant period of time in order to see results, implying that significant and sustained resources (e.g., capital, personnel) are required before the project can be fully adopted.

Observability: A high ranking means that the project is very visible to the targeted users and a low ranking means that greater efforts will need to be made to increase the project’s visibility.

| Transferability Scale |
| --- |
| Project-Diffusion Components | High | Moderate | Low |
| Relative Advantage |  |  |  |
| Compatibility |  |  |  |
| Ease of Adoption1 |  |  |  |
| Trialability |  |  |  |
| Observability |  |  |  |
| 1 For ease of adoption, “high” responses are positively related to a project’s rate of adoption, whereas “low” responses are negative related. For trialability, “high” responses are positively related. |

# Footnotes

Module 1:  Mapping the EMS Project summarizes the overall goal(s) of the project, which may include environmental, economic, and process-related goals.  In this module, the user should focus on the environmental goal(s) of the project and whether or not the project is achieving its environmental goal(s).

This module is not intended to result in a valuation of benefits that would occur in the context of a formal benefit-cost analysis.  Instead, the analyst will assemble available information and use it to guide the development of the project.

This module is not intended to result in a valuation of benefits that would occur in the context of a formal benefit-cost analysis.  Instead, the analyst will assemble available information and use it to guide the development of the innovation.

For more information on complete cost-benefit assessments and on preparing economic analyses, please see EPA’s National Center for Environmental Economics Web site.  http://yosemite.epa.gov/ee/epa/eed.nsf/Webpages/Guidelines.html

Economists assign other kinds of costs such as social welfare losses (i.e., rise in price or a decrease in the output of goods and services as a result of the project that raises prices for consumers and may decrease a producer’s revenues), transitional costs (i.e., the value of resources that are displaced because of innovation-induced reductions in production), and indirect costs (i.e. the adverse effects the project may have on product quality and productivity, or on markets for other goods and services).  These types of costs or cost savings are difficult to quantify and generally will not be available to the user.

1Rogers, E.  Diffusion of Innovations.   4th Edition.  The Free Press, New York: 1995.

# Text boxes

Among the questions managers need to answer are the following:

- Are programs meeting their stated goals and objectives?

- Are they using available resources efficiently and effectively?

- Do managers know what and how well programs are doing?

- Are there areas in which program performance could improve?

NOTE: If the user is in the federal government, there are restrictions under the Paperwork Reduction Act on surveys and questions that the federal government can ask of non-federal entities or persons.

For more information on survey/interview limits of federal entities, please see http://www.epa.gov/icr/icr.html for more details.

technical

assistance

More Fish Clean beaches

Developers/ builders trained

training

Healthier wetlands

-recruitment

-developers and builders acquire new technologies and change practice

trainees ready

Resources

-EPA

-State

-Local

-Private

-increased awareness of harmful effects

-increased awareness of new technologies and incentives

-materials

development

Reduction in non-point source pollutants in waterways

materials ready

NOTE:  If the user is trying to aggregate normalized data or compare normalized data across facilities – ensure that the basis for normalization is similar in order to be able to compare relative environmental performance.

Note:  An EMS by its very nature is not a static process.  In that same vein, good program management, performance measurement, and evaluation should be performed routinely throughout the life of the project.

For these activities

To produce these outputs

We use these resources

For these activities

So that the customers can change in these ways

Which leads to these results

Which leads to these outcomes

To produce these outputs

We use these resources

So that the customers can change in these ways

To produce these outputs

We use these resources

For these activities

Trainees receive TA

Clean, Safe, Swimmable, Fishable Water

Trainees aware of using new information

website