## Open Action Items
Action Item List - Open Items |  |  | Start new: | 2005-05-24
OSG WebPortal |  |  | Updated: | 2006-05-15
|  |  | PC= | Penelope Constanta
|  |  | MH = | Mari Herrera
|  |  | KY= | Katie Yurkewicz
|  |  | RP= | Ruth Pordes
|  |  | MT = | Marcia Teckenbrock
*****ONE TIME TASKS*****
* = High Priority
Action Item | By Whom | Current Date | Target date | Status/Actions/Issues | Effort
implement CVS | MT` | 2006-04-14 | ??? | Is this still desired?
Enhance Twiki Header | MT/KG | 11.15.05 | 6.1.06
new images on homepage | ALL | 2006-05-15 | 2006-06-15 | On hold until after SC05; meeting planned with Ruth, Katie, Kyle, Xeno Media & Marcia
Content Tsars page | MT | 11.15.05 | ongoing | We have some people identified, but the issue is how to get them to do it.
Move test site into production | MT/KG/CSS | 2006-04-14 | 5.1.06 | Finalizing support agreement with FNAL/CD/CSS
*****OPERATIONS (ONGOING ITEMS)*****
Action Item | By Whom |  |  | Status/Actions/Issues | Effort
OSG mambo Web Maintenance | MH/MT |  | ongoing | an on-call is expected to help with this in May/June, 2006. | MT: 10%, MH: 20-30%
MailList Support | MH |  |  | Make sure there is more than one owner for all mailing lists. | 5-10%
Determine Document Views Needed and give to Marcia | RP, PC
Encouraging update of Twiki content | MT |  | ongoing
Creating and maintaining Conference pages | MH |  | ongoing | Mari has successfully been doing this for some time; on call to help in May or June, 2006 | 20%
DocDB data validation and updates | MT/MH |  | ongoing | on call to help in May or June, 2006
Write scripts for DocDB query display | MT |  |  | Marcia has taken Learning Tree course in Perl Programming. Will begin development | Was to be 40-50% effort beginning 9/6, but DocDB has continued to consume most of time.

## Closed Action Items
Action Item List - Closed Items
<project name>
ID | Action Item | By Whom | Finished | Status/Actions Taken
| SC05 Flyer | MT | 10.11.05 |  | 11.11.05
| Facilitate testing/performance of MySQL and web server | MT, CSS |  |  | 8.30.05 | Server is now performing adequately. New item for testing mambo falls to Mari.
| Add second calendar for recurring meetings | KG/MT |  |  | 8.30.05 | Discussed at 8/30 and 9/6 docs meeting. Kyle cannot create a second calendar. Marcia will create a static page for recurring meetings.
| Redo At Work Page/Decommission Plone | MT |  |  | 9.30.05 | Marcia/Ruth has sent email to everyone with info in Plone. Links will be changed to point to Twiki
| Convert pages to new template | MT |  |  | 7.15.05 | DONE
| Review Conference page procedures | ALL |  |  | 10.15.05 | Mari has a new template that is being reviewed. Marcia will bring up at 10/4 Docs meeting.
| Learn Mambo administration | MT |  |  |  | DONE
| Write Project Definition | MT |  |  | 6.10.05 | DONE | 1/4 day
| Catalog pages to get a feel for types of information that is out there | MH/LM |  |  | 6.24.05 | DONE | 1/4 day
| MailLists - define for project plan and send to Marcia | MH |  |  | 6.24.05 | DONE | 1/4 day
| New web template | MT |  |  |  | DONE | 2 weeks
| Mailing Lists | MH |  |  | 8.30.05 | Make sure there is more than one owner for each list. Are all lists being used? Do we need to close more lists to allow posts only from members? | 1 day
| Meet with Indiana folks to discuss deliverables for this Project. |  |  |  |  | CANCELLED | 1 day
| Test Eric's API | MT | 2005-09-02 |  | 10.20.05 | John Urish has been working on development for Numi. API is a lot more rudimentary than we hoped.
| Encourage CSS to revamp Plone help pages | PC | 2005-09-02 |  |  | Jim Fromm and Marc Mengel are working on this. Target date is for the documentation to be complete. No longer part of this project.
√ | Fix Lines in template | KG |  |  | 9.30.05 | Request per Katie - decided against this.
√ | Add rollover menu item for Grid Computing on CD Home Page | MH |  |  | 10.7.05
√ | Create January 06 Consortium Meeting pages | MH |  |  | 9.30.05
√ | Document Views for Each Technical Group with Query Results | MT | 2005-09-02 |  |  | Marcia taking this over
√ | January Consortium Meeting pages | MH | 11.15.05 |  | 11.30.05 | there will be updates up until the meeting, but the bulk of pages will be in place.
√ | Finish installing and configuring mambo on test machine | MT | 4.6.06 |  | 12.31.05 | Done in April, 2006
| OSG/Plone Web Maintenance | MH/MT |  |  |  | Plone site decommissioned | MT: 10%, MH: 20-30%

## WBS
WBS for <project name>
|  | Last Update: | <date>
Date to
ID | WBS Item/Subitems | Status | Complete | Team Involved
1 | <WBS Item>
1.1 | <sub item>
1.2 | <sub item>
1.3 | <sub item>
1.4 | <sub item>
1.5 | <sub item>
2 | <WBS Item>
<etc>

## Top Risks
| Top Risks Chart | <project name>
| Last Update: | date>
ID | Risk Statement |  | Prob | Loss | Exp | Risk Handling Action | Who | Date
| Condition | Consequence
1
2
3
4
5
6
7
8
9
10