## ShipDatesProject
Item | Baseline Ship Date | Projected Ship Date | Actual Ship Date | Comments
Adapters | 2006-07-14 |  | 2006-07-17
Disk&Endcap Tooling | 2006-07-21 |  | 2006-07-14
System test pipes, etc | 2006-07-28 |  | 2006-07-28 | PP1a to PP1b
System test extensions, plate,etc |  |  | 2006-08-03
SQP 1(A3-4) | 2006-08-04 |  | 2006-08-09
ISPs first shipment | 2006-08-11 |  | 2006-08-11 | A5,A6,A7,A8
Endcap A | 2006-08-23 |  | 2006-08-23
SQP 2(A5-6) | 2006-08-25 |  | 2006-09-15 | Going to batch shipping
ISPs 2nd shipment | 2006-08-25 |  | 2006-08-24 | C1-2, C3-4
Barrel Frame | 2006-09-08 |  | 2006-09-06
ISPs 3rd shipment | 2006-09-01 |  | 2006-08-24 | C5-6, C7-8
SQP 3(A7-8) | 2006-09-15 |  | 2006-09-18
SQP 4(A1-2) | 2006-10-06 |  | 2006-09-26
Barrel capillaries complete | 2006-10-06 |  | 2006-12-15 | Reference capillaries from CERN delayed by 2 weeks. Concerns about 1st three batches. Remade. Additional parts delay from France. Leaks after C3F8? More sample testing underway. Decision to go but lost many from sample testing. More spares
Endplates, trolleys | 2006-10-13 |  | 2006-10-03 | Endplates only
BPPS A | 2006-10-13 |  | 2006-10-09 | Also trolley parts
SQP 5 | 2006-10-20 |  | 2006-10-24 | C1-2
BPSS C | 2006-10-27 |  | 2006-10-09
SQP 6 | 2006-11-03 |  | 2006-10-24 | C3-4
Cans, Buckets, etc complete | 2006-11-10 |  | 2006-12-15 | Mods from insertion trial
SQP 7 | 2006-11-27 |  | 2006-11-08 | C5-6
SQP 8 | 2006-12-15 |  | 2006-11-08 | C7-8
Opto-cooling parts complete | 2006-12-15 |  | 2006-12-08
Updated on | 2006-12-18

## ShipDatesM&O
Item | Baseline Ship Date | Projected Ship Date | Actual Ship Date | Comments
Pixel Mounts | 2006-11-27 |  | 2006-11-28
Opto capillary | 2006-12-22 |  | 2006-12-01 | Complete, unless design changes
LEMO demating tools(2) | 2006-12-22 |  | 2007-01-08
Springs | 2006-12-22 |  | 2006-12-15
Luer mating tools | 2006-12-22 |  | 2007-01-21 | All delivered but operation needs verification
Ship IR camera | 2007-01-10 |  | 2007-01-10
Ship test module | 2007-01-08 |  | 2007-01-02
Flexures | 2007-01-08 | 2007-05-04 |  | Last barrel by 1/26. Forward 5/4
Opto-tubes for trials | 2007-01-12 |  | 2007-01-12
Ship Touch1 | 2007-01-15 |  | 2007-01-12
Improved flare tool | 2007-01-15 | 2007-01-26 |  | Needs more work from Rod
Inlet plug/exhaust extension | 2007-01-15 | 2007-02-15 |  | 1st set to CERN 1/8 with Ahmet. Need additional nuts. First set of Delrin nuts sent
HEX repair kit | 2007-01-16 |  | 2007-01-21 | Mario took to CERN
Rotation backbone-backbone | 2007-01-18 |  | 2007-01-18 | In the mail
1/4 sealing plugs | 2007-01-18 |  | 2007-01-04 | Large hole mods done at CERN
DST rails | 2007-01-19 |  | 2007-01-19 | In the mail
Opto-inlet extensions | 2007-01-26 | 2007-01-26 |  | In progress with Rod
SLA BCM inserts | 2007-01-26 | 2007-01-26 |  | No prints yet
Beam pipe bellows arms | 2007-02-16 | 2007-02-16 |  | 1st half 2/2 to go with Rod
HEX spares, tooling | 2007-02-01 | 2007-04-01 |  | Change in planning and overall schedule
Corrugated panels for LEMO | 2007-03-15 | 2007-03-15 |  | Need drawings
Updated on | 2007-01-22