U.S. ATLAS PROJECT OFFICE

Physics Department

UPTON, NEW YORK 11973

November 22, 2005

Mr. Pepin Carolan

Department of Energy

Fermi Area Office

POB 2000

Batavia, IL 60510

Dr. Samuel Aronson

Associate Laboratory Director

Brookhaven National Laboratory

Upton, NY  11973

SUBJECT:  U.S. ATLAS Research Program Quarterly Status Report

Dear Sirs:

Attached please find U.S. ATLAS Research Program Quarterly Status Report No. 5 for the period July-September 2005.

Sincerely yours,

Howard A. Gordon

U.S. ATLAS Deputy Research Program Manager

Head, U.S. ATLAS Project Office

Distribution:

Abolins, M.

Alam, S.

Aronson, S.

Baker, K.

Barnett, M.

Bensinger, J.

Blair, R.

Butehorn, C.

Byon-Wagner, A.

Carolan, P. - DOE

Cleland, W.

Coles, M. – NSF

Crawford, G. - DOE

De, K.

Dodd, J.

Ernst, R.

Errede, S.

Feldman, G.

Ferbel, T. - DOE

Gilchriese, M.

Goldberg, M. – NSF

Grillo, A.

Harrison, M. – PAP

Hinchliffe, I.

Huth, J.

Kagan, H.

Kane, S.

Kirby, D.

Kogut, J.

Lankford, A.

Larsen, R. - PAP

Lissauer, D.

Lubatti, H.

Mantsch, P. - PAP

Meyers, P. – PAP

Neal, H.

Norton, S.

Ogren, H.

Oh, S.

Parsons, J.

Pilcher, J.

Polychronakos, V.

Price, L.

Pripstein, M. - NSF

Rijssenbeek, M.

Rutherfoord, J.

Seiden, A.

Seidel, S.

Shank, J.

Shochet, M.

Skubic, P.

Slattery, P.

Sliwa, K.

Sondericker, J.

Stroynowski, R.

Taylor, F.

Tuts, M.

Whitaker, S.

Willocq, S.

Wolbers, S. - PAP

Williams, H.

Willis, W.

Wu, S.L.

research program STATUS REPORT NO. 5

REPORTING PERIOD

July-September 2005

# Table of Contents

Table of Contents	3

1.	Executive Associate Project Manager’s Summary (J. Shank, BU)	4

2.	Technical Progress Reports	4

2.1 Physics	4

2.2 Software	5

2.3 Facilities	16

3.1 M&O Silicon	22

3.2 M&O TRT	26

3.3 M&O Argon	28

3.4 M&O Tile	35

3.5 M&O Muon	38

3.6 M&O Trigger	43

3.	Financial Report (Chuck Butehorn, BNL)	46

# Executive Associate Project Manager’s Summary (J. Shank, BU)

The focus of the physics and computing effort during this quarter was the preparation for the upcoming series of exercises called Computer System Commissioning (CSC, formerly called Data Challenge 3). This preparation relies heavily on our recent experience with Data Challenge 2 (DC2) and production for the Rome Physics workshop.

In the area of physics simulation, we incorporated new, more sophisticated event generators, such as MC@NLO. In the core software area, again, most of the effort was on correcting issues learned from DC2 and preparing for CSC, where we will need the framework for distributed analysis working at scale. This work involved incorporating new LCG software components such as COOL and LCG 3D project tools.  In the subsystem software, the emphasis was on the ongoing detector commissioning work.

In the facilities area, there were many upgrades to increase the capacity for CSC. The T1 network plan for getting to 20Gb/s by 2006 was worked out with ESNET. The T1 storage capacity was doubled. Similarly, the Tier2 centers increased both disk and storage capacity with major purchases at UTA (160 dual node machines) and 60 IBM Xeons at Boston University.  In addition to the hardware upgrades a major achievement of this quarter was the planning and beginning of execution of a major new system for running production on the world wide grid. This new system is called PanDA for Production and Distributed Analysis.  This system is designed with all our extensive DC2 experience and our leadership role in the overall ATLAS production system team at CERN as a basis. We now have an aggressive, comprehensive plan that will be carried out next quarter, with the goal of having a scalable, widely used system by the end of the next quarter.

# Technical Progress Reports

## 2.1 Physics

2.1 Subsystem Manager's Summary 	Ian Hinchliffe (Lawrence Berkeley Laboratory)

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Pythia 6.3 | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| RTT testing implemented | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| start DC3 event generation | 1-Dec-05 | -- | 1-Dec-05 | On Schedule |
| Complete CSC testing sample (atlas sample B) | 12-Dec-05 | [New] | 12-Dec-05 | On Schedule (See #1) |
| complete 100 inverse picobar CSC event generation | 30-Jan-06 | [New] | 30-Jan-06 | On Schedule |
| release 12.0.0 | 14-Feb-06 | [New] | 14-Feb-06 | On Schedule |

Note #1  Needed before full CSC production can start

Work in this quarter was focused on preparation for DC3/CSC.

The event main event generators Pythia and Herwig were migrated to new versions (6.323 and 6.507). The former involves new physics implementation of Parton showers so the events can be different and extensive validation is needed. Nre tools were provided to help in diagnosing problems quickly and efficiently. Bugs were identified and subsequently fixed by the Pythia authors. ATLAS is using a patched version of Herwig as the Herwig authors could not release a version in time for ATLAS release 11.0.0

The ATLAS physics community is starting to make extensive use of more sophisticated event generators such as MC@NLO, Sherpa and Alpgen. The basic infrastructure to support these has been in place for some time. During this cycle the atlas interfaces were updated to all the new versions. Extensive interactions with the ATLAS user community and the external Monte Carlo authors took place as bugs were reported, diagnosed and fixed.

All event generation will be done by the ATLAS production system to ensure data integrity and reproducibility. New scripts to run all of the types of event generators are being made available and will be tested extensively in the next reporting period.

## 2.2 Software

2.2 Subsystem Manager's Summary

Srini Rajagopalan (Brookhaven National Laboratory)

The physics analysis in preparation for the Rome Physics Workshop in June 2005 has stress tested several components of software tools, including the ability to analyze data in a distributed manner. ATLAS has also gone through a review of each major software component, both architecture and application software. This, coupled with the lessons learned from the Rome physics exercise and Data Challenge 2, has allowed ATLAS to develop a plan that addresses the core of these issues. The Data Challenge 3 has now been broken down into a series of independent commissioning tests of the different software components as part of the Computing System Commissioning (CSC). Each component has been assigned a coordinator who will be coming up with a plan for the commissioning of these tests. In addition to CSC, ATLAS is preparing for the commissioning of the detector. Many of the sub-systems are expected to begin their independent commissioning that would include electronics calibration, monitoring and standalone cosmic ray data beginning 2006 leading to a combined cosmic ray commissioning of the ATLAS detector in 2007. A software plan for detector commissioning has been laid out by many sub-systems and being executed.

The U.S. continues to play a critical role in the ATLAS software. The Research Program Funds have allowed us to add the much needed functionalities to the core software framework, completing the infrastructure for handling detector geometry descriptions and deploy the architecture to save Event Data using LCG products. We have established personnel in calorimeter and muon reconstruction and monitoring software to provide support for software infrastructure needs for these sub-systems. A new PanDA project has been launched in the U.S. that brings together the experiences with the distributed analysis (DIAL) project and the production of large simulation data sample for the Rome physics workshop. PanDA will, as the name says, support both production and distributed analysis. A workshop to discuss the design of such a software framework was held at BNL and rapid prototyping is underway to demonstrate the feasibility of this project.

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| ATLAS Computing TDR & LCG TDR | 30-Jul-05 | -- | 30-Jul-05 | Completed |
| Release 11.0.0 software for Commissioning | 30-Sep-05 | 30-Sep-05 | 15-Dec-05 | Delayed (See #1) |
| Software available for DC3 | 30-Sep-05 | 30-Dec-05 | 15-Mar-06 | Delayed (See #2) |
| Release 12.0.0 for commissioning | 15-Mar-06 | [New] | 15-Mar-06 | On Schedule |

Note #1  Release 11.0.0 has been released. There are ongoing bug fixes which will be completed by the end of the year. In addition, there are minimal functionalities in Release 11.0.0 for use in commissioning. More significant developments geared toward cosmic ray commissioning are ongoing and a major release is expected in February-March 2006.

Note #2  DC2 delayed.... DC3 delayed

2.2.1 Coordination

2.2.2 Core Services

2.2.2.1 Framework

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integration of Seal plug-in Mechanism | 30-Sep-04 | -- | 14-Nov-05 | Delayed (See #1) |
| History & Property Mech Integ | 30-Dec-04 | 14-Sep-05 | 14-Feb-06 | Delayed (See #2) |
| Support for Reconstruction on Demand | 30-Dec-04 | -- | 30-Dec-05 | Delayed (See #3) |
| High-level job configuration design and tools | 14-Sep-05 | 14-Sep-05 | 14-Feb-06 | Delayed (See #4) |
| promote and fix creation-on-demand of services | 14-Sep-05 | -- | 14-Sep-05 | Completed |
| port of Gaudi and Control to gcc 3.4.4 | 1-Feb-06 | [New] | 1-Feb-06 | On Schedule (See #5) |
| python-accessible Property Repository | 1-Feb-06 | [New] | 1-Feb-06 | On Schedule (See #6) |
| Full chain and Interactive Tutorials | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |
| new generation development tool (AthASK evolution) | 8-Feb-06 | 8-Feb-06 | 8-Sep-06 | Delayed (See #7) |
| use GaudiPython to provide interactive access to (selected) framework functionality | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |

Note #1  Done for dictionary loading. Priority lowered for integration in Gaudi

Note #2  not vital for the "Rome workshop" release (10 according to current plans). Persistency using POOL has been tested but requires the new generation of dictionary tools (LCG Reflex) that will become available when the new version of ROOT is released (after release 11)

Note #3  this is going to be needed in particular to support "pick mode" reconstruction from the event display. At this point we do not expect this to be needed before the "Cosmic Ray" data taking in 06

Note #4  Developed prototypes of two new tools. The first is a code generator that starting from the ATLAS C++ librarues, produces python modules describing the properties of each Gaudi object alongside their default values. This is considered a building block of any level job configuration and should be ready in Feb 06 (about one month before rel 12). A prototype high-level job configuration scheme which organizes job configuration in terms of the data needed by the user is being tested using Configurables.

Note #5  32 bit architecture

Note #6  design and provide tools to fill a Gaudi property repository from python. Important to detect immediately syntax errors in job options, and to provide information to job configuration editors and browsers.

Note #7  this work has not yet started because the developer in charge of it has left ATLAS. The new post-doc hire that will take over will start 1-Feb-06

2.2.2.2 EDM Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype Support for Integer Keys | 30-Sep-03 | 30-Sep-05 | 30-Sep-06 | Delayed (See #1) |
| Support for History Objects | 30-Mar-04 | 14-Sep-05 | 14-Feb-06 | Delayed (See #2) |
| Integrate CLID Database Generation | 30-Jun-04 | 14-Sep-05 | 14-Sep-06 | Delayed (See #3) |
| Integration with POOL-Cache Manager | 30-Jun-04 | -- | 31-Dec-05 | Delayed (See #4) |
| support DataLinks across different stores | 23-Feb-05 | 23-Sep-05 | 23-Sep-06 | Delayed (See #5) |
| new DataVector | 31-Aug-05 | 31-Aug-05 | 30-Nov-05 | Delayed (See #6) |
| evaluate the need of object aliases and versioning in StoreGate | 14-Sep-05 | 14-Sep-05 | 14-Sep-06 | Delayed (See #7) |
| speed-up lookup of objects in transient store only | 14-Sep-05 | -- | 14-Sep-05 | Completed |

Note #1  HLT group agreed to reschedule this non-vital performance optimization. It may not be needed at all if Identiable Container iterator access is optimized.

Note #2  transient part complete but no persistency yet. Rescheduled to DC3.

Persistency relies on new version of LCG Reflex not available for release 11.

Note #3  considered non-critical. May be cancelled.

Note #4  this in a non critical optimization, that will probably will be delayed or even canceled

Note #5  mechanism is there "in principle". Need to be tested and fixed as needed. Also need to evaluate the viability of "long" links that can be dereferenced outside their store context.

Note #6  prototype complete and tested. Needs enhancement to LGC Reflex that will be available after release 11.

Note #7  prototype allowing multiple version of a data object completed. Needs input from high-level job configuration before it will take its final form.

2.2.2.3 Detector Description

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| MYSQL Lite DD I/O + replica available | 1-Jul-05 | -- | 1-Jul-05 | Completed |
| Misaligned geometry model available | 1-Sep-05 | -- | 1-Sep-05 | Completed |
| All Identifiers in DD database | 1-Oct-05 | -- | 1-Oct-05 | Delayed (See #1) |
| DC3 Detector Description Quality Control Tests Passed | 1-Jan-06 | -- | 1-Jan-06 | On Schedule |

Note #1  This is still an important item. However this semester we have been mostly busy with preparing the misaligned LAr calorimeter and in fact helping everybody in the LAr get ready to use this in simulation. And so this has been delayed.

Joe Boudreau (University of Pittsburgh)

* A lot of work was done leading up to the use of LAr GeoModel. Most of it was consulting with experts in the Endcap and the Barrel EM calorimeter.

* For example the geometry reshuffling in the barrel was done.

* Also the placement of misalignment transforms all over the LAr, and both in the model and in the database.

* And work on the simulation side to be able to translate the misaligned model into Geant. This was essentially the adaptation to "multiple tree tops". These are not directly related to misalignment but needed to be brought in when we misaligned the barrel.

* Upgrade the geometry of the cryostat barrel.

* Support to Database project. Vakho has now become the database release coordinator. This formalizes what he has already been doing at the 10-15% level.

* Consultation to other groups on the topics of DD database usage, auto geometry configuration.

* Re-enabling certain aspects of the simulation after the transition to GeoModel, such as the calibration hits and the control of run options.

2.2.2.4 Graphics

Joe Boudreau (University of Pittsburgh)

* We now use geometry auto detect in v-atlas. This is probably the first time it's applied within ATLAS.

* We added command line switches to connect to the Oracle database (overriding site configuration).

* We put support for the H6 testbeam. This testbeam now has a dedicated display.

* We put support for a new kind of calib hit in LAr.

* Few more objects added to banks system.

2.2.2.5 Analysis Tools

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| access ROOT analysis tools from python | 14-Sep-05 | -- | 14-Sep-05 | Completed (See #1) |
| access Atlas Data from python | 8-Feb-06 | -- | 8-Feb-06 | On Schedule (See #2) |
| access c++ classes from python | 8-Feb-06 | -- | 8-Feb-06 | On Schedule |

Note #1  pyROOT provides access to most ROOT analysis tools, but still under active development and maintenance to complete the project and respond to new requirements, like the introduction of a python interface to the new LCG Reflex package.

Note #2  works with current lcg reflection API. A new python/C++ interface will have to be developed to support LCG Reflex API (which comes with ROOT5)

2.2.2.6 Grid Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Prototype Implementation for Grid Monitoring Architecture | 30-Sep-03 | 30-Sep-05 | 30-Sep-06 | Delayed (See #1) |
| Job Transformations in Python | 14-Feb-06 | [New] | 14-Feb-06 | On Schedule (See #2) |

Note #1  This is work is partly covered under Grid Tools and Services to provide monitoring of jobs submitted on the Grid. No capability within Athena exists due to lack of any assigned resources.

Note #2  translate existing job transformations (and supporting tools) to python

2.2.3 Database

David Malon (ANL)

Areas of emphasis in this reporting period were distributed data management, development of infrastructure in support of schema evolution, re-evaluation of event-level metadata infrastructure and requirements based upon lessons learned from the successful deployment of tag database infrastructure for the June Rome physics workshop, and evaluation of next-generation database replica deployment strategies based upon proposed LCG 3D project deliverables and Open Science Grid edge services plans (to be prototyped in the coming quarters). Prioritization has been driven principally by the requirements and timetable of the international ATLAS Computing System Commissioning (CSC) initiative.

The distributed data management effort, an area of critical need, was successfully augmented late in this reporting period by a strong new hire at Brookhaven, Alexei Klimentov.

2.2.3.1 Server and Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Support logical connection naming, and logical/physical connection mapping | 8-Jul-05 | -- | 8-Jul-05 | Completed |
| Deployment of connection indirection layer | 10-Oct-05 | -- | 10-Oct-05 | On Schedule |
| Architecture for database deployment on OSG | 14-Nov-05 | -- | 14-Nov-05 | On Schedule |
| 3D testbed slice test (Tier0/1/2) | 12-Dec-05 | -- | 12-Dec-05 | On Schedule |
| Grid database access test using transport-level security | 12-Dec-05 | -- | 12-Dec-05 | On Schedule |
| User-level documentation for access to database services | 27-Mar-06 | [New] | 27-Mar-06 | On Schedule |

2.2.3.2 Common Data Management

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena I/Fs for Physical Placement Control Defined | 30-Sep-03 | -- | 15-Sep-05 | Completed (See #1) |
| Support for Multiple Transaction Contexts | 30-Jun-04 | -- | 14-Nov-05 | Delayed (See #2) |
| Support for Placement Control | 30-Sep-04 | -- | 7-Nov-05 | Delayed (See #3) |
| Support for Cross-Type Conversion | 30-Dec-04 | -- | 14-Nov-05 | Delayed (See #4) |
| Consistent I/O control model implemented for event and non-event data | 26-Sep-05 | -- | 26-Sep-05 | Completed |
| Don Quijote tools for data aggregation | 1-Nov-05 | [New] | 1-Nov-05 | On Schedule |
| Transformation and software release descriptions in database | 1-Nov-05 | [New] | 1-Nov-05 | On Schedule |
| Schema evolution machinery deployed, with examples | 21-Nov-05 | -- | 21-Nov-05 | On Schedule |
| Dataset selection catalog prototype implemented | 15-Dec-05 | [New] | 15-Dec-05 | On Schedule |
| Technology evaluation and selection for DDM catalogs | 27-Feb-06 | [New] | 27-Feb-06 | On Schedule |
| User-level documentation for Athena I/O infrastructure | 27-Mar-06 | [New] | 27-Mar-06 | On Schedule |

Note #1  Pending January 2004 DC2 event store readiness workshop.

Delayed until after DC2.

31 December 2004: On schedule with respect to revised forecast.

31 March 2005: To be decided at April 2005 event store workshop.

30 June 2005: Deferred until POOL infrastructure improves.

30 September 2005: Placement control by type and key delivered.

If additional functionality is required by new physics analysis use cases, an additional milestone will be entered.

Note #2  delayed until after DC2

31 December 2004: On schedule with respect to revised forecast.

31 March 2005: Revised schedule pending April 2005 event store workshop.

30 June 2005: Requires additional POOL functionality.

30 September 2005: This may be delayed in the next quarter until a 2006 release, based upon international ATLAS release priorities.

Note #3  Delayed until after DC2.

31 December 2004: On schedule with respect to revised forecast, but delivery date is subject to reprioritization of workload to support 2005 ATLAS physics workshop.

31 March 2005: Delayed to meet international ATLAS schedule (not needed for Rome production). Revised schedule pending April 2005 event store workshop.

30 June 2005: Deferred until POOL infrastructure improves.

30 September 2005: On schedule with respect to forecast.

Note #4  31 December 2004: Schedule for this task will depend upon reprioritization of functional additions in support of the 2005 ATLAS Physics Workshop.

31 March 2005: Revised schedule pending April 2005 event store workshop.

30 June 2005: Proper implementation requires improvements to ROOT. Requirements have been forwarded to the ROOT team via the LCG Architects Forum.

On schedule with respect to forecast, but ROOT delivery schedule may delay delivery of some of the desired functionality until next year.

2.2.3.3 Event Store

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Unique EDO Identification Infrastructure | 30-Sep-04 | -- | 31-Jan-06 | Delayed (See #1) |
| Job-level history object and configuration persistence prototype | 2-Oct-05 | -- | 2-Oct-05 | On Schedule (See #2) |
| Processing stage output to registration streams | 2-Oct-05 | 2-Oct-05 | 23-Sep-05 | Completed |
| Event store I/O performance tuning | 12-Dec-05 | -- | 12-Dec-05 | On Schedule |
| Processing stage specification as a retrieval scope | 19-Dec-05 | -- | 19-Dec-05 | On Schedule |
| Schema evolution infrastructure prototype based upon transient/persistent separation | 27-Jan-06 | [New] | 27-Jan-06 | On Schedule |
| Athena interface to set/get technology-specific attributes (POOL) | 27-Feb-06 | [New] | 27-Feb-06 | On Schedule |
| Infrastructure to support stream- and run-level metadata | 27-Mar-06 | [New] | 27-Mar-06 | On Schedule |

Note #1  Delayed until after DC2.

31 December 2004: On schedule with respect to revised forecast.

31 March 2005: Priority reduced (not needed for Rome physics workshop). Revised schedule to be determined at April 2005 event store workshop.

30 June 2005: ATLAS-wide reprioritization: deferred until after Release 12

30 September 2005: Further delay is possible, as Release 12 itself is delayed and priorities for Release 13 are reassessed.

Note #2  30 September 2005: Actual delivery may be later in the quarter because the prototype requires new versions of LCG dictionary software that will not be delivered to us until later in the quarter.

2.2.3.5 Collections, Catalogs, Metadata

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Athena Interface/Read/Write Access to Collection-Level Metadata | 30-Dec-03 | -- | 19-Dec-05 | Delayed (See #1) |
| Integration of Collection Support & Bookkeeping | 30-Mar-04 | -- | 19-Dec-05 | Delayed (See #2) |
| Tag database support for access to upstream processing stages | 24-Oct-05 | -- | 24-Oct-05 | On Schedule |
| Performance evaluation of collection-based versus sequential (file-based) event access | 16-Dec-05 | [New] | 16-Dec-05 | On Schedule |
| Collection replication tests using LCG 3D infrastructure | 19-Dec-05 | -- | 19-Dec-05 | On Schedule |
| Tag database infrastructure for Tier0 scaling tests | 16-Jan-06 | [New] | 16-Jan-06 | On Schedule |
| Evaluation of strategies for support of variable-length structures in tags | 27-Feb-06 | [New] | 27-Feb-06 | On Schedule |

Note #1  Pending January 2004 DC2 event store readiness workshop.

Delayed until after DC2. Not needed for combined test beam because this metadata will also be available from the conditions database.

31 March 2005: Date subject to revision after April 2005 event store workshop.

31 December 2004: Delayed once again because of ATLAS DC2 delays.

30 June 2005: Deferred until integration with bookkeeping and new distributed data management infrastructure is possible.

30 September 2005: This milestone is still pending integration with bookkeeping and the new distributed data management effort, some of which may be handled by the Orsay and Glasgow groups.

Note #2  Principally a Grenoble responsibility, with some U.S. involvement on the collections end. On the critical path for DC2.

31 December 2004: Delayed once again because of DC2 delays.

31 March 2005: Descoped by international ATLAS from DC2. Revised schedule to be determined at event store workshop in April 2005.

30 June 2005: Delayed until role of AMI (not a U.S. product) in overall ATLAS data management system is decided.

30 September 2005: 30 June 05 comment stands.

2.2.4 Application Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Geometry Model Based Detector Description used for Reconstruction | 30-Sep-03 | 30-Dec-05 | 1-Oct-05 | Delayed (See #1) |
| Prototype Definition of Event-Level Physics Metadata (tag) | 30-Dec-03 | -- | 30-Dec-05 | Delayed (See #2) |
| RTF Recommendations Implemented | 30-Dec-03 | -- | 1-Oct-05 | Delayed (See #3) |
| Access to Alignment in Reconstruction | 30-Sep-04 | 30-Jun-05 | 30-Dec-05 | Delayed (See #4) |
| Realistic ATLAS simulation | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule (See #5) |
| Reconstruction for Commissioning | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule (See #6) |

Note #1  Mostly done... LAr GeoModel under implementation. Expect completion in October 2005.

Note #2  This is in progress - An Event Tag task force has been setup by ATLAS to address this. Expect first draft by the end of the year.

Note #3  Well in progress. Calorimeter completed, RTF recommended EDM for Tracking delayed due to lack of manpower.

Note #4  Access to alignment constants are being implemented.

Note #5  Introducing realism in the ATLAS simulation software including misalignment and detector imperfections.

Note #6  The reconstruction software needed for commissioning exercises including the cosmic ray commissioning.

2.2.4.1 Simulation

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Update material in GEANT4 simulation to match engineering design. | 31-Jan-06 | [New] | 31-Jan-06 | On Schedule |

2.2.4.2 Subsystem Reconstruction

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Muon implementation of Tracking classes. | 1-Oct-05 | -- | 1-Oct-05 | On Schedule |

2.2.4.3 Combined Reconstruction

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Validate Rome/Initial layout reconstruction. | 1-Apr-05 | -- | 1-Apr-05 | Completed |
| Combined Inner Detector and Muon System use of Tracking classes. | 1-Oct-05 | -- | 1-Oct-05 | On Schedule |

2.2.4.4 Analysis

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Introduce tag database | 1-Jun-05 | 1-Dec-05 | 1-Jun-05 | Completed |
| US -Base Analysis Effort for Rome workshop completed | 6-Jun-05 | -- | 6-Jun-05 | Completed |
| Improve data access to AOD and ESD | 1-Oct-05 | -- | 1-Oct-05 | On Schedule |
| Event selection with tag database | 1-Jan-06 | 1-Jan-06 | 1-Jan-05 | Completed |

2.2.4.5 Trigger

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Define US Role in Trigger Software. | 10-Mar-05 | -- | 15-Oct-05 | Delayed (See #1) |
| Host Trigger Workshop at UC Irvine. | 10-Mar-05 | -- | 15-Apr-05 | Completed |

Note #1  Ongoing discussions with ATLAS TDAQ group, hopefully to conclude during the TDAQ workshop in Mainz on Oct. 15.

2.2.4.6 Combined Testbeam Software

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Analysis of CTB data for Rome Physics Workshop. | 6-Jun-05 | -- | 6-Jun-05 | Completed |

2.2.5 Software Support

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Release version 1.0 of NICOS with the support for project-oriented builds | 30-Sep-05 | -- | 30-Sep-05 | Completed |
| Install and support ATLAS releases and associated external software at BNL | 30-Dec-05 | -- | 30-Dec-05 | On Schedule |
| Release first stable version of ATN (ATLAS Testing Nightly Tool) | 30-Dec-05 | -- | 30-Dec-05 | On Schedule |
| Support ATLAS software nightly builds at BNL and CERN | 30-Dec-05 | -- | 30-Dec-05 | On Schedule |

Alexander Undrus (Brookhaven National Laboratory)

During this quarter NICOS, control system of ATLAS nightly builds, was upgraded to new version 1.0 supporting the project-oriented nightly builds. The project builds were synchronized according to their dependency and the build status was posted on the "global" NICOS web page. By the end of the quarter 21 different nightly builds of ATLAS software were performed daily at CERN (including project builds). The nightly builds were checked with about 70 unit and integration tests performed in the ATN testing framework integrated with NICOS. At BNL new ATLAS software releases were promptly installed, usually in one to two days after CERN installation. The mirrors of ATLAS CVS repository and ATLAS nightly builds were supported. The LXR server, alxr.usatlas.bnl.gov, provided the collaboration-wide service for fast searches of ATLAS software.

## 2.3 Facilities

2.3 Subsystem Manager's Summary

Razvan Popescu (Brookhaven National Laboratory)

The FY05 recruitment augmented the support to operations, workload management development, storage, databases and networking.

The Tier1 center obtained approval to increase ESNET connectivity to 20Gb/sec by Spring '06 and proceeded to prepare the necessary internal backbone upgrade.

Using the experience gained during the successful participation to Service Challange III, the storage system capability will be doubled by spring '06, in time for Service Challenge IV.

During this quarter, we saw the start-up of operations of the SouthWest Tier 2 (SWT2) consisting of the University of Texas at Arlington (UTA), Oklahoma University (OU), Langston University (LU), and the University of New Mexico (UNM).

The UTA procurement process for a 166 compute nodes cluster and 20TB of storage had been started. BU negotiated the purchase of a 56 processor blade center from IBM. The system has been delivered at the end of the quarter.

As preparation for the roll-out of the Tier2 cluster, UTA has used the existing facility, the Distributed and Parallel Computing Cluster (DPCC), to support ATLAS activities. This has included the installation of a prototype DCache system for testing data management issues between Tier1 and Tier2 sites. UTA has also participated in the roll-out of the DQ2 data management system that will be used for the new US-ATLAS data production system.

Progress continues on developing advanced networking capabilities through projects like UltraLight, Terapaths, Lambda Station and OSCARS. Demonstrations were prepared to highlight these research projects at Supercomputing in Seattle. Terapaths has demonstrated QoS augmented data transfers betweeen Brookhaven and Michigan as part of this preparation.

A preproposal to Open Science Grid was prepared for networking. Brookhaven, Caltech, Fermilab, University of Florida and the University of Michigan all collaborated on this preproposal, which focuses on delivering a managed network component to OSG. We expect to have a response during the next quarter.

GTS delivered release of Capone version 1.2: this is the final planned production release which is able to scale to more then 4000 jobs and which supports job state persistency necessary for crash recovery. It will cover ATLAS needs until PanDA becomes production operational.

After running DC2/Rome production for 1.5 years, ATLAS grid production has been shut down during this quarter, for a long awaited work on grid tools and services. A new version of workload management system is being developed in the US -- the PanDA project. The PanDA (Production and Distributed Analysis) system is using a new design taking advantage of the DDM (Distributed Data Management) system being developed ATLAS-wide, and integrating with the Distributed Analysis system.

2.3.1 Tier 1 Facility

2.3.1.1 Management/Administration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FY05 BNL Tier1 Facility Recruitment | 30-Jun-05 | -- | 30-Jun-05 | Completed |

Razvan Popescu (Brookhaven National Laboratory)

The FY05 recruitment had been completed. Four new hires have been effectively integrated in the operations support, with assignments on production control development and support, general operations, dCache and DataBases support and development and networking.

2.3.1.2 Tier 1 Fabric Infrastructure

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Review and upgrade infrastructure services | 31-May-05 | -- | 31-May-05 | Completed |
| Begin Procurement of expanded LAN Infrastructure | 1-Dec-05 | [New] | 1-Dec-05 | On Schedule |
| Expanded LAN Infrastructure Order Placed | 15-Dec-05 | [New] | 15-Dec-05 | On Schedule |
| Begin Installation of Expanded LAN Infrastructure | 15-Jan-06 | [New] | 15-Jan-06 | On Schedule |
| Expanded LAN Infrastructure Operational | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule |
| Expanded Facility Power and Cooling Capacity Available | 31-Mar-06 | [New] | 31-Mar-06 | On Schedule |

Razvan Popescu (Brookhaven National Laboratory)

The U.S. ATLAS infrastructure services have been moved to a more resourceful hardware platform and updated.

In parallel with the upgrade of the BNL's (ESNET) WAN connectivity to 20Gb/s, the laboratory's LAN infrastructure will be modified to support the increased bandwidth and provide extended services to the U.S. ATLAS facility.

2.3.1.4 Tier 1 Storage Systems

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Procurement of New Tape Subsystem | 1-Dec-05 | [New] | 1-Dec-05 | On Schedule |
| New Tape Subsystem Order Placed | 15-Dec-05 | [New] | 15-Dec-05 | On Schedule |
| Begin Installation of New Tape Subsystem | 15-Jan-06 | [New] | 15-Jan-06 | On Schedule |
| New Tape Subsystem Operational | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule |

2.3.1.5 Tier 1 Wide Area Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Service Challenge III | 31-Jul-05 | -- | 31-Jul-05 | Completed (See #1) |
| OSG 0.4.0 Deployed and Operational | 31-Dec-05 | [New] | 31-Dec-05 | On Schedule |
| Service Challenge III - service phase | 31-Dec-05 | [New] | 31-Dec-05 | On Schedule |
| All required SC4 Software for Baseline Services Deployed | 31-Jan-06 | [New] | 31-Jan-06 | On Schedule |
| BNL Wide Area Network Upgrade Operational | 28-Feb-06 | [New] | 28-Feb-06 | On Schedule |
| 10Gbs BNL Tier 1 <-> Tier 0 Dedicated Connectivity Operational | 31-Mar-06 | [New] | 31-Mar-06 | On Schedule |

Note #1  SC3 -- throughput phase -- was completed in time, the Tier1 demonstrating its ability to sustain disk-disk data streams in excess of 120MB/s, between BNL and CERN, while sending data downstream, to the Tier2 facilities.

2.3.1.6 Tier 1 Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| OSG Support Center | 15-Aug-05 | -- | 15-Aug-05 | Completed (See #1) |
| 500CPU, 150Disk, 200WAN=>Disk, 300Tape,200WAN=>Tape | 15-Feb-06 | [New] | 15-Feb-06 | On Schedule |

Note #1  The U.S. ATLAS OSG Support Center at BNL had begun its operations providing direct support to U.S. ATLAS users and point-of-contact service for interactions with other VOs.

2.3.2 Tier 2 Facilities

Kaushik De (University of Texas at Arlington)

During this quarter, we saw the start-up of operations of the SouthWest Tier 2 (SWT2). The SWT2 consists of the University of Texas at Arlington (UTA), Oklahoma University (OU), Langston University (LU), and the University of New Mexico (UNM). The SWT2 has started periodic planning workshops, the first of which took place in August at UTA. The next one is scheduled at OU. All purchases, software infrastructure and usage activities for the SWT2 will be coordinated through these technical meetings.

The SWT2 has selected Dell as the vendor for the first hardware purchase. Numerous meetings were held with Dell HPC division to iterate on the design of the cluster. Dell is providing substantial discounts to SWT2. We have decided to purchase the same basic system for all locations, even though the order is placed by individual campuses. OU will acquire a cluster which is 25% of the size of the UTA cluster, using DOE-Epscor funds. LU is also buying a smaller cluster.

Hardware and Physical Infrastructure news (UTA):

We have placed the order for the initial hardware for UTA’s portion of the Southwestern Tier2 facility. The cluster consists of 160 dual-processor compute nodes, six dual-processor head nodes, and 20TB of network storage. The compute nodes include two 3.2GHz Pentium Xeon processors, 4GB RAM, and a 160GB SATA disk drive. The head nodes use the same processors as the compute nodes but have 8GB RAM, and dual 73GB SCSI disk drives in a RAID1 configuration.

The network storage is comprised of a 20TB SAN system based on SATA disk drives from DataDirect Networks along with 6 dedicated I/O nodes to serve the storage to the cluster. An additional 16TB of storage will be created in a DCache pool by using a portion of the storage on each compute node.

The cluster will be housed at the UTA Computing Center, a state-of-the-art computing facility, that provides 24X7 monitored operations. The amenities of the facility include service from two separate power grids, a 350KVA generator, and redundant network links. UTA has just completed the construction of a new Chemistry and Physics Building that will be used for housing additional computing hardware for the SWT2.

Installed Software (UTA):

As preparation for the roll-out of the Tier2 cluster, UTA has used our existing facility, the Distributed and Parallel Computing Cluster (DPCC), to support ATLAS activities. This has included the installation of a prototype DCache system for testing data management issues between Tier1 and Tier2 sites. UTA has also participated in the roll-out of the DQ2 data management system that will be used for the new US-ATLAS data production system.

We have also installed the ATLAS analysis system known as DIAL at DPCC to support DIAL’s development. DPCC allows the developers to experiment with a remote cluster and refine usage patterns related to distributed analysis. DPCC also allows the developers to integrate DIAL with the local batch system manager PBS.

DPCC will begin soon an OS upgrade process to better support the latest ATLAS software releases. We are replacing the current operating system with Red Hat Enterprise Linux 3.

Hires (UTA):

Patrick McGuigan was hired as the system administrator for the UTA cluster.

Usage (UTA):

DPCC has been partitioned into two separate clusters that allows us to continue supporting on-going MC production as well as help prepare for the upcoming data challenges. In addition, DPCC provided a dedicated gatekeeper for OSG integration testbed.

Hardware Infrastructure (OU and LU):

A 40 node cluster with the same configuration at UTA was ordered from Dell. Delivery is expected early in the next quarter. LU also placed their order.

Discussions are underway regarding a second A/C unit and UPS at the Ou computing center for the new SWT2 cluster.

Software (OU):

OU has OSG 0.2.1 installed on both the OUHEP test cluster and OSCER, as well as dCache and DQ2 at OUHEP. dCache is fully functional, as far as I can tell, but DQ2 needs some more configuration, which hopefully shouldn't take much longer now that I have most of it pacmanized.

Hire (OU):

Two positions have been advertised.

Usage (OU):

Existing cluster are being used for OSG testing and integration, including dCache and DQ2, and also for ATLAS production, and hopefully very soon for Panda testing and then production as well, as soon as DQ2 is up and running.

2.3.2.1 Tier 2-A "Currently Indiana/Chicago Prototype"

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| OSG Integration Installation testing | 1-May-05 | -- | 1-Jun-05 | Completed |

2.3.2.2 Tier 2-B "Currently Boston Prototype"

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Integrate operations with US ATLAS Support Center | 31-Aug-05 | -- | 31-Aug-05 | Completed |
| Service Challenge III | 31-Aug-05 | -- | 31-Aug-05 | Completed |
| dCache Installation | 15-Sep-05 | 15-Sep-05 | 15-Jan-06 | Delayed (See #1) |

Note #1  The dCache installation had to yield resources to other system upgrades. The deployment was not critical at this phase.

Saul Youssef (Boston University)

In the past quarter at we have upgraded our main cluster to SL3 and installed OSG for grid middleware. We've negotiated a purchase of an additional 56 processor blade center with IBM. The center has just been delivered at the end of this quarter.

Our site has participated in the ATLAS service challenges, has been used as a site for PanDA testing and production and as a production site for individual ATLAS users.

2.3.3 Wide Area Network

Shawn McKee (University of Michigan)

The T0-T1 Networking meeting was held at CERN to discuss the future LHC OPN (Optical Private Network). Four working groups were convened to provide a roadmap for this network: Routing, Security, Operations and Monitoring. A followup meeting will occur during Supercomputing 2005. Shawn McKee, US ATLAS Networking, is organizing the Monitoring activity for the LHC OPN.

Progress continues on developing advanced networking capabilities through projects like UltraLight, Terapaths, Lambda Station and OSCARS. Demonstrations are being prepared to highlight these research projects at Supercomputing in Seattle. Terapaths has demonstrated QoS augmented data transfers between Brookhaven and Michigan as part of this preparation.

A preproposal to OSG (Open Science Grid) was prepared for networking. Brookhaven, Caltech, Fermilab, University of Florida and the University of Michigan all collaborated on this preproposal, which focuses on delivering a managed network component to OSG. We expect to have a response during the next quarter.

The HENP (High-Energy/Nuclear Physics) SIG at Internet2 didn't meet during the Fall Internet2 meeting and will next convene during the Spring 2006 meeting.

2.3.4 Grid Tools & Services

2.3.4.2 Workflow Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| PANDA Prototype | 15-Nov-05 | [New] | 15-Nov-05 | On Schedule |
| Maintain CAPONE workflow management solution | 31-Dec-05 | [New] | 31-Dec-05 | On Schedule |
| PANDA Production Ready | 15-Jan-06 | [New] | 15-Jan-06 | On Schedule |

Razvan Popescu (Brookhaven National Laboratory)

Maintenance of the USATLAS Capone executor:

- Release of Capone version 1.2: this is the final planned production release which is able to scale to more then 4000 jobs and which supports job state persistency necessary for crash recovery. It will cover ATLAS needs until PanDA becomes production operational.

- Maintenance of version 1.2, improving usability, adding minor features, fixing bugs.

- Adapted to changes due to OSG sites (Capone was initially designed for Grid3 and is currently working with OSG Production and ITB grids).

- Improved documentation and provided user support.

Programming for USATLAS PanDA executor:

- Development of the Brokerage package.

- Initial design and development of the JobScheduler.

- Packaging of the PanDA packages (PanDA JS, PandaSrv, PandaJDE, PanDA, auxiliary DQ-Client). Provided the initial version of the packaging scripts and Pacman file templates.

2.3.4.3 Data Services

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Deployment, Testing, Evaluation of DMS3 Server | 30-Mar-05 | -- | 1-May-05 | Completed |

2.3.5 Grid Production

Kaushik De (University of Texas at Arlington)

After running DC2/Rome production for 1.5 years, ATLAS grid production has been shut down during this quarter, for long awaited work on grid tools and services. A new version of Prodsys is being developed. In the U.S., the PanDA project was started. The PanDA (Production and Distributed Analysis) system is being developed from scratch, with a completely new architecture, to take advantage of the DDM (Distributed Data Management) system being developed ATLAS-wide, and to integrate better with Distributed Analysis. Further details can be found in: https://uimon.cern.ch/twiki/bin/view/atlas/Panda

Grid production with the first generation Capone production system continued at a reduced level. Capone will continue to be used for production until PanDA is certified for production services.

OSG testbed moved to production services at most US ATLAS sites. Many of these sites are now in the process of OS upgrade to SLC3 or RHEL3.

## 3.1 M&O Silicon

Alex Grillo (UCSC)

The production of spare pixel modules and subassemblies (disk sectors) began during this reporting period. The production of spare pixel optical boards started at Ohio State at the end of September. Pixel support tube is at CERN and integration with SCT barrel has succeeded. Installation of Type 4 cables is in progress in the CERN cavern.

All four SCT barrels are now at CERN and have passed acceptance testing. Three of the four barrels have been inserted into the Outer Thermal Enclosure. Services and shielding issues continue to require attention and consultation as their final construction and installation progress.

The ROD software has been functional for pixels and SCT for some time. Modifications are underway to improve performance of the software.

3.1.1 Pixels

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start of Pre-Operations for Pixels | 1-Oct-05 | 6-Nov-05 | 1-Oct-05 | On Schedule |

Murdock Gilchriese (Lawrence Berkeley Laboratory)

The production of spare pixel modules and subassemblies (disk sectors) began during this reporting period.

3.1.1.1 Pre-Operations

Maurice Garcia-Sciveres (Lawrence Berkeley Laboratory)

LBL Pixel Pre-Operations

Production wafer thinning & dicing

Running smoothly, but chip testing after icing is manpower limited. The number of chips needed at the bump vendor has steadily increased as spares have been added. An estimated 24 wafers must still be processed, which could be done in 8 weeks by a 1FTE effort. However, the present level of 2 part-time students will likely extend for 12 more weeks to handle this load.

Fixturing/equipment/facilities

Two chillers in the module test setup have failed. This caused a roughly 2 week delay in module testing. One chiller has been repaired using parts from the other one. This is enough to return to full operation (done), but there is now no spare.

Building 77 clean room occupation has started. Disk 1C is not in the clean room, and production service panels will be moved in as soon as final room preparations are complete.

Hot Modules

Barrel module testing continues, albeit with some delay (see above)

Sector and Disk Production

Disks 1C, 2C, 3C, and 2A are now loaded and tested. Disk 2A is waiting for final survey. None have had cooling pipes added yet. Disk 1A loading will be next, however, all 8 sectors for it are not yet available. There has been a 3-4 week delay in loading of modules on sectors due to lack of bare sector availability. This problem has now been solved and sector loading has resumed. The number of new sectors needed to complete disk 1A is 4, with the first of them already in progress and to be finished this week. However, they need to be tested and accepted before they can be “certified” for D1A use. We therefore can fully load neither D1A nor D3A until all D1A sectors have been accepted (because one of the existing, presumed D3A sectors may have to be promoted to D1A if something goes wrong with one of these 4 outstanding sectors). All modules for these 4 outstanding sectors have been fully tested and identified. Sector loading and testing is now expected to proceed at 1/week rate.

Type 1 services (in support tube)

All terminated wire harnesses have been received from LEMO USA. The PP0 boards for the “A” side have all been completed and inspected. The bare boards for the “C” side PP0 have been fabricated and received; loading and flex lamination are in progress. The cutting of wire harnesses and terminating to the PP0 boards is in progress at bldg. 77A. The rate is 1.5/week. The A-side termination is 40% complete.

One of two prototype outer octants has been tested with real modules operated with at modified TurboDAQ setup. All circuits are fully functional. A long term high voltage test is planned for a production service panel.

Activities at CERN

Pixel support tube is at CERN and integration with SCT barrel has succeeded.

Installation of Type 4 cables is in progress in cavern.

Murdock Gilchriese (Lawrence Berkeley Laboratory)

The production of spare optical boards started at Ohio State at the end of September.

3.1.2 SCT

Alex Grillo (UCSC)

All four barrels are now at CERN and have passed acceptance testing. Three of the four barrels have been inserted into the Outer Thermal Enclosure. The fourth barrel will be inserted in October followed by preparations for insertion into the TRT.

Cable testing at CERN is underway and will require a substantial amount of work for the collaboration. Two UCSC people are contributing to that effort.

Many issues regarding grounding ties for enclosures and supports, patch panel connections and cable clamps, cable splice, testing and installation details, heater patch panels, and power supply testing and installation still require attention and are being worked by regular phone meetings and visits to CERN.

3.1.2.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Pre-Operations for all Barrels running together | 1-Aug-05 | -- | 11-Nov-05 | Delayed (See #1) |
| Pre-Operations of SCT Inside ID | 1-Oct-05 | -- | 28-Feb-06 | Delayed (See #2) |

Note #1  The schedule for pre-operations testing at CERN is running well. All four barrels have been delivered to CERN but they were delayed slightly relative to the original schedule. With this delivery schedule of barrels, the completion of the four barrel assembly and planned tests has now slipped to mid-November.

Note #2  Completion of the four barrel assembly having slipped to mid-November, the expected date for completion of integration of barrel SCT and barrel TRT along with planned tests is end of Feb-06, well before deadline for lowering into UX15 in March.

Alex Grillo (UCSC)

With the arrival of barrels 5 and then 4, Forest again traveled to CERN in July to help with the acceptance testing. Sofia remains stationed at CERN.

The acceptance testing was completed successfully but with only partial functional electrical testing of each barrel because of limited test equipment in SR1. Continuity tests of all harness and modules did find a few problems which were corrected. Barrel insertion into the Outer Thermal Enclosure was initiated with all but the one barrel installed prior to quarter end. The final barrel will be installed in early October followed by insertion of the whole SCT Barrel section into the TRT.

Sofia and Forest have also been taking shifts testing power cables as they are delivered to CERN. This is an enormous job with an initial estimate of 6400 man-hours required to complete all cable testing. The estimate is being re-evaluated but all SCT institutions are being asked to contribute manpower for this effort.

In other areas of SCT Electronics Coordination, Ned and Alex have been dealing with almost daily issues including grounding ties for enclosures and supports, patch panel connections and cable clamps, cable splice, testing and installation details, heater patch panels, and power supply testing and installation. Melbourne finally accepted responsibility to complete the testing of the power supply crate backplanes that they supplied and are sending personnel to do the testing. Sofia modified PVSS software and dummy load boards so that the testing could be accomplished efficiently once the personnel arrived.

3.1.3 RODs

Abraham Seiden (UCSC)

The ROD software has been functional for pixels and SCT for some time. Modifications are underway to improve performance of the software.

3.1.3.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Pre-Operations of RODs with Full SCT Barrel | 1-Aug-05 | -- | 1-Sep-05 | Completed |
| Pre-Operations for RODs with Pixel System | 1-Oct-05 | 1-Oct-05 | 1-Dec-05 | Delayed (See #1) |

Note #1  The software has most of the functionality needed. Updates are in progress to incorporate needed functions

Abraham Seiden (UCSC)

The software has most of the functionality needed. Updates are in progress to incorporate needed functions

3.1.3.1.1 RODs Pre-operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Firmware and Software Complete for Macro Assembly Site (Wisc) | 15-Mar-05 | 15-Aug-05 | 15-Mar-05 | Completed (See #1) |
| SCT/Pixel DAQ Functional with ROD (Wisc) | 15-Jul-05 | 15-Jul-05 | 15-Dec-05 | Delayed (See #2) |
| ROD Integrated into Consolidated Beam Test (Wisc) | 15-Aug-05 | -- | 15-Aug-05 | Completed (See #3) |

Note #1  The current firmware and software is functional and in use by the SCT. The code is in the long term process of being updated. This process will continue for several years.

Note #2  The software is functional. Software updates are being performed to add needed changes.

Note #3  The software is integrated with the tests at CERN. It is being updated as part of the long-term process of improving the code.

## 3.2 M&O TRT

3.2 Subsystem Manager's Summary 	Harold Ogren (Indiana University)

This period of the TRT work was extremely active. All of the modules have been installed, so the major work was testing. The testing can be divided into two major efforts- Service Systems commissioning, and electronics commissioning.

Service system commissioning

Active gas:

Each of the installed modules is supplied with an active ionization gas through two ports on one end. The gas flows through the module and exits through two ports on the back end. In both front and back ends the two ports are connected to a "Y" which will be attached to an active gas manifold that services 6 modules. The initial testing was a pressure check that verified the gas tightness of each module as it was installed. This is done by using an argon gas mixture. Each module was overpressured by 0.3 PSI, and held for about 12 hours, monitored with a very sensitive pressure meter. All the modules passed the criteria of 0.1 mBar/Bar-min. This work was completed in June, 2005 for the individual modules. Then, when the active gas manifolds arrived during the August- September period, the same test was done with groups of three modules attached to the manifold to test that all connections were tight. This work is continuing in the October period as manifolds were replaced and removed. (a topic that will be covered later.)

CO2 flushing gas:

Three modules in a "stack" have CO2 gas flowing serially through them with the input at the small radii (module of type 1) and the exit into atmospheric pressure at the outer radii of module type 3. As the final layer of modules (Type 3) was inserted, the chain of modules was tested for good flow of CO2. This was completed in June, 2005. Further testing of the connections of the flexible tubing that attaches as the small radii and connects to the CO2 source in PPB1 will be done in the December when the final services (cooling ) are attached.

Cooling manifold

The electronics must be cooled during operation. This is done by flowing fluorinert at about 18o C through a triangular cooling plate on the face of each module. There are two triangular plates for each module end. The electronics printed circuit boards are attached to the cooling plates and thermal compound is used to give a good thermal contact to the plates. The fluorinert is supplied the plate by a cooling manifold. The fluid flows first through one triangle, then with a PEEK jumper feeds into the other triangular plate and finally passes through the entire module length in a PEEK tube, exits at the far end of the module ( cooling the shell of the module internally), and attaches to a cooling return manifold. Each module has electronics at either end, so there is a return and supply at both ends, and two PEEK tubes passing through each module for internal cooling.

The cooling manifold was designed to be made from stainless steel with brazed connections for all ports to the PEEK tubing.

The manifold was installed and tested during the period August and September. The manifold was divided into quadrants, each supplying and returning cooling from 8 modules. The final sectors were installed on September 15, 2005. Initial pressures tests on the sectors were made before installation and all were leak tight when installed. Once installed, the commissioning activities began, with a flow test of all lines which requires measuring pressures and flows of fluorinert in all parts of the manifold. This was completed.

Cooling Manifold Leaks

During the remainder of the month of September the cooling was used in sectors by the electronics group to systematically look at all stacks of modules and determine if the electronic channels were working and whether the noise was acceptable. This work was called Sector testing. At the very beginning of October a small leak appeared in one of the cooling connections being used for the sector testing. The manifold was removed and a series of tests were begun on the quality of brazed joints. Details of further tests will be given in the future M&O reports, but the entire cooling manifold integrity is in question and will have to be removed and tested.

Electronics Commissioning

Sector testing is now well advanced. There is a clear set of tools and procedures in place for verifying sectors and about 1/4 of the barrel has been covered. This requires that the cooling and services are running for a group of 3 or 6 modules. The tools that have been developed allow us to examine the thresholds and rates of all channels, and record them in a data base.

System tests

A sector of modules in the upper quadrant and a sector in the lower quadrant have been chose for cosmic ray tests, which constitutes our on going system test of the barrel. We are developing tools to measure efficiency, resolution, and alignment and then to port those tools to the end cap.

We are also checking out production wiring harnesses and pre-production patch panels against the end cap and barrel structures - so far everything is looking good.

3.2.1 TRT-Subsystem

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Completed TRT Barrel | 1-Jan-05 | -- | 15-Sep-05 | Completed |
| Install ID in Detector/Start Commissioning Entire ID | 1-Oct-05 | -- | 1-Oct-05 | On Schedule |

3.2.1.1 TRT Pre-Operations

3.2.1.1.4 TRT-6 mod-check

Rick Van Berg (University of Pennsylvania)

System and sector testing is now well advanced. There is a clear set of tools and procedures in place for verifying sectors and about 1/4 of the barrel has been covered.

The system test is running in parallel and we have discovered a pattern of high noise channels near the HV foils on the sides of Module 3s. The problem has been traced to high analog return impedance in that area and we have demonstrated that installing RF shorts across the HV foils in the gaps provided for that purpose eliminates the problem - the question being investigated at the moment is how to install those RF shorts in the most efficient fashion given the constricted area.

We have also started running cosmics in the barrel and are trying to develop tools to measure efficiency, resolution, and alignment and then to port those tools to the end cap.

We are also checking out production wiring harnesses and pre-production patch panels against the end cap and barrel structures - so far everything is looking good. The next challenge will be installing end cap cable trays and measuring/checking noise performance.

## 3.3 M&O Argon

The commissioning of the Endcap C was competed in the spring and the preparations for its transport to the pit have started. The commissioning of the Endcap A followed the same pattern as that of Endcap C. The cold test started in May and continued through September. All cryogenic and high voltage components performed well. A portable readout crate of the front end electronics was used to check on the signal propagation in the cold. The preparations for the transport to the pit have started. Much of the cryogenics work centered on the commissioning of the UNICOS software. This software will be tested after the barrel cryostat will be moved to its final position in November. The cabling trays for various services and cooling manifolds were mounted on the barrel LAr+tilecal assembly in reparation for the move.

The electronics pre-operations started with the establishment of the Electronics Maintenance Facility (EMF) in one of the surface buildings at Point 1. Tests of the front-end and the back-end readout boards before insertion onto the corresponding crates are done at EMF. Since the barrel cryostat is still in the temporary position, the final cabling and services are not available. A temporary portable power, cooling and readout systems have been established. These allow to commission one crate at a time. At the end of September 9 full readout crates have been commissioned. This work will need to be re-checked after the move when the final cabling and optical fibers will be completed. The commissioning of the front-end readout system is also hampered by the delays of the delivery of the DC-DC power supplies.

The Level 1 Receiver system has been installed starting in July. Its commissioning has started but only the general connectivity and timing issues can be tested. Full commissioning will start only after the cabling connecting front-end readout to the Receiver crates will become available in February 2006.

3.3.1 Mechanical Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commission Cryogenic Connection Lines to the Barrel at z=0 | 10-Sep-05 | 10-Oct-05 | 10-Jan-06 | Delayed (See #1) |
| Commission Vacuum Pumps, Monitoring etc. for Barrel | 30-Sep-05 | 30-Oct-05 | 30-Jan-06 | Delayed (See #2) |

Note #1-2  Move of the cryostat to its final position has been delayed until November.

3.3.1.1 Pre-Operations and Commissioning

3.3.1.1.2 Feedthrough

Michael Rijssenbeek (SUNY Stony Brook)

HV Feedthroughs

All HV Modules are constructed, tested, and prepared. The HV tests of all three LAr Cryostats were successful, with HV problems, beyond known problem spots in the calorimeters, occurring only due to faulty HV power supplies. We are awaiting the start of commissioning of the Liquid Argon calorimeters in the ATLAS pit for final commissioning.

We foresee period of intensive travel and testing when the new (final) HV cables and HV supplies will be installed and connected to the feedthroughs.

We also need to work on the connections of the temperature sensors and heater resistors on the HV Feedthrough bulkhead. This work will also be done in the commissioning period.

3.3.1.2 Operations

3.3.1.2.1 Cryostat

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Re-commissioning Underground Complete | 1-Dec-05 | 1-Dec-05 | 1-Mar-06 | Delayed (See #1) |

Note #1  Move of the cryostat to the final position delayed to November. Recommissioning will start after the cryo connections are complete.

John Sondericker (Brookhaven National Laboratory)

Barrel Cryostat Operations

Mechanical work has continued throughout the reporting quarter in connecting whatever Barrel Cryostat sub systems are able to be completed before the detector is moved to its center, final position in the UX - 15 hall. Testing is scheduled to take place the end of this fiscal year. Cryostat cool down, fill and pre-operations modes will stress the newly installed systems by putting each through extensive testing programs. Nothing will be overlooked and great care will be taken to assess all facets of operation to assure reliability of safety, vacuum, cryogenic and electrical systems.

3.3.1.2.3 Cryogenics

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commissioning of Pit Cryogenics Complete | 1-Jul-05 | 1-Jul-05 | 1-Mar-06 | Delayed (See #1) |

Note #1  Move of the calorimeter to its final position delayed until November.

John Sondericker (Brookhaven National Laboratory)

Cryogenics Operations

Testing CERN's UNICOS software for control of the ATLAS Nitrogen Refrigerator (ANRS) and Distribution System is scheduled to take place in September/October of '05. ATLAS Nitrogen Refrigerator System (ANRS) controls were programmed at BNL in Concept, a well supported commercial process language and used with first run success to accept the refrigerator in March '05. However, CERN demands that all control software for LHC be written in their own UNICOS language. Work started at BNL last April to reprogram the ANRS in UNICOS. However, progress was slow during the first three or four months of work because attempting to make headway in UNICOSizing the ANRS controls without supporting documentation and its copious bugs did not lead to productivity. Some relief was found by communication with CERN by phone, E mail and using a private network for debugging UNICOS itself. At this time it appears that Margareta has battled her way through most of the bugs and has compiled her own documentation so the ANRS UNICOS test date of January '06 is likely. Pre-cool down tests of Cryostat sub-system are designed to evaluate and hopefully validate each of the cryogenic sub-systems for the ATLAS detector.

Ten Quality Meters (QM) were installed in UX - 15 in preparation for the Barrel Cryostat cool down test scheduled for the month of January '06. Remaining to install are the cables and other small but necessary items.

3.3.1.2.4 FCAL

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Commissioning of Endcap A Above Ground Complete | 1-Jun-04 | -- | 1-Sep-05 | Completed |
| Commissioning of EndcapC in the Pit Complete | 1-Feb-06 | -- | 1-Feb-06 | On Schedule |

3.3.1.3 Maintenance

3.3.1.3.2 Feedthrough

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Barrel HV Operations (SB) | 1-Sep-05 | 1-Oct-05 | 1-Feb-06 | Delayed (See #1) |

Note #1  Calorimeter move to its final position is delayed until November.

3.3.1.3.3 Cryogenics

John Sondericker (Brookhaven National Laboratory)

Cryogenic Maintenance

As End Cap C was near completion of its tests last March, one of its three quality meters, used to monitor the percent of N2 liquid in its cooling loops, ceased working. These are high impedance capacitive devices in liquid nitrogen. While the ailing device was still cold, it was found to be short circuited to ground. No doubt caused by something conductive getting stuck between the capacitive plates of the QM. Sometimes the short will disappear when warm but after QM warm up to room temperature the problem remained. The shorted meter was removed after completion of End Cap C testing and replaced by a spare. We have discussed this failure with CERN cryogenic people but have not had the chance to travel there and investigate the cause first hand.

Sometime before the January cold test of the barrel, BNL will send someone to check out the shorted QM, mentioned above, and perform maintenance on the complete QM system. This is necessary since all QM's were removed from test piping and welded in their UX - 15 final position.

3.3.2 Electronic Liquid Argon M&O

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the First Crates on the Truck | 30-Mar-05 | -- | 10-Aug-05 | Completed |
| Operation of the First Full Crate on the Truck (stand alone) | 30-Apr-05 | -- | 10-Aug-05 | Completed |
| Operation of all Crates on the Truck | 30-Jun-05 | -- | 30-Apr-06 | Delayed (See #1) |
| Operation of the First Full Crate on the Truck Linked to USA15 | 30-Jun-05 | -- | 30-Dec-05 | Delayed (See #2) |
| Operation of all Crates on the Truck stand alone | 30-Sep-05 | -- | 30-Apr-06 | Delayed (See #3) |
| Complete Commissioning of Barrel Optical Links (SMU) | 15-Dec-05 | 15-Dec-05 | 1-Mar-06 | Delayed (See #4) |
| Complete Commissioning of EndcapC Optical Links (SMU) | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |

Note #1  Cryostat move to its final position and start of the partial cabling will happen before completion of commissioning

Note #2  Cryostat move to its final position has been delayed.

Note #3  Cryostat move to its final position and start of the partial cabling will happen before completion of commissioning

Note #4  Fibers will not be installed until February

3.3.2.1 Pre-Operations and Commissioning

3.3.2.1.3 System Crate Integration

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Completion of Documentation of Level 1 Trigger Interface for Liquid Argon and Tile Calorimeters (Pitt) | 31-Jul-04 | -- | 1-Dec-05 | Delayed (See #1) |

Note #1  Documentation almost complete. Documents need to be updated with final versions of hardware.

Francesco Lanni (Brookhaven National Laboratory)

1. Replacement of the FCAL baseplane on the EndCap side C after some damage to the signal connectors occurred during the Bldg. 180 system tests.

2. Preparation of the EndCap Cryostat side-C for transport to Point-1 after end of cold tests. 4 pedestals have been removed, including baseplanes, warm cables and all the plumbing and pneumatic valves for the feedthrough vacuum

3. Commissioning of the portable cooling system to be used during installation and commissioning of the Front-End electronics on the barrel cryostat while in the parking position. A long run test with few cooling plates concluded successfully. Measurements deserved the purpose of controlling the purity of the deionized water and corrosion effects on the cooling plates itself

4. Commissioning of the first 8 power supplies on the lab on surface (EMF) with a minimal dummy load (10% of maximum power) and after installation in the pit. 6 out of 8 power supplies are equipped with bypass capacitors on the output voltage that later have been decided by the collaboration to be replaced given the failure rates. Uninstall and return to BNL of those power supply planned to be completed before the cryostat rolls into the final position at z=0 (end of October). The remaining 2 power supplies have been commissioned after installation in the pit with the production front-end electronics. However a new failure mechanism has been identified where a filter inductor on the output voltage fails by an unknown mechanism resulting either in the break of the ferrite core or a complete detaching of the solder joints. The problem is being investigated at BNL and at the manufacturer site

5. Pressure tests of the cooling services on the barrel calorimeter. The installation of the Front-End crate services on the barrel calorimeter has been completed. Technical coordination ran pressure tests on all the cooling sector and identified leaks in several location that have been identified in the temperature sensors inserted into the manifolds and pipe assemblies. Replacement of the parts and retest have been completed successfully. The failing part has been sent back to the manufacturer for failure analysis: because of an excess of stress on the assembly during handling the vacuum fitting broke internally.

6. Installation and commissioning of the Embedded Local Monitoring Boards (ELMBs) on each location of the barrel front-end crates. Commissioning included communication and signal quality tests on the routing scheme of the CANBus cables between the ELMBs and the dedicated DCS (=Detector Control System) workstation in USA-15.

7. Development of the DCS software through the Atlas wide adopted SCADA architecture (PVSS-II and JCOP framework): control of the cooling, system crate voltages, status of LV and 280V power supplies is being monitored and logged periodically in the condition database. Basic functionality established. Integration in the standard Atlas DCS framework is in progress.

3.3.2.1.4 Front End Board

John Parsons (Columbia University (Nevis Laboratory))

Front end board installation and commissioning on the EMBarrel continues. 9 crates of boards have been fully tested. The remaining crates are almost half-populated with FEBs, but they are as yet untested.

Commissioning has so far been taking place in the Truck position using a temporary DAQ. Once the EMBarrel move to the IP is complete, final commissioning of the FE with the RODs will start.

A test stand has been set up in B180 to allow testing and pre-ops of the FEBs for the HEC, which must be equipped with the preshapers. This test will begin in early November.

3.3.2.1.5 Level 1 Trigger

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Commissioning of Receiver System in Truck Position (Pitt) | 28-Feb-05 | 28-May-05 | 1-Jul-05 | Completed |
| Start Commissioning of Barrel Receiver System (Pitt) | 31-Aug-05 | 31-Aug-05 | 15-Nov-05 | Delayed (See #1) |
| Complete Commissioning of Barrel Receiver System (Pitt) | 31-Dec-05 | -- | 31-Dec-05 | Delayed (See #2) |
| Maintenance Procedures for Receiver Modules Complete (Pitt) | 31-Dec-05 | -- | 31-Dec-05 | Delayed (See #3) |
| Start commissioning of EndcapC Receiver System (Pitt) | 1-Jan-06 | -- | 1-Jan-06 | Delayed (See #4) |
| Complete Commissioning of EndcapC Receiver System (Pitt) | 1-Mar-06 | -- | 1-Mar-06 | Delayed (See #5) |

Note #1 - 2 Barrel not in final location

Note #3  Need barrel in final location to finalize procedures

Note #4-5  Need barrel in final location

Bill Cleland (University of Pittsburgh)

Components of the Receiver system ware shipped to CERN over a three month period beginning near the end of July, 2005.  The shipments include all receiver and transition modules, controller modules, and monitoring modules. A few of the remapping boards (the ones with active summing circuits) are still being assembled and tested at Pitt. These are used only in the endcap, and they will arrive at CERN by Dec 05. Upon receipt of a shipment of modules, the crew at CERN performs routine tests to verify that no damage has occurred in transit. The 9U crates, outfitted with the receiver backplane, have been at CERN for some time and were installed in their final position in USA15 over the summer.

One problem that was identified was the occasional failure of one of the components, a pulse transformer, after the module has passed the acceptance tests at Pitt. The rate is relatively low, of order 0.3%, but the cause is unknown. This component requires care in assembly, as the maximum temperature specified by the manufacturer is close to the temperature required for the wave-soldering operation in the assembly process. We presume that the failure arises from the thermal stress received by the transformer in the assembly process and takes some time to become evident. We replace the components as necessary, and we have not yet seen a failure of any replacement transformer. We have introduced specific checks on the transformers of both types, which are performed just before shipment and after arrival to ascertain whether the shipping process itself is a cause of the failure. The failure rate, though small, is large enough that we prefer to repair the modules at CERN rather than return the modules to Pitt. For this reason we have shipped to CERN a special desoldering workstation which is to be used in the replacement process, and we are planning to train our postdoc to carry out the operation.

The installation and commissioning of the Receiver system takes place as part of the commissioning of the liquid argon front end electronics. As a crate is commissioned, the main readout is checked using the calibration system, and then the trigger signals are checked. There are two types of tests: connectivity and amplitude/timing studies. The connectivity checks are designed mainly to find faults in the FEC backplane, as this is the one component in the system that has not yet been individually checked. We assume that the front end board and tower builder board are faultless, and we pulse all possible trigger paths to verify that one and only one trigger sum is active for each pulsing pattern, and that it is in the expected channel. This will locate any shorts or opens in the interconnections between the frond end board and the tower builder. The second tests, which checks the gains of the different elements of the trigger chain, as well as the timing of the pulses, is carried out by pulsing a given depth layer of a given cell and  reconstructing the amplitude and timing of the pulse seen in both the main readout and in the trigger path. The measured amplitude and timing are compared with the expected values and any errors are reported. The connectivity tests, which require about 2 hours, are made during the physical commissioning of the crate, as it is during this tests the physical connections may need to be examined. The amplitude/timing test is carried out at a later time, as it requires only remote contact with the front end crate.

Procedures for the commissioning and testing of the front end crates have been developed over the period (May-Oct) when the barrel calorimeter was located on the truck, using temporary cables and, in some cases, prototype electronics. The commissioning of the system with the calorimeter in position and the final cables in place will begin in early 2006, once the connectors have been mounted on the trigger cables. The Receiver crates for the barrel have been filled with modules and are operational. Other crates will be filled as needed.

3.3.2.3 Maintenance

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Long Term Burn-in of FEBs at BNL Complete | 1-Jun-05 | -- | 1-Jun-06 | Delayed (See #1) |

Note #1  Equipment will be available after completion of the FEB production and testing.

3.3.2.3.3 System Crate

Francesco Lanni (Brookhaven National Laboratory)

In a couple of location on the barrel cryostat cooling manifold have been found damaged. Particularly the quick disconnect fittings have been found broken presumably because of some object falling. It required replacement of the fitting.

3.3.3 Beam Test

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Operation of the first production FEB in a System Crate | 30-Mar-05 | -- | 30-May-06 | Delayed (See #1) |
| Long Term Stability Test of Production FEB Started | 30-Jun-05 | 30-Jun-06 | 30-Jun-05 | Completed |

Note #1  No decision has been made on the date for the start of the new beam test.

3.3.3.1 FCal Hadronic Tail Measurement

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| FCal Electrical Test Bench Completed (Ariz) | 15-Mar-05 | -- | 20-Dec-05 | Delayed (See #1) |
| FCalA Electrical Cold Test (Ariz) | 20-Jun-05 | -- | 20-Sep-05 | Delayed (See #2) |

Note #1  Problems with other (non ATLAS) projects have kept our electronics staff from starting on the FCal Electrical Test Bench project. The mechanical parts, however, are progressing nicely.

Note #2  The EndCap A cryostat is cooling down and is projected to be filled with Argon by mid-August. Then follows a 6 week period of electrical testing. We will start with the HV testing in August and finish the HV continuity tests in mid-September, assuming the cryostat stays on schedule.

## 3.4 M&O Tile

3.4 Subsystem Manager's Summary

Larry Price (Argonne National Laboratory)

Work during this period included additional checking and addition of interface materials on extended barrel modules and ITCs in preparation for their installation in the pit as soon as the barrel is moved to z=0.  Testing and validation of installed components such as the electronics drawers on the modules and readout electronics and power supplies in the USA15 electronics area continued to require time.  Increasing levels of work was expended on preparation for the drawer by drawer commissioning that will begin on the barrel as soon as it is at z=o and connected to cables and services.  As 3-in-1 cards and optical interface boards are received from the drawer testing program, they are repaired.  Since cables are a frequent source of the problems discovered, more robust cables are being installed on the boards when they are received for repair.  Commissioning preparations include software developments in the areas of control, databases and monitoring.  The design of the MBTS counters was finalized and prints were generated. The scintillators for the MBTS counters were machined by the MSU machine shops and the Aluminum boxes for the counters were ordered from a vendor.

3.4.1 TileCal - Specific Costs

3.4.1.1 Pre-Operations 	Steve Errede (University of Illinois, Urbana-Champaign)

Dave Forshier - one of our UIUC technicians continued to work full-time at CERN along with other TileCal technicians on installation & the cabling up & testing of ATLAS TileCal, under the daily supervision of Bob Stanek & Irene Vichou.

Irene Vichou continued with her work at CERN as the coordinator of the Services Installation and testing. She is responsible for the generation and up-to-date maintenance of the cabling database for TileCal (Oracle application interfaced through Excel tables) so that the installation crew/supervisors have the necessary information to locate any/all cables/pipes etc. and the possibility to store the results of controls/checks before giving the final OK for operation.

Bob Stanek (Argonne National Laboratory)

During this period Argonne engineers and physicists planned the movement of the Extended Barrel from 185 to Pt. 1. Although an engineer based at CERN provided the immediate attention, we looked at any missing details which could have delayed the move. Mainly this involved verifying safety devices were correctly designed and in place.

There were several "expert weeks" in the pit where the finger LV supplies were operated in conjunction with the Chicago trigger boards. Argonne personnel were involved in these tests as well as some analysis of the correlation of the production RODs and the mobile DAQ system. We found issues related to stability and noise. There is a continuing study of how to reduce the noise problems.

We did tests at CERN on the trigger cables after having assembled them for the past year. We discovered that the differential skew within a pair was unacceptable, and a program to acquire new cables was launched. In the meantime, trigger cables plus other cables were fitted with connectors assisted by an Argonne technician.

An Argonne technician - Leon Reed - began work at CERN in September part time for Tiles and part time for TC. Leon had spent some of the period preparing the barrel finger region for future commissioning.

We found that the barrel had electronics that were failing, both readout sides and the HV sides. An intense program was established to certify drawers before the (now delayed) end-of-September move to z=0. Many problems were discovered and repaired.

Kaushik De (University of Texas at Arlington)

Armen Vartapetian spent a month at CERN performing final pre-installation checks on the ITC. All modules have been light sealed at the ITC end. A pre-installation test was also done with a complete set of scintillators, along with Ron Richards.

Armen continued work on QC procedures and presented draft plans at meetings.

Kaushik De arrived at CERN for his sabbatical leave at the end of August. He will be working on ITC installation and commissioning issues.

Jim Pilcher (University of Chicago)

During the past quarter approximately 25 3in1 cards were received for testing and repair. Cabling continues to be the dominant source of problems for the returned cards. The new style of cable is being installed on all cards received for repair.  The 30 cards received in the previous quarter have also been repaired with the new cables.

Three optical interface boards were received from CERN.  Interconnection cables were replaced and the boards returned.

Extensive work has been done on testing and exercising electronics drawers. Software and procedures were developed for routine use of the laser (now with led's as light source) and charge injection calibration systems, including repeated measurement of pedestals.  The system was used for a program of stability testing on the drawers that were available for testing during the summer.  CANbus communication, TTC communication, and DCS measurements and control were tested and exercised.  More importantly, the test systems and procedures provided a dry run for the systematic drawer by drawer commissioning and acceptance testing that will begin as soon as possible after the barrel calorimeter is moved to z=0.

As first low voltage power supplies became available for testing with the new ELMB motherboards, they were placed in fingers and connected to drawers.  Extensive testing was done on performance with respect to stability and noise.

Software development was done for control and processing of charge injection calibration runs.

Larry Price (Argonne National Laboratory)

Database structures were set up in the CERN MTF (Material Tracking Folders) system and the ATLAS Conditions database COOL for recording appropriate summaries of the data to be taken during commissioning.  Programs were written on the Tilecal end to process commissioning data and write files in formats appropriate for insertion of data in the databases.  Planning was done for the storage and accessing of DCS data (voltages, temperatures, etc.) during commissioning, but exercising of the system could not be done because the interface between the DCS software called PVSS and COOL is not ready yet.  The system for storing fragment id's and other data needed for TDAQ initialization in the TDAQ OKS database was reviewed and revised in preparation for commissioning.  Database work was also done with the Valencia group to prepare for transfer of optimal filtering coefficients from COOL to the Tilecal RODs.

Considerable work was done on online monitoring systems to the point where it was possible to begin to make comparisons with offline performance results.  Systems were developed both at the low-level using the Italian GNAM monitoring program and at a higher level with the Athena monitoring program (though full use awaits the HLT release for TDAQ-01-04-00).

Testing and validation of the drawers with the portable DAQ system continued. A pattern of HV trips was found in a few of the drawers being tested (11 out of 80 tested).  Further investigation is under way.

Support was provided for the cosmic ray commissioning test which provided the first "real" data from ATLAS detector components in the underground cavern.  A more extensive set of cosmic data was taken in September, when we were able to use 8 final ROD boards and a final ROS readout with the TDAQ system.  We were able to test the operation of DSP code in the RODs.

3.4.2 Calibration & Monitoring

Joey Huston (Michigan State University)

During the period of July-Sept, the design of the MBTS counters were finalized and prints were generated. The scintillator for the MBTS counters were machined by the MSU machine shops and the Aluminum boxes for the counters were ordered from a vendor.

At CERN, the mounting holes for the cryostat counters were drilled at tapped for the modules where they were left off. The vapor liners were installed in EBA and EBC and preparations were made to transport the module/cradle to the pit area.

3.4.3 Tilecal System Common Costs

## 3.5 M&O Muon

3.5 Subsystem Manager's Summary 	Frank Taylor (MIT)

Effort on the Muon system during the third quarter of FY05 concentrated on the Phase I certification of both MDT and CSC chambers to be Ready for Installation (‘RFI’), the setting up of various operation sites (BW-L, BW-S and EIL4 work stations) in B180 for installation of commissioning of chamber and alignment components mounted on support structures and the first installations and commissioning of BW sectors and EIL4 stations in B180.

During July-September 2005 a milestone was achieved in the completion of all the Phase I Commissioning of the 240 MDT chambers in B184 at CERN. Much credit for the completion of this work goes the Michigan and Seattle teams, who were supported by the BMC team over the summer 05.

No significant systematic flaw was uncovered in the Phase I commissioning of the 240 MDT chambers, such as broken wires, etc. The certification data generated during the Phase I were entered in the Michigan chamber certification database, but in order to be compliant with the ATLAS installation database, these data are being transferred to the MTF database managed by CERN.

The so-called 'Phase 1.9' commissioning of the MDT chambers was organized and conducted by Alex Marin, BU who worked with Boston, Brandeis, Harvard and MIT students to good effect. Included in this work are the mounting and checking of the final CSM-4 card, the mounting of B-sensors and associated cabling and the photogrammetry measurement of the chamber alignment targets and B-sensor mounts. All 80 of the Side C EM chamber series were completed.

At the end of September 2005, 30 of the 32 Cathode Strip Chambers were integrated with electronics, cooling plates and Faraday cages and tested at BNL. These chambers will be ready for shipping to CERN in early 2006 once the B184 test station is prepared.

Planning for the CSC final certification and installation work at CERN was undertaken. The chambers will be integrated with their support frames (built in St. Petersburg, Russia) and alignment fixtures and will be checked one last time in B184 at CERN. Some of the support frames have already been shipped to CERN and one has been transported all the way to BNL where it is being checked and integrated with a chamber. In addition, the CSC installation tool, constructed at St. Petersburg, is now at CERN and is ready to use.

Work continued in Building 180 on the construction, installation and commissioning of Big Wheel Sectors and EIL4 stations on the ‘Saleve side’. A milestone was reached with the completion of the first BW-L sector (Sector 09C). All 5 of the EML chambers were installed on the sector thereby validating the procedures and tooling. A small change was found necessary in the installation tooling for the EML1 chamber – but was easily corrected. The 9.5 m alignment bar was certified in the alignment clean room in B180 and it along with all other alignment sensors were integrated in the sector.

The Phase II commissioning of the Sector 09C was started. This included verification of leak tightness and flow rates of the chambers in the sector, connection of the chamber and alignment readout electronics and a survey of the geometry of the chambers in the sector by photogrammetry and by using the alignment system itself.

Both the EIL4 A13 and C13 chambers were installed in their respective support frames along with their associated alignment bar in August. The MDT part was integrated with the TGC half on the frames. Phase II commissioning of these stations was started.

In September the work area and tooling for the BW-S Sector assemblies were prepared in the ‘Jura’ side of B180 and the assembly of the first BW-S sector started. Difficulties were encountered in configuration of KM and strut plates requiring EMS1 to be mounted and dismounted several times. After analysis it was determined that the strut plates had to be stiffened. In addition, it was ascertained that the tilt table on which the aluminum of the sector is assembled had a subtle distortion when in the vertical position. All these problems were sorted out and the 5 EMS chambers of Sector C04 were installed in October.

While much was accomplished during this period, the progress of the installation and commissioning of sectors and EIL4 stations was slower than planned. Several impediments, such as slow and confused shipping of material to make the sectors were a factor, as well as the speed of assembly of the tooling needed to install the sectors. Improvement on these fronts is expected (promised) but efforts by all teams on organization, part inventory, logistics, etc. (US and CERN) are needed. The schedules for installation of the BWs and EIL4 stations are being closely watched.

3.5.1 MDT Pre-operations, Operations & Maintenance

3.5.1.1 MDT Pre-Operations

3.5.1.1.1 Set-up of MDT Test & Test Station

James Bensinger (Brandeis University)

Both large and small sector verticalizer stands are operational. Photogrammetry system for both stands is also operational.

3.5.1.1.2 Pre-Operations of MDT Chambers -Phase 1

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start Pre-Operations MDT SW Chambers -Phase 1 | 2-Mar-05 | -- | 2-Jul-05 | Completed |
| Finish MDT SW Pre-Operations - Phase 1 | 1-Jul-05 | -- | 15-Jul-05 | Completed |
| Pre-operations of MDT Chambers - Phase 1 (MIT) | 31-Jul-05 | -- | 31-Jul-05 | Completed |

George Brandenberg (Harvard University)

One grad student, Lashkar Kashif, has been in residence at CERN and working on chamber commissioning, mostly phase 1.9. During July and August he was joined by two new grad students, Jina Suh and Srivas Prasad.

Steve Sansone in the LPPC machine shop has been steadily making miscellaneous parts for chambers with high priority as they are needed at CERN. Rick Haggerty has been mothballing the BMC chamber production line tooling and equipment. Everything is being labeled by chamber type in the event a replacement is required.

Sarah Harder in the LPPC electronics shop has been retesting problem mezz boards that are returned from CERN and repairing them as needed. She has now retested about 10% of the original production. Many boards appear to be OK and were possibly set aside during installation because of a chamber problem. Boards that require repair have damaged connectors or need a replacement ASD chip with a lower threshold spread.

Edward Diehl (University of Michigan)

Edward Diehl is compiling phase I chamber commissioning data for all endcap chambers. He has most of the US chamber data, and is now getting data from the Russian chambers being commissioned in B184. The next step is to input this data into the CERN Oracle DB.

We also wrote an ATLAS note describing phaseI commissioning, ATL-COM-MUON-2005-017. This note was spearheaded by Zhengguo Zhao and Edward Diehl, and had major contributions from Claudio Ferretti.

We hired Iouri Sedykh, to do a detailed analysis of the 2 chambers which had been damaged in a crane accident last year. Yuri had previously worked for the CERN x-ray group and has wide experience analyzing x-ray data. Yuri has written a report which we will turn into an ATLAS note. His preliminary results can be seen at: http://agenda.cern.ch/fullAgenda.php?ida=a053244 .

James Bensinger (Brandeis University)

Phase I modification of all US chambers is complete.

3.5.1.1.3 Pre-Operations of MDT Chambers -Phase 11

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start BW Single Sector Test | 1-Jul-04 | 10-Aug-05 | 8-Aug-05 | Completed (See #1) |
| Setup BW Sector Assembly Station (Brandeis) | 15-Mar-05 | 1-Jun-05 | 15-Mar-05 | Completed (See #2) |
| Production of First BW Sector (Brandeis) | 15-Apr-05 | 15-Jun-05 | 8-Jul-05 | Completed (See #3) |
| Installation of Chamber in First BW Sector (Brandeis) | 15-Jun-05 | 3-Aug-05 | 5-Aug-05 | Completed (See #4) |
| Start BW MDT Phase 11 Commissioning | 1-Aug-05 | 15-Aug-05 | 8-Aug-05 | Completed (See #5) |
| Start BW Mechanical MDT & Alignment Installation in Bldg 180 | 1-Aug-05 | 1-Sep-05 | 23-May-05 | Completed (See #6) |
| Pre-operations of MDT Chambers - Phase 2 (Boston) | 30-Sep-05 | 30-Sep-05 | 30-Sep-06 | Delayed (See #7) |
| Pre-operations of MDT Chambers - Phase 2 (MIT) | 30-Sep-05 | 30-Sep-05 | 30-Sep-06 | Delayed (See #8) |
| Complete all 16 EIL4 MDT-TGC Assemblies | 14-Mar-06 | [New] | 14-Mar-06 | On Schedule |

Note #1  Sector commissioning of sector C09 began August 8. Moved to Storage on November 3. Single sector test was done as part of commissioning.

Note #2  Delayed - but as of 4-Aug-05 complete.

Note #3  The first BW-L sector was put together with Pakistani crew in July-05. Delays were encountered in setting up the tooling (tilt table and A-frame) due to several factors - including completion of FEA model of structures needed for TIS certification.

Note #4  Complete as of 5-August-05. Measurements of chamber positions are underway and Phase II commissioning has started.

Note #5  Started as of 8-Aug-05 with the connection of LV, HV, DCS, fiber optics and alignment cables.

Note #6  Alignment bar installed in sector C09 May 23 and chamber installation in the same sector began July 11.

Note #7 - 8 Work will continue until all the MDT chambers are installed and commissioned on the support structures.

Edward Diehl (University of Michigan)

We did a wide variety of work on big wheel (BW) sector commissioning. J. Chapman, Bing Zhou, Curtis Weaverdyck, Jeff Gregory have been resident at CERN all year, and Dan Levin joined them in July. They all worked to get the sector commissioning underway.

J. Chapman. Jeff Gregory, and Tiesheng Dai developed a multi-chamber DAQ system to read out an entire sector at once (5 chambers). They built 4 of these systems: one for the BW large sectors, one for the BW small sectors, one for EIL4 chambers, and one spare.

J. Chapman and J. Ameel also worked out a system for labeling sector cables, and a program to create labels, and store cable this data for the database.

Curtis Weaverdyck worked extensively on sector mechanical issues and developing chamber handling and installation techniques. He also helped install a 2nd "verticalizer", an tool which removes chambers from shipping boxes and rotates it upright so that it can be picked up by the chamber installation tool for installation on a sector. This verticalizer is for use for BW small sectors (already had one for BW large sectors). Curtis also worked on developing techniques chamber spacer frame adjustment with tension rods described here: http://agenda.cern.ch/fullAgenda.php?ida=a055494

Dan Levin and Manuela Cirilli worked on getting infrastructure installed in B180, such as the installation of gas supply lines for the chamber gas. They also developed a method to measure the gas flow throw each chamber in a sector to verify an uniform flow rate in all chambers. This is described at http://agenda.cern.ch/fullAgenda.php?ida=a055494 .

J. Chapman, C. Ferretti, and Manuela Cirilli are working on the developing the DB tables for data from phase II sector integration. This work is described at http://agenda.cern.ch/fullAgenda.php?ida=a055494 .

James Bensinger (Brandeis University)

Phase II for the BW has begun. We have assembled 1 small and 1 large sector and are working on the next sector on both the small and large stands. For the first time we are limited by the availability of labor (Pakistani) rather than the availability of parts.

3.5.2 CSC Pre-Operations, Operations & Maintenance

3.5.2.1 CSC Pre-Operations

3.5.2.1.2 Pre-Operations of CSC Chambers - Phase 1

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Complete Pre-operations of CSC Chambers - Phase 1 (BNL) | 30-Jun-05 | 30-Aug-05 | 30-Sep-05 | Completed |

3.5.2.1.3 Pre-Operations of CSC Chambers - Phase 2

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Start CSC Installation & Phase 11 Commissioining on SW in Bldg 191 | 1-Sep-05 | 1-Nov-05 | 1-Jun-06 | Delayed (See #1) |

Note #1  The reason that the SW is delayed (CSC, Phase 2, etc.) is that the Endcap Toroids are delayed thereby delaying our occupancy of Bldg 191 where the SW work will be done.

3.5.3 Alignment System Pre-Operations, Operations & Maintenance

3.5.3.1 Alignment System Pre-Operations

3.5.3.1.1 Pre-Ops Stage Area for Alignment Parts

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Validation of Alignment Components (Brandeis) | 15-Apr-05 | -- | 30-May-05 | Completed (See #1) |

Note #1  The alignment component test station is operational in Alignment/Services room in B180. The alignment bars for EIL4 13A&C have been tested and installed on their respective chamber frames. The alignment bar for Sector 9C and 3C (BW-L sectors) have been tested and installed on their sectors.

## 3.6 M&O Trigger

3.6 Subsystem Manager's Summary

Andrew Lankford (University of California, Irvine)

Pre-operations activities involved Pre-series system commissioning (hardware and software), rack commissioning, commissioning of Monitoring software, support of development of detector-specific software, and integration of Tilecal readout with the Pre-series system. Commissioning of HLT and DAQ software through large-scale tests was a focus during the beginning of the period. Operations activities involved software maintenance, hardware maintenance on the Pre-series system, and system and network administration.

3.6.1 Pre-Operations

| Milestone | Baseline | Previous | Forecast | Status |
| --- | --- | --- | --- | --- |
| Begin Operations Supervisor RoI Builder Support | 1-Mar-06 | -- | 1-Mar-06 | On Schedule |

Andrew Lankford (University of California, Irvine)

Software commissioning:

Kolos concentrated on Large Scale Tests of HLT/DAQ software at CERN for much of July. He focused on the scalability and performance of the Monitoring services, for which he is responsible, and he participated in the debugging and running of the integrated tests.

Hardware commissioning:

Unel coordinated commissioning and operation of the Pre-series system. Stancu participated in the operational aspects of the Pre-series system.

Detector support:

Kolos continued to lead the Monitoring Group in its study of subdetector monitoring requirements. This group also discussed application of the ATLAS Event Display with Monitoring services. He presented the status and planning of Online Monitoring Commissioning at the ATLAS Technical Management Board and at the ATLAS Software & Computing Workshop. He worked on application of the Athena-based Processing Task, which runs in the Event Filter, for monitoring during commissioning. This monitoring scheme was successfully tested at Point 1 with the TileCal detector. He also provided support to Inner Detector groups with application of ROD Crate DAQ facilities for Monitoring.

Unel integrated Tilecal readout with the Pre-series system. He also participated in meetings between the TDAQ Sysadmin group and detectors.

Bernard Pope (Michigan State University)

Comune worked on the creation of the final requirement document for the HLT Core Software and started the complete redesign and coding of the Steering software according to this requirements document and to more stringent computing performance. This new implementation is needed because of the inclusion of realistic trigger menus in the HLT framework, and also to meet the new computing performance targets that, in the recent system review, proved to be absolutely unachievable with the old software. Comune presented first results at a PESA HLT algorithm meeting. The modifications have been incorporated into release 10.5.0 of the trigger software. In addition, Comune has been working on the design and implementation of a persistency framework that enables the production of AOD data from the Trigger software. This software will enable the creation and delivery of the Trigger Decision to any physics analysis and is regarded of extreme importance in the PESA community.

Robert Blair (ANL)

The RoI Builder software was adapted to properly handle the new eformat (v3).

3.6.2 Operations

Andrew Lankford (University of California, Irvine)

Software maintenance:

Kolos produced several patches to fix bugs found in Monitoring software components (Information Service, Online Histogramming and Event Dump). He coordinated the preparation to the build of the new TDAQ software release, including preparation of the Monitoring software components for which he is responsible.

Hardware maintenance:

Stancu performed Pre-series network equipment firmware upgrades where appropriate. Hewlett Packard technical support from was contacted in order to address a SNMP related problem (truncated bulk requests) in the LVL2 and EF concentrator switches.

Operations:

Unel coordinated system administration activities at Point 1 and in TDAQ test labs.

Bernard Pope (Michigan State University)

Ermoline continued to work on the installation of equipment in, as well as the DCS control and monitoring of, the racks in SDX1. He participated in a PVSS course at CERN in the beginning of August in order to start the TDAQ rack DCS application development. A representative from CIAT (the providers of the rack cooling system) visited CERN and discussed refined requirements, especially for the powering of the fan rotation sensors. The RITTAL sliding shelves were added to each rack and more sequential power units were ordered. The configuration of the pre-series racks was updated in the Rack Wizard and new features were added -- connectors on the components in order to associate them with the cabling database. More sequential power units were received and one broken unit was sent to the company for repair. A bid for the 52U racks on the lower level of SDX1 has been received from RITTAL. Ermoline attended LECC05 in Heidelberg and made a presentation (ATLAS DAQ/HLT Infrastructure). A paper for the conference proceedings has been submitted.

3.6.3 CERN Common Costs

3.10 Subsystem Manager's Summary

David Lissauer (Brookhaven National Laboratory)

Barrel Toroid Magnet:  The Barrel Toroid Warm structure has been completed and the release of the jacks started.  All beams are in place and now the final shimming is being done on Section 5 (last section).  Plans for the dismantling of the platforms have been developed.  It will be done by a team of Russian engineers and technicians who will come for the four weeks needed for the job.

Installation Task Force:  A new baseline schedule has been decided. The new schedule has small changes in compare to the old one. The main features are still the same. The EC calorimeters will be assembled in by early ’06 and soon after that we will measure the solenoid field.

Muon Chamber Preparations:  The brackets for most of the barrel muon rails have been installed. Rail installation will start next week after the final rail machining is complete for the first set this week.  The installation of the next set of BMS chambers will start right after the release of the jacks on the warm structure.  This work will take place in parallel to the installation of the HS arches (which will complete the HS structure).  It is still not a bottleneck but will become one by early next year if the installation goes as expected and the preparation rate does not increase.

Inner Detector Installation:  The Barrel SCT and TRT are nearly complete in Building SR1 (Surface Building).  This is a major milestone for both the barrel TRT and the SCT.  The next step will be to insert the SCT into the TRT – this step is expected to take place at the end of November early December 2005. At that time the new system will be commissioned on the surface and installation in the hall is scheduled for spring 2006.

Over the summer 2005, we received reports from the Pixel Project that they had significant damage to 43 pixel staves.  The damage is to the cooling lines that developed pinholes due to corrosion of the aluminum pipes. The problem is that the tubes are integrated in the stave design and cannot be replaced easily. An investigation on how best to proceed is on going. The best case scenario will be if one can find a way to repair the cooling pipes – but this does not look very promising at this stage. The worse case scenario is that the 43 staves will have to be written off – probably with the sensors that are already mounted on them.  This is due to the fact that the sensors are glued on the staves and will be damaged if one tries to remove them.

Inner Detector Upgrade:  Discussion on future organization of the ID upgrade took place. I presented a straw-man layout for the ID upgrade that might be used for the basis of work organization in the future and the development of the engineering at the Project Office.

Inner Detector Upgrade Workshop:  A three day Inner detector upgrade workshop took place in Genoa in mid-July 2005.  I gave a talk on layout options and chaired the session. The workshop attracted ~70 ATLAS people and was well organized. It covered all aspects from sensor technology, integration issues, readout electronics and organization issues. There was a general consensus that the upgrade will be needed by 2014-2015. The upgraded tracker needs to be a complete replacement of the present one. The time scale is already tight – taking into consideration the new challenges that we will be facing. They include a factor of 10 in particle density and in radiation levels. This implies a high level of multiplexing and a need to reduce the power per channel by roughly a factor of 4-10. This seems possible but not trivial.

Technical Manpower:  One of the key engineers who is currently working in Technical Coordination is leaving CERN. This engineer had received an offer for a permanent CERN staff position, but has received a better offer in his home country.  The difficulty in keeping key technical personnel is a problem that we have to face.

Calorimeter Installation:  The Tile Assembly (19 modules on the cradle) and the LAr EC cryostats for side C were transported to the surface building to prepare for installation during November 2005.  The Tile and LAr will be stored in the surface building until the installation takes place.  Discussions with the surveyors took place to define all the survey needs for calorimeter installation.

LHC Schedule:  The installation of the Cryo-ring is progressing slowly.  The cooldown test was interrupted due to a break in one of the connections and will resume in a week or two after small repairs.  The magnet connection is the next critical item.  No magnets have been connected to the Cryo-ring and these connections will not start until after the Cryo-ring tests are finished.  Start up of beam is now expected not before spring to summer of 2008.

Rail and Barrel Calorimeter Positioning:  A meeting with the survey team took place to decide on the final placement of the experimental rails. Discussions of the calculations that I presented took place and there was a general agreement that we will place the rails at -1mm form nominal positions and the calorimeter between 1-2 mm below nominal depending on the sag observed during the cal installation. The survey team has agreed to link the high-resolution hydrostatic survey system to the fixed point near the wall that is expected to be stable.

ATLAS Upgrade:  The upgrade steering group met.  Discussions on future organization took place and the procedure for approving and supporting R&D took place. I presented a straw man layout for the ID that will now be used for the simulation.  The straw man layout was a result of the discussions in the Genoa workshop and work that we did at BNL for simulations with Pavel Nevski and Sue Duffin (Norton).

# Financial Report (Chuck Butehorn, BNL)