Rare Symmetry Violating Processes Project

Work Breakdown Structure

Current RSVP WBS Structure
Ver. 3.0    October 4, 2004

| System | WBS | Description | System Manager |
| --- | --- | --- | --- |
| Project Office | 1.1 | Project Office | W. Willis, Columbia University/BNL; J. Kotcher, Columbia University/BNL (Deputy) |
| KOPIO | 1.2 |  | M. Marx, SUNY Stony Brook |
|  | 1.2.1 | Vacuum System | TBD |
|  | 1.2.2 | Preradiator | Toshio Numao, TRIUMF |
|  | 1.2.3 | Calorimeter | Vladimir Issakov, Yale |
|  | 1.2.4 | Charged Particle Veto | Andries vanderSchaaf, Zurich |
|  | 1.2.5 | Photon Veto | Oleg Mineev, INR Moscow |
|  | 1.2.6 | Catcher | Noburo Sasao, Kyoto University |
|  | 1.2.7 | Trigger | Nello Nappi, Perugia |
|  | 1.2.8 | DAQ | George Redlinger, BNL |
|  | 1.2.9 | Offline Computing | Renee Poutissou, TRIUMF |
|  | 1.2.10 | Detector Systems | Ralph Brown, BNL |
|  | 1.2.11 | Project Services | Steve Kane, BNL |
| MECO | 1.3 |  | M. Hebert, University of California, Irvine |
|  | 1.3.1 | Extinction | W. Molzon (acting), UC Irvine |
|  | 1.3.2 | Production Target and Shield | M. Hebert (acting), UC Irvine |
|  | 1.3.3 | Solenoids | B. Smith, MIT |
|  | 1.3.4 | Muon Beamline | W. Morse, BNL Physics |
|  | 1.3.5 | Tracker | E. Hungerford, Houston |
|  | 1.3.6 | Calorimeter | P. Nemethy, NYU |
|  | 1.3.7 | Cosmic Ray Shield | J. Kane, William & Mary |
|  | 1.3.8 | DAQ & Online Computing | K. Kumar, UMass |
|  | 1.3.9 | Simulations and Offline Analysis | TBD |
|  | 1.3.10 | Installation and Integration | TBD |
|  | 1.3.11 | MECO Project Office | M. Hebert, UC Irvine |
| AGS | 1.4 |  | P. Pile, BNL |
|  | 1.4.1 | AGS/Booster | K. Brown |
|  | 1.4.2 | Switchyard | A. Pendzick |
|  | 1.4.3 | KOPIO | C. Pearson |
|  | 1.4.4 | MECO | D. Phillips |
|  | 1.4.5 | Project Administration | P. Pile |

Rare Symmetry Violating Processes Project

Work Breakdown Structure

Current RSVP WBS Structure
Ver. 2.0 September 23, 2004

WBS 1.0: STAR Time of Flight Project

Work Breakdown Structure

April 29, 2005

System		WBS	Description			System Manager

Project Office		1.1	Project Director		G. Eppley; Rice

Project Engineer		R. L. Brown; BNL

US-China Project	1.2	Project Manager		H. Huang; UCLA

Coordination

Detector-Mechanical	1.3	Project Manager		W. J. Llope; Rice

Systems

Tray Ass’y & Test	1.3.1	Subsystem Manager		J. Hoffmann; UT

Gas System		1.3.2	Subsystem Manager		L. Kotchenda; MEPHI

HV System		1.3.3	Subsystem Manager		V. Ghazikhanian; UCLA

Start Detector		1.3.4	Subsystem Manager		W. J. Llope; Rice

Infrastructure		1.3.5	Subsystem Manager		D. Padrazo; BNL

Electronics Systems	1.4	Project Manager		J. Schambach; UT

Board Purchase &	1.4.1	Subsystem Manager		T. Nussbaum; Rice

Test

Integration & System	1.4.2	Subsystem Manager		T. Nussbaum; Rice

Testing

Installation &		1.4.3	Subsystem Manager		J. Schambach; UT

Commissioning

Configuration &	1.4.4	Subsystem Manager		TBD

Control Software

Low Voltage		1.4.5	Subsystem Manager		V. Ghazikhanian; UCLA

Systems

Contingency Analysis

This document describes how the contingency for a given WBS element is to be calculated.  If a Project Manager or subsystem Manager has a reason why these factors are not appropriate, this must be documented in the Cost Book.

Risk is a function of the following factors:  The sophistication of the technology, the maturity of the design effort, the accuracy of the cost sources and the impact of delays in the schedule.  Risk analysis shall be performed for each WBS element at the lowest level estimated.  Results of this analysis will be related to a contingency which shall be listed for each WBS element.  The goal is to make the method of contingency determination uniform amongst all project WBS elements.

Definitions

Base Cost Estimate – The estimated cost of doing things correctly the first time; UNLESS from past experience you are fairly certain that it will take more time.  In other words, contingency is NOT to be included in the base cost.

Cost Contingency – The amount of money, above and beyond the base cost, that is required to ensure the project's success. This money is used only for omissions and unexpected difficulties that may arise.  Contingency funds are held by the Project Director.

Risk Factors

Technical Risk – Look only at the technical content or technology required to complete the element.  Technical risk has to do with how common the technology is that's required to accomplish the task or fabricate the component.  If the technology is so common that the element can be bought "off-the-shelf", i.e., there are several vendors that stock and sell the item, it has very low technical risk, therefore a risk factor of 1 is appropriate.  On the opposite end of the scale are elements that extend the current "state-of-the-art" in this technology.  These are elements that carry technical risk factors of 10 or 15.  Between these are: making modifications to existing designs (risk factor 2-3), creating a new design which does not require state-of-the-art technology (risk factor 4 & 6), and creating a design which requires R&D, and advances the state-of-the-art slightly (risk factor 8 & 10).

Cost Risk – Look only at the data available at the time you establish an estimate of the cost.  It may help to subdivide cost risk into 4 categories.

The first category is for elements for which you have a recent price quote from a vendor or a recent catalog price. If the price of the complete element, or the sum of its parts, can be found in a catalog, the appropriate risk factor to be applied is 1. If you have an engineering drawing or specification for the element, and a reliable vendor has recently quoted a price based on these, the cost risk factor to be applied is 2. Similarly, if a vendor has quoted a price based on a sketch that represents the element, and the element's design will not change prior to its fabrication, the appropriate cost risk factor would be 3.

The second category is for elements for which you or your institution has some relevant experience.  If the element is similar to something you've done previously, and you know the cost of this similar experience, the cost risk factor is 4.  If the element is something in which you have not had recent experience, but is something which your institution is capable of doing, the cost risk is 6.  If the element is not necessarily similar to something you have done before, and is not similar to your institutions' in-house capabilities, but is something that your institution feels comfortable estimating, the risk factor is 8.

The third category is for elements for which you have information that, when scaled, can give insight into the cost of an element or series of elements.  The cost risk factor for this category is 10.

The fourth category is for elements for which you have made a more or less educated guess, using your judgment as an engineer or physicist.  If you have had experience of a similar nature, but not necessarily designing, fabricating or installing another device, and feel comfortable estimating the labor type and quantity necessary to perform this function, a cost risk factor of 15 would be appropriate.

If you do not have suitable background or experience to estimate an item, don't estimate it yourself, ask someone with more appropriate experience to estimate it for you.  If you do it yourself anyway, you can see how in some cases the appropriate contingency could be thousands of per cent and all the guidelines in the world for establishing contingency wouldn't do any good!

Schedule Risk – If a delay in the completion of the element could lead to a delay in a critical path or near critical path component, the schedule risk is 8.  If a delay in the completion of the element could cause a schedule slip in a subsystem which is not on the critical path, the schedule risk is 4.  Only elements where a delay in their completion would not affect the completion of any other item have schedule risks of 2.

Design Risk – Directly related to the maturity of the design effort. When the element design is nearly complete, quantity counts and parts lists finished, the risk associated with design maturity is for all intents and purposes nil; therefore a risk factor of 0 is applied.  This is also the case when the element is an "off-the-shelf" item and the parts counts and quantities are finalized.  When the element is still just an idea or concept, with crude sketches the only justification for the cost estimate, the risk associated with design state is high or 15.  Between these two extremes are the stages of conceptual design and preliminary  design.  In conceptual design, when layout drawings of the entire element are approaching completion, some preliminary scoping analyses have been completed, and parts counts are preliminary, the design risk factor is 8.  During preliminary design, when there are complete layout drawings, some details worked out, complete parts counts, and some analysis for sizing and showing design feasibility, the appropriate design risk is 4.

Weighting Factors

The weight applied to the risk factors depends on whether their are multiple or single risks involved in completing an element.

The weights applied to technical risk depend upon whether the element requires you to push the current state-of-the-art in design, manufacturing, or both.  Obviously, if the element requires you to push both, the weight to be applied is high, or 4; if either the design or manufacturing are commonplace, the weighting factor is 2.

For weights applied to cost risk, the two factors are material costs and labor costs.  If either of these are in doubt, but not both, the weight to be applied to cost risk is 1.  If they are both in doubt, the weight applied is 2.

The weight factor given to schedule risk is always 1.

The weight factor given to design risk is always 1 and so is not shown explicitly.

Procedure

The following is the procedure for estimating contingency. If you are using the Project Access database to enter the estimate, these risk and weighting factors can be input directly, and Access will perform the calculations for Steps 3-5 automatically. If the task is complete, the contingency should be equal to zero:

Step 1 – Compare the conceptual state of the element with Table 1 to determine risk factors.  A technical risk factor is assigned based on the technology level of the design.  A design risk factor is assigned based upon the current state (maturity) of the design.  A cost risk factor is assigned based on the estimating methodology used to arrive at a cost estimate for that element.  Similarly, a schedule risk factor is identified based on that element's criticality to the overall schedule.

Step 2 – Compare the potential risk within an element with Table 2 to determine the appropriate weighting factors.

Step 3 – Multiply the individual risk factors by the appropriate weighting factors and then sum them to determine the composite contingency percentage.

Step 4 – Do this for each element at its lowest level.

Step 5 – Calculate the dollar amount of contingency for an element by multiplying the base cost by the composite contingency percentage.

TABLE 1

TECHNICAL, COST, SCHEDULE and DESIGN RISK FACTORS

Risk Factor Technical Cost Schedule Design 0 Not used Not used Not used Detail design > 50% done 1 Existing design and off-the-shelf H/W Off-the-shelf or catalog item Not used Not used 2 Minor modifications to an existing design Vendor quote from established drawings No schedule impact on any other item Not used 3 Extensive modifications to an existing design Vendor quote with some design sketches Not used Not used 4 New design; nothing exotic In-house estimate based on previous similar experience Delays completion of non-critical subsystem item Preliminary design >50% done; some analysis done 6 New design; different from established designs or existing technology In-house estimate for item with minimal experience but related to existing capabilities Not used Not used 8 New design; requires some R&D but does not advance the state-of-the-art In-house estimate for item with minimal experience and minimal in-house capability Delays completion of critical path subsystem item Conceptual design phase; some drawings; many sketches 10 New design of new technology; advances state-of-the-art Top-down estimate from analogous programs Not used Not used 15 New design; well beyond current state-of-the-art Engineering judgment Not used Concept only

TABLE 2

TECHNICAL, COST, SCHEDULE and DESIGN WEIGHTING FACTORS

Risk Factor Condition Weighting Factor Technical Design OR Manufacturing 2 Design AND Manufacturing 4 Cost Material Cost OR Labor Rate 1 Material Cost AND Labor Rate 2 Schedule Same for all 1 Design Same for all 1