Managing Risk as a Resource using the Defect Detection and Prevention process

Steven L. Cornford, Ph.D

Jet Propulsion Laboratory

California Institute of Technology

Pasadena, CA 91109

NASA Code QE is funding a number of programs to develop and implement improvements in the efficacy and efficiency of Verification and Validation and Risk Management processes for space-flight projects. A physics-of-failure-based Defect Detection and Prevention (DDP) methodology has been developed and is currently being implemented on various JPL projects and as part of JPL’s new model-based development environment.   The DDP process weights the criticality of the various relevant failure modes by including the likelihood and impact on mission requirements.   The net effectiveness of various subsets of PACTs (Preventative measures, Analyses, process Controls and Tests) can then be evaluated against these weighted failure modes to obtain the residual risk for each of these failure modes and the associated resource costs to achieve these risk levels.  This identifies the project-relevant “tall pole” failure modes and design drivers and allows real time tailoring with the evolution of the design and technology content. The Defect Detection and Prevention methodology allows risk management in its truest sense: identifies and assesses risk, provides options and tools for risk decision making and mitigation and allows for real-time tracking of current risk status.

# Introduction

JPL continues to make progress in its challenge from NASA to fabricate and operate spacecraft Faster, Better and Cheaper (FBC)[].  No longer is the posture one of risk avoidance but rather one of risk management.  A key element of NASA/JPL’s Risk Management approach is to consider “risk as a resource”[].   Like schedule, mass and power, risk is now a resource to be traded against other resources and optimized subject to constraints.  This process has been partially enabled by the NASA Code Q focus on developing better tools and methods for managing risk .

The typical NASA/JPL  project development cycle is evolving to an 18 month development cycle in which decisions will need to be made almost “real-time” in a model-based development environment.  Like any decision, there is a chance that it will be wrong.  This leads to the chance that something fails.  This is where risk is introduced - What is the risk of failure due to a given decision or action?  Since risk can be reduced by expending resources, and risk itself is a resource, it would be valuable to have an integrated methodology for trading these resources.

Early decisions usually have the most influence on the project risk, but given the realities of the fast-track spacecraft development cycle, it is often necessary to make decision based on incomplete data.  Furthermore, each of these decisions may result in different, or additional, derived requirements.  The DDP process allows the requirements to be captured, the current risks to be estimated, and allows tradeoffs to be made with the available data.  This data regarding risks and consequences ranges from engineering judgement to actual flight article test data depending on the stage of the project development process.   The DDP process integrates this variety of data in a “top down” approach which is synchronized to the project development cycle.

# Approaches to Measuring Risk

In order to fully utilize risk as a resource, and make quantitative comparisons and decisions, it is necessary to quantify risk (before and after various mitigation activities).  However, some risks are difficult to quantify, especially in ultra-low volume spacecraft fabrication. Historically, experienced engineers used their vast experience to minimize project risk. However, this technique was neither quantitative nor systematic.  Other techniques were introduced to resolve these shortcomings, but each has their own pros and cons, as summarized in Table 1.

Engineering Judgement Pros: Quick and dirty, Tailored to specific project under evaluations, Utilizes the experience of the best and brightest, Widely used Cons: Not systematic or quantitative, Only as good as the expert opinions provided

MIL-STD-217-type Calculations Pros: Systematic approach, Provides detailed failure rate numbers, Includes approach for modifying failure rates due to hardware characteristics, Widely used Cons: Only valid for random failures, Does not address design, workmanship or manufacturing defects

Physics of Failure (For example: []) Pros: Validated models using underlying physics (no guesswork), Identifies specific parameters and points the way to additional experiments or evaluations, Can incorporate stochastic or systematic sources of parametric error, Widely used Cons: Not really applicable for functional performance anomalies (or engineering of failure), Can get extremely complex and difficult to validate if expanded to include all varieties of workmanship or manufacturing defects, Bottoms-up approach which can get very large if extended to spacecraft systems

Table 1  Summary of the pros and cons of various risk measurement techniques

It would be desirable to have an approach that integrates the best of the various current approaches.  At the highest level, the approach should be able to begin with historical corporate data and expert judgement, gaining accuracy and precision, as required, at the lower levels [].  This can come from failure rates, physics of failure modes, “root cause” data from internal or external sources, focused experiments, etc.  The DDP process provides a means of integrating this variety of data.

# DDP Methodology

In addition to integrating the best features of the various means of risk measurement, the process for implementing DDP is systematic and synchronized with the project life cycle.  It can capture the evolving requirements, document the rationale for decisions (so they could be revisited later with better information) and provide a current ranked risk list to provide focus for the project design team.   It is also integrable into JPL’s future model-based development environment.

## DDP is a Four-step Process

The application of the DDP process involves four steps: 1) Develop the Requirements Matrix, 2) Develop the Effectiveness Matrix, 3) Optimize the Residual Risk (subject to constraints) and 4) Iterate with the Project Life Cycle. The key constituents of these steps of the DDP process are the Failure Modes (or Mechanisms at lower levels), Mission/Project Requirements (may be derived requirements at lower levels) and the suite of available PACTs.   The Failure Modes, Requirements and PACTs occur at various levels that range from mission level down to the device or semiconductor level.  The DDP process is tailored to evolve with the project development cycle to allow risk elements to be identified as early as possible and remain consistent with the necessary initial allocation of resources and facility scheduling.

The Failure Modes may be found by a variety of techniques: Fault Trees, FMECAs, Brainstorming with “critical mass” of experts, etc.  As lower levels of failure modes are identified, they will eventually reach the “root cause” or mechanism level and standard physics of failure evaluations may be performed as required.  However, one of the key goals of the DDP process is to allow “good enough” decisions to be made at as high a level as possible.  These identified failure modes are critical to the DDP process and show up in both the Requirements Matrix and in the Effectiveness Matrix which are described below.

## Developing the Requirements Matrix (RM)

The RM (see Figure 1) consists of mapping failure modes against the requirements where the entries in the matrix are an evaluation of the impact on the requirement should the failure mode occur.  Note that the requirements may be individually weighted relative to their importance and the failure modes may be weighted by their a priori probability of occurrence (i.e. with no mitigation activities) - in most cases this weighting factor is chosen to be 1.0.

The primary utility of the RM is to identify the “tall pole” failure modes; that is,  the sum of the impacts (and likelihood) of a particular failure mode on all of the weighted requirements.  Repeating this for all of the failure modes, and sorting by magnitude of residual risk provides a list of the “tall pole” failure modes.  This list is essentially equivalent to the well-known Significant Risk List.

The requirements may also be evaluated to identify “design drivers” and irrelevant requirements.   This is accomplished by summing across all failure mode impacts, for a given requirement, to accumulate a total representing the extent to which various requirements are impacted by the potential failure modes.

## Developing the Effectiveness Matrix (EM)

The EM consists of evaluating the effectiveness of the various PACT options effectiveness (i.e. probability of NOT detecting or preventing) against the weighted failure modes (see Figure 1).  PACT options for detecting and preventing failure modes range from design rules to system level tests and have varying effectiveness against different failure modes.   The goal is to select the minimum set that achieves the desired risk level within constraints.

The entries in the EM represent the chance for “escape” and the product of these entries, for a given failure mode, yield the residual risks.  The EM is thus the means by which to evaluate the overall effectiveness of a given PACT collection.  The determination of the effectiveness of a given PACT on a given failure mode can be accomplished a number of ways.  One can use historical data, results of experiments or measurements, at the “root cause” level one can also use data from the literature.

Figure 1  The Requirements and Effectiveness matrices.

## Optimizing the Residual Risk

One can now form the product for each failure mode, of the impact should it occur, with the likelihood that it will escape into the mission, and the result is the residual risk.  Since each PACT has varying effectiveness against different failure modes, one can (and must) “mix and match” different PACT combinations each of which has associated resource expenditures.  For example, a design decision like additional shielding or redundancy may require more mass, while a decision to perform a test means allocation of schedule and money.  Figure 2 illustrates the Risk Balance for a given scenario.  Note that the line in the risk balance is the location where each failure mode is receiving risk reduction proportional to its importance.

### Iterate versus Project Life Cycle

As discussed previously, the requirements and hardware maturity evolve with the project life cycle.  Their refinement to lower levels may result in modification of various levels of requirements.   Similarly, the evolution of the design results in evolved failure modes.  The DDP process allows one to capture these changes, evaluate their impact on the “tall pole failure modes”, identify design drivers, update the Effectiveness matrix and re-evaluate the Residual Risk.

# Summary

The Defect Detection and Prevention process for risk management has been described.  This process evaluates the impact of the project relevant failure modes on the project requirements.  It then evaluates the effectiveness of a given collection of PACTs and allows optimization of this collection subject to resource constraints.  It identifies the current “tall pole failure modes” (residual risk) and design drivers, documents decision rationale, and provides a current list of the project-required PACTs.  It also can identify areas where focused studies are required.

The DDP is currently in use at JPL and has seen a variety of pilot applications from the spacecraft level to Multi-chip module level.  The tool for implementation is currently spreadsheet-based, but a relational data-based tool which can accommodate Monte Carlo evaluations using statistical distributions of effectiveness and impact entries.  After a number of pilot implementations, we have accumulated a number of lessons learned that will be the subject of another paper.  Briefly, there must be concurrent usage of a  “critical mass” of expertise and the process is more quickly performed at lower levels of assembly (e.g. a given technology or device).

# Acknowledgements

I would like to thank Philip Barela, Dr. Gary Blackwood, Mark Gibbel, Tom Gindorf, Dr. Michael Greenfield and Tim Larson for many valuable discussions.  I would also like to thank the members of the Reliability Technology group for their help in implementing and refining the DDP methodology.

The research described in this paper was carried out by the Jet Propulsion Laboratory, California Institute of Technology under a contract with the National Aeronautics and Space Administration through Code Q.

#### References

# Footnotes

I am using the word “failure” here in its broadest sense: failure to meet all of the mission/project requirements.

PACTs are everything which can be done to prevent or detect failures; PACT= Preventative measures, Analyses, process Controls and Tests.

# Endnotes

.  National Aeronautics and Space Administration, NASA Strategic Management Handbook, Washington D.C., April 1996b

.   M. A. Greenfield and T. E. Gindorf, Risk as a Resource – A New Paradigm, Proceedings of the ESREL 96 – PSAM III Conference,  Create, Greece, Vol. 3,  pp. 1597, Springer-Verlag, Berlin, June 24 – 28, 1996

.   Liam Sarsfield, “The Cosmos on a Shoe String”, RAND Critical Technologies Institute, Washington D. C., MR-864-OSTP, 1998

.   For example, M. Sander, “Develop New Products Project”, JPL Internal document, 1997

.  P.Lall, M.Pecht, “An Integrated Physics-of-Failure Approach to Reliability Assessment”, Advances in Electronic Packaging, ASME EEP-Vol.4-1, 1993.

.   S. Cornford and M. Gibbel, Methodology for Physics & Engineering of Reliable Products, WESCON 96 Proceedings, Anaheim, CA, October 22-24, 1996

# Text boxes

Figure 2  Graphical depiction of the multiplication of the impacts of the identified failure modes and the probability of escaping the selected detection and prevention activities.