# Initiatives to Eliminate the Social Security Administration Hearing Backlog

# Status as of December 28, 2007

# Introduction

In his testimony to Congress on May 23, 2007, Commissioner Astrue reported that the Social Security Administration (SSA) has developed a four-pronged plan to eliminate the backlog of requests for hearings and prevent its recurrence, based on (1) compassionate allowances; (2) improving performance; (3) increasing adjudicatory capacity; and

(4) increasing efficiency with automation and business processes.  This report covers the status of initiatives 2, 3 and 4 as of the end of Fiscal Year 2007.  The Office of Disability and Income Security Programs (ODISP) has responsibility for initiative 1, compassionate allowances.

# Improving Hearing Performance

- Reduce Aged Cases – In Fiscal Year 2007 (FY 07) the Office of Disability and Adjudication Review (ODAR) had 63,770 cases that would be over 1,000 days old as of 09/28/07.  At the end of FY 07, 108 aged cases remained.  For FY 2008, aged cases were redefined as cases that would be 900 days old or older by 09/26/2008.  Entering FY 08, 135,160 aged cases remained in this category.  As of close of business December 28, 2007, the hearing operation reports 88,176 aged cases pending 900 days or more.

- Study Authorization of Senior Attorney Adjudicators – The interim final rule was published 08/09/07 providing certain attorney advisors the ability to adjudicate fully favorable decisions.  This initiative was implemented on 11/01/07 with the release of a Chief Judge Bulletin.  As of 12/28/07, 2530 Senior Attorney decisions have been issued.

- Hire Additional Administrative Law Judges (ALJs) – Based on the certificate of eligible candidates provided by the Office of Personnel Management, ODAR will interview 427 candidates during the period 01/08/08 – 02/01/08.  Interviews will be conducted by teams of Administrative Law Judges (ALJs) using standardized interview questions.  ODAR anticipates hiring up to 150 ALJs.

# Increase Adjudicatory Capacity

- Fill ALJ Dockets to Capacity – We are continuing the successful overtime initiative of the Deputy Commissioner of Operations (DCO) with 15,000 hours allocated to DCO for the first quarter of FY 08.   As of 12/28/07, DCO employees worked 14,208 hours of overtime and completed over 124,000 tasks.  We are also continuing the successful streamlined folder assembly process for pending paper cases.  As of 12/28/07, 6,264 paper cases were identified for streamlined folder assembly and 2,057 of these were prepared by DCO employees.  We plan to continue encouraging ALJs to use this method of case preparation to prepare the remainder of our paper backlog cases for hearing.

# Improve ALJ Productivity – The Chief Administrative Law Judge issued a letter to all ALJs on October 31, 2007, asking them to issue 500 – 700 legally sufficient decisions each year, move cases out of ALJ-controlled categories on a timely basis and hold scheduled hearings absent a good reason to cancel or postpone hearings.

- Remand Cases to Disability Determination Services (DDSs) - For the first quarter of FY 08, the Informal Remand initiative concentrated on eight of the states with the largest paper backlogs.  More than 13,000 cases from these eight states were remanded to DDSs in the first quarter of FY 08.  From 10/01/07 through 12/28/07, 9,050 Informal Remands were processed by the DDSs, with a reversal rate of 37 percent.  These were a mix of cases that had been sent to the DDSs during FY 07 and cases that were sent to the DDSs at the beginning of FY 08.  Planning is currently underway to continue this initiative for the second quarter of FY 08.

- Implement Medical Expert Screening Process – There are two aspects to this initiative: (1) By using interrogatories, ALJs secured additional information on childhood cases from Pediatric Medical Units (PMUs) in Boston and Seattle.  Approximately 170 cases were sent to the PMUs.  (2) Using profiles, hearing offices will identify cases that could benefit from a review by a medical expert prior to assignment of the case to an ALJ.  Three interrogatory templates (two for adults and one for children) were developed using the Office of Quality Performance (OQP) profile scores.  These have been vetted by the Disability Policy Council, the Office of Disability Programs, and the Office of General Counsel.  The medical expert will provide written answers to a brief set of questions.  If the answers suggest the claimant is disabled, the case will be routed to an adjudicator for review and final decision.  If the answers do not result in a favorable decision being issued, the written answers will be included in the record.  We are awaiting a legal opinion from the Office of General Counsel before this project can begin.

- Open National Hearing Center (NHC) – The NHC opened in October.  The first 100 cases were received from the Cleveland Hearing Office.  After an initial period of training for new staff, attorneys and legal assistants began working from this location on 11/05/07.  On 12/17/07, Chief Judge Frank Cristaudo conducted the first hearing in the National Hearing Center and issued a favorable decision on the case prior to the Christmas holidays.  Judge Gill, the Acting Chief Judge of the NHC, also conducted NHC hearings the week of December 17, 2007, supporting the Cleveland hearing office.  To date, the NHC has conducted 18 video hearings.  During December 2007, the Office of the Chief Administrative Law Judge (OCALJ) made arrangements with the Atlanta and Chicago Regions to send cases from the Atlanta and Detroit Hearing Offices on a monthly basis to the NHC.  In January 2008, Deputy Chief Judge Nancy Griswold will also be conducting hearings at the NHC.  Two more ALJs reported to the NHC the week of January 7, 2008.

# Increasing Efficiency with Automation and Improved Business Process

- Develop a New Case Processing and Management System for the Appeals Council – A Case Processing and Management System is scheduled to be released in late January 2008.

- Increase Amount of Data Propagated to the HO Case Processing System – Case Processing and Management System (CPMS) enhancements in

January 2008 will provide additional propagated information from the Disability Determination and Transmittal (SSA-831) into the Case Processing and Management System (CPMS).

- Provide the Ability to Sign Decisions Electronically – The ability for ALJs and Senior Attorneys to sign cases electronically is expected to be in place by late January 2008.

- Centralize Printing and Mailing – A pilot will begin in four hearing offices to test this functionality on January 28, 2008.

- Enhance Hearing Office Management Information - ODAR continues to develop tracking mechanisms and data sheets to provide support to management at all levels.  New Disability Adjudication Reporting Tools (DART) reports have recently been developed for tracking aged cases, informal remands and Senior Attorney Adjudicator dispositions on a daily basis.  The CPMS release scheduled for late January 2008 will include additional reports to support the Senior Attorney Adjudicator program as well as new functionality for workload listing reports.

- Provide Support to Send Additional Documents to the Electronic Folder - Analysis and planning for this initiative are ongoing.

- Provide Shared Access to the Electronic Folder - Enhancements for

January 2008 will include the ability to provide shared jurisdiction allowing temporary transfer of electronic cases for pulling and decision-writing assistance.

- Expand Internet Support for Representatives – With additional Electronic Records Express (ERE) functionality, representatives will be able to view folders electronically through a secure website.  Plans are to pilot the program with selected representatives beginning June 2008.

- Provide Additional Video Hearing Equipment – The 158 new video units acquired with FY 07 funds are now being shipped for installation.  Sites required by service area realignment have been given priority.  ODAR will also begin the testing of desktop video units in FY 08.

- Update Hearing Office Systems Infrastructure – Over $9 million was spent in FY 07 on installations and upgrades of servers, video teleconferencing equipment and telecommunications equipment in the hearing offices and for the set-up of the National Hearing Center in Falls Church, Virginia.  This initiative is continuing in FY 2008.

- Electronic File Assembly (ePulling) – The contract was awarded to ECompex in September 2007 to develop this software.  This software has the potential to automate the identification of duplicate documents, classify documents and sequentially number pages in a document.  Subject matter experts from hearing offices came to headquarters to work on the knowledge base prior to the pilot in November 2007.  The pilot is scheduled for the spring of 2008.

- Implement eScheduling – Planning and analysis for software to automate scheduling of hearings are underway and will continue throughout FY 2008.

Currently, ODAR is meeting with potential vendors to discuss the ODAR business process as it relates to scheduling.

- Transition to the Electronic Folder – During FY 07, ODAR implemented a major change in its business process which involved transition from processing hearings using paper folders to processing hearings using electronic folders.  As of 12/28/07, 65 percent of our pending workload is electronic, with 483,754 electronic folders and 265,308 paper folders.

- Have Appeals Council Issue Final Decisions when Possible to Reduce Remands – In FY 07, Administrative Appeals Judges (AAJs) met with their staffs to discuss ways to identify appropriate cases and provide guidance for issuing final decisions.  During the last quarter of FY 07 and continuing into FY 08, there has been an increase in the number of final decisions issued by the Appeals Council.

- Mandate Findings Integrated Templates (FIT) Decision Writing System –Usage of the FIT by decision writers has continued to increase and FIT was used for over 99 percent of the decisions written in December 2007.  ODAR is developing guidance in preparation for the directive to mandate FIT usage.

- Provide Improved Training to Hearing Office Management Teams – New course curriculum for Hearing Office Directors, Group Supervisors and Hearing Office Chief ALJs was delivered in the summer of 2007.  Training includes Orientation, Distance Learning and onsite classroom training for hearing specific tasks.  In early December 2007, an OCALJ management training website was completed and information for all users will be released shortly.

- Extend Cooperation Between Hearing Offices and Field Office/Area Director Offices –   On 11/19/2007, the Associate Commissioner for Public Service and Operations Support issued a memo to all Regional Commissioners with suggestions to expedite the transfer of appeals to hearing offices.  The memo resulted from a national workgroup made up of representatives from DCO and ODAR to encourage regional and local initiatives for enhanced communication and cooperation.  During FY 07 and continuing into FY 08, there have also been a number of successful initiatives between ODAR, OQP and DCO at the regional and local levels.  ODAR continues to meet cooperatively with other SSA components to address areas of mutual concern.

- Establish a Standardized Electronic Business Process and Conduct Manual Time Allocation Studies – In cooperation with OQP, assessment of best practices in the current business process is underway.  Teams of employees from ODAR and OQP have been visiting hearing offices to analyze the current electronic folder process, identify best practices, problems and risks, and gather information from employee stakeholders to identify what they want and need to improve the

electronic hearing process.  The teams have also been gathering hearing office task times and identifying quality assurance points in the hearing office workflow.  So far, the teams have conducted seven hearing office visits and have an additional five visits scheduled for January 2008.  After these visits are completed, all the data will be analyzed to formulate a proposal for standardized electronic business processes.  On an ongoing basis, the teams are identifying best practices which can be implemented in hearing offices throughout the country.

- Implement Quality Assurance Program for Hearings Process – ODAR is currently working with OQP to develop an in-line review for the hearing office business process as well as a post-adjudicative review process for the Senior Attorney Adjudicator program.  A draft process has been approved by OCALJ and OQP is assisting with the formula for selecting cases for review.  ODAR is currently working on creating a program to capture the information which will be gathered during the review process and writing instructions for the rollout of the initial phase of this program.  ODAR is working on the quality process in conjunction with the standardized electronic business process.

- Expand OQP Review of Reconsideration Denials Using Profiles – OQP will review 14,000 reconsideration denial determinations prior to effectuation to provide feedback to DDS and SSA management, to make recommendations for addressing problems and ultimately to reduce the volume of hearing requests.  This review began in September 2007 and will continue throughout FY 2008.

- Continue Decision Writer Productivity Improvement Initiative

Hearing offices continue to use the decision writer statistical index report introduced in the beginning of FY 07 to assess decision writer productivity.

- Effectuate Temporary Service Area Realignments/Interregional Case Transfers – OCALJ presented the Service Area Realignment Plan to the Commissioner on December 10, 2007, and received approval to implement.  OCALJ is working with the Office of Legislation and Congressional Affairs (OLCA) to facilitate Congressional notification.  Once the Congressional notifications are mailed by OLCA, OCALJ will schedule a conference call with the Regional Chief ALJs to explain the Service Area Realignment plan and answer any questions concerning implementation.  OCALJ anticipates that the plan will be implemented in two phases, with the first phase planned for completion by the end of January 2008.

- Use Weekly Workload Reporting and Monitoring - The Chief Judge continues to strongly encourage managers to monitor workload processing data on a weekly basis.  ODAR is committed to developing workload reports to monitor hearing office performance this way.

- Collocate Remote Hearing Sites with SSA District Offices – The joint workgroup composed of representatives from ODAR and DCO has developed a plan for collocation of hearing offices with district offices that it expects to deliver to the Commissioner by the end of January 2008.

- Improved Public ALJ Alleged Misconduct Complaint Process -The Office of the General Counsel, Office of the Chief Administrative Law Judge, Office of Appellate Operations and Office of Labor Management and Employee Relations have been meeting regularly to make immediate improvements under current rules and to clarify the complaint process for claimants.  The group continues to study the process and to consider improvements, some of which may involve regulatory changes.  The goal is to make the ALJ complaint process both fair and effective for SSA, the ALJs and the American people.