Database Projects

JTrumbo

March 2005

Contents

Freeware & Postgres Mini Sam

Oracle 10 Upgrade

Oracle Rman 10g Testing

Advanced Security Option

Backup & Recovery

Oem10 Installation

Cad

CMS Detector Database

Fundamentals of database design class

Unexpected Pleasures

To be covered in a subsequent project meeting

SDSS

CDF & D0 daily maintenance

Databases Project

JTrumbo

March 2005

Freeware & Postgres Mini Sam

Project manager’s summary

Freeware & Postgres Mini Sam is a 2 pronged project.  Freeware documentation needs updating, dbas need freeware cross training.  Mini Sam is a product created by J.Trumbo last year that allows individual developers to quickly create, destroy, recreate small sam schemas in their own oracle accounts complete with sam seed data.  S.Lebedeva took this schema a step further by transforming it to postgres. Needless to say, this is an experiment in a non Oracle dependant sam.

The postgres ddl was packaged into kits.  Morag Burgon-Lyon at Glasgow is attempting to run a dbserver against this schema, as well as testing and commenting on the postgres product.

R.Jetton has been spending effort cross training in mysql and postgres, including bringing web documentation up to date. This has been an ‘as time permits’ activity.

Resources used (budget, effort)

S.Lebedeva spent ~   writing java code that reads the sam oracle ddl and transforms it to postgres ddl.   35 days

Mini sam to postgres  oct, 27% nov 30% dec & jan , 35% feb,

Freeware documentation 20% mar.

R.Jetton cross training in freeware dba skills and documentation.  3 days.

Jan 5%, Feb&mar 10%

A.Kumar worked with S.Lebedeva as a sam schema consultant.

Schedule/Milestones

Cross training is done as time permits. No schedule has been announced for db server testing on postgres mini sam.

Titles and links

http://www-css.fnal.gov/dsg/external/freeware/

http://www-css.fnal.gov/dsg/internal/sam/index.htm

Databases Project

JTrumbo

March 2005

Oracle Enterprise Manager 10 Installation (OEM10)

Project manager’s summary

D.Bonham is the lead dba, C.Kastner is the lead sysadmin for the OEM 10 implementation. OEM is Oracle Enterprise Manager, proprietary software that monitors, alerts, schedules database and system jobs.  OEM 10 will be installed on Linux machines housed in FCC.  These machines were delivered ~Mar 1, 2005.  OEM 10 implementation must be complete before the Oracle databases move to v10. OEM 10 will need thorough testing and parallel testing against existing databases.  Dsg will continue to put effort into maintenance of both hardware and software in the future.

Resources used (budget, effort)

Resources will include a dba and sysadmin, working together initially for requirements and hardware implementation.

D.Bonham 4 days

Mar. 20%

C.Kastner 2 days

Feb 2%, mar. 9%

Schedule/Milestones

March 2005, machines delivered and setup in FCC.

Dsg would like full implementation by mid May/early June.

Titles and links

http://www-css.fnal.gov/dsg/internal/oem/OEMPlan/OEM10g_hardware_requirements.html

http://www-css.fnal.gov/dsg/internal/oem/OEMPlan/OEM10g_new_machines_setup.html

http://www-css.fnal.gov/dsg/internal/oem/OEMPlan/linux_system_setup_10g.html

Databases Project

JTrumbo

March 2005

Oracle 10 upgrade

Project manager’s summary

Upgrade to Oracle 10 on the books to begin fy 2005.  Normal procedures would demand this upgrade begin, as Oracle 10 has been available for over a year.  Oracle 10 will provide enhancements for streams and backup and recovery of large databases.  The CMS database machines are running Oracle 10, but at this time are not considered mission critical to monitor. Only toolman is being used to monitor the CMS v10 instances.

Resources used (budget, effort)

No resources has been expended on the Oracle 10 upgrade thus far.  Just began thinking of a plan in Mar. 2005.  OEM (Oracle Enterprise Manager) must be upgraded to 10 before the databases, as OEM 9 is incompatible with Oracle 10.

Starting documentation for plan will be based on the CMS experience.

Schedule/Milestones

Oracle 10 upgrade for critical systems is dependant on OEM moving to 10 first. OEM 10 was be covered in another section.

Dsg will begin moving non mission critical databases to 10, those non dependant on OEM 10 for monitoring, in Apr. 2005.   It is not expected all databases will be migrated to Oracle 10 before Oct.

Titles and links

http://www-css.fnal.gov/dsg/internal/cms/CMS/Oracle10gonbagernode_cmscald.htm

http://www-css.fnal.gov/dsg/internal/cms/CMS/upgrade_cmscaldr10103.htm

Databases Project

JTrumbo

March 2005

Oracle Advanced Security Option

Project manager’s summary

R.Jetton has researched the implementation of Oracle Advanced Security Option.  OAS will provide a kerberized logon environment to Oracle databases.  This will be a welcome extra layer of security. However, R.Jetton has found a show stopper. OAS has a 30 byte connect string limitation.  This is too short to handle the Fermi kcron method.  R.Jetton continues as a low priority, discussion with Oracle and Fermi security as to how to get around this issue.  Oracle has suggested using ldap "light-weight directory access protocol", where the ldap server is configured to a) use our kdc's for the kerberos part, and b) automatically map long principals like 

rjetton/krcon/fcdfdata012.fnal.gov@FNAL.GOV 

to 

rjetton@FNAL.GOV

Resources used (budget, effort)

R.Jetton has spent ~48 hours prototyping this technology.

Oct 5%, nov 5%, dec 5%, jan 5%, feb 5% , mar 5%

Schedule/Milestones

Currently this project is being handled as time requires.  There is no scheduled implementation dates.  Previous to this testing, it was hoped OAS would be implemented fy 2005.  Due to the effort from both Oracle and Fermi, this now seems unrealistic unless uninterrupted, dedicated time can be found.  Work and communications between Fermi and Oracle tech support continues.

Titles and links

http://www-css.fnal.gov/dsg/internal/oracle_advanced_security/index.html

Databases Project

JTrumbo

March 2005

Backup & Recovery

Project manager’s summary

The bulk of backup & recovery has been spent trying to get Oracle rman backups to a san, verify the san is writing and not corrupting the data on ied disks, and restoration testing.  A new validate utility must be built & run against the rman disk pieces to insure restorability.  This validate technology had to be learned and tested. Backup and recovery to the san from d0ora1 databases seems to be going smoothly.  Work from d0ora2 has been significantly delayed due to the problems encountered getting the correct qlogic card with firmware that is compatible with the sun systems as well as the clarion arrays.  This issue combined with 1 down time a month for opportunity to ‘test’ on this unique configuration has led to delay.  Dsg cannot say with confidence the san technology scales to vldbs, until the d0ora2 database is successfully taken to the san for a period of testing.

Dsg is also looking to implement san technology to its other instances.  Dsg is planning on purchasing additional san area fy 2005, to use for the cdf backups.

A big success in the backup recovery arena was the flawless full recovery of d0ofprd1 from d0ora2 to the new cdf online machine.  The cdf machine, while in burn in phase was used to stage this recovery. It is significant because d0ofprd1 has been too large for several years for a test recovery to be done.  This recovery gave us benchmarks as to the time it will take to fully recover 1TB from an rman.

Testing rman recoveries from 32b oracle and os installs to 64b oracle and os installs was also test successfully.

Backup and recovery testing for miscomp was done with the tibs technology. Tibs was used for miscomp backups (small database) after the operators left and automated tape backups were no longer available.

Resources used (budget, effort)

D.Bonhan has been performing the rman testing.  53 days.

Nov, 82%(parttime), dec 85%, (pt), jan 80% (pt) , feb 76% (pt), mar. 50%(full time)

S.Kovich has been performing the sysadmin testing on d0ora1 and d0ora2. 14 days.

Schedule/Milestones

Apr. 5, another fiber card will be installed in d0ora2 to see if the san can be seen. We are attempting to have 2 cards available and test both (if necessary) during this downtime. Results of this test may prove we need to purchase a fiber card from sun.

Again, this testing of scalability of backup and recovery is greatly hindered due to a once a month downtime window, and the unique configuration d0ora2 and its clarion array.

Schedule of moving additional database backups to san is dependent on purchase and delivery of san hardware.  D0ora2 & d0ora1 currently are allocated all available san hardware.

Titles and links

http://www-css.fnal.gov/dsg/internal/SAN/san_index.htm

Databases Project

JTrumbo

March 2005

Cad

Project manager’s summary

Cad has been working this year toward the implementation of the 3 tier architecture for TeamCenter Engineering for Ideas.  This implementation of the 2 middle tier servers will host the TeamCenter/Ideas application and the Ansys license server.  Two Sun database server machines will host the Oracle databases.

The middle tier machines are Windows boxes to be supported by A.Romero, the database machines will be 2 Sun solaris boxes supported by C.Kastner.  Dsg will also support the dev/int/prod databases to be installed.

Thus far effort of a couple of hours has been made by A.Romero to assist in the requirement planning and purchase of the mid tier machines. He has not yet installed these machines.

C.Kastner has also spent time doing the requirements and purchase req for the database server machine.

Once all hardware and software is available, implementation of the applications will require resources from both C.Kastner & A.Romero, as well as additional support from dba(s), as C.Kaster has never implemented an Oracle database.

Resources used (budget, effort)

C.Kastner has spent approximately 5 days gathering requirements, writing reqs, etc. We expect more time to be dedicated after the hardware arrives.

A.Romero is waiting for delivery of Windows 2000 Server software for the 2 mid tier machines. This is a requirement for Ideas.

Schedule/Milestones

Hardware for the middle tier arrived mid Feb. A.Romero is waiting for a software delivery before the implementation of the Windows machines can be done.  A.Romero will commence with installation when the software arrives, due within 30 days.

The Sun machines for the database machines are on order.  Should also arrive ~ the first of Apr.

Titles and links

See the license server and oracle server requirements links.

http://www-css.fnal.gov/dsg/internal/cad/index.html

Databases Project

JTrumbo

March 2005

CMS Detector Databases at Fermilab

Project manager’s summary

CMS Detector Database CMS detector databases at Fermi Lab are being used for development, integration of CMS calibration databases. Once developed and tested applications will be deployed on the production databases.  10g database has been deployed for development , integration and production databases.   Development, Integration and production databases are already in place at FERMILAB. Development and integration/production databases are deployed on Dell Power Edge 700 powered with dual 3.2 GHz processors, 2GB of RAM and 2 250Gb of Disks and Linux ES Release 3 .

Oracle Designer is used for all database design and development work including space report and generation of ddls. A review process is established with application data modelers and database support group. All data model design standards are adhered before deployment application in integration and production instances.

Slow Control, Pixel, Calibration and Equipment management schemas are deployed in development databases.  Dsg provides tuning to application developers as needed.

Database replication is being discussed. CMS replication of data from Tier 0 and Tier 1 may be merged in 3D (Distributed Deployment of Databases) project. A test bed has been established between CERN and FERMI to test streams deployment for database replication using 10g.  So far requirement submitted by CMS, the application metadatasystem(RefDB) will be replicated from t0 to t1 site.

A Case study has been presented by Dsg team on database development and deployment during LHC database Workshop for On-line and off-line developers in Jan 2005 at CERN, presented by A.Kumar.

Resources used (budget, effort)

Anil Kumar, primary database administrator  24 days, includes a trip to cern

Oct, 20%, nov 20%, dec 20% jan 20%, feb 20%

Maurine Mihalek , primary system administrator  for uscmsdb01  11.5 days

Oct 20%, nov 15%, dec. 10%, jan 5%, feb 5%, mar. 2%

Stefan Piperov       - Primary System Administrator for uscmsb03 and bager  PPD-EPP

Schedule/Milestones

-  Sep 2004  Upgrade to CMS databases to 10.1.0.3

- Nov 2004  CMS Pixel Data Model Review.

- Jan 2004   Case Study on Database Application Deployment

- Feb 2005   CMS databases patched for Oracle Critical Security Patch

- Oct 2005   Getting Ready for Slice Test. Review data models for application as needed and deploy schema on a need basis.

Presentations/reports/documentations

Case Study on Database Application Deployment LHC Database Workshop at CERN  Jan 205 http://www-css.fnal.gov/dsg/external/workshops/lhc_db_workshop_files/frame.htm

Database Backups at a Glance : http://www-css.fnal.gov/dsg/internal/backups/backups_status_2005.html

Titles and links

CMS Db Support Page http://www-css.fnal.gov/dsg/internal/cms/index.htm

3D Project :   ( Distributed Deployment of Databases ) http://www-css.fnal.gov/dsg/internal/3d/index.htm

Databases Project

JTrumbo

March 2005

Fundamentals of Database Design Class

Project manager’s summary

J.Trumbo wrote and presented a class discussing commercial and freeware database selection criteria, relational design philosophy, lessons learned, etc.  This is a generic class for users not familiar with nuisances of available database technology.

This project consists of a .ppt for a class of ~10 people.  J.Trumbo worked with S.Panacek and M.Votava to design.  Class was given Feb. 2005.   Class discusses mysql, postgres and oracle, the 3 supported databases in DSG.

Resources used (budget, effort)

Approximately 40 hours J.Trumbo

Schedule/Milestones

This class is available for future use. The class size of 10 proved efficient.  Class took ~4 hours to present.

http://www-css.fnal.gov/dsg/external/workshops/index.htm

Databases Project

JTrumbo

March 2005

Unexpected Pleasures

Project manager’s summary

Two issues were raised over the last 3-4 months that have proven unplanned resource usage.  Implementation of the d0 luminosity application and the responsibilities for the cdf online management.

A large request for unavailable space from the d0 lum group on d0ora2 prompted a switch in strategies late in 2004. There was not enough free database space on d0ora2 to house the luminosity database.  Plans had to be made to purchase in additional hardware. In the mean time, to allow loading of data immediately, resources at both the system and dba levels were diverted to setup a temporary database to allow loading to proceed.

Dsg has also taken sysadmin responsibility for cdf’s online environment. This added responsibility came during a time when a new cdf online machine was being installed.  There have been numerous issues with this new responsibility, not the least of which is the discovery that the database backup procedure had data corruption, and the entire backup procedure needed revamping immediately to insure the database be recoverable if necessary.

Resources used (budget, effort)

J.Trumbo  lumimosity, 5 days, cdf 20 days

lum 25% in dec

cdf 15% dec, 25% jan, 50% feb, 65% mar.

N.Stanfield

Lum 20% dec, 4 days

Cdf 10% feb, 2 days

R.Jetton

Lum 6 days

Cdf 24 days

M.Mihalek

Cdf 15 days

A.Kumar

lum, 2 days

S.Kovich

Lum 3 days

Schedule/Milestones

Luminosity hardware is not fully delivered, we are missing disk.  Luminosity will be moved from its temporary box/instance to Oracle 10 on the new box as soon as the hardware arrives. Hardware includes a new dev and prod box, disks for prod, disks for dev are being recycled from d0mino.

Dsg took responsibility for the cdf online database machines feb. 28, 2005, in coordination with the RunII department.  Simultaneously, Dsg is implementing the replacement box for cdf online production, and a new backup recovery method for the database.

Titles and links

Several links for cdf online plans under

http://www-css.fnal.gov/dsg/internal/cdf_onl_dbs/index.htm

Luminosity

http://www-css.fnal.gov/dsg/internal/d0_ofl_dbs/D0_databases_servers_linux/index.htm