## Project Plan
Regional Logistics Program Project Plan EXAMPLE
Tasks |  | % Complete | Labor/ Work | Duration | Start Date | End Date | Dependencies | Resources
Logistics Planning
Develop CONOPS and Supporting Manuals |  |  | 307 hours | 218 days | 2008-09-01 | 2009-07-01
1 | Collect and review existing plans, agreements, and MOUs, using Synch Matrix (sources should include national, regional, and local documents) |  | 70 hours | 45 days | 2008-09-01 | 2008-10-31 17:00 | N/A
2 | Generate draft of CONOPS to address capability gaps and optimize resource deployment |  | 40 hours | 45 days | 2008-11-03 08:00 | 2009-01-02 17:00 | 1
3 | Generate draft of Supporting Manuals |  | 40 hours | 45 days | 2008-11-03 08:00 | 2009-01-02 17:00 | 1
4 | Review of drafts by regional partners |  | 50 hours | 15 days | 2009-01-05 08:00 | 2009-01-23 17:00 | 2,3
5 | Incorporate edits from regional partners |  | 10 hours | 7 days | 2009-01-26 08:00 | 2009-02-03 17:00 | 4
6 | Request independent peer review of document (either by consultants or another jurisdiction) |  | 40 hours | 43 days | 2009-02-04 08:00 | 2009-04-03 17:00 | 5
7 | Incorporate peer review comments and generate final draft of CONOPS |  | 20 hours | 32 days | 2009-04-06 08:00 | 2009-05-19 17:00 | 6
8 | Incorporate peer review comments and generate final draft of Supporting Manuals |  | 20 hours | 32 days | 2009-04-06 08:00 | 2009-05-19 17:00 | 6
9 | Coordinate final drafts through regional partners |  | 15 hours | 18 days | 2009-05-20 08:00 | 2009-06-12 17:00 | 7,8
10 | Issue final plans/manuals |  | 2 hours | 13 days | 2009-06-15 08:00 | 2009-07-01 17:00 | 9
Establish Support System |  |  | 1048 hours | 478 days | 2008-10-01 | 2010-07-30
11 | Site local logistics centers (LLC) in local jurisdictions |  | 240 hours | 108 days | 2008-10-01 08:00 | 2009-02-27 17:00 | N/A
12 | Begin to meet with federal, state and local logistics professionals, procurement officers, vendors, and transporters |  | 500 hours | 133 days | 2009-03-02 08:00 | 2009-09-02 17:00 | N/A
13 | Plan Regional Logistics Council (RLC) meeting |  | 10 hours | 10 days | 2009-08-20 08:00 | 2009-09-02 17:00 | N/A
14 | Convene Regional Logistics Council (RLC) and coordinate planning and capacity building |  | 8 hours | 1 day | 2009-09-03 | 2009-09-03 | 13
15 | Begin to establish blanket purchase agreements with vendors throughout the country |  | 240 hours | 129 days | 2009-09-04 08:00 | 2010-03-03 17:00 | 14
16 | Meet with non-profit groups to plan and build event capacity |  | 60 hours | 107 days | 2010-03-04 08:00 | 2010-07-30 17:00 | 15
Determine Staff, Supply, and Equipment Sources |  |  | 430 hours | 152 days | 2008-10-01 | 2009-04-30
17 | Establish requirements for staff, supplies and equipment |  | 30 hours | 33 days | 2008-10-01 08:00 | 2008-11-14 17:00 | N/A
18 | Assess local, state, and other regional partners for capability to meet requirements and determine needs |  | 120 hours | 44 days | 2008-11-17 08:00 | 2009-01-15 17:00 | 17
19 | Develop a work plan for closing shortfalls (mix of contracts, MOUs, EMAC requests and federal mission assignments) |  | 15 hours | 21 days | 2009-01-02 08:00 | 2009-01-30 17:00 | N/A
20 | For contracts and MOUs, assess local, state, and federal (GSA) contracts for applicable vendors |  | 40 hours | 20 days | 2009-02-02 08:00 | 2009-02-27 17:00 | 19
21 | For contracts and MOUs, assess vendors' capability to deliver good or service |  | 30 hours | 10 days | 2009-03-02 08:00 | 2009-03-13 17:00 | 20
22 | For contracts and MOUs, determine and list any items that are required and not on contract |  | 10 hours | 10 days | 2009-02-02 08:00 | 2009-02-13 17:00 | N/A
23 | Determine if items required and not on contract are stockpile requirements or if there is an acceptable level of risk to allow "just in time" delivery |  | 20 hours | 20 days | 2009-02-16 08:00 | 2009-03-13 17:00 | 22
24 | For contracts and MOUs, draft specifications and scopes of work for each good or service |  | 40 hours | 20 days | 2009-02-02 08:00 | 2009-02-27 17:00 | N/A
25 | Release specifications and scopes of work for bidding purposes |  | 5 hours | 10 days | 2009-03-02 08:00 | 2009-03-13 17:00 | 24
26 | Develop plan to address post-disaster donations management |  | 120 hours | 34 days | 2009-03-16 08:00 | 2009-04-30 17:00 | N/A
Solicit Feedback from all Regional Stakeholders |  |  | 600 hours | 195 days | 2008-09-01 | 2009-05-29
27 | Solicit comments from regional stakeholders on all plan components |  | 120 hours | 65 days | 2008-09-01 08:00 | 2008-11-28 17:00 | N/A
28 | Coordinate interim drafts of manuals with regions |  | 80 hours | 45 days | 2008-12-01 08:00 | 2009-01-30 17:00 | 27
29 | Beta test site assessment materials with each regional stakeholder |  | 400 hours | 85 days | 2009-02-02 08:00 | 2009-05-29 17:00 | 28
Pre-Script Mission Assignments for State, EMAC, and Federal Assets |  |  | 340 hours | 196 days | 2008-09-01 | 2009-06-01
30 | Identify external pre-packaged assets |  | 180 hours | 65 days | 2008-09-01 08:00 | 2008-11-28 17:00 | N/A
31 | Map how, where and when external support assets support overall response |  | 60 hours | 65 days | 2008-12-01 08:00 | 2009-02-27 17:00 | 30
32 | For EMAC and federal mission assignments, pre-script and pre-coordinate the requests with NEMA and FEMA |  | 100 hours | 66 days | 2009-03-02 08:00 | 2009-06-01 17:00 | 31
Establish Commodity Distribution Sites |  |  | 615 hours | 174 days | 2009-01-01 | 2009-09-01
33 | Determine operational model (type, location, layout) |  | 300 hours | 65 days | 2009-01-01 08:00 | 2009-04-01 17:00 | N/A
34 | Identify and map large open areas (1-2 acres) |  | 180 hours | 44 days | 2009-04-02 08:00 | 2009-06-02 17:00 | N/A
35 | Assess locations for usability (site visits) |  | 15 hours | 22 days | 2009-05-04 08:00 | 2009-06-02 17:00 | N/A
36 | Develop site-specific layout for each location |  | 60 hours | 31 days | 2009-06-03 08:00 | 2009-07-15 17:00 | 35
37 | Develop prepared public information messages about distribution centers |  | 60 hours | 21 days | 2009-08-04 08:00 | 2009-09-01 17:00 | 36
Establish Staging Areas |  |  | 555 hours | 174 days | 2009-01-01 | 2009-09-01
38 | Identify and map large open areas (5+ acres) |  | 180 hours | 42 days | 2009-01-01 08:00 | 2009-02-27 17:00 | N/A
39 | Assess locations for usability (site visits) |  | 15 hours | 20 days | 2009-02-02 08:00 | 2009-02-27 17:00 | N/A
40 | Develop site-specific layout for each location |  | 60 hours | 33 days | 2009-03-02 08:00 | 2009-04-15 17:00 | 39
41 | Work with FEMA/States to operationalize staging areas |  | 300 hours | 99 days | 2009-04-16 08:00 | 2009-09-01 17:00 | 40
Identify Fleet Assets (Local, State, Federal) |  |  | 270 hours | 88 days | 2008-10-01 | 2009-01-30
42 | Coordinate with local, state, federal agency fleet managers to include their assets in the supply chain, as appropriate |  | 250 hours | 88 days | 2008-10-01 08:00 | 2009-01-30 17:00 | N/A
43 | Create central tracker to maintain data and agency managers' contact information |  | 20 hours | 88 days | 2008-10-01 08:00 | 2009-01-30 17:00 | N/A
Develop Delivery Routes |  |  | 100 hours | 129 days | 2009-09-02 | 2010-03-01
44 | Establish delivery routes from staging areas to commodity distribution areas |  | 80 hours | 87 days | 2009-09-02 08:00 | 2009-12-31 17:00 | 37,41
45 | Prioritize debris removal operations to align with priority supply routes |  | 20 hours | 41 days | 2010-01-04 08:00 | 2010-03-01 17:00 | 44
Establish Strategic Communications Plan and Backup Plan to Link all Logistics Elements |  |  | 380 hours | 174 days | 2009-02-02 | 2009-10-01
46 | Identify all major decision points for purchasing, requesting and mobilizing assets (e.g. local/state/federal disaster declarations, hazards projected to hinder logistics support operations, etc.) |  | 300 hours | 174 days | 2009-02-02 08:00 | 2009-10-01 17:00 | N/A
47 | Track decision points through a process map or flow chart |  | 80 hours | 174 days | 2009-02-02 08:00 | 2009-10-01 17:00 | N/A
Develop Master Time-Phased Force Deployment List |  |  | 185 hours | 132 days | 2009-06-01 | 2009-12-01
48 | Identify all major decision points for purchasing, requesting and mobilizing assets (e.g. local/state/federal disaster declarations, hazards projected to hinder logistics support operations, etc.) |  | 20 hours | 45 days | 2009-06-01 08:00 | 2009-07-31 17:00 | N/A
49 | Set timeline goals for mobilizing support assets |  | 15 hours | 23 days | 2009-08-03 08:00 | 2009-09-02 17:00 | 48
50 | Develop a time-phased matrix based on decision points, timing goals and expected asset availability over time |  | 150 hours | 64 days | 2009-09-03 08:00 | 2009-12-01 17:00 | 49
Plan Security for all Logistics Elements |  |  | 480 hours | 110 days | 2009-04-01 | 2009-09-01
51 | Develop plan to address post-disaster regional credentialing |  | 300 hours | 43 days | 2009-04-01 08:00 | 2009-05-29 17:00 | N/A
52 | Test the plan, as developed, through RCPGP activities via a HSEEP compliant drill or exercise |  | 100 hours | 11 days | 2009-06-01 08:00 | 2009-06-15 17:00 | 51
53 | Determine availability of local, state, and federal assets |  | 40 hours | 34 days | 2009-06-16 08:00 | 2009-07-31 17:00 | 52
54 | Pre-determine EMAC and Federal requests for security assistance (pre-locate teams) |  | 40 hours | 22 days | 2009-08-03 08:00 | 2009-09-01 17:00 | 53
Examine Impact of Hazards to Regional Food Suppliers |  |  | 215 hours | 108 days | 2009-02-02 | 2009-07-01
55 | Complete risk assessment (hazard impact to food commerce) |  | 120 hours | 43 days | 2009-02-02 08:00 | 2009-04-01 17:00 | N/A
56 | Meet with key representatives from the retail food industry |  | 15 hours | 32 days | 2009-04-02 08:00 | 2009-05-15 17:00 | 55
57 | Develop framework for regional food supply recovery plan |  | 80 hours | 33 days | 2009-05-18 08:00 | 2009-07-01 17:00 | 56
Demobilization |  |  | 190 hours | 66 days | 2009-04-01 | 2009-07-01
58 | Develop plan for facility consolidation as event de-escalates |  | 80 hours | 33 days | 2009-04-01 08:00 | 2009-05-15 17:00 | N/A
59 | Develop process for coordinating redistribution of excess supplies |  | 80 hours | 32 days | 2009-05-01 08:00 | 2009-06-15 17:00 | N/A
60 | Coordinate deactivation of staff |  | 30 hours | 23 days | 2009-06-01 08:00 | 2009-07-01 17:00 | N/A
Rollout Meetings with Regional Stakeholder |  |  | 124 hours | 66 days | 2009-09-01 | 2009-12-01
61 | Develop project plan for rolling out plan templates to stakeholders |  | 90 hours | 22 days | 2009-09-01 08:00 | 2009-09-30 17:00 | N/A
62 | Assign planners as "consultants" to groups of stakeholders |  | 6 hours | 8 days | 2009-09-21 08:00 | 2009-09-30 17:00 | N/A
63 | Conduct rollout planning meetings with stakeholders |  | 8 hours | 10 days | 2009-10-01 08:00 | 2009-10-14 17:00 | 62
64 | Meetings and support to stakeholders as they roll out the program |  | 20 hours | 34 days | 2009-10-15 08:00 | 2009-12-01 17:00 | 63
Developing HSEEP Plan |  |  | 400 hours | 217 days | 2009-05-01 | 2010-03-01
65 | Following development of each plan or manual, it will be tested using one or more Homeland Security Exercise and Evaluation Program (HSEEP) compliant exercise method, ranging from decision-making tabletops to functional exercises |  | 400 hours | 217 days | 2009-05-01 08:00 | 2010-03-01 17:00 | N/A
Establish ALERT Teams
Develop Training Curricula |  |  | 300 hours | 88 days | 2008-07-31 | 2008-12-01
66 | Contract with vendor to develop classroom-based training program |  | 20 hours | 22 days | 2008-07-31 08:00 | 2008-08-29 17:00 | N/A
67 | Develop curriculum |  | 80 hours | 32 days | 2008-09-02 08:00 | 2008-10-15 17:00 | 66
68 | Determine field training requirements |  | 40 hours | 32 days | 2008-09-02 08:00 | 2008-10-15 17:00 | N/A
69 | Establish activation and notification protocols for staff |  | 40 hours | 32 days | 2008-09-02 08:00 | 2008-10-15 17:00 | N/A
70 | Meet with jurisdictions to solicit feedback on training curriculum |  | 60 hours | 12 days | 2008-10-16 08:00 | 2008-10-31 17:00 | 67-69
71 | Incorporate comments from regional jurisdictions into training program |  | 20 hours | 10 days | 2008-11-03 08:00 | 2008-11-14 17:00 | 70
72 | Pilot training curriculum |  | 40 hours | 11 days | 2008-11-17 08:00 | 2008-12-01 17:00 | 71
Recruit Team |  |  | 480 hours | 197 days | 2008-07-31 | 2009-05-01
73 | Identify team leadership |  | 80 hours | 67 days | 2008-07-31 08:00 | 2008-10-31 17:00 | N/A
74 | Recruit team members from UASI jurisdictions |  | 320 hours | 107 days | 2008-11-03 08:00 | 2009-03-31 17:00 | 73
75 | Conduct staff training |  | 80 hours | 23 days | 2009-04-01 08:00 | 2009-05-01 17:00 | 74
Train Team |  |  | 3000 hours | 412 days | 2009-01-01 | 2010-07-30
76 | Schedule training for teams throughout the site |  | 200 hours | 108 days | 2009-01-01 08:00 | 2009-06-01 17:00 | N/A
77 | Complete training according to schedule |  | 2800 hours | 412 days | 2009-01-01 08:00 | 2010-07-30 17:00 | N/A
Develop Notification and Deployment Protocol |  |  | 150 hours | 131 days | 2009-05-01 | 2009-10-30
78 | Establish activation protocol |  | 150 hours | 131 days | 2009-05-01 08:00 | 2009-10-30 17:00 | N/A
Procure Equipment and Supplies |  |  | 310 hours | 261 days | 2009-05-01 | 2010-04-30
79 | Identify standard clothing and supply package for a team member |  | 60 hours | 44 days | 2009-05-01 08:00 | 2009-07-01 17:00 | N/A
80 | Procure and distribute equipment |  | 250 hours | 217 days | 2009-07-02 08:00 | 2010-04-30 17:00 | 79
Technology Support
Incorporate Data into CALMS (or like database) |  |  | 750 hours | 348 days | 2008-10-01 | 2010-01-29
81 | Organize data for CALMS program upload |  | 250 hours | 131 days | 2008-10-01 08:00 | 2009-04-01 17:00 | N/A
82 | Prepare data for upload and to de-conflict potential issues |  | 250 hours | 132 days | 2009-04-02 08:00 | 2009-10-02 17:00 | 81
83 | Upload data into system |  | 250 hours | 85 days | 2009-10-05 08:00 | 2010-01-29 17:00 | 82
Develop Software Program to Link Mission Requests across all Jurisdictions |  |  | 1150 hours | 347 days | 2009-02-02 | 2010-06-01
84 | Conduct analysis of existing federal, state, and local systems |  | 120 hours | 43 days | 2009-02-02 08:00 | 2009-04-01 17:00 | N/A
85 | Develop programming language that can convert local and state mission requests from existing formatting into a system accessible by federal officials and vendors |  | 240 hours | 22 days | 2009-04-02 08:00 | 2009-05-01 17:00 | 84
86 | Review COTS solutions for resource tracking |  | 30 hours | 23 days | 2009-05-04 08:00 | 2009-06-03 17:00 | N/A
87 | Develop work plan for procuring these solutions and determine how they will support existing plans |  | 60 hours | 42 days | 2009-06-04 08:00 | 2009-07-31 17:00 | 86
88 | Identify funding streams to support procurement and sustainment |  | 40 hours | 43 days | 2009-08-03 08:00 | 2009-09-30 17:00 | 87
89 | Beta test systems |  | 480 hours | 87 days | 2009-10-01 08:00 | 2010-01-29 17:00 | 88
90 | Develop a project plan for rolling out the system to the jurisdictions |  | 30 hours | 21 days | 2010-02-01 08:00 | 2010-03-01 17:00 | 89
91 | Roll out the system to the jurisdictions |  | 30 hours | 22 days | 2010-03-02 08:00 | 2010-03-31 17:00 | 90
92 | Conduct analysis of existing federal, state, and local systems |  | 120 hours | 44 days | 2010-04-01 08:00 | 2010-06-01 17:00 | 91
Information Sharing
Establish Website |  |  | 750 hours | 108 days | 2009-02-02 | 2009-07-01
93 | Determine layout of website |  | 180 hours | 20 days | 2009-02-02 08:00 | 2009-02-27 17:00 | N/A
94 | Develop content areas |  | 480 hours | 45 days | 2009-03-02 08:00 | 2009-05-01 17:00 | 93
95 | Initiate and promote website via strategic communications |  | 60 hours | 22 days | 2009-05-04 08:00 | 2009-06-02 17:00 | 94
96 | Manage and update website |  | 30 hours | 43 days | 2009-05-04 08:00 | 2009-07-01 17:00 | N/A
Emergency Logistics Conference |  |  | 540 hours | 65 days each year | 2/2/2009 and 2/1/2010 | 5/1/2009 and 4/30/2010
97 | Plan and organize annual logistics conference |  | 300 hours | 52 days | 2/2/2009 and 2/1/2010 | 4/14/2009 and 4/14/2010 | N/A
98 | Hold logistics conference |  | 240* hours | 13 days | 4/15/2009 and 4/15/2010 | 5/1/2009 and 4/30/2010 | 97
*Could fluctuate dramatically depending upon the number of attendees