1.0	INTRODUCTION

1.1	Scope

This Statement of Work (SOW) defines the tasks required for project management, configuration management, and quality control; temporary storage; site surveys; installation and site test of previously purchased systems; removal, refurbishment, configuration, factory test, re-installation, and site test of previously installed systems; warranty; engineering enhancements, and training.

Paragraphs in this SOW that are applicable only to Rapid Deployment Voice Switch (RDVS) are identified by “(RDVS)” at the beginning of the paragraph.   Paragraphs that are applicable only to Enhanced Terminal Voice Switch (ETVS) are identified by “(ETVS)” at the beginning of the paragraph.  Paragraphs that are applicable only to Digital Voice Recorder (DVR) are identified by “(DVR)” at the beginning of the paragraph.  Paragraphs without any identifier are applicable to RDVS, ETVS, and DVR.

2.0	APPLICABLE DOCUMENTS

2.1	Document Listing

NFPA-70 National Electric Code

Northrop Grumman Denro Systems ISO-9001-2000 Recertification with Lloyds of London on 6 October 2005.

(DVR)	Operations and Maintenance Manual, Series 2 DVR2, 080997-001  D

(DVR)	Air Traffic User’s Guide, DVR2, 081920-001  A

(RDVS)	RDVS IIA Enhanced Baseline Factory Acceptance Test (FAT) Procedures, First Edition, 21 October 1997.

(RDVS)	RDVS IIA Factory Acceptance Test Procedures BCU/CSU T1 Operation, Enhanced Large System Baseline, 7 November 2005.

(RDVS)	Enhanced ICSS Model 3080H Operations and Maintenance Manual, TPM0204400, 12 April 2002

(RDVS)	Enhanced ICSS Model 3080F Operations and Maintenance Manual, TPM9906201, 21 December 1999

(RDVS)	Enhanced ICSS Model 3080 Operator Manual, TPM0204100, April 2002

(RDVS)	Enhanced ICSS Model 3080 System User Manual, TPM0204200, April 2002

(RDVS)	Enhanced ICSS Model 3080H Operations and Maintenance Manual, Transmission Network Supplement, Seattle, 0810020-901, October 2003

(ETVS)	ETVS Specification (FAA-E-2894A)

(ETVS)	ETVS Production Acceptance Test Procedures, Revision C, 9 April 2002

(ETVS)	ETVS Technical Instruction Book, Volume 1 (TI 6650.53)

(ETVS)	Operator Manual for the ETVS

(ETVS)	ETVS Supervisor Configuration Terminal (SCT) Users Manual (TI 6650.54A)

3.0	REQUIREMENTS

3.1	Project Management

The Contractor shall perform project management including planning, organizing, directing, and controlling all activities necessary to meet the requirements of this Statement of Work.

The Contractor shall continuously monitor the technical and cost performance of this contract and of related subcontracts that are under the Contractor’s control.  Technical and cost performance monitoring shall include the monitoring of vendor activities through either the Contractor or Subcontractor(s).  The Contractor shall control all contract activities including Subcontractor and vendor activities.

The Contractor shall assign a Project Manager who shall have the responsibility for controlling and coordinating all of the work performed under this contract.  The Contractor shall provide the Project Manager with the authority and adequate resources to ensure efficient and timely program execution. The Project Manager shall be the single focal point in the Contractor’s activity for all of the required project tasks. The Project Manager shall be prepared at all times to present and discuss the current status of all contract requirements with the Contracting Officer and the Contracting Officer’s Technical Representative (COTR).

The project management effort shall also include all activities related to material procurement cycles, inventory management, and the engineering support and manufacturing support disciplines necessary to produce line replaceable units (LRUs).

The Contractor shall plan, support, conduct and participate in reviews at the Contractor’s facilities, when requested by the Government.

The Contractor shall participate in a Post-Award Conference at the Contractor’s facilities.

The Contractor shall perform Configuration Management and Quality Assurance in accordance with the Northrop Grumman Denro Systems ISO-9001-2000 Recertification with Lloyds of London on 6 October 2005.

As part of the project management effort, The Contractor shall provide a Personnel Qualification Report that provides documentation on the qualifications of Contractor training personnel.  Revisions shall be submitted based on changes in employee assignments and additional education.   If the personnel conducting training have previously conducted the same training under the RDVS IIA or DVR contracts, they do not need to be included in a Personnel Qualification Report under this contract.  (CDRL G022)

3.2	Temporary Storage

As ordered by the Government, the Contractor shall provide month-to-month temporary storage service for RDVS, ETVS, and DVR systems.

The storage facility shall provide a safe, secure, and suitable environment for sensitive equipment, including a climate-controlled space impervious to extreme hot or cold temperatures, rapid temperature variations, and excessive humidity.  The air shall be filtered to protect against dust particles, or the equipment otherwise dust-protected by wrapping or containerization.  Access to the facility shall be controlled by an on-site resident manager or routinely patrolled.  The facility shall be adequately insured for liability and loss of contents in the event of common disasters or theft.  The Contractor shall assume total responsibility and accountability for all equipment while being transported to the storage facility, while in storage, and while being transported to the site designated for delivery.

Dates for delivering the systems on-site will be established by the Government via letter or contract modification.  The Contractor shall remove the system from storage with sufficient time to deliver it on-site in accordance with the established on-site delivery date.

3.2.1	Systems Continuing in Storage at Start of Contract Activities

(RDVS)  For RDVS systems that were put in storage under the RDVS IIA contract, the Contractor shall continue storage under this contract.  The cost of removing these systems from storage and shipping them to site was included under the RDVS IIA contract.

(DVR)  For DVR systems that were put in storage under the DVR contract and are in storage at the start of DVR activities on this contract, the Contractor shall continue storage under this contract.  The cost of removing these systems from storage and shipping them to the installation site was covered under the DVR contract.

3.2.2	Systems Put in Storage After Start of Contract Activities

For any RDVS, ETVS, and DVR systems put into storage after the start of RDVS, ETVS, or DVR activities respectively, the storage effort under this contract includes putting these systems in storage and removing them from storage, excluding shipping costs.

The Government plans to use task orders to address shipping arrangements and cover the shipping costs associated with putting these systems in storage and shipping them to the installation site.

## 3.3	RDVS and ETVS Site Surveys

### 3.3.1	Site Survey Conduct

(RDVS, ETVS)  As ordered by the Government, the Contractor shall conduct a detailed site survey in conjunction with Government representatives to determine the system configuration to which the RDVS or ETVS system will be configured and to determine the preparation requirements of the site.  The Government will provide completed site worksheets at the time of ordering.  This site survey shall begin within 15 days of the Government's order for the site survey.

(RDVS, ETVS)  While performing site surveys, Contractor personnel shall abide by all security provisions of the Federal Aviation Administration (FAA) locations being visited.

### 3.3.2	Site Survey Report, Site Installation Plan, and SIIATD

(RDVS, ETVS)  The Contractor shall deliver a Site Survey Report (SSR) for each site for which a Contractor site survey has been conducted.  The SSR shall identify key technical information regarding the site specific aspects of configuration of the system, and modifications required for power, communication lines or interfaces, cabling, grounding, and ducting for the RDVS or ETVS system installation.  The SSR shall also identify facility requirements for and modifications necessary to allow access for installation of cable, conduit, and back room and position equipment.  To support planning, site related activities that are the responsibility of the Government will be separately identified in the SSR.

(RDVS) The SSR shall also outline the methods and procedures that will be implemented during the course of the system installation.  The SSR shall include the completed site survey worksheets containing equipment ordering information, a complete CLIN list including site spares, and shall define the system generation functions.  The SSR shall also list the specific tests that are applicable to Factory Acceptance Test (FAT) and Site Acceptance Test (SAT).  (CDRL B002, Preliminary Submittal)

(RDVS)  This Site Survey Report shall constitute a draft of the Site Installation Plan (SIP).

(RDVS)  The Contractor shall develop and deliver a SIP for each site for which a Contractor a site survey has been conducted after Government comments on the SSR have been received.  The Site Installation Plan, in addition to containing all information included in the SSR, shall include the cable interconnect drawing.  The Contractor shall use the Government approved SIP to configure the system to be delivered. (CDRL B002, Final Submittal)

(ETVS) The SSR shall include the completed site survey worksheets containing equipment ordering information and a complete recommended list including site replaceable spares, assemblies, and consumables for each site configuration.  This list shall contain the CLIN No., part number, national stock number (NSN), item description, and recommended quantity information. (CDRL: E03)

(ETVS) The Contractor shall provide in a site specific Site Installation, Integration, and Acceptance Test Document (SIIATD), information regarding equipment delivery, installation, or storage for the site in question.  The Contractor shall provide as an addendum to the site specific SIIATD a tailored set of test procedures for use during the site acceptance test.  The test procedures shall address the specific configuration ordered for the site. (CDRL:  E02a)

3.4	Deliver, Configure, Install, and Test Systems

(RDVS)  As ordered by the Government, the Contractor shall deliver, install, configure (if required), integrate, and test RDVS systems at Government designated sites in accordance with the Government approved Site Installation Plan.

(ETVS)  As ordered by the Government, the Contractor shall deliver, install, configure (if required), integrate, and test ETVS systems at Government designated sites in accordance with the Government specific Site Installation, Integration, and Acceptance Test Document.

(DVR)  As ordered by the Government, the Contractor shall deliver, configure, install, integrate and test DVR systems at Government designated facilities in accordance with the Government approved On Site Installation, Integration, & Test Plan (SIITP) and specified system configuration.

The Contractor shall provide the personnel, equipment, software, materials, and services including technical and administrative support required for these efforts.  The Contractor shall provide full-time supervision and direction of its personnel and Subcontractors during all phases of the installation activity.  The Contractor shall assign a site installation manager to function as the Contractor's installation interface with the Government.  The site installation manager shall be responsible to the Contractor's project manager.  The site installation manager shall be responsible for integration, control, and coordination of all activities at the site.

(RDVS)  The site installation manager for RDVS systems shall have previous experience in installing the RDVS system.

(ETVS)  The site installation manager for ETVS systems shall have previous experience in installing the ETVS system.

(DVR)  The site installation manager for DVR systems shall have previous experience in installing the DVR system.

The Contractor shall be responsible for site installation activities for all systems.  Site installation activities include, but are not limited to, off-loading, placement, physical installation, configuration, and electrical installation and cabling, and testing.

The Government plans to use task orders to accomplish this work

### 3.4.1	Packing, Shipping, Off-Loading, and Unpacking, Placement and In-Brief

The Contractor shall be responsible for the packing, shipping, off-loading, and placement of all system equipment and material from the Contractor's plant or Contractor’s storage site to the Government designated installation sites.  Off-loading, moving, unpacking, and placing equipment in the designated location within the facility shall be the Contractor's responsibility.  In no case shall a system be delivered to a site without a designated Contractor representative present at the site to accept the system from the shipper.

The Contractor shall conduct an installation in-briefing prior to initiating installation activities.

(RDVS)  For RDVS, the Government will provide facility space for staging during reconfiguration, installation, integration, and testing in accordance with the provisions described in RDVS Site Installation Plan.

(ETVS)  For ETVS, the Government will provide facility space in accordance with the provisions described in the site survey report and the SIIATD.

(DVR)  For DVR, space within the facilities will be provided, but may be very limited for Contractor staging during installation, integration, and testing.

The Contractor shall remove the packing and shipping materials and other installation generated materials from the site as directed by the Site Technical Onsite Representative (TOR), but no later than the conclusion of Site Acceptance Test.

3.4.2	Inventory

Prior to installation, the Contractor shall conduct an inventory to determine that all equipment has been delivered onsite including system equipment and cabling, site spares, and any items required to configure the system in accordance with the RDVS SIP, ETVS SIIATD, or DVR specified system configuration.

### 3.4.3	 Physical Installation

(RDVS, ETVS) The Contractor shall physically connect RDVS or ETVS system "back room" equipment to the Government designated location within the facility.  The Contractor shall supply all mounting hardware and tools necessary to attach the RDVS or ETVS system to collocated rack assemblies, facility flooring, or other connection points as identified in the RDVS Site Installation Plan or ETVS SIIATD.  The Contractor shall be responsible for emplacement of RDVS or ETVS system position equipment in designated pre-prepared locations in the facility.

(RDVS, ETVS, DVR) If specific mechanical installation methods for meeting earthquake requirements are included in the installation task order, the Contractor shall meet those requirements.

(DVR)  The Contractor shall install the DVR rack(s) in the location determined by the Site TOR on site.  This location may be a standalone environment, adjacent to an existing row of similar equipment racks, or in between two existing similar equipment racks.  If the location is not standalone, the Contractor shall attach adjacent equipment racks by using 1/4" x 20 machine bolts of appropriate length, with hex nuts or similar fastener, in sufficient quantities to ensure mechanical safety for personnel working around the equipment rack, if there are existing bolts holes, or if the local manager authorizes that holes may be drilled in the existing equipment racks.  The Contractor shall use two 1/4" flat washers and a lock washer on each bolt if appropriate.

(DVR)  If the facility floor is wood, the Contractor shall attach the racks to the floor using 1/4" lag screws of appropriate length, along with lock washers and flat washers in a minimum of two of the bolt holes in the bottom of the equipment rack, in sufficient quantities to ensure mechanical safety for personnel working around the equipment rack.

(DVR)  If the facility floor is concrete, the Contractor shall attach the racks to the floor using 1/4" lead caulking anchors and 1/4" x 20 machine bolts of appropriate length, along with lock washers and flat washers in a minimum of two of the bolt holes in the bottom of the equipment rack, in sufficient quantities to ensure mechanical safety for personnel working around the equipment rack.

(DVR)  If the facility has a raised floor, the Contractor shall attach the racks to the floor in a manner similar to adjacent racks, to ensure mechanical safety for personnel working around the equipment rack.

(DVR)  Connection to other points, such as a wall, cable tray, conduit, etc. will vary from facility to facility and shall be accomplished in a manner similar to existing racks, to ensure mechanical safety for personnel working around the equipment rack.

### 3.4.4	Electrical Installation and Cabling

The Contractor shall provide and install all cabling, wiring, connectors, and associated hardware within the RDVS, ETVS, and DVR systems. This requirement includes Contractor furnished electrical cabling and connectors for all special test equipment.  The Contractor shall supply all tools and test equipment necessary to install and checkout cabling.  The Contractor shall accomplish all electrical work in accordance with NFPA-70.

### 3.4.4.1	Connection to Power

(RDVS)  For RDVS systems, the Government will provide power cabling from the power source (circuit breaker panel) to the designated RDVS rack location as specified in the Site Installation Plan and the Contractor shall connect the power cabling to the RDVS system.

(ETVS)  For ETVS systems, the Contractor shall provide power cabling from the Government provided power source (circuit breaker panel) to the designated ETVS rack location as specified in the SIIATD and the Contractor shall connect the power cabling to the ETVS system.

(DVR)  For DVR systems, the Contractor shall provide power cabling to connect to the existing single phase AC branch circuit or receptacle within the equipment room using appropriately sized insulated copper wire and a form of mechanical protection such as EMT conduit in a manner similar to existing.

### 3.4.4.2	Connection to Demarcation Point

(RDVS)  For RDVS systems, the Government will provide trunk, radio, and recorder signal cabling from the FAA demarcation point to the designated RDVS rack location as specified in the Site Installation Plan.  The Contractor shall connect this signal cabling to the RDVS system.

(ETVS)  For ETVS systems, the Contractor shall provide trunk, radio, and recorder signal cabling from the FAA demarcation point to the designated ETVS rack location as specified in the SIIATD.  The Contractor shall connect this signal cabling to the ETVS system.

(DVR)  For DVR systems, the Contractor shall provide appropriate multi-conductor cable to interface with the existing demarcation blocks for voice channels in a manner similar to existing, as specified in the SIITP. Types of demarcation blocks may include, but are not limited to, 66 blocks, taper pin blocks, mix terminal blocks, JP-1-B blocks, TC blocks, jack fields, J-boxes, punch down blocks, and christmas tree blocks.

3.4.4.3	Connection to Ground

(RDVS)  For RDVS, the Contractor shall provide and install all ground cables from the RDVS system to FAA ground plates.

(ETVS)  For ETVS, the Contractor shall provide and install all ground cables from the ETVS system to FAA ground plates.

(DVR)  For DVR, the Contractor shall provide and install all ground cables from the DVR system to an existing facility ground plate or duct(s).  The Contractor shall make connections using a pressure type connector such as a Blackburn LB-70, appropriate split bolt connector or similar in a manner similar to existing.

3.4.5	Configuration

(RDVS, ETVS) If the configuration of the system in the Government approved RDVS Site Installation Plan or Government approved ETVS SIIATD is different than the configuration of the system as delivered, the Contractor shall update the system configuration so that it matches the RDVS SIP or ETVS SIIATD.  The Contractor shall record the updated configuration data (part number, revision, serial number, location in system) for use in the site acceptance document.  The Contractor shall record the configuration data (part number, revision, and serial number) of any parts being removed and shall ship these parts back to the factory.

3.4.6	Handling of Failures during Installation and Test

(RDVS) When LRU failures occur in during the installation and test activities, the Contractor shall replace the LRU with new one (one that has never been fielded at a site) from the Additional Lot of Production Equipment.  The Contractor shall return the failed unit to the factory and shall repair it and then use it to replenish the Additional Lot of Production Equipment.

(ETVS) When LRU failures occur in during the installation and test activities, the Contractor shall replace the LRU with new one (one that has never been fielded at a site).  The Contractor shall return the failed unit to the factory and shall repair it and then use it to replenish the source of the replacement part.  If the failed LRU is under warranty, the Contractor shall repair or replace it at no cost to the Government.

(DVR)  For DVR systems that were put in storage under the DVR contract and are in storage at the start of DVR activities on this contract, the Contractor shall replace failed LRUs using Contractor owned factory stock.  The Contractor shall repair or replace the failed unit at their own cost.

(DVR) For DVR systems that were not in storage at the start of DVR activities on this contract, if failures occur, the Contractor shall notify the Contracting Officer and request direction regarding how to proceed.  The Government plans to use task orders to cover this repair activity.

3.4.7	Site Acceptance Test

3.4.7.1	Test Conduct

The Contractor shall conduct the Site Acceptance Test to verify that the system meets the system functional and performance requirements, to verify freedom from production defects, to verify continued performance of production sensitive aspects of the system after shipment and installation at Government facilities and to inventory and confirm that the site spares complement is complete and all are in functional order.  The Contractor shall perform a Site Acceptance Test on each system the Contractor delivers and installs.

(RDVS)  The Contractor shall perform the RDVS Site Acceptance Test in accordance with RDVS IIA Enhanced Baseline Factory Acceptance Test (FAT) Procedures, including any addendums and the test procedures for BCU/CSU T1 Operations.  The Contractor shall perform all of the test cases specified in the Site Installation Plan.

(ETVS) The Contractor shall perform the ETVS Site Acceptance Test Procedures.  The Contractor shall perform all of the test cases specified in the ETVS SIIATD.

(DVR)  The Contractor shall perform the DVR Site Acceptance Test in accordance with the procedures in the SIITP.

The Contractor shall conduct the Site Acceptance Test in the presence of the Site Technical Onsite Representative (TOR) or designated representative who will witness all the tests and validate the test results.

3.4.7.2 	Site Acceptance Test Report

(RDVS)  For each RDVS system installed and tested, the Contractor shall deliver a Site Acceptance Test Report documenting the results of the site acceptance test and initial performance settings of the equipment.  This document shall consist of updated configuration load sheets, cabling diagram for the system as tested, test data sheets, and test discrepancy reports, presented in a Government approved Contractor format.   If the Site Interconnect Drawing delivered as part of the SIP has changed as a result of the installation activities, then the Contractor shall update this drawing and include the updated drawing in the Site Acceptance Test Report.  The Contractor shall also provide a copy of the Government-signed Form FAA-256 in the Site Acceptance Test Report.  (CDRL C004)

(ETVS) For each ETVS, the Contractor shall deliver a Site Acceptance Report (SAR) documenting the results of the site acceptance tests, discrepancy report(s), initial performance settings of the equipment, and a copy of the signed FAA Form 256 or DD Form 250.  (CDRL E04)

3.4.7.3 	Retest

Any discrepancies found during the site acceptance test shall compel the Contractor to determine the reason for the non-compliance and report the cause of the non-compliance to the Government prior to start of retest.

The Contractor shall take all corrective action necessary to ensure full compliance with the RDVS, ETVS, or DVR Test Procedures.  If the corrective action is to replace LRU(s), cables or similar items, the Contractor shall perform the replacement, update the configuration data, verify correct operation, and request the Site TOR allow retest to start.  If the corrective action is complex or cannot readily be determined, the Contractor shall notify the Contracting Officer prior to initiating any further diagnostic work, repair or rework.  The Contractor shall complete all repair or rework prior to retest.

The Government will determine the extent of retest required.

3.4.8	Manuals

3.4.8.1	Standard RDVS Manuals

(RDVS) For 3080F systems, the Contractor shall deliver 3 copies of the RDVS 3080F Operations and Maintenance Manual with each system.

(RDVS) For 3080H systems, the Contractor shall deliver 3 copies of the RDVS 3080H Operations and Maintenance Manual with each system.

(RDVS) The Contractor shall deliver 3 copies of the RDVS Operator’s Manual with each system.

(RDVS) The Contractor shall deliver 3 copies of the RDVS System User Manual with each system.

(RDVS)  For systems that were put in storage under the RDVS IIA contract, the manuals were provided under that contract shall be delivered with the system.  For other systems, the Government plans to accomplish this work using task orders.

3.4.8.2	RDVS O&M Manual Supplements

(RDVS)  As ordered by the Government, the Contractor shall prepare Operations and Maintenance (O&M) Manual Supplements for the Bridge Control Units (BCUs) and any Channel Service Units (CSUs) or Fiber Optic equipment in the system.  The O&M Manual Supplement shall be prepared using the Seattle O&M Manual Supplement previously approved under the RDVS IIA contract as a template.

(RDVS)  The Government plans to use task orders to accomplish this work.

3.4.8.3	DVR Manuals

(DVR) For DVR2 systems, The Contractor shall deliver 2 copies of Operations and Maintenance Manual, Series 2, DVR2 with each system.

(DVR) For DVR2 systems, The Contractor shall deliver 2 copies of Air Traffic User’s Guide, DVR2 with each system.

3.4.8.4	ETVS Manuals

(ETVS) For ETVS systems, the Contractor shall deliver 2 copies of the approved ETVS Technical Instruction Book, Volume 1 (TI 6650.53) with each system.

(ETVS) For ETVS systems, the Contractor shall deliver one copy of the approved Operator Manual for the ETVS with the equipment for each operator/supervisory position.

(ETVS) For ETVS systems, the Contractor shall deliver one set of the approved ETVS Supervisor Configuration Terminal (SCT) Users Manual (TI 6650.54A) with the equipment for each configuration terminal.

3.4.9	Acceptance and Outbrief

The Contractor shall prepare the Form FAA-256 or DD-250 as directed by the Government.

The Contractor shall conduct an out-briefing prior to departing the facility to review the installation, action items, and exceptions to be included on the Form FAA-256 or DD-250.

Acceptance of the system by the Government will occur after successful completion of site acceptance test.  The Site TOR or designated representative will sign the Form FAA-256 or DD-250.

### 3.4.10	Constraints

The Contractor shall perform all installation, integration, and testing activities on a non-interference basis.  The Contractor shall make adequate provisions in Contractor personnel staffing and procedures to allow for flexible use of the on-site personnel to avoid conflicts with Government activities at the installation site.

Contractor personnel shall abide by all security provisions of the Government designated facility.

(RDVS, ETVS) If site personnel request changes outside the scope of the Government approved RDVS Site Installation Plan or ETVS SIIATD, the Contractor shall notify the Contracting Officer and shall not make the changes until directed by the Contracting Officer.

### 3.4.11	Tools and Test Equipment

The Contractor shall provide all tools, test equipment, and test jigs for all installation, integration, testing, and maintenance activities on the RDVS, ETVS, and DVR systems during site acceptance.

The Contractor’s use of Government furnished tools and test equipment during the installation, integration, and testing period is prohibited, unless first approved by the Government.

### 3.5	Remove Previously Delivered Systems, Refurbish, Configure, and Test

### 3.5.1	Removal and Refurbishment

As ordered by the Government, the Contractor shall remove previously delivered RDVS, ETVS, and DVR systems and ship them back to the factory for refurbishment, or to another site as directed by the Government.  The Contractor shall perform an inventory and prepare a packing list containing all equipment being removed from the site prior to shipment of that equipment.

As ordered by the Government, the Contractor shall refurbish RDVS, ETVS, and DVR systems.  The refurbishment shall include evaluating whether a LRU or item can be reasonably restored to near-new condition.  The Contractor shall present the results of this evaluation to the Contracting Officer.  The Contracting Officer will make the final determination as to which items the Contractor shall restore and repair and will provide disposition instructions for any items not being restored.

The Contractor shall restore the items designated for restoration.  The Contractor shall system test all LRUs to ensure they are fully functional.

The Government plans to use task orders to accomplish this work.

3.5.2	Configuration

As ordered by the Government, the Contractor shall configure and integrate systems in accordance with the Government approved RDVS SIP, ETVS SIIATD, or DVR specified system configuration.

As ordered by the Government, the Contractor shall produce limited quantities of LRUs to enable the configuration of RDVS, ETVS, and DVR systems.

The Government plans to use task orders to accomplish this work.

3.5.3	Factory Acceptance Test

3.5.3.1	Test Conduct

The Contractor shall conduct the Factory Acceptance Test to verify that the system is equipped as specified in the Site Installation Plan, to verify freedom from production defects, and verify continued performance of production sensitive aspects of the system.  The Contractor shall perform a Factory Acceptance Test on each assembled system prior to shipping it to the designated site.  The Contractor shall notify the Government at least two working days prior to the start of Factory Acceptance Test.  The Government may require that the tests on a system be conducted in the presence of a Government designated representative.

As part of the Factory Acceptance Test, the Contractor shall test all spares for a system to verify freedom from defects, and verify continued performance of production sensitive aspects of the system.

(RDVS) The Contractor shall perform the RDVS factory acceptance test in accordance with the RDVS IIA Enhanced Baseline Factory Acceptance Test (FAT) Procedures and the test procedures for BCU/CSU T1 Operations.  The Contractor shall perform all of the test cases specified in the Site Installation Plan.

(ETVS) The Contractor shall perform the ETVS Production Acceptance Test Procedures.  The Contractor shall perform all of the test cases specified in the ETVS SIIATD.

(DVR) The Contractor shall perform the DVR factory acceptance test in accordance with the procedures in the SIITP.

3.5.3.2	Factory Acceptance Test Report

(RDVS) The Contractor shall prepare a Factory Acceptance Test Report for each system undergoing Factory Acceptance Test.  This report shall consist of configuration sheets for the unit under test, test data sheets, reports, and test discrepancy reports, presented in a Government approved Contractor format.  (CDRL C003)

(ETVS) The Contractor shall prepare a Production Acceptance Test Report for each system undergoing Production Acceptance Test.  This report shall consist of configuration sheets for the unit under test, test data sheets, reports, and test discrepancy reports, presented in a Government approved Contractor format.  (CDRL E05)

3.5.3.3 	Retest

Any discrepancies found during the factory acceptance test shall compel the Contractor to determine the reason for the non-compliance and report the cause of the non-compliance to the Government prior to start of retest.

The Contractor shall take all corrective action necessary to ensure full compliance with the RDVS, ETVS, or DVR Test Procedures.  If the corrective action is to replace LRU(s), cables or similar items, the Contractor shall perform the replacement, update the configuration data, verify correct operation, and request the Quality Reliability Officer (QRO) allow retest to start.  If the corrective action is complex or cannot readily be determined, the Contractor shall notify the Contracting Officer prior to initiating any further diagnostic work, repair or rework.  The Contractor shall complete all repair or rework prior to retest.

The Government will determine the extent of retest required.

3.5.3.4	Factory Acceptance

For systems delivered to the FAA, the Contractor shall prepare the Form FAA-256.  For systems delivered to the DoD, the Contractor shall prepare the Form DD-250.

Acceptance of the system by the Government will occur after successful completion of factory acceptance test.  The designated Government representative will sign the Form FAA-256 or DD-250.

After acceptance, the Contractor shall pack and ship these systems to site or storage as directed by the Government.

3.6	Warranty

(DVR) For new production equipment (not refurbished equipment), the Contractor shall provide a one-year warranty that commences upon the Government’s acceptance of each DVR system, including ancillary equipment, at the final destination following installation and site acceptance test of the system.  The Contractor shall repair or replace all hardware, software and firmware furnished under this contract that fails or become defective without charge to the Government. LRUs shall be replaced or repaired to restore them to a serviceable operating condition meeting the original performance specifications.  All repaired LRUs shall successfully undergo a system level test prior to shipment.

(ETVS) For new production equipment (not refurbished equipment), the Contractor shall repair or replace, at no cost to the Government, all hardware, software, and firmware components that are found to be defective or become inoperative during the first twelve (12) months after the Government acceptance of each item.  Each replacement item shall meet the requirements of the ETVS specification, FAA-E-2894A.

3.6.1	Turnaround Time Requirements

(DVR) The Contractor shall provide warranty services that meet the following turnaround times as specified by the Government for each order:

a)	For Priority 1 (Emergency replacement), the Contractor shall ship serviceable LRUs to the FAA site within 24 hours, after receipt of a request from the FAA Logistics Center official designated in writing.

b)	For Priority 2 replacement, the Contractor shall ship serviceable LRUs to the FAA site within 48 hours, after receipt of a request from the FAA Logistics Center official designated in writing.

c)	For Priority 5 (Routine Repair), the Contractor shall ship the serviceable LRUs to the FAA site within eight (8) working days after receipt of a request from the FAA Logistics Center official designated in writing.

3.7	Engineering Enhancements

As ordered by the Government, The Contractor shall develop, design and test engineering enhancements or other modifications to system hardware, firmware, or software.  These efforts shall include the development of any and all changes or additions to system documentation.  The Contractor shall prepare Engineering Change Proposals (ECPs) documenting these changes.  The Contractor shall present the ECPs to the Government for approval.

As ordered by the Government, the Contractor shall incorporate approved ECPs into systems in storage or systems being installed under this contact.

The Government plans to use task orders to accomplish this work.

3.8	Training

3.8.1	DVR Course Conduct

(DVR)  As ordered by the Government, the Contractor shall conduct the approved Operation and Maintenance Course for DVR1 systems using the FAA Academy approved DVR1 Training Materials.  The Operation and Maintenance Training shall be conducted upon completion of the installation, during the same week as the installation.

(DVR)  As ordered by the Government, the Contractor shall conduct the FAA Academy approved DVR2 Operations Course.  The Operation Training shall be conducted upon completion of the installation, during the same week as the installation.

(DVR)  As ordered by the Government, the Contractor shall conduct the FAA Academy approved DVR2 Maintenance Course.  The Maintenance Training shall be conducted upon completion of the installation, during the same week as the installation.

(DVR)  No more than 6 students will be included per class at each site.

(DVR)  The Contractor shall use all the previously approved DVR Training Materials and documentation.

(DVR)  All previously approved Student Materials, Achievement Tests, Student Critique Sheets, End of Course Evaluation Questionnaires, Class Rosters and Certificates of Training shall be provided or administered by the Contractor.

(DVR)  The Government plans to use task orders to accomplish this work

3.8.3	RDVS BCU Training

(RDVS)  As ordered by the Government, the Contractor shall prepare site specific Bridge Controller training material using the training material previously approved under the RDVS IIA contract as a template.

(RDVS)  As ordered by the Government, the Contractor shall conduct BCU training onsite.  All Student Materials, Student Critique Sheets, End of Course Evaluation Questionnaires, Class Rosters and Certificates of Training shall be provided or administered by the Contractor.

(RDVS)  The Government plans to use task orders to accomplish this work.

3.9	Task Orders

The Contractor shall, as ordered by the Government, provide technical personnel and the necessary materials to perform a variety of tasks at the Contractor’s plant, field sites, or other locations as directed by the Government.  The tasks shall include, but are not limited to:

a.	Performing all of the activities specifically identified in this SOW as being accomplished by task order;

b.	Providing assistance during the cutover to operational service of any system;

c.	Conducting special training which the Contractor is qualified to provide;

d.	Moving, modifying, and relocating equipment at field sites;

e.	Providing technical personnel and support during meetings at field sites and other Government designated locations;

f.	Providing on site troubleshooting of system failures or performance and/or functional anomalies;

g.	Providing in-depth engineering analysis and assessments of hardware, software and documentation problems dealing with supportability, maintainability, reliability, performance and operation of the supported equipment.

For all task orders, the Contractor’s personnel being provided shall have experience on the Contractor’s RDVS IIA, ETVS, or DVR equipment and shall have knowledge of the system’s hardware, software, firmware and functional and performance features sufficient to perform the assigned task(s).

The Contractor shall prepare and deliver a letter type task order report for each task order after it is completed.  Specific items to be included in the report, in addition to those required by CDRL J001, will be specified by the Government in the task order Statement of Work.  (CDRL J001)